## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 46735352.04
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 46735352.04
|  | Less: Total Assigned |  | 44732635.86
|  | Total Unassigned / Unallocated |  | 2002716.18
DA22 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
C | 8983.03 | DCA CC SHB Exterior Envelope Improvements | Josh H | 0 | 27942.31 | 27942.31 | 27942.31 | 27942.31 | 0 | 0
| 9186.01 | DHS CC Strategic Space Planning | Jennie E. | 0 | 8517795.65 | 8517795.65 | 6928568.8 | 6763023.58 | 165545.22 | 1589226.85
| 9186.02 | DHS CC Strategic Space Planning (SLFRF) | Jennie E. | 0 | 10432829.63 | 10432829.63 | 10432829.63 | 10432829.63 | 0 | 0
| 9186.03 | DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds | Jennie E. | 0 | 982346 | 982346 | 906934.08 | 892201.19 | 14732.89 | 75411.92
| 9186.04 | DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - (SLFRF) Funds | Jennie E. | 0 | 1312670.37 | 1312670.37 | 1306151.9 | 1296897.23 | 9254.67 | 6518.47
| 9186.05 | DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds | Jennie E. | 0 | 105976.83 | 105976.83 | 105976.83 | 105976.83 | 0 | 0
| 9186.06 | DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - (SLFRF) Funds | Jennie E. | 0 | 761653.55 | 761653.55 | 761653.55 | 756787.88 | 4865.67 | 0
| 9186.07 | DHS CC Strategic Space Planning (Hoover B Level) - (SLFRF) Funds | Jennie E. | 0 | 15000 | 15000 | 11722.5 | 2143.85 | 9578.65 | 3277.5
C | 9203.00 | DOC NCCF Treatment Center EIFS Replacement | James T | 0 | 24510.47 | 24510.47 | 24510.47 | 24510.47 | 0 | 0
C | 9204.00 | DVA IVH Dack Sundeck Roof Replacement | Brad T | 0 | 64000 | 64000 | 64000 | 64000 | 0 | 0
C | 9216.00 | DHS STS Cottage Dorm Conversion | Jennifer K | 0 | 6385054.11 | 6385054.11 | 6385054.11 | 6385054.11 | 0 | 0
C | 9217.01 | DHS WRC CDC Warehouse Power Upgrades | Jennifer K | 0 | 148899.03 | 148899.03 | 148899.03 | 148899.03 | 0 | 0
C | 9220.00 | DHS IMHI Boiler Installation Engineering (2021) | Doug C | 0 | 4650 | 4650 | 4650 | 4650 | 0 | 0
C | 9221.00 | DOC NCF Warehouse Overhead Door Expansion | Brad T | 0 | 7490 | 7490 | 7490 | 7490 | 0 | 0
C | 9221.01 | DOC NCF Warehouse Overhead Door Expansion | Brad T | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 9222.00 | DHS WRC 2021 Storm Damage Repairs (29C20) | Jennifer K | 0 | 427420.24 | 427420.24 | 427420.24 | 427420.24 | 0 | 0
C | 9223.00 | DOC CCF Kitchen & Laundry Facility Design Project | Brad T | 0 | 598321.43 | 598321.43 | 598321.43 | 598321.426 | 0.004 | 0
C | 9238.00 | ABD Warehouse Racking Improvements | Jennie E. | 0 | 2172780.15 | 2172780.15 | 2172780.15 | 2172780.15 | 0 | 0
C | 9239.00 | DOC-NCF-IPI Homes for Iowa Facility Project | Brad T | 0 | 43963.14 | 43963.14 | 43963.14 | 43963.14 | 0 | 0
C | 9239.01 | DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse (SLFRF) | Brad T | 0 | 1929092.95 | 1929092.95 | 1929092.95 | 1929092.95 | 0 | 0
C | 9241.00 | ILEA JOH New Storage Building | Brad T | 0 | 2187.16 | 2187.16 | 2187.16 | 2187.16 | 0 | 0
C | 9242.00 | DAS CC Lucas Elevator Replacements | Brad T | 0 | 1963201.35 | 1963201.35 | 1963201.35 | 1963201.35 | 0 | 0
C | 9243.00 | DOC NCCF Grease Interceptor Evaluation | James T | 0 | 4320 | 4320 | 4320 | 4320 | 0 | 0
C | 9259.00 | DAS CC Finkbine St Paving and Parking Lot 5 Replacement | Doug C. | 0 | 240000 | 240000 | 240000 | 240000 | 0 | 0
C | 9260.00 | DHS WRC New Fire Sprinkler Systems | Jennifer K | 0 | 127223.77 | 127223.77 | 127223.77 | 127223.77 | 0 | 0
C | 9261.00 | DHS GRC New Fire Sprinkler Systems | Doug C | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 9266.00 | DHS GRC Administration Entrance Stairs & Ramp Repair | Jennie E. | 0 | 184158.32 | 184158.32 | 184158.32 | 184158.32 | 0 | 0
C | 9267.00 | DHS CHMHI CCUSO Door and Intercom Control Conversion | Jennie E. | 0 | 446243.55 | 446243.55 | 446243.55 | 446243.55 | 0 | 0
C | 9268.00 | DAS CC Tunnel Joint Evaluation | Josh H | 0 | 35651.1 | 35651.1 | 35651.1 | 35651.1 | 0 | 0
C | 9280.00 | DVA IVC Asphalt Road Resurfacing | Brad T | 0 | 320199.32 | 320199.32 | 320199.32 | 320199.32 | 0 | 0
C | 9281.00 | DVA IVC Irrigation System Improvements | Brad T | 0 | 66228.28 | 66228.28 | 66228.28 | 66228.28 | 0 | 0
C | 9282.00 | DAS CC Parking Lot 1 Replacement | Jennie E. | 0 | 74791.21 | 74791.21 | 74791.21 | 74791.21 | 0 | 0
| 9283.00 | DHS CHMHI Voldeng Building 1st Floor Remodel | Jennie E. | 0 | 8900000 | 8900000 | 8571718.56 | 6472384.72 | 2099333.84 | 328281.44
C | 9285.00 | DPS P15 Property Disposal | Barb B. | 0 | 956.25 | 956.25 | 956.25 | 956.25 | 0 | 0
C | 9286.00 | DPS Fleet & Supply Level 2 Floor Framing | James T | 0 | 11887.35 | 11887.35 | 11887.35 | 11887.35 | 0 | 0
C | 9289.00 | DOC FDCF Bldg H Gym Loft and Concessions | Jennifer K | 0 | 205218.89 | 205218.89 | 205218.89 | 205218.89 | 0 | 0
C | 9295.00 | DOC NCF BAS Panel Upgrade | Brad T | 0 | 190689.63 | 190689.63 | 190689.63 | 190689.63 | 0 | 0
|  | DA22 (MOU) Totals |  | 0 | 46735352.04 | 46735352.04 | 44732635.86 | 42429324.916 | 2303310.944 | 2002716.18
4306027.124

## RECAP #8983.03
DCA CC SHB Exterior Envelope Improvements
Project # 8983.03
| Program code 898303 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Josh H.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 27942.31
C | Ryan Companies |  | 24577.6 | 24577.6 | 0
C | PM TIME |  | 3364.71 | 3364.71 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 27942.31 | 27942.31 | 27942.31 | 0 | 0
Closed 08/04/22

## #8983.03 Funds Rec'd
DCA CC SHB Exterior Envelope Improvements
Project # 8983.03
Program code 898303 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Josh H.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25922035700 | 2022-02-04 | 28000 | 28000
|  |  | Return Funds to Agency | IET 33522216900 | 2022-08-04 | -57.69 | -57.69
| Total Requested | 0 | Total Transferred |  |  | 27942.31 | 27942.31

## #8983.03 Ryan Companies CA
DCA CC SHB Exterior Envelope Improvements
Project # 8983.03
Program code 898303 |  |  | Major Program 4E02
Ryan Companies |  |  | Vendor: 00003035285
Acct. Codes-0506-335-DA22-9255 |  |  | RFP0215335062-Ryan9112015
Project Manager - Josh H. |  |  | Activity code: CMGR
Doc # | Date | Activity |  | Contract Total | Payment Amount | Total Paid | Balance
PO 33522099200 | 2022-02-10 | CO #3(Split between MM21 &DA22) | 24577.6 | 24577.6 |  |  | 24577.6
PRC 3352209PN9200 | 2022-02-15 | Inv. 4729-14 (100% to MM19) |  | 24577.6 | 0 | 0 | 24577.6
PRC 3352209PM9200 | 2022-03-28 | Inv. 47290-015(Split between MM19, MM21, & DA22) |  | 24577.6 | 6444.5 | 6444.5 | 18133.1
PRC 3352209PP9200 | 2022-04-15 | Inv. 47290-016 (Split between MM19, MM21 & DA22) |  | 24577.6 | 17064.58 | 23509.08 | 1068.52
PO 33522099200 | 2022-05-05 | CO #4 (Split between MM19 & MM22) | 0 | 24577.6 |  | 23509.08 | 1068.52
PRC 3352209PQ9200 | 2022-05-13 | Inv. 4729CA-17 (split between MM19 & MM22) |  | 24577.6 | 0 | 23509.08 | 1068.52
PO 33522099200 | 2022-06-15 | CO #5 (100% to MM21) | 0 | 24577.6 |  | 23509.08 | 1068.52
PRC 3352209PR9200 | 2022-06-15 | Inv. 4729CA-18 (split between MM19 & MM22) |  | 24577.6 | 0 | 23509.08 | 1068.52
PO 33522099200 | 2022-06-21 | CO #6 (100% to MM22) $0.00 CO | 0 | 24577.6 |  | 23509.08 | 1068.52
PRC 3352209PS9200 | 2022-07-20 | Inv. 4729CA-19 (split between DA22 & MM22) |  | 24577.6 | 1068.52 | 24577.6 | 0
|  |  |  | 24577.6 |  | 24577.6 | 0
|  |  |  | 24577.6 |  | 24577.6 | 0
|  |  |  | 24577.6 |  | 24577.6 | 0
|  | Totals: | 24577.6 |  | 24577.6 |  | 0
|  | R528 (closed 10/29/20) | 155603.38 |  | 155603.38 |  | 0
|  | MM19 (Closed 06/15/2022) | 563476.99 |  | 563476.99 |  | 0
|  | MM21 | 11015.84 |  | 4524.6 |  | 6491.24
|  | MM22 | 182000.01 |  | #N/A |  | #N/A
|  | Total contract: | 936673.82 |  | #N/A |  | #N/A

## #8983.03 PM TIME
DCA CC SHB Exterior Envelope Improvements
Project # 8983.03
Program code 898303 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Josh H.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 3375 | 3375 |  |  | 3375
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28,2022 |  | 3375 | 600 | 600 | 2775
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 3375 | 1675 | 2275 | 1100
CDE 33522098900 | 2022-04-08 | Moving PM Time to DA18 8983.01 | -10.29 | 3364.71 | -10.29 | 2264.71 | 1100
IET DAS202210115300001 | 2022-05-06 | PM April 1-April 29, 2022 |  | 3364.71 | 500 | 2764.71 | 600
CDE 33522129901 | 2022-05-06 | Moving Pm Time from R20M 9883.02 |  | 3364.71 | 25 | 2789.71 | 575
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 3364.71 | 450 | 3239.71 | 125
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 3364.71 | 75 | 3314.71 | 50
CDE 33522193900 | 2022-07-12 | Moving Pm Time to DA22 9883.03 |  | 3364.71 | 50 | 3364.71 | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 39.03 | 3403.74 | 39.03 | 3403.74 | 0
CDE 33523353209 | 2022-12-21 | Move PM time to 9997.23 MM23 | -39.03 | 3364.71 | -39.03 | 3364.71 | 0
|  |  |  | 3364.71 |  | 3364.71 | 0
|  |  |  | 3364.71 |  | 3364.71 | 0
|  |  |  | 3364.71 |  | 3364.71 | 0
|  | Totals: | 3364.71 |  | 3364.71 |  | 0
Note on D9: Huggins, Joni [DAS]: Re: PM Time Budget Inbox Herman, Josh 10:22 AM (4 minutes ago) to me Please create a PM Time budget of $5,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 8983.03 DA22 PM Time $Joni Herman, Josh Feb 15, 2022, 2:23 PM (20 hours ago) to me Please set it to $3,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 8983.03 PM Time DA22 FY22 Herman, Josh Fri, May 13, 2:35 PM (3 days ago) to me Please add $425 to the PMTime budget for a total of $3,214.71 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #8983.03 Misc
DCA CC SHB Exterior Envelope Improvements
Project # 8983.03
Program code 898303 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Josh H.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9186.01
DHS CC Strategic Space Planning
Project # 9186.01
| Program code 918601 |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursements
| Funds received per MOU | 8517795.65
C | Shive Hattery |  | 75642.24 | 75642.24 | 0 |  | 0
| PM TIME (HHS) |  | 350000 | 184454.78 | 165545.22 |  | 0
| PM TIME (DA) |  | 0 | -5.3291e-14 | 5.3291e-14 |  | 0
| SP TIME (HHS) |  | 0 | 0 | 0 |  | 0
| SP TIME (DA) |  | 0 | 0 | 0 |  | 0
| Misc. |  | 400492.27 | 400492.27 | 0 |  | 0
C | DCI Group |  | 0 | 0 | 0 |  | 0
C | Shive Hattery (2) |  | 0 | 0 | 0 |  | 0
C | Atlas One |  | 4225 | 4225 | 0 |  | 0
C | Controlled Asbestos |  | 3493.12 | 3493.12 | 0 |  | 0
| DCI Group 22-037 CA (P) |  | 565861.19 | 565861.19 | 0 |  | 29964.01
C | Holmes Murphy |  | 9236 | 9236 | 0 |  | 0
| Ball Team (P) |  | 1437876.7 | 1437876.7 | 0 |  | 75835.99
| Elite Fire Sprinkler Systems (P) |  | 135678.52 | 135678.52 | 0 |  | 23309.78
| Ideal Floors (P) |  | 528681.59 | 528681.59 | 0 |  | 46322.98
| All Makes-Furniture (P) |  | 2371984.41 | 2371984.41 | 0 |  | 140261.02
| Bergstrom Construction (P) |  | 11323.06 | 11323.06 | 0 |  | 8676.94
| Tri-City Electric (P) |  | 652814.56 | 652814.56 | 0 |  | 34554.76
| Central Iowa Mechanical (P) |  | 379822.13 | 379822.13 | 0 |  | 203073.87
| Cominkey Glass |  | 1438.01 | 1438.01 | 0 |  | 1366.69
| Total Project Cost | 8517795.65 | 6928568.8 | 6763023.58 | 165545.22 | 1589226.85 | 563366.04

## #9186.01 Funds Rec'd
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 401AL 12172021 | 2021-12-17 | 100000 | 100000
|  |  | Funds received without program code | CDR 33522354800 | 2021-12-20 | 0 | 0
|  |  | Return FY22 Funds to Agency | IET 33522215810 | 2022-08-03 | -73257.85 | -73257.85
|  |  | Received FY23 Funds from Agency | IET 401ML238001 082622 | 2022-08-26 | 73257.85 | 73257.85
|  |  | Funds received without program code | CDR 33523241900 | 2022-08-26 | 0 | 0
|  |  | MOU Amendment #1 | IET 401AL 02142023 | 2023-02-14 | 3100000 | 3100000
|  |  | Return FY23 Funds to Agency | IET 33523234910 | 2023-08-22 | -2993923.02 | -2993923.02
|  |  | Received FY24 Funds from Agency | IET 33523234910 | 2023-09-05 | 2993923.02 | 2993923.02
|  |  | CDR to move Revenue 9186.01 to 9186.05 | CDR 33524082810 | 2024-03-22 | -500000 | -500000
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33524087802 | 2024-03-27 | -50000 | -50000
|  |  | Funds Recv'd | CDR 00524163101 | 2024-06-11 | 13376.48 | 13376.48
|  |  | Return funds to Agency per PM | IET 33524192800 | 2024-07-10 | -110087.38 | -110087.38
|  |  | Return funds to Agency per PM | IET 33524192803 | 2024-07-10 | -482543 | -482543
|  |  | Return FY24 Funds to Agency | IET 33524226905 | 2024-08-13 | -8778.81 | -8778.81
|  |  | MOU Amendment #1 | IET 335ML282006 081424 | 2024-08-15 | 5000000 | 5000000
|  |  | Return FY24 Funds to Agency Correction | IET 33524226905A | 2024-08-21 | -21410.16 | -21410.16
|  |  | Land sales proceeds for Lucas | IET 400ML233005 082024 | 2024-08-23 | 2379395.55 | 2379395.55
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525257910 | 2024-09-13 | -10000 | -10000
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525281800 | 2024-10-07 | -728708.54 | -728708.54
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525298911 | 2024-10-24 | -46811.57 | -46811.57
|  |  | Received FY25 Funds | IET 33525226905 | 2024-10-24 | 30188.97 | 30188.97
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525299902 | 2024-10-25 | -2469 | -2469
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525351901 | 2024-12-16 | -144356.89 | -144356.89
| Total Requested | 0 | Total Transferred |  |  | 8517795.65 | 8517795.65

## #9186.01 Shive Hattery
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP1820335153
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522063904 | 2022-03-04 | PO Procore | 30000 | 30000 |  |  | 30000
PRC 3352206PA3904 | 2022-04-06 | Inv. 4203301-1 |  | 30000 | 4793 | 4793 | 25207
PRC 3352206PB3904 | 2022-04-28 | Inv. 4203301-2 |  | 30000 | 4929 | 9722 | 20278
PRC 3352206PC3904 | 2022-06-03 | Inv. 4203301-3 |  | 30000 | 7970 | 17692 | 12308
PRC 3352206PD3904 | 2022-06-30 | Inv. 4203301-4 |  | 30000 | 2218.9 | 19910.9 | 10089.1 | FY22
PO 33523063904 | 2022-08-29 | Rolled to FY23 | 0 | 30000 |  | 19910.9 | 10089.1
PRC 3352306PE3904 | 2022-08-29 | Inv. 4203301-5 |  | 30000 | 417.5 | 20328.4 | 9671.6
PRC 3352306PF3904 | 2022-08-29 | Inv. 4203301-6 |  | 30000 | 1844.44 | 22172.84 | 7827.16
PO 33523063904 | 2022-09-15 | CO 1 | 49500 | 79500 |  | 22172.84 | 57327.16
PRC 3352306PG3904 | 2022-09-28 | Inv. 4203301-7 |  | 79500 | 18344 | 40516.84 | 38983.16
PRC 3352306PH3904 | 2022-11-14 | Inv. 4203301-8 |  | 79500 | 23725.7 | 64242.54 | 15257.46
PRC 3352306PI3904 | 2022-12-05 | Inv. 4203301-9 |  | 79500 | 7593.2 | 71835.74 | 7664.26
PRC 3352306PJ3904 | 2023-03-27 | Inv. 4203301-10 |  | 79500 | 3806.5 | 75642.24 | 3857.76
PO 33523063904 | 2023-06-28 | Closing PO per PM | -3857.76 | 75642.24 |  | 75642.24 | 0
|  |  |  | 75642.24 |  | 75642.24 | 0
|  |  |  | 75642.24 |  | 75642.24 | 0
|  |  |  | 75642.24 |  | 75642.24 | 0
|  | Totals | 75642.24 |  | 75642.24 |  | 0 | FINAL
|  | Project Initiation,Vision,Roles,Goals,Drivers | 4998 |  | 4998 |  | 0
|  | Workplace Strategy | 24998.84 |  | 24998.84 |  | 0
|  | CO #1 | 45645.4 |  | 45645.4 |  | 0
|  | Total: | 75642.24 |  | 75642.24 |  | 0

## #9186.01 PM TIME (HHS)
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  |  | Major Program 4D08
PM TIME (HHS) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 627O
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 350000 | 350000 |  |  | 350000
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30,2021 |  | 350000 | 325 | 325 | 349675
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 350000 | 850 | 1175 | 348825
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 350000 | 475 | 1650 | 348350
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 350000 | 1000 | 2650 | 347350
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 350000 | 1000 | 3650 | 346350
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 350000 | 1150 | 4800 | 345200
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 350000 | 650 | 5450 | 344550
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 350000 | 250 | 5700 | 344300
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 350000 | -250 | 5450 | 344550
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 350000 | 275 | 5725 | 344275
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 350000 | 1980 | 7705 | 342295
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 350000 | 1100 | 8805 | 341195
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 350000 | 2035 | 10840 | 339160
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 350000 | 1430 | 12270 | 337730
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 169.13 | 350169.13 | 169.13 | 12439.13 | 337730
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -169.13 | 350000 | -169.13 | 12270 | 337730
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1507.6 | 351507.6 | 1507.6 | 13777.6 | 337730
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1507.6 | 350000 | -1507.6 | 12270 | 337730
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 703.15 | 350703.15 | 703.15 | 12973.15 | 337730
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -703.15 | 350000 | -703.15 | 12270 | 337730
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1281.39 | 351281.39 | 1281.39 | 13551.39 | 337730
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1281.39 | 350000 | -1281.39 | 12270 | 337730
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 981.64 | 350981.64 | 981.64 | 13251.64 | 337730
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -981.64 | 350000 | -981.64 | 12270 | 337730
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 350000 | 605 | 12875 | 337125
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 350000 | 302.33 | 13177.33 | 336822.67
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 350000 | 2650.42 | 15827.75 | 334172.25
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July, August, Sept 2022 | 409.34 | 350409.34 | 409.34 | 16237.09 | 334172.25
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -409.34 | 350000 | -409.34 | 15827.75 | 334172.25
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 350000 | 725.22 | 16552.97 | 333447.03
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 350000 | 4397.8 | 20950.77 | 329049.23
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 350000 | 1176.48 | 22127.25 | 327872.75
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 350000 | 5174.69 | 27301.94 | 322698.06
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 350000 | 688.8 | 27990.74 | 322009.26
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 350000 | 4050.1 | 32040.84 | 317959.16
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 350000 | 882.13 | 32922.97 | 317077.03
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 350000 | 6179.8 | 39102.77 | 310897.23
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 350000 | 663.91 | 39766.68 | 310233.32
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 350000 | 5546.6 | 45313.28 | 304686.72
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 350000 | 951.31 | 46264.59 | 303735.41
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 350000 | 6060.9 | 52325.49 | 297674.51
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 350000 | 645.27 | 52970.76 | 297029.24
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 350000 | 3339.8 | 56310.56 | 293689.44
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 350000 | 638.67 | 56949.23 | 293050.77
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 350000 | 4432.9 | 61382.13 | 288617.87
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 350000 | 652.03 | 62034.16 | 287965.84
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 350000 | 5230.3 | 67264.46 | 282735.54
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 350000 | 463.55 | 67728.01 | 282271.99
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 350000 | 3501.6 | 71229.61 | 278770.39
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 350000 | 677.48 | 71907.09 | 278092.91
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 350000 | 4969.4 | 76876.49 | 273123.51
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 350000 | 1080.95 | 77957.44 | 272042.56
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 350000 | 9530 | 87487.44 | 262512.56
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 350000 | 1431.67 | 88919.11 | 261080.89
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 350000 | 7216.3 | 96135.41 | 253864.59
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 350000 | 859.81 | 96995.22 | 253004.78
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 350000 | 6518.1 | 103513.32 | 246486.68
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 350000 | 353.73 | 103867.05 | 246132.95
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 350000 | 8478.4 | 112345.45 | 237654.55
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 350000 | 1053.94 | 113399.39 | 236600.61
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 350000 | 8724 | 122123.39 | 227876.61
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 350000 | 897.17 | 123020.56 | 226979.44
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 350000 | 8197.8 | 131218.36 | 218781.64
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 350000 | 898.48 | 132116.84 | 217883.16
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 350000 | 9806.6 | 141923.44 | 208076.56
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 350000 | 1509.14 | 143432.58 | 206567.42
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 350000 | 7682.1 | 151114.68 | 198885.32
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 350000 | 431.78 | 151546.46 | 198453.54
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 350000 | 3843.8 | 155390.26 | 194609.74
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 350000 | 830.2 | 156220.46 | 193779.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 350000 | 5538.9 | 161759.36 | 188240.64
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 350000 | 385.79 | 162145.15 | 187854.85
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 350000 | 2562.9 | 164708.05 | 185291.95
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 350000 | 206.44 | 164914.49 | 185085.51
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 350000 | 2061.5 | 166975.99 | 183024.01
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 350000 | 321.18 | 167297.17 | 182702.83
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 350000 | 3427.4 | 170724.57 | 179275.43
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 350000 | 752.53 | 171477.1 | 178522.9
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 350000 | 3254.8 | 174731.9 | 175268.1
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 350000 | 747.37 | 175479.27 | 174520.73
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 350000 | 5350.3 | 180829.57 | 169170.43
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 350000 | 261.81 | 181091.38 | 168908.62
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 350000 | 1796.6 | 182887.98 | 167112.02
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 350000 | 177.3 | 183065.28 | 166934.72
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 350000 | 1389.5 | 184454.78 | 165545.22
[5 empty] | 350000 |  | 184454.78 | 165545.22
|  |  | Totals | 350000 |  | 184454.78 |  | 165545.22
Note on E9: Huggins, Joni [DAS]: Re: PM Time Budget Herman, Josh Please create a PM Time budget of $5,000. Thank you, Josh Josh Herman CPM, Owner Representative 9186.01 (DA22) PM Time Budget Herman, Josh 1:36 PM (2 hours ago) to me Please increase from $5,000 to $8,150 Thank you, Josh 186.01 (DA22) PM Time $Joni Herman, Josh 7:58 AM (1 minute ago) to me Please adjust from $8,150 to $10,900. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9186.01 PM Time DA22 $Joni Herman, Josh 12:17 PM (28 minutes ago) to me Please adjust from $10,900 to $12,110. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9186.01 (DA22) PM Time $Joni Herman, Josh 9:27 AM (18 minutes ago) to me Please add the remaining $4,108.75 unallocated to PM Time Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Herman, Josh 10:27 AM (10 minutes ago) to John, me Go ahead and increase the MISC by $285 and take it out of the PM Time budget. Thank you, Josh Fwd: 9186.01 PM time budget $Joni Elliott, Jennie Mar 20, 2023, 7:57 PM (13 hours ago) to me Please increase the budget for PM time to $75,000.00 in project 9186.01. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244! 9186.01 - DHS CC Strategic Space Planning $John Elliott, Jennie Please increase "PM Time (HHS)" in project 9186.01 (DA22) to a total of $100,000.00 "Contracted" Thank you, Jennie Elliott 9186.01-.06 PM/SP budget time changes Elliott, Jennie n you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.01 HHS $Joni Elliott, Jennie Fri, Aug 30, 3:14 PM (5 days ago) to me Please increase DAS PM Time in 9186.01 to a total of $350,000.00 in the Contracted Line Thank you, Jennie Elliott99186.01 HHS $Joni Elliott, Jennie Fri, Aug 30, 3:14 PM (5 days ago) to me Please increase DAS PM Time in 9186.01 to a total of $350,000.00 in the Contracted Line Thank you, Jennie Elliott186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000 9186.01 HHS $Joni Elliott, Jennie Aug 30, 2024, 3:14 PM (5 days ago) to me Please increase DAS PM Time in 9186.01 to a total of $350,000.00 in the Contracted Line Thank you, Jennie Elliott

## #9186.01 PM TIME (DA)
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  |  | Major Program 4D08
PM TIME (DA) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26L
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 0 | 64.78 | 64.78 | -64.78
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 0 | 584.9 | 649.68 | -649.68
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 0 | 30.33 | 680.01 | -680.01
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 0 | 193.7 | 873.71 | -873.71
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 0 | 338.6 | 1212.31 | -1212.31
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 0 | 1625.9 | 2838.21 | -2838.21
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 0 | 79.89 | 2918.1 | -2918.1
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 0 | 644.7 | 3562.8 | -3562.8
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 0 | 78.29 | 3641.09 | -3641.09
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 0 | 575.4 | 4216.49 | -4216.49
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 0 | 66.39 | 4282.88 | -4282.88
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 0 | 334.7 | 4617.58 | -4617.58
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for June 1-30, 2023 from 9186.01 to 9186.05 |  | 0 | -64.78 | 4552.8 | -4552.8
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for June 1-30, 2023 from 9186.01 to 9186.05 |  | 0 | -584.9 | 3967.9 | -3967.9
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for July 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -30.33 | 3937.57 | -3937.57
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for July 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -193.7 | 3743.87 | -3743.87
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for August 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -338.6 | 3405.27 | -3405.27
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for August 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -1625.9 | 1779.37 | -1779.37
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for October 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -79.89 | 1699.48 | -1699.48
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for October 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -644.7 | 1054.78 | -1054.78
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for December 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -78.29 | 976.49 | -976.49
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for December 1-31, 2023 from 9186.01 to 9186.05 |  | 0 | -575.4 | 401.09 | -401.09
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for February 1-29, 2024 from 9186.01 to 9186.05 |  | 0 | -66.39 | 334.7 | -334.7
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for February 1-29, 2024 from 9186.01 to 9186.05 |  | 0 | -334.7 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | -5.3291e-14 |  | 5.3291e-14
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie Jul 13, 2023, 4:26 PM (15 hours ago) to me Please see directions below. Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov On Thu, Jul 13, 2023 at 1:09 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Just following up this Have you had a chance to review? Thanks John On Wed, Jul 12, 2023 at 9:50 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Could you please review the following projects that would be over budget if we post PM time 9186.01 DA22 E26L amount to post 43.06+21.72+41.50+106.70+436.70=649.68 - For PM Time (DA) please allocate $50,000 to the contracted line. 9186.02 DA22 SLFRF HHS SP Time amount to post 7481.25 - For SP Time (HHS) please allocate $10,000 to the contracted line. 9186.02 DA22 SLFRF DA SP Time 16862.50 - For SP Time (DA) please allocate $20,000 to the contracted line.

## #9186.01 SP TIME (HHS)
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  |  | Major Program 4D08
SP TIME (HHS) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26M
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9186.01 SP TIME (DA)
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  |  | Major Program 4D08
SP TIME (DA) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26N
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
IET DAS202405115300001 | 2023-12-07 | 2507 | Space Planning |  | 0 | 47.5 | 47.5 | -47.5
CDE 33524082813 | 2024-03-22 | 2507 | CDE Space Planning from 9186.01 to 9186.05 |  | 0 | -47.5 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Elliott, Jennie 1:58 PM (2 minutes ago) to me Yes, go ahead and set the budget to $500 for now please. Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Fri, Dec 8, 2023 at 1:37 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie we have an amount to post to 9186.01 but there is no budget set up for this eDAS code Can we have a budget to set up?

## #9186.01 Misc
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202208115300001 | 2022-03-07 | 2507 |  | Space Planning Services Febraury 01-28, 2022 | DAS2022081153 | 658.75 | 658.75
IET DAS202209115300001 | 2022-04-08 | 2507 |  | Space Planning Services March 01-31, 2022 | DAS2022091153 | 382.5 | 1041.25
IET DAS202211115300001 | 2022-06-07 | 2507 |  | Space Planning Services May 01-31, 2022 | DAS2022111153 | 127.5 | 1168.75
IET DAS202212115300001 | 2022-07-08 | 2507 |  | Space Planning Services June 01-30, 2022 | DAS2022121153 | 212.5 | 1381.25
IET DAS202301115300001 | 2022-09-08 | 2507 |  | Space Planning Services August 01-31, 2022 | DAS2023011153 | 451.25 | 1832.5
IET DAS202303115300001 | 2022-10-07 | 2507 |  | Space Planning Services September 01-30, 2022 | DAS2023031153 | 237.5 | 2070
IET DAS202304115300001 | 2022-11-08 | 2507 |  | Space Planning Services October 01-31, 2022 | DAS2023041153 | 356.25 | 2426.25
IET DAS202305115300001 | 2022-12-07 | 2507 |  | Space Planning Services November 01-30, 2022 | DAS2023051153 | 95 | 2521.25
IET DAS202307115300001 | 2023-02-07 | 2507 |  | Space Planning Services January 01-31, 2023 | DAS2023071153 | 285 | 2806.25
IET DAS202308115300001 | 2023-03-07 | 2507 |  | Space Planning Services February 01-28, 2023 | DAS2023081153 | 4916.25 | 7722.5
IET DAS202309115300001 | 2023-04-07 | 2507 |  | Space Planning Services March 01-31, 2023 | DAS2023091153 | 2208.75 | 9931.25
IET DAS202310115300001 | 2023-05-07 | 2507 |  | Space Planning Services April 01-30, 2023 | DAS2023101153 | 21850 | 31781.25
IET 33523156902 | 2023-06-01 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356866 | 618 | 32399.25
IET DAS202311115300001 | 2023-06-07 | 2507 |  | Space Planning Services May 01-31, 2023 | DAS2023111153 | 13015 | 45414.25
IET 33523164801 | 2023-06-13 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356876 & 356877 | 1926 | 47340.25
IET 33523187901 | 2023-06-30 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356884 | 1373 | 48713.25
GAX 33523184800 | 2023-07-03 | 9500 | CNST | Tri-City Electric V#(00002106567) | Inv. 291418 | 1782 | 50495.25
IET 33523188803 | 2023-07-07 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356888 | 19386.84 | 69882.09
CDE 33523201803 | 2023-07-20 | 9500 | CNST | Office of the Chief Information Officer | Inv. 9186.01-01 | 10364.69 | 80246.78
IET DAS202401115300001 | 2023-08-07 | 2507 |  | Space Planning Services July 01-31, 2023 | DAS2024011153 | 570 | 80816.78
IET 33524249905 | 2023-09-06 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356902 | 901 | 81717.78
IET 335FY24918601 | 2023-09-07 | 2398 | CNST | ICN Bill July 2023 | Inv. 677169 | 2280 | 83997.78
CDE 33524264803 | 2023-09-21 | 9500 | CNST | Office of the Chief Information Officer | Inv. 9186.01-02 | 124376.28 | 208374.06
GAX 33524268802 | 2023-09-25 | 9500 | CNST | Opex Corp V#(00002094981) | Inv. 10011574 | 3099.14 | 211473.2
IET 33524268804 | 2023-09-25 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356912 | 1133 | 212606.2
PRC 33524307804 | 2023-11-03 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV033595 | 4273.44 | 216879.64
IET 33524310804 | 2023-11-06 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356932 | 29955.62 | 246835.26
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 715 | 247550.26
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Custodial Service November 01-30, 2023 | DAS2024051153 | 966.68 | 248516.94
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Locksmith & Key Services November 01-30, 2023 | DAS2024051153 | 758.36 | 249275.3
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Grounds November 01-30, 2023 | DAS2024051153 | 236.02 | 249511.32
IET 33524352802 | 2023-12-18 | 2398 | CNST | ICN Bill August-November 2023 | Inv. 679044 & 684675 | 920 | 250431.32
IET 33524352803 | 2023-12-18 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356943 | 24841.35 | 275272.67
PRC 33524361802 | 2023-12-27 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2543128 | 1902.5 | 277175.17
IET 33524011800 | 2024-01-11 | 2398 | CNST | ICN Bill December 2023 | Inv. 686553 | 18060.34 | 295235.51
CDE 33524012800 | 2024-01-12 | 2507 |  | Move Expense from 9186.01 to 9268.01 Nov Procurement time |  | -330 | 294905.51
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing January 01-31, 2024 | DAS2024071153 | 1271 | 296176.51
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Electrical Services February 01-28, 2024 | DAS2024081153 | 16034.04 | 312210.55
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Carpentry February 01-28, 2024 | DAS2024081153 | 124.57 | 312335.12
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing February 01-28, 2024 | DAS2024081153 | 20068.28 | 332403.4
PRC 33524079800 | 2024-03-19 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL344 | 5.64 | 332409.04
GAX 33524079804 | 2024-03-19 | 9500 | CNST | Waldinger Corp V#(00002116105) | Inv. 74989E-001 | 459.55 | 332868.59
CDE 33524080808 | 2024-03-20 | 9500 |  | Iowa Department of Inspections & Appeals V#(00000042700) |  | 30081.1 | 362949.69
GAX 33524081916 | 2024-03-21 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010686-IN | 5133.6 | 368083.29
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services Move Expense from 9186.01 to 9186.05 | DAS2023081153 | -4061.25 | 364022.04
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023091153 | -1947.5 | 362074.54
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023101153 | -11542.5 | 350532.04
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023111153 | -5890 | 344642.04
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356884 | -220 | 344422.04
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356888 | -19386.84 | 325035.2
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356902 | -901 | 324134.2
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill July 2024 from 9186.01 to 9186.05 | Inv. 677169 | -2280 | 321854.2
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill August-November 2023 from 9186.01 to 9186.05 | Inv. 679044 & 684675 | -920 | 320934.2
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill December 2023 from 9186.01 to 9186.05 | Inv. 686553 | -18060.34 | 302873.86
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Electrical Services from 9186.01 to 9186.05 | DAS2024081153 | -16034.04 | 286839.82
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Heating/Ventilation/Air Conditioning/Plumbing from 9186.01 to 9186.05 | DAS2024081153 | -20068.28 | 266771.54
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Electrical Services March 01-31, 2024 | DAS2024091153 | 91.94 | 266863.48
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing March 01-31, 2024 | DAS2024091153 | 1607.66 | 268471.14
IET DAS202410115300001 | 2024-05-07 | 2321 |  | Association Rate | DAS2024101153 | 145.83 | 268616.97
IET DAS202411115300001 | 2024-06-10 | 2321 |  | Association Rate | DAS2024111153 | 145.83 | 268762.8
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Locksmith & Key Services June 01-30, 2024 | DAS2024121153 | 12761.51 | 281524.31
IET DAS202412115300001 | 2024-07-10 | 2321 |  | Association Rate | DAS2024121153 | 476.58 | 282000.89
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Custodial Service June 01-30, 2024 | DAS2024121153 | 1837.54 | 283838.43
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Grounds June 01-30, 2024 | DAS2024121153 | 86.93 | 283925.36
GAX 33524193906 | 2024-07-11 | 9500 | CNST | Trinity Construction V#(VS000004014) | Inv. 2305 | 9811.93 | 293737.29
PRCI 33525250901 | 2024-09-06 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357064 | 5130.02 | 298867.31
CDE 33525257909 | 2024-09-13 | 9255 |  | Iowa Department of Inspections & Appeals V#(00000042700) | Inv. 9186.01-01 | 8594.6 | 307461.91
CDE 33525257910 | 2024-09-13 | 9500 | CNST | Office of the Chief Information Officer | Inv. 9186.01-001 | 31904.07 | 339365.98
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Electrical Services August 01-31,2024 | DAS2025021153 | 1527.08 | 340893.06
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Locksmith & Key Services August 01-31,2024 | DAS2025021153 | 190.54 | 341083.6
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Custodial Service September 01-31,2024 | DAS2025031153 | 231.14 | 341314.74
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Custodial Service October 01-31,2024 | DAS2025041153 | 229.49 | 341544.23
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Locksmith & Key Services October 01-31,2024 | DAS2025041153 | 1324.12 | 342868.35
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing October 01-31,2024 | DAS2025041153 | 1310.33 | 344178.68
PRC 33525318910 | 2024-11-13 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv.799566 | 8080 | 352258.68
PRC 33525318911 | 2024-11-13 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2609398 | 1292.5 | 353551.18
PRCI 33525341907 | 2024-12-05 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357125 | 4166.08 | 357717.26
PRCI 33525341910 | 2024-12-05 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357108 & 357109 | 612 | 358329.26
IET DAS202505115300001 | 2024-12-06 | 2507 |  | Locksmith & Key Services November 01-30, 2024 | DAS2025051153 | 2571.33 | 360900.59
IET DAS202505115300001 | 2024-12-06 | 2507 |  | Electrical Services November 01-30, 2024 | DAS2025051153 | 2466.65 | 363367.24
IET DAS202505115300001 | 2024-12-06 | 2501 |  | Infrastructure Consulting OCIO | DAS2025051153 | 326.31 | 363693.55
PRCI 33525344903 | 2024-12-09 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357110 & 357113 | 3382.31 | 367075.86
PCRI 33525365902 | 2024-12-30 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357121 & 357122 | 5990.83 | 373066.69
PRC 33525024900 | 2025-01-24 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2618394 | 237.5 | 373304.19
PRCI 33525024901 | 2025-01-24 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357133 & 357128 | 4606.27 | 377910.46
PRC 33525024907 | 2025-01-24 | 9500 | CNST | Control Installations of Iowa dba Basepoint Bldg Automations SpectraSource V#(00002115535) | Inv. 157707 | 2632.9 | 380543.36
GAX 33525036905 | 2025-02-05 | 9500 | CNST | US Heritage V#(00003226336) | Inv. 2025057 | 2500 | 383043.36
IET DAS202507115300001 | 2025-02-11 | 2507 |  | Locksmith & Key Services January 01-31, 2025 | DAS2025071153 | 155.18 | 383198.54
IET DAS202507115300001 | 2025-02-12 | 2507 |  | Electrical Services January 01-31, 2025 | DAS2025071153 | 432.47 | 383631.01
PRC 33525044902 | 2025-02-12 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2626609 | 227.5 | 383858.51
IET DAS202507115300001 | 2025-02-11 | 2501 |  | OCIO Vendor Pass-Through | DAS2025071153 | 274.95 | 384133.46
GAX 33525049902 | 2025-02-18 | 9500 | CNST | Tri-City Electric V#(00002106567) | Inv. 327620 | 444.31 | 384577.77
GAX 33525050901 | 2025-02-19 | 9500 | CNST | 1st Interiors V#(00002103654) | Inv. PT3711A | 1038 | 385615.77
CDE 33525055906 | 2025-02-24 | 9500 | CNST | Correcting Event Type on CDE 33525257910 |  | 0 | 385615.77
GAX 33525090901 | 2025-03-31 | 9500 | CNST | Premier Ceiling V#(00003226645) | Inv. 191345800 | 440.1 | 386055.87
GAX 33525090902 | 2025-03-31 | 9500 | CNST | Ideal Floors V#(00002126112) | Inv. 32979 | 1967 | 388022.87
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Locksmith & Key Services March 01-31, 2025 | DAS2025091153 | 3241.07 | 391263.94
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Electrical Services March 01-31, 2025 | DAS2025091153 | 261.77 | 391525.71
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Custodial Services March 01-31, 2025 | DAS2025091153 | 317 | 391842.71
PRCI 33525118904 | 2025-04-28 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357173 | 448 | 392290.71
PRC 33525118905 | 2025-04-28 | 9500 | CNST | Communication Innovators V#(00002119160) | Inv. 121209 | 536.25 | 392826.96
IET 33525118910 | 2028-04-25 | 2398 | CNST | ICN Bill November 2024 | Inv. 711411-013 | 644.76 | 393471.72
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Locksmith & Key Services April 1-30, 2025 | DAS2025101153 | 4061.33 | 397533.05
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Locksmith & Key Services April 1-30, 2025 | DAS2025101153 | 95.27 | 397628.32
PRC 33525140906 | 2025-05-20 | 9500 | CNST | Control Installations V#(00002115535) | Inv. 163765 | 2649.9 | 400278.22
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Fire Watch May 1-31, 2025 | DAS2025111153 | 214.05 | 400492.27
400492.27
|  |  |  | Totals: |  | 400492.27

## #9186.01 DCI Group #21-007.1 CA
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
DCI Group #21-007.1 CA |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523068801 | 2023-03-09 | PO Procore (Discarded in I-3) |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9186.01 Shive Hattery (2)
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Shive Hattery (2) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP1820335153
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523068802 | 2023-03-09 | PO Procore (Discarded in I-3) |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0
|  | Schematic Design Fee | 0 |  |  |  | 0
|  | Design Development Fee | 0 |  |  |  | 0
|  | Construction Documents Fee | 0 |  |  |  | 0
|  | Bidding Assistance Fee | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9186.01 Atlas One
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Atlas One |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523137802 | 2023-05-17 | DO Procore | 5605 | 5605 |  |  | 5605
DO 33523137802 | 2023-07-21 | CO #1 | -1380 | 4225 |  | 0 | 4225
PRC 3352313PA7802 | 2023-07-21 | Inv. 2510125 |  | 4225 | 4225 | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  |  |  | 4225 |  | 4225 | 0
|  | Totals | 4225 |  | 4225 |  | 0 | FINAL
|  | Field Technician Time (32 Hours at $75/Hour) | 2400 |  | 2400 |  | 0
|  | Hygienist (20 hours at $95/Hour) | 1900 |  | 1900 |  | 0
|  | Adminstraction Time (3 Hours at $45/Hour) | 135 |  | 135 |  | 0
|  | Suspected Asbestos Sample Analysis ($10/Sample for 72 samples) | 720 |  | 720 |  | 0
|  | Suspected Lead Based Paint Sample Analysis ($15/Sample for 30 samples) | 450 |  | 450 |  | 0
|  | CO #1 | -1380 |  | -1380 |  | 0
|  | Total: | 4225 |  | 4225 |  | 0

## #9186.01 Controlled Asbestos
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Controlled Asbestos |  |  | Vendor Code: 00002118118
Acct. Codes-0506-335-DA22-9255 |  |  | MA21060
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524284803 | 2023-10-11 | DO I/3 | 5298.88 | 5298.88 |  |  | 5298.88
PRC 3352428PA4803 | 2023-12-08 | Inv. 0010665-IN |  | 5298.88 | 3493.12 | 3493.12 | 1805.76
DO 33524284803 | 2024-07-19 | Closing PO Vendor and PM | -1805.76 | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  |  |  | 3493.12 |  | 3493.12 | 0
|  | Totals: | 3493.12 |  | 3493.12 |  | 0
|  | Line 1 - 4 hrs x $58 | 203 |  | 203 |  | 0
|  | Line 1 - Drive - .5 hrs x 1 trip | 0 |  |  |  | 0
|  | Line 5 - 80 hrs x 10 trip | 3248 |  | 3248 |  | 0
|  | Line 5 - Drive - .5 hrs x 10 trip | 0 |  |  |  | 0
|  | Line 7 - Air Samples | 0 |  |  |  | 0
|  | Line 11 - Non Friable $64 x 0.1 Ton | 0 |  |  |  | 0
|  | Line 12 - 11 Trips x 12 miles = 132 Mi x 0.39 | 42.12 |  | 42.12 |  | 0
|  | Total | 3493.12 |  | 3493.12 |  | 0

## #9186.01 DCI Group 22-037 CA
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
DCI Group #22-037 CA |  |  | Vendor Code: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524289801 | 2023-10-16 | PO Procore | 1248145.46 | 1248145.46 |  |  | 1248145.46
PRC 3352428PA9801 | 2023-12-08 | Inv. 23-007 CA-01 |  | 1248145.46 | 24800.98 | 24800.98 | 1223344.48
PRC 3352428PB9801 | 2023-12-27 | Inv. 23-007 CA 02 |  | 1248145.46 | 78533.96 | 103334.94 | 1144810.52
PRC 3352428PC9801 | 2024-02-21 | Inv. 23-007 CA 03 |  | 1248145.46 | 66991.44 | 170326.38 | 1077819.08
PRC 3352428PD9801 | 2024-04-15 | Inv. 23-007 CA 04 |  | 1248145.46 | 148644.89 | 318971.27 | 929174.19
PO 33524289801 | 2024-04-24 | Close PO per PM | -682284.27 | 565861.19 |  | 318971.27 | 246889.92
PO 33524289801A | 2024-04-24 | Open PO per PM (Unencumbered) |  | 565861.19 |  | 318971.27 | 246889.92
PRC 3352428PE9801A | 2024-05-13 | Inv. 23-007 CA 05 |  | 565861.19 | 94697.2 | 413668.47 | 152192.72
GAX 33524184908 | 2024-07-02 | Inv. 23-007 CA 06(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
GAX 33524213901 | 2024-07-31 | Inv. 23-007 CA-07(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72 | FY24
PO 33525289801A | 2024-08-16 | Roll to FY25 | 0 | 565861.19 |  | 413668.47 | 152192.72
PRC 3352528PH9801A | 2024-09-04 | Inv. 23-007 CA 08(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PRC 3352528PI9801A | 2024-11-24 | Inv. 23-007 CA 09(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PRC 3352528PJ9801A | 2024-12-03 | Inv. 23-007 CA 10(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PRC 3352528PK9801A | 2024-12-30 | Inv. 23-007 CA 11(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PRC 3352528PL9801A | 2025-01-27 | Inv. 23-007 CA 12(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PRC 3352528PM9801A | 2025-02-17 | Inv. 23-007 CA 13(100% to 918602) |  | 565861.19 | 0 | 413668.47 | 152192.72
PO 33525289801B | 2025-04-16 | Correcting PO Division |  | 565861.19 |  | 413668.47 | 152192.72
PRC 3352528PN9801B | 2025-04-16 | Inv. 23-007 CA 14(Split w/ 918602) |  | 565861.19 | 30236.91 | 443905.38 | 121955.81
PRC 3352528PO9801B | 2025-04-25 | Inv. 23-007 CA 15(100% to 918601) |  | 565861.19 | 41614.42 | 485519.8 | 80341.39
PRC 3352528PP9801B | 2025-05-10 | Inv. 23-007 CA 16(100% to 918601) |  | 565861.19 | 41712.64 | 527232.44 | 38628.75
PRC 3352528PQ9801B | 2025-06-23 | Inv. 23-007 CA 17(100% to 918601) |  | 565861.19 | 38628.75 | 565861.19 | -2.0373e-10
|  |  |  | 565861.19 |  | 565861.19 | -2.0373e-10
|  |  |  | 565861.19 |  | 565861.19 | -2.0373e-10
|  |  |  | 565861.19 |  | 565861.19 | -2.0373e-10
|  | Totals: | 565861.19 |  | 565861.19 |  | 0
PO number above is assigned to Procore PO, and created in IA Advantage as Unencumbered due to Paper Contract.
Will create payments as funds become available to charge against this project.
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Construction Management Staff Hours | 582007.44 |  | 311310.44 |  | 270697
|  | Reimbursable Expenses | 160400 |  | 62158.94 |  | 98241.06
|  | Construction Management Fee | 258848.1 |  | 51769.62 |  | 207078.48
|  | Split Funding 9186.02 06/17/24 | -587587.07 |  |  |  | -587587.07
|  | CO #1 01/28/25 100% to 9186.02 | 0 |  |  |  | 0
|  | CO #2 02/18/25 100% to 9186.01 | 182156.73 |  | 140622.19 |  | 41534.54
|  | Total: 9186.01 | 595825.2 |  | 565861.19 |  | 29964.01
|  | 9186.02 06/17/24 SLFRF Funds | 725277.04 |  | 682120.77 |  | 43156.27
|  | Total Contract: 9186.01 and 9186.02 | 1321102.24 |  | 1247981.96 |  | 73120.28

## #9186.01 Holmes Murphy
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Holmes Murphy |  |  | Vendor Code: 00002110543
Acct. Codes-0506-335-DA22-9255 |  |  | MA18142E
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524292801 | 2023-10-19 | DO Procore | 9236 | 9236 |  |  | 9236
PRC 3352429PA2801 | 2023-11-03 | Inv. 733286 |  | 9236 | 9236 | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  |  |  | 9236 |  | 9236 | 0
|  | Totals: | 9236 |  | 9236 |  | 0

## #9186.01 Ball Team
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Ball Team |  |  | Vendor Code: 00003090419
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299805 | 2023-10-26 | PO Procore | 1437876.7 | 1437876.7 |  |  | 1437876.7
GAX 33524342805 | 2023-12-08 | Inv. 9186.01-001 |  | 1437876.7 | 29114.27 | 29114.27 | 1408762.43 | 1532.33
GAX 33524036903 | 2024-02-05 | Inv. 9186.01-002 |  | 1437876.7 | 69537.15 | 98651.42 | 1339225.28 | 5192.18
GAX 33524079806 | 2024-03-19 | Inv. 9186.01-003 |  | 1437876.7 | 195812.1 | 294463.52 | 1143413.18 | 15498.08
GAX 33524099800 | 2024-04-08 | Inv. 9186.01-004 |  | 1437876.7 | 250896.9 | 545360.42 | 892516.28 | 28703.18
GAX 33524130802 | 2024-05-09 | Inv. 9186.01-005 |  | 1437876.7 | 413005.85 | 958366.27 | 479510.43 | 50440.33
GAX 33524184906 | 2024-07-02 | Inv. 9186.02-06(100% to 918602) |  | 1437876.7 | 0 | 958366.27 | 479510.43 | 50440.33
CDE 33524192801 | 2024-07-10 | Move Expenses from 9186.01 to 9186.02 |  | 1437876.7 | -69537.15 | 888829.12 | 549047.58 | 46780.48
CDE 33524192802 | 2024-07-10 | Move Expenses from 9186.01 to 9186.02 |  | 1437876.7 | -413005.85 | 475823.27 | 962053.43 | 25043.33
GAX 33525213903 | 2024-07-31 | Inv. 9186.02-07(Split with 9186.02) |  | 1437876.7 | 15588.55 | 491411.82 | 946464.88 | 25863.77 | FY24
PO 33525299805 | 2024-08-26 | Roll to FY25 | 0 | 1437876.7 |  | 491411.82 | 946464.88
GAX 33525248902 | 2024-09-04 | Inv. 9186.02-08(Split with 9186.02) |  | 1437876.7 | 1904.75 | 493316.57 | 944560.13 | 25964.02
GAX 33525271906 | 2024-09-27 | Inv. 9186.02-09(100% to 9186.01) |  | 1437876.7 | 121513.7 | 614830.27 | 823046.43 | 32359.48
GAX 33525309903 | 2024-10-04 | Inv. 9186.02-10(Split with 9186.02) |  | 1437876.7 | 126672.9 | 741503.17 | 696373.53 | 39026.47
GAX 33525351906 | 2024-12-16 | Inv. 9186.02-11(100% to 9186.01) |  | 1437876.7 | 55783.05 | 797286.22 | 640590.48 | 41962.42
GAX 33525027904 | 2025-01-27 | Inv. 9186.02-12(100% to 9186.01) |  | 1437876.7 | 83535.4 | 880821.62 | 557055.08 | 46359.02
GAX 33525055902 | 2025-02-24 | Inv. 9186.02-13(100% to 9186.01) |  | 1437876.7 | 157373.21 | 1038194.83 | 399681.87 | 54641.83
GAX 33525090912 | 2025-03-31 | Inv. 9186.02-14(100% to 9186.01) |  | 1437876.7 | 131832.24 | 1170027.07 | 267849.63 | 61580.37
GAX 33525115910 | 2025-04-25 | Inv. 9186.01-15(100% to 9186.01) |  | 1437876.7 | 111760.94 | 1281788.01 | 156088.69 | 67462.53
GAX 33525135900 | 2025-05-15 | Inv. 9186.01-16(100% to 9186.01) |  | 1437876.7 | 112913.72 | 1394701.73 | 43174.97 | 73405.36
GAX 33525176901 | 2025-06-25 | Inv. 9186.01-17(Split W/9186.02) |  | 1437876.7 | 103283.05 | 1497984.78 | -60108.08 | 78841.31
CDE 33525177902 | 2025-06-26 | Move Expenses from 9186.01 to 9186.02 |  | 1437876.7 | -60108.08 | 1437876.7 | 0 | 75835.91
|  |  |  | 1437876.7 |  | 1437876.7 | 0
|  |  |  | 1437876.7 |  | 1437876.7 | 0
|  |  |  | 1437876.7 |  | 1437876.7 | 0
|  | Totals: | 1437876.7 |  | 1437876.7 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Base Bid | 2482000 |  | 951196.62 |  | 1530803.38
|  | CO 1 - 01/24/2024 Split w/9186.02 | 3600 |  | 3420 |  | 180
|  | CO 2 - 02/09/2024 | 6819 |  | 6478.05 |  | 340.95
|  | CO 3 - 02/26/2024 100% to 9186.01 | -9224 |  | -8762.8 |  | -461.2
|  | CO 4 - 04/11/2024 100% to 9186.01 | 884 |  | 839.8 |  | 44.2
|  | CO 5 - 04/24/2024 100% to 9186.01 | 5468 |  | 5194.6 |  | 273.4
|  | CO 6 - 05/28/2024 100% to 9186.01 | 16409 |  | 15588.55 |  | 820.45
|  | CO 7 - 06/14/2024 100% to 9186.01 | 9651 |  | 9168.45 |  | 482.55
|  | Split funding to 9186.02 06/17/24 | -1560861.73 |  | 0 |  | -1560861.73
|  | Moved Expenses from 9186.01 to 9186.02 | -73197 |  | -69537.15 |  | -3659.85
|  | Moved Expenses from 9186.01 to 9186.02 | -434743 |  | -413005.85 |  | -21737.15
|  | CO #8 07/03/2024 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #9 09/04/2024 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #10 10/02/2024 100% to 9186.01 | 8875 |  | 8431.25 |  | 443.75
|  | CO #11 10/22/2024 100% to 9186.01 | 133077 |  | 126423.14 |  | 6653.86
|  | CO #12 11/22/2024 100% to 9186.01 | 403630 |  | 383556.65 |  | 20073.35
|  | CO #13 01/06/2025 Split w/9186.02 | 92877 |  | 88233.15 |  | 4643.85
|  | CO #14 04/10/2025 100% to 9186.01 | 20471 |  | 19447.45 |  | 1023.55
|  | CO #15 05/07/2025 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #16 06/25/2025 100% to 9186.02 | 0 |  | 0 |  | 0
|  | Moved Expenses from 9186.01 to 9186.02 | -63113.4 |  | -60108.08 |  | -3005.32
|  | Split Funding to 9186.02 06/17/24 | 471090.82 |  | 371312.87 |  | 99777.95
|  | Total: 9186.01 | 1513712.69 |  | 1437876.7 |  | 75835.99
|  | 9186.02 06/17/2024 SLFRF Funds | 1813849.39 |  | 1654724.03 |  | 159125.36
|  | Total Contract: 9186.01 and 9186.02 | 3327562.08 |  | 3092600.73 |  | 234961.35

## #9186.01 Elite Fire Sprinkler
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Elite Fire Sprinkler Systems |  |  | Vendor Code: 00003212887
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299808 | 2023-10-26 | PO Procore | 135678.52 | 135678.52 |  |  | 135678.52
GAX 33524080809 | 2024-03-20 | Inv. Pay App 1 and 2 |  | 135678.52 | 115899.05 | 115899.05 | 19779.47 | 6099.95
GAX 33524113802 | 2024-04-23 | Inv. Pay App 3 |  | 135678.52 | 8621.25 | 124520.3 | 11158.22 | 6553.7
GAX 33524184907 | 2024-07-02 | Inv. 9186.02-Pay App 4(100% to 9186.02) |  | 135678.52 | 0 | 124520.3 | 11158.22
GAX 33524213902 | 2024-07-31 | Inv. 9186.02-Pay App 4.1(100% to 9186.02) |  | 135678.52 | 0 | 124520.3 | 11158.22 |  | FY24
PO 33525299808 | 2024-08-26 | Roll to FY25 | 0 | 135678.52 |  | 124520.3 | 11158.22
GAX 33525271910 | 2024-09-27 | Inv. 9186.02-Pay App 5(100% to 9186.02) |  | 135678.52 | 0 | 124520.3 | 11158.22
GAX 33525326902 | 2024-11-21 | Inv. 9186.02-Pay App 6(Split W/ 9186.02) |  | 135678.52 | 6022.05 | 130542.35 | 5136.17 | 6870.65
GAX 33525036904 | 2025-02-05 | Inv. 9186.02-Pay App 7(Split W/ 9186.02) |  | 135678.52 | 528.2 | 131070.55 | 4607.97 | 6898.45
GAX 33525065903 | 2025-03-06 | Inv. 9186.02-Pay App 12(100% to 9186.02) |  | 135678.52 | 0 | 131070.55 | 4607.97
GAX 33525175900 | 2025-06-24 | Inv. 9186.02-Pay App 13(100% to 9186.01) |  | 135678.52 | 4607.97 | 135678.52 | 0 | 7140.98
|  |  |  | 135678.52 |  | 135678.52 | 0
|  |  |  | 135678.52 |  | 135678.52 | 0
|  | Totals: | 135678.52 |  | 135678.52 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Base Bid | 216085 |  | 124520.3 |  | 91564.7
|  | CO #1 | -8000 |  |  |  | -8000
|  | Split Funding 9186.02 06/17/24 | -83564.7 |  |  |  | -83564.7
|  | CO #2 09/26/24 No Cost CO | 0 |  |  |  | 0
|  | CO #3 10/15/24 100% to 918601 | 7451 |  | 6550.25 |  | 900.75
|  | CO #4 11/22/24 100% to 918601 | 20118 |  |  |  | 20118
|  | CO #5 02/26/25 100% to 918601 | 728 |  | 691.6 |  | 36.4
|  | CO #6 04/15/25 100% to 918601 | 6171 |  | 3916.37 |  | 2254.63
|  | CO #7 05/07/25 No Cost CO | 0 |  |  |  | 0
|  | Total: 9186.01 | 158988.3 |  | 135678.52 |  | 23309.78
|  | 9186.02 06/17/24 SLFRF Funds | 83564.7 |  | 70513.27 |  | 13051.43
|  | Total Contract: 9186.01 and 9186.02 | 242553 |  | 206191.79 |  | 36361.21

## #9186.01 Ideal Floors
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Ideal Floors |  |  | Vendor Code: 00002126112
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299811 | 2023-10-26 | PO Procore | 528681.59 | 528681.59 |  |  | 528681.59
GAX 33524354802 | 2023-12-20 | Inv. 31767 |  | 528681.59 | 10165 | 10165 | 518516.59
GAX 33524354802 | 2024-01-02 | Inv. 31767 (EFT Returned by Financial Institution) |  | 528681.59 | -10165 | 0 | 528681.59
GAX 0801OT010424F | 2024-01-04 | Inv. 31767 (Replacement Warrant issued by SAE) |  | 528681.59 | 10165 | 10165 | 518516.59 | 535
GAX 33524115802 | 2024-04-24 | Inv. 32321 |  | 528681.59 | 471916.47 | 482081.47 | 46600.12 | 25372.69
GAX 33524219902 | 2024-08-06 | Inv. 9186.02-03(100% to 9186.02) |  | 528681.59 | 0 | 482081.47 | 46600.12 |  | FY24
PO 33525299811 | 2024-08-26 | Roll to FY25 | 0 | 528681.59 |  | 482081.47 | 46600.12
GAX 33525248901 | 2024-09-04 | Inv. 9186.02-04(100% to 9186.02) |  | 528681.59 | 0 | 482081.47 | 46600.12
GAX 33525365905 | 2024-12-30 | Inv. 9186.02-06(100% to 9186.02) |  | 528681.59 | 0 | 482081.47 | 46600.12
GAX 33525055903 | 2025-02-24 | Inv. 32943(100% to 9186.01) |  | 528681.59 | 27674.45 | 509755.92 | 18925.67 | 26829.24
GAX 33525065902 | 2025-03-06 | Inv. 9186.02-07(100% to 9186.02) |  | 528681.59 | 0 | 509755.92 | 18925.67
GAX 33525177904 | 2025-06-26 | Inv. 9186.02-08(Split w/ 9186.02) |  | 528681.59 | 18925.67 | 528681.59 | 0 | 27825.33
|  |  |  | 528681.59 |  | 528681.59 | 0
|  |  |  | 528681.59 |  | 528681.59 | 0
|  |  |  | 528681.59 |  | 528681.59 | 0
|  | Totals: | 528681.59 |  | 528681.59 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Base Bid-Split funding to 9186.02 06/17/24 | 549765 |  | 451645.37 |  | 98119.63
|  | Split funding to 9186.02 06/17/24 | -475416.2 |  |  |  | -475416.2
|  | CO #1-Split funding to 9186.02 06/17/24 | 19717 |  | 18731.15 |  | 985.85
|  | CO #2-Split funding to 9186.02 06/17/24 | 12321 |  | 11704.95 |  | 616.05
|  | CO #3 06/19/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #4 09/04/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #5 10/22/24 100% to 9186.01 | 1750.76 |  | 1663.22 |  | 87.54
|  | CO #6 11/22/24 100% to 9186.01 | 60302 |  | 44936.9 |  | 15365.1
|  | CO #7 05/07/25 No Cost CO | 0 |  | 0 |  | 0
|  | Split funding from 9186.01 | 406565.01 |  | 0 |  | 406565.01
|  | Total: 9186.01 | 575004.57 |  | 528681.59 |  | 46322.98
|  | 9186.02 06/17/24 SLFRF Funds | 83457.07 |  | 79284.23 |  | 4172.84
|  | Total Contract: 9186.01 and 9186.02 | 658461.64 |  | 607965.82 |  | 50495.82

## #9186.01 All Makes
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
All Makes-Furniture |  |  | Vendor Code: 00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA23148
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524325801 | 2023-11-21 | PO Procore | 1780472.55 | 1780472.55 |  |  | 1780472.55
GAX 33524185907 | 2024-07-02 | Inv. 311713(100% to 918602) |  | 1780472.55 | 0 | 0 | 1780472.55
GAX 33524211900 | 2024-07-29 | Inv. 311892, 311880, 311798(100% to 918602) |  | 1780472.55 | 0 | 0 | 1780472.55 |  | FY24
PO 33525325801 | 2024-08-26 | Roll to FY25 | 591511.86 | 2371984.41 |  | 0 | 2371984.41
GAX 33525249906 | 2024-09-05 | Inv. 311980, 311981, 312083, 312085, 312088(100% to (9186.01) |  | 2371984.41 | 1780472.55 | 1780472.55 | 591511.86 | 93709.08
GAX 33525304903 | 2024-10-30 | Inv. 312214(100% to 9186.01) |  | 2371984.41 | 81419.75 | 1861892.3 | 510092.11 | 97994.34
GAX 33525310900 | 2024-11-05 | Inv. 312133, 312084, 312085-2, 312270, 312271(100% to 9186.01) |  | 2371984.41 | 151783.66 | 2013675.96 | 358308.45 | 105982.96
GAX 33525365906 | 2024-12-30 | Inv. 312299(100% to 918602) |  | 2371984.41 | 0 | 2013675.96 | 358308.45
GAX 33525043901 | 2025-02-11 | Inv. 312389, 312473(100%to 9186.01) |  | 2371984.41 | 4365.1 | 2018041.06 | 353943.35 | 106212.7
GAX 33525062901 | 2025-03-04 | Inv. 312655, 312659(100% to 9186.01) |  | 2371984.41 | 67661.87 | 2085702.93 | 286281.48 | 109773.85
GAX 33525104901 | 2025-04-14 | Inv. 312792, 312740, 312791, 312784 (100% to 9186.01) |  | 2371984.41 | 80310.64 | 2166013.57 | 205970.84 | 114000.72
GAX 33525174908 | 2025-06-23 | Inv. 312887, 312865, 312921, 312888 (Split w/ 9186.02) |  | 2371984.41 | 205970.84 | 2371984.41 | 0 | 124841.3
|  |  |  | 2371984.41 |  | 2371984.41 | 0
|  | Totals: | 2371984.41 |  | 2371984.41 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Furniture | 4638459.85 |  | 2130675.55 |  | 2507784.3
|  | CO #1 | -47872.36 |  |  |  | -47872.36
|  | CO #2 | 9516.26 |  |  |  | 9516.26
|  | CO #3 | 3448.25 |  | 1379.3 |  | 2068.95
|  | CO #4 - Not Used | 0 |  | 0 |  | 0
|  | Split funding 9186.02 06/17/24 | -2400000 |  |  |  | -2400000
|  | CO #5 100% to 9186.01 | 7869 |  | 7869 |  | 0
|  | CO #6 100% to 9186.01 10/08/24 | -30220.75 |  | -28709.71 |  | -1511.04
|  | CO #7 Split with 918602 01/23/25 | 216258.02 |  | 154974.94 |  | 61283.08
|  | CO #8 100% to 9186.01 01/23/25 | 81655.17 |  | 74319.94 |  | 7335.23
|  | CO #9 100% to 9186.01 03/04/25 | 7132.62 |  | 6775.99 |  | 356.63
|  | CO#10 100% to 9186.01 03/07/25 | 25999.37 |  | 24699.4 |  | 1299.97
|  | Total: 9186.01 | 2512245.43 |  | 2371984.41 |  | 140261.02
|  | 9186.02 06/17/24 SLFRF Funds | 2407538.56 |  | 2281545.83 |  | 166612.49
|  | Total Contract: 9186.01 and 9186.02 | 4919783.99 |  | 4653530.24 |  | 266253.75

## #9186.01 Bergstrom Construction
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Bergstrom Construction |  |  | Vendor Code: 00002110114
Acct. Codes-0506-335-DA22-9255 |  |  | MA 23199
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524082920 | 2024-03-22 | DO Procore | 11323.06 | 11323.06 |  |  | 11323.06
PRC 3352408PA2920 | 2024-04-23 | Inv. 8581 |  | 11323.06 | 2224.85 | 2224.85 | 9098.21
PRC 3352408PB2920 | 2024-07-26 | Inv. 8581-2 |  | 11323.06 | 9098.21 | 11323.06 | 0 | FY24
PO 33525082920 | 2024-08-26 | Roll To FY25 | 0 | 11323.06 |  | 11323.06 | 0
PO 33525082920 | 2025-01-31 | Closing Encumbered PO |  | 11323.06 |  | 11323.06 | 0
PO 33525082920A | 2025-01-31 | Opening as Unencumbered |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  |  |  | 11323.06 |  | 11323.06 | 0
|  | Totals: | 11323.06 |  | 11323.06 |  | 0
|  | Materials + 15% markup | 4945.54 |  | 3363.26 |  | 1582.28
|  | 173 hours@$87.02/hr | 15054.46 |  | 7959.8 |  | 7094.66
|  | Total | 20000 |  | 11323.06 |  | 8676.94

## #9186.01 Tri-City Electric
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Tri-City Electric |  |  | Vendor Code: 00002106567
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299809 | 2023-10-26 | DO Procore |  | 0 |  |  | 0
GAX 33524208917 | 2024-07-26 | Inv. 313794(100% to 918602) |  | 0 | 0 | 0 | 0 |  | FY24
PO 33525299809 | 2024-08-26 | Roll to FY25 | 517173.8 | 517173.8 |  | 0 | 517173.8
GAX 33525249904 | 2024-09-05 | Inv. 315236(100% to 918602) |  | 517173.8 | 0 | 0 | 517173.8
GAX 33525309901 | 2024-11-04 | Inv. 320785(100% to 9186.01) |  | 517173.8 | 80719.49 | 80719.49 | 436454.31 | 4248.39
GAX 33525326905 | 2024-11-21 | Inv. 320790(Split w/9186.02) |  | 517173.8 | 14351.39 | 95070.88 | 422102.92 | 5003.73
GAX 33525003908 | 2025-01-03 | Inv. 323025(Split w/9186.02) |  | 517173.8 | 18234.35 | 113305.23 | 403868.57 | 5963.43
GAX 33525035911 | 2025-02-24 | Inv. 324684(Split w/9186.02) |  | 517173.8 | 65674.4 | 178979.63 | 338194.17 | 9419.98
GAX 33525065901 | 2025-03-06 | Inv. 326892(Split w/9186.02) |  | 517173.8 | 185490.54 | 364470.17 | 152703.63 | 19182.64
CDE 33525133911 | 2025-05-13 | Moving Expense to 9186.01 From 9186.02 | 135640.76 | 652814.56 | 135640.76 | 500110.93 | 152703.63 | 26321.68
GAX 33525139900 | 2025-05-19 | Inv. 328857(Split w/9186.02) |  | 652814.56 | 27217.31 | 527328.24 | 125486.32 | 27754.17
GAX 33525155900 | 2025-06-04 | Inv. 332294(Split w/9186.02) |  | 652814.56 | 100856.02 | 628184.26 | 24630.3 | 33062.37
CDE 33525177906 | 2025-06-26 | Moving Expense to 9186.01 From 9186.02 |  | 652814.56 | -20942.47 | 607241.79 | 45572.77 | 32156.19
GAX 33525178911 | 2025-06-27 | Inv. 334277 (Split w/9186.02) |  | 652814.56 | 45572.77 | 652814.56 | 0 | 34554.76
|  |  |  | 652814.56 |  | 652814.56 | 0
|  |  |  | 652814.56 |  | 652814.56 | 0
|  | Totals: | 652814.56 |  | 652814.56 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Split Funding 9186.02 06/17/24 | 325000 |  | 190361.45 |  | 134638.55
|  | CO #001 02/02/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #002 02/12/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #003 03/22/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #004 04/05/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #005 04/23/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #006 05/28/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #007 06/14/24 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #008 07/11/24 100% To 918602 | 0 |  | 0 |  | 0
|  | CO #009 09/04/24 100% To 918601 | 8201.06 |  | 7791.01 |  | 410.05
|  | CO #010 10/04/24 100% To 918602 | 0 |  | 0 |  | 0
|  | CO #011 10/24/24 100% To 918601 | 39010.9 |  | 37060.34 |  | 1950.56
|  | CO #012 12/12/24 100% To 918602 | 0 |  | 0 |  | 0
|  | CO #013 01/06/25 100% to 9186.01 | 318845.77 |  | 302903.47 |  | 15942.3
|  | CO #14 02/18/25 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #15 04/29/25 100% to 9186.02 | 0 |  | 0 |  | 0
|  | CO #16 06/12/25 100% to 9186.02 | 0 |  | 0 |  | 0
|  | Moved Expenses from 9186.02 to 9186.01 | 142779.75 |  | 135640.76 |  | 7138.99
|  | Moved Expenses from 9186.01 to 9186.02 | -21848.65 |  | -20942.47 |  | -906.18
|  | Split funding from 9186.01 | -124619.51 |  | 0 |  | -124619.51
|  | Total: 9186.01 | 687369.32 |  | 652814.56 |  | 34554.76
|  | 9186.02 06/17/24 SLFRF Funds | 2415739.07 |  | 2294306.79 |  | 121432.28
|  | Total Contract: 9186.01 and 9186.02 | 3103108.39 |  | 2947121.35 |  | 155987.04

## #9186.01 Central Iowa Mechanic
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Central Iowa Mechanical |  |  | Vendor Code: 00002109717
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524297801 | 2024-06-17 | PO Procore |  | 0 |  |  | 0 |  | FY24
PO 33525297801 | 2024-08-26 | Roll to FY25 | 379822.13 | 379822.13 |  | 0 | 379822.13
GAX 33525250903 | 2024-09-06 | Inv. 2391310-6(100% to 918602) |  | 379822.13 | 0 | 0 | 379822.13
GAX 33525304902 | 2024-10-30 | Inv. 2391310-7(100% to 918601) |  | 379822.13 | 107987.91 | 107987.91 | 271834.22 | 5683.59
GAX 33525080906 | 2025-03-21 | Inv. 2391310-8(Split w/918602) |  | 379822.13 | 234531.71 | 342519.62 | 37302.51 | 18027.38
GAX 33525155901 | 2025-06-04 | Inv. 2391310-9(Split w/918602) |  | 379822.13 | 37302.51 | 379822.13 | 0 | 19990.71
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  |  |  | 379822.13 |  | 379822.13 | 0
|  | Totals: | 379822.13 |  | 379822.13 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Split Funding 9186.02 06/17/24 | 400000 |  | 323177.62 |  | 76822.38
|  | CO #5 07/11/2024 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #6 09/04/2024 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #7 09/17/2024 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #8 10/22/2024 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #9 11/22/2024 100% to 918601 | 182896 |  | 56644.51 |  | 126251.49
|  | CO #10 02/25/2025 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #11 03/04/2025 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #12 05/07/2025 100% to 918602 | 0 |  | 0 |  | 0
|  | CO #13 06/24/25 100% to 918602 | 0 |  | 0 |  | 0
|  | Total: 9186.01 | 582896 |  | 379822.13 |  | 203073.87
|  | 9186.02 06/17/2024 | 1768125 |  | 1587007.76 |  | 181117.24
|  | Total Contract: 9186.01 and 9186.02 | 2351021 |  | 1966829.89 |  | 384191.11

## #9186.01 Cominskey Glass
DHS CC Strategic Space Planning
Project # 9186.01
Program code 918601 |  |  | Major Program 4D08
Cominskey Glass |  |  | Vendor Code: 00002118031
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525299807 | 2024-10-15 | Paper Contract | 1438.01 | 1438.01 |  |  | 1438.01
GAX 33525365903 | 2024-12-30 | Inv. 9186.01-04(Split w/9186.02) |  | 1438.01 | 1438.01 | 1438.01 | 0 | 75.69
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  |  |  | 1438.01 |  | 1438.01 | 0
|  | Totals: | 1438.01 |  | 1438.01 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | CO # 2 10/15/2024 100% to 9186.01 | 1513.7 |  | 1438.01 |  | 75.69
|  | CO # 3 10/24/2024 100% to 9186.01 | 1291 |  | 0 |  | 1291
|  | CO #4 01/16/2025 100% to 9186.02 | 0 |  |  |  | 0
|  | CO #5 05/07/2025 100% to 9186.02 | 0 |  |  |  | 0
|  | CO #6 06/19/2025 No Cost CO | 0 |  |  |  | 0
|  | Total 9186.01: | 2804.7 |  | 1438.01 |  | 1366.69
|  | 9186.02 10/24/2024 | 137501.54 |  | 109990.08 |  | 27511.46
|  | Total Contract: 9186.01 and 9186.02: | 140306.24 |  | 111428.09 |  | 28878.15

## RECAP #9186.02
DHS CC Strategic Space Planning
Project # 9186.02
| Program code 918602 SLFRF |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursements
| Funds received per MOU | 10432829.63
C | DCI Group |  | 88415.74 | 88415.74 | 0 |  | 0
| PM TIME (HHS) |  | 0 | 0 | 0 |  | 0
| PM TIME (DA) |  | 0 | 0 | 0 |  | 0
| SP TIME (HHS) |  | 22752.5 | 22752.5 | 0 |  | 0
| SP Time (DA) |  | 0 | 0 | 0 |  | 0
| PM Time (Ground Floor) |  | 25190.41 | 25190.41 | 0 |  | 0
| Misc. |  | 35336.48 | 35336.48 | 0 |  | 0
| Shive Hattery (P) |  | 968359.4 | 968359.4 | 0 |  | 47592.6
C | Heartland Finishes |  | 0 | 0 | 0 |  | 0
C | Ralph Smith (P) |  | 0 | 0 | 0 |  | 0
C | Shyft Collective (P) |  | 0 | 0 | 0 |  | 0
C | All Makes (P) |  | 0 | 0 | 0 |  | 0
C | Conference Technologies Inc. (P) |  | 0 | 0 | 0 |  | 0
| System Works LLC (P) |  | 11110 | 11110 | 0 |  | 12950
C | Control Installations of Iowa Inc. |  | 0 | 0 | 0 |  | 0
C | Waldinger Corporation |  | 0 | 0 | 0 |  | 0
| Central Iowa Mechanical (P) |  | 1587007.76 | 1587007.76 | 0 |  | 181117.24
C | Clark Glass (P) |  | 4801.39 | 4801.39 | 0 |  | 0
| MWE Services (P) |  | 517370.95 | 517370.95 | 0 |  | 27230.05
| Tri-City Electric (P) |  | 2294306.79 | 2294306.79 | 0 |  | 121432.28
C | Waldinger Corporation (2) |  | 0 | 0 | 0 |  | 0
| DCI Group 22-037 CA (P) |  | 682120.77 | 682120.77 | 0 |  | 43156.27
| Ball Team (P) |  | 1654724.03 | 1654724.03 | 0 |  | 159125.36
| Elite Fire Sprinkler Systems (P) |  | 70513.27 | 70513.27 | 0 |  | 13051.43
| Ideal Floors (P) |  | 79284.23 | 79284.23 | 0 |  | 4172.84
| All Makes-Furniture (P) |  | 2281545.83 | 2281545.83 | 0 |  | 166612.49
| Comiskey Glass (P) |  | 109990.08 | 109990.08 | 0 |  | 27511.46
| Total Project Cost | 10432829.63 | 10432829.63 | 10432829.63 | 0 | 0 | 803952.02

## #9186.02 Funds Rec'd
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | SLFRF | IET 401BD138001 051923 | 2023-05-19 | 200000 | 200000
|  |  | SLFRF | IET 401BD159003 060823 | 2023-06-08 | 200000 | 200000
|  |  | SLFRF | IET 401BD200002 071923 | 2023-07-19 | 115846.19 | 115846.19
|  |  | SLFRF | IET 401BD200003 071923 | 2023-07-19 | 184153.81 | 184153.81
|  |  | SLFRF | IET 401BD279001 100623 | 2023-10-06 | 200000 | 200000
|  |  | SLFRF | IET 401BD340003 120623 | 2023-12-07 | 850000 | 850000
|  |  | SLFRF | IET 401BD355001 122123 | 2023-12-21 | 800000 | 800000
|  |  | SLFRF | IET 401BD356001 122223 | 2023-12-22 | 100000 | 100000
|  |  | SLFRF | IET 401BD060003 022924 | 2024-02-29 | 900000 | 900000
|  |  | CDR to move Revenue 9186.02 to 9186.06 | CDR 33524082811 | 2024-03-22 | -775000 | -775000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33524087803 | 2024-03-27 | -50000 | -50000
|  |  | SLFRF | IET 401BD107002 041624 | 2024-04-16 | 900000 | 900000
|  |  | CDR to move Revenue 9186.02 to 9186.07 | CDR 33524170801 | 2024-06-18 | -15000 | -15000
|  |  | SLFRF | IET 401ML173001 062124 | 2024-06-24 | 5785500 | 5785500
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525249908 | 2024-09-05 | -50000 | -50000
|  |  | SLRF Recv'd in Program 918602 | IET 400RJ312001 110824 | 2024-11-12 | 500000 | 500000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525317900 | 2024-11-12 | -5000 | -5000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525340907 | 2024-12-05 | -115000 | -115000
|  |  | SLFRF | IET 400ML355001 122024 | 2024-12-20 | 1000000 | 1000000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525365900 | 2024-12-30 | -25000 | -25000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525003909 | 2025-01-03 | -100000 | -100000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525013908 | 2025-01-13 | -100000 | -100000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525041900 | 2025-02-10 | -100000 | -100000
|  |  | SLFRF Program 918602 | IET 400NJS059001 022825 | 2025-03-04 | 800000 | 800000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525062900 | 2025-03-04 | -800000 | -800000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525181910 | 2025-06-30 | 32329.63 | 32329.63
| Total Requested | 0 | Total Transferred |  |  | 10432829.63 | 10432829.63
`

## #9186.02 DCI Group
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523068801 | 2023-03-09 | Paper Contract Procore | 89223.96 | 89223.96 |  |  | 89223.96
GAX 33523142802 | 2023-05-22 | Inv. 23-007-01 |  | 89223.96 | 11848.82 | 11848.82 | 77375.14
GAX 33523179801 | 2023-06-28 | Inv. 23-007 PC-02 |  | 89223.96 | 23746.43 | 35595.25 | 53628.71
GAX 33523201801 | 2023-07-20 | Inv. 23-007 PC-03 |  | 89223.96 | 12250.94 | 47846.19 | 41377.77
GAX 33524283801 | 2023-10-10 | Inv. 23-007 PC-04 |  | 89223.96 | 23612.75 | 71458.94 | 17765.02
GAX 33524342806 | 2023-12-08 | Inv. 23-007 PC-05 FINAL | -808.22 | 88415.74 | 16956.8 | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  |  |  | 88415.74 |  | 88415.74 | 1.2051e-11
|  | Totals: | 88415.74 |  | 88415.74 |  | 0 | FINAL
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project. Program code will be SLFRF.
Procore created contract: | 801 CMPC-9186.01-002
CM Staff Hours | 89223.96
FINAL - total expended | 88415.74

## #9186.02 PM TIME (HHS)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
PM TIME (HHS) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E25U
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9186.02 PM TIME (DA)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
PM TIME (DA) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26O
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9186.02 SP TIME (HHS)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
SP TIME (HHS) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26P
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 22752.5 | 22752.5 |  |  | 22752.5
IET DAS202312115300001 | 2023-07-07 | 2507 | Space Planning Service |  | 22752.5 | 7481.25 | 7481.25 | 15271.25
IET DAS202401115300001 | 2023-08-07 | 2507 | Space Planning Service |  | 22752.5 | 2826.25 | 10307.5 | 12445
IET DAS202402115300001 | 2023-09-07 | 2507 | Space Planning Service |  | 22752.5 | 3515 | 13822.5 | 8930
IET DAS202403115300001 | 2023-10-08 | 2507 | Space Planning Service |  | 22752.5 | 2303.75 | 16126.25 | 6626.25
IET DAS202404115300001 | 2023-11-08 | 2507 | Space Planning Service |  | 22752.5 | 736.25 | 16862.5 | 5890
IET DAS202405115300001 | 2023-12-07 | 2507 | Space Planning Service |  | 22752.5 | 1116.25 | 17978.75 | 4773.75
IET DAS202406115300001 | 2024-01-08 | 2507 | Space Planning Service |  | 22752.5 | 688.75 | 18667.5 | 4085
IET DAS202407115300001 | 2024-02-07 | 2507 | Space Planning Service |  | 22752.5 | 142.5 | 18810 | 3942.5
IET DAS202408115300001 | 2024-03-05 | 2507 | Space Planning Service |  | 22752.5 | 403.75 | 19213.75 | 3538.75
IET DAS202410115300001 | 2024-05-07 | 2507 | Space Planning Service |  | 22752.5 | 285 | 19498.75 | 3253.75
IET DAS202412115300001 | 2024-07-10 | 2507 | Space Planning Service |  | 22752.5 | 166.25 | 19665 | 3087.5
IET DAS202502115300001 | 2024-09-09 | 2507 | Space Planning Service |  | 22752.5 | 3087.5 | 22752.5 | 0
[5 empty] | 22752.5 |  | 22752.5 | 0
[5 empty] | 22752.5 |  | 22752.5 | 0
[5 empty] | 22752.5 |  | 22752.5 | 0
[5 empty] | 22752.5 |  | 22752.5 | 0
|  |  | Totals: | 22752.5 |  | 22752.5 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie Jul 13, 2023, 4:26 PM (15 hours ago) to me Please see directions below. Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov On Thu, Jul 13, 2023 at 1:09 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Just following up this Have you had a chance to review? Thanks John On Wed, Jul 12, 2023 at 9:50 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Could you please review the following projects that would be over budget if we post PM time 9186.01 DA22 E26L amount to post 43.06+21.72+41.50+106.70+436.70=649.68 - For PM Time (DA) please allocate $50,000 to the contracted line. 9186.02 DA22 SLFRF HHS SP Time amount to post 7481.25 - For SP Time (HHS) please allocate $10,000 to the contracted line. 9186.02 DA22 SLFRF DA SP Time 16862.50 - For SP Time (DA) please allocate $20,000 to the contracted line. 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (41 minutes ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000

## #9186.02 SP TIME (DA)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
SP TIME (DA) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E26Q
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
IET DAS202312115300001 | 2023-07-07 | 2507 | Space Planning Service |  | 0 | 16862.5 | 16862.5 | -16862.5
IET DAS202401115300001 | 2023-08-07 | 2507 | Space Planning Service |  | 0 | 4702.69 | 21565.19 | -21565.19
IET DAS202402115300001 | 2023-09-07 | 2507 | Space Planning Service |  | 0 | 3942.5 | 25507.69 | -25507.69
IET DAS202403115300001 | 2023-10-08 | 2507 | Space Planning Service |  | 0 | 4417.5 | 29925.19 | -29925.19
IET DAS202404115300001 | 2023-11-08 | 2507 | Space Planning Service |  | 0 | 2303.75 | 32228.94 | -32228.94
IET DAS202405115300001 | 2023-12-07 | 2507 | Space Planning Service |  | 0 | 2636.25 | 34865.19 | -34865.19
IET DAS202406115300001 | 2024-01-08 | 2507 | Space Planning Service |  | 0 | 1448.75 | 36313.94 | -36313.94
IET DAS202407115300001 | 2024-02-07 | 2507 | Space Planning Service |  | 0 | 23.75 | 36337.69 | -36337.69
IET DAS202408115300001 | 2024-03-05 | 2507 | Space Planning Service |  | 0 | 3657.5 | 39995.19 | -39995.19
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -16862.5 | 23132.69 | -23132.69
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -4702.69 | 18430 | -18430
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -3942.5 | 14487.5 | -14487.5
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -4417.5 | 10070 | -10070
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -2303.75 | 7766.25 | -7766.25
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -2636.25 | 5130 | -5130
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -1448.75 | 3681.25 | -3681.25
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -23.75 | 3657.5 | -3657.5
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 0 | -3657.5 | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie Jul 13, 2023, 4:26 PM (15 hours ago) to me Please see directions below. Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov On Thu, Jul 13, 2023 at 1:09 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Just following up this Have you had a chance to review? Thanks John On Wed, Jul 12, 2023 at 9:50 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Could you please review the following projects that would be over budget if we post PM time 9186.01 DA22 E26L amount to post 43.06+21.72+41.50+106.70+436.70=649.68 - For PM Time (DA) please allocate $50,000 to the contracted line. 9186.02 DA22 SLFRF HHS SP Time amount to post 7481.25 - For SP Time (HHS) please allocate $10,000 to the contracted line. 9186.02 DA22 SLFRF DA SP Time 16862.50 - For SP Time (DA) please allocate $20,000 to the contracted line.

## #9186.02 PM Time (Ground FLoor)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
PM Time (Ground Floor) |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 909P
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 25190.41 | 25190.41 |  |  | 25190.41
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 25190.41 | 9.74 | 9.74 | 25180.67
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 25190.41 | 87.9 | 97.64 | 25092.77
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 25190.41 | 51.82 | 149.46 | 25040.95
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 25190.41 | 565.9 | 715.36 | 24475.05
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 25190.41 | 182.25 | 897.61 | 24292.8
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 25190.41 | 929.4 | 1827.01 | 23363.4
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 25190.41 | 57.34 | 1884.35 | 23306.06
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 25190.41 | 510.4 | 2394.75 | 22795.66
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 25190.41 | 126.76 | 2521.51 | 22668.9
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 25190.41 | 846 | 3367.51 | 21822.9
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 25190.41 | 209.13 | 3576.64 | 21613.77
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 25190.41 | 1387.7 | 4964.34 | 20226.07
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 25190.41 | 253.98 | 5218.32 | 19972.09
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 25190.41 | 2534.4 | 7752.72 | 17437.69
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 25190.41 | 406.26 | 8158.98 | 17031.43
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 25190.41 | 4334.3 | 12493.28 | 12697.13
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 25190.41 | 578.13 | 13071.41 | 12119
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 25190.41 | 2500.5 | 15571.91 | 9618.5
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 25190.41 | 416.84 | 15988.75 | 9201.66
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 25190.41 | 2984.6 | 18973.35 | 6217.06
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 25190.41 | 407.48 | 19380.83 | 5809.58
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 25190.41 | 2799.1 | 22179.93 | 3010.48
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 25190.41 | 341.08 | 22521.01 | 2669.4
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 25190.41 | 2669.4 | 25190.41 | 0
[5 empty] | 25190.41 |  | 25190.41 | 0
[5 empty] | 25190.41 |  | 25190.41 | 0
[5 empty] | 25190.41 |  | 25190.41 | 0
|  |  | Totals: | 25190.41 |  | 25190.41 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie Jul 13, 2023, 4:26 PM (15 hours ago) to me Please see directions below. Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov On Thu, Jul 13, 2023 at 1:09 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Just following up this Have you had a chance to review? Thanks John On Wed, Jul 12, 2023 at 9:50 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie Could you please review the following projects that would be over budget if we post PM time 9186.01 DA22 E26L amount to post 43.06+21.72+41.50+106.70+436.70=649.68 - For PM Time (DA) please allocate $50,000 to the contracted line. 9186.02 DA22 SLFRF HHS SP Time amount to post 7481.25 - For SP Time (HHS) please allocate $10,000 to the contracted line. 9186.02 DA22 SLFRF DA SP Time 16862.50 - For SP Time (DA) please allocate $20,000 to the contracted line. 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (41 minutes ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000 Re: PM Time Posted 9186.02 DA22 $Joni Elliott, Jennie 1:03 PM (18 minutes ago) to me Please increase PM Time (Ground Floor) to a total "Contracted" value of $40,000 Thank you, Jennie Elliott

## #9186.02 Misc
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202402115300001 | 2023-09-07 | 2323 |  | Leasing Services August 01-31, 2023 | DAS2024021153 | 142.5 | 142.5
IET 33524310808 | 2023-11-06 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356931 | 603 | 745.5
GAX 33524341800 | 2023-12-07 | 9500 | CNST | T&M Services Inc V#(00003096009) | Inv. #DM2313769 | 157 | 902.5
IET DAS202406115300001 | 2024-01-08 | 2323 |  | Leasing Services December 01-31, 2023 | DAS2024061153 | 237.5 | 1140
GAX 33524024800 | 2024-01-24 | 9500 | CNST | Conference Technologies V#(00003055217) | Inv. ST231000626 | 400 | 1540
IET DAS202407115300001 | 2024-02-07 | 2323 |  | Leasing Services January 01-31,2024 | DAS2024071153 | 23.75 | 1563.75
GAX 33524080810 | 2024-03-20 | 9500 | CNST | Lint Van Lines V#(00002108977) | Inv. 16177 | 1224 | 2787.75
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services February 01-29, 2024 | DAS2024021153 | -142.5 | 2645.25
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356931 | -603 | 2042.25
CDE 33524082815 | 2024-03-22 | 9500 | CNST | T&M Services Inc V#(00003096009) | Inv. #DM2313769 | -157 | 1885.25
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services February 01-29, 2024 | DAS2024061153 | -237.5 | 1647.75
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Conference Technologies V#(00003055217) | Inv. ST231000626 | -400 | 1247.75
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services February 01-29, 2024 | DAS2024071153 | -23.75 | 1224
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Lint Van Lines V#(00002108977) | Inv. 16177 | -1224 | 0
IET DAS202410115300001 | 2024-05-07 | 2323 |  | Leasing Services April 01-30, 2024 | DAS2024101153 | 427.5 | 427.5
IET DAS202411115300001 | 2024-06-10 | 2323 |  | Leasing Services May 01-31, 2024 | DAS2024111153 | 47.5 | 475
IET DAS202412115300001 | 2024-07-10 | 2323 |  | Leasing Services June 01-30, 2024 | DAS2024121153 | 190 | 665
IET DAS202501115300001 | 2024-08-07 | 2323 | CNST | Leasing Services July 01-31,2024 | DAS2025011153 | 261.25 | 926.25
GAX 33525257912 | 2024-09-13 | 9500 | CNST | Merchants Bonding V#( 003092511) | Inv. 9186.02-01 | 252.71 | 1178.96
IET DAS202502115300001 | 2024-09-09 | 2323 |  | Leasing Services August 01-31, 2024 | DAS2025021153 | 190 | 1368.96
IET 33525282902 | 2024-10-07 | 9210 | CNST | ICN Bill - August | Inv. 705629 | 985.27 | 2354.23
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Space Planning September 01-30, 2024 | DAS2025031153 | 1163.75 | 3517.98
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning Ocotober 01-31, 2024 | DAS2025041153 | 6460 | 9977.98
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Services December 01-31,2024 | Inv. DAS2025061153 | 3206.25 | 13184.23
IET 33525038901 | 2025-02-07 | 9210 | CNST | ICN Bill - January | Inv. 715274-013 | 2964.89 | 16149.12
GAX 33525048906 | 2025-02-17 | 9500 | CNST | ServiceMaster V#(00002111536) | Inv. DSM-00014-WTR | 7800.32 | 23949.44
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Space Planning Services Febraury 01-28, 2025 | DAS2025081153 | 190 | 24139.44
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Services March 01-31, 2025 | DAS2025091153 | 2992.5 | 27131.94
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Space Planning Services April 01-30, 2025 | DAS2025101153 | 902.5 | 28034.44
GAX 33525140900 | 2025-05-20 | 9500 | CNST | Opex Corp V#(00002094981) | Inv. 10035504 | 3374.64 | 31409.08
PRC 33525140904 | 2025-05-20 | 9500 | CNST | Control Installations V#(00002115535) | Inv. 163591 | 2302.9 | 33711.98
PRCI 33525140905 | 2025-05-20 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357189 | 1197 | 34908.98
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Space Plannig May 01-31, 2025 | DAS2025111153 | 427.5 | 35336.48
35336.48
35336.48
35336.48
|  |  |  | Totals: |  | 35336.48

## #9186.02 Shive Hattery
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Shive Hattery (2) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP1820335153
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523068802 | 2023-03-09 | Paper Contract Procore | 968359.4 | 968359.4 |  |  | 968359.4
GAX 33523142803 | 2023-05-22 | Inv. 4203302-1 |  | 968359.4 | 113000 | 113000 | 855359.4
GAX 33523152803 | 2023-06-01 | Inv. 4203302-2 |  | 968359.4 | 172000 | 285000 | 683359.4
GAX 33523201800 | 2023-07-20 | Inv. 4203302-3 |  | 968359.4 | 153000 | 438000 | 530359.4
GAX 33524236805 | 2023-08-24 | Inv. 4203302-4 |  | 968359.4 | 88000 | 526000 | 442359.4
GAX 33524250800 | 2023-09-07 | Inv. 4203302-5 |  | 968359.4 | 22000 | 548000 | 420359.4
GAX 33524283802 | 2023-10-10 | Inv. 4203302-6 (Split between 9186.02 and 9186.06) |  | 968359.4 | 24500 | 572500 | 395859.4
GAX 33524342802 | 2023-12-08 | Inv. 4203302-7 |  | 968359.4 | 11852 | 584352 | 384007.4
GAX 33524003802 | 2024-01-03 | Inv. 4203302-8 |  | 968359.4 | 9288 | 593640 | 374719.4
GAX 33524003803 | 2024-01-03 | Inv. 4203302-9 |  | 968359.4 | 3612 | 597252 | 371107.4
GAX 33524052801 | 2024-02-21 | Inv. 4203302-10 |  | 968359.4 | 12166.4 | 609418.4 | 358941
GAX 33524113800 | 2024-04-22 | Inv. 4203302-11 |  | 968359.4 | 44747.4 | 654165.8 | 314193.6
GAX 33524120802 | 2024-04-29 | Inv. 4203302-12 |  | 968359.4 | 9684.7 | 663850.5 | 304508.9
GAX 33524157807 | 2024-06-05 | Inv. 4203302-13 |  | 968359.4 | 6450 | 670300.5 | 298058.9
GAX 33524184905 | 2024-07-02 | Inv. 4203302-14 |  | 968359.4 | 48922.9 | 719223.4 | 249136
GAX 33524194903 | 2024-07-12 | Inv. 4203302-15 |  | 968359.4 | 5160 | 724383.4 | 243976 | FY24
PO 33525068802 | 2024-08-16 | Roll to FY25 | 0 | 968359.4 |  | 724383.4 | 243976
GAX 33525249905 | 2024-09-05 | Inv. 4203302-16 |  | 968359.4 | 11610 | 735993.4 | 232366
GAX 33525271905 | 2024-09-27 | Inv. 4203302-17 |  | 968359.4 | 70075 | 806068.4 | 162291
GAX 33525309902 | 2024-11-04 | Inv. 4203302-18 |  | 968359.4 | 48188 | 854256.4 | 114103
GAX 33525341908 | 2024-12-06 | Inv. 4203302-19 |  | 968359.4 | 29212 | 883468.4 | 84891
GAX 33525013907 | 2025-01-13 | Inv. 4203302-20 |  | 968359.4 | 19925 | 903393.4 | 64966
GAX 33525035912 | 2025-02-04 | Inv. 4203302-21 |  | 968359.4 | 12962 | 916355.4 | 52004
GAX 33525058900 | 2025-02-27 | Inv. 4203302-22 |  | 968359.4 | 33809.2 | 950164.6 | 18194.8
GAX 33525090911 | 2025-03-31 | Inv. 4203302-23 |  | 968359.4 | 10302.4 | 960467 | 7892.4
GAX 33525125904 | 2025-05-05 | Inv. 4203302-24 |  | 968359.4 | 7892.4 | 968359.4 | 0
|  |  |  | 968359.4 |  | 968359.4 | 0
|  |  |  | 968359.4 |  | 968359.4 | 0
|  | Totals: | 968359.4 |  | 968359.4 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project. Program code will be SLFRF.
Procore created contract: | 80 CMPC-9186.01-002
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Schematic Design | 113000 |  | 113000 |  | 0
|  | Design Development | 215000 |  | 215000 |  | 0
|  | Construction Documents | 220000 |  | 220000 |  | 0
|  | Bidding Assistance | 21000 |  | 21000 |  | 0
|  | CO 1 | 7000 |  | 7000 |  | 0
|  | CO 2 (Voided in Procore) | 0 |  |  |  | 0
|  | CO 3 | 0 |  |  |  | 0
|  | CO 4 | 140852 |  | 140852 |  | 0
|  | CO 5 | 11852 |  | 5716.4 |  | 6135.6
|  | CO 6 | 25000 |  | 25000 |  | 0
|  | CO 7 | -7080 |  | -7080 |  | 0
|  | CO 8 | 5700 |  | 5700 |  | 0
|  | CO 9 | 8000 |  | 8000 |  | 0
|  | CO 10 | 172848 |  | 172848 |  | 0
|  | CO 11 - 10/08/2024 | 7080 |  | 7080 |  | 0
|  | CO 12 - 11/12/2024 | 22000 |  | 17543 |  | 4457
|  | CO 13 - 01/28/2025 | 28900 |  | 16700 |  | 12200
|  | CO 14 - 06/05/2025 | 24800 |  |  |  | 24800
|  | Total: 9186.02 | 1015952 |  | 968359.4 |  | 47592.6
|  | 9186.06 DA22 (Closed) | 7080 |  | 7080 |  | 0
|  | Total Contract: | 1023032 |  | 975439.4 |  | 47592.6

## #9186.02 Heartland Finishes
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Heartland Finishes |  |  | Vendor: 00002097604
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21421B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222801 | 2023-08-10 | DO I/3 | 28673 | 28673 |  |  | 28673
PRC 3352422PA2801 | 2023-10-11 | Inv. 16150 |  | 28673 | 28673 | 28673 | 0
CDE 33524307808 | 2023-11-03 | Correct Program Code on pay app |  | 28673 | 0 | 28673 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -28673 | 0 | -28673 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0 | FINAL
|  | Labor | 25725 |  | 25725 |  | 0
|  | Material | 2948 |  | 2948 |  | 0
|  | Total | 28673 |  | 28673 |  | 0

## #9186.02 Ralph Smith
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Ralph Smith |  |  | Vendor: 00002106937
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21267
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222802A | 2023-11-06 | DO I/3 | 83372 | 83372 |  |  | 83372
PRC 3352422PA2802A | 2023-11-06 | Inv. 30044 |  | 83372 | 83372 | 83372 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -83372 | 0 | -83372 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0 | FINAL
|  | Labor | 34224 |  | 34224 |  | 0
|  | Material | 49148 |  | 49148 |  | 0
|  | Total | 83372 |  | 83372 |  | 0

## #9186.02 Shyft Collective
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Shyft Collective |  |  | Vendor Code: VS000000587
Acct. Codes-0506-335-DA22-9255 |  |  | MA#23200
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222803A | 2023-08-10 | DO I/3 | 81740 | 81740 |  |  | 81740
PRC 3352422PA2803A | 2023-12-07 | Inv. 0001REV |  | 81740 | 81740 | 81740 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -81740 | 0 | -81740 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Wall and Ceiling repair and replace 85.00/hr | 7225 |  | 7225 |  | 0
|  | Material Handling Equipment Maintenance and Repair | 69730 |  | 69730 |  | 0
|  | CO #1 | 4785 |  | 4785 |  | 0
|  | Total | 81740 |  | 81740 |  | 0

## #9186.02 All Makes
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
All Makes |  |  | Vendor Code: 00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA#23148
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222804A | 2023-08-10 | DO I/3 | 465280.24 | 465280.24 |  |  | 465280.24
PRC 3352422PA2804A | 2024-02-02 | Inv. 311116 |  | 465280.24 | 465280.24 | 465280.24 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -465280.24 | 0 | -465280.24 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Furniture Office | 465280.24 |  | 465280.24 |  | 0
|  | Total | 465280.24 |  | 465280.24 |  | 0

## #9186.02 Conference Tech
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Conference Technologies Inc. |  |  | Vendor Code: 00002133110
Acct. Codes-0506-335-DA22-9255 |  |  | MA #22036B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524241801A | 2023-08-29 | DO I/3 | 4823.66 | 4823.66 |  |  | 4823.66
DO 33524241801A | 2023-10-03 | CO #1 | 1292.32 | 6115.98 |  | 0 | 6115.98
PRC 3352424PA1801A | 2024-01-09 | Inv. JC134320 |  | 6115.98 | 6115.98 | 6115.98 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -6115.98 | 0 | -6115.98 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Video and Audio Systems | 4823.66 |  | 4823.66 |  | 0
|  | CO #1 | 1292.32 |  | 1292.32 |  | 0
|  | Total | 6115.98 |  | 4823.66 |  | 0

## #9186.02 System Works LLC
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
System Works LLC |  |  | Vendor Code: 00002144353
Acct. Codes-0506-335-DA22-9260 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524250801 | 2023-09-07 | Paper Contract Procore | 11110 | 11110 |  |  | 11110
GAX 33524113801 | 2024-04-23 | Inv. 11686 |  | 11110 | 8070 | 8070 | 3040
GAX 33524199903 | 2024-07-17 | Inv. 11871 |  | 11110 | 3040 | 11110 | 0 | FY24
PO 33525250801 | 2024-08-16 | Roll to FY25 | 0 | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  |  |  | 11110 |  | 11110 | 0
|  | Totals: | 11110 |  | 11110 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project. Program code will be SLFRF.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Lucas Building Commissioning | 19845 |  | 10260 |  | 9585
|  | Sofware | 1275 |  | 850 |  | 425
|  | CO #1 01/06/25 | 2940 |  |  |  | 2940
|  | Total Contract: 9186.02 | 24060 |  | 11110 |  | 12950

## #9186.02 Control Installations
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Control Installations of Iowa Basepoint |  |  | Vendor Code: 00002115535
Acct. Codes-0506-335-DA22-9255 |  |  | MA#20360A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524258800A | 2023-09-15 | DO I-3 | 23576 | 23576 |  |  | 23576
DO 33524258800A | 2024-02-15 | CO #1 | 0 | 23576 |  | 0 | 23576
PRC 3352425PA8800A | 2024-02-15 | Inv. 144266 | -4277.5 | 19298.5 | 19298.5 | 19298.5 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -19298.5 | 0 | -19298.5 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0 | FINAL
|  | Building Automation Products | 8467.1 |  | 8467.1 |  | 0
|  | Building Automation Services | 10831.4 |  | 10831.4 |  | 0
|  | Total | 19298.5 |  | 19298.5 |  | 0

## #9186.02 Waldinger
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Waldinger |  |  | Vendor Code: 00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21012A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524283803A | 2023-10-10 | DO I-3 | 27723 | 27723 |  |  | 27723
PRC 3352428PA3803A | 2024-03-06 | Inv. 7142120-1 | -10835.11 | 16887.89 | 16887.89 | 16887.89 | 0
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -16887.89 | 0 | -16887.89 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0 | FINAL
|  | Labor | 15554.43 |  | 15554.43 |  | 0
|  | Materials | 1333.46 |  | 1333.46 |  | 0
|  | Total | 16887.89 |  | 16887.89 |  | 0

## #9186.02 Central Iowa Mech.
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Central Iowa Mechanical |  |  | Vendor Code: 00002109717
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524297801 | 2023-10-24 | PO Procore | 1587007.76 | 1587007.76 |  |  | 1587007.76
GAX 33524342804 | 2023-12-08 | Inv. 2391310-1 |  | 0 | 55442 | 55442 | 1531565.76 | 2918
GAX 33524019800 | 2024-01-19 | Inv. 2391310-2 |  | 0 | 167822.25 | 223264.25 | 1363743.51 | 11750.75
GAX 33524079808 | 2024-03-19 | Inv. 2391310-3 |  | 0 | 78018.75 | 301283 | 1285724.76 | 15857
GAX 33524094928 | 2024-04-03 | Inv. 2391310-4 |  | 0 | 224482.5 | 525765.5 | 1061242.26 | 28724.5
GAX 33524094928A | 2024-04-04 | Inv. 2391310-4A (Amount Correction) |  | 0 | 20000 | 545765.5 | 1041242.26
GAX 33524198902 | 2024-07-15 | Inv. 9186.02-05 |  | 0 | 495161.85 | 1040927.35 | 546080.41 | 54785.65 | FY24
PO 33525297801 | 2024-08-16 | Roll to FY25 | 0 | 0 |  | 1040927.35 | 546080.41
GAX 33525250903 | 2024-09-06 | Inv. 2391310-6(100% to 918602) |  | 0 | 379686.49 | 1420613.84 | 166393.92 | 74769.16
GAX 33525304902 | 2024-10-30 | Inv. 2391310-7(100% to 918601) |  | 0 | 0 | 1420613.84 | 166393.92
GAX 33525080906 | 2025-03-21 | Inv. 2391310-8(Split w/918601) |  | 0 | 90519.8 | 1511133.64 | 75874.12 | 79533.36
GAX 33525155901 | 2025-06-04 | Inv. 2391310-9(Split w/918602) |  | 0 | 75874.12 | 1587007.76 | 0 | 83526.73
|  |  |  | 0 |  | 1587007.76 | 0
|  | Totals: | 1587007.76 |  | 1587007.76 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Base Bid | 1957620 |  | 1469317.96 |  | 488302.04
|  | CO #1 01/24/24 | 3019 |  | 2868.05 |  | 150.95
|  | CO #2 02/12/24 | 12461 |  | 11837.95 |  | 623.05
|  | CO #3 02/26/24 | 10682 |  | 10173.55 |  | 508.45
|  | CO #4 03/20/24 | -749 |  | -711.55 |  | -37.45
|  | Split Funding 9186.01 06/17/24 | -400000 |  | 0 |  | -400000
|  | CO #5 07/11/24 100% to 918602 | 1721 |  | 1634.95 |  | 86.05
|  | CO #6 09/04/24 100% to 918602 | 24619 |  | 23388.05 |  | 1230.95
|  | CO #7 09/17/24 100% to 918602 | 52024 |  | 49422.8 |  | 2601.2
|  | CO #8 10/22/24 100% to 918602 | 29624 |  | 19076 |  | 10548
|  | CO #9 11/22/24 100% to 918601 | 0 |  | 0 |  | 0
|  | CO #10 02/25/25 100% to 918602 | 17586 |  | 0 |  | 17586
|  | CO #11 03/04/25 100% to 918602 | 26570 |  | 0 |  | 26570
|  | CO #12 05/07/25 100% to 918602 | 28207 |  | 0 |  | 28207
|  | CO #13 06/24/25 100% to 918602 | 4741 |  |  |  | 4741
|  | Total 9186.02: | 1768125 |  | 1587007.76 |  | 181117.24
|  | 9186.01 06/17/24 HHS Funds | 582896 |  | 379822.13 |  | 203073.87
|  | Total Contract 9186.01 and 9186.02: | 2351021 |  | 1966829.89 |  | 384191.11

## #9186.02 Clark Glass
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Clark Glass |  |  | Vendor Code: 00002109698
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299807 | 2023-10-26 | PO Procore | 4801.39 | 4801.39 |  |  | 4801.39
GAX 33524354803 | 2023-12-20 | Inv. 9186.02-01 |  | 4801.39 | 4801.39 | 4801.39 | 0 | 252.71 | Retainage balance transferred to 9186.02 Cominskey Glass
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  |  |  | 4801.39 |  | 4801.39 | 0
|  | Totals: | 4801.39 |  | 4801.39 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  | Base Bid | 4801.39 |  | 4801.39 |  | 0
|  | CO #001 02/02/24 | 0 |  |  |  | 0
|  | Total | 4801.39 |  | 4801.39 |  | 0
PO closed at the request of the project mananager. 05/24/24
Company out of business.
Retainage will go to Bonding company "Comiskey Glass" per Tender Agreement.

## #9186.02 MWE Services
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
MWE Services |  |  | Vendor Code: 00003212732
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299810 | 2023-10-26 | PO Procore | 517370.95 | 517370.95 |  |  | 517370.95
GAX 33524361800 | 2023-12-27 | Inv. 9186.02-001 |  | 517370.95 | 233286.75 | 233286.75 | 284084.2 | 12278.25
GAX 33524078800 | 2024-03-18 | Inv. 9186.02-002 |  | 517370.95 | 143450 | 376736.75 | 140634.2 | 19828.25
GAX 33524094803 | 2024-04-03 | Inv. 9186.02-003 |  | 517370.95 | 14765.85 | 391502.6 | 125868.35 | 20605.4
GAX 33524138907 | 2024-05-17 | Inv. 9186.02-004 |  | 517370.95 | 727.7 | 392230.3 | 125140.65 | 20643.7 | FY24
PO 33525299810 | 2024-08-16 | Roll to FY25 | 0 | 517370.95 |  | 392230.3 | 125140.65
GAX 33525271904 | 2024-09-27 | Inv. 9186.02-005 |  | 517370.95 | 36638.65 | 428868.95 | 88502 | 22572.05
GAX 33525281901 | 2024-10-07 | Inv. 9186.02-006 |  | 517370.95 | 15580 | 444448.95 | 72922 | 23392.05
GAX 33525027900 | 2025-01-27 | Inv. 9186.02-007 |  | 517370.95 | 13634.4 | 458083.35 | 59287.6 | 24109.65
GAX 33525104900 | 2025-04-14 | Inv. 9186.02-008 |  | 517370.95 | 40466.2 | 498549.55 | 18821.4 | 26239.45
GAX 33525125402 | 2025-05-05 | Inv. 9186.02-009 |  | 517370.95 | 14133.15 | 512682.7 | 4688.25 | 26983.3
GAX 33525154913 | 2025-06-03 | Inv. 9186.02-010 |  | 517370.95 | 4688.25 | 517370.95 | 6.0027e-11 | 27230.05
|  |  |  | 517370.95 |  | 517370.95 | 6.0027e-11
|  |  |  | 517370.95 |  | 517370.95 | 6.0027e-11
|  |  |  | 517370.95 |  | 517370.95 | 6.0027e-11
|  | Totals: | 517370.95 |  | 517370.95 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  | Base Bid | 493500 |  | 469143.6 |  | 24356.4
|  | CO #1 01/23/24 | 1043 |  | 1043 |  | 0
|  | CO #2 03/05/24 | -2021 |  | -2021 |  | 0
|  | CO #3 04/19/24 | 2787 |  | 2787 |  | 0
|  | CO #4 06/13/24 | -8181 |  | -8181 |  | 0
|  | CO #5 09/04/24 | 0 |  | 0 |  | 0
|  | CO #6 10/22/24 | 1433 |  | 1361.35 |  | 71.65
|  | CO #7 12/31/24 | 41163 |  | 39104.85 |  | 2058.15
|  | CO #8 04/15/25 | 14877 |  | 14133.15 |  | 743.85
|  | CO #9 05/07/25 No Cost CO | 0 |  | 0 |  | 0
|  | Total | 544601 |  | 517370.95 |  | 27230.05

## #9186.02 Tri-City Electric
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Tri-City Electric |  |  | Vendor Code: 00002106567
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299809 | 2023-10-26 | PO Procore | 2429947.55 | 2429947.55 |  |  | 2429947.55
GAX 33524342803 | 2023-12-08 | Inv. 300839 |  | 2429947.55 | 166888.63 | 166888.63 | 2263058.92 | 8783.63
GAX 33524064900 | 2024-03-04 | Inv. 302407 |  | 2429947.55 | 126794.34 | 293682.97 | 2136264.58 | 15457.02
GAX 33524078801 | 2024-03-18 | Inv. 304656 |  | 2429947.55 | 413221.31 | 706904.28 | 1723043.27 | 37205.58
GAX 33524115914 | 2024-04-24 | Inv. 306273 |  | 2429947.55 | 507125.6 | 1214029.88 | 1215917.67 | 63896.44
GAX 33524127904 | 2024-05-06 | Inv. 308088 |  | 2429947.55 | 460965.93 | 1674995.81 | 754951.74 | 88157.88
CDE 33524127800 | 2024-05-06 | Correct Program Code Inv. 306273 |  | 2429947.55 | 0 | 1674995.81 | 754951.74
GAX 33524193924 | 2024-07-11 | Inv. 310862 |  | 2429947.55 | 93469.06 | 1768464.87 | 661482.68 | 93077.31
GAX 33524208917 | 2024-07-26 | Inv. 313794(100% to 918602) |  | 2429947.55 | 242478.39 | 2010943.26 | 419004.29 | 105839.36 | FY24
PO 33525299809 | 2024-08-16 | Roll to FY25 | 0 | 2429947.55 |  | 2010943.26 | 419004.29
GAX 33525249904 | 2024-09-05 | Inv. 315236(100% to 918602) |  | 2429947.55 | 142753.03 | 2153696.29 | 276251.26 | 113352.72
GAX 33525309901 | 2024-11-04 | Inv. 320785(100% to 9186.01) |  | 2429947.55 | 0 | 2153696.29 | 276251.26
GAX 33525326905 | 2024-11-21 | Inv. 320790(Split w/9186.01) |  | 2429947.55 | 164253.1 | 2317949.39 | 111998.16 | 121997.69
GAX 33525003908 | 2025-01-03 | Inv. 323025(Split w/9186.01) |  | 2429947.55 | 15835.64 | 2333785.03 | 96162.52 | 122831.14
GAX 33525035911 | 2025-02-24 | Inv. 324684(Split w/9186.01) |  | 2429947.55 | 502.51 | 2334287.54 | 95660.01 | 122857.59
GAX 33525065901 | 2025-03-06 | Inv. 326892(Split w/9186.01) |  | 2429947.55 | 14395.35 | 2348682.89 | 81264.66 | 123615.24
CDE 33525133911 | 2025-05-13 | Moving Expense to 9186.01 From 9186.02 | -135640.76 | 2294306.79 | -135640.76 | 2213042.13 | 81264.66 | 116476.25
GAX 33525139900 | 2025-05-19 | Inv. 328857(Split w/9186.01) |  | 2294306.79 | 5675.41 | 2218717.54 | 75589.25 | 116774.96
GAX 33525155900 | 2025-06-04 | Inv. 332294(Split w/9186.01) |  | 2294306.79 | 13969.33 | 2232686.87 | 61619.92 | 117510.19
CDE 33525177906 | 2025-06-26 | Moving Expense to 9186.01 From 9186.02 |  | 2294306.79 | 20942.47 | 2253629.34 | 40677.45 | 118416.37
GAX 33525178911 | 2025-06-27 | Inv. 334277 (Split w/9186.01) |  | 2294306.79 | 40677.45 | 2294306.79 | 3.4925e-10 | 120557.28
|  |  |  | 2294306.79 |  | 2294306.79 | 3.4925e-10
|  | Totals: | 2294306.79 |  | 2294306.79 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Base Bid | 2524821.61 |  | 2207387.45 |  | 317434.16
|  | CO #001 02/02/24 100% to 9186.02 | -4111.97 |  | -3906.37 |  | -205.6
|  | CO #002 02/12/24 100% to 9186.02 | -2996.77 |  | -2846.93 |  | -149.84
|  | CO #003 03/22/24 100% to 9186.02 | 1222.24 |  | 1161.13 |  | 61.11
|  | CO #004 04/05/24 100% to 9186.02 | 2555.04 |  | 2427.29 |  | 127.75
|  | CO #005 04/23/24 100% to 9186.02 | 604.03 |  | 573.83 |  | 30.2
|  | CO #006 05/28/24 100% to 9186.02 | 21944.86 |  | 20847.62 |  | 1097.24
|  | CO #007 06/14/24 100% to 9186.02 | 4811.87 |  | 4571.28 |  | 240.59
|  | Split Funding 9186.01 06/17/24 | -325000 |  | 0 |  | -325000
|  | CO #008 07/11/24 100% to 9186.02 | 6496.23 |  | 6171.42 |  | 324.81
|  | CO #009 09/04/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #010 10/04/24 100% to 9186.02 | 118340.76 |  | 112423.72 |  | 5917.04
|  | CO #011 10/24/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #012 12/12/24 100% to 9186.02 | 2305.96 |  | 2190.66 |  | 115.3
|  | CO #013 01/06/25 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #14 02/18/25 100% to 9186.02 | 9887.24 |  | 9392.89 |  | 494.35
|  | CO #15 04/29/25 100% to 9186.02 | 16352.93 |  | 15535.29 |  | 817.64
|  | CO #16 06/12/25 100% to 9186.02 | 34816.63 |  | 33075.8 |  | 1740.83
|  | Moved Expenses from 9186.02 to 9186.01 | -142779.75 |  | -135640.76 |  | -7138.99
|  | Moved Expenses from 9186.01 to 9186.02 | 21848.65 |  | 20942.47 |  | 906.18
|  | Split funding from 9186.01 | 124619.51 |  | 0 |  | 124619.51
|  | Total 9186.02: | 2415739.07 |  | 2294306.79 |  | 121432.28
|  | Split Funding 9186.01 06/17/24 | 687369.32 |  | 652814.56 |  | 34554.76
|  | Total Contract 9186.01 and 9186.02: | 3103108.39 |  | 2947121.35 |  | 155987.04

## #9186.02 Waldinger (2)
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Waldinger |  |  | Vendor Code: 00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | MA#20452A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524303803A | 2023-10-30 | DO I-3 | 3179 | 3179 |  |  | 3179
PRC 3352430PA3803A | 2024-02-26 | Inv. 75272E-001 |  | 3179 | 2278.89 | 2278.89 | 900.11
CDE 33524082817 | 2024-03-22 | Move Project to 9186.06 | -3179 | 0 | -2278.89 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0 | CLOSED AND MOVED TO 9186.06
|  | Labor | 1507.55 |  | 1507.55 |  | 0
|  | Materials | 771.34 |  | 771.34 |  | 0
|  | Total | 2278.89 |  | 2278.89 |  | 0

## #9186.02 DCI Group 22-037 CA
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
DCI Group 22-037 CA |  |  | Vendor Code: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524289801A | 2024-04-24 |  | 682120.77 | 682120.77 |  |  | 682120.77
GAX 33524184908 | 2024-07-02 | Inv. 23-007 CA 06(100% to 918602) |  | 682120.77 | 163813.03 | 163813.03 | 518307.74
GAX 33524213901 | 2024-07-31 | Inv. 23-007 CA-07(100% to 918602) |  | 682120.77 | 99692.3 | 263505.33 | 418615.44 | FY24
PO 33525289801A | 2024-08-16 | Roll to FY25 | 0 | 682120.77 |  | 263505.33 | 418615.44
PRC 3352528PH9801A | 2024-09-04 | Inv. 23-007 CA 08(100% to 918602) |  | 682120.77 | 66420.69 | 329926.02 | 352194.75
PRC 3352528PI9801A | 2024-11-24 | Inv. 23-007 CA 09(100% to 918602) |  | 682120.77 | 145611.5 | 475537.52 | 206583.25 |  | `
PRC 3352528PJ9801A | 2024-12-03 | Inv. 23-007 CA 10(100% to 918602) |  | 682120.77 | 54804.39 | 530341.91 | 151778.86
PRC 3352528PK9801A | 2024-12-30 | Inv. 23-007 CA 11(100% to 918602) |  | 682120.77 | 56114.74 | 586456.65 | 95664.12
PRC 3352528PL9801A | 2025-01-27 | Inv. 23-007 CA 12(100% to 918602) |  | 682120.77 | 43632.48 | 630089.13 | 52031.64
PRC 3352528PM9801A | 2025-02-17 | Inv. 23-007 CA 13(100% to 918602) |  | 682120.77 | 40836.29 | 670925.42 | 11195.35
PO 33525289801B | 2025-04-16 | Correcting PO Division of Funds |  | 682120.77 |  | 670925.42 | 11195.35
PRC 3352528PN9801B | 2025-04-16 | Inv. 23-007 CA 14(Split w/ 918602) |  | 682120.77 | 11195.35 | 682120.77 | 0
PRC 3352528PO9801B | 2025-04-25 | Inv. 23-007 CA 15(100% to 918601) |  | 682120.77 | 0 | 682120.77 | 0
PRC 3352528PP9801B | 2025-05-10 | Inv. 23-007 CA 16(100% to 918601) |  | 682120.77 | 0 | 682120.77 | 0
PRC 3352528PQ9801B | 2025-06-23 | Inv. 23-007 CA 17(100% to 918601) |  | 682120.77 | 0 | 682120.77 | 0
|  |  |  | 682120.77 |  | 682120.77 | 0
|  |  |  | 682120.77 |  | 682120.77 | 0
|  |  |  | 682120.77 |  | 682120.77 | 0
|  | Totals: | 682120.77 |  | 682120.77 |  | 0
PO number above is assigned to Procore PO, and created in IA Advantage as Unencumbered due to Paper Contract.
Will create payments as funds become available to charge against this project.
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | PO Amount | 587587.07 |  | 579841.02 |  | 7746.05
|  | CO #1 01/28/25 100% to 9186.02 | 137689.97 |  | 102279.75 |  | 35410.22
|  | CO #2 02/18/25 100% to 9186.01 | 0 |  | 0 |  | 0
|  | Total 9186.02: | 725277.04 |  | 682120.77 |  | 43156.27
|  | 9186.01 06/17/24 HHS Funds | 595825.2 |  | 565861.19 |  | 29964.01
|  | Total Contract 9186.01 and 9186.02: | 1321102.24 |  | 1247981.96 |  | 73120.28

## #9186.02 Ball Team
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Ball Team |  |  | Vendor Code: 00003090419
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299805 |  |  | 1654724.03 | 1654724.03 |  |  | 1654724.03 | 0
GAX 33524184906 | 2024-07-02 | Inv. 9186.02-06(100% to 918602) |  | 1654724.03 | 321472.42 | 321472.42 | 1333251.61 | 16919.6
CDE 33524192801 | 2024-07-10 | Move Expenses from 9186.01 to 9186.02 |  | 1654724.03 | 69537.15 | 391009.57 | 1263714.46 | 20579.45
CDE 33524192802 | 2024-07-10 | Move Expenses from 9186.01 to 9186.02 |  | 1654724.03 | 413005.85 | 804015.42 | 850708.61 | 42316.6
GAX 33525213903 | 2024-07-31 | Inv. 9186.02-07(Split with 9186.01) |  | 1654724.03 | 517573.05 | 1321588.47 | 333135.56 | 69557.29 | FY24
PO 33525299805 | 2024-08-16 | Roll to FY25 | 0 | 1654724.03 |  | 1321588.47 | 333135.56
GAX 33525248902 | 2024-09-04 | Inv. 9186.02-08(Split with 9186.01) |  | 1654724.03 | 176002.08 | 1497590.55 | 157133.48 | 78820.56
GAX 33525271906 | 2024-09-27 | Inv. 9186.02-09(100% to 9186.01) |  | 1654724.03 | 0 | 1497590.55 | 157133.48
GAX 33525309903 | 2024-10-04 | Inv. 9186.02-10(Split with 9186.01) |  | 1654724.03 | 28658.65 | 1526249.2 | 128474.83 | 80328.9
GAX 33525351906 | 2024-12-16 | Inv. 9186.02-11(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525027904 | 2025-01-27 | Inv. 9186.02-12(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525055902 | 2025-02-24 | Inv. 9186.02-13(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525090912 | 2025-03-31 | Inv. 9186.02-14(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525115910 | 2025-04-25 | Inv. 9186.01-15(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525135900 | 2025-05-15 | Inv. 9186.01-16(100% to 9186.01) |  | 1654724.03 | 0 | 1526249.2 | 128474.83
GAX 33525176901 | 2025-06-25 | Inv. 9186.01-17(Split W/9186.01) |  | 1654724.03 | 68366.75 | 1594615.95 | 60108.08 | 83927.15
CDE 33525177900 | 2025-06-26 | Move Expenses from 9186.01 to 9186.02 |  | 1654724.03 | 60108.08 | 1654724.03 | 2.4738e-10 | 86932.55
|  |  |  | 1654724.03 |  | 1654724.03 | 2.4738e-10
|  | Totals: | 1654724.03 |  | 1654724.03 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | 9186.01 06/17/24 HHS Funds | 1560861.73 |  | 1011632.6 |  | 549229.13
|  | CO #1 01/24/24 Split w/9186.01 | 3621 |  | 3414.95 |  | 206.05
|  | CO #2 02/09/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #3 02/26/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #4 04/11/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #5 04/24/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #6 04/24/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | Moved Expenses from 9186.01 to 9186.02 | 73197 |  | 69537.15 |  | 3659.85
|  | Moved Expenses from 9186.01 to 9186.02 | 434743 |  | 413005.85 |  | 21737.15
|  | CO #7 06/14/202 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #8 07/03/2024 100% to 9186.02 | 9632 |  | 9150.4 |  | 481.6
|  | CO #9 09/04/2024 100% to 9186.02 | 20535 |  | 19508.25 |  | 1026.75
|  | CO #10 10/02/2024 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #11 10/22/2024 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #12 11/22/2024 Split w/9186.01 | 12861 |  | 0 |  | 12861
|  | CO #13 01/06/2025 Split w/9186.02 | 12893 |  | 0 |  | 12893
|  | CO #14 04/10/2025 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #15 05/07/2025 100% to 9186.02 | 83598 |  | 68366.75 |  | 15231.25
|  | CO #16 06/25/2025 100% to 9186.02 | 9885 |  | 0 |  | 9885
|  | Moved Expenses from 9186.01 to 9186.02 | 63113.48 |  | 60108.08 |  | 3005.4
|  | Split Funding to 9186.02 06/17/24 | -471090.82 |  |  |  | -471090.82
|  | Total | 1813849.39 |  | 1654724.03 |  | 159125.36
|  | 9186.01 06/17/24 HHS Funds | 1513712.69 |  | 1437876.7 |  | 75835.99
|  | Total Contract 9186.01 and 9186.02: | 3327562.08 |  | 3092600.73 |  | 234961.35

## #9186.02 Elite Fire Sprinkler
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Elite Fire Sprinkler Systems |  |  | Vendor Code: 00003212887
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299808 |  |  | 70513.27 | 70513.27 |  |  | 70513.27 | 0
GAX 33524184907 | 2024-07-02 | Inv. 9186.02-Pay App 4(100% to 9186.01) |  | 70513.27 | 8855.9 | 8855.9 | 61657.37 | 466.1
GAX 33524213902 | 2024-07-31 | Inv. 9186.02-Pay App 4.1(100% to 9186.01) |  | 70513.27 | 45013.37 | 53869.27 | 16644 | 2835.23 | FY24
PO 33525299808 | 2024-08-16 | Roll to FY25 | 0 | 70513.27 |  | 53869.27 | 16644
PO 33525299808 | 2024-09-04 | CO#2 (No Cost CO) | 0 | 70513.27 |  | 53869.27 | 16644
GAX 33525271910 | 2024-09-27 | Inv. 9186.02-Pay App 5(100% to 9186.01) |  | 70513.27 | 11157.75 | 65027.02 | 5486.25 | 3422.48
GAX 33525326902 | 2024-11-21 | Inv. 9186.02-Pay App 6(Split W/ 9186.01) |  | 70513.27 | 2351.25 | 67378.27 | 3135 | 3546.23
GAX 33525036904 | 2025-02-05 | Inv. 9186.02-Pay App 7(Split W/ 9186.01) |  | 70513.27 | 783.75 | 68162.02 | 2351.25 | 3587.48
GAX 33525065903 | 2025-03-06 | Inv. 9186.02-Pay App 12(100% to 9186.02) |  | 70513.27 | 2351.25 | 70513.27 | 0 | 3711.23
GAX 33525175900 | 2025-06-24 | Inv. 9186.02-Pay App 13(100% to 9186.01) |  | 70513.27 | 0 | 70513.27 | 0
|  |  |  | 70513.27 |  | 70513.27 | 0
|  |  |  | 70513.27 |  | 70513.27 | 0
|  |  |  | 70513.27 |  | 70513.27 | 0
|  | Totals: | 70513.27 |  | 70513.27 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Split Funding 9186.02 06/17/24 | 83564.7 |  | 70513.27 |  | 13051.43
|  | Total 9186.02: | 83564.7 |  | 70513.27 |  | 13051.43
|  | 9186.01 06/17/24 HHS Funds | 158988.3 |  | 135678.52 |  | 23309.78
|  | CO #2 09/26/24 No Cost CO | 0 |  |  |  | 0
|  | CO #3 10/15/24 100% to 918601 | 0 |  |  |  | 0
|  | CO #4 11/22/24 100% to 918601 | 0 |  |  |  | 0
|  | CO #5 02/26/25 100% to 918601 | 0 |  |  |  | 0
|  | CO #6 04/15/25 100% to 918601 | 0 |  |  |  | 0
|  | CO #7 05/07/25 No Cost CO | 0 |  |  |  | 0
|  | Total Contract 9186.01 and 9186.02: | 242553 |  | 206191.79 |  | 36361.21

## #9186.02 Ideal Floors
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Ideal Floors |  |  | Vendor Code: 00002126112
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299811 | 2024-04-24 | PO Procore | 79284.23 | 79284.23 |  |  | 79284.23 | 0
GAX 33524219902 | 2024-08-06 | Inv. 9186.02-03(100% to 9186.02) |  | 79284.23 | 46346.34 | 46346.34 | 32937.89 | 2439.27 | FY24
PO 33525299811 | 2024-08-16 | Roll to FY25 | 0 | 79284.23 |  | 46346.34 | 32937.89
GAX 33525248901 | 2024-09-04 | Inv. 9186.02-04(100% to 9186.02) |  | 79284.23 | 12066.77 | 58413.11 | 20871.12 | 3074.36
GAX 33525365905 | 2024-12-30 | Inv. 9186.02-06(100% to 9186.02) |  | 79284.23 | 17811.24 | 76224.35 | 3059.88 | 4011.79
GAX 33525055903 | 2025-02-24 | Inv. 32943(100% to 9186.01) |  | 79284.23 | 0 | 76224.35 | 3059.88
GAX 33525065902 | 2025-03-06 | Inv. 9186.02-07(100% to 9186.02) |  | 79284.23 | 1682.38 | 77906.73 | 1377.5 | 4100.34
GAX 33525177904 | 2025-06-26 | Inv. 9186.02-08(Split w/ 9186.01) |  | 79284.23 | 1377.5 | 79284.23 | 1.1823e-11 | 4172.84
|  |  |  | 79284.23 |  | 79284.23 | 1.1823e-11
|  |  |  | 79284.23 |  | 79284.23 | 1.1823e-11
|  |  |  | 79284.23 |  | 79284.23 | 1.1823e-11
|  |  |  | 79284.23 |  | 79284.23 | 1.1823e-11
|  |  |  | 79284.23 |  | 79284.23 | 1.1823e-11
|  | Totals: | 79284.23 |  | 79284.23 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Split funding 9186.01 06/17/24 | 475416.2 |  | 65408.65 |  | 410007.55
|  | CO #1-Split Funding 9186.01 06/17/24 | 6573 |  | 6244.35 |  | 328.65
|  | CO #2-Split Funding 9186.01 06/17/24 | 4107 |  | 3901.64 |  | 205.36
|  | CO #3 06/19/24 100% to 9186.02 | 1628.64 |  | 1547.21 |  | 81.43
|  | CO #4 09/04/24 100% to 9186.02 | 2297.24 |  | 2182.38 |  | 114.86
|  | CO #5 10/22/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #6 11/22/24 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #7 05/07/25 No Cost CO | 0 |  | 0 |  | 0
|  | Split funding to 9186.02 | -406565.01 |  | 0 |  | -406565.01
|  | Total 9186.02: | 83457.07 |  | 79284.23 |  | 4172.84
|  | 9186.01 06/17/24 HHS Funds | 575004.57 |  | 528681.59 |  | 46322.98
|  | Total Contract 9186.01 and 9186.02: | 658461.64 |  | 607965.82 |  | 50495.82

## #9186.02 All Makes-Furniture
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
All Makes-Furniture |  |  | Vendor Code: 00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA23148
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524325801 | 2024-06-17 | PO Procore | 2281545.83 | 2281545.83 |  |  | 2281545.83
GAX 33524185907 | 2024-07-02 | Inv. 311713(100% to 918602) |  | 2281545.83 | 840620.24 | 840620.24 | 1440925.59 | 44243.17
GAX 33524211900 | 2024-07-29 | Inv. 311892, 311880, 311798(100% to 918602) |  | 2281545.83 | 1389100.58 | 2229720.82 | 51825.01 | 117353.74 | FY24
PO 33525325801 | 2024-08-16 | Roll to FY25 | 0 | 2281545.83 |  | 2229720.82 | 51825.01
GAX 33525249906 | 2024-09-05 | Inv. 311980, 311981, 312083, 312085, 312088(100% to (9186.01) |  | 2281545.83 | 0 | 2229720.82 | 51825.01
GAX 33525304903 | 2024-10-30 | Inv. 312214(100% to 9186.01) |  | 2281545.83 | 0 | 2229720.82 | 51825.01
GAX 33525310900 | 2024-11-05 | Inv. 312133, 312084, 312085-2, 312270, 312271(100% to 9186.01) |  | 2281545.83 | 0 | 2229720.82 | 51825.01
GAX 33525365906 | 2024-12-30 | Inv. 312299(100% to 918602) |  | 2281545.83 | 11205.25 | 2240926.07 | 40619.76 | 117943.49
GAX 33525043901 | 2025-02-11 | Inv. 312389, 312473(100%to 9186.01) |  | 2281545.83 | 0 | 2240926.07 | 40619.76
GAX 33525062901 | 2025-03-04 | Inv. 312655, 312659(100% to 9186.01) |  | 2281545.83 | 0 | 2240926.07 | 40619.76
GAX 33525104901 | 2025-04-14 | Inv. 312792, 312740, 312791, 312784 (100% to 9186.01) |  | 2281545.83 | 0 | 2240926.07 | 40619.76
GAX 33525174907 | 2025-06-23 | Inv. 312887, 312865, 312921, 312888 (Split w/ 9186.01) |  | 2281545.83 | 40619.76 | 2281545.83 | 0 | 120081.37
|  |  |  | 2281545.83 |  | 2281545.83 | 0
|  |  |  | 2281545.83 |  | 2281545.83 | 0
|  |  |  | 2281545.83 |  | 2281545.83 | 0
|  | Totals: | 2281545.83 |  | 2281545.83 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Split Funding 9186.01 06/17/24 | 2400000 |  | 2240926.07 |  | 159073.93
|  | CO #5 100% to 9186.01 | 0 |  | 0 |  | 0
|  | CO #6 100% to 9186.01 10/08/24 | 0 |  | 0 |  | 0
|  | CO #7 Split with 918602 01/23/25 | 7538.56 |  |  |  | 7538.56
|  | CO #8 100% to 9186.01 01/23/25 | 0 |  | 0 |  | 0
|  | CO #9 100% to 9186.01 03/04/25 | 0 |  | 0 |  | 0
|  | CO#10 100% to 9186.01 03/07/25 | 0 |  | 40619.76 |  | 0
|  | Total 9186.02: | 2407538.56 |  | 2281545.83 |  | 166612.49
|  | 9186.01 06/17/24 HHS Funds | 2512245.43 |  | 2371984.41 |  | 140261.02
|  | Total Contract 9186.01 and 9186.02: | 4919783.99 |  | 4653530.24 |  | 266253.75

## #9186.02 Comiskey Glass
DHS CC Strategic Space Planning
Project # 9186.02
Program code 918602 SLFRF |  |  | Major Program 4D08
Comiskey Glass |  |  | Vendor Code: 00002118031
Acct. Codes-0506-335-DA22-9255 |  |  | RFB918601-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split with 9186.01
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524299807 | 2024-06-17 | PO Procore | 109990.08 | 109990.08 |  |  | 109990.08
GAX 33524208916 | 2024-07-26 | Inv. 9186.02-01 |  | 109990.08 | 40315.73 | 40315.73 | 69674.35 | 2121.89 | FY24
PO 33525299807 | 2024-08-16 | Roll to FY25 | 0 | 109990.08 |  | 40315.73 | 69674.35
GAX 33525271907 | 2024-09-27 | Inv. 9186.02-02 |  | 109990.08 | 24144.7 | 64460.43 | 45529.65 | 3392.66
GAX 33525288900 | 2024-10-14 | Inv. 9186.02-03 |  | 109990.08 | 17109.5 | 81569.93 | 28420.15 | 4293.16
GAX 33525365903 | 2024-12-30 | Inv. 9186.01-04(Split w/9186.02) |  | 109990.08 | 28420.15 | 109990.08 | 0 | 5788.96
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  |  |  | 109990.08 |  | 109990.08 | 0
|  | Totals: | 109990.08 |  | 109990.08 |  | 0
PO number above is assigned to Procore PO, but not created in IA Advantage due to Paper Contract.
Will create GAX payments as funds become available to charge against this project.
Procore created contract:
|  |  | Contract Amounts: |  | Expenses: |  | Remainder/Pending Reimbursement:
|  | Contract | 123854.55 |  | 110242.79 |  | 13611.76
|  | CO # 1 09/04/24 | -252.71 |  | -252.71 |  | 0
|  | CO # 2 10/15/24 Open 918601 | 0 |  |  |  | 0
|  | CO # 3 10/24/2024 100% to 9186.01 | 0 |  |  |  | 0
|  | CO #4 01/16/2025 100% to 9186.02 | 12931.45 |  |  |  | 12931.45
|  | CO #5 05/0720/25 100% to 9186.02 | 968.25 |  |  |  | 968.25
|  | CO #6 06/19/2025 No Cost CO | 0 |  |  |  | 0
|  | Total 9186.02: | 137501.54 |  | 109990.08 |  | 27511.46
|  | 9186.01 | 2804.7 |  | 1438.01 |  | 1366.69
|  | Total Contract 9186.01 and 9186.02: | 140306.24 |  | 111428.09 |  | 28878.15
Clark Glass PO closed at the request of the project mananager. 05/24/24
Clark Glass Company out of business.
Retainage will go to Bonding company "Comiskey Glass" per Tender Agreement.

## RECAP #9186.03
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
| Program code 918603 |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursement
| Funds received per MOU | 982346
C | All Makes (P) |  | 624217.13 | 624217.13 | 0
| PM TIME |  | 15000 | 267.11 | 14732.89
| Misc. |  | 130202.95 | 130202.95 | 0
C | Ralph N Smith |  | 103487 | 103487 | 0
C | Heartland Paint |  | 34027 | 34027 | 0
| Total Project Cost | 982346 | 906934.08 | 892201.19 | 14732.89 | 75411.92 | 0

## #9186.03 Funds Rec'd
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33524087802 | 2024-03-27 | 50000 | 50000
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525257913 | 2024-09-13 | 10000 | 10000
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525281800 | 2024-10-07 | 728708.54 | 728708.54
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525298911 | 2024-10-24 | 46811.57 | 46811.57
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525299902 | 2024-10-25 | 2469 | 2469
|  |  | CDR to move Revenue 9186.01 to 9186.03 | CDR 33525351901 | 2024-12-16 | 144356.89 | 144356.89
| Total Requested | 0 | Total Transferred |  |  | 982346 | 982346

## #9186.03 All Makes
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  | Major Program 4D08
All Makes |  |  | Vendor:00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA 23148
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524171800 | 2024-06-19 | DO IA Advantage (Unencumbered) | 624217.13 | 624217.13 |  |  | 624217.13 | FY24
DO 33525171800 | 2024-08-26 | Roll to FY25 |  | 624217.13 |  | 0 | 624217.13
PRC 3352517PA1800 | 2024-10-25 | Inv. 312267 |  | 624217.13 | 624217.13 | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  |  |  | 624217.13 |  | 624217.13 | 0
|  | Totals: | 624217.13 |  | 624217.13 |  | 0 | FINAL
|  | Total Contract | 624217.13 |  | 624217.13 |  | 0
|  | Total | 624217.13 |  | 624217.13 |  | 0

## #9186.03 PM TIME
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  |  | Major Program 4D08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 908Z
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15000 | 15000 |  |  | 15000
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 15000 | 10.33 | 10.33 | 14989.67
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 15000 | 83.6 | 93.93 | 14906.07
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 15000 | 15.18 | 109.11 | 14890.89
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 15000 | 158 | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
[5 empty] | 15000 |  | 267.11 | 14732.89
|  |  | Totals: | 15000 |  | 267.11 |  | 14732.89
Note on E9: Jurgenson, John [DAS]: 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (1 hour ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000 Elliott, Jennie 8:55 AM (13 minutes ago) to me, John Please make the following changes. Reduce PM Time budget in 9186.03 to $15,000 in the "Contracted" Line Transfer $5,000 from 9186.02 to 9186.04 Reduce PM Time budget in 9186.06 to $44,952.50 in the "Contracted" Line Thank you, Jennie Elliott

## #9186.03 Misc
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Space Planning Services April 01-30, 2024 | DAS2024101153 | 3871.25 | 3871.25
IET DAS202411115300001 | 2024-06-10 | 2507 |  | Space Planning Services May 01-31, 2024 | DAS2024111153 | 285 | 4156.25
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Space Planning Services June 01-30, 2024 | DAS2024121153 | 1021.25 | 5177.5
PRCI 33525257911 | 2024-09-13 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357059 | 6881.61 | 12059.11
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Space Planning Services August 01-31, 2024 | DAS2025021153 | 902.5 | 12961.61
PRC 33525282905 | 2024-10-08 | 9500 | CNST | Heartland Finishes V#(00002097604) | Inv. 18804 | 12750 | 25711.61
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Space Planning September 01-30, 2024 | DAS2025031153 | 1163.75 | 26875.36
IET DAS202503115300001 | 2024-10-09 | 2507 |  | HVAC Services September 01-30, 2024 | DAS2025031153 | 1541.12 | 28416.48
GAX 33525290903 | 2024-10-16 | 9500 | CNST | Smart Clean V#(VS000000269) | Inv. 12073 | 550 | 28966.48
PRCI 33525304900 | 2024-10-30 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357094 | 2469 | 31435.48
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Custodial Services October 01-31, 2024 | DAS2025041153 | 524.76 | 31960.24
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning October 01-31, 2024 | DAS2025041153 | 3681.25 | 35641.49
GAX 33525339905 | 2024-12-03 | 9500 | CNST | American Graphics V#(00003113118) | Inv. 0038118 | 2714.74 | 38356.23
IET 33525351902 | 2024-12-16 | 9500 | CNST | ICN Bill - November | Inv. 711411 | 33812.88 | 72169.11
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Electrical Services December 01-31, 2024 | Inv. DAS2025061153 | 350.47 | 72519.58
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Services December 01-31, 2024 | Inv. DAS2025061153 | 1472.5 | 73992.08
GAX 33525028902 | 2025-01-28 | 9500 | CNST | CTI V#(00003055217) | Inv. P-INV015511 | 2569.7 | 76561.78
IET DAS202507115300001 | 2025-02-11 | 2507 |  | Carpentry | DAS2025071153 | 426.32 | 76988.1
GAX 33525062906 | 2025-03-04 | 9500 | CNST | All Makes V#(00002110818) | Inv. 312479 | 409.32 | 77397.42
GAX 33525062906 | 2025-03-04 | 9500 | CNST | All Makes V#(00002110818) | Inv. 312478 | 2122.5 | 79519.92
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Locksmith & Key Services February 01-28, 2025 | DAS2025081153 | 155.18 | 79675.1
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Electrical Services February 01-28, 2025 | DAS2025081153 | 49886.6 | 129561.7
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Services March 01-31, 2025 | DAS2025091153 | 641.25 | 130202.95
130202.95
130202.95
130202.95
|  |  |  | Totals: |  | 130202.95

## #9186.03 Ralph N Smith
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  | Major Program 4D08
Ralph N. Smith |  |  | Vendor: 00002106937
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21267
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525232904 | 2024-08-16 | DO Procore(Unencumbered) | 103487 | 103487 |  |  | 103487
PRC 3352523PA2904 | 2024-10-14 | Inv. 30866 |  | 103487 | 103487 | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  |  |  | 103487 |  | 103487 | 0
|  | Totals: | 103487 |  | 103487 |  | 0
|  | Labor | 42882 |  | 42882 |  | 0
|  | Material | 60605 |  | 60605 |  | 0
|  | Total | 103487 |  | 103487 |  | 0
|  | Total Contract | 103487 |  | 103487 |  | 0
|  | Total | 103487 |  | 103487 |  | 0

## #9186.03 Heartland Paint
DHS CC Strategic Space Planning (Hoover 1st Floor South Attorney General) - HHS Funds
Project # 9186.03
Program code 918603 |  |  | Major Program 4D08
Heartland Paint |  |  | Vendor: 00002097604
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21267
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525236904 | 2024-08-23 | DO Procore(Unencumbered) | 34027 | 34027 |  |  | 34027
PRC 3352523PA6904 | 2024-10-08 | Inv. 18805 |  | 34027 | 34027 | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  |  |  | 34027 |  | 34027 | 0
|  | Totals: | 34027 |  | 34027 |  | 0
|  | Labor | 30600 |  | 30600 |  | 0
|  | Material | 3427 |  | 3427 |  | 0
|  | Total | 34027 |  | 34027 |  | 0
|  | Total Contract | 34027 |  | 34027 |  | 0
|  | Total | 34027 |  | 34027 |  | 0

## RECAP #9186.04
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
| Program code SLFRF |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursement
| Funds received per MOU | 1312670.37
C | DCI Group (P) |  | 12250.55 | 12250.55 | 0 |  | 0
| PM TIME |  | 25000 | 15745.33 | 9254.67 |  | 0
| Misc. |  | 102911.13 | 102911.13 | 0 |  | 0
C | All Makes (P) |  | 581834.54 | 581834.54 | 0 |  | 0
C | Neumann Monson (P) |  | 57125 | 57125 | 0 |  | 0
C | CTI (P) |  | 41196.79 | 41196.79 | 0 |  | 0
C | Modern Piping Services (P) |  | 58696 | 58696 | 0 |  | 0
C | Eick & Day Construction (P) |  | 216677.32 | 216677.32 | 0 |  | 0
C | Waldinger Corporation (P) |  | 153696.7 | 153696.7 | 0 |  | 0
| DCI Group(2) (P) |  | 39271.56 | 39271.56 | 0 |  | 20723.48
C | All Makes (2) |  | 3132.14 | 3132.14 | 0 |  | 0
| AGI |  | 0 | 0 | 0 |  | 3886.88
C | All Makes(3) |  | 14360.17 | 14360.17 | 0 |  | 0
| Total Project Cost | 1312670.37 | 1306151.9 | 1296897.23 | 9254.67 | 6518.47 | 24610.36

## #9186.04 Funds Rec'd
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33524087803 | 2024-03-27 | 50000 | 50000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525249908 | 2024-09-05 | 50000 | 50000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525317900 | 2024-11-12 | 5000 | 5000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525340907 | 2024-12-05 | 115000 | 115000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525365900 | 2024-12-30 | 25000 | 25000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525003909 | 2025-01-03 | 100000 | 100000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525013908 | 2025-01-13 | 100000 | 100000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525041900 | 2025-02-10 | 100000 | 100000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525062900 | 2025-03-04 | 800000 | 800000
|  |  | CDR to move Revenue 9186.02 to 9186.04 | CDR 33525181910 | 2025-06-30 | -32329.63 | -32329.63
| Total Requested | 0 | Total Transferred |  |  | 1312670.37 | 1312670.37

## #9186.04 DCI Group
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524115800 | 2024-04-24 | PO Procore (Unencumbered) | 12250.55 | 12250.55 |  |  | 12250.55
GAX 33524190902 | 2024-07-08 | Inv. 24-012 PC-01 |  | 12250.55 | 1451.5 | 1451.5 | 10799.05
PRC 3352411PB5800 | 2024-07-26 | Inv. 24-012 PC 02 |  | 12250.55 | 2750.09 | 4201.59 | 8048.96 | FY24
PO 33525115800 | 2024-08-16 | Roll to FY25 |  | 12250.55 |  | 4201.59 | 8048.96
PRC 3352511PC5800 | 2024-09-04 | Inv. 24-012 PC-03 |  | 12250.55 | 2199.83 | 6401.42 | 5849.13
PRC 3352511PD5800 | 2024-09-27 | Inv. 24-012 PC 04 |  | 12250.55 | 2936.87 | 9338.29 | 2912.26
PRC 3352511PE5800 | 2024-10-22 | Inv. 24-012 PC 05 |  | 12250.55 | 2912.26 | 12250.55 | 0
PO 33525115800 | 2025-03-10 | Closing Per PM |  | 12250.55 |  | 12250.55 | 0
|  |  |  | 12250.55 |  | 12250.55 | 0
|  |  |  | 12250.55 |  | 12250.55 | 0
|  |  |  | 12250.55 |  | 12250.55 | 0
|  |  |  | 12250.55 |  | 12250.55 | 0
|  |  |  | 12250.55 |  | 12250.55 | 0
|  | Totals: | 12250.55 |  | 12250.55 |  | 0
|  | Total Contract | 12250.55 |  | 12250.55 |  | 0
|  | Total: 9186.04 | 12250.55 |  | 12250.55 |  | 0

## #9186.04 PM TIME
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  |  | Major Program 4D08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 909A
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 25000 | 25000 |  |  | 25000
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 25000 | 5.42 | 5.42 | 24994.58
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 25000 | 39.3 | 44.72 | 24955.28
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 25000 | 141.69 | 186.41 | 24813.59
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 25000 | 1256.4 | 1442.81 | 23557.19
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 25000 | 121.85 | 1564.66 | 23435.34
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 25000 | 1006.3 | 2570.96 | 22429.04
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 25000 | 100.65 | 2671.61 | 22328.39
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 25000 | 920.6 | 3592.21 | 21407.79
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 25000 | 72.37 | 3664.58 | 21335.42
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 25000 | 791.8 | 4456.38 | 20543.62
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 25000 | 261.97 | 4718.35 | 20281.65
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 25000 | 1334.6 | 6052.95 | 18947.05
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 25000 | 275.68 | 6328.63 | 18671.37
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 25000 | 2453.6 | 8782.23 | 16217.77
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 25000 | 103.71 | 8885.94 | 16114.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 25000 | 699.6 | 9585.54 | 15414.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 25000 | 176.66 | 9762.2 | 15237.8
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 25000 | 1174.1 | 10936.3 | 14063.7
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 25000 | 82.13 | 11018.43 | 13981.57
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 25000 | 816.4 | 11834.83 | 13165.17
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 25000 | 247.5 | 12082.33 | 12917.67
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 25000 | 2639.7 | 14722.03 | 10277.97
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 25000 | 119.08 | 14841.11 | 10158.89
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 25000 | 515.6 | 15356.71 | 9643.29
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 25000 | 37.68 | 15394.39 | 9605.61
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 25000 | 271.8 | 15666.19 | 9333.81
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 25000 | 9.84 | 15676.03 | 9323.97
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 25000 | 69.3 | 15745.33 | 9254.67
[5 empty] | 25000 |  | 15745.33 | 9254.67
[5 empty] | 25000 |  | 15745.33 | 9254.67
|  |  | Totals: | 25000 |  | 15745.33 |  | 9254.67
Note on E9: Jurgenson, John [DAS]: 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (1 hour ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000

## #9186.04 Misc
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Space Planning Services April 01-30, 2024 | DAS2024101153 | 332.5 | 332.5
IET DAS202411115300001 | 2024-06-10 | 2507 |  | Space Planning Services May 01-31, 2024 | DAS2024111153 | 142.5 | 475
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Space Planning Services June 01-30, 2024 | DAS2024121153 | 1876.25 | 2351.25
IET DAS202501115300001 | 2024-08-07 | 2507 |  | Space Planning Services July 01-31, 2024 | DAS2025021153 | 356.25 | 2707.5
PRCI 33525250902 | 2024-09-06 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357067 & 357076 | 14060.79 | 16768.29
PRCI 33525257903 | 2024-09-12 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357045 | 1639 | 18407.29
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Space Planning Services August 01-31, 2024 | DAS2025021153 | 4963.75 | 23371.04
IET 33525282901 | 2024-10-07 | 9210 | CNST | ICN Bill - August | Inv. 705629 | 312 | 23683.04
IET 33525282901 | 2024-10-07 | 9210 | CNST | ICN Bill - August | Inv. 705629 | 152.33 | 23835.37
IET 33525282901 | 2024-10-07 | 9210 | CNST | ICN Bill - August | Inv. 705629 | 90.5 | 23925.87
IET 33525282901 | 2024-10-07 | 9210 | CNST | ICN Bill - August | Inv. 705629 | 78 | 24003.87
PRC 33525282907 | 2024-10-07 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV043244 | 758.7 | 24762.57
PRC 33525282908 | 2024-10-07 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2599216 | 1148.75 | 25911.32
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Space Planning September 01-30, 2024 | DAS2025031153 | 1710 | 27621.32
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Fire Watch Service October 01-31,2024 | DAS2025041153 | 80.42 | 27701.74
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning October 01-31,2024 | DAS2025041153 | 1425 | 29126.74
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing | DAS2025041153 | 143.16 | 29269.9
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Electrical Services October 01-31,2024 | DAS2025041153 | 457.06 | 29726.96
GAX 33525344901 | 2024-12-09 | 9500 | CNST | Waldinger Corp V#(00002116105) | Inv. 82553T-001 | 1050 | 30776.96
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Services December 01-31, 2024 | Inv. DAS2025061153 | 1068.75 | 31845.71
GAX 33525015904 | 2025-01-15 | 9500 | CNST | Walsh Door & Security V#(00002113318) | Inv. 821258 | 8550 | 40395.71
GAX 33525035903 | 2025-02-04 | 9500 |  | Insight V#(00002100702) | Inv. 1101230904 | 4955 | 45350.71
PRCI 33525035906 | 2025-02-04 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357147 | 93 | 45443.71
PRCI 33525035906 | 2025-02-04 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357148 | 3412.25 | 48855.96
IET DAS202507115300001 | 2025-02-11 | 2507 |  | Fire Watch Services January 01-31, 2025 | DAS2025071153 | 331.38 | 49187.34
IET DAS202507115300001 | 2025-02-11 | 2501 |  | Infrastructure Consulting January 01-31, 2025 | DAS2025071153 | 271.93 | 49459.27
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Space Planning Services February 01-31, 2025 | DAS2025081153 | 261.25 | 49720.52
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Infrastructure Consulting February 01-31, 2025 | DAS2025081153 | 54.38 | 49774.9
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Custodial Service February 01-31, 2025 | DAS2025081153 | 3173.12 | 52948.02
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing February 01-31, 2025 | DAS2025081153 | 3038.44 | 55986.46
IET 33525077903 | 2025-03-18 | 9210 | CNST | ICN Bill - February | Inv. 717206 - 003 | 25446.23 | 81432.69
GAX 33525093901 | 2025-04-03 | 9500 |  | American Graphics V#(00003113118) | Inv. 0039509 | 668.5 | 82101.19
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Electrical Services March 01-31, 2025 | DAS2025091153 | 3179.93 | 85281.12
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Services March 01-31, 2025 | DAS2025091153 | 10260 | 95541.12
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Locksmith & Key Services April 1-30, 2025 | DAS2025101153 | 2123.64 | 97664.76
IET DAS202510115300001 | 2025-05-09 | 2501 |  | Infrastructure Consulting April 1-30, 2025 | DAS2025101153 | 326.31 | 97991.07
IET DAS202510115300001 | 2025-05-09 | 2501 |  | Infrastructure Consulting April 1-30, 2025 | DAS2025101153 | 271.93 | 98263
IET DAS202510115300001 | 2025-05-09 | 2501 |  | Infrastructure Consulting April 1-30, 2025 | DAS2025101153 | 271.93 | 98534.93
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Space Planning Services April 01-30, 2025 | DAS2025101153 | 1496.25 | 100031.18
GAX 33525157901 | 2025-06-06 | 9500 |  | American Graphics V#(00003113118) | Inv. 0040306 | 234.2 | 100265.38
PRC 33525157905 | 2025-06-06 | 9500 |  | All Makes V#(00002110818) | Inv. 312955 | 478.74 | 100744.12
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Electrical Services May 01-31, 2025 | DAS2025111153 | 168.62 | 100912.74
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Painting Services May 01-31, 2025 | DAS2025111153 | 1710.66 | 102623.4
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Space Plannig May 01-31, 2025 | DAS2025111153 | 261.25 | 102884.65
PRCI 33525178910 | 2025-06-27 | 9210 |  | Iowa Prison Industries V#(250DOCIPI00) | Inv. 044281 | 22.75 | 102907.4
PRCI 33525181902 | 2025-06-30 | 9210 |  | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357220 | 3.73 | 102911.13
102911.13
|  |  |  | Totals: |  | 102911.13

## #9186.04 All Makes
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
All Makes |  |  | Vendor:00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA #22314A
Project Manager - Jennie E. |  |  | Activity code:CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524166803 | 2024-06-14 | PO Procore (Unencumbered) |  | 0 |  |  | 0 | FY24
DO 33525166803 | 2024-08-16 | Roll to FY25 | 581834.54 | 581834.54 |  | 0 | 581834.54
DO 33525166803A | 2024-08-19 | CO #1 |  | 581834.54 |  | 0 | 581834.54
DO 33525166803A | 2025-03-05 | Close to open as SLFRF |  | 581834.54 |  | 0 | 581834.54
DO 33525166803B | 2025-03-05 | Open with SLFRF as Project |  | 581834.54 |  | 0 | 581834.54
PRC 3352516PA6803B | 2025-03-05 | Inv. 312599 & 312600 |  | 581834.54 | 581834.54 | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  |  |  | 581834.54 |  | 581834.54 | 0
|  | Totals: | 581834.54 |  | 581834.54 |  | 0
|  | Total | 581595.02 |  | 581595.02 |  | 0
|  | CO #1 | 239.52 |  | 239.52 |  | 0
|  | Total: 9186.04 | 581834.54 |  | 581834.54 |  | 0

## #9186.04 Neumann Monson
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
Neumann Monson |  |  | Vendor:00002116371
Acct. Codes-0506-335-DA22-9260 |  |  | RFP 918604-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524185905 | 2024-07-03 | PO Procore | 57125 | 57125 |  |  | 57125
DO 33524185905A | 2024-07-31 | Corrected PO Amount and changed to (Unencumbered) |  | 57125 |  | 0 | 57125 | FY24
DO 33525185905A | 2024-08-13 | Roll to FY25 |  | 57125 |  | 0 | 57125
PRC 3352518PA5905A | 2024-09-05 | Inv. 9186.04-01 |  | 57125 | 17225 | 17225 | 39900
PRC 3352518PB5905A | 2024-09-27 | Inv. 9186.04-02 |  | 57125 | 17225 | 34450 | 22675
PRC 3352518PC5905A | 2024-12-23 | Inv. 9186.04-03 |  | 57125 | 9430 | 43880 | 13245 |  | `
PRC 3352518PD5905A | 2025-02-04 | Inv. 9186.04-04 |  | 57125 | 4415 | 48295 | 8830
PRC 3352518PE5905A | 2025-05-05 | Inv. 9186.04-05 |  | 57125 | 8830 | 57125 | 0
|  |  |  | 57125 |  | 57125 | 0
|  |  |  | 57125 |  | 57125 | 0
|  |  |  | 57125 |  | 57125 | 0
|  |  |  | 57125 |  | 57125 | 0
|  |  |  | 57125 |  | 57125 | 0
|  | Totals: | 57125 |  | 57125 |  | 0 | FINAL
|  | 50% Construction Docs | 17225 |  | 17225 |  | 0
|  | 100% Construction Docs | 17225 |  | 17225 |  | 0
|  | Bidding/Negotiations | 5015 |  | 5015 |  | 0
|  | Construction Phase | 17660 |  | 17660 |  | 0
|  | Total 9186.04: | 57125 |  | 57125 |  | 0

## #9186.04 CTI
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
CTI |  |  | Vendor: 00002133110
Acct. Codes-0506-335-DA22-9255 |  |  | MA#22036B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525232900 | 2024-08-19 | DO Procore (Unencumbered) | 41196.79 | 41196.79 |  |  | 41196.79
PRC 3352523PA2900 | 2025-02-06 | Inv. P-INV017486 |  | 41196.79 | 41196.79 |  | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  |  |  | 41196.79 |  | 0 | 41196.79
|  | Totals: | 41196.79 |  | 41196.79 |  | 0
|  | Contract | 41196.79 |  | 41196.79 |  | 0
|  | Total: 9186.04 | 41196.79 |  | 41196.79 |  | 0

## #9186.04 Modern Piping
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
Modern Piping Services |  |  | Vendor: 00002108094
Acct. Codes-0506-335-DA22-9255 |  |  | RFB 918604-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525284900 | 2024-10-10 | PO Procore (Unencumbered) | 58696 | 58696 |  |  | 58696
PRC 3352528PA4900 | 2025-01-03 | Inv. 73748 |  | 58696 | 50940.9 | 50940.9 | 7755.1 | 2681.1
PRC 3352528PB4900 | 2025-02-24 | Inv. 74691 |  | 58696 | 3870.3 | 54811.2 | 3884.8 | 2884.8
PRC 3352528PC4900 | 2025-03-17 | Inv. 75240 |  | 58696 | 950 | 55761.2 | 2934.8 | 2934.8
PRC 3352528PD4900 | 2025-04-14 | Inv. 7577R - Retainage |  | 58696 | 2934.8 | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  |  |  | 58696 |  | 58696 | 0
|  | Totals: | 58696 |  | 58696 |  | 0 | FINAL
|  | Contract | 56182 |  | 56182 |  | 0
|  | CO #1 02/18/25 | 2514 |  | 2514 |  | 0
|  | Total: 9186.04 | 58696 |  | 58696 |  | 0

## #9186.04 Eick & Day
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
Eick & Day |  |  | Vendor: VS000005512
Acct. Codes-0506-335-DA22-9255 |  |  | RFB 918604-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525288902 | 2024-10-14 | PO Procore (Unencumbered) | 216677.32 | 216677.32 |  |  | 216677.32
PRC 3352528PA8902 | 2024-12-06 | Inv. 24795.01 |  | 216677.32 | 90501.65 | 90501.65 | 126175.67 | 4763.24
PRC 3352528PB8902 | 2025-03-04 | Inv. 24795.02 |  | 216677.32 | 104040.21 | 194541.86 | 22135.46 | 10239.05
PRC 3352528PC8902 | 2025-03-17 | Inv. 24795.03 |  | 216677.32 | 9387.34 | 203929.2 | 12748.12 | 10733.12
PRC 3352528PD8902 | 2025-04-22 | Inv. 24795.04 |  | 216677.32 | 1914.25 | 205843.45 | 10833.87 | 10833.87
PRC 3352528PE8902 | 2025-05-05 | Inv. 24795.05 - Retainage |  | 216677.32 | 10833.87 | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  |  |  | 216677.32 |  | 216677.32 | 0
|  | Totals: | 216677.32 |  | 216677.32 |  | 0
|  | Contract | 201449 |  | 201449 |  | 0
|  | CO #1 12/12/24 | 1344.6 |  | 1344.6 |  | 0
|  | CO #2 01/10/25 | 7240.6 |  | 7240.6 |  | 0
|  | CO #3 01/14/25 | 5104.71 |  | 5104.71 |  | 0
|  | CO #4 02/21/25 | 1538.41 |  | 1538.41 |  | 0
|  | Total 9186.04: | 216677.32 |  | 216677.32 |  | 0

## #9186.04 Waldinger Corp
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
Waldinger Corp |  |  | Vendor: 00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | RFB 918604-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525304908 | 2024-10-30 | PO Procore (Unencumbered) | 153696.7 | 153696.7 |  |  | 153696.7
PRC 3352530PA4908 | 2024-12-06 | Inv. 82682E-001 |  | 153696.7 | 19783.04 | 19783.04 | 133913.66 | 1041.21
PRC 3352530PB4908 | 2025-01-21 | Inv. 82682E-002 |  | 153696.7 | 106300.72 | 126083.76 | 27612.94 | 6635.99
PRC 3352530PC4908 | 2025-02-05 | Inv. 82682E-003 |  | 153696.7 | 14763.9 | 140847.66 | 12849.04 | 7413.04
PRC 3352530PD4908 | 2025-03-21 | Inv. 82682E-004 |  | 153696.7 | 3786.7 | 144634.36 | 9062.34 | 7612.34
PRC 3352530PE4908 | 2025-04-07 | Inv. 82682E-005 |  | 153696.7 | 1377.5 | 146011.86 | 7684.84 | 7684.84
PRC 3352530PF4908 | 2025-04-25 | Inv. 82682E-006 - Retainage |  | 153696.7 | 7684.84 | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  |  |  | 153696.7 |  | 153696.7 | 0
|  | Totals: | 153696.7 |  | 153696.7 |  | 0 | FINAL
|  | Contract | 140945 |  | 140945 |  | 0
|  | CO #1 12/31/24 | 7201 |  | 7201 |  | 0
|  | CO #2 01/28/25 | 1564.7 |  | 1564.7 |  | 0
|  | CO #3 02/18/25 | 3986 |  | 3986 |  | 0
|  | Total 9186.04: | 153696.7 |  | 153696.7 |  | 0

## #9186.04 DCI Group (2)
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
DCI Group(2) |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525312904 | 2024-11-07 | PO Procore (Unencumbered) | 39271.56 | 39271.56 |  |  | 39271.56
PRC 3352531PA2904 | 2024-12-30 | Inv. 24-012 CA 01 |  | 39271.56 | 14161.12 | 14161.12 | 25110.44
PRC 3352531PB2904 | 2025-01-27 | Inv. 24-012 CA 02 |  | 39271.56 | 8826.6 | 22987.72 | 16283.84
PRC 3352531PC2904 | 2025-02-17 | Inv. 24-012 CA 03 |  | 39271.56 | 9932.1 | 32919.82 | 6351.74
PRC 3352531PD2904 | 2025-03-21 | Inv. 24-012 CA 04 |  | 39271.56 | 4830.2 | 37750.02 | 1521.54
PRC 3352531PE2904 | 2025-04-22 | Inv. 24-012 CA 05 |  | 39271.56 | 1521.54 | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  |  |  | 39271.56 |  | 39271.56 | -5.457e-12
|  | Totals: | 39271.56 |  | 39271.56 |  | 0
|  | CM Staff Hours | 58495.04 |  | 38551.56 |  | 19943.48
|  | Reimbursables | 1500 |  | 720 |  | 780
|  | Total 9186.04: | 59995.04 |  | 39271.56 |  | 20723.48

## #9186.04 All Makes (2)
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
All Makes (2) |  |  | Vendor:00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA #22314A
Project Manager - Jennie E. |  |  | Activity code:CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525036903 | 2025-02-05 | DO Procore (Unencumbered) | 3132.14 | 3132.14 |  |  | 3132.14
PRC 3352503PA6903 | 2025-04-03 | Inv. 312803 |  | 3132.14 | 3132.14 | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  |  |  | 3132.14 |  | 3132.14 | 0
|  | Totals: | 3132.14 |  | 3132.14 |  | 0 | FINAL
0
|  | Total: 9186.04 | 3132.14 |  | 3132.14 |  | 0

## #9186.04 AGI
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
AGI |  |  | Vendor: 00003113118
Acct. Codes-0506-335-DA22-9500 |  |  | MA005 240051900A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525111902 | 2025-04-21 | PO Procore (Unencumbered) |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Labor | 1100 |  |  |  | 1100
|  | Reimbursables | 2786.88 |  |  |  | 2786.88
|  | Total: | 3886.88 |  | 0 |  | 3886.88

## #9186.04 All Makes (3)
DHS CC Strategic Space Planning (Hoover 3rd Floor Dept of Admin Serv) - SLFRF Funds
Project # 9186.04
Program code SLFRF |  |  | Major Program 4D08
All Makes |  |  | Vendor:00002110818
Acct. Codes-0506-335-DA22-9500 |  |  | MA #22314A
Project Manager - Jennie E. |  |  | Activity code:CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525112902 | 2025-04-22 | PO Procore (Unencumbered) | 14360.17 | 14360.17 |  |  | 14360.17
PRC 3352511PA2902 | 2025-05-28 | Inv. 312857 |  | 14360.17 | 1996.55 | 1996.55 | 12363.62
PRC 3352511PB2902 | 2025-06-10 | Inv. 312944 |  | 14360.17 | 12363.62 | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  |  |  | 14360.17 |  | 14360.17 | 0
|  | Totals: | 14360.17 |  | 14360.17 |  | 0 | FINAL
|  | Contract | 12363.62 |  | 12363.62 |  | 0
|  | CO 1 | 1996.55 |  | 1996.55 |  | 0
|  | Total: | 14360.17 |  | 14360.17 |  | 0

## RECAP #9186.05
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds
Project # 9186.05
Program code 918605 |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 105976.83
VendorA |  | 0 | 0 | 0
PM TIME |  | 4665.08 | 4665.08 | 0
Misc. |  | 101311.75 | 101311.75 | 0
Total Project Cost | 105976.83 | 105976.83 | 105976.83 | 0 | 0

## #9186.05 Funds Rec'd
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds
Project # 9186.05
Program code 918605 |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | CDR to move Revenue 9186.01 to 9186.05 | CDR 33524082810 | 2024-03-22 | 500000 | 500000
|  |  | Return funds to Agency per PM | IET 33524192800 | 2024-07-10 | -394023.17 | -394023.17
| Total Requested | 0 | Total Transferred |  |  | 105976.83 | 105976.83

## #9186.05 Vendor A
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds
Project # 9186.05
Program code 918605 |  |  | Major Program 4D08
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9186.05 PM TIME
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds
Project # 9186.05
Program code 918605 |  |  |  | Major Program 4D08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 909B
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4665.08 | 4665.08 |  |  | 4665.08
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for June 1-30, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 64.78 | 64.78 | 4600.3
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for June 1-30, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 584.9 | 649.68 | 4015.4
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for July 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 30.33 | 680.01 | 3985.07
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for July 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 193.7 | 873.71 | 3791.37
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for August 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 338.6 | 1212.31 | 3452.77
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for August 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 1625.9 | 2838.21 | 1826.87
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for October 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 79.89 | 2918.1 | 1746.98
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for October 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 644.7 | 3562.8 | 1102.28
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for December 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 78.29 | 3641.09 | 1023.99
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for December 1-31, 2023 from 9186.01 to 9186.05 |  | 4665.08 | 575.4 | 4216.49 | 448.59
CDE 33524082812 | 2024-03-22 | 2507 | CDE Finance Support for February 1-29, 2024 from 9186.01 to 9186.05 |  | 4665.08 | 66.39 | 4282.88 | 382.2
CDE 33524082812 | 2024-03-22 | 9500 | CDE DAS Services for February 1-29, 2024 from 9186.01 to 9186.05 |  | 4665.08 | 334.7 | 4617.58 | 47.5
CDE 33524082813 | 2024-03-22 | 2507 | CDE Space Planning from 9186.01 to 9186.05 |  | 4665.08 | 47.5 | 4665.08 | 2.2737e-13
[5 empty] | 4665.08 |  | 4665.08 | 2.2737e-13
[5 empty] | 4665.08 |  | 4665.08 | 2.2737e-13
[5 empty] | 4665.08 |  | 4665.08 | 2.2737e-13
|  |  | Totals: | 4665.08 |  | 4665.08 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: 9186.01/9186.02 - Additional project numbers and moving of contracts $John Elliott, Jennie 8:24 AM (53 minutes ago) to me For 9186.05 please use $6,000.00 For 9186.06 please leave at $0.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Fri, Mar 22, 2024 at 9:00 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Sorry PM time budget John On Fri, Mar 22, 2024 at 8:55 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Jennie What budget would you like on each of the projects 9186.05~.06? John 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (41 minutes ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000

## #9186.05 Misc
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - HHS Funds
Project # 9186.05
Program code 918605 |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services Move Expense from 9186.01 to 9186.05 | DAS2023081153 | 4061.25 | 4061.25
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023091153 | 1947.5 | 6008.75
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023101153 | 11542.5 | 17551.25
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Space Planning Services from 9186.01 to 9186.05 | DAS2023111153 | 5890 | 23441.25
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356884 | 220 | 23661.25
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356888 | 19386.84 | 43048.09
CDE 33524082814 | 2024-03-22 | 9500 | CNST | CDE Iowa Prison Industries V#(250DOCIPI00) from 9186.01 to 9186.05 | Inv. 356902 | 901 | 43949.09
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill July 2024 from 9186.01 to 9186.05 | Inv. 677169 | 2280 | 46229.09
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill August-November 2023 from 9186.01 to 9186.05 | Inv. 679044 & 684675 | 920 | 47149.09
CDE 33524082814 | 2024-03-22 | 2398 | CNST | CDE ICN Bill December 2023 from 9186.01 to 9186.05 | Inv. 686553 | 18060.34 | 65209.43
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Electrical Services from 9186.01 to 9186.05 | DAS2024081153 | 16034.04 | 81243.47
CDE 33524082814 | 2024-03-22 | 2507 |  | CDE Heating/Ventilation/Air Conditioning/Plumbing from 9186.01 to 9186.05 | DAS2024081153 | 20068.28 | 101311.75
101311.75
101311.75
101311.75
101311.75
101311.75
|  |  |  | Totals: |  | 101311.75

## RECAP #9186.06
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
| Program code 918606 |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursements
| Funds received per MOU | 761653.55
C | Shive Hattery |  | 7080 | 7080 | 0 |  | 0
| SP TIME |  | 44952.5 | 40086.83 | 4865.67 |  | 0
| Misc. |  | 3381.5 | 3381.5 | 0 |  | 0
C | Heartland Finishes |  | 28673 | 28673 | 0 |  | 0
C | Ralph Smith (P) |  | 83372 | 83372 | 0 |  | 0
C | Shyft Collective (P) |  | 81740 | 81740 | 0 |  | 0
C | All Makes (P) |  | 465280.24 | 465280.24 | 0 |  | 0
C | Conference Technologies Inc. (P) |  | 6115.98 | 6115.98 | 0 |  | 0
C | Control Installations of Iowa Inc. |  | 19298.5 | 19298.5 | 0 |  | 0
C | Waldinger Corporation |  | 16887.89 | 16887.89 | 0 |  | 0
C | Waldinger Corporation (2) |  | 2278.89 | 2278.89 | 0 |  | 0
C | American Marking (P) |  | 2593.05 | 2593.05 | 0 |  | 0
| Total Project Cost | 761653.55 | 761653.55 | 756787.88 | 4865.67 | 0 | 0

## #9186.06 Funds Rec'd
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | CDR to move Revenue 9186.02 to 9186.06 | CDR 33524082811 | 2024-03-22 | 775000 | 775000
|  |  | Return funds to Agency per PM | IET 33524192800 | 2024-07-10 | -13346.45 | -13346.45
| Total Requested | 0 | Total Transferred |  |  | 761653.55 | 761653.55

## #9186.06 Shive Hattery
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP1820335153
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523068802 | 2024-03-25 | Paper Contract Procore | 7080 | 7080 |  |  | 7080
GAX 33524283802 | 2023-10-10 | Inv. 4203302-6 (Split between 9186.02 and 9186.06) |  | 7080 | 7080 | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  |  |  | 7080 |  | 7080 | 0
|  | Totals: | 7080 |  | 7080 |  | 0
PO number above is assigned to Procore PO, but not created in I/3 due to Paper Contract.
Will create GAX payments as funds become available to charge against this project. Program code will be SLFRF.
Procore created contract:
|  | CO 1 (Split with 9186.02) | 4420 |  | 4420 |  | 0
|  | CO 3 (Split with 9186.02) | 2660 |  | 2660 |  | 0
|  | Total | 7080 |  | 7080 |  | 0

## #9186.06 PM TIME
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  |  | Major Program 4D08
SP TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 909C
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 44952.5 | 44952.5 |  |  | 44952.5
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 16862.5 | 16862.5 | 28090
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 4702.69 | 21565.19 | 23387.31
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 3942.5 | 25507.69 | 19444.81
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 4417.5 | 29925.19 | 15027.31
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 2303.75 | 32228.94 | 12723.56
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 2636.25 | 34865.19 | 10087.31
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 1448.75 | 36313.94 | 8638.56
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 23.75 | 36337.69 | 8614.81
CDE 33524082815 | 2024-03-22 | 2507 | Space Planning Service |  | 44952.5 | 3657.5 | 39995.19 | 4957.31
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 44952.5 | 10.84 | 40006.03 | 4946.47
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 44952.5 | 80.8 | 40086.83 | 4865.67
[5 empty] | 44952.5 |  | 40086.83 | 4865.67
[5 empty] | 44952.5 |  | 40086.83 | 4865.67
[5 empty] | 44952.5 |  | 40086.83 | 4865.67
|  |  | Totals: | 44952.5 |  | 40086.83 |  | 4865.67
Note on E9: Jurgenson, John [DAS]: 9186.01-.06 PM/SP budget time changes $John Elliott, Jennie 9:55 AM (39 minutes ago) to me Can you please make the following changes for PM/SP time. Increase SP Time in 9186.06 to total "contracted" of $45,000 Increase PM Time in 9186.05 to total "contracted" of $10,000 Move $50,000 from 9186.02 to 9186.04 Establish PM time of $50,000 in 9186.04 Move $50,000 from 9186.01 to 9186.03 Establish PM time of $50,000 in 9186.03 Increase SP Time (HHS) in 9186.02 to total "contracted" of $35,000 Increase PM Time (HHS) in 9186.01 to total "contracted" of $150,000

## #9186.06 Misc
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services | DAS2024021153 | 142.5 | 142.5
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 356931 | 603 | 745.5
CDE 33524082815 | 2024-03-22 | 9500 | CNST | T&M Services Inc V#(00003096009) | Inv. #DM2313769 | 157 | 902.5
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services | DAS2024061153 | 237.5 | 1140
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Conference Technologies V#(00003055217) | Inv. ST231000626 | 400 | 1540
CDE 33524082815 | 2024-03-22 | 2323 |  | Leasing Services | DAS2024071153 | 23.75 | 1563.75
CDE 33524082815 | 2024-03-22 | 9500 | CNST | Lint Van Lines V#(00002108977) | Inv. 16177 | 1224 | 2787.75
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Space Planning Services April 01-30, 2024 | DAS2024101153 | 475 | 3262.75
IET DAS202411115300001 | 2024-06-10 | 2507 |  | Space Planning Services May 01-31, 2024 | DAS2024111153 | 71.25 | 3334
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning Services October 01-31, 2024 | DAS2025041153 | 47.5 | 3381.5
3381.5
3381.5
|  |  |  | Totals: |  | 3381.5

## #9186.06 Heartland Finishes
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Heartland Finishes |  |  | Vendor:00002097604
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21421B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222801 | 2023-08-10 | DO I/3 | 28673 | 28673 |  |  | 28673
PRC 3352422PA2801 | 2023-10-11 | Inv. 16150 |  | 28673 | 28673 | 28673 | 0
CDE 33524307808 | 2023-11-03 | Correct Program Code on pay app |  | 28673 | 0 | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  |  |  | 28673 |  | 28673 | 0
|  | Totals: | 28673 |  | 28673 |  | 0 | FINAL
|  | Labor | 25725 |  | 25725 |  | 0
|  | Material | 2948 |  | 2948 |  | 0
|  | Total | 28673 |  | 28673 |  | 0

## #9186.06 Ralph Smith
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Ralph Smith |  |  | Vendor:00002106937
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21267
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222802A | 2023-11-06 | DO I/3 | 83372 | 83372 |  |  | 83372
PRC 3352422PA2802A | 2023-11-06 | Inv. 30044 |  | 83372 | 83372 | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  |  |  | 83372 |  | 83372 | 0
|  | Totals: | 83372 |  | 83372 |  | 0 | FINAL
|  | Labor | 34224 |  | 34224 |  | 0
|  | Material | 49148 |  | 49148 |  | 0
|  | Total | 83372 |  | 83372 |  | 0

## #9186.06 Shyft Collective
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Shyft Collective |  |  | Vendor:VS000000587
Acct. Codes-0506-335-DA22-9255 |  |  | MA#23200
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222803A | 2023-08-10 | DO I/3 | 81740 | 81740 |  |  | 81740
PRC 3352422PA2803A | 2023-12-07 | Inv. 0001REV |  | 81740 | 81740 | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  |  |  | 81740 |  | 81740 | 0
|  | Totals: | 81740 |  | 81740 |  | 0
|  | Wall and Ceiling repair and replace 85.00/hr | 7225 |  | 7225 |  | 0
|  | Material Handling Equipment Maintenance and Repair | 69730 |  | 69730 |  | 0
|  | CO #1 | 4785 |  | 4785 |  | 0
|  | Total | 81740 |  | 81740 |  | 0

## #9186.06 All Makes
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
All Makes |  |  | Vendor:00002110818
Acct. Codes-0506-335-DA22-9255 |  |  | MA$23148
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524222804A | 2023-08-10 | DO I/3 | 465280.24 | 465280.24 |  |  | 465280.24
PRC 3352422PA2804A | 2024-02-02 | Inv. 311116 |  | 465280.24 | 465280.24 | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  |  |  | 465280.24 |  | 465280.24 | 0
|  | Totals: | 465280.24 |  | 465280.24 |  | 0
|  | Furniture Office | 465280.24 |  | 465280.24 |  | 0
|  | Total | 465280.24 |  | 465280.24 |  | 0

## #9186.06 Conference Technologie
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Conference Technologies Inc. |  |  | Vendor:00002133110
Acct. Codes-0506-335-DA22-9255 |  |  | MA#22036B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524241801A | 2023-08-29 | DO I/3 | 4823.66 | 4823.66 |  |  | 4823.66
DO 33524241801A | 2023-10-03 | CO #1 | 1292.32 | 6115.98 |  | 0 | 6115.98
PRC 3352424PA1801A | 2024-01-09 | Inv. JC134320 |  | 6115.98 | 6115.98 | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  |  |  | 6115.98 |  | 6115.98 | 0
|  | Totals: | 6115.98 |  | 6115.98 |  | 0
|  | Video and Audio Systems | 4823.66 |  | 4823.66 |  | 0
|  | CO #1 | 1292.32 |  | 1292.32 |  | 0
|  | Total | 6115.98 |  | 6115.98 |  | 0

## #9186.06 Control Installations
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Control Installations |  |  | Vendor:00002115535
Acct. Codes-0506-335-DA22-9255 |  |  | MA#20360A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524258800A | 2023-09-15 | DO I-3 | 23576 | 23576 |  |  | 23576
DO 33524258800A | 2024-02-15 | CO #1 | 0 | 23576 |  | 0 | 23576
PRC 3352425PA8800A | 2024-02-15 | Inv. 144266 | -4277.5 | 19298.5 | 19298.5 | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  |  |  | 19298.5 |  | 19298.5 | 0
|  | Totals: | 19298.5 |  | 19298.5 |  | 0
|  | Building Automation Products | 8467.1 |  | 8467.1 |  | 0
|  | Building Automation Services | 10831.4 |  | 10831.4 |  | 0
|  | Total | 38597 |  | 38597 |  | 0

## #9186.06 Waldinger Corporation
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Waldinger |  |  | Vendor:00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | MA#21012A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524283803A | 2023-10-10 | DO I-3 | 27723 | 27723 |  |  | 27723
PRC 3352428PA3803A | 2024-03-06 | Inv. 7142120-1 | -10835.11 | 16887.89 | 16887.89 | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  |  |  | 16887.89 |  | 16887.89 | 0
|  | Totals: | 16887.89 |  | 16887.89 |  | 0 | FINAL
|  | Labor | 15554.43 |  | 15554.43 |  | 0
|  | Materials | 1333.46 |  | 1333.46 |  | 0
|  | Total | 33775.78 |  | 33775.78 |  | 0

## #9186.06 Waldinger Corporat (2)
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
Waldinger Corp. (2) |  |  | Vendor:00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | MA#20452A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524303803A | 2023-10-30 | DO I-3 (Unencumbered) | 2278.89 | 2278.89 |  |  | 2278.89
PRC 3352430PA3803A | 2024-02-26 | Inv. 75272E-001 |  | 2278.89 | 2278.89 | 2278.89 | 0
DO 33524303803A | 2024-07-26 | Close DO per PM |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  |  |  | 2278.89 |  | 2278.89 | 0
|  | Totals: | 2278.89 |  | 2278.89 |  | 0
|  | Labor | 1507.55 |  | 1507.55 |  | 0
|  | Materials | 771.34 |  | 771.34 |  | 0
|  | Total | 2278.89 |  | 2278.89 |  | 0

## #9186.06 American Marking
DHS CC Strategic Space Planning (Hoover 1st Floor Auditor Office) - SLFRF Funds
Project # 9186.06
Program code 918606 |  |  | Major Program 4D08
American Marking |  |  | Vendor:00003113118
Acct. Codes-0506-335-DA22-9255 |  |  | MA#240051900
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524085801A | 2024-03-25 | DO IA Advantage (Unencumbered) | 2593.05 | 2593.05 |  |  | 2593.05
DO 3352408PA5801A | 2024-05-13 | Inv. 0035822 |  | 2593.05 | 2593.05 | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  |  |  | 2593.05 |  | 2593.05 | 0
|  | Totals: | 2593.05 |  | 2593.05 |  | 0
PO number above is assigned to Procore PO, and created in IA Advantage as Unencumbered due to Paper Contract.
Will create payments as funds become available to charge against this project.
|  |  | 2593.05 |  | 2593.05 |  | 0
|  | Total | 2593.05 |  | 2593.05 |  | 0

## RECAP #9186.07
DHS CC Strategic Space Planning (Hoover B Level) - SLFRF Funds
Project # 9186.07
Program code 918607 |  |  | Major Program 4D08
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 15000
VendorA |  | 0 | 0 | 0
PM TIME |  | 10000 | 421.35 | 9578.65
Misc. |  | 1722.5 | 1722.5 | 0
Total Project Cost | 15000 | 11722.5 | 2143.85 | 9578.65 | 3277.5

## #9186.07 Funds Rec'd
DHS CC Strategic Space Planning (Hoover B Level) - SLFRF Funds
Project # 9186.07
Program code 918607 |  |  | Major Program 4D08
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | CDR to move Revenue 9186.02 to 9186.07 | CDR 33524170801 | 2024-06-18 | 15000 | 15000
| Total Requested | 0 | Total Transferred |  |  | 15000 | 15000

## #9186.07 Vendor A
DHS CC Strategic Space Planning (Hoover B Level) - SLFRF Funds
Project # 9186.07
Program code 918607 |  |  | Major Program 4D08
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9186.07 PM TIME
DHS CC Strategic Space Planning (Hoover B Level) - SLFRF Funds
Project # 9186.07
Program code 918607 |  |  |  | Major Program 4D08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 909N
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10000 | 15.92 | 15.92 | 9984.08
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10000 | 80.8 | 96.72 | 9903.28
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10000 | 10.42 | 107.14 | 9892.86
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10000 | 91.8 | 198.94 | 9801.06
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10000 | 11.52 | 210.46 | 9789.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10000 | 77.5 | 287.96 | 9712.04
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 16.59 | 304.55 | 9695.45
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 116.8 | 421.35 | 9578.65
[5 empty] | 10000 |  | 421.35 | 9578.65
[5 empty] | 10000 |  | 421.35 | 9578.65
[5 empty] | 10000 |  | 421.35 | 9578.65
[5 empty] | 10000 |  | 421.35 | 9578.65
|  |  | Totals: | 10000 |  | 421.35 |  | 9578.65
Note on E9: Huggins, Joni [DAS]: 9186.07 Hoover B level $Joni Elliott, Jennie Fri, Aug 30, 3:15 PM (5 days ago) to me Please establish PM time in 9186.07 for $10,000 Thank you, Jennie Elliott

## #9186.07 Misc
DHS CC Strategic Space Planning (Hoover B Level) - SLFRF Funds
Project # 9186.07
Program code 918607 |  |  |  | Major Program 4D08
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Space Planning Services September 01-30, 2024 | Inv. DAS2025031153 | 593.75 | 593.75
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Services December 01-31, 2024 | Inv. DAS2025061153 | 308.75 | 902.5
PRCI 33525035907 | 2025-02-04 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357145 | 677.5 | 1580
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Services March 01-31, 2025 | DAS2025091153 | 142.5 | 1722.5
1722.5
1722.5
1722.5
1722.5
1722.5
1722.5
1722.5
1722.5
|  |  |  | Totals: |  | 1722.5

## RECAP #9203.00
DOC NCCF Treatment Center EIFS Replacement
Project # 9203.00
| Program code 920300 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 24510.47
C | Wilson Group |  | 24510.47 | 24510.47 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 24510.47 | 24510.47 | 24510.47 | 0 | 0
Closed 12/22/23

## #9203.00 Funds Rec'd
DOC NCCF Treatment Center EIFS Replacement
Project # 9203.00
Program code 920300 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - James T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 221020213 | 2021-10-20 | 25000 | 25000
|  |  | MOU Amend 1 | IET 221221214 | 2021-12-21 | 2500 | 2500
|  |  | Return FY22 funds to agency | IET 33522215811 | 2022-08-03 | -27500 | -27500
|  |  | Received FY23 funds from agency | IET 230831221 | 2022-08-31 | 27500 | 27500
|  |  | Return FY23 funds to agency | IET 33523227908 | 2023-08-15 | -4113.98 | -4113.98
|  |  | Received FY24 funds from agency | IET 240831235 | 2023-08-31 | 4113.98 | 4113.98
|  |  | Transferred with incorrect Unit | CDR 33524244900 | 2023-09-01 | 0 | 0
|  |  | Return Funds to Agency | IET 33524356805 | 2023-12-22 | -2989.53 | -2989.53
| Total Requested | 0 | Total Transferred |  |  | 24510.47 | 24510.47

## #9203.00 Wilson Group
DOC NCCF Treatment Center EIFS Replacement
Project # 9203.00
Program code 920300 |  |  | Major Program 4E02
Wilson Group |  |  | Vendor: 00003053970
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B: 920300-01
Project Manager - James T |  |  | Activity code: BRUM
Split with MM21
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522294800 | 2021-10-19 | PO Procore | 22125 | 22125 |  |  | 22125
PRC 3352229PA4800 | 2021-11-22 | Inv. 9203.007-1 (100% to MM21) |  | 22125 | 0 | 0 | 22125
PO 33522294800 | 2022-01-04 | CO 1 (Split between DA22 and MM21) | 2491.86 | 24616.86 |  | 0 | 24616.86
PO 33522294800 | 2022-01-25 | CO 2 (100% to MM21) | 0 | 24616.86 |  | 0 | 24616.86
PRC 3352229PB4800 | 2022-04-06 | Inv. 9203.007-2 (100% to MM21) |  | 24616.86 | 0 | 0 | 24616.86
PO 33522294800 | 2022-05-18 | CO 3 (100% DA22) | -648.24 | 23968.62 |  | 0 | 23968.62
PRC 3352229PC4800 | 2022-07-07 | Inv. 9203.007-3 (100% to MM21) |  | 23968.62 | 0 | 0 | 23968.62 |  | FY22
PO 33523294800 | 2022-08-31 | Rolled to FY23 | 0 | 23968.62 |  | 0 | 23968.62
PRC 3352329PD4800 | 2022-08-08 | Inv. 9203.007-4 (100% to MM21) |  | 23968.62 | 0 | 0 | 23968.62
PRC 3352329PE4800 | 2022-09-07 | Inv. 9203.007-5 (split between MM21 & DA22) |  | 23968.62 | 8419.37 | 8419.37 | 15549.25 | 443.13
PO 33523294800 | 2022-09-15 | CO #4 (split between MM21 & DA22) | 648.24 | 24616.86 |  | 8419.37 | 16197.49
PO 33523294800 | 2022-09-27 | CO #5 (100% to MM21) | 0 | 24616.86 |  | 8419.37 | 16197.49
PRC 3352329PF4800 | 2022-10-11 | Inv. 9203.007-6 (split between MM21 & DA22) |  | 24616.86 | 12616.08 | 21035.45 | 3581.41 | 1107.13
PO 33523294800 | 2022-10-31 | CO #7 (100% to MM21) | 0 | 24616.86 |  | 21035.45 | 3581.41
PRC 3352329PG4800 | 2022-11-14 | Inv. 9203.00-7 (Split Between DA22 &MM21) |  | 24616.86 | 2456.96 | 23492.41 | 1124.45 | 1236.44
PO 33523294800 | 2022-11-18 | CO #8 (100% to MM21) | 0 | 24616.86 |  | 23492.41 | 1124.45
PO 33523294800 | 2022-12-09 | CO #9 (No cost) | 0 | 24616.86 |  | 23492.41 | 1124.45
CDE 33523348900 | 2022-12-14 | Moving Expense from MM21 to DA22 | -106.39 | 24510.47 | -106.39 | 23386.02 | 1124.45 | 1230.84
PRC 3352329PH4800 | 2022-12-05 | Inv. 9203.00-8 (100% to MM21) |  | 24510.47 | 0 | 23386.02 | 1124.45 | 1230.84
PRC 3352329PI4800 | 2023-01-12 | Inv. 9203.00-9 (100% to MM21) |  | 24510.47 | 0 | 23386.02 | 1124.45 | 1230.84
PO 33523294800 | 2023-02-13 | CO #10 (No cost) | 0 | 24510.47 |  | 23386.02 | 1124.45
PO 33523294800 | 2023-05-16 | CO #11 (100% to MM21) | 0 | 24510.47 |  | 23386.02 | 1124.45
PO 33523294800 | 2023-06-21 | CO #12 (No Cost) | 0 | 24510.47 |  | 23386.02 | 1124.45 |  | FY23
PO 33524294800 | 2023-08-28 | Roll to FY24 | 0 | 24510.47 |  | 23386.02 | 1124.45
PO 33524294800 | 2023-09-06 | CO #13 (100% to MM21) | 0 | 24510.47 |  | 23386.02 | 1124.45 | 1124.45 | edited per CO13
PRC 3352429PJ4800 | 2023-10-26 | Inv. 9203.00-10 (100% to MM21) |  | 24510.47 | 0 | 23386.02 | 1124.45
PRC 3352429PK4800 | 2023-10-27 | Inv. 9203.00-11 - Retainage(Split Between MM21 & DA22) |  | 24510.47 | 1124.45 | 24510.47 | 0
|  | Totals: | 24510.47 |  | 24510.47 |  | 0
|  | MM21 | 397700.23 |  | 397700.23 |  | 0
|  | Total Contract: | 422210.7 |  | 422210.7 |  | 0
CO #6 was an internal only, did not come through Procore
6/30/23*CDE moved expense but not retainage due. Will pay $1124.45 Retainage out of DA22 and remainder from MM21.

## #9203.00 PM TIME
DOC NCCF Treatment Center EIFS Replacement
Project # 9203.00
Program code 920300 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - James T |  |  |  | eDAS C014
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 381.75 | 381.75 | 381.75 | 381.75 | 0
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -381.75 | 0 | -381.75 | 0 | 0
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 2022 | 252.12 | 252.12 | 252.12 | 252.12 | 0
CDE 33523075200 | 2023-03-07 | 9500 | Move PM time to 9997.23 MM23 | -252.12 | 0 | -252.12 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9203.00 Misc
DOC NCCF Treatment Center EIFS Replacement
Project # 9203.00
Program code 920300 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9204.00
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
| Program code 920400 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 64000
C | MTS Contracting |  | 40000 | 40000 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
C | For Sure Roofing |  | 24000 | 24000 | 0
| Total Project Cost | 64000 | 64000 | 64000 | 0 | 0
Closed 05/31/2023

## #9204.00 Funds Rec'd
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
Program code 920400 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET032222100 | 2022-03-22 | 64000 | 64000
|  |  | Return FY22 Funds to Agency | IET 33522216805 | 2022-08-04 | -23324.03 | -23324.03
|  |  | Received FY23 Funds from Agency | IET081122100 | 2022-08-15 | 23324.03 | 23324.03
| Total Requested | 0 | Total Transferred |  |  | 64000 | 64000

## #9204.00 MTS Contracting
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
Program code 920400 |  |  | Major Program 4B03
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #920400-02
Project Manager - Brad T |  |  | Activity code: BRUM
Split with MM21
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522087800 | 2022-03-25 | PO Procore | 40000 | 40000 |  |  | 40000
PRC 3352208PA7800 | 2022-06-21 | Inv. 22-4240A-1 (split between MM21 & DA22) |  | 40000 | 19693.5 | 19693.5 | 20306.5 | 1036.5 | FY22
PO 33523087800 | 2022-08-15 | Rolled to FY23 | 0 | 40000 |  | 19693.5 | 20306.5
PRC 3352308PB7800 | 2022-11-14 | Inv. 22-4240B (split between MM21 & DA22) |  | 40000 | 15142.05 | 34835.55 | 5164.45 | 1833.45
PRC 3352308PC7800 | 2023-01-10 | Inv. 22-4240C (split between MM21 & DA22) |  | 40000 | 3164.45 | 38000 | 2000 | 2000
PRC 3352308PD7800 | 2023-01-26 | Inv. 22-4240D (100% to MM21) |  | 40000 | 0 | 38000 | 2000 | 2000
PRC 3352308PE7800 | 2023-03-01 | Inv. 22-4240 Retainage(Split Between MM21&DA22) |  | 40000 | 2000 | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  |  |  | 40000 |  | 40000 | 0
|  | Totals | 40000 |  | 40000 |  | 0
|  | MM21 | 91225 |  | 91225 |  | 0
|  | Total Contract: | 131225 |  | 131225 |  | 0

## #9204.00 PM TIME
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
Program code 920400 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T |  |  |  | eDAS 723X
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 208.13 | 208.13 | 208.13 | 208.13 | 0
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -208.13 | 0 | -208.13 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9204.00 Misc
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
Program code 920400 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9204.00 For Sure Roofing
DVA IVH Dack Sundeck Roof Replacement
Project # 9204.00
Program code 920400 |  |  | Major Program 4B03
For Sure Roofing |  |  | Vendor: 00003081739
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #920400-02
Project Manager - Brad T |  |  | Activity code: BRUM
Split with MM21
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522087801 | 2022-03-25 | PO Procore | 24000 | 24000 |  |  | 24000
PRC 3352208PA7801 | 2022-07-26 | Inv. 9204.00-01 (split between MM21 & DA22) |  | 24000 | 20982.47 | 20982.47 | 3017.53 | 1104.34 | FY22
PO 33523087801 | 2022-08-15 | Rolled to FY23 | 0 | 24000 |  | 20982.47 | 3017.53
PRC 3352308PB7801 | 2023-01-10 | Inv. 9204.00-02 (split between MM21 & DA22) |  | 24000 | 1817.54 | 22800.01 | 1199.99 | 1199.99
PRC 3352308PC7801 | 2023-05-18 | Inv. 9204.00-03 - Retainage (split between MM21 & DA22) |  | 24000 | 1199.99 | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  |  |  | 24000 |  | 24000 | 0
|  | Totals: | 24000 |  | 24000 |  | 0
|  | MM21 | 56118 |  | 56118 |  | 0
|  | Total Contract: | 80118 |  | 80118 |  | 0

## #9213.00 Funds Rec'd
IPI FDCF Bldg I Wall Demo
Project # 9213.00
Program code 921300 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Received FY22 funds from agency | IET 0A4645082421 | 2021-08-30 | 3571.25 | 3571.25
|  |  | Funds transferred with incorrect unit code | CDR 33522243800 | 2021-08-31 | -3571.25 | -3571.25
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #9216.00
DHS STS Cottage Dorm Conversion
Project # 9216.00
| Program code 921600 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 6385054.11
C | Story Construction |  | 26460.86 | 26460.86 | 0
C | PM TIME |  | 50525.54 | 50525.54 | 0
C | Builders Risk |  | 0 | 0 | 0
C | Misc. |  | 10501.46 | 10501.46 | 0
C | OPN Architects |  | 304345 | 304345 | 0
C | Controlled Asbestos, Inc. |  | 45610.08 | 45610.08 | 0
C | Story Construction (2) |  | 831199.32 | 831199.32 | 0
C | Tricon General Contractor |  | 2174998.18 | 2174998.18 | 0
C | Tri-City Electric |  | 1323301.79 | 1323301.79 | 0
C | Young Plumbing |  | 1512164.55 | 1512164.55 | 0
C | Norix Group |  | 81072 | 81072 | 0
C | Iowa Prison Industries |  | 10474.48 | 10474.48 | 0
C | Siemens-Damper Controls |  | 11200.85 | 11200.85 | 0
C | SystemWorks |  | 3200 | 3200 | 0
| Total Project Cost | 6385054.11 | 6385054.11 | 6385054.11 | 0 | 0
Closed 03/31/25

## #9216.00 Funds Rec'd
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 413AL 07092021 | 2021-07-26 | 6500000 | 6500000
|  |  | Return FY22 Funds to Agency | IET 33522222901 | 2022-08-10 | -6000976.83 | -6000976.83
|  |  | Received FY23 Funds From Agency | IET 415ML238002 082622 | 2022-08-26 | 6000976.83 | 6000976.83
|  |  | Return FY23 Funds to Agency | IET 33523228903 | 2023-08-16 | -1441294.8 | -1441294.8
|  |  | Received FY24 Funds From Agency | IET 33523228903B | 2023-09-07 | 1441294.8 | 1441294.8
|  |  | Return FY24 Funds to Agency | IET 33524226920 | 2024-08-13 | -124302.87 | -124302.87
|  |  | Return FY24 Funds to Agency Correction | IET 33524226920A | 2024-08-21 | -2819.32 | -2819.32
|  |  | Received FY25 Funds From Agency | IET 405EL25264007 | 2024-09-23 | 20000 | 20000
|  |  | Return Funds to Agency - Closing Project | IET 33525090916 | 2025-03-31 | -7823.7 | -7823.7
| Total Requested | 0 | Total Transferred |  |  | 6385054.11 | 6385054.11

## #9216.00 Story Construction
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B: RFP0215335062-Story9112015
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522216800 | 2021-08-04 | PO Procore | 15387.54 | 15387.54 |  |  | 15387.54
PRC 3352221PA6800 | 2021-09-15 | Inv. 32751 |  | 15387.54 | 2007.48 | 2007.48 | 13380.06
PRC 3352221PB6800 | 2021-10-15 | Inv. 32798 |  | 15387.54 | 1710.22 | 3717.7 | 11669.84
PRC 3352221PC6800 | 2021-11-17 | Inv. 32840 |  | 15387.54 | 2172.98 | 5890.68 | 9496.86
PRC 3352221PD6800 | 2021-12-16 | Inv. 32893 |  | 15387.54 | 2137.35 | 8028.03 | 7359.51
PO 33522216800 | 2021-12-16 | CO #1 | 5850 | 21237.54 |  | 8028.03 | 13209.51
PRC 3352221PE6800 | 2022-01-18 | Inv. 32936 |  | 21237.54 | 2686.22 | 10714.25 | 10523.29
PRC 3352221PF6800 | 2022-02-17 | Inv. 32978 |  | 21237.54 | 7851.32 | 18565.57 | 2671.97
PO 33522216800 | 2022-02-18 | CO #2 | 7850.17 | 29087.71 |  | 18565.57 | 10522.14
PRC 3352221PG6800 | 2022-03-23 | Inv. 33020-Final PC | -2626.85 | 26460.86 | 7895.29 | 26460.86 | 0
|  |  |  | 26460.86 |  | 26460.86 | 0
|  |  |  | 26460.86 |  | 26460.86 | 0
|  |  |  | 26460.86 |  | 26460.86 | 0
|  | Totals: | 26460.86 |  | 26460.86 |  | 0 | Final Invoice
|  | CM Services | 15013.14 |  | 15013.14 |  | 0
|  | Reimbursables | 224.64 |  | 224.64 |  | 0
|  | CO #1 | 3450 |  | 3450 |  | 0
|  | CO #2 | 7773.08 |  | 7773.08 |  | 0
|  | Total: | 26460.86 |  | 26460.86 |  | 0

## #9216.00 PM TIME
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-0304
Project Manager - Jennifer K. |  |  |  | eDAS S07T
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 50525.54 | 50525.54 |  |  | 50525.54
IET DAS202201115300001 | 2021-08-06 |  | PM-Jul. 01-Jul. 22, 2021 |  | 50525.54 | 175 | 175 | 50350.54
IET DAS202202115300001 | 2021-09-08 |  | PM-July 23-August 19, 2021 |  | 50525.54 | 425 | 600 | 49925.54
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 50525.54 | 1800 | 2400 | 48125.54
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 50525.54 | 1075 | 3475 | 47050.54
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 50525.54 | 1575 | 5050 | 45475.54
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30,2021 |  | 50525.54 | 1325 | 6375 | 44150.54
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 50525.54 | 1150 | 7525 | 43000.54
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 50525.54 | 1475 | 9000 | 41525.54
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 50525.54 | 1400 | 10400 | 40125.54
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 50525.54 | 1175 | 11575 | 38950.54
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 50525.54 | 1275 | 12850 | 37675.54
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 50525.54 | 500 | 13350 | 37175.54
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 50525.54 | 575 | 13925 | 36600.54
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 50525.54 | -575 | 13350 | 37175.54
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 50525.54 | 632.5 | 13982.5 | 36543.04
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 50525.54 | 1265 | 15247.5 | 35278.04
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 50525.54 | 1952.5 | 17200 | 33325.54
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 50525.54 | 1072.5 | 18272.5 | 32253.04
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 50525.54 | 1347.5 | 19620 | 30905.54
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 322.81 | 50848.35 | 322.81 | 19942.81 | 30905.54
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -322.81 | 50525.54 | -322.81 | 19620 | 30905.54
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1167.88 | 51693.42 | 1167.88 | 20787.88 | 30905.54
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1167.88 | 50525.54 | -1167.88 | 19620 | 30905.54
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 1218.75 | 51744.29 | 1218.75 | 20838.75 | 30905.54
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -1218.75 | 50525.54 | -1218.75 | 19620 | 30905.54
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 843.08 | 51368.62 | 843.08 | 20463.08 | 30905.54
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -843.08 | 50525.54 | -843.08 | 19620 | 30905.54
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 1348.37 | 51873.91 | 1348.37 | 20968.37 | 30905.54
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1348.37 | 50525.54 | -1348.37 | 19620 | 30905.54
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 50525.54 | 715 | 20335 | 30190.54
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 50525.54 | 202.87 | 20537.87 | 29987.67
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 50525.54 | 1778.51 | 22316.38 | 28209.16
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: October 2022 | 66.64 | 50592.18 | 66.64 | 22383.02 | 28209.16
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -66.64 | 50525.54 | -66.64 | 22316.38 | 28209.16
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 50525.54 | 262.34 | 22578.72 | 27946.82
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 50525.54 | 1590.85 | 24169.57 | 26355.97
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 50525.54 | 314.18 | 24483.75 | 26041.79
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 50525.54 | 1381.93 | 25865.68 | 24659.86
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 50525.54 | 333.93 | 26199.61 | 24325.93
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 50525.54 | 1963.1 | 28162.71 | 22362.83
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 50525.54 | 210.53 | 28373.24 | 22152.3
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 50525.54 | 1475.1 | 29848.34 | 20677.2
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 50525.54 | 209.38 | 30057.72 | 20467.82
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 50525.54 | 1784.6 | 31842.32 | 18683.22
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 50525.54 | 194.11 | 32036.43 | 18489.11
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 50525.54 | 1238.6 | 33275.03 | 17250.51
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 50525.54 | 456.88 | 33731.91 | 16793.63
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 50525.54 | 2550.6 | 36282.51 | 14243.03
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 50525.54 | 253.25 | 36535.76 | 13989.78
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 50525.54 | 1759.5 | 38295.26 | 12230.28
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 50525.54 | 135.56 | 38430.82 | 12094.72
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 50525.54 | 1088.9 | 39519.72 | 11005.82
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 50525.54 | 91.92 | 39611.64 | 10913.9
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 50525.54 | 695.4 | 40307.04 | 10218.5
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 50525.54 | 158.8 | 40465.84 | 10059.7
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 50525.54 | 1165.6 | 41631.44 | 8894.1
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 50525.54 | 71.8 | 41703.24 | 8822.3
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 50525.54 | 630 | 42333.24 | 8192.3
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 50525.54 | 192.23 | 42525.47 | 8000.07
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 50525.54 | 970.2 | 43495.67 | 7029.87
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 50525.54 | 54.65 | 43550.32 | 6975.22
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 50525.54 | 414.8 | 43965.12 | 6560.42
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 50525.54 | 147.27 | 44112.39 | 6413.15
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 50525.54 | 1311.6 | 45423.99 | 5101.55
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 50525.54 | 109.14 | 45533.13 | 4992.41
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 50525.54 | 903.6 | 46436.73 | 4088.81
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 50525.54 | 47.61 | 46484.34 | 4041.2
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 50525.54 | 435.7 | 46920.04 | 3605.5
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 50525.54 | 118.56 | 47038.6 | 3486.94
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 50525.54 | 1291.1 | 48329.7 | 2195.84
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 50525.54 | 85.35 | 48415.05 | 2110.49
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 50525.54 | 435.2 | 48850.25 | 1675.29
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 50525.54 | 18.46 | 48868.71 | 1656.83
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 50525.54 | 166.1 | 49034.81 | 1490.73
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 50525.54 | 19.67 | 49054.48 | 1471.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 50525.54 | 132.6 | 49187.08 | 1338.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 50525.54 | 9.7 | 49196.78 | 1328.76
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 50525.54 | 62.3 | 49259.08 | 1266.46
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 50525.54 | 41.07 | 49300.15 | 1225.39
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 50525.54 | 410.1 | 49710.25 | 815.29
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 50525.54 | 7.6 | 49717.85 | 807.69
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 50525.54 | 84.2 | 49802.05 | 723.49
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 50525.54 | 135.79 | 49937.84 | 587.7
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 50525.54 | 587.7 | 50525.54 | 1.0232e-11
[5 empty] | 50525.54 |  | 50525.54 | 1.0232e-11
[5 empty] | 50525.54 |  | 50525.54 | 1.0232e-11
[5 empty] | 50525.54 |  | 50525.54 | 1.0232e-11
|  |  | Totals: | 50525.54 |  | 50525.54 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: DA22 9216.00 Budgets Jennifer Kleene, Jennifer 12:52 PM (9 hours ago) to me Please create a PM Time budget of $15,000.00 and a Builder's Risk budget of $7,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative PM Time Changes $Joni Kleene, Jennifer 2:50 PM (2 minutes ago) to me, Scott Please increase the PM Time budget for DA20 9167.00 by $440.00. Please increase the PM Time budget for DA21 9215.00 by $880.00. Please increase the PM Time budget for DA22 9216.00 by $6,600.00. Please create a PM Time budget for MM21 9298.00 for $6,000.00. Please create a PM Time budget for MM21 9299.00 for $4,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes $Joni Kleene, Jennifer Fri, Feb 3, 4:46 PM (3 days ago) to me, Scott Please increase the PM Time budget for DA22 9216.00 by $10,000.00. Please increase the PM Time budget for MM22 9217.00 by $1,100.00. Please increase the PM Time budget for MM22 9279.00 by $4,400.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 10:28 AM (2 hours ago) to me Sorry about that. Please increase the PM Time for DA22 9216.00 by $14,960.00 and increase the PM Time for MM23 9279.20 by $22,440.00. Regards, Jennifer PM Time Changes $Joni Kleene, Jennifer 11:59 AM (31 minutes ago) to me, Scott For MM22 9244.00, please increase the PM Time budget by $4,000.00 For MM23 9268.01, please increase the PM Time budget by $8,800.00 For DA22 9216.00, please increase the PM Time budget by $4,000.00 For DA23 9293.00, please increase the PM Time budget by $3,500.00 For DA24 9377.00, please increase the PM Time budget by $4,400.00 Please Close DA22 Project 9216.00 External $Joni Kleene, Jennifer Mar 29, 2025, 10:45 AM (2 days ago) to me, Christopher, Robert All invoices have been paid and all DAS costs have posted, so please close DA22 project 9216.00 DHS STS Cottage Dorm Conversion and return the remaining $7,823.70 to STS. Regards, Jennifer

## #9216.00 BR
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  |  | Major Program 4B02
Builders Risk |  |  |  | Internal documents
Builders Risk = 9501
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Activity Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: DA22 9216.00 Budgets Jennifer Kleene, Jennifer 12:52 PM (9 hours ago) to me Please create a PM Time budget of $15,000.00 and a Builder's Risk budget of $7,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative 1 of 4 DA22 9216.00 $John Kleene, Jennifer 7:47 AM (14 minutes ago) to me Please decrease the line item for Builders Risk by $3,336.00 and delete if possible. This was charged in the miscellaneous tab instead. Regards, Jennifer

## #9216.00 Misc
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522347902 | 2021-12-13 | 9500 | CMGR | ATC Group V#(00002134218) | Inv. 2387669-Final | 2408.75 | 2408.75
PRC 33522084901 | 2022-03-25 | 9500 | CNST | Rapids Reproductions V#(900002111375) | Inv. 419295-0 | 1456.08 | 3864.83
PRC 33522088900 | 2022-03-29 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 419240-0 | 31.88 | 3896.71
GAX 33522111900 | 2022-04-20 | 9500 | CNST | System Works V#(00002144353) | Inv. 10711-Final | 2175 | 6071.71
GAX 33522158800 | 2022-06-06 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 654720 | 3336 | 9407.71
GAX 33523019903 | 2023-01-19 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2477184-Final | 567.5 | 9975.21
PRC 33523188801 | 2023-07-07 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2507899 | 526.25 | 10501.46
10501.46
10501.46
10501.46
10501.46
10501.46
|  |  |  | Totals: |  | 10501.46

## #9216.00 OPN Architects
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: 921600-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522270802 | 2021-09-24 | PO Procore | 252695 | 252695 |  |  | 252695
PRC 3352227PA0802 | 2021-10-04 | Inv. 21830000-1 |  | 252695 | 5460 | 5460 | 247235
PRC 3352227PB0802 | 2021-11-30 | Inv. 21830000-2 |  | 252695 | 40221 | 45681 | 207014
PO 33522270802 | 2021-12-02 | CO 1 | 41000 | 293695 |  | 45681 | 248014
PRC 3352227PC0802 | 2021-12-06 | Inv. 21830000-3 |  | 293695 | 35660.08 | 81341.08 | 212353.92
PRC 3352227PD0802 | 2022-01-13 | Inv. 21830000-4 |  | 293695 | 104371.38 | 185712.46 | 107982.54
PRC 3352227PE0802 | 2022-02-09 | Inv. 21830000-5 |  | 293695 | 14067.09 | 199779.55 | 93915.45
PRC 3352227PF0802 | 2022-03-29 | Inv. 21830000-6 |  | 293695 | 11299 | 211078.55 | 82616.45
PRC 3352227PG0802 | 2022-04-08 | Inv. 21830000-7 |  | 293695 | 10918.48 | 221997.03 | 71697.97
PRC 3352227PH0802 | 2022-05-11 | Inv. 21830000-8 |  | 293695 | 7223 | 229220.03 | 64474.97
PRC 3352227PI0802 | 2022-06-24 | Inv. 21830000-9 |  | 293695 | 4372.83 | 233592.86 | 60102.14
PRC 3352227PJ0802 | 2022-07-11 | Inv. 21830000-10 |  | 293695 | 4724.54 | 238317.4 | 55377.6 | FY22
PO 33523270802 | 2022-08-29 | Roll to FY23 | 0 | 293695 |  | 238317.4 | 55377.6
PRC 3352327PK0802 | 2022-08-29 | Inv. 21830000-11 |  | 293695 | 3867.43 | 242184.83 | 51510.17
PRC 3352327PL0802 | 2022-09-20 | Inv. 21830000-12 |  | 293695 | 2818.8 | 245003.63 | 48691.37
PRC 3352327PM0802 | 2022-10-05 | Inv. 21830000-13 |  | 293695 | 3797.52 | 248801.15 | 44893.85
PRC 3352327PN0802 | 2022-11-03 | Inv. 21830000-14 |  | 293695 | 4752.94 | 253554.09 | 40140.91
PRC 3352327PO0802 | 2022-12-06 | Inv. 21830000-15 |  | 293695 | 5637.6 | 259191.69 | 34503.31
PRC 3352327PP0802 | 2023-01-17 | Inv. 21830000-16 |  | 293695 | 5746.63 | 264938.32 | 28756.68
PRC 3352327PQ0802 | 2023-02-10 | Inv. 21830000-17 |  | 293695 | 2779 | 267717.32 | 25977.68
PO 33523270802 | 2023-02-21 | CO 2 (No Cost) | 0 | 293695 |  | 267717.32 | 25977.68
PRC 3352327PR0802 | 2023-04-12 | Inv. 21830000-18 |  | 293695 | 4698.36 | 272415.68 | 21279.32
PO 33523270802 | 2023-06-13 | CO 3 | 8750 | 302445 |  | 272415.68 | 30029.32
PRC 3352327PS0802 | 2023-07-24 | Inv. 21830000-19 |  | 302445 | 7012.31 | 279427.99 | 23017.01 | FY23
PO 33524270802 | 2023-08-28 | Roll to FY24 | 0 | 302445 |  | 279427.99 | 23017.01
PRC 3352427PT0802 | 2023-09-26 | Inv. 21830000-20 |  | 302445 | 2786.92 | 282214.91 | 20230.09
PO 33524270802 | 2023-11-21 | CO 4 | 1900 | 304345 |  | 282214.91 | 22130.09
PRC 3352427PU0802 | 2024-02-12 | Inv. 21830000-21 |  | 304345 | 18480.09 | 300695 | 3650
PRC 3352427PV0802 | 2024-07-18 | Inv. 21830000-22 |  | 304345 | 3550 | 304245 | 100 | FY24
PO 33525270802 | 2024-08-26 | Roll to FY25 |  | 304345 |  | 304245 | 100
PRC 3352527PW0802 | 2025-03-05 | Inv. 21830000-23 Final |  | 304345 | 100 | 304345 | -1.819e-11
|  |  |  | 304345 |  | 304345 | -1.819e-11
|  |  |  | 304345 |  | 304345 | -1.819e-11
|  | Totals: | 304345 |  | 304345 |  | 0 | FINAL
|  | Design Development Documents | 55342.5 |  | 55342.5 |  | 0
|  | Construction Documents | 115032.5 |  | 115032.5 |  | 0
|  | Bidding & Negotiation | 12400 |  | 12400 |  | 0
|  | Construction Phase | 59580 |  | 59580 |  | 0
|  | Cost Estimation Services | 10340 |  | 10340 |  | 0
|  | CO1 | 41000 |  | 41000 |  | 0
|  | CO3 | 8750 |  | 8750 |  | 0
|  | CO4 | 1900 |  | 1900 |  | 0
|  | Total: | 304345 |  | 304345 |  | 0

## #9216.00 Controlled Asbestos
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Controlled Asbestos, Inc. |  |  | Vendor: 00002118118
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B: MA21060
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522020904 | 2022-01-20 | DO Procore | 18442.07 | 18442.07 |  |  | 18442.07 | FY22
DO 33523020904 | 2022-08-29 | Rolled to FY23 | 0 | 18442.07 |  | 0 | 18442.07
DO 33523020904 | 2023-04-05 | CO 1 | 31370.34 | 49812.41 |  | 0 | 49812.41
PRC 3352302PA0904 | 2023-08-11 | Inv. 0010578-IN-FINAL | -4202.33 | 45610.08 | 45610.08 | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  |  |  | 45610.08 |  | 45610.08 | 0
|  | Totals: | 45610.08 |  | 45610.08 |  | 0
|  | Contract Line 1-Hourly Rate Normal Business (791.4555X $58.00/hr) | 41960.48 |  | 41960.48 |  | 0
|  | Contract Line 7-Materials (1 Lump Sum) | 1016.6 |  | 1016.6 |  | 0
|  | Contract Line10-Friable Disposal Fee (3.11 tons X $75/ton) | 151.04 |  | 151.04 |  | 0
|  | Contract Line 12-Mileage (6806 Miles X $0.39/Mile) | 2481.96 |  | 2481.96 |  | 0
|  | Total: | 45610.08 |  | 45610.08 |  | 0

## #9216.00 Story Construction CA
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522073800 | 2022-03-11 | PO Procore | 742439.6 | 742439.6 |  |  | 742439.6
PO 33522073800 | 2022-04-06 | CO 1 | 6381 | 748820.6 |  | 0 | 748820.6
PRC 3352207PA3800 | 2022-04-28 | Inv. 33068 |  | 748820.6 | 12734 | 12734 | 736086.6
PRC 3352207PB3800 | 2022-05-20 | Inv. 33111 |  | 748820.6 | 28900.69 | 41634.69 | 707185.91
PRC 3352207PC3800 | 2022-06-23 | Inv. 33157 |  | 748820.6 | 21084 | 62718.69 | 686101.91
PRC 3352207PD3800 | 2022-07-20 | Inv. 33208 |  | 748820.6 | 21158.03 | 83876.72 | 664943.88 | FY22
PO 33523073800 | 2022-08-29 | Roll to FY23 | 0 | 748820.6 |  | 83876.72 | 664943.88
PRC 3352307PE3800 | 2022-08-31 | Inv. 33265 |  | 748820.6 | 40123.37 | 124000.09 | 624820.51
PO 33523073800 | 2022-09-16 | CO #2 | 86031.92 | 834852.52 |  | 124000.09 | 710852.43
PRC 3352307PF3800 | 2022-09-20 | Inv. 33330 |  | 834852.52 | 41375.26 | 165375.35 | 669477.17
PRC 3352307PG3800 | 2022-10-18 | Inv. 33389 |  | 834852.52 | 45394.83 | 210770.18 | 624082.34
PRC 3352307PH3800 | 2022-11-21 | Inv. 33447 |  | 834852.52 | 58727.66 | 269497.84 | 565354.68
PRC 3352307PI3800 | 2022-12-20 | Inv. 33503 |  | 834852.52 | 57815.3 | 327313.14 | 507539.38
PRC 3352307PJ3800 | 2023-01-20 | Inv. 33571 |  | 834852.52 | 32639.9 | 359953.04 | 474899.48
PRC 3352307PK3800 | 2023-02-17 | Inv. 33624 |  | 834852.52 | 52701.05 | 412654.09 | 422198.43
PRC 3352307PL3800 | 2023-03-21 | Inv. 33676 |  | 834852.52 | 38027.45 | 450681.54 | 384170.98
PRC 3352307PM3800 | 2023-04-19 | Inv. 33724 |  | 834852.52 | 42868.97 | 493550.51 | 341302.01
PRC 3352307PN3800 | 2023-05-22 | Inv. 33780 |  | 834852.52 | 56826.46 | 550376.97 | 284475.55
PRC 3352307PO3800 | 2023-06-22 | Inv. 33829 |  | 834852.52 | 33201.64 | 583578.61 | 251273.91
PO 33523073800 | 2023-06-28 | CO #3 (No Cost) | 0 | 834852.52 |  | 583578.61 | 251273.91
PRC 3352307PP3800 | 2023-07-25 | Inv. 33886 |  | 834852.52 | 41311.14 | 624889.75 | 209962.77 | FY23
PO 33524073800 | 2023-08-28 | Roll to FY24 | 0 | 834852.52 |  | 624889.75 | 209962.77
PRC 3352407PQ3800 | 2023-09-08 | Inv. 33945 |  | 834852.52 | 34911.02 | 659800.77 | 175051.75
PRC 3352407PR3800 | 2023-09-25 | Inv. 33999 |  | 834852.52 | 40248.19 | 700048.96 | 134803.56
PO 33524073800 | 2023-10-16 | CO #4 | 1783.1 | 836635.62 |  | 700048.96 | 136586.66
PRC 3352407PS3800 | 2023-10-18 | Inv. 34060 |  | 836635.62 | 47270.78 | 747319.74 | 89315.88
PRC 3352407PT3800 | 2023-11-27 | Inv. 34113 |  | 836635.62 | 56737 | 804056.74 | 32578.88
PRC 3352407PU3800 | 2023-12-21 | Inv. 34154 |  | 836635.62 | 8681.62 | 812738.36 | 23897.26
PRC 3352407PV3800 | 2024-01-18 | Inv. 34201 |  | 836635.62 | 10246 | 822984.36 | 13651.26
PRC 3352407PW3800 | 2024-02-16 | Inv. 34243 |  | 836635.62 | 3448.1 | 826432.46 | 10203.16
PO 33524073800 | 2024-05-16 | CO #5 (No Cost) | 0 | 836635.62 |  | 826432.46 | 10203.16
PRC 3352407PX3800 | 2024-06-14 | Inv. 34389 |  | 836635.62 | 3095 | 829527.46 | 7108.16
PRC 3352407PY3800 | 2024-07-26 | Inv. 34434 |  | 836635.62 | 1274.36 | 830801.82 | 5833.8 | FY24
PO 33525073800 | 2024-08-26 | Roll to FY25 |  | 836635.62 |  | 830801.82 | 5833.8
PRC 3352507PZ3800 | 2024-12-16 | Inv. 34652 |  | 836635.62 | 397.5 | 831199.32 | 5436.3
PO 33525073800 | 2025-03-10 | Closing Per PM | -5436.3 | 831199.32 |  | 831199.32 | -2.7285e-11
|  |  |  | 831199.32 |  | 831199.32 | -2.7285e-11
|  | Totals: | 831199.32 |  | 831199.32 |  | 0
|  | CM Services | 398920 |  | 398920 |  | 0
|  | CM Fee | 182044.6 |  | 182044.6 |  | 0
|  | General Conditions | 152316.42 |  | 152316.42 |  | 0
|  | Reimbursables | 4153.92 |  | 4153.92 |  | 0
|  | CO 1 | 5949.36 |  | 5949.36 |  | 0
|  | CO 2 | 86031.92 |  | 86031.92 |  | 0
|  | CO 3 (No Cost) | 0 |  |  |  | 0
|  | CO 4 | 1783.1 |  | 1783.1 |  | 0
|  | CO 5 (No Cost) | 0 |  |  |  | 0
|  | Total: | 831199.32 |  | 831199.32 |  | 0

## #9216.00 Tricon General
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Tricon General Contractor |  |  | Vendor: 00002124028
Acct. Codes-0506-335-DA22-9255 |  |  | 921600-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522081903 | 2022-03-22 | PO Procore | 2070000 | 2070000 |  |  | 2070000
PO 33522081903 | 2022-05-26 | CO #1 | 24342 | 2094342 |  | 0 | 2094342
PRC 3352208PA1903 | 2022-08-04 | Inv. AIA #01 |  | 2094342 | 105614.4 | 105614.4 | 1988727.6 | 5558.67 | FY22
PO 33523081903 | 2022-08-29 | Rolled to FY23 | 0 | 2094342 |  | 105614.4 | 1988727.6
PO 33523081903 | 2022-08-31 | CO #2 | 2320.81 | 2096662.81 |  | 105614.4 | 1991048.41
PRC 3352308PB1903 | 2022-09-07 | Inv. 9216.00 - AIA #2 |  | 2096662.81 | 167768.71 | 273383.11 | 1823279.7 | 14388.59
PRC 3352308PC1903 | 2022-10-27 | Inv. 9216.00 - AIA #3 |  | 2096662.81 | 446616.1 | 719999.21 | 1376663.6 | 37894.72
PO 33523081903 | 2022-11-02 | CO #3 | 57520.69 | 2154183.5 |  | 719999.21 | 1434184.29
PRC 3352308PD1903 | 2022-12-02 | Inv. 9216.00 - AIA #4 |  | 2154183.5 | 300470.49 | 1020469.7 | 1133713.8 | 53708.98
PO 33523081903 | 2022-12-20 | CO #4 | 3116.4 | 2157299.9 |  | 1020469.7 | 1136830.2
PO 33523081903 | 2022-12-29 | CO #5 | 5607.28 | 2162907.18 |  | 1020469.7 | 1142437.48
PRC 3352308PE1903 | 2023-01-17 | Inv. 9216.00 - AIA #5 |  | 2162907.18 | 63586.37 | 1084056.07 | 1078851.11 | 56525.44
PO 33523081903 | 2023-02-09 | CO #6 | 16790.81 | 2179697.99 |  | 1084056.07 | 1095641.92
PRC 3352308PF1903 | 2023-03-07 | Inv. 9216.00-06 |  | 2179697.99 | 226102.38 | 1310158.45 | 869539.54 | 68955.76
PO 33523081903 | 2023-04-06 | CO #7 | 9465.99 | 2189163.98 |  | 1310158.45 | 879005.53
PRC 3352308PG1903 | 2023-05-04 | Inv. 9216.00-07 |  | 2189163.98 | 156828.69 | 1466987.14 | 722176.84 | 77209.92
PO 33523081903 | 2023-06-13 | CO #8 | 1645.04 | 2190809.02 |  | 1466987.14 | 723821.88
PO 33523081903 | 2023-06-28 | CO #9 | -27048.01 | 2163761.01 |  | 1466987.14 | 696773.87
PRC 3352308PH1903 | 2023-08-08 | Inv. 9216.00 - AIA #8 |  | 2163761.01 | 140157.72 | 1607144.86 | 556616.15 | 84586.64 | FY23
PO 33524081903 | 2023-08-28 | Roll to FY24 | 0 | 2163761.01 |  | 1607144.86 | 556616.15
PRC 3352408PI1903 | 2023-09-20 | Inv. 9216.00 - AIA #9 |  | 2163761.01 | 399217.5 | 2006362.36 | 157398.65 | 105598.08
PO 33524081903 | 2023-09-22 | CO #10 | 11237.17 | 2174998.18 |  | 2006362.36 | 168635.82
PRC 3352408PJ1903 | 2023-11-13 | Inv. 9216-10 |  | 2174998.18 | 40220.85 | 2046583.21 | 128414.97 | 107714.97
PRC 3352408PK1903 | 2024-05-16 | Inv. 9216.00-#11-Closeout |  | 2174998.18 | 19665 | 2066248.21 | 108749.97 | 108749.97
PRC 3352408PL1903 | 2024-06-01 | Inv. 9216.00 Retainage |  | 2174998.18 | 108749.97 | 2174998.18 | 0
|  | Totals: | 2174998.18 |  | 2174998.18 |  | 0
***Stored Materials Breakdown. Current store materials are subtracted from the invoice totals****
|  |  | Store Materials | Store Materials
|  | This Period | Previous Invoice | Current Invoice | Actual Payment
PRC 3352208PA1903 | 2022-08-04 | 62166.67 | 0 | 49007 | 105615
PRC 3352308PB1903 | 2022-09-07 | 119540.63 | 49007 | 106065 | 167768.71
PRC 3352308PC1903 | 2022-10-27 | 273570.08 | 106065 | 302617.15 | 446616.1
PRC 3352308PD1903 | 2022-12-02 | 287567.75 | 302617.15 | 331334.15 | 300470.49
PRC 3352308PE1903 | 2023-01-17 | 66402.83 | 331334.15 | 331334.15 | 63586.37
PRC 3352308PF1903 | 2023-03-07 | 238532.7 | 331334.15 | 331334.15 | 226102.38
PRC 3352308PG1903 | 2023-05-04 | 165082.85 | 331334.15 | 331334.15 | 156828.69
PRC 3352308PH1903 | 2023-08-08 | 147534.44 | 331334.15 | 331334.15 | 140157.72
PRC 3352308PI1903 | 2023-09-20 | 420228.94 | 331334.15 | 331334.15 | 399217.5
PRC 3352308PJ1903 | 2023-11-13 | 42337.74 | 331334.15 | 331334.15 | 40220.85
PRC 3352408PK1903 | 2024-05-16 | 20700 | 331334.15 | 331334.15 | 19665
PRC 3352408PL1903 | 2024-06-01 | 331334.15 | 331334.15 | 0 | 108749.97
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0

## #9216.00 Tri-City Electric
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Tri-City Electric |  |  | Vendor: 00002106567
Acct. Codes-0506-335-DA22-9255 |  |  | 921600-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522082901 | 2022-03-23 | PO Procore | 1030715 | 1030715 |  |  | 1030715
PO 33522082901 | 2022-06-24 | CO 1 | 185597.95 | 1216312.95 |  | 0 | 1216312.95 |  | FY22
PO 33523082901 | 2022-08-29 | Roll to FY23 | 0 | 1216312.95 |  | 0 | 1216312.95
PRC 3352308PA2901 | 2022-08-31 | Inv. 274258 |  | 1216312.95 | 51300 | 51300 | 1165012.95 | 2700
PRC 3352308PB2901 | 2022-09-16 | Inv. 274896 |  | 1216312.95 | 12952.56 | 64252.56 | 1152060.39 | 3381.72
PO 33523082901 | 2022-09-19 | CO #2 | 19004.02 | 1235316.97 |  | 64252.56 | 1171064.41
PRC 3352308PC2901 | 2022-10-14 | Inv. 276116 |  | 1235316.97 | 128741.14 | 192993.7 | 1042323.27 | 10157.57
PRC 3352308PD2901 | 2022-11-18 | Inv. 278430 |  | 1235316.97 | 195423 | 388416.7 | 846900.27 | 20442.99
PO 33523082901 | 2022-11-18 | CO #3 | 776.37 | 1236093.34 |  | 388416.7 | 847676.64
PRC 3352308PE2901 | 2022-12-09 | Inv. 279711 |  | 1236093.34 | 99993.45 | 488410.15 | 747683.19 | 25705.8
PO 33523082901 | 2022-12-16 | CO #4 | 11087.63 | 1247180.97 |  | 488410.15 | 758770.82
PRC 3352308PF2901 | 2023-01-05 | Inv. 281011 |  | 1247180.97 | 160900.8 | 649310.95 | 597870.02 | 34174.29
PO 33523082901 | 2023-02-10 | CO #5 | 3882.75 | 1251063.72 |  | 649310.95 | 601752.77
PRC 3352308PG2901 | 2023-02-17 | Inv. 283086R |  | 1251063.72 | 82449.3 | 731760.25 | 519303.47 | 38513.73
PRC 3352308PH2901 | 2023-03-21 | Inv. 285509 |  | 1251063.72 | 144277.72 | 876037.97 | 375025.75 | 46107.34
PRC 3352308PI2901 | 2023-04-20 | Inv. 287147 |  | 1251063.72 | 63968.13 | 940006.1 | 311057.62 | 49474.13
PO 33523082901 | 2023-06-13 | CO #6 | 21723.02 | 1272786.74 |  | 940006.1 | 332780.64
PO 33523082901 | 2023-06-23 | CO #7 | 2965.6 | 1275752.34 |  | 940006.1 | 335746.24
PRC 3352308PJ2901 | 2023-07-17 | Inv. 292706 |  | 1275752.34 | 134376.52 | 1074382.62 | 201369.72 | 56546.58 | FY23
PO 33524082901 | 2023-08-28 | Roll to FY24 | 0 | 1275752.34 |  | 1074382.62 | 201369.72
PRC 3352408PK2901 | 2023-09-14 | Inv. 295536 |  | 1275752.34 | 124939.32 | 1199321.94 | 76430.4 | 63122.34
PO 33524082901 | 2023-09-22 | CO #8 | 29795.45 | 1305547.79 |  | 1199321.94 | 106225.85
PRC 3352408PL2901 | 2023-11-17 | Inv. 300015 |  | 1305547.79 | 28305.69 | 1227627.63 | 77920.16 | 64612.1
PRC 3352408PM2901 | 2024-01-11 | Inv. 303037 |  | 1305547.79 | 2850 | 1230477.63 | 75070.16 | 64762.1
PRC 3352408PN2901 | 2024-05-03 | Inv. 303039-Closeout |  | 1305547.79 | 9792.6 | 1240270.23 | 65277.56 | 65277.5
PO 33524082901 | 2024-05-14 | CO #9 | 17754 | 1323301.79 |  | 1240270.23 | 83031.56
PRC 3352408PO2901 | 2024-06-10 | Inv. 303041 Release Retainage |  | 1323301.79 | 65277.5 | 1305547.73 | 17754.06 | 0
PRC 3352408PP2901 | 2024-07-25 | Inv. 313909 |  | 1323301.79 | 16866.36 | 1322414.09 | 887.7 | 887.7 | FY24 | Will be paid out in FY25 additional work being done.
PO 33525082901 | 2024-08-26 | Roll to FY25 |  | 1323301.79 |  | 1322414.09 | 887.7
PRC 3352508PQ2901 | 2024-12-12 | Inv. 322384RETAINAGE |  | 1323301.79 | 887.7 | 1323301.79 | 0
|  |  |  | 1323301.79 |  | 1323301.79 | 0
|  |  |  | 1323301.79 |  | 1323301.79 | 0
|  | Totals: | 1323301.79 |  | 1323301.79 |  | 0

## #9216.00 Young Plumbing
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Young Plumbing |  |  | Vendor: 00002109600
Acct. Codes-0506-335-DA22-9255 |  |  | 921600-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522087904 | 2022-03-25 | PO Procore | 1450400 | 1450400 |  |  | 1450400
PRC 3352208PA7904 | 2022-07-29 | Inv. 9216.00-01 |  | 1450400 | 11521.6 | 11521.6 | 1438878.4 | 606.4 | FY22
PO 33523087904 | 2022-08-29 | Roll to FY23 | 0 | 1450400 |  | 11521.6 | 1438878.4
PO 33523087904 | 2022-09-09 | CO #1 | 30863.63 | 1481263.63 |  | 11521.6 | 1469742.03
PRC 3352308PB7904 | 2022-09-09 | Inv. 9216.00-02 |  | 1481263.63 | 25020.15 | 36541.75 | 1444721.88 | 1923.25
PRC 3352308PC7904 | 2022-09-29 | Inv. 9216.00-03 |  | 1481263.63 | 248100.18 | 284641.93 | 1196621.7 | 14981.17
PRC 3352308PD7904 | 2022-10-14 | Inv. 9216.00-04 |  | 1481263.63 | 314274.51 | 598916.44 | 882347.19 | 31521.95
PO 33523087904 | 2022-11-02 | CO #2 | 425.5 | 1481689.13 |  | 598916.44 | 882772.69
PRC 3352308PE7904 | 2022-11-03 | Inv. 9216.00-05 |  | 1481689.13 | 74965.45 | 673881.89 | 807807.24 | 35467.5
PRC 3352308PF7904 | 2022-12-13 | Inv. 9216.00-06 |  | 1481689.13 | 10519.57 | 684401.46 | 797287.67 | 36021.17
PRC 3352308PG7904 | 2023-02-07 | Inv. 9216.00-07 |  | 1481689.13 | 65531 | 749932.46 | 731756.67 | 39470.17
PO 33523087904 | 2023-02-21 | CO #3 (No Cost) | 0 | 1481689.13 |  | 749932.46 | 731756.67
PRC 3352308PH7904 | 2023-03-21 | Inv. 9216.00-08 |  | 1481689.13 | 169400.2 | 919332.66 | 562356.47 | 48385.97
PO 33523087904 | 2023-04-11 | CO #4 | 6926.02 | 1488615.15 |  | 919332.66 | 569282.49
PRC 3352308PI7904 | 2023-04-20 | Inv. 9216.00-09 |  | 1488615.15 | 96945.12 | 1016277.78 | 472337.37 | 53488.345
PRC 3352308PJ7904 | 2023-05-31 | Inv. 9216.00-10 |  | 1488615.15 | 19734.86 | 1036012.64 | 452602.51 | 54527.025
PRC 3352308PK7904 | 2023-06-06 | Inv. 9216.00-11 |  | 1488615.15 | 95374.3 | 1131386.94 | 357228.21 | 59546.725
PO 33523087904 | 2023-06-13 | CO #5 | 9965.53 | 1498580.68 |  | 1131386.94 | 367193.74
PO 33523087904 | 2023-06-28 | CO #6 | 6901.6 | 1505482.28 |  | 1131386.94 | 374095.34
PRC 3352308PL7904 | 2023-07-28 | Inv. 9216.00-12 |  | 1505482.28 | 135511.84 | 1266898.78 | 238583.5 | 66678.935 | FY23
PO 33524087904 | 2023-08-28 | Roll to FY24 | 0 | 1505482.28 |  | 1266898.78 | 238583.5
PRC 3352408PM7904 | 2023-09-08 | Inv. 9216.00-13 |  | 1505482.28 | 76569.05 | 1343467.83 | 162014.45 | 70708.89
PO 33524087904 | 2023-09-20 | CO #7 | -5232.73 | 1500249.55 |  | 1343467.83 | 156781.72
PRC 3352408PN7904 | 2023-12-12 | Inv. 9216.00-14 |  | 1500249.55 | 67990.39 | 1411458.22 | 88791.33 | 74287.33
PO 33524087904 | 2024-05-14 | CO #8 | 11915 | 1512164.55 |  | 1411458.22 | 100706.33
PRC 3352408PO7904 | 2024-06-19 | Inv. 9216.00-15 - Closeout |  | 1512164.55 | 13778.8 | 1425237.02 | 86927.53 | 75012.53
PRC 3352408PP7904 | 2024-07-02 | Inv. 9216.00-16-Retainage |  | 1512164.55 | 75012.53 | 1500249.55 | 11915 | 0
PRC 3352408PQ7904 | 2024-07-30 | Inv. 9216.00-17 |  | 1512164.55 | 8489.44 | 1508738.99 | 3425.56 | 446.81 | FY24
PO 33525087904 | 2024-08-26 | Roll to FY25 |  | 1512164.55 |  | 1508738.99 | 3425.56
PRC 3352508PR7904 | 2025-02-19 | Inv. 9216.00-18 |  | 1512164.55 | 2829.81 | 1511568.8 | 595.75 | 595.75
PRC 3352508PS7904 | 2025-02-25 | Inv. 9216.00-19 Retainage |  | 1512164.55 | 595.75 | 1512164.55 | 0
|  |  |  | 1512164.55 |  | 1512164.55 | 0
|  | Totals: | 1512164.55 |  | 1512164.55 |  | 0 | FINAL

## #9216.00 Norix Group
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Norix Group |  |  | Vendor: 00002100261
Acct. Codes-0506-335-DA22-9255 |  |  | MA20374B
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522151801 | 2022-05-31 | DO Procore | 81072 | 81072 |  |  | 81072 | FY22
DO 33523151801 | 2022-08-29 | Rolled to FY23 | 0 | 81072 |  | 0 | 81072
PRC 3352315PA1801 | 2022-09-06 | Inv. INV96469 |  | 81072 | 81072 | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  |  |  | 81072 |  | 81072 | 0
|  | Totals: | 81072 |  | 81072 |  | 0
|  | Contract Line 5 - Institutional Furniture, All Types (50% off list price for beds) | 58080 |  | 58080 |  | 0
|  | Contract Line 5 - Institutional Furniture, All Types (50% off list price for storage units) | 22992 |  | 22992 |  | 0
|  | Total: | 81072 |  | 81072 |  | 0

## #9216.00 IA Prison Ind
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
IA Prison Industries |  |  | Vendor: 250DOCIPI00
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522151900 | 2022-05-31 | DO Procore | 10474.48 | 10474.48 |  |  | 10474.48
DO 33522151900 | 2022-07-19 | Discard DO | -10474.48 | 0 |  | 0 | 0
PO 33522151900A | 2022-07-19 | PO Procore | 10474.48 | 10474.48 |  | 0 | 10474.48
PRCI 3352215PA1900A | 2022-07-19 | Inv. 371218 |  | 10474.48 | 5784.48 | 5784.48 | 4690
PO 33522151900A | 2022-07-26 | Update PO amount in I/3 | 0 | 10474.48 |  | 5784.48 | 4690
PRCI 3352215PB1900A | 2022-07-26 | Inv. 329089 |  | 10474.48 | 4690 | 10474.48 | 0
PO 33522151900A | 2022-08-30 | Update PO amount in I/3 | 0 | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  |  |  | 10474.48 |  | 10474.48 | 0
|  | Totals: | 10474.48 |  | 10474.48 |  | 0 | Final Invoice
|  | 10 Jaguar Eclipse Task Chairs | 4690 |  | 4690 |  | 0
|  | 48 Antimicrobial Matresses (30x75) | 5784.48 |  | 5784.48 |  | 0
|  | Total: | 10474.48 |  | 10474.48 |  | 0
**Invoices need to be processed as PRCI
**Edit PO amount in I/3 as PRCI's are created & approved

## #9216.00 Siemens-Damper Control
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
Siemens-Damper Control |  |  | Vendor: 00002089900
Acct. Codes-0506-335-DA22-9255 |  |  | MA00520358A
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524134904 | 2022-03-25 | PO Procore | 11200.85 | 11200.85 |  |  | 11200.85
PRC 3352413PA4904 | 2024-08-07 | Inv. 5331472417 |  | 11200.85 | 10640.81 | 10640.81 | 560.04
DO 33524134904A | 2024-08-19 | DO Closed on Pay app #1 by mistake |  | 11200.85 |  | 10640.81 | 560.04 | FY24
DO 33525134904A | 2024-08-26 | Roll to FY25 |  | 11200.85 |  | 10640.81 | 560.04
PRC 3352513PB4904A | 2025-02-28 | Inv. 5331510974 FINAL |  | 11200.85 | 560.04 | 11200.85 | 0
|  |  |  | 11200.85 |  | 11200.85 | 0
|  |  |  | 11200.85 |  | 11200.85 | 0
|  |  |  | 11200.85 |  | 11200.85 | 0
|  |  |  | 11200.85 |  | 11200.85 | 0
|  |  |  | 11200.85 |  | 11200.85 | 0
|  | Totals: | 11200.85 |  | 11200.85 |  | 0 | FINAL
|  | Line 1 Building Automation Products | 2632.05 |  | 2632.05 |  | 0
|  | Line 2 Building Automation Services | 8568.8 |  | 8568.8 |  | 0
|  | Total: | 11200.85 |  | 11200.85 |  | 0

## #9216.00 SystemWorks
DHS STS Cottage Dorm Conversion
Project # 9216.00
Program code 921600 |  |  | Major Program 4B02
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0506-335-DA22-9255 |  |  | MA21396B
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524137915 | 2024-05-16 | DO Procore | 3200 | 3200 |  |  | 3200 | FY24
DO 33525137915 | 2024-08-26 | Roll to FY25 |  | 3200 |  | 0 | 3200
PRC 3352513PA7915 | 2025-02-17 | Inv. 12130 - Final |  | 3200 | 3200 | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  |  |  | 3200 |  | 3200 | 0
|  | Totals: | 3200 |  | 3200 |  | 0 | Final

## RECAP #9217.01
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
| Program code 921701 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 148899.03
C | Bluestone Engineering |  | 17458 | 17458 | 0
C | PM TIME |  | 3641.06 | 3641.06 | 0
C | Misc. |  | 0 | 0 | 0
C | Story Construction |  | 17763.1 | 17763.1 | 0
C | Waldinger Corporation |  | 110036.87 | 110036.87 | 0
| Total Project Cost | 148899.03 | 148899.03 | 148899.03 | 0 | 0
Closed 04/20/23

## #9217.01 Funds Rec'd
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUCDCPOWERUPGRADES | 2021-10-07 | 150000 | 150000
|  |  | MOU Amend #1 | IET MOUCDCPOWERAMEND1 | 2022-01-12 | 40000 | 40000
|  |  | Return FY22 Funds to Agency | IET 33522220800 | 2022-08-08 | -93027.25 | -93027.25
|  |  | Received FY23 Funds from Agency | IET MOURETFUNDS9217.01 | 2022-08-29 | 93027.25 | 93027.25
|  |  | Received Funds in Incorrect Unit | CDR 33523242901 | 2022-08-30 | 0 | 0
|  |  | Return Funds to Agency | IET 33523110800 | 2023-04-20 | -41100.97 | -41100.97
| Total Requested | 0 | Total Transferred |  |  | 148899.03 | 148899.03

## #9217.01 Bluestone Engineering
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  | Major Program 4B02
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0506-335-DA22-9260 |  |  | IRFP921700-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split with 9217.00 MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522238802 | 2021-10-08 | CO 1 (100% DA22) | 9650 | 9650 |  |  | 9650
PRC 3352223PC8802 | 2021-11-17 | Inv. 11349 (100% to MM22) |  | 9650 | 0 | 0 | 9650
PRC 3352223PD8802 | 2021-12-09 | Inv. 11416 (split between MM22 & DA22) |  | 9650 | 7237.5 | 7237.5 | 2412.5
PRC 3352223PE8802 | 2021-01-24 | Inv. 11506 (100% to MM22) |  | 9650 | 0 | 7237.5 | 2412.5
PO 33522238802 | 2022-02-08 | CO 2(100% to DA22) | 7808 | 17458 |  | 7237.5 | 10220.5
PRC 3352223PF8802 | 2022-02-09 | Inv. 11558(split between DA22 & MM22) |  | 17458 | 2412.5 | 9650 | 7808
PRC 3352223PG8802 | 2022-03-22 | Inv. 11600(split between DA22 & MM22) |  | 17458 | 780.8 | 10430.8 | 7027.2
PRC 3352223PH8802 | 2022-07-26 | Inv. 11872(100% to MM22) |  | 17458 | 0 | 10430.8 | 7027.2 | FY22
PO 33523238802 | 2022-08-30 | Rolled to FY23 | 0 | 17458 |  | 10430.8 | 7027.2
PRC 3352323PI8802 | 2022-08-31 | Inv. 11963 (100% to MM22) |  | 17458 | 0 | 10430.8 | 7027.2
PRC 3352323PJ8802 | 2022-10-06 | Inv. 11989 (Split between DA22 & MM22) |  | 17458 | 6246.4 | 16677.2 | 780.8
PRC 3352323PK8802 | 2023-01-19 | Inv. 12201 (Split between DA22 & MM22) |  | 17458 | 390.4 | 17067.6 | 390.4
PRC 3352323PL8802 | 2023-02-22 | Inv. 12310 - FINAL (Split between DA22 & MM22) |  | 17458 | 390.4 | 17458 | 0
|  |  |  | 17458 |  | 17458 | 0
|  |  |  | 17458 |  | 17458 | 0
|  |  |  | 17458 |  | 17458 | 0
|  |  |  | 17458 |  | 17458 | 0
|  |  |  | 17458 |  | 17458 | 0
|  | Totals: | 17458 |  | 17458 |  | 0 | FINAL
|  | 9217.00 MM22 | 45912 |  | 45912 |  | -3.4106e-13
|  | Total Contract: | 63370 |  | 63370 |  | -3.4106e-13

## #9217.01 PM TIME
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS 906X
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 3641.06 | 3641.06 |  |  | 3641.06
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 3641.06 | 350 | 350 | 3291.06
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 3641.06 | 275 | 625 | 3016.06
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30,2021 |  | 3641.06 | 200 | 825 | 2816.06
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 3641.06 | 275 | 1100 | 2541.06
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 3641.06 | 200 | 1300 | 2341.06
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 3641.06 | 100 | 1400 | 2241.06
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 3641.06 | 50 | 1450 | 2191.06
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 3641.06 | 125 | 1575 | 2066.06
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 3641.06 | 100 | 1675 | 1966.06
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 3641.06 | 75 | 1750 | 1891.06
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 3641.06 | -75 | 1675 | 1966.06
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 3641.06 | 82.5 | 1757.5 | 1883.56
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 3641.06 | 165 | 1922.5 | 1718.56
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 3641.06 | 412.5 | 2335 | 1306.06
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 3641.06 | 82.5 | 2417.5 | 1223.56
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 3641.06 | 110 | 2527.5 | 1113.56
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 34.75 | 3675.81 | 34.75 | 2562.25 | 1113.56
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -34.75 | 3641.06 | -34.75 | 2527.5 | 1113.56
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 152.33 | 3793.39 | 152.33 | 2679.83 | 1113.56
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -152.33 | 3641.06 | -152.33 | 2527.5 | 1113.56
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 257.48 | 3898.54 | 257.48 | 2784.98 | 1113.56
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -257.48 | 3641.06 | -257.48 | 2527.5 | 1113.56
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 64.85 | 3705.91 | 64.85 | 2592.35 | 1113.56
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -64.85 | 3641.06 | -64.85 | 2527.5 | 1113.56
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 110.07 | 3751.13 | 110.07 | 2637.57 | 1113.56
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -110.07 | 3641.06 | -110.07 | 2527.5 | 1113.56
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 3641.06 | 220 | 2747.5 | 893.56
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 3641.06 | 41.62 | 2789.12 | 851.94
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 3641.06 | 364.83 | 3153.95 | 487.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August, October 2022 | 136.94 | 3778 | 136.94 | 3290.89 | 487.11
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -136.94 | 3641.06 | -136.94 | 3153.95 | 487.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 3641.06 | 22.48 | 3176.43 | 464.63
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 3641.06 | 136.35 | 3312.78 | 328.28
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 3641.06 | 60.81 | 3373.59 | 267.47
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 3641.06 | 267.47 | 3641.06 | 0
[5 empty] | 3641.06 |  | 3641.06 | 0
|  |  | Totals: | 3641.06 |  | 3641.06 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time changes $Selma Kleene, Jennifer Tue, Nov 2, 3:29 PM (21 hours ago) to me, Scott For DA22 9217.01, please create a PM Time budget for $1,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-0454 ¦ Mobile: 515-822-8197 ¦ Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov DA22 9217.01 Budget $Selma Kleene, Jennifer 10:22 AM (4 hours ago) to me Please increase the PM Time budget for DA22 9217.01 to $2,500.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Increase $Joni Kleene, Jennifer 12:17 PM (33 minutes ago) to me, Scott Please increase the following PM Time budgets: MM21 8982.01 by $1,000.00 DA21 9215.00 by $300.00 DA20 9159.00 by $500.00 DA22 9217.01 by $300.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes $Joni Kleene, Jennifer Jan 6, 2023, 4:07 PM (3 days ago) to me, Scott Please make the following changes: MM22 Project 9219.00 - increase PM time by $770.00. DA22 Project 9217.01 - increase PM time by $550.00. DA20 Project 9159.00 - increase PM time by $550.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes $Joni Kleene, Jennifer 2:52 PM (5 minutes ago) to me, Scott Please create a PM Time budget for $6,600.00 for MM23 Project 9339.00. Please increase the PM Time budget for DA22 9217.01 by $500.00 Please increase the PM Time budget for MM21 9298.00 by $6,600.00 Please increase the PM Time budget for DA20 9159.00 by $1,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close pro Kleene, Jennifer 12:42 PM (25 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer Kleene, Jennifer 12:42 PM (25 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer ects MM22 9217.00 and DA22 9217.01 External Inbox Kleene, Jennifer 12:42 PM (25 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer PM Time Budget Changes $Joni Kleene, Jennifer 2:52 PM (6 minutes ago) to me, Scott Please create a PM Time budget for $6,600.00 for MM23 Project 9339.00. Please increase the PM Time budget for DA22 9217.01 by $500.00 Please increase the PM Time budget for MM21 9298.00 by $6,600.00 Please increase the PM Time budget for DA20 9159.00 by $1,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close projects MM22 9217.00 and DA22 9217.01 External Inbox Kleene, Jennifer 12:42 PM (25 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer Kleene, Jennifer 12:42 PM (25 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer

## #9217.01 Misc
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9217.01 Story Construction
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522014800 | 2022-01-14 | PO Procore | 17881.06 | 17881.06 |  |  | 17881.06
PRC 3352201PA4800 | 2022-02-17 | Inv. 32980 |  | 17881.06 | 1780.5 | 1780.5 | 16100.56
PRC 3352201PB4800 | 2022-03-22 | Inv. 33022 |  | 17881.06 | 1677 | 3457.5 | 14423.56
PRC 3352201PC4800 | 2022-04-28 | Inv. 33069 |  | 17881.06 | 2491.5 | 5949 | 11932.06
PRC 3352201PD4800 | 2022-05-19 | Inv. 33112 |  | 17881.06 | 4548.99 | 10497.99 | 7383.07
PRC 3352201PE4800 | 2022-06-20 | Inv. 33158 |  | 17881.06 | 556.5 | 11054.49 | 6826.57
PRC 3352201PF4800 | 2022-07-18 | Inv. 33209 |  | 17881.06 | 79.5 | 11133.99 | 6747.07 | FY22
PO 33523014800 | 2022-08-30 | Rolled to FY23 | 0 | 17881.06 |  | 11133.99 | 6747.07
PRC 3352301PG4800 | 2022-08-30 | Inv. 33266 |  | 17881.06 | 1113 | 12246.99 | 5634.07
PRC 3352301PH4800 | 2022-09-26 | Inv. 33331 |  | 17881.06 | 651.6 | 12898.59 | 4982.47
PRC 3352301PI4800 | 2022-10-18 | Inv. 33390 |  | 17881.06 | 878.01 | 13776.6 | 4104.46
PRC 3352301PJ4800 | 2022-11-21 | Inv. 33448 |  | 17881.06 | 709 | 14485.6 | 3395.46
PRC 3352301PK4800 | 2022-12-19 | Inv. 33504 |  | 17881.06 | 2091 | 16576.6 | 1304.46
PRC 3352301PL4800 | 2023-01-20 | Inv. 33572 |  | 17881.06 | 1186.5 | 17763.1 | 117.96
PO 33523014800 | 2023-03-01 | Closing PO Per PM Request | -117.96 | 17763.1 |  | 17763.1 | 9.5213e-13
|  |  |  | 17763.1 |  | 17763.1 | 9.5213e-13
|  |  |  | 17763.1 |  | 17763.1 | 9.5213e-13
|  |  |  | 17763.1 |  | 17763.1 | 9.5213e-13
|  | Totals: | 17763.1 |  | 17763.1 |  | 0
|  | CM Services | 17689 |  | 17689 |  | 0
|  | Reimbursables | 74.1 |  | 74.1 |  | 0
|  | Total Contract: | 17763.1 |  | 17763.1 |  | 0

## #9217.01 Waldinger Corporation
DHS WRC CDC Warehouse Power Upgrades
Project # 9217.01
Program code 921701 |  |  | Major Program 4B02
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: 005 20452
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522021800 | 2022-01-21 | PO Procore | 138519.39 | 138519.39 |  |  | 138519.39
PRC 3352202PA1800 | 2022-05-20 | Inv. 63323E-001 |  | 138519.39 | 35211.79 | 35211.79 | 103307.6 | 1853.26
PO 33522021800 | 2022-06-15 | CO #1 (no cost) | 0 | 138519.39 |  | 35211.79 | 103307.6
PRC 3352202PB1800 | 2022-08-04 | Inv. 63323E-002 |  | 138519.39 | 38521.17 | 73732.96 | 64786.43 | 3880.69 | FY22
PO 33523021800 | 2022-08-30 | Rolled to FY23 | 0 | 138519.39 |  | 73732.96 | 64786.43
PRC 3352302PC1800 | 2022-08-30 | Inv. 63323E-003 |  | 138519.39 | 26092.22 | 99825.18 | 38694.21 | 5253.97
PO 33523021800 | 2022-12-29 | CO #2 | -28482.52 | 110036.87 |  | 99825.18 | 10211.69
PRC 3352302PD1800 | 2023-01-06 | Inv. 63323E-004 |  | 110036.87 | 2981.82 | 102807 | 7229.87 | 5410.9
PRC 3352302PE1800 | 2023-02-10 | Inv. 63323E-005 |  | 110036.87 | 1728.02 | 104535.02 | 5501.85 | 5501.8485
PRC 3352302PF1800 | 2023-02-20 | Inv. 63323E-006-Retainage |  | 110036.87 | 5501.85 | 110036.87 | 0
|  |  |  | 110036.87 |  | 110036.87 | 0
|  |  |  | 110036.87 |  | 110036.87 | 0
|  |  |  | 110036.87 |  | 110036.87 | 0
|  | Totals: | 110036.87 |  | 110036.87 |  | 0

## RECAP #9220.00
DHS IMHI Boiler Installation Engineering (2021)
Project # 9220.00
| Program code 922000 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Doug C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 4650
C | IMEG Corporation |  | 3750 | 3750 | 0
C | PM TIME |  | 900 | 900 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 4650 | 4650 | 4650 | 0 | 0
Closed 06/10/22

## #9220.00 Funds Rec'd
DHS IMHI Boiler Installation Engineering (2021)
Project # 9220.00
Program code 922000 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Doug C.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | 40922080501 | 2021-08-05 | 5000 | 5000
|  |  | Return Remaining Funds to Agency | IET 33522161800 | 2022-06-10 | -350 | -350
| Total Requested | 0 | Total Transferred |  |  | 4650 | 4650

## #9220.00 IMEG Corporation
DHS IMHI Boiler Installation Engineering (2021)
Project # 9220.00
Program code 922000 |  |  | Major Program 4B02
IMEG Corporation |  |  | Vendor: 00003106665
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B: SRVV5
Project Manager - Doug C. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522236800 | 2021-08-20 | PO Procore | 3750 | 3750 |  |  | 3750
PRC 3352223PA6800 | 2021-10-07 | Inv. 9220.00-01 |  | 3750 | 3750 | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  |  |  | 3750 |  | 3750 | 0
|  | Totals: | 3750 |  | 3750 |  | 0

## #9220.00 PM TIME
DHS IMHI Boiler Installation Engineering (2021)
Project # 9220.00
Program code 922000 |  |  | Major Program 4B02
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Doug C.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 900 | 900 |  |  | 900
IET DAS202201115300001 | 2021-08-06 | PM-Jul. 01-Jul. 22, 2021 |  | 900 | 100 | 100 | 800
IET DAS202202115300001 | 2021-09-08 | PM-July 23-August 19, 2021 |  | 900 | 200 | 300 | 600
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 900 | 200 | 500 | 400
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 900 | 300 | 800 | 100
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 900 | 100 | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  |  |  | 900 |  | 900 | 0
|  | Totals: | 900 |  | 900 |  | 0
Note on D9: Wray, Ronda [DAS]: Re: PM Time Budge $Ronda Carper, Douglas Aug 12, 2021, 2:31 PM (1 day ago) to me, Scott Set PM time to $500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov On Thu, Aug 12, 2021 at 2:16 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: DA22: 9220.00 - Need budget set up to post PM time for $100.00 Thanks, Ronda Re: PM Time Budget $Selma Carper, Douglas 7:15 AM (3 hours ago) to me MM20: 9141.00 Post $500.00 to MM20, switch the remaining to MM21. DA22: 9220.00 Increase PM budget to $800.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov. Carper, Douglas 8:10 AM (19 minutes ago) to me, Scott 9178.00 Is MM21. 9220.00 Increase PM budget to $900.00. 9280.00 Set PM Budget to $8,000.00. 9281.00 Set PM Budget to $8,000.00. 9282.00 Set PM Budget to $3,000.00. 9284.00 Set PM Budget to $3,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov

## #9220.00 Misc
DHS IMHI Boiler Installation Engineering (2021)
Project # 9220.00
Program code 922000 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Doug C.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9221.00
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.00
| Program code 922100 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 7490
C | Shive Hattery |  | 4490 | 4490 | 0
C | PM TIME |  | 2000 | 2000 | 0
C | Misc. |  | 1000 | 1000 | 0
| Total Project Cost | 7490 | 7490 | 7490 | 0 | 0
Closed 5/31/22

## #9221.00 Funds Rec'd
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.00
Program code 922100 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 245229221 | 2021-08-20 | 15000 | 15000
|  |  | Return Remaining Funds to Agency | IET 33522154800 | 2022-06-03 | -7510 | -7510
| Total Requested | 0 | Total Transferred |  |  | 7490 | 7490

## #9221.00 Shive Hattery
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.00
Program code 922100 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: SRVV5
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522279801 | 2021-10-06 | PO Procore | 4490 | 4490 |  |  | 4490
PRC 3352227PA9801 | 2021-11-04 | Inv. 4216390-1 |  | 4490 | 4490 | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  |  |  | 4490 |  | 4490 | 0
|  | Totals: | 4490 |  | 4490 |  | 0

## #9221.00 PM TIME
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.00
Program code 922100 |  |  | Major Program 4B01
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Brad T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 2000 | 2000 |  |  | 2000
IET DAS202202115300001 | 2021-09-08 | PM-July 23-August 19, 2021 |  | 2000 | 275 | 275 | 1725
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 2000 | 2100 | 2375 | -375
CDE 33522307801 | 2021-11-03 | Moving PM time from 9221.00 to 9222.00 |  | 2000 | -1525 | 850 | 1150
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 2000 | 975 | 1825 | 175
CDE 33522313800 | 2021-11-09 | Moving PM time from 9221.00 to 9222.00 |  | 2000 | -625 | 1200 | 800
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 2000 | 600 | 1800 | 200
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec 30,2021 |  | 2000 | 175 | 1975 | 25
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 2000 | 25 | 2000 | 0
|  |  |  | 2000 |  | 2000 | 0
|  |  |  | 2000 |  | 2000 | 0
|  |  |  | 2000 |  | 2000 | 0
|  |  |  | 2000 |  | 2000 | 0
|  | Totals: | 2000 |  | 2000 |  | 0
Note on D9: Durakovic, Selma [DAS]: Re: PM Time Budget Inbox Tonyan, Bradley 11:25 AM (1 hour ago) to me Selma, Sorry as I thought I emailed a PM budget on this but maybe I didn't. Please set up the PM budget at $4,000. Thank you, Brad Tonyan, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Mon, Sep 13, 2021 at 11:22 AM Durakovic, Selma <selma.durakovic@iowa.gov> wrote: Brad, DA22 9221.00 - No available funds to post PM time in the amount of $275.00 Please advise. Thank you, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov

## #9221.00 Misc
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.00
Program code 922100 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522256500 | 2021-09-09 | 9500 | CMGR | Terracon Construction V#(2116512) | Inv. TF62726 | 1000 | 1000
1000
1000
1000
1000
1000
1000
1000
1000
1000
1000
1000
|  |  |  | Totals: |  | 1000

## RECAP #9221.01
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.01
Program code 922101 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 7/14/22

## #9221.01 Funds Rec'd
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.01
Program code 922101 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9221.01 Vendor A
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.01
Program code 922101 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9221.01 PM TIME
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.01
Program code 922101 |  |  | Major Program 4B01
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Brad T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 143.09 | 143.09 | 143.09 | 143.09 | 0
CDE 33523353209 | 2022-12-21 | Move PM time to 9997.23 MM23 | -143.09 | 0 | -143.09 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9221.01 Misc
DOC NCF Warehouse Overhead Door Expansion
Project # 9221.01
Program code 922101 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9222.00
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
| Program code 9222.00 |  |  | Major Program 3D02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 427420.24
C | Story Construction |  | 4063.26 | 4063.26 | 0
C | PM TIME |  | 4852.5 | 4852.5 | 0
C | Misc. |  | 1871.9 | 1871.9 | 0
C | Shive Hattery |  | 33250 | 33250 | 0
C | Story Construction (2) |  | 31785.58 | 31785.58 | 0
C | Koopman Roofing (dba Hopkins Roofing Inc) |  | 351597 | 351597 | 0
| Total Project Cost | 427420.24 | 427420.24 | 427420.24 | 0 | 0
Closed 01/06/2023

## #9222.00 Funds Rec'd
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUSTORMDAMAGEROOFS | 2021-08-19 | 586880 | 586880
|  |  | Return funds to Agency | IET 33522308200 | 2021-11-05 | -120000 | -120000
|  |  | Return FY22 funds to agency | IET 33522215813 | 2022-08-03 | -66972.15 | -66972.15
|  |  | Received FY23 Funds from Agency | IET MOURETFUNDS9222.00 | 2022-08-29 | 66972.15 | 66972.15
|  |  | Received Funds in Incorrect Unit | CDR 33523242902 | 2022-08-30 | 0 | 0
|  |  | Reutrned Funds to Agency per PM | IET 33523006900 | 2023-01-06 | -39459.76 | -39459.76
| Total Requested | 0 | Total Transferred |  |  | 427420.24 | 427420.24

## #9222.00 Story Construction
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522238800 | 2021-08-20 | PO Procore | 16076.47 | 16076.47 |  |  | 16076.47
PRC 3352223PA8800 | 2021-10-18 | Inv. 32797-Final | -12013.21 | 4063.26 | 4063.26 | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  |  |  | 4063.26 |  | 4063.26 | 0
|  | Totals: | 4063.26 |  | 4063.26 |  | 0 | Final Invoice
|  | CM Services | 4063.26 |  | 4063.26 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 4063.26 |  | 4063.26 |  | 0

## #9222.00 PM TIME
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Jennifer K
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 4852.5 | 4852.5 |  |  | 4852.5
CDE 33522307801 | 2021-11-03 | Moving PM time from 9221.00 to 9222.00 |  | 4852.5 | 1525 | 1525 | 3327.5
CDE 33522313800 | 2021-11-09 | Moving PM time from 9221.00 to 9222.00 |  | 4852.5 | 625 | 2150 | 2702.5
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 4852.5 | 200 | 2350 | 2502.5
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec 30,2021 |  | 4852.5 | 275 | 2625 | 2227.5
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 4852.5 | 150 | 2775 | 2077.5
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28,2022 |  | 4852.5 | 25 | 2800 | 2052.5
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 4852.5 | 25 | 2825 | 2027.5
IET DAS202210115300001 | 2022-05-06 | PM April 1-April 29, 2022 |  | 4852.5 | 25 | 2850 | 2002.5
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 4852.5 | 200 | 3050 | 1802.5
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 4852.5 | 400 | 3450 | 1402.5
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 4852.5 | 275 | 3725 | 1127.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Credit |  | 4852.5 | -275 | 3450 | 1402.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Reposted correct amount |  | 4852.5 | 302.5 | 3752.5 | 1100
IET DAS202301115300001 | 2022-09-08 | PM-August 1-August 31, 2022 |  | 4852.5 | 220 | 3972.5 | 880
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 4852.5 | 165 | 4137.5 | 715
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 4852.5 | 165 | 4302.5 | 550
IET DAS202305115300001 | 2022-12-19 | PM Time-November 1- Novemer 30, 2022 |  | 4852.5 | 550 | 4852.5 | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 439.73 | 5292.23 | 439.73 | 5292.23 | 0
CDE 33523353209 | 2022-12-21 | Move PM time to 9997.23 MM23 | -439.73 | 4852.5 | -439.73 | 4852.5 | 0
IET DAS202305115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 203.11 | 5055.61 | 203.11 | 5055.61 | 0
CDE 33523353210 | 2022-12-22 | Move PM time to 9997.23 MM23 | -203.11 | 4852.5 | -203.11 | 4852.5 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Sept 9997.23 disbursement | 102.99 | 4955.49 | 102.99 | 4955.49 | 0
CDE 33523353211 | 2022-12-21 | Move PM time to 9997.23 MM23 | -102.99 | 4852.5 | -102.99 | 4852.5 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 129.71 | 4982.21 | 129.71 | 4982.21 | 0
CDE 33523353207 | 2022-12-22 | Move PM time to 9997.23 MM23 | -129.71 | 4852.5 | -129.71 | 4852.5 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 550.36 | 5402.86 | 550.36 | 5402.86 | 0
CDE 33523353208 | 2022-12-22 | Move PM time to 9997.23 MM23 | -550.36 | 4852.5 | -550.36 | 4852.5 | 0
|  |  |  | 4852.5 |  | 4852.5 | 0
|  | Totals: | 4852.5 |  | 4852.5 |  | 0
Note on D9: Jenkins, Jennifer [DAS]: PM Time Changes Jennifer Kleene, Jennifer 11:13 AM (2 hours ago) to me Please make the following changes to PM Time Budgets: MM19 9168.00 increase by $400.00 MM20 8982.01 increase by $2,000 DA20 8982.01 increase by $200.00 DA22 9222.00 Create a budget for $6,000 MM19 9064.00 increase by $1,000.00 MM20 9145.00 increase by $2,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative

## #9222.00 Misc
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  |  | Major Program 3D02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522280800 | 2021-09-30 | 9500 | CMGR | ATC Group Services V# (00002134218) | Inv. 2373629-Final | 1152.5 | 1152.5
GAX 33522300800 | 2021-10-27 | 9500 | BRUM | Controlled Asbestos V# (00002118118) | Inv. 0010279-IN | 719.4 | 1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
1871.9
|  |  |  | Totals: |  | 1871.9

## #9222.00 Shive Hattery
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: Emergency
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522246802 | 2021-09-03 | PO Procore | 32500 | 32500 |  |  | 32500
PRC 3352224PA6802 | 2021-10-07 | Inv. 4215820-1 |  | 32500 | 17250 | 17250 | 15250
PRC 3352224PB6802 | 2021-11-08 | Inv. 4215820-2 |  | 32500 | 1250 | 18500 | 14000
PRC 3352224PC6802 | 2021-12-09 | Inv. 4215820-3 |  | 32500 | 3500 | 22000 | 10500
PRC 3352224PD6802 | 2022-06-08 | Inv. 4215820-4 |  | 32500 | 6300 | 28300 | 4200
PRC 3352224PE6802 | 2022-07-11 | Inv. 4215820-5 |  | 32500 | 3920 | 32220 | 280 | FY22
PO 33523246802 | 2022-08-30 | Rolled to FY23 | 0 | 32500 |  | 32220 | 280
PO 33523246802 | 2022-11-16 | CO 1 | 750 | 33250 |  | 32220 | 1030
PRC 3352324PF6802 | 2022-11-28 | Inv. 4215820-6 |  | 33250 | 1030 | 33250 | 0
|  |  |  | 33250 |  | 33250 | 0
|  |  |  | 33250 |  | 33250 | 0
|  |  |  | 33250 |  | 33250 | 0
|  |  |  | 33250 |  | 33250 | 0
|  | Totals: | 33250 |  | 33250 |  | 0
|  | Storm Damage Evaluation | 1000 |  | 1000 |  | 0
|  | Design Development Phase | 9750 |  | 9750 |  | 0
|  | Construction Documents Phase | 6500 |  | 6500 |  | 0
|  | Bidding Phase | 1250 |  | 1250 |  | 0
|  | Construction Phase | 14000 |  | 14000 |  | 0
|  | CO 1 | 750 |  | 750 |  | 0
|  | Total: | 33250 |  | 32500 |  | 0

## #9222.00 Story Construction (2)
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522273800 | 2021-09-30 | PO Procore | 32282.9 | 32282.9 |  |  | 32282.9
PRC 3352227PA3800 | 2021-11-17 | Inv. 32844 |  | 32282.9 | 8514.75 | 8514.75 | 23768.15
PRC 3352227PB3800 | 2022-01-06 | Inv. 32897 |  | 32282.9 | 5095.05 | 13609.8 | 18673.1
PRC 3352227PC3800 | 2022-01-18 | Inv. 32940 |  | 32282.9 | 2641.31 | 16251.11 | 16031.79
PRC 3352227PD3800 | 2022-02-17 | Inv. 32982 |  | 32282.9 | 271.68 | 16522.79 | 15760.11
PRC 3352227PE3800 | 2022-03-22 | Inv. 33026 |  | 32282.9 | 81.18 | 16603.97 | 15678.93
PRC 3352227PF3800 | 2022-04-28 | Inv. 33072 |  | 32282.9 | 398.32 | 17002.29 | 15280.61
PRC 3352227PG3800 | 2022-05-20 | Inv. 33115 |  | 32282.9 | 416.72 | 17419.01 | 14863.89
PRC 3352227PH3800 | 2022-06-20 | Inv. 33162 |  | 32282.9 | 3933.8 | 21352.81 | 10930.09
PRC 3352227PI3800 | 2022-07-20 | Inv. 33213 |  | 32282.9 | 6162.75 | 27515.56 | 4767.34 | FY22
PO 33523273800 | 2022-08-30 | Rolled to FY23 | 0 | 32282.9 |  | 27515.56 | 4767.34
PRC 3352327PJ3800 | 2022-08-30 | Inv. 33269 |  | 32282.9 | 1464.47 | 28980.03 | 3302.87
PRC 3352327PK3800 | 2022-09-23 | Inv. 33334 |  | 32282.9 | 738.19 | 29718.22 | 2564.68
PRC 3352327PL3800 | 2022-10-17 | Inv. 33393 |  | 32282.9 | 1154.91 | 30873.13 | 1409.77
PRC 3352327PM3800 | 2022-11-29 | Inv. 33451 - FINAL | -497.32 | 31785.58 | 912.45 | 31785.58 | 3.3538e-12
|  |  |  | 31785.58 |  | 31785.58 | 3.3538e-12
|  |  |  | 31785.58 |  | 31785.58 | 3.3538e-12
|  | Totals: | 31785.58 |  | 31785.58 |  | 0 | FINAL
|  | CM Services | 31578.1 |  | 31578.1 |  | 0
|  | Reimbursables | 207.48 |  | 207.48 |  | 0
|  | Total: | 31785.58 |  | 31785.58 |  | 0

## #9222.00 Hopkins Roofing
DHS WRC 2021 Storm Damage Repairs (29C20)
Project # 9222.00
Program code 9222.00 |  |  | Major Program 3D02
Hopkins Roofing (Koopman Roofing) |  |  | Vendor: 00003054888
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B: Emergency
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522302800 | 2021-10-28 | PO Procore | 337130 | 337130 |  |  | 337130
PO 33522302800 | 2021-12-20 | CO 1 (no cost) | 0 | 337130 |  | 0 | 337130
PRC 3352230PA2800 | 2022-01-06 | Inv. 9222-01 |  | 337130 | 91758.12 | 91758.12 | 245371.88 | 4829.38
PO 33522302800 | 2022-06-07 | CO #2 (no cost) | 0 | 337130 |  | 91758.12 | 245371.88
PO 33522302800 | 2022-06-24 | CO 3 | 14467 | 351597 |  | 91758.12 | 259838.88
PRC 3352230PB2800 | 2022-07-11 | Inv. 8394 |  | 351597 | 239029.01 | 330787.13 | 20809.87 | 17409.87 | FY22
PO 33523302800 | 2022-08-30 | Rolled to FY23 | 0 | 351597 |  | 330787.13 | 20809.87
PRC 3352330PC2800 | 2022-10-27 | Inv. 8599 |  | 351597 | 3230 | 334017.13 | 17579.87 | 17579.87
PRC 3352330PD2800 | 2022-11-02 | Inv. 9222-04 Retainage |  | 351597 | 17579.87 | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  |  |  | 351597 |  | 351597 | 0
|  | Totals: | 351597 |  | 351597 |  | 0

## RECAP #9223.00
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
| Program code 922300 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 598321.43
C | Samuels Group |  | 83461.73 | 83461.726 | 0.004
C | PM TIME |  | 33007.74 | 33007.74 | 0
C | Misc. |  | 2260.96 | 2260.96 | 0
C | Farnsworth Group |  | 463801 | 463801 | 0
C | Denovo LLC |  | 9710 | 9710 | 0
C | Team Services |  | 6080 | 6080 | 0
| Total Project Cost | 598321.43 | 598321.43 | 598321.426 | 0.004 | 0
Closed 01/30/2024

## #9223.00 Funds Rec'd
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25563A22001 | 2021-08-25 | 30000 | 30000
|  |  | MOU Amend #1 | IET 25563A22003 | 2021-11-04 | 1000000 | 1000000
|  |  | Return FY22 Funds to Agency | IET 33522215814 | 2022-08-03 | -846830.1 | -846830.1
|  |  | Received FY23 Funds from Agency | IET 25563A23004 | 2022-08-24 | 846830.1 | 846830.1
|  |  | Return FY23 Funds to Agency | IET 33523227911 | 2023-08-15 | -431678.57 | -431678.57
| Total Requested | 0 | Total Transferred |  |  | 598321.43 | 598321.43

## #9223.00 PM TIME
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS S12H
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 33007.74 | 33007.74 |  |  | 33007.74
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 33007.74 | 3400 | 3400 | 29607.74
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 33007.74 | 1750 | 5150 | 27857.74
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 33007.74 | 2325 | 7475 | 25532.74
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30,2021 |  | 33007.74 | 1600 | 9075 | 23932.74
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 33007.74 | 1800 | 10875 | 22132.74
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 33007.74 | 2700 | 13575 | 19432.74
CDE 33522074901 | 2022-03-15 |  | Moving PM Time from MM21 9202.00 |  | 33007.74 | 800 | 14375 | 18632.74
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 33007.74 | 300 | 14675 | 18332.74
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 33007.74 | 100 | 14775 | 18232.74
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 33007.74 | 125 | 14900 | 18107.74
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 33007.74 | 1650 | 16550 | 16457.74
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 33007.74 | 575 | 17125 | 15882.74
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 33007.74 | -575 | 16550 | 16457.74
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 33007.74 | 632.5 | 17182.5 | 15825.24
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 33007.74 | 2062.5 | 19245 | 13762.74
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 33007.74 | 1100 | 20345 | 12662.74
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 33007.74 | 2970 | 23315 | 9692.74
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 33007.74 | 2117.5 | 25432.5 | 7575.24
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 597.53 | 33605.27 | 597.53 | 26030.03 | 7575.24
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -597.53 | 33007.74 | -597.53 | 25432.5 | 7575.24
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1570.41 | 34578.15 | 1570.41 | 27002.91 | 7575.24
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1570.41 | 33007.74 | -1570.41 | 25432.5 | 7575.24
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 703.15 | 33710.89 | 703.15 | 26135.65 | 7575.24
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -703.15 | 33007.74 | -703.15 | 25432.5 | 7575.24
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1870.14 | 34877.88 | 1870.14 | 27302.64 | 7575.24
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1870.14 | 33007.74 | -1870.14 | 25432.5 | 7575.24
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 1453.57 | 34461.31 | 1453.57 | 26886.07 | 7575.24
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1453.57 | 33007.74 | -1453.57 | 25432.5 | 7575.24
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 33007.74 | 2145 | 27577.5 | 5430.24
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 33007.74 | 361.71 | 27939.21 | 5068.53
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 33007.74 | 3171.03 | 31110.24 | 1897.5
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July, August, October 2022 | 342.57 | 33350.31 | 342.57 | 31452.81 | 1897.5
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -342.57 | 33007.74 | -342.57 | 31110.24 | 1897.5
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 33007.74 | 1457.5 | 32567.74 | 440
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 33007.74 | 440 | 33007.74 | -1.5916e-12
[5 empty] | 33007.74 |  | 33007.74 | -1.5916e-12
[5 empty] | 33007.74 |  | 33007.74 | -1.5916e-12
[5 empty] | 33007.74 |  | 33007.74 | -1.5916e-12
[5 empty] | 33007.74 |  | 33007.74 | -1.5916e-12
|  |  | Totals: | 33007.74 |  | 33007.74 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time - 9223.00 in DA22 $Selma Herman, Josh 10:38 AM (2 hours ago) to me Please set the PM Time budget to $7,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov PM Time $Selma Herman, Josh Dec 1, 2021, 9:18 AM (1 day ago) to me For 9170 in DA20 please add $2,400 to PM time. For 9223 in DA22 please add $18,000 to PM Time. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov PM Time Updates $Joni Herman, Josh Dec 1, 2022, 10:33 AM (23 hours ago) to me Please update the following: 8983.02 MM22 Add $4,500 to $30,000 total 9223.00 DA22 Add $5,000 for $30,000 total Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov PM Time Updates $Joni Herman, Josh Dec 1, 2022, 10:33 AM (23 hours ago) to me Please update the following: 8983.02 MM22 Add $4,500 to $30,000 total 9223.00 DA22 Add $5,000 for $30,000 total Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Herman, Josh 8:29 AM (36 minutes ago) to DAS, me For 9223 please increase from $30,000 to $45,000. For 9314 please increase as much as needed to cover PM Time. I'm gonna be closing it after PM Time posts. Thank you, Josh Tonyan, Brad 11:10 AM (2 minutes ago) to me John, Yes, please increase to cover the overage. Thanks, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Apr 11, 2023 at 10:32 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Brad Can you please check on project 9223.00 in DA22 The PM time i'm posting will put the budget over by 345.80 Would you like to increase it?

## #9223.00 Samuels Group
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | Samuels9112015
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522250501 | 2021-09-02 | PO Procore | 17689.8 | 17689.8 |  |  | 17689.8
PRC 3352225PA0501 | 2021-10-07 | Inv. 7352.01922300 |  | 17689.8 | 4058.96 | 4058.96 | 13630.84
PRC 3352225PB0501 | 2021-11-10 | Inv. 7352.02922300 |  | 17689.8 | 3557.84 | 7616.8 | 10073
PO 33522250501 | 2021-12-09 | CO #1 | 81321.64 | 99011.44 |  | 7616.8 | 91394.64
PRC 3352225PC0501 | 2021-12-13 | Inv. 7352.03922300 |  | 99011.44 | 2631.46 | 10248.26 | 88763.18
PRC 3352225PD0501 | 2022-02-04 | Inv. 7352.04922300 |  | 99011.44 | 1964.58 | 12212.84 | 86798.6
PRC 3352225PE0501 | 2022-02-10 | Inv. 7352.05922300 |  | 99011.44 | 8791.38 | 21004.22 | 78007.22
PRC 3352225PF0501 | 2022-07-13 | Inv. 7352.06922300 |  | 99011.44 | 11636.18 | 32640.4 | 66371.04 | FY22
PO 33523250501 | 2022-08-25 | Rolled to FY23 | 0 | 99011.44 |  | 32640.4 | 66371.04
PRC 3352325PG0501 | 2022-08-11 | Inv. 7352.07922300 |  | 99011.44 | 1399.556 | 34039.956 | 64971.484
PRC 3352325PH0501 | 2022-09-11 | Inv. 7352.08922300 |  | 99011.44 | 1524.04 | 35563.996 | 63447.444
PRC 3352325PI0501 | 2022-10-04 | Inv. 7352.09922300 |  | 99011.44 | 8484.67 | 44048.666 | 54962.774
PRC 3352325PJ0501 | 2022-11-09 | Inv. 7352.10922300 |  | 99011.44 | 9968.81 | 54017.476 | 44993.964
PRC 3352325PK0501 | 2022-12-09 | Inv. 7352.11922300 |  | 99011.44 | 11497.87 | 65515.346 | 33496.094
PRC 3352325PL0501 | 2023-01-11 | Inv. 7352.12922300 |  | 99011.44 | 5883.43 | 71398.776 | 27612.664
PRC 3352325PM0501 | 2023-02-08 | Inv. 7352.13922300 |  | 99011.44 | 10492.37 | 81891.146 | 17120.294
PRC 3352325PN0501 | 2023-03-06 | Inv. 7352.14922300 |  | 99011.44 | 1054.81 | 82945.956 | 16065.484
PRC 3352325PO0501 | 2023-07-06 | Inv. 7352.15922300 |  | 99011.44 | 515.77 | 83461.726 | 15549.714 | FY23
PO 33524250501 | 2023-08-28 | Roll to FY24 | 0 | 99011.44 |  | 83461.726 | 15549.714
PO 33524250501 | 2024-01-29 | Closing the PO Per PM Request | -15549.71 | 83461.73 |  | 83461.726 | 0.004
|  | Totals: | 83461.73 |  | 83461.726 |  | 0.004
|  | CM Services | 17229.8 |  | 17229.8 |  | 0
|  | Construction Phase | 460 |  | 460 |  | 0
|  | CO #1 | 65771.93 |  | 65771.93 |  | 0
|  | Total: | 83461.73 |  | 83461.73 |  | 0

## #9223.00 Misc
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522054900 | 2022-02-23 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV017980 | 54 | 54
PRC 33523249803 | 2022-09-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV023363 | 169.2 | 223.2
PRC 33523279902 | 2022-10-06 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV024181 | 254.52 | 477.72
PRC 33523031800 | 2023-01-31 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV027143 | 1783.24 | 2260.96
2260.96
2260.96
|  |  |  | Totals: |  | 2260.96

## #9223.00 Farnsworth Group
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: 922300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522319801 | 2021-11-12 | PO Procore | 600466 | 600466 |  |  | 600466
PRC 3352231PA9801 | 2021-12-14 | Inv. 9223.00-01 |  | 600466 | 18958.35 | 18958.35 | 581507.65
PRC 3352231PB9801 | 2022-01-21 | Inv. 9223.00-02 |  | 600466 | 82152.85 | 101111.2 | 499354.8
PRC 3352231PC9801 | 2022-07-14 | Inv. 9223.00-03 |  | 600466 | 25277.8 | 126389 | 474077 | FY22
PO 33523319801 | 2022-08-25 | Rolled to FY23 | 0 | 600466 |  | 126389 | 474077
PRC 3352331PD9801 | 2022-08-11 | Inv. 9223.00-04 |  | 600466 | 13635.4 | 140024.4 | 460441.6
PRC 3352331PE9801 | 2022-09-01 | Inv. 9223.00-05 |  | 600466 | 20453.1 | 160477.5 | 439988.5
PRC 3352331PF9801 | 2022-09-13 | Inv. 9223.00-06 |  | 600466 | 16362.48 | 176839.98 | 423626.02
PRC 3352331PG9801 | 2022-11-15 | Inv. 9223.00-07 |  | 600466 | 85903.02 | 262743 | 337723
PRC 3352331PH9801 | 2022-11-17 | Inv. 9223.00-08 |  | 600466 | 86697.5 | 349440.5 | 251025.5 |  | 3
PRC 3352331PI9801 | 2022-12-12 | Inv. 9223.00-09 |  | 600466 | 78027.75 | 427468.25 | 172997.75
PRC 3352331PJ9801 | 2023-01-11 | Inv. 9223.00-10 |  | 600466 | 8669.75 | 436138 | 164328
PRC 3352331PK9801 | 2023-02-16 | Inv. 9223.00-11 |  | 600466 | 23913 | 460051 | 140415
PO 33523319801 | 2023-02-23 | CO 1 | 3750 | 604216 |  | 460051 | 144165
PRC 3352331PL9801 | 2023-03-14 | Inv. 9223.00-12 |  | 604216 | 3750 | 463801 | 140415 | FY23
PO 33524319801 | 2023-08-28 | Roll to FY24 | 0 | 604216 |  | 463801 | 140415
PO 33524319801 | 2024-01-30 | Closing per PM Request | -140415 | 463801 |  | 463801 | 0
|  |  |  | 463801 |  | 463801 | 0
|  |  |  | 463801 |  | 463801 | 0
|  |  |  | 463801 |  | 463801 | 0
|  | Totals: | 463801 |  | 463801 |  | 0
|  | Schematic Design Documents | 126389 |  | 126389 |  | 0
|  | Design Development | 140104 |  | 140104 |  | 0
|  | Construction Documents | 173395 |  | 173395 |  | 0
|  | Bidding/Negotiating | 23913 |  | 23913 |  | 0
|  | Construction Administration | 0 |  |  |  | 0
|  | Total: | 463801 |  | 463801 |  | 0

## #9223.00 Denovo LLC
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Denovo LLC |  |  | Vendor: 00003187582
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: 922300-02
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522019803 | 2022-01-19 | PO Procore | 34840 | 34840 |  |  | 34840
PRC 3352201PA9803 | 2022-07-13 | Inv. 22.0001.01 |  | 34840 | 1456.5 | 1456.5 | 33383.5 | FY22
PO 33523019803 | 2022-08-25 | Rolled to FY23 | 0 | 34840 |  | 1456.5 | 33383.5
PRC 3352301PB9803 | 2022-11-15 | Inv. 22.0001.02 |  | 34840 | 3398.5 | 4855 | 29985
PRC 3352301PC9803 | 2022-12-07 | Inv. 22.0001.03 |  | 34840 | 4855 | 9710 | 25130 | FY23
PO 33524019803 | 2023-08-28 | Roll to FY24 | 0 | 34840 |  | 9710 | 25130
PO 33524019803 | 2024-01-30 | Closing per PM Request | -25130 | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  |  |  | 9710 |  | 9710 | 0
|  | Totals: | 9710 |  | 9710 |  | 0
|  | Design Review | 9710 |  | 9710 |  | 0
|  | Construction Commissioning | 0 |  |  |  | 0
|  | Close Out/Final Report | 0 |  |  |  | 0
|  | Total: | 9710 |  | 9710 |  | 0

## #9223.00 Team Services
DOC CCF Kitchen & Laundry Facility Design Project
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Team Services |  |  | Vendor: 00002121152
Acct. Codes-0506-335-DA22-9255 |  |  | RFQ1822335371
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522041902 | 2022-02-10 | PO Procore | 6080 | 6080 |  |  | 6080
PRC 3352204PA1902 | 2022-04-27 | Inv. 1810037-0 |  | 6080 | 5600 | 5600 | 480
PRC 3352204PB1902 | 2022-05-04 | Inv. 1810263-1 FINAL |  | 6080 | 480 | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  |  |  | 6080 |  | 6080 | 0
|  | Totals: | 6080 |  | 6080 |  | 0

## RECAP #9238.00
ABD Warehouse Racking Improvements
Project # 9238.00
| Program code 923800 |  |  | Major Program 4B04
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 2172780.15
C | Samuels Group |  | 11386.81 | 11386.81 | 0
C | PM TIME |  | 17493.04 | 17493.04 | 0
C | Misc. |  | 264.8 | 264.8 | 0
C | Schemmer Associates |  | 54991.16 | 54991.16 | 0
C | Samuels Group (2) |  | 167477.66 | 167477.66 | 0
C | Tri-City Electric |  | 69741.72 | 69741.72 | 0
C | KPI Solution |  | 1839024.96 | 1839024.96 | 0
C | DSM Steel Fence |  | 12400 | 12400 | 0
| Total Project Cost | 2172780.15 | 2172780.15 | 2172780.15 | 0 | 0
Closed 11/30/23

## #9238.00 Funds Rec'd
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DAS092221 | 2021-09-22 | 75000 | 75000
|  |  | MOU Amend 1 | IET DAS050622 | 2022-05-06 | 2150000 | 2150000
|  |  | Return FY22 Funds to Agency | IET 33522215815 | 2022-08-03 | -2150025.48 | -2150025.48
|  |  | Received FY23 Funds from Agency | IET DAS083122B | 2022-08-24 | 2150025.48 | 2150025.48
|  |  | Return FY23 Funds to Agency | IET 33523227912 | 2023-08-15 | -168867.77 | -168867.77
|  |  | Received FY24 Funds from Agency | IET DAS081723 | 2023-08-21 | 168867.77 | 168867.77
|  |  | Return Funds to Agency | IET 33524334910 | 2023-11-30 | -52219.85 | -52219.85
| Total Requested | 0 | Total Transferred |  |  | 2172780.15 | 2172780.15

## #9238.00 Samuels Group
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B #: Samuels9112015
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522278800 | 2021-10-01 | PO Procore | 11445.72 | 11445.72 |  |  | 11445.72
PRC 3352227PA8800 | 2021-11-08 | Inv. 7358.01923800 |  | 11445.72 | 3049.44 | 3049.44 | 8396.28
PRC 3352227PB8800 | 2021-12-09 | Inv. 7358.02923800 |  | 11445.72 | 1334.88 | 4384.32 | 7061.4
PRC 3352227PC8800 | 2022-01-04 | Inv. 7358.03923800 |  | 11445.72 | 1407.16 | 5791.48 | 5654.24
PRC 3352227PD8800 | 2022-02-09 | Inv. 7358.04923800 |  | 11445.72 | 1622.54 | 7414.02 | 4031.7
PRC 3352227PE8800 | 2022-03-09 | Inv. 7358.05923800 |  | 11445.72 | 971.25 | 8385.27 | 3060.45
PRC 3352227PF8800 | 2022-04-14 | Inv. 7358.06923800 |  | 11445.72 | 3001.54 | 11386.81 | 58.91
PO 33522278800 | 2022-07-15 | Closing PO per vendor's request | -58.91 | 11386.81 |  | 11386.81 | -1.0516e-12
|  |  |  | 11386.81 |  | 11386.81 | -1.0516e-12
|  |  |  | 11386.81 |  | 11386.81 | -1.0516e-12
|  |  |  | 11386.81 |  | 11386.81 | -1.0516e-12
|  |  |  | 11386.81 |  | 11386.81 | -1.0516e-12
|  |  |  | 11386.81 |  | 11386.81 | -1.0516e-12
|  | Totals: | 11386.81 |  | 11386.81 |  | 0
|  | CM Services | 11337.28 |  | 11337.28 |  | 0
|  | Reimbursables | 49.53 |  | 49.53 |  | 0
|  | Total: | 11386.81 |  | 11386.81 |  | 0

## #9238.00 PM TIME
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  |  | Major Program 4B04
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 906W
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 17493.04 | 17493.04 |  |  | 17493.04
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 17493.04 | 300 | 300 | 17193.04
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 17493.04 | 1450 | 1750 | 15743.04
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 17493.04 | 850 | 2600 | 14893.04
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30,2021 |  | 17493.04 | 800 | 3400 | 14093.04
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 17493.04 | 850 | 4250 | 13243.04
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 17493.04 | 400 | 4650 | 12843.04
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 17493.04 | 900 | 5550 | 11943.04
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 17493.04 | 450 | 6000 | 11493.04
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 17493.04 | 800 | 6800 | 10693.04
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 17493.04 | 500 | 7300 | 10193.04
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 17493.04 | 750 | 8050 | 9443.04
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 17493.04 | -750 | 7300 | 10193.04
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 17493.04 | 825 | 8125 | 9368.04
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 17493.04 | 440 | 8565 | 8928.04
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 17493.04 | 660 | 9225 | 8268.04
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 17493.04 | 220 | 9445 | 8048.04
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 17493.04 | 330 | 9775 | 7718.04
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 404.01 | 17897.05 | 404.01 | 10179.01 | 7718.04
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -404.01 | 17493.04 | -404.01 | 9775 | 7718.04
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 379.44 | 17872.48 | 379.44 | 10154.44 | 7718.04
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -379.44 | 17493.04 | -379.44 | 9775 | 7718.04
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 438.09 | 17931.13 | 438.09 | 10213.09 | 7718.04
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -438.09 | 17493.04 | -438.09 | 9775 | 7718.04
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 154.71 | 17647.75 | 154.71 | 9929.71 | 7718.04
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -154.71 | 17493.04 | -154.71 | 9775 | 7718.04
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 264.71 | 17757.75 | 264.71 | 10039.71 | 7718.04
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -264.71 | 17493.04 | -264.71 | 9775 | 7718.04
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 17493.04 | 495 | 10270 | 7223.04
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 17493.04 | 228.15 | 10498.15 | 6994.89
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 17493.04 | 2000.1 | 12498.25 | 4994.79
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 2022 | 290.01 | 17783.05 | 290.01 | 12788.26 | 4994.79
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -290.01 | 17493.04 | -290.01 | 12498.25 | 4994.79
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 17493.04 | 319.54 | 12817.79 | 4675.25
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 17493.04 | 1937.7 | 14755.49 | 2737.55
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 17493.04 | 107.85 | 14863.34 | 2629.7
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 17493.04 | 474.35 | 15337.69 | 2155.35
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 17493.04 | 98.62 | 15436.31 | 2056.73
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 17493.04 | 579.2 | 16015.51 | 1477.53
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 17493.04 | 45.92 | 16061.43 | 1431.61
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 17493.04 | 322.3 | 16383.73 | 1109.31
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 17493.04 | 36.63 | 16420.36 | 1072.68
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 17493.04 | 309.1 | 16729.46 | 763.58
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 17493.04 | 11.69 | 16741.15 | 751.89
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 17493.04 | 76.4 | 16817.55 | 675.49
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 17493.04 | 15.59 | 16833.14 | 659.9
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 17493.04 | 88 | 16921.14 | 571.9
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 17493.04 | 7.79 | 16928.93 | 564.11
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 17493.04 | 52.5 | 16981.43 | 511.61
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 17493.04 | 56.51 | 17037.94 | 455.1
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 17493.04 | 455.1 | 17493.04 | 0
[5 empty] | 17493.04 |  | 17493.04 | 0
|  |  | Totals: | 17493.04 |  | 17493.04 |  | 0
`
Note on E9: Wray, Ronda [DAS]: Re: PM Time Budget $Ronda Carper, Douglas 9:41 AM (6 hours ago) to me DA 19: Increase PM time to $19,000.00. DA22: 9238.00 Set PM Time budget to $12,000.00. Sincerely, Doug Douglas L. Carper, PE, Re: 9238.00 ABD Warehouse Racking project 803 Schemmer Associates, Inc. $Selma Carper, Douglas Tue, Nov 9, 1:27 PM (19 hours ago) to me Selma, Reduce the PM budget to $6,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov On Tue, Nov 9, 2021 at 1:23 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Doug, Your PO request is for $56,905 and available budget balance that we have left to spend is $51,554.28; therefore, I can't create this PO due to not having enough funds to cover all of it. Can you please look at this and advise at your earliest convenience how I should proceed? image.png Thank you, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov Project 9238.00 $Selma Carper, Douglas 7:46 AM (33 minutes ago) to me Please increase the PM Time budget to $15,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Elliott, Jennie 2:21 PM (5 minutes ago) to me Please increase the total budget to $20,000 for PM Time. Thank you, Elliott, Jennie 9:44 AM (2 hours ago) to me, Scott, Leisa Please close the PM Time line item in project 9238.00 - ABD ANK Warehouse Racking Improvements and return all remaining funds to the ABD. Returned funds should be $52,219.85.

## #9238.00 Misc
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  |  | Major Program 4B04
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522104904 | 2022-04-14 | 9500 | CMGR | Beeline & Blue V#(00002108204) | Inv. 019727 | 264.8 | 264.8
264.8
264.8
264.8
264.8
264.8
264.8
264.8
264.8
264.8
264.8
264.8
|  |  |  | Totals: |  | 264.8

## #9238.00 Schemmer Associates
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
Schemmer Associates |  |  | Vendor: 00002134858
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B #: 923800-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522314800 | 2021-11-09 | PO Procore | 56905 | 56905 |  |  | 56905
PRC 3352231PA4800 | 2022-01-28 | Inv. 08421.00-1 |  | 56905 | 25405 | 25405 | 31500
PRC 3352231PB4800 | 2022-07-13 | Inv. 08421.001-2 |  | 56905 | 18377.48 | 43782.48 | 13122.52 | FY22
PO 33523314800 | 2022-08-25 | Rolled to FY23 | 0 | 56905 |  | 43782.48 | 13122.52
PRC 3352331PC4800 | 2022-09-11 | Inv. 08421.001-3 |  | 56905 | 925 | 44707.48 | 12197.52
PRC 3352331PD4800 | 2022-10-06 | Inv. 08421.001-4 |  | 56905 | 512.21 | 45219.69 | 11685.31
PRC 3352331PE4800 | 2022-11-08 | Inv. 08421.001-5 |  | 56905 | 970.97 | 46190.66 | 10714.34
PRC 3352331PF4800 | 2022-12-02 | Inv. 08421.001-6 |  | 56905 | 108.01 | 46298.67 | 10606.33
PRC 3352331PG4800 | 2023-01-05 | Inv. 08421.001-7 |  | 56905 | 534.48 | 46833.15 | 10071.85
PRC 3352331PH4800 | 2023-02-06 | Inv. 08421.001-8 |  | 56905 | 565.66 | 47398.81 | 9506.19
PRC 3352331PI4800 | 2023-03-01 | Inv. 08421.001-9 |  | 56905 | 332.94 | 47731.75 | 9173.25
PRC 3352331PJ4800 | 2023-05-22 | Inv. 08421.001-10 |  | 56905 | 1776.74 | 49508.49 | 7396.51
PRC 3352331PK4800 | 2023-06-01 | Inv. 08421.001-11 |  | 56905 | 1066.53 | 50575.02 | 6329.98
PRC 3352331PL4800 | 2023-06-28 | Inv. 08421.001-12 |  | 56905 | 4193.44 | 54768.46 | 2136.54 | FY23
PO 33524314800 | 2023-08-22 | Roll to FY24 | 0 | 56905 |  | 54768.46 | 2136.54
PRC 3352431PM4800 | 2023-08-22 | Inv. 08421.001-13 FINAL | -1913.84 | 54991.16 | 222.7 | 54991.16 | 0
|  | Totals: | 54991.16 |  | 54991.16 |  | 0 | FINAL
|  | Schematic Design Documents | 15870 |  | 15870 |  | 0
|  | Design Development Documents | 9535 |  | 9535 |  | 0
|  | Construction Documents | 15915 |  | 15915 |  | 0
|  | Bidding Assistance | 2450 |  | 2450 |  | 0
|  | Construction Administration | 11135 |  | 11135 |  | 0
|  | Reimbursables | 86.16 |  | 86.16 |  | 0
|  | Total: | 54991.16 |  | 54991.16 |  | 0

## #9238.00 Samuels Group (2)
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522132801 | 2022-05-12 | PO Procore | 167477.66 | 167477.66 |  |  | 167477.66
PRC 3352213PA2801 | 2022-06-02 | Inv. 7358.51923800 |  | 167477.66 | 6294.04 | 6294.04 | 161183.62
PRC 3352213PB2801 | 2022-07-05 | Inv. 7358.52923800 |  | 167477.66 | 5946.39 | 12240.43 | 155237.23 | FY22
PO 33523132801 | 2022-08-25 | Rolled to FY23 | 0 | 167477.66 |  | 12240.43 | 155237.23
PRC 3352313PC2801 | 2022-07-29 | Inv. 7358.53923800 |  | 167477.66 | 1934.54 | 14174.97 | 153302.69
PRC 3352313PD2801 | 2022-09-08 | Inv. 7358.54923800 |  | 167477.66 | 933.04 | 15108.01 | 152369.65
PRC 3352313PE2801 | 2022-10-03 | Inv. 7358.55923800 |  | 167477.66 | 6621.66 | 21729.67 | 145747.99
PRC 3352313PF2801 | 2022-11-08 | Inv. 7358.56923800 |  | 167477.66 | 1054.81 | 22784.48 | 144693.18
PRC 3352313PG2801 | 2022-12-09 | Inv. 7358.57923800 |  | 167477.66 | 5708.27 | 28492.75 | 138984.91
PRC 3352313PH2801 | 2023-01-09 | Inv. 7358.58923800 |  | 167477.66 | 6476.24 | 34968.99 | 132508.67
PRC 3352313PI2801 | 2023-02-06 | Inv. 7358.59923800 |  | 167477.66 | 19352.58 | 54321.57 | 113156.09
PRC 3352313PJ2801 | 2023-03-04 | Inv. 7358.60923800 |  | 167477.66 | 59372.54 | 113694.11 | 53783.55
PRC 3352313PK2801 | 2023-04-04 | Inv. 7358.61923800 |  | 167477.66 | 39143.37 | 152837.48 | 14640.18
PRC 3352313PL2801 | 2023-05-08 | Inv. 7358.62923800 |  | 167477.66 | 3998.86 | 156836.34 | 10641.32
PRC 3352313PM2801 | 2023-06-05 | Inv. 7358.63923800 |  | 167477.66 | 2995.9 | 159832.24 | 7645.42
PRC 3352313PN2801 | 2023-07-07 | Inv. 7358.64923800 |  | 167477.66 | 3555.13 | 163387.37 | 4090.29 | FY23
PO 33524132801 | 2023-08-22 | Roll to FY24 | 0 | 167477.66 |  | 163387.37 | 4090.29
PRC 3352413PO2801 | 2023-08-22 | Inv. 7358.65923800 |  | 167477.66 | 3735.5 | 167122.87 | 354.79
PRC 3352413PP2801 | 2023-08-23 | Inv. 7358.66923800-FINAL |  | 167477.66 | 354.79 | 167477.66 | -2.1885e-11
|  | Totals: | 167477.66 |  | 167477.66 |  | 0 | FINAL
|  | CM Services | 72473.84 |  | 72473.84 |  | 0
|  | Reimbursables | 1000 |  | 1000 |  | 0
|  | Fee | 94003.82 |  | 94003.82 |  | 0
|  | Total: | 167477.66 |  | 167477.66 |  | 0

## #9238.00 Tri-City Electric
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
Tri-City Electric Company |  |  | Vendor: 00002106567
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#923800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522153900 | 2022-05-31 | PO Procore | 49936 | 49936 |  |  | 49936 |  | FY22
PO 33523153900 | 2022-08-25 | Rolled to FY23 | 0 | 49936 |  | 0 | 49936
PRC 3352315PA3900 | 2022-09-27 | Inv. 276011 |  | 49936 | 2134.76 | 2134.76 | 47801.24 | 112.36
PRC 3352315PB3900 | 2023-02-07 | Inv. 282496 |  | 49936 | 22533.62 | 24668.38 | 25267.62 | 1298.34
PO 33523153900 | 2023-02-09 | CO 1 | 762.48 | 50698.48 |  | 24668.38 | 26030.1
PRC 3352315PC3900 | 2023-03-03 | Inv. 284277 |  | 50698.48 | 19035.89 | 43704.27 | 6994.21 | 2300.23
PO 33523153900 | 2023-03-29 | CO 2 | 19043.24 | 69741.72 |  | 43704.27 | 26037.45
PRC 3352315PD3900 | 2023-03-29 | Inv. 286198 |  | 69741.72 | 3984.89 | 47689.16 | 22052.56 | 2509.96
PRC 3352315PE3900 | 2023-05-03 | Inv. 287632 |  | 69741.72 | 12663.76 | 60352.92 | 9388.8 | 3176.47
PRC 3352315PF3900 | 2023-06-01 | Inv. 289671 |  | 69741.72 | 5427.32 | 65780.24 | 3961.48 | 3462.12
PRC 3352315PG3900 | 2023-06-21 | Inv. 290170 |  | 69741.72 | 474.39 | 66254.63 | 3487.09 | 3487.09
PRC 3352315PH3900 | 2023-07-07 | Inv. Invoice 290171 - Retainage |  | 69741.72 | 3487.09 | 69741.72 | 0
|  |  |  | 69741.72 |  | 69741.72 | 0
|  | Totals: | 69741.72 |  | 69741.72 |  | 0 | FINAL

## #9238.00 KPI Solution
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
KPI Solutions |  |  | Vendor: VS000009740
Acct. Codes-0506-335-DA22-9255 |  |  | RFB923800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522173900 | 2022-06-22 | PO Procore | 1830140.36 | 1830140.36 |  |  | 1830140.36 |  | FY22
PO 33523173900 | 2022-08-25 | Rolled to FY23 | 0 | 1830140.36 |  | 0 | 1830140.36
PRC 3352317PA3900 | 2023-03-09 | Inv. 117740 |  | 1830140.36 | 822486.26 | 822486.26 | 1007654.1 | 43288.76
PRC 3352317PB3900 | 2023-03-27 | Inv. 118013 |  | 1830140.36 | 657988.95 | 1480475.21 | 349665.15 | 77919.77
PO 33523173900 | 2023-04-27 | CO #1 | 8884.6 | 1839024.96 |  | 1480475.21 | 358549.75
PRC 3352317PC3900 | 2023-06-01 | Inv. 118477 |  | 1839024.96 | 164497.21 | 1644972.42 | 194052.54 | 86577.53
PRC 3352317PD3900 | 2023-07-14 | Inv. 119049 |  | 1839024.96 | 82481.19 | 1727453.61 | 111571.35 | 90918.65 | FY23
PO 33524173900 | 2023-08-22 | Roll to FY24 | 0 | 1839024.96 |  | 1727453.61 | 111571.35
PRC 3352417PE3900 | 2023-08-22 | Inv. 119453 |  | 1839024.96 | 2233.73 | 1729687.34 | 109337.62 | 91036.21
PRC 3352417PF3900 | 2023-08-23 | Inv. 119467 |  | 1839024.96 | 17386.34 | 1747073.68 | 91951.28 | 91951.28
PRC 3352417PG3900 | 2023-09-07 | Inv. 119549-Retainage |  | 1839024.96 | 91951.28 | 1839024.96 | 0
|  |  |  | 1839024.96 |  | 1839024.96 | 0
|  |  |  | 1839024.96 |  | 1839024.96 | 0
|  | Totals: | 1839024.96 |  | 1839024.96 |  | 0 | FINAL

## #9238.00 DSM Steel Fence
ABD Warehouse Racking Improvements
Project # 9238.00
Program code 923800 |  |  | Major Program 4B04
DSM Steel Fence |  |  | Vendor: 00002118848
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523103902 | 2023-04-13 | PO Procore | 12400 | 12400 |  |  | 12400
PRC 3352310PA3902 | 2023-05-08 | Inv. 60512 |  | 12400 | 12400 | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  |  |  | 12400 |  | 12400 | 0
|  | Totals: | 12400 |  | 12400 |  | 0

## RECAP #9239.00
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
| Program code 923900 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 43963.14
C | Samuels Group |  | 10867.64 | 10867.64 | 0
C | PM TIME |  | 5262.5 | 5262.5 | 0
C | Misc. |  | 0 | 0 | 0
C | Farnsworth Group |  | 27833 | 27833 | 0
| Total Project Cost | 43963.14 | 43963.14 | 43963.14 | 0 | 0
Closed 06/20/2023

## #9239.00 Funds Rec'd
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
Program code 923900 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23882022001 | 2021-10-05 | 75000 | 75000
|  |  | Funds transferred without program code | CDR 33522279500 | 2021-10-05 | 0 | 0
|  |  | Return FY22 Funds to Agency | IET 33522215816 | 2022-08-03 | -70972.67 | -70972.67
|  |  | Received FY23 funds from agency | IET 238A2023067 | 2022-08-31 | 70972.67 | 70972.67
|  |  | Funds transferred without program code | CDR 33523244800 | 2022-09-01 | 0 | 0
|  |  | Funds transferred per MOU Amend #1 to 9239.01 | CDR 33523171901 | 2023-06-20 | -31036.86 | -31036.86
| Total Requested | 0 | Total Transferred |  |  | 43963.14 | 43963.14

## #9239.00 Samuels Group
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
Program code 923900 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522132803 | 2022-05-12 | PO Procore | 13692.24 | 13692.24 |  |  | 13692.24
PRC 3352213PA2803 | 2022-06-02 | Inv. 7409.01923900 |  | 13692.24 | 530.4 | 530.4 | 13161.84
PRC 3352213PB2803 | 2022-06-30 | Inv. 7409.02923900 |  | 13692.24 | 846.93 | 1377.33 | 12314.91 | FY22
PO 33523132803 | 2022-08-31 | Rolled to FY23 | 0 | 13692.24 |  | 1377.33 | 12314.91
PRC 3352313PC2803 | 2022-09-06 | Inv. 7409.03923900 |  | 13692.24 | 968.79 | 2346.12 | 11346.12
PRC 3352313PD2803 | 2022-09-08 | Inv. 7409.04923900 |  | 13692.24 | 2067.47 | 4413.59 | 9278.65
PRC 3352313PE2803 | 2022-09-29 | Inv. 7409.05923900 |  | 13692.24 | 1407.18 | 5820.77 | 7871.47
PRC 3352313PF2803 | 2022-12-09 | Inv. 7409.06923900 |  | 13692.24 | 1431.52 | 7252.29 | 6439.95
PRC 3352313PG2803 | 2023-04-04 | Inv. 7409.07923900 |  | 13692.24 | 2489.6 | 9741.89 | 3950.35
PRC 3352313PH2803 | 2023-05-08 | Inv. 7409.08923900 |  | 13692.24 | 595.35 | 10337.24 | 3355
PRC 3352313PI2803 | 2023-06-05 | Inv. 7409.09923900 FINAL | -2824.6 | 10867.64 | 530.4 | 10867.64 | 0
|  |  |  | 10867.64 |  | 10867.64 | 0
|  |  |  | 10867.64 |  | 10867.64 | 0
|  | Totals: | 10867.64 |  | 10867.64 |  | 0 | FINAL
|  | CM Services | 10832.54 |  | 10832.54 |  | 0
|  | Reimbursables | 35.1 |  | 35.1 |  | 0
|  | Total: | 10867.64 |  | 10867.64 |  | 0

## #9239.00 PM TIME
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
Program code 923900 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS 906Y
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 5262.5 | 5262.5 |  |  | 5262.5
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 5262.5 | 275 | 275 | 4987.5
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 5262.5 | 600 | 875 | 4387.5
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 5262.5 | 150 | 1025 | 4237.5
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30, 2021 |  | 5262.5 | 50 | 1075 | 4187.5
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 5262.5 | 100 | 1175 | 4087.5
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 5262.5 | 75 | 1250 | 4012.5
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 5262.5 | 450 | 1700 | 3562.5
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 5262.5 | 475 | 2175 | 3087.5
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 5262.5 | 475 | 2650 | 2612.5
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 5262.5 | 300 | 2950 | 2312.5
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 5262.5 | -300 | 2650 | 2612.5
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 5262.5 | 330 | 2980 | 2282.5
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 5262.5 | 302.5 | 3282.5 | 1980
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 5262.5 | 220 | 3502.5 | 1760
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 5262.5 | 82.5 | 3585 | 1677.5
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 5262.5 | 82.5 | 3667.5 | 1595
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 388.52 | 5651.02 | 388.52 | 4056.02 | 1595
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -388.52 | 5262.5 | -388.52 | 3667.5 | 1595
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 311.94 | 5574.44 | 311.94 | 3979.44 | 1595
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -311.94 | 5262.5 | -311.94 | 3667.5 | 1595
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 198.56 | 5461.06 | 198.56 | 3866.06 | 1595
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -198.56 | 5262.5 | -198.56 | 3667.5 | 1595
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 93.4 | 5355.9 | 93.4 | 3760.9 | 1595
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -93.4 | 5262.5 | -93.4 | 3667.5 | 1595
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 73.13 | 5335.63 | 73.13 | 3740.63 | 1595
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -73.13 | 5262.5 | -73.13 | 3667.5 | 1595
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 5262.5 | 275 | 3942.5 | 1320
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 5262.5 | 330 | 4272.5 | 990
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 5262.5 | 467.5 | 4740 | 522.5
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 5262.5 | 110 | 4850 | 412.5
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 5262.5 | 412.5 | 5262.5 | 0
[5 empty] | 5262.5 |  | 5262.5 | 0
[5 empty] | 5262.5 |  | 5262.5 | 0
|  |  | Totals: | 5262.5 |  | 5262.5 |  | 0
Note on E9: Wray, Ronda [DAS]: PM Time Set up on New Project $Ronda Tonyan, Brad Oct 6, 2021, 8:58 AM (1 day ago) to me, Scott Finance, Can you please set up the following PM time budget below: - DA22 - 9239.00 - DOC NCF IPI Home for Iowa Facility Project - $5,000 Thank you, Brad Tonyan, Owner Representative Billables and PM Time Adjustments $Joni Tonyan, Brad Feb 23, 2023, 4:15 PM (17 hours ago) to me, Scott, Brad Finance, Please make the following changes with Josh moving on and Doug retiring as some of the projects are not on my billables sheet. While I am on it I have made some PM time adjustments to cover some of the billing changes or construction oversight. - DA20 - 9118.00 - Raise PM time budget $3,000 - MM21 - 9204.00 - Raise PM time budget $2,000 - MM22 - 9235.00 - Raise PM time budget $5,000 - DA22 - 9239.00 - Raise PM time budget $2,500 - DA22 - 9242.00 - Raise PM time budget $15,000 - DA22 - 9280.00 - Add this project to my billables as I took from Doug - DA22 - 9281.00 - Add this project to my billables as I took from Doug Thank you and I think that is all for now. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Fwd: DOC NCF IPI Homes for Iowa Facility Project: Action Required for Contract #MISC-9239.01-011: Miscellaneous - DAS Costs - PM Time Inbox Tonyan, Brad 9:50 AM (2 minutes ago) to me, Brad Finance, On project 9239.00 I am processing a "dummy invoice" to put the PM time charged in the DAS financials into Procore. If you could close the PM time financial on this project it would be appreciated and I will give direction soon on if we should return remaining funds to client or shift to project 9239.01. Thank you,

## #9239.00 Misc
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
Program code 923900 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9239.00 Farnsworth Group
DOC-NCF-IPI Homes for Iowa Facility Project
Project # 9239.00
Program code 923900 |  |  | Major Program 4E01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA22-9620 |  |  | RFP913300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523215800A | 2022-08-02 | PO Procore | 44892 | 44892 |  |  | 44892
PRC 3352321PA5800A | 2022-09-12 | Inv. 9239.00~.01-01 |  | 44892 | 6734 | 6734 | 38158
PRC 3352321PB5800A | 2022-10-27 | Inv. 9239.00~.01-02 |  | 44892 | 5050.5 | 11784.5 | 33107.5
PRC 3352321PC5800A | 2022-12-21 | Inv. 9239.00~.01-03 |  | 44892 | 3120 | 14904.5 | 29987.5
PRC 3352321PD5800A | 2023-03-14 | Inv. 9239.00~.01-04 |  | 44892 | 5746 | 20650.5 | 24241.5
PO 33523215800A | 2023-03-22 | CO #1 | -17059 | 27833 |  | 20650.5 | 7182.5
PRC 3352321PE5800A | 2023-04-04 | Inv. 9239.00~.01-05 |  | 27833 | 3160.3 | 23810.8 | 4022.2
PRC 3352321PF5800A | 2023-06-09 | Inv. 9239.00~.01-06 - Final |  | 27833 | 4022.2 | 27833 | 0
|  |  |  | 27833 |  | 27833 | 0
|  |  |  | 27833 |  | 27833 | 0
|  |  |  | 27833 |  | 27833 | 0
|  |  |  | 27833 |  | 27833 | 0
|  |  |  | 27833 |  | 27833 | 0
|  | Totals: | 27833 |  | 27833 |  | 0 | FINAL
|  | Schematic Design Documents | 6734 |  | 6734 |  | 0
|  | Design Development Documents | 6734 |  | 6734 |  | 0
|  | Construction Documents | 14365 |  | 14365 |  | 0
|  | Bidding | 0 |  |  |  | 0
|  | Construction Administration | 0 |  |  |  | 0
|  | Total: | 27833 |  | 27833 |  | 0

## RECAP #9239.01
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
| Program code 923901 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1929092.95
C | Farnsworth Group |  | 142779 | 142779 | 0
C | PM TIME |  | 22472.5 | 22472.5 | 0
C | Misc. |  | 1350.24 | 1350.24 | 0
C | Samuels Group #120PC |  | 8624.99 | 8624.99 | 0
C | Interstate Power & Light |  | 15692.56 | 15692.56 | 0
C | Van Maanen Electric |  | 144530.85 | 144530.85 | 0
C | Sunrise Post & Frame LLC |  | 691438.76 | 691438.76 | 0
C | Samuels Group #120CA |  | 111529.81 | 111529.81 | 0
C | Accurate Commercial |  | 706218.73 | 706218.73 | 0
C | Samuels Group #120CA-ECSB |  | 80538.84 | 80538.84 | 0
C | Interstate Power & Light (2) |  | 2065.09 | 2065.09 | 0
C | Interstate Power & Light (3) |  | 1851.58 | 1851.58 | 0
| Total Project Cost | 1929092.95 | 1929092.95 | 1929092.95 | 0 | 0
CLOSED 05/15/2024

## #9239.01 Funds Rec'd
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU Amendment #1 | IET 0ADASFIX060122 | 2022-06-01 | 100000 | 100000
|  |  | Return FY22 Funds to Agency | IET 33522215817 | 2022-08-03 | -98950 | -98950
|  |  | Received FY23 Funds from Agency | IET 0ADASFIX083122 | 2022-09-02 | 98950 | 98950
|  |  | Funds transferred without program code | CDR 33523249800 | 2022-09-06 | 0 | 0
|  |  | MOU Amendment #2 | IET 0ADASFIX110122 | 2022-11-01 | 900000 | 900000
|  |  | Funds transferred without program code | CDR 33523306800 | 2022-11-02 | 0 | 0
|  |  | Transfer funds from DA23 9239.01 to DA22 9239.1 Per PM | IET 33523048901 | 2023-02-17 | 1000000 | 1000000
|  |  | Funds transferred per MOU Amend #1 from 9239.00 | CDR 33523171901 | 2023-06-20 | 31036.86 | 31036.86
|  |  | Return FY23 Funds to Agency | IET 33523227913 | 2023-08-15 | -1325715.71 | -1325715.71
|  |  | Received FY24 Funds from Agency | IET 0ADASFIX082123 | 2023-08-23 | 1325715.71 | 1325715.71
|  |  | Funds transferred without program code | CDR 33524236901 | 2023-08-24 | 0 | 0
|  |  | Return Funds to Agency Per PM | IET 33524120913 | 2024-04-29 | -90000 | -90000
|  |  | Return Funds to Agency Per PM | IET 33524135909 | 2024-05-15 | -11943.91 | -11943.91
| Total Requested | 0 | Total Transferred |  |  | 1929092.95 | 1929092.95

## #9239.01 Farnsworth Group
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA22-9620 |  |  | RFP913300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523249805 | 2022-09-06 | PO Procore | 81675 | 81675 |  |  | 81675
PRC 3352324PA9805 | 2022-09-13 | Inv. 9239.01-1 |  | 81675 | 25863.75 | 25863.75 | 55811.25
PRC 3352324PB9805 | 2022-10-27 | Inv. 9239.01-2 |  | 81675 | 11979 | 37842.75 | 43832.25
PRC 3352324PC9805 | 2022-12-21 | Inv. 9239.01-3 |  | 81675 | 11706.75 | 49549.5 | 32125.5
PRC 3352324PD9805 | 2023-01-11 | Inv. 9239.01-4 |  | 81675 | 22869 | 72418.5 | 9256.5
PRC 3352324PE9805 | 2023-02-14 | Inv. 9239.01-5 |  | 81675 | 3811.5 | 76230 | 5445
PO 33523249805 | 2023-03-24 | CO #1 | 20914 | 102589 |  | 76230 | 26359
PO 33523249805 | 2023-03-31 | CO #2 | 19290 | 121879 |  | 76230 | 45649
PRC 3352324PF9805 | 2023-04-03 | Inv. 9239.01-6 |  | 121879 | 5445 | 81675 | 40204
PRC 3352324PG9805 | 2023-04-26 | Inv. 9239.01-7 |  | 121879 | 2091.4 | 83766.4 | 38112.6
PRC 3352324PH9805 | 2023-05-17 | Inv. 9239.01-8 |  | 121879 | 15224.84 | 98991.24 | 22887.76
PRC 3352324PI9805 | 2023-06-09 | Inv. 9239.01-9 |  | 121879 | 5096.6 | 104087.84 | 17791.16
PO 33523249805 | 2023-06-30 | CO #3 | 20900 | 142779 |  | 104087.84 | 38691.16
PRC 3352324PJ9805 | 2023-07-07 | Inv. 9239.01-10 |  | 142779 | 3987.92 | 108075.76 | 34703.24 | FY23
PO 33524249805 | 2023-08-24 | Roll to FY24 | 0 | 142779 |  | 108075.76 | 34703.24
PRC 3352424PK9805 | 2023-09-21 | Inv. 9239.01-11 |  | 142779 | 15471.04 | 123546.8 | 19232.2
PRC 3352424PL9805 | 2023-10-18 | Inv. 9239.01-12 |  | 142779 | 6061.7 | 129608.5 | 13170.5
PRC 3352424PM9805 | 2023-11-14 | Inv. 9239.01-13 |  | 142779 | 3344.42 | 132952.92 | 9826.08
PRC 3352424PN9805 | 2023-12-15 | Inv. 9239.01-14 |  | 142779 | 2717.98 | 135670.9 | 7108.1
PRC 3352424PO9805 | 2024-01-29 | Inv. 9239.01-15 |  | 142779 | 3554.4 | 139225.3 | 3553.7
PRC 3352424PP9805 | 2024-02-22 | Inv. 9239.01-16-Final |  | 142779 | 3553.7 | 142779 | 0
|  | Totals: | 142779 |  | 142779 |  | 0 | FINAL
|  | Schematic Design Documents | 21780 |  | 21780 |  | 0
|  | Design Development Documents | 16335 |  | 16335 |  | 0
|  | Construction Documents | 38115 |  | 38115 |  | 0
|  | Bidding | 5445 |  | 5445 |  | 0
|  | CO #1 | 20914 |  | 20914 |  | 0
|  | CO #2 | 19290 |  | 19290 |  | 0
|  | CO #3 | 20900 |  | 20900 |  | 0
|  | Total: | 142779 |  | 142779 |  | 0

## #9239.01 PM TIME
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS 907L
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 22472.5 | 22472.5 |  |  | 22472.5
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 22472.5 | 1050 | 1050 | 21422.5
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 22472.5 | 375 | 1425 | 21047.5
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 22472.5 | -375 | 1050 | 21422.5
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 22472.5 | 412.5 | 1462.5 | 21010
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 22472.5 | 742.5 | 2205 | 20267.5
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 22472.5 | 770 | 2975 | 19497.5
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 22472.5 | 687.5 | 3662.5 | 18810
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 22472.5 | 522.5 | 4185 | 18287.5
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 565.81 | 23038.31 | 565.81 | 4750.81 | 18287.5
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -565.81 | 22472.5 | -565.81 | 4185 | 18287.5
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 765.69 | 23238.19 | 765.69 | 4950.69 | 18287.5
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -765.69 | 22472.5 | -765.69 | 4185 | 18287.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 694.96 | 23167.46 | 694.96 | 4879.96 | 18287.5
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -694.96 | 22472.5 | -694.96 | 4185 | 18287.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 778.33 | 23250.83 | 778.33 | 4963.33 | 18287.5
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -778.33 | 22472.5 | -778.33 | 4185 | 18287.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 463.24 | 22935.74 | 463.24 | 4648.24 | 18287.5
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -463.24 | 22472.5 | -463.24 | 4185 | 18287.5
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 22472.5 | 495 | 4680 | 17792.5
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 22472.5 | 687.5 | 5367.5 | 17105
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 22472.5 | 797.5 | 6165 | 16307.5
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 22472.5 | 1127.5 | 7292.5 | 15180
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 22472.5 | 797.5 | 8090 | 14382.5
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 22472.5 | 770 | 8860 | 13612.5
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 22472.5 | 1320 | 10180 | 12292.5
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 22472.5 | 1430 | 11610 | 10862.5
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 22472.5 | 1787.5 | 13397.5 | 9075
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 22472.5 | 1677.5 | 15075 | 7397.5
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 22472.5 | 1595 | 16670 | 5802.5
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 22472.5 | 907.5 | 17577.5 | 4895
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 22472.5 | 1017.5 | 18595 | 3877.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 22472.5 | 797.5 | 19392.5 | 3080
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 22472.5 | 1045 | 20437.5 | 2035
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 22472.5 | 1237.5 | 21675 | 797.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 22472.5 | 797.5 | 22472.5 | 0
[5 empty] | 22472.5 |  | 22472.5 | 0
|  |  | Totals | 22472.5 |  | 22472.5 |  | 0
Note on E9: Huggins, Joni [DAS]: 9239.01 - DOC NCF IPI Homes for Iowa Facility Project - Warehouse $Joni Tonyan, Brad 1:02 PM (7 minutes ago) to me, Jennifer, Scott, Brad Finance, Now that the funding has been received for project 9239.01 would you please set up the PM time for this project to start at $10,000 as the initial funding is to get us through design. DA22 - 9239.01 - PM Time - $10,000 Thank you, J Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Re: 9239.01 - 801 CMPC - Samuels Group Exhibit #120PC - Warehouse $Selma Tonyan, Brad 3:47 PM (8 minutes ago) to me Selma, Please reduce the PM time by that amount so it works. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Sep 6, 2022 at 3:38 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi Brad, Can you please look at the financials and compare them to what you have in Procore? Somehow somewhere I'm short $344.68 and I can't build this PO in 9239.01. Let me know what you find out please. Or give me a call if that's easier. Respectfully, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov Re: DAS MOU - DOC NCF IPI Homes for Iowa Facility Project - Warehouse - 9239.01 Amendment #03 $Joni Tonyan, Brad 12:43 PM (3 minutes ago) to me, Jennifer, Joni Finance, Please adjust the PM time in project 9239.01 in DA22 from the current value of $9,655.32 to an overall total of $20,000. So increase the current total in the DA22 PM Time budget by $10,344.68. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov PM Time / Budget Adjustments $Joni Tonyan, Brad 1:33 PM (30 minutes ago) to me, Scott, Brad Finance, Please make the following adjustments/set ups: DA22: 9295.00 - Increase PM Time by $5K 9239.01 - Increase PM Time by $5K

## #9239.01 Misc
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523032902 | 2023-02-01 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV027142 | 649.79 | 649.79
PRC 33523173801 | 2023-06-22 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV031029 | 700.45 | 1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
1350.24
|  |  |  | Totals |  | 1350.24

## #9239.01 Samuels Group #120PC
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Samuels Group #120PC |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523249806 | 2022-09-06 | PO Procore | 8669.68 | 8669.68 |  |  | 8669.68
PRC 3352324PA9806 | 2022-09-09 | Inv. 7427.01923901 |  | 8669.68 | 622.4 | 622.4 | 8047.28
PRC 3352324PB9806 | 2022-09-30 | Inv. 7427.02923901 |  | 8669.68 | 1155.42 | 1777.82 | 6891.86
PRC 3352324PC9806 | 2022-11-07 | Inv. 7427.03923901 |  | 8669.68 | 2462.55 | 4240.37 | 4429.31
PRC 3352324PD9806 | 2022-12-09 | Inv. 7427.04923901 |  | 8669.68 | 660.3 | 4900.67 | 3769.01
PRC 3352324PE9806 | 2023-01-09 | Inv. 7427.05923901 |  | 8669.68 | 1721.09 | 6621.76 | 2047.92
PRC 3352324PF9806 | 2023-02-08 | Inv. 7427.06923901-Final | -44.69 | 8624.99 | 2003.23 | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  |  |  | 8624.99 |  | 8624.99 | 2.8422e-13
|  | Totals: | 8624.99 |  | 8624.99 |  | 0
|  | CM Services | 8499.89 |  | 8499.89 |  | 0
|  | Reimbursables | 125.1 |  | 125.1 |  | 0
|  | Total: | 8624.99 |  | 8624.99 |  | 0

## #9239.01 Interstate PowerLight
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Interstate Power & Light |  |  | Vendor: 00002106184
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523334902 | 2022-11-30 | PO Procore | 15692.76 | 15692.76 |  |  | 15692.76
PRC 3352333PA4902 | 2023-07-14 | Inv. 9238.01-01-Final | -0.2 | 15692.56 | 15692.56 | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  |  |  | 15692.56 |  | 15692.56 | 7.2758e-13
|  | Totals: | 15692.56 |  | 15692.56 |  | 0 | FINAL
|  | Line 1 Material Expense | 5811.03 |  | 5811.03 |  | 0
|  | Line 2 Labor Expense | 5130.05 |  | 5130.05 |  | 0
|  | Line 3 Vehicle Expense | 2429.48 |  | 2429.48 |  | 0
|  | Line 4 Iowa Advance Tax Adder | 2322 |  | 2322 |  | 0
|  | Total: | 15692.56 |  | 15692.56 |  | 0

## #9239.01 Van Maanen Electric
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Van Maanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA22-9255 |  |  | RFB923901-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523033902 | 2023-02-01 | PO Procore | 145520 | 145520 |  |  | 145520
PRC 3352303PA3902 | 2023-05-30 | Inv. 2249-01 |  | 145520 | 17032.76 | 17032.76 | 128487.24 | 896.46
PRC 3352303PB3902 | 2023-06-29 | Inv. 2249-02 |  | 145520 | 19874.76 | 36907.52 | 108612.48 | 1942.5 | FY23
PO 33524033902 | 2023-08-24 | Roll to FY24 | 0 | 145520 |  | 36907.52 | 108612.48
PRC 3352403PC3902 | 2023-08-24 | Inv. 2249-03 |  | 145520 | 9032.29 | 45939.81 | 99580.19 | 2417.88
PO 33524033902 | 2023-09-06 | CO #1 | -4244.89 | 141275.11 |  | 45939.81 | 95335.3
PO 33524033902 | 2023-10-19 | CO #2 | 3255.74 | 144530.85 |  | 45939.81 | 98591.04
PRC 3352403PD3902 | 2023-12-12 | Inv. 2249-04 |  | 144530.85 | 89982.05 | 135921.86 | 8608.99 | 7153.79
PRC 3352403PE3902 | 2024-02-07 | Inv. 2249-05 |  | 144530.85 | 1382.44 | 137304.3 | 7226.55 | 7226.55
PRC 3352403PF3902 | 2024-02-19 | Inv. 2249-06 Retainage |  | 144530.85 | 7226.55 | 144530.85 | 0
|  |  |  | 144530.85 |  | 144530.85 | 0
|  |  |  | 144530.85 |  | 144530.85 | 0
|  |  |  | 144530.85 |  | 144530.85 | 0
|  | Totals: | 144530.85 |  | 144530.85 |  | 0

## #9239.01 Sunrise Post & Frame
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Sunrise Post & Frame LLC |  |  | Vendor: 00003172529
Acct. Codes-0506-335-DA22-9255 |  |  | RFB923901-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523055800 | 2023-02-24 | PO Procore | 680025 | 680025 |  |  | 680025
PRC 3352305PA5800 | 2023-06-27 | Inv. 25210 |  | 680025 | 196984.15 | 196984.15 | 483040.85 | 10367.58
PRC 3352305PB5800 | 2023-07-17 | Inv. 23506 |  | 680025 | 287373.16 | 484357.31 | 195667.69 | 25492.48 | FY23
PO 33524055800 | 2023-08-24 | Roll to FY24 | 0 | 680025 |  | 484357.31 | 195667.69
PO 33524055800 | 2023-08-24 | CO #1 | 11413.76 | 691438.76 |  | 484357.31 | 207081.45
PRC 3352405PC5800 | 2023-08-24 | Inv. 25253 |  | 691438.76 | 54304.03 | 538661.34 | 152777.42 | 28350.58
PRC 3352405PD5800 | 2023-09-19 | Inv. 26059 |  | 691438.76 | 109505.16 | 648166.5 | 43272.26 | 34114.01
PRC 3352405PE5800 | 2023-11-27 | Inv. 158976 |  | 691438.76 | 2240.1 | 650406.6 | 41032.16 | 34231.91
PRC 3352405PF5800 | 2024-01-03 | Inv. 23524 |  | 691438.76 | 6460.24 | 656866.84 | 34571.92 | 34571.92
PRC 3352405PG5800 | 2024-01-11 | Inv. 25534 retainage |  | 691438.76 | 34571.92 | 691438.76 | 0
|  |  |  | 691438.76 |  | 691438.76 | 0
|  |  |  | 691438.76 |  | 691438.76 | 0
|  |  |  | 691438.76 |  | 691438.76 | 0
|  | Totals: | 691438.76 |  | 691438.76 |  | 0

## #9239.01 Samuels Group #120CA
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Samuels Group #120CA |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523055901 | 2023-02-24 | PO Procore | 107530.3 | 107530.3 |  |  | 107530.3
PRC 3352305PA5901 | 2023-03-06 | Inv. 7427.51923901 |  | 107530.3 | 2679.12 | 2679.12 | 104851.18
PRC 3352305PB5901 | 2023-04-04 | Inv. 7427.52923901 |  | 107530.3 | 4945.23 | 7624.35 | 99905.95
PRC 3352305PC5901 | 2023-05-11 | Inv. 7427.53923901 |  | 107530.3 | 4545.34 | 12169.69 | 95360.61
PRC 3352305PD5901 | 2023-06-07 | Inv. 7427.54923901 |  | 107530.3 | 11154.49 | 23324.18 | 84206.12
PO 33523055901 | 2023-06-08 | CO #1 | 4000 | 111530.3 |  | 23324.18 | 88206.12
PRC 3352305PE5901 | 2023-07-10 | Inv. 7427.55923901 |  | 111530.3 | 16808.59 | 40132.77 | 71397.53 | FY23
PO 33524055901 | 2023-08-24 | Roll to FY24 | 0 | 111530.3 |  | 40132.77 | 71397.53
PRC 3352405PF5901 | 2023-08-25 | Inv. 7427.56923901 |  | 111530.3 | 20965.94 | 61098.71 | 50431.59
PRC 3352405PG5901 | 2023-09-14 | Inv. 7427.57923901 |  | 111530.3 | 12725.39 | 73824.1 | 37706.2
PRC 3352405PH5901 | 2023-10-05 | Inv. 7427.58923901 |  | 111530.3 | 6924.1 | 80748.2 | 30782.1
PRC 3352405PI5901 | 2023-11-09 | Inv. 7427.59923901 |  | 111530.3 | 17740.01 | 98488.21 | 13042.09
PRC 3352405PJ5901 | 2023-12-13 | Inv. 7427.60923901 |  | 111530.3 | 6277.74 | 104765.95 | 6764.35
PRC 3352405PK5901 | 2024-01-05 | Inv. 7427.61923901 |  | 111530.3 | 3937.88 | 108703.83 | 2826.47
PRC 3352405PL5901 | 2024-02-02 | Inv. 7427.62923901 |  | 111530.3 | 2244.85 | 110948.68 | 581.62
PRC 3352405PM5901 | 2024-02-22 | Inv. 7427.63923901-FINAL | -0.49 | 111529.81 | 581.13 | 111529.81 | 1.4902e-11
|  |  |  | 111529.81 |  | 111529.81 | 1.4902e-11
|  | Totals: | 111529.81 |  | 111529.81 |  | 0 | FINAL
|  | CM Services | 63657.61 |  | 63657.61 |  | 0
|  | Reimbursables | 2596 |  | 2596 |  | 0
|  | Fees | 41276.2 |  | 41276.2 |  | 0
|  | CO #1 | 4000 |  | 4000 |  | 0
|  | Total: | 111529.81 |  | 111529.81 |  | 0

## #9239.01 Accurate Commercial
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Accurate Commercial |  |  | Vendor: 00003177484
Acct. Codes-0506-335-DA22-9255 |  |  | RFB923901-02
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523174803 | 2023-06-23 | PO Procore | 697000 | 697000 |  |  | 697000 |  | FY23
PO 33524174803 | 2023-08-24 | Roll to FY24 | 0 | 697000 |  | 0 | 697000
PO 33524174803 | 2023-10-19 | CO #1 | -6651.42 | 690348.58 |  | 0 | 690348.58
PRC 3352417PA4803 | 2023-10-23 | Inv. 2300411-1 |  | 690348.58 | 144510.06 | 144510.06 | 545838.52 | 7605.79
PRC 3352417PB4803 | 2023-11-16 | Inv. 2300411-2 |  | 690348.58 | 213473.52 | 357983.58 | 332365 | 18841.25
PO 33524174803 | 2023-11-21 | CO #2 | 1370.15 | 691718.73 |  | 357983.58 | 333735.15
PO 33524174803 | 2023-12-07 | CO #3 | 14500 | 706218.73 |  | 357983.58 | 348235.15
PRC 3352417PC4803 | 2023-12-15 | Inv. 2300411-3 |  | 706218.73 | 131195.83 | 489179.41 | 217039.32 | 25746.29
PO 33524174803 | 2024-01-10 | CO #4 (No Cost CO) | 0 | 706218.73 |  | 489179.41 | 217039.32
PRC 3352417PD4803 | 2024-01-19 | Inv. 2300411-4 |  | 706218.73 | 74776.66 | 563956.07 | 142262.66 | 29681.92
PRC 3352417PE4803 | 2024-02-19 | Inv. 2300411-5 |  | 706218.73 | 92715.95 | 656672.02 | 49546.71 | 34561.71
PRC 3352417PF4803 | 2024-05-03 | Inv. 2300411-6 |  | 706218.73 | 14235.75 | 670907.77 | 35310.96 | 35310.96
PRC 3352417PG4803 | 2024-05-13 | Inv. 2300411-7 Retainage |  | 706218.73 | 35310.96 | 706218.73 | 0
|  | Totals: | 706218.73 |  | 706218.73 |  | 0

## #9239.01 Samuels Group #120 (2)
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Samuels Group #120CA-ECSB |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524236801 | 2023-08-24 | PO Procore | 77576.36 | 77576.36 |  |  | 77576.36
PRC 3352423PA6801 | 2023-09-14 | Inv. 7427.70923901ECSB |  | 77576.36 | 13035.67 | 13035.67 | 64540.69
PRC 3352423PB6801 | 2023-10-05 | Inv. 7427.71923901ECSB |  | 77576.36 | 11728.5 | 24764.17 | 52812.19
PRC 3352423PC6801 | 2023-11-09 | Inv. 7427.72923901ECSB |  | 77576.36 | 14773.02 | 39537.19 | 38039.17
PRC 3352423PD6801 | 2023-12-13 | Inv. 7427.73923901ECSB |  | 77576.36 | 14817.81 | 54355 | 23221.36
PRC 3352423PE6801 | 2024-01-05 | Inv. 7427.74923901ECSB |  | 77576.36 | 8912.05 | 63267.05 | 14309.31
PO 33524236801 | 2024-01-24 | CO #1 | 3250 | 80826.36 |  | 63267.05 | 17559.31
PRC 3352423PF6801 | 2024-02-05 | Inv. 7427.75923901ECSB |  | 80826.36 | 10608.21 | 73875.26 | 6951.1
PRC 3352423PG6801 | 2024-03-06 | Inv. 7427.76923901ECSB |  | 80826.36 | 3237.64 | 77112.9 | 3713.46
PRC 3352423PH6801 | 2024-04-30 | Inv. 7427.77923901ECSB |  | 80826.36 | 1955.22 | 79068.12 | 1758.24
PRC 3352423PI6801 | 2024-05-06 | Inv. 7427.78923901ECSB |  | 80826.36 | 760.98 | 79829.1 | 997.26
PRC 3352423PJ6801 | 2024-05-14 | Inv. 7427.79923901ECSB-Final | -287.52 | 80538.84 | 709.74 | 80538.84 | 2.2737e-12
|  |  |  | 80538.84 |  | 80538.84 | 2.2737e-12
|  | Totals: | 80538.84 |  | 80538.84 |  | 0 | FINAL
|  | CM Services | 42436.36 |  | 42436.36 |  | 0
|  | Reimbursables | 7260 |  | 7260 |  | 0
|  | Fees | 27880 |  | 27880 |  | 0
|  | CO #1 | 2962.48 |  | 2962.48 |  | 0
|  | Total: | 80538.84 |  | 80538.84 |  | 0

## #9239.01 Interstate Power (2)
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Interstate Power & Light (2) |  |  | Vendor: 00002106184
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524270800 | 2023-09-27 | PO Procore | 1652.07 | 1652.07 |  |  | 1652.07
PO 33524270800 | 2023-11-16 | CO #1 | 413.02 | 2065.09 |  | 0 | 2065.09
PRC 3352427PA0800 | 2023-11-16 | Inv. WR4329322-Account#8533267865 |  | 2065.09 | 2065.09 | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  |  |  | 2065.09 |  | 2065.09 | 0
|  | Totals: | 2065.09 |  | 2065.09 |  | 0

## #9239.01 Interstate Power (3)
DOC-NCF-IPI Homes for Iowa Facility Project–Warehouse
Project # 9239.01
Program code 923901 |  |  | Major Program 4E01
Interstate Power & Light (3) |  |  | Vendor: 00002106184
Acct. Codes-0506-335-DA22-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524284804 | 2023-10-11 | PO Procore | 2015.21 | 2015.21 |  |  | 2015.21
PRC 3352428PA4804 | 2024-02-14 | Inv. WR#4337895-Account#8533267865 | -163.63 | 1851.58 | 1851.58 | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  |  |  | 1851.58 |  | 1851.58 | 0
|  | Totals: | 1851.58 |  | 1851.58 |  | 0 | FINAL

## RECAP #9241.00
ILEA JOH New Storage Building
Project # 9241.00
| Program code 924100 |  |  | Major Program 3A02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 2187.16
C | DCI Group |  | 1537.16 | 1537.16 | 0
C | PM TIME |  | 650 | 650 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 2187.16 | 2187.16 | 2187.16 | 0 | 0
Closed 2/10/22

## #9241.00 Funds Rec'd
ILEA JOH New Storage Building
Project # 9241.00
Program code 924100 |  |  | Major Program 3A02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | 46722000208 | 2021-10-11 | 30000 | 30000
|  |  | Return funds to Agency | IET 33522039900 | 2022-02-08 | -27812.84 | -27812.84
| Total Requested | 0 | Total Transferred |  |  | 2187.16 | 2187.16

## #9241.00 DCI Group
ILEA JOH New Storage Building
Project # 9241.00
Program code 924100 |  |  | Major Program 3A02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP0215335062-DCI9112015
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522321800 | 2021-11-16 | PO Procore | 2905.1 | 2905.1 |  |  | 2905.1
PRC 3352232PA1800 | 2021-12-20 | Inv. 21-050-01 |  | 2905.1 | 1007.09 | 1007.09 | 1898.01
PRC 3352232PB1800 | 2022-01-21 | Inv. 21-050 02 Final | -1367.94 | 1537.16 | 530.07 | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  |  |  | 1537.16 |  | 1537.16 | 0
|  | Totals: | 1537.16 |  | 1537.16 |  | 0

## #9241.00 PM TIME
ILEA JOH New Storage Building
Project # 9241.00
Program code 924100 |  |  | Major Program 3A02
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Brad T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 650 | 650 |  |  | 650
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 650 | 275 | 275 | 375
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 650 | 150 | 425 | 225
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec 30, 2021 |  | 650 | 50 | 475 | 175
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 650 | 175 | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  |  |  | 650 |  | 650 | 0
|  | Totals: | 650 |  | 650 |  | 0
Note on D9: Wray, Ronda [DAS]: PM Time Set up on New Project $Ronda Tonyan, Brad 12:44 PM (1 hour ago) to me, Scott Finance, Can you please set up the following PM time budget below: - DA22 - 9241.00 - ILEA JOH New Storage Building - $4,000 Thank you, Brad Tonyan, Owner Representative

## #9241.00 Misc
ILEA JOH New Storage Building
Project # 9241.00
Program code 924100 |  |  |  | Major Program 3A02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9242.00
DAS CC Lucas Elevator Replacements
Project # 9242.00
| Program code 924200 |  |  | Major Program 4D03
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1963201.35
C | DCI Group |  | 17520.06 | 17520.06 | 0
C | PM TIME |  | 37322.69 | 37322.69 | 0
C | Misc. |  | 7612.3 | 7612.3 | 0
C | OPN Architects |  | 149640 | 149640 | 0
C | DCI Group #21-041 CA |  | 155241.88 | 155241.88 | 0
C | Bergstrom Construction |  | 28700 | 28700 | 0
C | Air Con Mechanical |  | 181199.42 | 181199.42 | 0
C | Schumacher Elevator |  | 1377942 | 1377942 | 0
C | Control Installations |  | 8023 | 8023 | 0
| Total Project Cost | 1963201.35 | 1963201.35 | 1963201.35 | 0 | 0
Closed 05/08/24

## #9242.00 Funds Rec'd
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 005FY22PROJ924200 | 2021-10-18 | 1400000 | 1400000
|  |  | MOU Amend 1 | IET 005FY23PROJ924200 | 2022-07-15 | 600000 | 600000
|  |  | Return FY22 Funds to Agency | IET 33522215818 | 2022-08-03 | -1877930.36 | -1877930.36
|  |  | Received FY23 Funds From Agency | IET 005FY23PROJ924200A | 2022-08-04 | 1877930.36 | 1877930.36
|  |  | Return FY23 Funds to Agency-returned incorrect amount in FY22 | IET 33523257904 | 2022-09-14 | -600000 | -600000
|  |  | Receive FY22 Funds | IET 005FY22PROJ924200A1 | 2022-09-14 | 600000 | 600000
|  |  | Return FY23 Funds to Agency | IET 33523227914 | 2023-08-15 | -223651.44 | -223651.44
|  |  | Received FY24 Funds From Agency | IET 005FY24PROJ924200 | 2023-08-21 | 223651.44 | 223651.44
|  |  | Return FY24 Funds to Agency | IET 33524235808 | 2023-08-23 | -3324.65 | -3324.65
|  |  | FY23 Funds Received | IET 005FY23PROJ9242001 | 2023-08-24 | 3324.65 | 3324.65
|  |  | FY23 Funds Received | IET 005FY23PROJ924200B | 2023-08-24 | 3324.65 | 3324.65
|  |  | Reverse IET 005FY23PROJ9242001 | IET 335FY23PROJ924200 | 2023-08-25 | -3324.65 | -3324.65
|  |  | Return Funds to Agency Project Closed | IET 33524129809 | 2024-05-08 | -36798.65 | -36798.65
| Total Requested | 0 | Total Transferred |  |  | 1963201.35 | 1963201.35

## #9242.00 DCI Group
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP0215335062-DCI9112015
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522302801 | 2021-10-28 | PO Procore | 17526.13 | 17526.13 |  |  | 17526.13
PRC 3352230PA2801 | 2021-12-20 | Inv. 21-041 PC-01 |  | 17526.13 | 2701.54 | 2701.54 | 14824.59
PRC 3352230PB2801 | 2022-01-12 | Inv. 21-041 PC-02 |  | 17526.13 | 1402.76 | 4104.3 | 13421.83
PRC 3352230PC2801 | 2022-02-24 | Inv. 21-041 PC-03 |  | 17526.13 | 3096.28 | 7200.58 | 10325.55
PRC 3352230PD2801 | 2022-03-28 | Inv. 21-041 PC-04 |  | 17526.13 | 2849.36 | 10049.94 | 7476.19
PRC 3352230PE2801 | 2022-05-16 | Inv. 21-041 PC-05 |  | 17526.13 | 2711.66 | 12761.6 | 4764.53
PRC 3352230PF2801 | 2022-06-20 | Inv. 21-041 PC-06 |  | 17526.13 | 3811.74 | 16573.34 | 952.79
PRC 3352230PG2801 | 2022-07-18 | Inv. 21-041 PC-07 FINAL | -6.07 | 17520.06 | 946.72 | 17520.06 | -9.7344e-13
|  |  |  | 17520.06 |  | 17520.06 | -9.7344e-13
|  |  |  | 17520.06 |  | 17520.06 | -9.7344e-13
|  |  |  | 17520.06 |  | 17520.06 | -9.7344e-13
|  |  |  | 17520.06 |  | 17520.06 | -9.7344e-13
|  |  |  | 17520.06 |  | 17520.06 | -9.7344e-13
|  | Totals: | 17520.06 |  | 17520.06 |  | 0 | Final Invoice

## #9242.00 PM TIME
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T |  |  |  | eDAS 5889
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 37322.69 | 37322.69 |  |  | 37322.69
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 37322.69 | 525 | 525 | 36797.69
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 37322.69 | 625 | 1150 | 36172.69
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30, 2021 |  | 37322.69 | 950 | 2100 | 35222.69
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 37322.69 | 875 | 2975 | 34347.69
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 37322.69 | 800 | 3775 | 33547.69
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 37322.69 | 800 | 4575 | 32747.69
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 37322.69 | 950 | 5525 | 31797.69
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 37322.69 | 900 | 6425 | 30897.69
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 37322.69 | 1025 | 7450 | 29872.69
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 37322.69 | 600 | 8050 | 29272.69
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 37322.69 | -600 | 7450 | 29872.69
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 37322.69 | 660 | 8110 | 29212.69
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 37322.69 | 1017.5 | 9127.5 | 28195.19
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 37322.69 | 907.5 | 10035 | 27287.69
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 37322.69 | 742.5 | 10777.5 | 26545.19
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 37322.69 | 687.5 | 11465 | 25857.69
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 386.04 | 37708.73 | 386.04 | 11851.04 | 25857.69
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -386.04 | 37322.69 | -386.04 | 11465 | 25857.69
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1049.29 | 38371.98 | 1049.29 | 12514.29 | 25857.69
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -1049.29 | 37322.69 | -1049.29 | 11465 | 25857.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 819.05 | 38141.74 | 819.05 | 12284.05 | 25857.69
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -819.05 | 37322.69 | -819.05 | 11465 | 25857.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 840.61 | 38163.3 | 840.61 | 12305.61 | 25857.69
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -840.61 | 37322.69 | -840.61 | 11465 | 25857.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 609.52 | 37932.21 | 609.52 | 12074.52 | 25857.69
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -609.52 | 37322.69 | -609.52 | 11465 | 25857.69
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 37322.69 | 1045 | 12510 | 24812.69
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 37322.69 | 208.47 | 12718.47 | 24604.22
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 37322.69 | 1827.62 | 14546.09 | 22776.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 37322.69 | 300.84 | 14846.93 | 22475.76
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 37322.69 | 1824.34 | 16671.27 | 20651.42
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 37322.69 | 405.47 | 17076.74 | 20245.95
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 37322.69 | 1783.44 | 18860.18 | 18462.51
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 37322.69 | 243.78 | 19103.96 | 18218.73
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 37322.69 | 1433 | 20536.96 | 16785.73
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 37322.69 | 231.48 | 20768.44 | 16554.25
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 37322.69 | 1619.2 | 22387.64 | 14935.05
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 37322.69 | 197.53 | 22585.17 | 14737.52
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 37322.69 | 1665.1 | 24250.27 | 13072.42
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 37322.69 | 234.19 | 24484.46 | 12838.23
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 37322.69 | 1493.4 | 25977.86 | 11344.83
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 37322.69 | 401.9 | 26379.76 | 10942.93
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 37322.69 | 2247.3 | 28627.06 | 8695.63
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 37322.69 | 182.42 | 28809.48 | 8513.21
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 37322.69 | 1266.7 | 30076.18 | 7246.51
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 37322.69 | 148.77 | 30224.95 | 7097.74
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 37322.69 | 1192.7 | 31417.65 | 5905.04
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 37322.69 | 115.72 | 31533.37 | 5789.32
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 37322.69 | 875 | 32408.37 | 4914.32
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 37322.69 | 172.02 | 32580.39 | 4742.3
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 37322.69 | 1262.1 | 33842.49 | 3480.2
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 37322.69 | 126.37 | 33968.86 | 3353.83
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 37322.69 | 1116.4 | 35085.26 | 2237.43
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 37322.69 | 160.98 | 35246.24 | 2076.45
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 37322.69 | 810.8 | 36057.04 | 1265.65
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 37322.69 | 58.56 | 36115.6 | 1207.09
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 37322.69 | 442.6 | 36558.2 | 764.49
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 37322.69 | 76.99 | 36635.19 | 687.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 37322.69 | 687.5 | 37322.69 | 0
[5 empty] | 37322.69 |  | 37322.69 | 0
[5 empty] | 37322.69 |  | 37322.69 | 0
|  |  | Totals: | 37322.69 |  | 37322.69 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time Set up on New Project $Selma Tonyan, Brad 10:39 AM (2 hours ago) to me, Scott Finance, Can you please set up the following PM time budget below: - DA22 - 9242.00 - DAS CC Lucs Elevator Replacements - $15,000 Thank you, Brad Tonyan, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Billables and PM Time Adjustments $Joni Tonyan, Brad Feb 23, 2023, 4:15 PM (17 hours ago) to me, Scott, Brad Finance, Please make the following changes with Josh moving on and Doug retiring as some of the projects are not on my billables sheet. While I am on it I have made some PM time adjustments to cover some of the billing changes or construction oversight. - DA20 - 9118.00 - Raise PM time budget $3,000 - MM21 - 9204.00 - Raise PM time budget $2,000 - MM22 - 9235.00 - Raise PM time budget $5,000 - DA22 - 9239.00 - Raise PM time budget $2,500 - DA22 - 9242.00 - Raise PM time budget $15,000 - DA22 - 9280.00 - Add this project to my billables as I took from Doug - DA22 - 9281.00 - Add this project to my billables as I took from Doug Thank you and I think that is all for now. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Re: PM Time $John Tonyan, Brad 3:13 PM (9 minutes ago) to me John, Please see the following below: DA22 - 9242.00 - Increase budget by $5,000 please MM23 - 9306.00 - Increase budget by $3,000 please Thank you Re: PM Time Inbox Tonyan, Brad 2:58 PM (6 minutes ago) to DAS, me, Brad John and Finance, 9172.00 DA21 Amount to post 625.90 Brad update - Please raise total PM time budget to $60K 9242.00 DA22 Amount to post 751.30 Brad update - Please raise total PM time budget to $38K 9282.00 DA22 Amount to post 284.68 Brad update - Please increase only to cover this amount and stop charging edas time to DA22 and instead charge time to MM24 9282.00 org. 9291.00 MM22 Amount to post 1211.10 Brad update - Please raise total PM time budget to $25K 9324.00 MM23 Amount to post 459.80 Brad update - Please raise total PM time budget to $18K

## #9242.00 Misc
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  |  | Major Program 4D03
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202207115300001 | 2022-02-08 | 2507 |  | Space Planning Services | DAS2022071153 | 42.5 | 42.5
GAX 33522077900 | 2022-03-17 | 9500 | CNST | Schumacher Elevator(V#00002108471) | Inv. MISC-Document #90547406 | 828 | 870.5
IET 335FY22924200 | 2022-04-19 | 2398 |  | ICN Bill March 2022 | Inv. 643525 | 120 | 990.5
GAX 33522123900 | 2022-04-02 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2422884-Final | 1612.5 | 2603
IET DAS202210115300001 | 2022-05-06 | 2507 |  | Space Planning Services | DAS2022101153 | 21.25 | 2624.25
PRC 33522186901 | 2022-06-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV021924 | 302.53 | 2926.78
GAX 33523347803 | 2022-12-13 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2470879 - Final | 195 | 3121.78
IET DAS202305115300001 | 2022-12-07 | 2507 |  | Fire Watch 207137271 | DAS2023051153 | 312.51 | 3434.29
IET DAS202308115300001 | 2022-03-07 | 2507 |  | Space Planning Services | DAS2023081153 | 47.5 | 3481.79
IET DAS202309115300001 | 2023-04-07 | 2507 |  | Space Planning Services March 1-31, 2023 | DAS2023091153 | 47.5 | 3529.29
IET DAS202311115300001 | 2023-06-07 | 2507 |  | Lucas Elevators | DAS2023111153 | 191.35 | 3720.64
IET DAS202311115300001 | 2023-06-07 | 2501 |  | DAS elevator switch | DAS2023111153 | 519.51 | 4240.15
IET DAS202401115300001 | 2023-08-07 | 2507 |  | Space Planning Services | DAS2024011153 | 47.5 | 4287.65
IET 335FY23924200 | 2023-08-25 | 2398 |  | ICN Bill June 2023 | Inv. 673419 | 3324.65 | 7612.3
7612.3
7612.3
7612.3
|  |  |  | Totals: |  | 7612.3

## #9242.00 OPN Architects
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA22-9260 |  |  | RFP924200-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522336800 | 2021-12-02 | PO Procore | 149640 | 149640 |  |  | 149640
PRC 3352233PA6800 | 2022-02-08 | Inv. 21837000-1 |  | 149640 | 18256.08 | 18256.08 | 131383.92
PRC 3352233PB6800 | 2022-02-10 | Inv. 21837000-2 |  | 149640 | 23164.27 | 41420.35 | 108219.65
PRC 3352233PC6800 | 2022-03-21 | Inv. 21837000-3 |  | 149640 | 28873.04 | 70293.39 | 79346.61
PRC 3352233PD6800 | 2022-03-31 | Inv. 21837000-4 |  | 149640 | 1552.52 | 71845.91 | 77794.09
PRC 3352233PE6800 | 2022-05-16 | Inv. 21837000-5 |  | 149640 | 18319.67 | 90165.58 | 59474.42
PRC 3352233PF6800 | 2022-06-07 | Inv. 21837000-6 |  | 149640 | 1863.02 | 92028.6 | 57611.4
PRC 3352233PG6800 | 2022-07-08 | Inv. 21837000-7 |  | 149640 | 2144.2 | 94172.8 | 55467.2 | FY22
PO 33523336800 | 2022-08-09 | Rolled to FY23 | 0 | 149640 |  | 94172.8 | 55467.2
PRC 3352333PH6800 | 2022-09-20 | Inv. 21837000-8 |  | 149640 | 2153.63 | 96326.43 | 53313.57
PRC 3352333PI6800 | 2022-10-13 | Inv. 21837000-9 |  | 149640 | 10484.33 | 106810.76 | 42829.24
PRC 3352333PJ6800 | 2022-11-07 | Inv. 21837000-10 |  | 149640 | 6170.2 | 112980.96 | 36659.04
PRC 3352333PK6800 | 2022-12-08 | Inv. 21837000-11 |  | 149640 | 3309.09 | 116290.05 | 33349.95
PRC 3352333PL6800 | 2023-01-10 | Inv. 21837000-12 |  | 149640 | 2647.27 | 118937.32 | 30702.68
PRC 3352333PM6800 | 2023-02-07 | Inv. 21837000-13 |  | 149640 | 2647.27 | 121584.59 | 28055.41
PRC 3352333PN6800 | 2023-04-04 | Inv. 21837000-14 |  | 149640 | 5913.69 | 127498.28 | 22141.72
PRC 3352333PO6800 | 2023-05-05 | Inv. 21837000-15 |  | 149640 | 6194.62 | 133692.9 | 15947.1
PRC 3352333PP6800 | 2023-05-30 | Inv. 21837000-16 |  | 149640 | 2749.5 | 136442.4 | 13197.6
PRC 3352333PQ6800 | 2023-06-22 | Inv. 21837000-17 |  | 149640 | 1800.92 | 138243.32 | 11396.68
PRC 3352333PR6800 | 2023-07-13 | Inv. 21837000-18 |  | 149640 | 1821.55 | 140064.87 | 9575.13 | FY23
PO 33524336800 | 2023-08-22 | Roll to FY24 | 0 | 149640 |  | 140064.87 | 9575.13
PRC 3352433PS6800 | 2023-08-22 | Inv. 21837000-19 |  | 149640 | 1807.79 | 141872.66 | 7767.34
PRC 3352433PT6800 | 2024-04-16 | Inv. 21837000-20 |  | 149640 | 7767.34 | 149640 | 0
|  |  |  | 149640 |  | 149640 | 0
|  | Totals: | 149640 |  | 149640 |  | 0
|  | Design Development | 29850 |  | 29850 |  | 0
|  | 50% Construction Documents | 31140 |  | 31140 |  | 0
|  | 100% Construction Documents | 31020 |  | 31020 |  | 0
|  | Bidding/Negotiation Assistance | 2640 |  | 2640 |  | 0
|  | Construction Phase | 54990 |  | 54990 |  | 0
|  | Total: | 149640 |  | 149640 |  | 0

## #9242.00 DCI Group (2)
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
DCI Group #21-041 CA |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523223801 | 2022-08-02 | PO Procore | 155254.88 | 155254.88 |  |  | 155254.88
PRC 3352322PA3801 | 2022-09-20 | Inv. 21-041 CA-01 |  | 155254.88 | 8946.12 | 8946.12 | 146308.76
PRC 3352322PB3801 | 2022-11-07 | Inv. 21-041 CA-02 |  | 155254.88 | 6961.12 | 15907.24 | 139347.64
PRC 3352322PC3801 | 2022-11-14 | Inv. 21-041 CA-03 |  | 155254.88 | 7025.6 | 22932.84 | 132322.04
PRC 3352322PD3801 | 2023-01-18 | Inv. 21-041 CA-04 |  | 155254.88 | 17554.19 | 40487.03 | 114767.85
PRC 3352322PE3801 | 2023-03-15 | Inv. 21-041 CA-05 |  | 155254.88 | 30490.2 | 70977.23 | 84277.65
PRC 3352322PF3801 | 2023-04-25 | Inv. 21-041 CA-06 |  | 155254.88 | 16280.86 | 87258.09 | 67996.79
PRC 3352322PG3801 | 2023-06-22 | Inv. 21-041 CA-07 |  | 155254.88 | 38456.5 | 125714.59 | 29540.29
PRC 3352322PH3801 | 2023-07-13 | Inv. 21-041 CA-08 |  | 155254.88 | 16076.49 | 141791.08 | 13463.8 | FY23
PO 33524223801 | 2023-08-22 | Roll to FY24 | 0 | 155254.88 |  | 141791.08 | 13463.8
PRC 3352422PI3801 | 2023-11-13 | Inv. 21-041 CA-09 |  | 155254.88 | 12606.48 | 154397.56 | 857.32
PRC 3352422PJ3801 | 2024-03-04 | Inv. 21-041 CA-10 FINAL | -13 | 155241.88 | 844.32 | 155241.88 | 8.7539e-12
|  |  |  | 155241.88 |  | 155241.88 | 8.7539e-12
|  | Totals: | 155241.88 |  | 155241.88 |  | 0 | FINAL
|  | CM Staff Hours | 78184.78 |  | 78184.78 |  | 0
|  | CM Fee | 77057.1 |  | 77057.1 |  | 0
|  | Total: | 155241.88 |  | 155241.88 |  | 0

## #9242.00 Bergstrom Const
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #924200-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523228903 | 2022-08-16 | PO Procore | 28700 | 28700 |  |  | 28700
PRC 3352322PA8903 | 2023-01-17 | Inv. 8463-1 |  | 28700 | 14254.75 | 14254.75 | 14445.25 | 750.25
PRC 3352322PB8903 | 2023-03-29 | Inv. 8463-2 |  | 28700 | 5970.75 | 20225.5 | 8474.5 | 1064.5
PRC 3352322PC8903 | 2023-06-30 | Inv. 8463-3 |  | 28700 | 6089.5 | 26315 | 2385 | 1385 | FY23
PO 33524228903 | 2023-08-22 | Roll to FY24 | 0 | 28700 |  | 26315 | 2385
PRC 3352422PD8903 | 2024-02-14 | Inv. 8463-4 |  | 28700 | 950 | 27265 | 1435 | 1435
PRC 3352422PE8903 | 2024-03-01 | Inv. 8463-5 |  | 28700 | 1435 | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  |  |  | 28700 |  | 28700 | 0
|  | Totals: | 28700 |  | 28700 |  | 0

## #9242.00 Air Con Electric
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
Air Con Electric |  |  | Vendor: 00003095844
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #924200-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523228904 | 2022-08-16 | PO Procore | 127100 | 127100 |  |  | 127100
PRC 3352322PA8904 | 2022-11-28 | Inv. 1480 |  | 127100 | 19748.92 | 19748.92 | 107351.08 | 1039.43
PO 33523228904 | 2023-01-05 | CO #1 | 2253.62 | 129353.62 |  | 19748.92 | 109604.7
PRC 3352322PB8904 | 2023-01-17 | Inv. 1487 |  | 129353.62 | 57631.4 | 77380.32 | 51973.3 | 4072.68
PRC 3352322PC8904 | 2023-02-07 | Inv. 1492 |  | 129353.62 | 9949.11 | 87329.43 | 42024.19 | 4596.32
PO 33523228904 | 2023-02-09 | CO #2 | 4006 | 133359.62 |  | 87329.43 | 46030.19
PO 33523228904 | 2023-03-16 | CO #3 | 5045 | 138404.62 |  | 87329.43 | 51075.19
PRC 3352322PD8904 | 2023-03-21 | Inv. 1504 |  | 138404.62 | 2697.02 | 90026.45 | 48378.17 | 4738.27
PRC 3352322PE8904 | 2023-03-29 | Inv. 1519 |  | 138404.62 | 10073.96 | 100100.41 | 38304.21 | 5268.49
PO 33523228904 | 2023-04-12 | CO #4 | 12151.39 | 150556.01 |  | 100100.41 | 50455.6
PO 33523228904 | 2023-04-13 | CO #5 | 1065.13 | 151621.14 |  | 100100.41 | 51520.73
PRC 3352322PF8904 | 2023-04-25 | Inv. 1530 |  | 151621.14 | 7032.83 | 107133.24 | 44487.9 | 5638.65
PRC 3352322PG8904 | 2023-05-30 | Inv. 1546 |  | 151621.14 | 13571.89 | 120705.13 | 30916.01 | 6352.96
PO 33523228904 | 2023-05-31 | CO #6 | 9741.29 | 161362.43 |  | 120705.13 | 40657.3
PO 33523228904 | 2023-06-20 | CO #7 | 5499.97 | 166862.4 |  | 120705.13 | 46157.27
PRC 3352322PH8904 | 2023-06-22 | Inv. 1569 |  | 166862.4 | 9454.18 | 130159.31 | 36703.09 | 6850.55
PO 33523228904 | 2023-06-29 | CO #8 | 1073.46 | 167935.86 |  | 130159.31 | 37776.55
PRC 3352322PI8904 | 2023-07-06 | Inv. 1579 |  | 167935.86 | 5224.97 | 135384.28 | 32551.58 | 7125.55 | FY23
PO 33524228904 | 2023-08-22 | Roll to FY24 | 0 | 167935.86 |  | 135384.28 | 32551.58
PO 33524228904 | 2023-08-22 | CO #9 | 8307.95 | 176243.81 |  | 135384.28 | 40859.53
PRC 3352422PJ8904 | 2023-08-22 | Inv. 1596 |  | 176243.81 | 14299.83 | 149684.11 | 26559.7 | 7878.17
PRC 3352422PK8904 | 2023-08-23 | Inv. 1608 |  | 176243.81 | 7364.96 | 157049.07 | 19194.74 | 8265.79
PO 33524228904 | 2023-09-01 | CO #10 | 1481.95 | 177725.76 |  | 157049.07 | 20676.69
PO 33524228904 | 2023-09-19 | CO #11 | 3473.66 | 181199.42 |  | 157049.07 | 24150.35
PRC 3352422PL8904 | 2023-09-29 | Inv. 1626 |  | 181199.42 | 11508.13 | 168557.2 | 12642.22 | 8871.49
PRC 3352422PM8904 | 2024-03-05 | Inv. 1637 |  | 181199.42 | 2374.74 | 170931.94 | 10267.48 | 8996.48
PRC 3352422PN8904 | 2024-03-06 | Inv. 1637-01 |  | 181199.42 | 1207.45 | 172139.39 | 9060.03 | 9060.03
PRC 3352422PO8904 | 2024-03-18 | Inv. 1691 |  | 181199.42 | 9060.03 | 181199.42 | 0
|  | Totals: | 181199.42 |  | 181199.42 |  | 0 | FINAL

## #9242.00 Schumacher Elevator
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
Schumacher Elevator |  |  | Vendor: 00002108471
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #924200-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523229900 | 2022-08-17 | PO Procore | 1385342 | 1385342 |  |  | 1385342
PRC 3352322PA9900 | 2023-02-07 | Inv. 90573018 |  | 1385342 | 412376 | 412376 | 972966 | 21704
PRC 3352322PB9900 | 2023-02-09 | Inv. 90573350 |  | 1385342 | 63481.38 | 475857.38 | 909484.62 | 25045.12
PRC 3352322PC9900 | 2023-03-28 | Inv. 90575949 |  | 1385342 | 464229.84 | 940087.22 | 445254.78 | 49478.28
PRC 3352322PD9900 | 2023-04-04 | Inv. 90578459 |  | 1385342 | 47127.6 | 987214.82 | 398127.18 | 51958.68
PRC 3352322PE9900 | 2023-04-26 | Inv. 90581177 |  | 1385342 | 71605.78 | 1058820.6 | 326521.4 | 55727.4
PRC 3352322PF9900 | 2023-06-01 | Inv. 90583736 |  | 1385342 | 124576.35 | 1183396.95 | 201945.05 | 62284.05
PRC 3352322PG9900 | 2023-06-30 | Inv. 90586303 |  | 1385342 | 88736.65 | 1272133.6 | 113208.4 | 66954.4
PRC 3352322PH9900 | 2023-06-30 | Inv. 90589651 |  | 1385342 | 6626.25 | 1278759.85 | 106582.15 | 67303.15 | FY23
PO 33524229900 | 2023-08-22 | Roll to FY24 | 0 | 1385342 |  | 1278759.85 | 106582.15
PRC 3352422PI9900 | 2024-03-01 | Inv. 90599613 |  | 1385342 | 17125.65 | 1295885.5 | 89456.5 | 68204.5
PO 33524229900 | 2024-04-18 | CO #1 | -7400 | 1377942 |  | 1295885.5 | 82056.5
PRC 3352422PJ9900 | 2024-04-23 | Inv. 90612711 |  | 1377942 | 13159.4 | 1309044.9 | 68897.1 | 68897.1
PRC 3352422PK9900 | 2024-04-26 | Inv. 9242.00-11 Retainage |  | 1377942 | 68897.1 | 1377942 | 0
|  |  |  | 1377942 |  | 1377942 | 0
|  |  |  | 1377942 |  | 1377942 | 0
|  | Totals: | 1377942 |  | 1377942 |  | 0

## #9242.00 Control Installations
DAS CC Lucas Elevator Replacements
Project # 9242.00
Program code 924200 |  |  | Major Program 4D03
Control Installations |  |  | Vendor: 00002115535
Acct. Codes-0506-335-DA22-9255 |  |  | MA 20360
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523192800 | 2023-07-11 | DO Procore | 8023 | 8023 |  |  | 8023
PRC 3352319PA2800 | 2023-07-12 | Inv. 130305/134254 |  | 8023 | 8023 | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  |  |  | 8023 |  | 8023 | 0
|  | Totals: | 8023 |  | 8023 |  | 0
|  | Access Controls - Control Installations of Iowa - 134254 | 4074.89 |  | 4074.89 |  | 0
|  | Access Controls - Control Installations of Iowa - 130305 | 3948.11 |  | 3948.11 |  | 0
|  | Total: | 8023 |  | 8023 |  | 0

## RECAP #9243.00
DOC NCCF Grease Interceptor Evaluation
Project # 9243.00
| Program code 924300 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 4320
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 4320 | 4320 | 0
| Total Project Cost | 4320 | 4320 | 4320 | 0 | 0
Closed 9/2/22
Note on C8: Durakovic, Selma [DAS]: James Trower Projects & PM Time $Selma Trower, James Sep 2, 2022, 3:53 PM (12 days ago) to me Finance - Please see the below items: 9243.00 - DOC NCCF Grease Interceptor Evaluation: Please close this project (It was an evaluation only). 9286.00 - DPS Fleet & Supply Level 2 Floor Framing: It appears the DA22 funding was returned to DAS Finance. This project can be closed and it appears $212.65 will be returned to DPS. 9303.00 - DOC NCCF Kitchen Grease Pit Replacement: Please set up $6,000 in PM Time (MM22). Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9243.00 Funds Rec'd
DOC NCCF Grease Interceptor Evaluation
Project # 9243.00
Program code 924300 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 221025214 | 2021-10-26 | 4320 | 4320
0
| Total Requested | 0 | Total Transferred |  |  | 4320 | 4320

## #9243.00 Vendor A
DOC NCCF Grease Interceptor Evaluation
Project # 9243.00
Program code 924300 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - James T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9243.00 PM TIME
DOC NCCF Grease Interceptor Evaluation
Project # 9243.00
Program code 924300 |  |  | Major Program 4E01
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - James T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 162.5 | 162.5 |  |  | 162.5
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30 2021 |  | 162.5 | 25 | 25 | 137.5
CDE 33522363900 | 2021-12-29 | Moving PM Time expense to MM22 9997.22 | -25 | 137.5 | -25 | 0 | 137.5
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 137.5 | 125 | 125 | 12.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Credit |  |  | -125 | 0 | 137.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Reposted correct amount |  |  | 137.5 | 137.5 | 0
CDE 33523230900 | 2022-08-18 | Moving PM Time expense to MM22 9249.00 | -125 | 12.5 | -125 | 12.5 | 0
CDE 33523236901 | 2022-08-24 | Moving PM Time expense to MM22 9249.00 | -12.5 | 0 | -12.5 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9243.00 Misc
DOC NCCF Grease Interceptor Evaluation
Project # 9243.00
Program code 924300 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA22-9500 |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522019901 | 2022-01-19 | 9500 | CMGR | Shive Hattery V#(00002108803) | Inv. 4216560-1 | 4320 | 4320
4320
4320
4320
4320
4320
4320
4320
4320
4320
4320
4320
|  |  |  | Totals: |  | 4320

## RECAP #9259.00
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
| Program code 925900 |  |  | Major Program 3G01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Doug C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 240000
C | Iowa Contracting |  | 240000 | 240000 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 240000 | 240000 | 240000 | 0 | 0
Closed 01/18/2023

## #9259.00 Funds Rec'd
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Doug C.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU Amend #1 | 005FY23PROJ925900 | 2022-07-18 | 240000 | 240000
0
| Total Requested | 0 | Total Transferred |  |  | 240000 | 240000
*** Original MOU created Feb 2022 - was voided and created new MOU(Mislabeled as Amendmendment #1)

## #9259.00 Iowa Contracting
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
Iowa Contracting |  |  | Vendor: 00003106386
Acct. Codes-0506-335-DA22-9255 |  |  | RFB925900-02
Project Manager - Doug C. |  |  | Activity code: BRUM
Split with MM22 & R21M
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523206900 | 2022-07-18 | PO Procore | 240000 | 240000 |  |  | 240000
PRC 3352320PA6900 | 2022-09-12 | Inv. 9259.00-001(Split with DA22, MM22, & R21M) |  | 240000 | 213750 | 213750 | 26250 | 11250
PO 33523206900 | 2022-10-19 | CO 1(100% to MM22) | 0 | 240000 |  | 213750 | 26250
PO 33523206900 | 2022-11-02 | CO 2(100% to MM22) | 0 | 240000 |  | 213750 | 26250
PRC 3352320PB6900 | 2022-11-08 | Inv. 9259.00-002(Split with DA22, MM22, & R21M) |  | 240000 | 14250 | 228000 | 12000 | 12000
PRC 3352320PC6900 | 2022-12-12 | Inv. 9259.00-003(100% to MM22) |  | 240000 | 0 | 228000 | 12000 | 12000
PRC 3352320PD6900 | 2022-12-19 | Inv. 9259.00-004 Retainage (Split with DA22, MM22, & R21M) |  | 240000 | 12000 | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  |  |  | 240000 |  | 240000 | 0
|  | Totals: | 240000 |  | 240000 |  | 0
|  | MM22 | 488819.65 |  | 488819.65 |  | 0
|  | R21M | 60000 |  | 60000 |  | 0
|  | Total Contract: | 788819.65 |  | 788819.65 |  | 0

## #9259.00 PM TIME
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
PM TIME |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Doug C. |  |  | eDAS 907Z
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget | 110 | 110 |  |  | 110
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 110 | 100 | 100 | 10
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Credit |  | 110 | -100 | 0 | 110
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Reposted correct amount |  | 110 | 110 | 110 | 0
CDE 33523230901 | 2022-08-18 | Moving PM Time to MM22 9259.00 | -100 | 10 | -100 | 10 | 0
CDE 33523236902 | 2022-08-01 | Moving PM Time to MM22 9259.00 | -10 | 0 | -10 | 0 | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 68.47 | 68.47 | 68.47 | 68.47 | 0
CDE 33523353209 | 2022-12-21 | Move PM time to 9997.23 MM23 | -68.47 | 0 | -68.47 | 0 | 0
CDE 33523353210 | 2022-12-22 | Move PM time to 9997.23 MM23 | -47.43 | -47.43 | -47.43 | -47.43 | 0
CDE 33523363900 | 2022-12-29 | Move PM time from 9997.23 MM23 to DA22 | 47.43 | 0 | 47.43 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9259.00 Misc
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  |  | Major Program 3G01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Doug C.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9260.00
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
| Program code 926000 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 127223.77
C | Story Construction |  | 14420.42 | 14420.42 | 0
| PM TIME |  | 6719.35 | 6719.35 | 0
| Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 106084 | 106084 | 0
| Total Project Cost | 127223.77 | 127223.77 | 127223.77 | 0 | 0
Closed 04/20/23

## #9260.00 Funds Rec'd
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
Program code 926000 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0285
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUSPRINKLERSYSTEM | 2021-12-21 | 100000 | 100000
|  |  | MOU Amend 1 | IET MOUSPRINKLERAMEND1 | 2022-02-08 | 65000 | 65000
|  |  | MOU Amend 2 | IET MOUSPRINKLERAMEND2 | 2022-05-25 | 40000 | 40000
|  |  | Return FY22 Funds to Agency | IET 33522215819 | 2022-08-03 | -91018.1 | -91018.1
|  |  | Received FY23 Funds from Agency | IET MOURETFUNDS9260.00 | 2022-08-29 | 91018.1 | 91018.1
|  |  | Received Funds in Incorrect Unit | CDR 33523242900 | 2022-08-30 | 0 | 0
|  |  | Return Funds to Agency | IET 33523110808 | 2023-04-20 | -77776.23 | -77776.23
| Total Requested | 0 | Total Transferred |  |  | 127223.77 | 127223.77

## #9260.00 Story Construction
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
Program code 926000 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522363801 | 2021-12-27 | PO Procore | 16623.09 | 16623.09 |  |  | 16623.09
PRC 3352236PA3801 | 2022-01-18 | Inv. 32946 |  | 16623.09 | 3863.14 | 3863.14 | 12759.95
PRC 3352236PB3801 | 2022-02-17 | Inv. 32987 |  | 16623.09 | 3949.14 | 7812.28 | 8810.81
PRC 3352236PC3801 | 2022-03-22 | Inv. 33032 |  | 16623.09 | 961 | 8773.28 | 7849.81
PRC 3352236PD3801 | 2022-04-28 | Inv. 33078 |  | 16623.09 | 843 | 9616.28 | 7006.81
PRC 3352236PE3801 | 2022-05-19 | Inv. 33121 |  | 16623.09 | 969.14 | 10585.42 | 6037.67
PRC 3352236PF3801 | 2022-06-20 | Inv. 33166 |  | 16623.09 | 1210 | 11795.42 | 4827.67
PRC 3352236PG3801 | 2022-07-18 | Inv. 33220 |  | 16623.09 | 740 | 12535.42 | 4087.67 | FY22
PO 33523363801 | 2022-08-30 | Rolled to FY23 | 0 | 16623.09 |  | 12535.42 | 4087.67
PRC 3352336PH3801 | 2022-08-31 | Inv. 33276 |  | 16623.09 | 330 | 12865.42 | 3757.67
PRC 3352336PI3801 | 2022-09-20 | Inv. 33341 |  | 16623.09 | 220 | 13085.42 | 3537.67
PRC 3352336PJ3801 | 2022-10-18 | Inv. 33400 |  | 16623.09 | 1005 | 14090.42 | 2532.67
PRC 3352336PK3801 | 2023-01-20 | Inv. 33580 |  | 16623.09 | 110 | 14200.42 | 2422.67
PRC 3352336PL3801 | 2023-03-21 | Inv. 33680 - FINAL | -2202.67 | 14420.42 | 220 | 14420.42 | 0
|  |  |  | 14420.42 |  | 14420.42 | 0
|  |  |  | 14420.42 |  | 14420.42 | 0
|  |  |  | 14420.42 |  | 14420.42 | 0
|  | Total: | 14420.42 |  | 14420.42 |  | 0 | FINAL
|  | CM Services | 14390 |  | 14390 |  | 0
|  | Reimbursables | 30.42 |  | 30.42 |  | 0
|  | Total: | 14420.42 |  | 14420.42 |  | 0

## #9260.00 PM TIME
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
Program code 926000 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS 907B
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 6719.35 | 6719.35 |  |  | 6719.35
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec 30, 2021 |  | 6719.35 | 1550 | 1550 | 5169.35
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 6719.35 | 1200 | 2750 | 3969.35
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 6719.35 | 275 | 3025 | 3694.35
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 6719.35 | 300 | 3325 | 3394.35
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 6719.35 | 725 | 4050 | 2669.35
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 6719.35 | 925 | 4975 | 1744.35
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 6719.35 | 100 | 5075 | 1644.35
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 6719.35 | 75 | 5150 | 1569.35
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 6719.35 | -75 | 5075 | 1644.35
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 6719.35 | 82.5 | 5157.5 | 1561.85
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 6719.35 | 247.5 | 5405 | 1314.35
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 6719.35 | 220 | 5625 | 1094.35
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 6719.35 | 82.5 | 5707.5 | 1011.85
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 6719.35 | 137.5 | 5845 | 874.35
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 229.87 | 6949.22 | 229.87 | 6074.87 | 874.35
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -229.87 | 6719.35 | -229.87 | 5845 | 874.35
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 228.51 | 6947.86 | 228.51 | 6073.51 | 874.35
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -228.51 | 6719.35 | -228.51 | 5845 | 874.35
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 137.32 | 6856.67 | 137.32 | 5982.32 | 874.35
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -137.32 | 6719.35 | -137.32 | 5845 | 874.35
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 64.85 | 6784.2 | 64.85 | 5909.85 | 874.35
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -64.85 | 6719.35 | -64.85 | 5845 | 874.35
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 137.59 | 6856.94 | 137.59 | 5982.59 | 874.35
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -137.59 | 6719.35 | -137.59 | 5845 | 874.35
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 6719.35 | 137.5 | 5982.5 | 736.85
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 6719.35 | 36.42 | 6018.92 | 700.43
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 6719.35 | 319.21 | 6338.13 | 381.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 2022 | 171.19 | 6890.54 | 171.19 | 6509.32 | 381.22
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -171.19 | 6719.35 | -171.19 | 6338.13 | 381.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 6719.35 | 7.49 | 6345.62 | 373.73
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 6719.35 | 45.45 | 6391.07 | 328.28
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 6719.35 | 60.81 | 6451.88 | 267.47
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 6719.35 | 267.47 | 6719.35 | 0
[5 empty] | 6719.35 |  | 6719.35 | 0
[5 empty] | 6719.35 |  | 6719.35 | 0
[5 empty] | 6719.35 |  | 6719.35 | 0
|  |  | Totals: | 6719.35 |  | 6719.35 |  | 0
Note on E9: Huggins, Joni [DAS]: DA22 9260.00 PM Time FY22 Kleene, Jennifer Wed, Dec 22, 5:07 PM (5 days ago) to me, Scott Please create a PM Time budget for $4,000.00 for DA22 Project 9260.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Increases $Joni Kleene, Jennifer 12:28 PM (8 minutes ago) to me, Scott Please increase the PM Time budget for MM19 Project 9054.01 by $2,000.00. Please increase the PM Time budget for MM20 Project 8982.01 by $2,500.00. Please increase the PM Time budget for MM20 Project 9145.00 by $600.00. Please increase the PM Time budget for DA19 Project 9075.00 by $2,500.00. Please increase the PM Time budget for DA21 Project 9215.00 by $1,500.00. Please increase the PM Time budget for DA22 Project 9260.00 by $4,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Increases $Joni Kleene, Jennifer 12:28 PM (8 minutes ago) to me, Scott Please increase the PM Time budget for MM19 Project 9054.01 by $2,000.00. Please increase the PM Time budget for MM20 Project 8982.01 by $2,500.00. Please increase the PM Time budget for MM20 Project 9145.00 by $600.00. Please increase the PM Time budget for DA19 Project 9075.00 by $2,500.00. Please increase the PM Time budget for DA21 Project 9215.00 by $1,500.00. Please increase the PM Time budget for DA22 Project 9260.00 by $4,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close DA22 Project 9260.00 DHS WRC New Fire Sprinkler Systems External $John Kleene, Jennifer 2:55 PM (11 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS costs have posted, so please close Project #9260.00 and return the remaining $77,776.23 to WRC. Regards, Jennifer

## #9260.00 Misc
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
Program code 926000 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9260.00 Shive Hattery
DHS WRC New Fire Sprinkler Systems
Project # 9260.00
Program code 926000 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | 926000-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522045901 | 2022-02-11 | PO Procore | 121060 | 121060 |  |  | 121060
PRC 3352204PA5901 | 2022-04-05 | Inv. 2142201070-1 |  | 121060 | 67439 | 67439 | 53621
PRC 3352204PB5901 | 2022-05-18 | Inv. 2142201070-2 |  | 121060 | 21154.98 | 88593.98 | 32466.02
PRC 3352204PC5901 | 2022-07-26 | Inv. 2142201070-3 |  | 121060 | 7777.5 | 96371.48 | 24688.52 | FY22
PO 33523045901 | 2022-08-30 | Rolled to FY23 | 0 | 121060 |  | 96371.48 | 24688.52
PO 33523045901 | 2022-12-15 | CO #1 | -14976 | 106084 |  | 96371.48 | 9712.52
PRC 3352304PD5901 | 2023-01-06 | Inv. 2142201070-4 |  | 106084 | 7192.27 | 103563.75 | 2520.25
PRC 3352304PE5901 | 2023-01-25 | Inv. 2142201070-5 |  | 106084 | 2520.25 | 106084 | 0
|  |  |  | 106084 |  | 106084 | 0
|  |  |  | 106084 |  | 106084 | 0
|  |  |  | 106084 |  | 106084 | 0
|  |  |  | 106084 |  | 106084 | 0
|  |  |  | 106084 |  | 106084 | 0
|  | Total: | 106084 |  | 106084 |  | 0
|  | Design Development Docs | 44540 |  | 44540 |  | 0
|  | Fire Pump Evaluation | 19391 |  | 19391 |  | 0
|  | Bldg Fire Sprinkler Constuction Docs | 42153 |  | 42153 |  | 0
|  | Bldg Fire Sprinkler Bidding & Negotiation Assist | 0 |  |  |  | 0
|  | Total: | 106084 |  | 106084 |  | 0

## RECAP #9261.00
DHS GRC New Fire Sprinkler Systems
Project # 9261.00
| Program code 926100 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Doug C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 0
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 06/13/22
.

## #9261.00 Funds Rec'd
DHS GRC New Fire Sprinkler Systems
Project # 9261.00
Program code 926100 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Doug C.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9261.00 Vendor A
DHS GRC New Fire Sprinkler Systems
Project # 9261.00
Program code 926100 |  |  | Major Program 4B02
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Doug C. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9261.00 PM TIME
DHS GRC New Fire Sprinkler Systems
Project # 9261.00
Program code 926100 |  |  | Major Program 4B02
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Doug C.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 150 | 150 |  |  | 150
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28,2022 |  | 150 | 150 | 150 | 0
CDE 33522075901 | 2022-03-16 | Moving PM Time to MM22 9263.00 | -150 | 0 | -150 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9261.00 Misc
DHS GRC New Fire Sprinkler Systems
Project # 9261.00
Program code 926100 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Doug C.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9266.00
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
| Program code 926600 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 184158.32
C | Story Construction |  | 12909.66 | 12909.66 | 0
C | PM TIME |  | 5840 | 5840 | 0
C | Misc. |  | 1222 | 1222 | 0
C | Bluestone Engineering |  | 10250 | 10250 | 0
C | MLS Landscape & Design |  | 132248 | 132248 | 0
C | Story Construction #009CA |  | 21688.66 | 21688.66 | 0
| Total Project Cost | 184158.32 | 184158.32 | 184158.32 | 0 | 0
Closed 04/27/2023

## #9266.00 Funds Rec'd
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 407KM2201112201 | 2022-01-12 | 145000 | 145000
|  |  | Return FY22 Funds to Agency | IET 33522215820 | 2022-08-03 | -124733.34 | -124733.34
|  |  | Received FY23 Funds From Agency | IET 407KM23082433 | 2022-08-26 | 124733.34 | 124733.34
|  |  | MOU Amendment #1 | IET 407KM2308312201 | 2022-08-31 | 30000 | 30000
|  |  | Fund received MOU Amendment #2 | IET 407JP2312202201 | 2022-12-21 | 13500 | 13500
|  |  | Return Funds to Agency | IET 33523117901 | 2023-04-27 | -4341.68 | -4341.68
| Total Requested | 0 | Total Transferred |  |  | 184158.32 | 184158.32

## #9266.00 Story Construction
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522020901 | 2022-01-20 | PO Procore | 13555.32 | 13555.32 |  |  | 13555.32
PRC 3352202PA0901 | 2022-03-23 | Inv. 33037 |  | 13555.32 | 2574.72 | 2574.72 | 10980.6
PRC 3352202PB0901 | 2022-04-27 | Inv. 33083 |  | 13555.32 | 843.25 | 3417.97 | 10137.35
PRC 3352202PC0901 | 2022-05-23 | Inv. 33126 |  | 13555.32 | 1261.61 | 4679.58 | 8875.74
PRC 3352202PD0901 | 2022-06-23 | Inv. 33171 |  | 13555.32 | 3722.86 | 8402.44 | 5152.88
PRC 3352202PE0901 | 2022-07-18 | Inv. 33224 |  | 13555.32 | 4129.22 | 12531.66 | 1023.66 | FY22
PO 33523020901 | 2022-08-29 | Rolled to FY23 | 0 | 13555.32 |  | 12531.66 | 1023.66
PRC 3352302PF0901 | 2022-08-29 | Inv. 33281 |  | 13555.32 | 315 | 12846.66 | 708.66
PRC 3352302PG0901 | 2022-09-19 | Inv. 33345 |  | 13555.32 | 63 | 12909.66 | 645.66
PO 33523020901 | 2023-04-07 | Close per PM | -645.66 | 12909.66 |  | 12909.66 | 0
|  |  |  | 12909.66 |  | 12909.66 | 0
|  |  |  | 12909.66 |  | 12909.66 | 0
|  |  |  | 12909.66 |  | 12909.66 | 0
|  | Totals: | 12909.66 |  | 12909.66 |  | 0
|  | CM Services | 12736.5 |  | 12736.5 |  | 0
|  | Reimbursables | 173.16 |  | 173.16 |  | 0
|  | Total: | 12909.66 |  | 12909.66 |  | 0
Note on D9: Jurgenson, John [DAS]: Fwd: 9266.00 - CHMHI Admin Stair/Ramp - Story Construction PC Exhibit $John Elliott, Jennie Fri, Apr 7, 3:14 PM (3 days ago) to me Per the email string below, please close the Story contract in project 9266.00 in DA22. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov

## #9266.00 PM TIME
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 907I
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 5840 | 5840 |  |  | 5840
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 5840 | 150 | 150 | 5690
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 5840 | 600 | 750 | 5090
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 5840 | 350 | 1100 | 4740
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 5840 | 350 | 1450 | 4390
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 5840 | 600 | 2050 | 3790
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 5840 | 600 | 2650 | 3190
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 5840 | 400 | 3050 | 2790
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 5840 | -400 | 2650 | 3190
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 5840 | 440 | 3090 | 2750
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 5840 | 440 | 3530 | 2310
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 5840 | 1210 | 4740 | 1100
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 5840 | 385 | 5125 | 715
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 5840 | 385 | 5510 | 330
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 300.45 | 6140.45 | 300.45 | 5810.45 | 330
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -300.45 | 5840 | -300.45 | 5510 | 330
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 379.44 | 6219.44 | 379.44 | 5889.44 | 330
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -379.44 | 5840 | -379.44 | 5510 | 330
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 803.17 | 6643.17 | 803.17 | 6313.17 | 330
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -803.17 | 5840 | -803.17 | 5510 | 330
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 270.75 | 6110.75 | 270.75 | 5780.75 | 330
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -270.75 | 5840 | -270.75 | 5510 | 330
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 308.82 | 6148.82 | 308.82 | 5818.82 | 330
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -308.82 | 5840 | -308.82 | 5510 | 330
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 5840 | 330 | 5840 | 0
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: August 2022 | 130.51 | 5970.51 | 130.51 | 5970.51 | 0
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -130.51 | 5840 | -130.51 | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
[5 empty] | 5840 |  | 5840 | 0
|  |  | Totals: | 5840 |  | 5840 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Budgets $Joni Carper, Douglas 11:28 AM (3 hours ago) to me, Scott DA22 Funds 9266.00 PM Time $4,500.00. 9267.00 PM Time $7,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Re: PM Time for September Inbox Carper, Douglas 3:19 PM (3 minutes ago) to me, Joni INcrease PM Time to $6,000.00. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov On Fri, Oct 7, 2022 at 3:13 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Happy Friday, DA22 9266.00 Insufficient funds to post $1210.00 in PM Time Please advise Thank you ~Joni

## #9266.00 Misc
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522181904 | 2022-06-30 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 419680-0 | 65 | 65
GAX 33522199801 | 2022-07-13 | 9500 | CNST | Siouxland Certified Testing V#(00002117847) | Inv. SL18564 | 590 | 655
GAX 33523307903 | 2022-11-01 | 9500 | CNST | Siouxland Certified Testing V#(00002117847) | Inv. SL18908 | 531 | 1186
GAX 33523336803 | 2022-12-01 | 9500 | CNST | Siouxland Certified Testing V#(00002117847) | Inv. SL18968 | 36 | 1222
1222
1222
1222
1222
1222
1222
1222
1222
|  |  |  | Totals: |  | 1222

## #9266.00 Bluestone Engineering
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  | Major Program 4B02
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: 926500-02
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522102800 | 2022-04-12 | PO Procore | 10250 | 10250 |  |  | 10250
PRC 3352210PA2800 | 2022-06-29 | Inv. 11855 |  | 10250 | 4430 | 4430 | 5820 | FY22
PO 33523102800 | 2022-08-29 | Rolled to FY23 | 0 | 10250 |  | 4430 | 5820
PRC 3352310PB2800 | 2022-10-03 | Inv. 12044 |  | 10250 | 582 | 5012 | 5238
PRC 3352310PC2800 | 2022-10-17 | Inv. 12093 |  | 10250 | 2328 | 7340 | 2910
PRC 3352310PD2800 | 2023-01-19 | Inv. 12159 |  | 10250 | 2328 | 9668 | 582
PRC 3352310PE2800 | 2023-02-13 | Inv. 12324 |  | 10250 | 582 | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  |  |  | 10250 |  | 10250 | 0
|  | Totals: | 10250 |  | 10250 |  | 0
|  | Construction Documents | 3645 |  | 3645 |  | 0
|  | Bidding Phase | 785 |  | 785 |  | 0
|  | Construction Phase | 5820 |  | 5820 |  | 0
|  | Total: | 10250 |  | 10250 |  | 0

## #9266.00 MLS Landscape & Design
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  | Major Program 4B02
MLS Landscape & Design |  |  | Vendor: 00003038106
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: 926600-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523245803 | 2022-08-30 | PO Procore | 119000 | 119000 |  |  | 119000
PRC 3352324PA5803 | 2022-12-22 | Inv. 9266.00-1 |  | 119000 | 111919.49 | 111919.49 | 7080.51 | 5890.51
PO 33523245803 | 2023-01-04 | CO #1 | 13248 | 132248 |  | 111919.49 | 20328.51
PRC 3352324PB5803 | 2023-01-10 | Inv. 9266.00-2 |  | 132248 | 12585.6 | 124505.09 | 7742.91 | 6552.91
PRC 3352324PC5803 | 2023-02-01 | Inv. 9266.00-3 |  | 132248 | 1130.5 | 125635.59 | 6612.41 | 6612.41
PRC 3352324PD5803 | 2023-02-07 | Inv. 9266.00-Retainage |  | 132248 | 6612.41 | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  |  |  | 132248 |  | 132248 | 0
|  | Totals: | 132248 |  | 132248 |  | 0

## #9266.00 Story Construction (2)
DHS CHMHI Administration Stairs and Ramp Repair
Project # 9266.00
Program code 926600 |  |  | Major Program 4B02
Story Construction #009CA |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523257800 | 2022-09-14 | PO Procore | 22905.08 | 22905.08 |  |  | 22905.08
PRC 3352325PA7800 | 2022-10-18 | Inv. 33404 |  | 22905.08 | 4686.72 | 4686.72 | 18218.36
PRC 3352325PB7800 | 2022-11-28 | Inv. 33461 |  | 22905.08 | 5671.44 | 10358.16 | 12546.92
PRC 3352325PC7800 | 2022-12-20 | Inv. 33517 |  | 22905.08 | 3914.5 | 14272.66 | 8632.42
PRC 3352325PD7800 | 2023-01-23 | Inv. 33584 |  | 22905.08 | 4473.5 | 18746.16 | 4158.92
PRC 3352325PE7800 | 2023-03-01 | Inv. 22632 |  | 22905.08 | 2478.5 | 21224.66 | 1680.42
PRC 3352325PF7800 | 2023-03-20 | Inv. 33685-Final | -1216.42 | 21688.66 | 464 | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  |  |  | 21688.66 |  | 21688.66 | 0
|  | Totals: | 21688.66 |  | 21688.66 |  | 0 | FINAL
|  | CM Services | 21339 |  | 21339 |  | 0
|  | Reimbursables | 349.66 |  | 349.66 |  | 0
|  | Total: | 21688.66 |  | 21688.66 |  | 0

## RECAP #9267.00
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
| Program code 926700 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 446243.55
C | Story Construction |  | 21243.74 | 21243.74 | 0
| PM TIME |  | 15600.07 | 15600.07 | 0
| Misc. |  | 6849.85 | 6849.85 | 0
C | Bluestone Engineering |  | 32757.5 | 32757.5 | 0
C | Communication Innovators |  | 331177.82 | 331177.82 | 0
C | Story Construction(2) |  | 38614.57 | 38614.57 | 0
| Total Project Cost | 446243.55 | 446243.55 | 446243.55 | 0 | 0
Closed 01/12/2024

## #9267.00 Funds Rec'd
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 406KM2201112202 | 2022-01-12 | 245000 | 245000
|  |  | Return FY22 Funds to Agency | IET 33522215821 | 2022-08-03 | -201906.76 | -201906.76
|  |  | Received FY23 Funds From Agency | IET 406KM2308242202 | 2022-08-24 | 201906.76 | 201906.76
|  |  | MOU Amendment #1 | IET 406KM2308312201 | 2022-08-31 | 100000 | 100000
|  |  | MOU Amendment #2 | IET 406JP2311302201 | 2022-12-01 | 32000 | 32000
|  |  | MOU Amendment #3 | IET 406JP2302282301 | 2023-03-01 | 60000 | 60000
|  |  | MOU Amendment #4 | IET 406JP2304112301 | 2023-04-11 | 12000 | 12000
|  |  | Return FY23 Funds to Agency | IET 33523229927 | 2023-08-17 | -32300.34 | -32300.34
|  |  | Received FY24 Funds From Agency | IET 406MC2409112303 | 2023-09-11 | 32300.34 | 32300.34
|  |  | Return Funds to Agency | IET 33524012804 | 2024-01-12 | -2756.45 | -2756.45
| Total Requested | 0 | Total Transferred |  |  | 446243.55 | 446243.55

## #9267.00 Story Construction
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522019801 | 2022-01-19 | PO Procore | 17256.3 | 17256.3 |  |  | 17256.3
PRC 3352201PA9801 | 2022-02-21 | Inv. 32989 |  | 17256.3 | 1027.5 | 1027.5 | 16228.8
PRC 3352201PB9801 | 2022-03-22 | Inv. 33035 |  | 17256.3 | 2719.94 | 3747.44 | 13508.86
PRC 3352201PC9801 | 2022-04-28 | Inv. 33081 |  | 17256.3 | 1426.75 | 5174.19 | 12082.11
PRC 3352201PD9801 | 2022-05-19 | Inv. 33124 |  | 17256.3 | 1146.97 | 6321.16 | 10935.14
PRC 3352201PE9801 | 2022-06-22 | Inv. 33169 |  | 17256.3 | 3155.47 | 9476.63 | 7779.67
PRC 3352201PF9801 | 2022-07-18 | Inv. 33222 |  | 17256.3 | 5279.61 | 14756.24 | 2500.06 | FY22
PO 33523019801 | 2022-08-29 | Rolled to FY23 | 0 | 17256.3 |  | 14756.24 | 2500.06
PRC 3352301PG9801 | 2022-08-29 | Inv. 33279 |  | 17256.3 | 2326.5 | 17082.74 | 173.56
PO 33523019801 | 2022-09-07 | CO #1 | 3987.44 | 21243.74 |  | 17082.74 | 4161
PRC 3352301PH9801 | 2022-10-17 | Inv. 33402 |  | 21243.74 | 4161 | 21243.74 | 0
|  |  |  | 21243.74 |  | 21243.74 | 0
|  |  |  | 21243.74 |  | 21243.74 | 0
|  | Totals: | 21243.74 |  | 21243.74 |  | 0
|  | CM Services | 17126 |  | 17126 |  | 0
|  | Reimbursables | 230.49 |  | 230.49 |  | 0
|  | CO #1 | 3887.25 |  | 3887.25 |  | 0
|  | Totals: | 21243.74 |  | 21243.74 |  | 0

## #9267.00 PM TIME
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 907J
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15600.07 | 15600.07 |  |  | 15600.07
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 15600.07 | 200 | 200 | 15400.07
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 15600.07 | 400 | 600 | 15000.07
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 15600.07 | 550 | 1150 | 14450.07
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 15600.07 | 550 | 1700 | 13900.07
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 15600.07 | 550 | 2250 | 13350.07
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 15600.07 | 750 | 3000 | 12600.07
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 15600.07 | 350 | 3350 | 12250.07
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 15600.07 | -350 | 3000 | 12600.07
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 15600.07 | 385 | 3385 | 12215.07
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 15600.07 | 440 | 3825 | 11775.07
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 15600.07 | 330 | 4155 | 11445.07
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 15600.07 | 935 | 5090 | 10510.07
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 15600.07 | 110 | 5200 | 10400.07
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 275.2 | 15875.27 | 275.2 | 5475.2 | 10400.07
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -275.2 | 15600.07 | -275.2 | 5200 | 10400.07
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 379.44 | 15979.51 | 379.44 | 5579.44 | 10400.07
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -379.44 | 15600.07 | -379.44 | 5200 | 10400.07
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 219.04 | 15819.11 | 219.04 | 5419.04 | 10400.07
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -219.04 | 15600.07 | -219.04 | 5200 | 10400.07
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 657.53 | 16257.6 | 657.53 | 5857.53 | 10400.07
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -657.53 | 15600.07 | -657.53 | 5200 | 10400.07
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 88.23 | 15688.3 | 88.23 | 5288.23 | 10400.07
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -88.23 | 15600.07 | -88.23 | 5200 | 10400.07
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 15600.07 | 165 | 5365 | 10235.07
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 15600.07 | 76.05 | 5441.05 | 10159.02
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 15600.07 | 666.7 | 6107.75 | 9492.32
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 15600.07 | 289.11 | 6396.86 | 9203.21
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 15600.07 | 1753.16 | 8150.02 | 7450.05
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 15600.07 | 88.23 | 8238.25 | 7361.82
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 15600.07 | 388.11 | 8626.36 | 6973.71
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 15600.07 | 70.04 | 8696.4 | 6903.67
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 15600.07 | 412.7 | 9109.1 | 6490.97
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 15600.07 | 269.99 | 9379.09 | 6220.98
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 15600.07 | 1890.9 | 11269.99 | 4330.08
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 15600.07 | 55.26 | 11325.25 | 4274.82
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 15600.07 | 357.4 | 11682.65 | 3917.42
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 15600.07 | 108.96 | 11791.61 | 3808.46
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 15600.07 | 694.6 | 12486.21 | 3113.86
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 15600.07 | 125.98 | 12612.19 | 2987.88
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 15600.07 | 702.8 | 13314.99 | 2285.08
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 15600.07 | 136.92 | 13451.91 | 2148.16
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 15600.07 | 950 | 14401.91 | 1198.16
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 15600.07 | 52.19 | 14454.1 | 1145.97
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 15600.07 | 417.4 | 14871.5 | 728.57
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 15600.07 | 30.49 | 14901.99 | 698.08
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 15600.07 | 230.9 | 15132.89 | 467.18
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 15600.07 | 56.18 | 15189.07 | 411
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 15600.07 | 411 | 15600.07 | 0
[5 empty] | 15600.07 |  | 15600.07 | 0
|  |  | Totals: | 15600.07 |  | 15600.07 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Budgets $Joni Carper, Douglas 11:28 AM (3 hours ago) to me, Scott DA22 Funds 9266.00 PM Time $4,500.00. 9267.00 PM Time $7,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Re: 9267.00 DHS CHMHI CCUSO Door and Intercom Control Replacement Story Construction Exhibit #004CA $John Carper, Douglas Fri, Dec 16, 11:26 AM (3 days ago) to me, John Revise the PM TIme budget to $6,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Fwd: 9267.00 DA22 PM Time Budget $Joni Elliott, Jennie Mon, Mar 20, 8:02 PM (13 hours ago) to me Please increase the PM time budget in 9267.00 to $15,000 Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244! Elliott, Jennie 8:28 AM (5 hours ago) to me Can you please increase the PM Time budget in 9267.00 DHS CHMHI CCUSO Door and Intercom Control Conversion- DA22 to a total contracted amount of $17,500.

## #9267.00 Misc
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522181902 | 2022-06-30 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2435352-Final | 2812.5 | 2812.5
PRC 33522188901 | 2022-07-07 | 9500 | CNST | Rapid Reproductions V#(0000211375) | Inv. 419703-0 | 65 | 2877.5
PRC 33523336804 | 2022-12-02 | 9500 | CNST | Rapid Reproductions V#(0000211375) | Inv. 430235-0 | 173.87 | 3051.37
GAX 33523187902 | 2023-06-30 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010543-IN-FINAL & 0010540-IN-FINAL | 3798.48 | 6849.85
6849.85
6849.85
6849.85
6849.85
6849.85
6849.85
6849.85
6849.85
|  |  |  | Totals: |  | 6849.85

## #9267.00 Bluestone Engineering
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  | Major Program 4B02
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0506-335-DA22-9260 |  |  | 926700-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522081904 | 2022-03-22 | PO Procore | 32757.5 | 32757.5 |  |  | 32757.5
PRC 3352208PA1904 | 2022-04-20 | Inv. 11654 |  | 32757.5 | 1952 | 1952 | 30805.5
PRC 3352208PB1904 | 2022-06-29 | Inv. 11857 |  | 32757.5 | 20507.5 | 22459.5 | 10298 | FY22
PO 33523081904 | 2022-08-29 | Rolled to FY23 | 0 | 32757.5 |  | 22459.5 | 10298
PRC 3352308PC1904 | 2023-01-19 | Inv. 12138 |  | 32757.5 | 1029.8 | 23489.3 | 9268.2
PRC 3352308PD1904 | 2023-02-08 | Inv. 12323 |  | 32757.5 | 1029.8 | 24519.1 | 8238.4
PRC 3352308PE1904 | 2023-04-18 | Inv. 12384 & 12456 |  | 32757.5 | 1544.7 | 26063.8 | 6693.7
PRC 3352308PF1904 | 2023-05-22 | Inv. 12530 |  | 32757.5 | 4119.2 | 30183 | 2574.5
PRC 3352308PG1904 | 2023-07-11 | Inv. 12572 |  | 32757.5 | 2059.6 | 32242.6 | 514.9
PRC 3352308PH1904 | 2023-07-25 | Inv. 12682 |  | 32757.5 | 308.94 | 32551.54 | 205.96 | FY23
PO 33524081904 | 2023-08-28 | Roll to FY24 | 0 | 32757.5 |  | 32551.54 | 205.96
PRC 3352408PI1904 | 2023-12-20 | Inv. 12743-Final |  | 32757.5 | 205.96 | 32757.5 | 1.9043e-12
|  |  |  | 32757.5 |  | 32757.5 | 1.9043e-12
|  | Totals: | 32757.5 |  | 32757.5 |  | 0
|  | Construction Docs | 19520 |  | 19520 |  | 0
|  | Bid Phase | 2939.5 |  | 2939.5 |  | 0
|  | Construction Admin | 10298 |  | 10298 |  | 0
|  | Totals: | 32757.5 |  | 32757.5 |  | 0

## #9267.00 Communication Innovato
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  | Major Program 4B02
Communication Innovators |  |  | Vendor: 00002119160
Acct. Codes-0506-335-DA22-9255 |  |  | RFP/B#: 926700-02
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523342801 | 2022-12-08 | PO Procore | 286963 | 286963 |  |  | 286963
PRC 3352334PA2801 | 2023-02-07 | Inv. 9267.00-01 |  | 286963 | 103026.49 | 103026.49 | 183936.51 | 5422.45
PO 33523342801 | 2023-03-02 | CO #1 | 39725.28 | 326688.28 |  | 103026.49 | 223661.79
PO 33523342801 | 2023-03-07 | CO #2 | 4489.54 | 331177.82 |  | 103026.49 | 228151.33
PRC 3352334PB2801 | 2023-05-05 | Inv. 9267.00-02 |  | 331177.82 | 202216.29 | 305242.78 | 25935.04 | 16065.41
PO 33523342801 | 2023-05-08 | CO #3 (No Cost) | 0 | 331177.82 |  | 305242.78 | 25935.04
PO 33523342801 | 2023-06-06 | CO #4 (No Cost) | 0 | 331177.82 |  | 305242.78 | 25935.04
PRC 3352334PC2801 | 2023-06-14 | Inv. 9267.00-03 |  | 331177.82 | 5700 | 310942.78 | 20235.04 | 16365.41
PRC 3352334PD2801 | 2023-08-09 | Inv. 9267.00-04 |  | 331177.82 | 950 | 311892.78 | 19285.04 | 16415.41 | FY24
PO 33524342801 | 2023-08-28 | Roll to FY24 | 0 | 331177.82 |  | 311892.78 | 19285.04
PRC 3352434PE2801 | 2023-11-06 | Inv. 112606-1229 |  | 331177.82 | 2726.15 | 314618.93 | 16558.89 | 16558.89
PRC 3352434PF2801 | 2023-12-08 | Inv. 9267.00-06-Retainage |  | 331177.82 | 16558.89 | 331177.82 | 0
|  |  |  | 331177.82 |  | 331177.82 | 0
|  | Totals: | 331177.82 |  | 331177.82 |  | 0

## #9267.00 Story Construction (2)
DHS CHMHI CCUSO Door and Intercom Control Conversion
Project # 9267.00
Program code 926700 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523350801 | 2022-12-16 | PO Procore | 24965.89 | 24965.89 |  |  | 24965.89
PRC 3352335PA0801 | 2023-01-23 | Inv. 33582 |  | 24965.89 | 3995.94 | 3995.94 | 20969.95
PRC 3352335PB0801 | 2023-02-17 | Inv. 33630 |  | 24965.89 | 7416.84 | 11412.78 | 13553.11
PRC 3352335PC0801 | 2023-03-20 | Inv. 33683 |  | 24965.89 | 8937.55 | 20350.33 | 4615.56
PO 33523350801 | 2023-04-13 | CO #1 | 14042 | 39007.89 |  | 20350.33 | 18657.56
PRC 3352335PD0801 | 2023-04-18 | Inv. 33729 |  | 39007.89 | 4125.75 | 24476.08 | 14531.81
PRC 3352335PE0801 | 2023-05-22 | Inv. 33784 |  | 39007.89 | 4044.54 | 28520.62 | 10487.27
PRC 3352335PF0801 | 2023-06-21 | Inv. 33833 |  | 39007.89 | 3122.95 | 31643.57 | 7364.32
PRC 3352335PG0801 | 2023-07-14 | Inv. 33891 |  | 39007.89 | 835.53 | 32479.1 | 6528.79 | FY23
PO 33524350801 | 2023-08-28 | Roll to FY24 | 0 | 39007.89 |  | 32479.1 | 6528.79
PRC 3352435PH0801 | 2023-11-21 | Inv. 34117 |  | 39007.89 | 5373.79 | 37852.89 | 1155
PRC 3352435PI0801 | 2023-12-20 | Inv. 34158-Final | -393.32 | 38614.57 | 761.68 | 38614.57 | 0
|  |  |  | 38614.57 |  | 38614.57 | 0
|  | Totals: | 38614.57 |  | 38614.57 |  | 0 | FINAL
|  | CM Services | 23929.89 |  | 23929.89 |  | 0
|  | Reimbursables | 666 |  | 666 |  | 0
|  | CO #1 | 14018.68 |  | 14018.68 |  | 0
|  | Totals: | 38614.57 |  | 38614.57 |  | 0

## RECAP #9268.00
DAS CC Tunnel Joint Evaluation
Project # 9268.00
| Program code 926800 |  |  | Major Program 4E17
Recap
Acct. Codes-0506-335-DA22
Project Manager - Josh H.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 35651.1
C | Shive Hattery |  | 34493.6 | 34493.6 | 0
C | PM TIME |  | 1157.5 | 1157.5 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 35651.1 | 35651.1 | 35651.1 | 0 | 0
Close 01/18/2023

## #9268.00 Funds Rec'd
DAS CC Tunnel Joint Evaluation
Project # 9268.00
Program code 926800 |  |  | Major Program 4E17
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Josh H.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 005FY22PROJ926800 | 2022-04-15 | 36000 | 36000
|  |  | Return FY22 Funds to Agency | IET 33522215822 | 2022-08-03 | -2981.08 | -2981.08
|  |  | Received FY23 Funds from Agency | IET 00523PROJ926800A | 2022-08-04 | 2981.08 | 2981.08
|  |  | Return Funds to Agency | IET 33523019901 | 2023-01-18 | -348.9 | -348.9
| Total Requested | 0 | Total Transferred |  |  | 35651.1 | 35651.1

## #9268.00 Shive Hattery
DAS CC Tunnel Joint Evaluation
Project # 9268.00
Program code 926800 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9110 |  |  | RFP926800-01
Project Manager - Josh H. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522108902 | 2022-04-12 | PO Procore | 34493.6 | 34493.6 |  |  | 34493.6
PRC 3352210PA8902 | 2022-05-17 | Inv. 21422019401 (Split between DA22, MM20 & R21M) |  | 34493.6 | 3449.36 | 3449.36 | 31044.24
PRC 3352210PB8902 | 2022-07-07 | Inv. 2142201940-2 (Split between DA22, R21M& MM20) |  | 34493.6 | 24145.52 | 27594.88 | 6898.72
PRC 3352210PC8902 | 2022-07-20 | Inv. 2142201940-3 (Split between DA22, R21M& MM20) |  | 34493.6 | 5174.04 | 32768.92 | 1724.68 | FY22
PO 33523108902 | 2022-08-10 | Rolled to FY23 | 0 | 34493.6 |  | 32768.92 | 1724.68
PRC 3352310PD8902 | 2022-09-11 | Inv. 2142201940-4 (Split between MM20, DA22 & R21M) |  | 34493.6 | 1724.68 | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  |  |  | 34493.6 |  | 34493.6 | 0
|  | Totals: | 34493.6 |  | 34493.6 |  | 0
|  | MM20 | 52211 |  | 52211 |  | 0
|  | R21M (closed 9/12/22) | 8623.4 |  | 8623.4 |  | 0
|  | Total: | 95328 |  | 95328 |  | 0

## #9268.00 PM TIME
DAS CC Tunnel Joint Evaluation
Project # 9268.00
Program code 926800 |  |  | Major Program 4E17
PM TIME |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - Josh H. |  |  | eDAS 862R
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget Amount | 1157.5 | 1157.5 |  |  | 1157.5
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 1157.5 | 150 | 150 | 1007.5
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 1157.5 | 100 | 250 | 907.5
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 1157.5 | 175 | 425 | 732.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Credit |  | 1157.5 | -175 | 250 | 907.5
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Reposted correct amount |  | 1157.5 | 192.5 | 442.5 | 715
IET DAS202301115300001 | 2022-09-08 | PM-August 1-August 31, 2022 |  | 1157.5 | 275 | 717.5 | 440
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 1157.5 | 275 | 992.5 | 165
IET DAS202305115300001 | 2022-12-19 | PM Time-November 1- Novemer 30, 2022 |  | 1157.5 | 55 | 1047.5 | 110
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 100.18 | 1257.68 | 100.18 | 1147.68 | 110
CDE 33523353209 | 2022-12-21 | Move PM time to 9997.23 MM23 | -100.18 | 1157.5 | -100.18 | 1047.5 | 110
IET DAS202305115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 209.39 | 1366.89 | 209.39 | 1256.89 | 110
CDE 33523353210 | 2022-12-22 | Move PM time to 9997.23 MM23 | -209.39 | 1157.5 | -209.39 | 1047.5 | 110
IET DAS202205115300001 | 2022-12-07 | PM Time-Sept 9997.23 disbursement | 175.8 | 1333.3 | 175.8 | 1223.3 | 110
CDE 33523353211 | 2022-12-21 | Move PM time to 9997.23 MM23 | -175.8 | 1157.5 | -175.8 | 1047.5 | 110
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 37.76 | 1195.26 | 37.76 | 1085.26 | 110
CDE 33523353208 | 2022-12-22 | Move PM time to 9997.23 MM23 | -37.76 | 1157.5 | -37.76 | 1047.5 | 110
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 1157.5 | 110 | 1157.5 | 0
|  |  |  | 1157.5 |  | 1157.5 | 0
|  |  |  | 1157.5 |  | 1157.5 | 0
|  | Totals: | 1157.5 |  | 1157.5 |  | 0
Note on D9: Durakovic, Selma [DAS]: 9268.00 DA22 PM Time $Selma Herman, Josh 8:13 AM (35 minutes ago) to me Please set the PM time budget to $1,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time DA22 9268.00 FY23 Herman, Josh 3:11 PM (4 minutes ago) to me Sorry, please make it $1,350. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov On Mon, Dec 19, 2022 at 3:09 PM Herman, Josh <josh.herman@iowa.gov> wrote: Please increase PM Time from $1,000 to $1,300. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time DA22 9268.00 FY23 Herman, Josh 3:11 PM (4 minutes ago) to me Sorry, please make it $1,350. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov On Mon, Dec 19, 2022 at 3:09 PM Herman, Josh <josh.herman@iowa.gov> wrote: Please increase PM Time from $1,000 to $1,300. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time DA22 9268.00 FY23 Herman, Josh 3:11 PM (4 minutes ago) to me Sorry, please make it $1,350. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov On Mon, Dec 19, 2022 at 3:09 PM Herman, Josh <josh.herman@iowa.gov> wrote: Please increase PM Time from $1,000 to $1,300. Thank you, Josh CLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.govCLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.govCLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.govC LOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.govLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov CLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov CLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov CLOSE - 9268.00 in MM20 & DA22 $Joni Herman, Josh Jan 18, 2023, 9:37 AM (23 hours ago) to me, Scott Please close project 9268.00 in MM20 and DA22. Funds remaining in both orgs can be returned. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #9268.00 Misc
DAS CC Tunnel Joint Evaluation
Project # 9268.00
Program code 926800 |  |  |  | Major Program 4E17
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Josh H.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9280.00
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
| Program code 928000 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 320199.32
C | DCI Group |  | 9182.91 | 9182.91 | 0
C | PM TIME |  | 5484.43 | 5484.43 | 0
C | Misc. |  | 74.95 | 74.95 | 0
C | Horizon Architecture |  | 23600 | 23600 | 0
C | Grimes Asphalt |  | 274382.01 | 274382.01 | 0
C | DCI Group#2 |  | 7475.02 | 7475.02 | 0
| Total Project Cost | 320199.32 | 320199.32 | 320199.32 | 0 | 0
Closed 05/10/2023

## #9280.00 Funds Rec'd
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 67022000771 | 2022-03-02 | 340000 | 340000
|  |  | Return FY22 Funds to Agency | IET 33522216800 | 2022-08-04 | -313785.17 | -313785.17
|  |  | Received FY23 Funds from Agency | IET 67023000300 | 2022-08-15 | 313785.17 | 313785.17
|  |  | Funds received without Program Code | CDR 33523228900 | 2022-08-16 | 0 | 0
|  |  | Return Funds to Agency | IET 33523130902 | 2023-05-10 | -19800.68 | -19800.68
| Total Requested | 0 | Total Transferred |  |  | 320199.32 | 320199.32

## #9280.00 DCI Group
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522089802 | 2022-03-30 | PO Procore | 9401.71 | 9401.71 |  |  | 9401.71
PRC 3352208PA9802 | 2022-07-07 | Inv. 22-013 PC-01 |  | 9401.71 | 5025.27 | 5025.27 | 4376.44
PRC 3352208PB9802 | 2022-07-18 | Inv. 22-013 PC-02 |  | 9401.71 | 1064.56 | 6089.83 | 3311.88 | FY22
PO 33523089802 | 2022-08-16 | Rolled to FY23 | 0 | 9401.71 |  | 6089.83 | 3311.88
PRC 3352308PC9802 | 2022-09-20 | Inv. 22-013 PC-03 |  | 9401.71 | 2256.87 | 8346.7 | 1055.01
PRC 3352308PD9802 | 2022-11-08 | Inv. 22-013 PC-04 FINAL | -218.8 | 9182.91 | 836.21 | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  |  |  | 9182.91 |  | 9182.91 | -1.1937e-12
|  | Totals: | 9182.91 |  | 9182.91 |  | 0 | FINAL
|  | CM Staff Hours | 9151.71 |  | 9151.71 |  | 0
|  | Reimbursable Expenses (not to exceed) | 31.2 |  | 31.2 |  | 0
|  | Total: | 9182.91 |  | 9182.91 |  | 0

## #9280.00 PM TIME
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS E21I
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget Amount | 5484.43 | 5484.43 |  |  | 5484.43
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 5484.43 | 150 | 150 | 5334.43
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 5484.43 | 150 | 300 | 5184.43
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 5484.43 | 300 | 600 | 4884.43
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 5484.43 | 50 | 650 | 4834.43
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 5484.43 | 250 | 900 | 4584.43
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 5484.43 | -250 | 650 | 4834.43
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 5484.43 | 275 | 925 | 4559.43
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 5484.43 | 495 | 1420 | 4064.43
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 5484.43 | 110 | 1530 | 3954.43
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 5484.43 | 770 | 2300 | 3184.43
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 5484.43 | 880 | 3180 | 2304.43
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 177.99 | 5662.42 | 177.99 | 3357.99 | 2304.43
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -177.99 | 5484.43 | -177.99 | 3180 | 2304.43
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 426.87 | 5911.3 | 426.87 | 3606.87 | 2304.43
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -426.87 | 5484.43 | -426.87 | 3180 | 2304.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 73.01 | 5557.44 | 73.01 | 3253.01 | 2304.43
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -73.01 | 5484.43 | -73.01 | 3180 | 2304.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 541.5 | 6025.93 | 541.5 | 3721.5 | 2304.43
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -541.5 | 5484.43 | -541.5 | 3180 | 2304.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 705.87 | 6190.3 | 705.87 | 3885.87 | 2304.43
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -705.87 | 5484.43 | -705.87 | 3180 | 2304.43
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 5484.43 | 220 | 3400 | 2084.43
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 5484.43 | 57.04 | 3457.04 | 2027.39
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 5484.43 | 500.02 | 3957.06 | 1527.37
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September, October 2022 | 116.46 | 5600.89 | 116.46 | 4073.52 | 1527.37
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -116.46 | 5484.43 | -116.46 | 3957.06 | 1527.37
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 5484.43 | 94.28 | 4051.34 | 1433.09
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 5484.43 | 571.8 | 4623.14 | 861.29
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 5484.43 | 44.07 | 4667.21 | 817.22
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 5484.43 | 193.85 | 4861.06 | 623.37
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 5484.43 | 90.57 | 4951.63 | 532.8
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 5484.43 | 532.8 | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
[5 empty] | 5484.43 |  | 5484.43 | 0
|  |  | Totals: | 5484.43 |  | 5484.43 |  | 0
Note on E9: Huggins, Joni [DAS]: Carper, Douglas 8:10 AM (17 minutes ago) to me, Scott 9178.00 Is MM21. 9220.00 Increase PM budget to $900.00. 9280.00 Set PM Budget to $8,000.00. 9281.00 Set PM Budget to $8,000.00. 9282.00 Set PM Budget to $3,000.00. 9284.00 Set PM Budget to $3,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9280.00-PM Time Shift and Closure of Funds $Joni Tonyan, Brad 1:28 PM (12 minutes ago) to me, Brad, Scott Finance, Please complete the following finance adjustments below and when done you can close the financials in this org and return the remaining funds to the client. DA22 - 9280.00 PM time - $2,515.57 - Reduce PM Time to $0 Contingency - $17,285.11 Budget Remaining Unspent when adding PM Time and Contingency together - $19,800.68 Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov

## #9280.00 Misc
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523238900 | 2022-08-26 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. 023262 | 74.95 | 74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
|  |  |  | Totals: |  | 74.95

## #9280.00 Horizon Architecture
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  | Major Program 4B03
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA22-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522094901 | 2022-04-04 | PO Procore | 23600 | 23600 |  |  | 23600
PRC 3352209PA4901 | 2022-07-05 | Inv. 9280.00-01 |  | 23600 | 17545 | 17545 | 6055
PRC 3352209PB4901 | 2022-07-07 | Inv. 9280.00-02 |  | 23600 | 1930 | 19475 | 4125 | FY22
PO 33523094901 | 2022-08-16 | Rolled to FY23 | 0 | 23600 |  | 19475 | 4125
PRC 3352309PC4901 | 2023-02-07 | Inv. 9280.00-03 |  | 23600 | 2200 | 21675 | 1925
PRC 3352309PD4901 | 2023-03-14 | Inv. 9280.00-04 - Final |  | 23600 | 1925 | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  |  |  | 23600 |  | 23600 | 0
|  | Totals: | 23600 |  | 23600 |  | 0 | FINAL
|  | Survey, Design, & Documentation | 16100 |  | 16100 |  | 0
|  | Project Management | 4500 |  | 4500 |  | 0
|  | Bidding Assistance | 1000 |  | 1000 |  | 0
|  | Construction Administration | 1000 |  | 1000 |  | 0
|  | Closeout | 1000 |  | 1000 |  | 0
|  | Total: | 23600 |  | 23600 |  | 0

## #9280.00 Grimes Asphalt
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  | Major Program 4B03
Grimes Asphalt |  |  | Vendor Code: 00003039533
Acct. Codes-0506-335-DA22-9255 |  |  | RFB #928000-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523291901 | 2022-10-17 | PO Procore VC#00002114819 | 253810.25 | 253810.25 |  |  | 253810.25
PO 33523291901 | 2022-10-28 | CO 1 | 20571.76 | 274382.01 |  | 0 | 274382.01
PRC 3352329PA1901 | 2023-01-05 | Inv. 9280.00-01 |  | 274382.01 | 258251.71 | 258251.71 | 16130.3 | 13592.2
PO 33523291901A | 2023-02-14 | Opening new PO with correct vendor code |  | 274382.01 |  | 258251.71 | 16130.3
PRC 3352329PB1901A | 2023-04-11 | Inv. 9280.00-02 |  | 274382.01 | 2411.19 | 260662.9 | 13719.11 | 13719.11
PRC 3352329PC1901A | 2023-04-14 | Inv. 9280.00-03-Retainage |  | 274382.01 | 13719.11 | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  |  |  | 274382.01 |  | 274382.01 | 0
|  | Totals: | 274382.01 |  | 274382.01 |  | 0

## #9280.00 DCI Group (2)
DVA IVC Asphalt Road Resurfacing
Project # 9280.00
Program code 928000 |  |  | Major Program 4B03
DCI Group #2 |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523304901 | 2022-10-28 | PO Procore | 7906.43 | 7906.43 |  |  | 7906.43
PRC 3352330PA4901 | 2023-01-18 | Inv. 22-013 CA-01 FINAL | -431.41 | 7475.02 | 7475.02 | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  |  |  | 7475.02 |  | 7475.02 | 0
|  | Totals: | 7475.02 |  | 7475.02 |  | 0 | Final
|  | CM Staff Hours | 7277.02 |  | 7277.02 |  | 0
|  | Reimbursable Expenses | 198 |  | 198 |  | 0
|  | Total: | 7475.02 |  | 7475.02 |  | 0

## RECAP #9281.00
DVA IVC Irrigation System Improvements
Project # 9281.00
| Program code 928100 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 66228.28
C | DCI Group |  | 6342.44 | 6342.44 | 0
| PM TIME |  | 4641.53 | 4641.53 | 0
| Misc. |  | 0 | 0 | 0
| Horizon Architecture |  | 18100 | 18100 | 0
C | Shive Hattery |  | 27063 | 27063 | 0
C | DCI Group(2) |  | 10081.31 | 10081.31 | 0
| Total Project Cost | 66228.28 | 66228.28 | 66228.28 | 0 | 0
Closed 05/10/2023

## #9281.00 Funds Rec'd
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 67022000770 | 2022-03-02 | 450000 | 450000
|  |  | Return FY22 Funds to Agency | IET 33522216801 | 2022-08-04 | -424707.56 | -424707.56
|  |  | Received FY23 funds from agency | IET 67023000295 | 2022-08-09 | 424707.56 | 424707.56
|  |  | Return Funds to Agency Per PM & Vendor | IET 33523131900 | 2023-05-10 | -383771.72 | -383771.72
| Total Requested | 0 | Total Transferred |  |  | 66228.28 | 66228.28

## #9281.00 DCI Group
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522089803 | 2022-03-30 | PO Procore | 9603.64 | 9603.64 |  |  | 9603.64
PRC 3352208PA9803 | 2022-07-07 | Inv. 22-014 PC-01 |  | 9603.64 | 4872.67 | 4872.67 | 4730.97
PRC 3352208PB9803 | 2022-07-18 | Inv. 22-014 PC-02 FINAL | -3261.2 | 6342.44 | 1469.77 | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  |  |  | 6342.44 |  | 6342.44 | 0
|  | Totals: | 6342.44 |  | 6342.44 |  | 0 | Final Invoice
|  | Pre-Construction Management Staff Hours | 6311.24 |  | 6311.24 |  | 0
|  | Reimbursable Expenses (not to exceed) | 31.2 |  | 31.2 |  | 0
|  | Total: | 6342.44 |  | 6342.44 |  | 0

## #9281.00 PM TIME
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS E21J
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 4641.53 | 4641.53 |  |  | 4641.53
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 4641.53 | 150 | 150 | 4491.53
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 4641.53 | 150 | 300 | 4341.53
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 4641.53 | 300 | 600 | 4041.53
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 4641.53 | 250 | 850 | 3791.53
IET DAS202301115300001 | 2022-08-10 |  | PM-July 1-July 29, 2022 |  | 4641.53 | 200 | 1050 | 3591.53
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 4641.53 | -200 | 850 | 3791.53
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 4641.53 | 220 | 1070 | 3571.53
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 4641.53 | 165 | 1235 | 3406.53
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 4641.53 | 440 | 1675 | 2966.53
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 4641.53 | 275 | 1950 | 2691.53
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 319.86 | 4961.39 | 319.86 | 2269.86 | 2691.53
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -319.86 | 4641.53 | -319.86 | 1950 | 2691.53
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 109.52 | 4751.05 | 109.52 | 2059.52 | 2691.53
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -109.52 | 4641.53 | -109.52 | 1950 | 2691.53
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 309.43 | 4950.96 | 309.43 | 2259.43 | 2691.53
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -309.43 | 4641.53 | -309.43 | 1950 | 2691.53
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 220.59 | 4862.12 | 220.59 | 2170.59 | 2691.53
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -220.59 | 4641.53 | -220.59 | 1950 | 2691.53
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 4641.53 | 330 | 2280 | 2361.53
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 4641.53 | 76.05 | 2356.05 | 2285.48
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 4641.53 | 666.7 | 3022.75 | 1618.78
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September, October 2022 | 55.94 | 4697.47 | 55.94 | 3078.69 | 1618.78
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -55.94 | 4641.53 | -55.94 | 3022.75 | 1618.78
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 4641.53 | 73.54 | 3096.29 | 1545.24
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 4641.53 | 445.95 | 3542.24 | 1099.29
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 4641.53 | 61.7 | 3603.94 | 1037.59
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 4641.53 | 271.39 | 3875.33 | 766.2
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 4641.53 | 111.1 | 3986.43 | 655.1
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 4641.53 | 655.1 | 4641.53 | 0
[5 empty] | 4641.53 |  | 4641.53 | 0
[5 empty] | 4641.53 |  | 4641.53 | 0
[5 empty] | 4641.53 |  | 4641.53 | 0
[5 empty] | 4641.53 |  | 4641.53 | 0
[5 empty] | 4641.53 |  | 4641.53 | 0
|  |  | Totals: | 4641.53 |  | 4641.53 |  | 0
Note on E9: Huggins, Joni [DAS]: Carper, Douglas 8:10 AM (17 minutes ago) to me, Scott 9178.00 Is MM21. 9220.00 Increase PM budget to $900.00. 9280.00 Set PM Budget to $8,000.00. 9281.00 Set PM Budget to $8,000.00. 9282.00 Set PM Budget to $3,000.00. 9284.00 Set PM Budget to $3,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9281.00-PM Time Shift and Closure of Funds $Joni Tonyan, Brad Attachments 1:59 PM (51 minutes ago) to me, Scott, Brad Finance, Please complete the following finance adjustments below and when done you can close the financials in this org and return the remaining funds to the client. Note that I also completed a dummy invoice and approved on DAS Finance behalf as it was a placeholder only. DA22 - 9281.00 PM time - $3,358.47 - Reduce PM Time to $0 Horizon Architecture - $3,900.00 shall be removed from there contract and put to general project fund. Final invoice in Procore with email PDF to confirm with Horizon they are done invoicing. I also attached it here. Contingency - $376,513.25 Budget Remaining Unspent when adding PM Time, Horizon and Contingency together - $383,771.72 Please let me know if you have any questions and when this is completed. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov

## #9281.00 Misc
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9281.00 Horizon Architecture
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  | Major Program 4B03
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA22-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522125901 | 2022-05-05 | PO Procore | 22000 | 22000 |  |  | 22000
PRC 3352212PA5901 | 2022-07-06 | Inv. 9281.00-01 |  | 22000 | 16685 | 16685 | 5315
PRC 3352212PB5901 | 2022-07-07 | Inv. 9281.00-02 |  | 22000 | 1415 | 18100 | 3900 | FY22
PO 33523125901 | 2022-08-10 | Rolled to FY23 | 0 | 22000 |  | 18100 | 3900
PO 33523125901 | 2023-05-10 | Closing PO per PM & Vendor request | -3900 | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  |  |  | 18100 |  | 18100 | 0
|  | Totals: | 18100 |  | 18100 |  | 0
|  | Survey, Desgin, Documentation | 16300 |  | 16300 |  | 0
|  | Project Mngmt | 1800 |  | 1800 |  | 0
|  | Bidding Assistance | 0 |  |  |  | 0
|  | Construction Administration | 0 |  |  |  | 0
|  | Closeout | 0 |  |  |  | 0
|  | Total: | 18100 |  | 18100 |  | 0

## #9281.00 Shive Hattery
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  | Major Program 4B03
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFB928100-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523294900 | 2022-10-19 | PO Procore | 27063 | 27063 |  |  | 27063
PRC 3352329PA4900 | 2023-01-17 | Inv. 2142205760-1 |  | 27063 | 14760 | 14760 | 12303
PRC 3352329PB4900 | 2023-04-12 | Inv. 2142205760-2 |  | 27063 | 9403 | 24163 | 2900
PRC 3352329PC4900 | 2023-04-18 | Inv. 2142205760-3 Final |  | 27063 | 2900 | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  |  |  | 27063 |  | 27063 | 0
|  | Totals: | 27063 |  | 27063 |  | 0

## #9281.00 DCI Group (2)
DVA IVC Irrigation System Improvements
Project # 9281.00
Program code 928100 |  |  | Major Program 4B03
DCI Group(2) |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523319901 | 2022-11-15 | PO Procore | 10401.11 | 10401.11 |  |  | 10401.11
PRC 3352331PA9901 | 2023-01-18 | Inv. 22-014 EVAL-01 |  | 10401.11 | 7504.67 | 7504.67 | 2896.44
PRC 3352331PB9901 | 2023-03-15 | Inv. 22-014 EVAL-02 |  | 10401.11 | 1425.89 | 8930.56 | 1470.55
PRC 3352331PC9901 | 2023-04-25 | Inv. 22-014 EVAL-03 FINAL | -319.8 | 10081.31 | 1150.75 | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  |  |  | 10081.31 |  | 10081.31 | 0
|  | Totals: | 10081.31 |  | 10081.31 |  | 0 | FINAL
|  | CM Hours | 10081.31 |  | 10081.31 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Total: | 10081.31 |  | 10081.31 |  | 0

## RECAP #9282.00
DAS CC Parking Lot 1 Replacement
Project # 9282.00
| Program code 928200 |  |  | Major Program 4G01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 74791.21
C | DCI Group |  | 11003.34 | 11003.34 | 0
C | PM TIME |  | 7272.87 | 7272.87 | 0
C | Misc. |  | 0 | 0 | 0
C | Bolton & Menk |  | 56515 | 56515 | 0
| Total Project Cost | 74791.21 | 74791.21 | 74791.21 | 0 | 0
Closed 10/09/2024

## #9282.00 Funds Rec'd
DAS CC Parking Lot 1 Replacement
Project # 9282.00
Program code 928200 |  |  | Major Program 4G01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 005FY22PROJ928200 | 2022-02-09 | 75000 | 75000
|  |  | Return FY22 Funds to Agency | IET 33522216802 | 2022-08-04 | -39679.46 | -39679.46
|  |  | Received FY23 Funds From Agency | IET 005FY23PROJ928200A | 2022-08-04 | 39679.46 | 39679.46
|  |  | Return FY23 Funds to Agency | IET 33523228915 | 2023-08-16 | -17084.77 | -17084.77
|  |  | Received FY24 Funds From Agency | IET 005FY24PROJ928200 | 2023-08-21 | 17084.77 | 17084.77
|  |  | Return FY24 Funds to Agency | IET 33524226906 | 2024-08-13 | -1347.79 | -1347.79
|  |  | Received FY25 Funds From Agency | IET 005FY25PROJ928200 | 2024-08-27 | 1347.79 | 1347.79
|  |  | Return Funds to Agency | IET 33525283901 | 2024-10-09 | -208.79 | -208.79
| Total Requested | 0 | Total Transferred |  |  | 74791.21 | 74791.21

## #9282.00 DCI Group
DAS CC Parking Lot 1 Replacement
Project # 9282.00
Program code 928200 |  |  | Major Program 4G01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522102907 | 2022-04-12 | PO Procore | 11504.11 | 11504.11 |  |  | 11504.11
PRC 3352210PA2907 | 2022-07-07 | Inv. 22-016 PC-01 |  | 11504.11 | 3073.98 | 3073.98 | 8430.13
PRC 3352210PB2907 | 2022-07-15 | Inv. 22-016 PC-02 |  | 11504.11 | 1417.56 | 4491.54 | 7012.57 | FY22
PO 33523102907 | 2022-08-09 | Rolled to FY23 | 0 | 11504.11 |  | 4491.54 | 7012.57
PRC 3352310PC2907 | 2022-09-20 | Inv. 22-016 PC-03 |  | 11504.11 | 2740.89 | 7232.43 | 4271.68
PRC 3352310PD2907 | 2022-11-08 | Inv. 22-016 PC-04 |  | 11504.11 | 1841.25 | 9073.68 | 2430.43
PRC 3352310PE2907 | 2022-11-14 | Inv. 22-016 PC-05 |  | 11504.11 | 519.7 | 9593.38 | 1910.73
PRC 3352310PF2907 | 2023-01-18 | Inv. 22-016 PC-06 |  | 11504.11 | 718.82 | 10312.2 | 1191.91
PRC 3352310PG2907 | 2023-03-20 | Inv. 22-016 PC-07 FINAL | -500.77 | 11003.34 | 691.14 | 11003.34 | 2.16e-12
|  |  |  | 11003.34 |  | 11003.34 | 2.16e-12
|  |  |  | 11003.34 |  | 11003.34 | 2.16e-12
|  |  |  | 11003.34 |  | 11003.34 | 2.16e-12
|  |  |  | 11003.34 |  | 11003.34 | 2.16e-12
|  | Totals: | 11003.34 |  | 11003.34 |  | 0 | FINAL
|  | CM Services | 11003.34 |  | 11003.34 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 11003.34 |  | 11003.34 |  | 0

## #9282.00 PM TIME
DAS CC Parking Lot 1 Replacement
Project # 9282.00
Program code 928200 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS E21K
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 7272.87 | 7272.87 |  |  | 7272.87
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 7272.87 | 50 | 50 | 7222.87
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 7272.87 | 250 | 300 | 6972.87
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 7272.87 | 400 | 700 | 6572.87
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 7272.87 | 250 | 950 | 6322.87
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 7272.87 | 500 | 1450 | 5822.87
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 7272.87 | -500 | 950 | 6322.87
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 7272.87 | 550 | 1500 | 5772.87
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 7272.87 | 220 | 1720 | 5552.87
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 7272.87 | 330 | 2050 | 5222.87
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 7272.87 | 385 | 2435 | 4837.87
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 7272.87 | 165 | 2600 | 4672.87
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 382.08 | 7654.95 | 382.08 | 2982.08 | 4672.87
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -382.08 | 7272.87 | -382.08 | 2600 | 4672.87
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 189.73 | 7462.6 | 189.73 | 2789.73 | 4672.87
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -189.73 | 7272.87 | -189.73 | 2600 | 4672.87
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 219.04 | 7491.91 | 219.04 | 2819.04 | 4672.87
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -219.04 | 7272.87 | -219.04 | 2600 | 4672.87
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 270.75 | 7543.62 | 270.75 | 2870.75 | 4672.87
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -270.75 | 7272.87 | -270.75 | 2600 | 4672.87
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 132.36 | 7405.23 | 132.36 | 2732.36 | 4672.87
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -132.36 | 7272.87 | -132.36 | 2600 | 4672.87
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 7272.87 | 110 | 2710 | 4562.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: August, September 2022 | 159.84 | 7432.71 | 159.84 | 2869.84 | 4562.87
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -159.84 | 7272.87 | -159.84 | 2710 | 4562.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 7272.87 | 15.22 | 2725.22 | 4547.65
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 7272.87 | 92.28 | 2817.5 | 4455.37
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 7272.87 | 19.6 | 2837.1 | 4435.77
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 7272.87 | 86.24 | 2923.34 | 4349.53
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 7272.87 | 98.62 | 3021.96 | 4250.91
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 7272.87 | 579.2 | 3601.16 | 3671.71
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 7272.87 | 18.63 | 3619.79 | 3653.08
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 7272.87 | 167.1 | 3786.89 | 3485.98
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 7272.87 | 66.51 | 3853.4 | 3419.47
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 7272.87 | 424.5 | 4277.9 | 2994.97
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 7272.87 | 94.8 | 4372.7 | 2900.17
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 7272.87 | 527.4 | 4900.1 | 2372.77
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 7272.87 | 7.79 | 4907.89 | 2364.98
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 7272.87 | 52.5 | 4960.39 | 2312.48
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 7272.87 | 174.53 | 5134.92 | 2137.95
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 7272.87 | 1400.3 | 6535.22 | 737.65
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 7272.87 | 42.21 | 6577.43 | 695.44
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 7272.87 | 372.3 | 6949.73 | 323.14
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 7272.87 | 53.44 | 7003.17 | 269.7
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 7272.87 | 269.7 | 7272.87 | 0
[5 empty] | 7272.87 |  | 7272.87 | 0
[5 empty] | 7272.87 |  | 7272.87 | 0
[5 empty] | 7272.87 |  | 7272.87 | 0
|  |  | Totals: | 7272.87 |  | 7272.87 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Pm Time Budget Inbox Carper, Douglas 2:34 PM (19 minutes ago) to me, Scott 9155.01 MM19 Increase PM Budget to $6,000.00. 9261.00 Time should be for 9263.00, got off a line. 9282.00 Set PM Time Budget to $3,000.00. 9283.00 Set PM Time Budget to $10,000.00. 9284.00 Set PM Time Budget to $3,500.00. Sincerely, Doug Carper, Douglas 8:10 AM (17 minutes ago) to me, Scott 9178.00 Is MM21. 9220.00 Increase PM budget to $900.00. 9280.00 Set PM Budget to $8,000.00. 9281.00 Set PM Budget to $8,000.00. 9282.00 Set PM Budget to $3,000.00. 9284.00 Set PM Budget to $3,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9282.00 DAS CC Parking Lot #1 Replacement $John Elliott, Jennie 2:15 PM (1 minute ago) to me Please increase PM time Contracted to a total of $5,000 in 9282.00 DAS CC Parking Lot #1 Replacement Thank you PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K DA22 - 9282.00 - Please increase PM time by $2K

## #9282.00 Misc
DAS CC Parking Lot 1 Replacement
Project # 9282.00
Program code 928200 |  |  |  | Major Program 4G01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9282.00 Bolton & Menk
DAS CC Parking Lot 1 Replacement
Project # 9282.00
Program code 928200 |  |  | Major Program 4G01
Bolton & Menk |  |  | Vendor: 00002104085
Acct. Codes-0506-335-DA22-9260 |  |  | RPF925900-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522130901 | 2022-05-10 | PO Procore | 49879 | 49879 |  |  | 49879
PRC 3352213PA0901 | 2022-07-08 | Inv. 0291357 |  | 49879 | 10598.5 | 10598.5 | 39280.5
PRC 3352213PB0901 | 2022-07-18 | Inv. 0293039 |  | 49879 | 19280.5 | 29879 | 20000 | FY22
PO 33523130901 | 2022-08-09 | Roll to FY23 | 0 | 49879 |  | 29879 | 20000
PRC 3352313PC0901 | 2022-09-07 | Inv. 0295088 |  | 49879 | 6945.6 | 36824.6 | 13054.4
PRC 3352313PD0901 | 2022-12-07 | Inv. 0299894 |  | 49879 | 868.2 | 37692.8 | 12186.2
PRC 3352313PE0901 | 2023-01-03 | Inv. 0301929 |  | 49879 | 868.2 | 38561 | 11318
PO 33523130901 | 2023-01-03 | CO 1 | 4564 | 54443 |  | 38561 | 15882
PRC 3352313PF0901 | 2023-01-17 | Inv. 0303928 |  | 54443 | 1114.5 | 39675.5 | 14767.5
PRC 3352313PG0901 | 2023-02-17 | Inv. 0305103 |  | 54443 | 3449.5 | 43125 | 11318 | FY23
PO 33524130901 | 2023-08-22 | Roll to FY24 | 0 | 54443 |  | 43125 | 11318
PO 33524130901 | 2023-08-22 | CO 2 (Voided in Procore) |  | 54443 |  | 43125 | 11318
PO 33524130901 | 2023-08-22 | CO 3 | 2072 | 56515 |  | 43125 | 13390
PRC 3352413PH0901 | 2024-01-10 | Inv. 0325095 |  | 56515 | 1500 | 44625 | 11890
PRC 3352413PI0901 | 2024-02-02 | Inv. 0326781, 0328501 |  | 56515 | 3761.3 | 48386.3 | 8128.7
PRC 3352413PJ0901 | 2024-03-25 | Inv. 0330482 |  | 56515 | 1397.7 | 49784 | 6731
PRC 3352413PK0901 | 2024-04-15 | Inv. 0332754 |  | 56515 | 518 | 50302 | 6213
PRC 3352413PL0901 | 2024-05-06 | Inv. 0334787 |  | 56515 | 3365.5 | 53667.5 | 2847.5
PRC 3352413PM0901 | 2024-06-13 | Inv. 0336829 |  | 56515 | 569.5 | 54237 | 2278
PRC 3352413PN0901 | 2024-06-24 | Inv. 0338862 |  | 56515 | 1139 | 55376 | 1139 | FY24
PO 33525130901 | 2024-08-26 | Roll to FY25 |  | 56515 |  | 55376 | 1139
PRC 3352513PO0901 | 2024-10-24 | Inv. 0340536 |  | 56515 | 1139 | 56515 | 0
|  |  |  | 56515 |  | 56515 | 0
|  |  |  | 56515 |  | 56515 | 0
|  | Totals: | 56515 |  | 56515 |  | 0 | FINAL
|  | 50% Construction Docs | 21197 |  | 21197 |  | 0 |  | `
|  | 100% Constructions Docs | 17364 |  | 17364 |  | 0
|  | Bidding/Negotiation Asst | 2000 |  | 2000 |  | 0
|  | Construction Phase | 9318 |  | 9318 |  | 0
|  | CO 1 | 4564 |  | 4564 |  | 0
|  | CO 3 | 2072 |  | 2072 |  | 0
|  | Total: | 56515 |  | 56515 |  | 0

## RECAP #9283.00
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
| Program code 928300 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 8900000
C | Story Construction |  | 67388.88 | 67388.88 | 0
| PM TIME |  | 212000 | 72453.11 | 139546.89
| Misc. |  | 8340.22 | 8340.22 | 0
| KPE Consulting Engineers Inc. |  | 411475 | 370423.58 | 41051.42
C | ATC Group |  | 6735 | 6735 | 0
C | Bear Creek Archeology |  | 5625 | 5625 | 0
C | DCI Group |  | 19357.79 | 19357.79 | 0
| Elite Fire Sprinkler Systems |  | 205824 | 182366.75 | 23457.25
| Haselhoff Construction |  | 5678009.66 | 4588588.15 | 1089421.51
| REW Services Corp |  | 93708 | 88072.61 | 5635.39
| Communication Innovators |  | 400768 | 246905 | 153863
C | Holmes Murphy |  | 15234 | 15234 | 0
| Schumacher Elevator CO. |  | 210055.1 | 165721.88 | 44333.22
| DCI Group |  | 1237197.91 | 635172.75 | 602025.16
| MTS Contracting |  | 34724 | 0 | 34724
| Total Project Cost | 8900000 | 8571718.56 | 6472384.72 | 2099333.84 | 328281.44

## #9283.00 Funds Rec'd
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA22-0234
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 406KM22021522 | 2022-02-15 | 200000 | 200000
|  |  | Return FY22 Funds to Agency | IET 33522216803 | 2022-08-04 | -182306.53 | -182306.53
|  |  | Received FY23 Funds From Agency | IET 406KM2308242201 | 2022-08-26 | 182306.53 | 182306.53
|  |  | MOU Amendment #1 | IET 406JP2302082301 | 2023-02-08 | 1900000 | 1900000
|  |  | Return FY23 Funds to Agency | IET 33523228916 | 2023-08-16 | -1825741.08 | -1825741.08
|  |  | Received FY24 Funds From Agency | IET 406MC2409142303 | 2023-09-14 | 1825741.08 | 1825741.08
|  |  | MOU Amend #2 | IET 406JP2410252301 | 2023-10-25 | 6000000 | 6000000
|  |  | Return FY24 Funds to Agency | IET 33524226907 | 2024-08-13 | -7629582.16 | -7629582.16
|  |  | Return FY24 Funds to Agency Correction | IET 33524226907A | 2024-08-20 | -4777.98 | -4777.98
|  |  | Received FY25 Funds From Agency | IET 41KM2509162401 | 2024-09-16 | 6885714 | 6885714
|  |  | MOU Voldeng Remodel | IET DASPROJECTS 092524 | 2024-09-26 | 748646.14 | 748646.14
|  |  | MOU Amend #3 | IET 41JP2510182401 | 2024-10-21 | 800000 | 800000
| Total Requested | 0 | Total Transferred |  |  | 8900000 | 8900000

## #9283.00 Story Construction
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522089800 | 2022-03-30 | PO Procore | 25148.08 | 25148.08 |  |  | 25148.08
PRC 3352208PA9800 | 2022-05-20 | Inv. 33129 |  | 25148.08 | 1880.44 | 1880.44 | 23267.64
PRC 3352208PB9800 | 2022-06-22 | Inv. 33174 |  | 25148.08 | 2459 | 4339.44 | 20808.64
PRC 3352208PC9800 | 2022-07-18 | Inv. 33227 |  | 25148.08 | 2210.44 | 6549.88 | 18598.2 | FY22
PO 33523089800 | 2022-08-29 | Rolled to FY23 | 0 | 25148.08 |  | 6549.88 | 18598.2
PRC 3352308PD9800 | 2022-08-29 | Inv. 33283 |  | 25148.08 | 1535 | 8084.88 | 17063.2
PRC 3352308PE9800 | 2022-09-20 | Inv. 33348 |  | 25148.08 | 1150 | 9234.88 | 15913.2
PRC 3352308PF9800 | 2022-10-17 | Inv. 33406 |  | 25148.08 | 1410 | 10644.88 | 14503.2
PRC 3352308PG9800 | 2022-11-28 | Inv. 33464 |  | 25148.08 | 1070 | 11714.88 | 13433.2
PRC 3352308PH9800 | 2022-12-20 | Inv. 33519 |  | 25148.08 | 1710 | 13424.88 | 11723.2
PRC 3352308PI9800 | 2023-01-23 | Inv. 33586 |  | 25148.08 | 2255 | 15679.88 | 9468.2
PRC 3352308PJ9800 | 2023-02-17 | Inv. 33634 |  | 25148.08 | 6121 | 21800.88 | 3347.2
PRC 3352308PK9800 | 2023-03-20 | Inv. 33687 |  | 25148.08 | 1115 | 22915.88 | 2232.2 |  | `
PO 33523089800 | 2023-03-22 | CO #1 | 11972 | 37120.08 |  | 22915.88 | 14204.2
PRC 3352308PL9800 | 2023-04-18 | Inv. 33733 |  | 37120.08 | 3518 | 26433.88 | 10686.2
PRC 3352308PM9800 | 2023-05-22 | Inv. 33788 |  | 37120.08 | 1470 | 27903.88 | 9216.2
PO 33523089800 | 2023-06-21 | CO #2 | 13548.83 | 50668.91 |  | 27903.88 | 22765.03
PRC 3352308PN9800 | 2023-06-21 | Inv. 33836 |  | 50668.91 | 2570 | 30473.88 | 20195.03
PRC 3352308PO9800 | 2023-07-17 | Inv. 33894 |  | 50668.91 | 2212 | 32685.88 | 17983.03 | FY23
PO 33524089800 | 2023-08-28 | Roll to FY24 | 0 | 50668.91 |  | 32685.88 | 17983.03
PRC 3352408PP9800 | 2023-09-19 | Inv. 33951 |  | 50668.91 | 10076.5 | 42762.38 | 7906.53
PO 33524089800 | 2023-09-19 | CO #3 | 10413.41 | 61082.32 |  | 42762.38 | 18319.94
PRC 3352408PQ9800 | 2023-09-29 | Inv. 34005 |  | 61082.32 | 8265.5 | 51027.88 | 10054.44
PRC 3352408PR9800 | 2023-10-17 | Inv. 34066 |  | 61082.32 | 3452.5 | 54480.38 | 6601.94
PO 33524089800 | 2023-11-15 | CO #4 | 7970.02 | 69052.34 |  | 54480.38 | 14571.96
PRC 3352408PS9800 | 2023-11-21 | Inv. 34119 |  | 69052.34 | 3517.5 | 57997.88 | 11054.46
PRC 3352408PT9800 | 2024-01-17 | Inv. 34205 - Final | -1663.46 | 67388.88 | 9391 | 67388.88 | 6.3665e-12
|  |  |  | 67388.88 |  | 67388.88 | 6.3665e-12
|  |  |  | 67388.88 |  | 67388.88 | 6.3665e-12
|  | Totals: | 67388.88 |  | 67388.88 |  | 0 | FINAL
|  | CM Services | 24340 |  | 24340 |  | 0
|  | Reimbursables | 808.08 |  | 808.08 |  | 0
|  | CO #1 | 11972 |  | 11972 |  | 0
|  | CO #2 | 13548.83 |  | 13548.83 |  | 0
|  | CO #3 | 10265.21 |  | 10265.21 |  | 0
|  | CO #4 | 6454.76 |  | 6454.76 |  | 0
|  | Total: | 67388.88 |  | 67388.88 |  | 0

## #9283.00 PM TIME
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E21L
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 212000 | 212000 |  |  | 212000
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28,2022 |  | 212000 | 100 | 100 | 211900
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 212000 | 350 | 450 | 211550
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 212000 | 950 | 1400 | 210600
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 212000 | 750 | 2150 | 209850
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 212000 | 1000 | 3150 | 208850
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 212000 | 450 | 3600 | 208400
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 212000 | -450 | 3150 | 208850
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 212000 | 495 | 3645 | 208355
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 212000 | 660 | 4305 | 207695
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 212000 | 605 | 4910 | 207090
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 212000 | 605 | 5515 | 206485
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 212000 | 550 | 6065 | 205935
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 236.87 | 212236.87 | 236.87 | 6301.87 | 205935
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -236.87 | 212000 | -236.87 | 6065 | 205935
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 569.17 | 212569.17 | 569.17 | 6634.17 | 205935
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -569.17 | 212000 | -569.17 | 6065 | 205935
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 401.58 | 212401.58 | 401.58 | 6466.58 | 205935
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -401.58 | 212000 | -401.58 | 6065 | 205935
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 425.46 | 212425.46 | 425.46 | 6490.46 | 205935
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -425.46 | 212000 | -425.46 | 6065 | 205935
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 441.18 | 212441.18 | 441.18 | 6506.18 | 205935
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -441.18 | 212000 | -441.18 | 6065 | 205935
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 212000 | 110 | 6175 | 205825
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 212000 | 171.11 | 6346.11 | 205653.89
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 212000 | 1500.08 | 7846.19 | 204153.81
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: August, September 2022 | 145.46 | 212145.46 | 145.46 | 7991.65 | 204153.81
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -145.46 | 212000 | -145.46 | 7846.19 | 204153.81
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 212000 | 174.99 | 8021.18 | 203978.82
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 212000 | 1061.12 | 9082.3 | 202917.7
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 212000 | 558.82 | 9641.12 | 202358.88
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 212000 | 2457.97 | 12099.09 | 199900.91
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 212000 | 189.61 | 12288.7 | 199711.3
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 212000 | 1115.3 | 13404 | 198596
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 212000 | 250.1 | 13654.1 | 198345.9
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 212000 | 1752.3 | 15406.4 | 196593.6
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 212000 | 124.69 | 15531.09 | 196468.91
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 212000 | 995.7 | 16526.79 | 195473.21
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 212000 | 357.46 | 16884.25 | 195115.75
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 212000 | 2278 | 19162.25 | 192837.75
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 212000 | 559.06 | 19721.31 | 192278.69
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 212000 | 3121.2 | 22842.51 | 189157.49
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 212000 | 341.87 | 23184.38 | 188815.62
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 212000 | 2373.7 | 25558.08 | 186441.92
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 212000 | 197.91 | 25755.99 | 186244.01
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 212000 | 1592.1 | 27348.09 | 184651.91
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 212000 | 310.81 | 27658.9 | 184341.1
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 212000 | 2349.3 | 30008.2 | 181991.8
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 212000 | 190.23 | 30198.43 | 181801.57
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 212000 | 1395.8 | 31594.23 | 180405.77
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 212000 | 240.81 | 31835.04 | 180164.96
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 212000 | 2127.4 | 33962.44 | 178037.56
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 212000 | 306.47 | 34268.91 | 177731.09
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 212000 | 1542.4 | 35811.31 | 176188.69
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 212000 | 159.39 | 35970.7 | 176029.3
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 212000 | 1206.7 | 37177.4 | 174822.6
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 212000 | 221.89 | 37399.29 | 174600.71
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 212000 | 1973.4 | 39372.69 | 172627.31
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 212000 | 131.75 | 39504.44 | 172495.56
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 212000 | 1091 | 40595.44 | 171404.56
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 212000 | 120.13 | 40715.57 | 171284.43
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 212000 | 1096.4 | 41811.97 | 170188.03
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 212000 | 200.79 | 42012.76 | 169987.24
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 212000 | 2188.2 | 44200.96 | 167799.04
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 212000 | 429.01 | 44629.97 | 167370.03
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 212000 | 2183.2 | 46813.17 | 165186.83
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 212000 | 130.03 | 46943.2 | 165056.8
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 212000 | 1157.4 | 48100.6 | 163899.4
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 212000 | 478.62 | 48579.22 | 163420.78
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 212000 | 3189 | 51768.22 | 160231.78
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 212000 | 433.58 | 52201.8 | 159798.2
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 212000 | 2882.5 | 55084.3 | 156915.7
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 212000 | 180.57 | 55264.87 | 156735.13
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 212000 | 1804.8 | 57069.67 | 154930.33
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 212000 | 269.58 | 57339.25 | 154660.75
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 212000 | 2876.4 | 60215.65 | 151784.35
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 212000 | 669.55 | 60885.2 | 151114.8
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 212000 | 2897.6 | 63782.8 | 148217.2
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 212000 | 309.01 | 64091.81 | 147908.19
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 212000 | 2210.2 | 66302.01 | 145697.99
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 212000 | 352.22 | 66654.23 | 145345.77
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 212000 | 2418.2 | 69072.43 | 142927.57
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 212000 | 382.88 | 69455.31 | 142544.69
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 212000 | 2997.8 | 72453.11 | 139546.89
[5 empty] | 212000 |  | 72453.11 | 139546.89
[5 empty] | 212000 |  | 72453.11 | 139546.89
|  |  | Totals: | 212000 |  | 72453.11 |  | 139546.89
Note on E9: Huggins, Joni [DAS]: Re: Pm Time Budget Inbox Carper, Douglas 2:34 PM (21 minutes ago) to me, Scott 9155.01 MM19 Increase PM Budget to $6,000.00. 9261.00 Time should be for 9263.00, got off a line. 9282.00 Set PM Time Budget to $3,000.00. 9283.00 Set PM Time Budget to $10,000.00. 9284.00 Set PM Time Budget to $3,500.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9283.00 - Increase PM Time Inbox Elliott, Jennie 12:39 PM (2 minutes ago) to DAS, me Please increase PM time in project 9283.00 by $30,000, thus making total PM time budget $40,000 9283.00 - DHS CHMHI Voldeng - PM Time $Joni Elliott, Jennie May 31, 2024, 4:11 PM (3 days ago) to me Please increase PM Time to a total of $212,000.00 in the "Contracted" line. Thank you, Jennie Elliott

## #9283.00 Misc
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code: 548
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522181903 | 2022-06-30 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2435371-Final | 4402.5 | 4402.5
PRC 33524355800 | 2023-12-21 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL198 | 363.89 | 4766.39
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 550 | 5316.39
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 302.5 | 5618.89
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 82.5 | 5701.39
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -935 | 4766.39
PRC 33524169901 | 2024-06-17 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL622 | 898.83 | 5665.22
PRC 33525090909 | 2025-03-31 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2638144 | 2675 | 8340.22
8340.22
8340.22
8340.22
8340.22
|  |  |  | Totals: |  | 8340.22

## #9283.00 KPE Consulting
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
KPE Consulting Engineers Inc. |  |  | Vendor: 00003012020
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: 928300-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522157800 | 2022-06-03 | PO Procore | 116600 | 116600 |  |  | 116600
PRC 3352215PA7800 | 2022-07-06 | Inv. 8471 |  | 116600 | 3591.09 | 3591.09 | 113008.91 | FY22
PO 33523157800 | 2022-08-29 | Roll to FY23 | 0 | 116600 |  | 3591.09 | 113008.91
PRC 3352315PB7800 | 2022-08-29 | Inv. 9283.00-002 |  | 116600 | 3298.91 | 6890 | 109710
PRC 3352315PC7800 | 2022-09-15 | Inv. 9283.00-003 |  | 116600 | 2292.5 | 9182.5 | 107417.5
PO 33523157800 | 2022-10-28 | CO 1 | 31700 | 148300 |  | 9182.5 | 139117.5
PRC 3352315PD7800 | 2022-12-20 | Inv. 9283.00-4 |  | 148300 | 39248.94 | 48431.44 | 99868.56
PRC 3352315PE7800 | 2023-01-16 | Inv. 9283.00-005 |  | 148300 | 14181.38 | 62612.82 | 85687.18
PRC 3352315PF7800 | 2023-02-15 | Inv. 9283.00-006 |  | 148300 | 3045 | 65657.82 | 82642.18
PO 33523157800 | 2023-03-14 | CO 2 | 30150 | 178450 |  | 65657.82 | 112792.18
PRC 3352315PG7800 | 2023-04-18 | Inv. 9283.00-007 |  | 178450 | 11128.85 | 76786.67 | 101663.33
PO 33523157800 | 2023-04-27 | CO 3 | 184100 | 362550 |  | 76786.67 | 285763.33
PRC 3352315PH7800 | 2023-05-22 | Inv. 9283.00-008 |  | 362550 | 34540.97 | 111327.64 | 251222.36
PRC 3352315PI7800 | 2023-06-19 | Inv. 9283.00-009 |  | 362550 | 34516.5 | 145844.14 | 216705.86
PO 33523157800 | 2023-06-21 | CO 4 | 24850 | 387400 |  | 145844.14 | 241555.86
PRC 3352315PJ7800 | 2023-07-17 | Inv. 9283.00-002-10 |  | 387400 | 74799.61 | 220643.75 | 166756.25 | FY23
PO 33524157800 | 2023-08-28 | Roll to FY24 | 0 | 387400 |  | 220643.75 | 166756.25
PRC 3352415PK7800 | 2023-09-19 | Inv. 9283.00-011 |  | 387400 | 58813.25 | 279457 | 107943
PRC 3352415PL7800 | 2023-09-29 | Inv. 9283.00-12 |  | 387400 | 14878 | 294335 | 93065
PRC 3352415PM7800 | 2024-01-26 | Inv. 9283.00-13 |  | 387400 | 9915 | 304250 | 83150
PRC 3352415PN7800 | 2024-06-17 | Inv. 9283.00-14 |  | 387400 | 1797 | 306047 | 81353 | FY24
PO 33525157800 | 2024-08-26 | Roll to FY25 | 0 | 387400 |  | 306047 | 81353
PRC 3352515PO7800 | 2024-09-17 | Inv. 9283.00-15 |  | 387400 | 7500 | 313547 | 73853
PRC 3352515PP7800 | 2024-09-26 | Inv. 9283.00-16 |  | 387400 | 10748.25 | 324295.25 | 63104.75
PRC 3352515PQ7800 | 2024-10-16 | Inv. 9283.00-17 |  | 387400 | 12952.14 | 337247.39 | 50152.61
PRC 3352515PR7800 | 2024-11-20 | Inv. 9283.00-18 |  | 387400 | 9669.63 | 346917.02 | 40482.98
PO 33525157800 | 2024-12-09 | CO 5 | 8500 | 395900 |  | 346917.02 | 48982.98
PRC 3352515PS7800 | 2024-12-18 | Inv. 9283.00-19 |  | 395900 | 1500 | 348417.02 | 47482.98
PRC 3352515PT7800 | 2025-01-13 | Inv. 9283.00-20 |  | 395900 | 2730 | 351147.02 | 44752.98
PRC 3352515PU7800 | 2025-02-17 | Inv. 9283.00-21 |  | 395900 | 4900 | 356047.02 | 39852.98
PRC 3352515PV7800 | 2025-03-17 | Inv. 9283.00-22 |  | 395900 | 5040 | 361087.02 | 34812.98
PO 33525157800 | 2025-04-14 | CO 6 | 11600 | 407500 |  | 361087.02 | 46412.98
PRC 3352515PW7800 | 2025-04-25 | Inv. 9283.00-23 |  | 407500 | 1390 | 362477.02 | 45022.98
PRC 3352515PX7800 | 2025-05-09 | Inv. 9283.00-24 |  | 407500 | 4017.2 | 366494.22 | 41005.78
PO 33525157800 | 2025-06-09 | CO 7 | 3975 | 411475 |  | 366494.22 | 44980.78
PRC 3352515PY7800 | 2025-06-16 | Inv. 9283.00-25 |  | 411475 | 3929.36 | 370423.58 | 41051.42
|  |  |  | 411475 |  | 370423.58 | 41051.42
|  |  |  | 411475 |  | 370423.58 | 41051.42
|  |  |  | 411475 |  | 370423.58 | 41051.42
|  | Totals: | 411475 |  | 370423.58 |  | 41051.42
|  | Design Development | 36350 |  | 36350 |  | 0
|  | Construction Documents | 43100 |  | 43100 |  | 0
|  | Bidding | 5875 |  | 5875 |  | 0
|  | Construction Administration | 31275 |  | 28282.02 |  | 2992.98
|  | CO 1 | 31700 |  | 31700 |  | 0
|  | CO 2 | 30150 |  | 30150 |  | 0
|  | CO 3 | 184100 |  | 156450 |  | 27650
|  | CO 4 | 24850 |  | 24850 |  | 0
|  | CO 5 | 8500 |  | 8500 |  | 0
|  | CO 6 | 11600 |  | 5166.56 |  | 6433.44
|  | CO 7 | 3975 |  |  |  | 3975
|  | Total: | 411475 |  | 370423.58 |  | 41051.42

## #9283.00 ATC Group
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA22-9255 |  |  | MA# 20262C
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524262803 | 2023-09-19 | DO Procore | 9417.5 | 9417.5 |  |  | 9417.5
PRC 3352426PA2803 | 2023-12-20 | Inv. 2543131 |  | 9417.5 | 4510 | 4510 | 4907.5 | FY24
PO 33525262803 | 2024-08-26 | Roll to FY25 |  | 9417.5 |  | 4510 | 4907.5
PO 33525262803 | 2024-10-02 | CO #1 | 2375 | 11792.5 |  | 4510 | 7282.5
PRC 3352526PB2803 | 2024-11-13 | Inv. 2602024 - FINAL | -5057.5 | 6735 | 2225 | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  |  |  | 6735 |  | 6735 | 0
|  | Totals: | 6735 |  | 6735 |  | 0 | FINAL
|  | Field Technician | 1425 |  | 1425 |  | 0
|  | Industrial Hygienist | 2755 |  | 2755 |  | 0
|  | Asbestos Samples | 90 |  | 90 |  | 0
|  | Lead Paint Samples | 60 |  | 60 |  | 0
|  | Adminstrative Time | 180 |  | 180 |  | 0
|  | Air Samples | 0 |  |  |  | 0
|  | CO #1 Lead | 2225 |  | 2225 |  | 0
|  | Total: | 6735 |  | 4510 |  | 0

## #9283.00 Bear Creek Archeology
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Bear Creek Archeology |  |  | Vendor: 00002117915
Acct. Codes-0506-335-DA22-9260 |  |  | 928300-02
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524292800 | 2023-10-19 | PO Procore | 5625 | 5625 |  |  | 5625
PRC 3352429PA2800 | 2024-01-22 | Inv. 24-04 |  | 5625 | 5625 | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  |  |  | 5625 |  | 5625 | 0
|  | Totals: | 5625 |  | 5625 |  | 0

## #9283.00 DCI Group
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524004900 | 2024-01-04 | DO Procore | 19829.04 | 19829.04 |  |  | 19829.04
PRC 3352400PA4900 | 2024-03-18 | Inv. 23-054 PC-01 |  | 19829.04 | 11413.37 | 11413.37 | 8415.67
PRC 3352400PB4900 | 2024-05-07 | Inv. 23-054 PC 02 FINAL | -471.25 | 19357.79 | 7944.42 | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  |  |  | 19357.79 |  | 19357.79 | 0
|  | Totals: | 19357.79 |  | 19357.79 |  | 0 | FINAL
|  | Construction Management | 18757.51 |  | 18757.51 |  | 0
|  | Reimbursable | 600.28 |  | 600.28 |  | 0
|  | Total: | 19357.79 |  | 19357.79 |  | 0

## #9283.00 Elite Fire Sprinkler
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Elite Fire Sprinkler |  |  | Vendor: 00003212887
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#928300-02
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524142904 | 2024-05-21 | PO Procore | 195880 | 195880 |  |  | 195880 |  | FY24
PO 33525142904 | 2024-08-26 | Roll to FY25 | 0 | 195880 |  | 0 | 195880
PRC 3352514PA2904 | 2024-09-17 | Inv. Pay App 1 |  | 195880 | 16387.5 | 16387.5 | 179492.5 | 862.5
PRC 3352514PB2904 | 2024-09-27 | Inv. Pay App 2 |  | 195880 | 16767.5 | 33155 | 162725 | 1745
PRC 3352514PC2904 | 2024-10-31 | Inv. Pay App 3.00* |  | 195880 | 94544.95 | 127699.95 | 68180.05 | 6721.05
PRC 3352514PD2904 | 2024-12-06 | Inv. Pay App 4 |  | 195880 | 28262.5 | 155962.45 | 39917.55 | 8208.55
PO 33525142904 | 2024-12-18 | CO #1 | 2997 | 198877 |  | 155962.45 | 42914.55
PO 33525142904 | 2024-12-31 | CO #2 | 4196 | 203073 |  | 155962.45 | 47110.55
PRC 3352514PE2904 | 2025-01-14 | Inv. Pay App 5 |  | 203073 | 14152.15 | 170114.6 | 32958.4 | 8953.4
PO 33525142904 | 2025-01-24 | CO #3 | 776 | 203849 |  | 170114.6 | 33734.4
PRC 3352514PF2904 | 2025-02-05 | Inv. Pay App 6 |  | 203849 | 3986.2 | 174100.8 | 29748.2 | 9163.2
PO 33525142904 | 2025-02-18 | CO #4 | 358 | 204207 |  | 174100.8 | 30106.2
PRC 3352514PG2904 | 2025-03-04 | Inv. Pay App 7 |  | 204207 | 6729.8 | 180830.6 | 23376.4 | 9517.4
PO 33525142904 | 2025-05-22 | CO #5 (No Cost) | 0 | 204207 |  | 180830.6 | 23376.4
PO 33525142904 | 2025-06-10 | CO#6 | 1617 | 205824 |  | 180830.6 | 24993.4
PRC 3352514PH2904 | 2025-06-30 | Inv. Pay App 8 |  | 205824 | 1536.15 | 182366.75 | 23457.25 | 9598.25
|  |  |  | 205824 |  | 182366.75 | 23457.25
|  |  |  | 205824 |  | 182366.75 | 23457.25
|  |  |  | 205824 |  | 182366.75 | 23457.25
|  |  |  | 205824 |  | 182366.75 | 23457.25
|  | Totals: | 205824 |  | 182366.75 |  | 23457.25
*Vendor has previously used Inv. Pay App 3

## #9283.00 Haselhoff Construction
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Haselhoff Construction |  |  | Vendor: 00002118715
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#928300-02
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524142905 | 2024-05-21 | PO Procore | 5071100 | 5071100 |  |  | 5071100 |  | FY24
PO 33525142905 | 2024-08-26 | Roll to FY25 | 0 | 5071100 |  | 0 | 5071100
PRC 3352514PA2905 | 2024-09-17 | Inv. 9283.00-01 |  | 5071100 | 46025.1 | 46025.1 | 5025074.9 | 2422.37
PRC 3352514PB2905 | 2024-09-27 | Inv. 9283.00-02 |  | 5071100 | 87304.06 | 133329.16 | 4937770.84 | 7017.32
PO 33525142905 | 2024-10-10 | CO #1 | 15730.47 | 5086830.47 |  | 133329.16 | 4953501.31
PO 33525142905 | 2024-10-14 | CO #2 | -4600 | 5082230.47 |  | 133329.16 | 4948901.31
PRC 3352514PC2905 | 2024-10-15 | Inv. 9283.00-03 |  | 5082230.47 | 313396.21 | 446725.37 | 4635505.1 | 23511.87
PO 33525142905 | 2024-10-24 | CO #3 | 1782 | 5084012.47 |  | 446725.37 | 4637287.1
PO 33525142905 | 2024-11-04 | CO #4 | 96303.4 | 5180315.87 |  | 446725.37 | 4733590.5
PRC 3352514PD2905 | 2024-11-20 | Inv. 9283.00-04 |  | 5180315.87 | 358151.78 | 804877.15 | 4375438.72 | 42361.97
PO 33525142905 | 2024-12-10 | CO #5 | 1892.7 | 5182208.57 |  | 804877.15 | 4377331.42
PRC 3352514PE2905 | 2024-12-18 | Inv. 9283.00-05 |  | 5182208.57 | 408396.74 | 1213273.89 | 3968934.68 | 63856.54
PRC 3352514PF2905 | 2025-01-14 | Inv. 9283.00-06 |  | 5182208.57 | 312786.59 | 1526060.48 | 3656148.09 | 80318.98
PO 33525142905 | 2025-01-24 | CO #6 | 13437.6 | 5195646.17 |  | 1526060.48 | 3669585.69
PRC 3352514PG2905 | 2025-02-17 | Inv. 9283.00-07 |  | 5195646.17 | 370498.7 | 1896559.18 | 3299086.99 | 99818.92
PO 33525142905 | 2025-02-18 | CO #7 | 1947 | 5197593.17 |  | 1896559.18 | 3301033.99
PO 33525142905 | 2025-03-06 | CO #8 | 234510.34 | 5432103.51 |  | 1896559.18 | 3535544.33
PRC 3352514PH2905 | 2025-03-10 | Inv. 9283.00-08 |  | 5432103.51 | 605561.82 | 2502121 | 2929982.51 | 131690.59
PO 33525142905 | 2025-03-18 | CO #9 | 45224.3 | 5477327.81 |  | 2502121 | 2975206.81
PRC 3352514PI2905 | 2025-04-08 | Inv. 9283.00-09 |  | 5477327.81 | 190392.5 | 2692513.5 | 2784814.31 | 141711.26
PRC 3352514PJ2905 | 2025-05-09 | Inv. 9283.00-10 |  | 5477327.81 | 431815.21 | 3124328.71 | 2352999.1 | 164438.38
PO 33525142905 | 2025-06-03 | CO #10 | 197709.9 | 5675037.71 |  | 3124328.71 | 2550709
PRC 3352514PK2905 | 2025-06-10 | Inv. 9283.00-11 |  | 5675037.71 | 571688.16 | 3696016.87 | 1979020.84 | 194527.23
PO 33525142905 | 2025-06-10 | CO #11 | 2971.95 | 5678009.66 |  | 3696016.87 | 1981992.79
PRC 3352514PL2905 | 2025-06-30 | Inv. 9283.00-12 |  | 5678009.66 | 892571.28 | 4588588.15 | 1089421.51 | 241504.69
|  |  |  | 5678009.66 |  | 4588588.15 | 1089421.51
|  |  |  | 5678009.66 |  | 4588588.15 | 1089421.51
|  | Totals: | 5678009.66 |  | 4588588.15 |  | 1089421.51

## #9283.00 REW Services Corp
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
REW Services Corp |  |  | Vendor: 00003105700
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#928300-02
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524142906 | 2024-05-21 | PO Procore | 93708 | 93708 |  |  | 93708 |  | FY24
PO 33525142906 | 2024-08-26 | Roll to FY25 | 0 | 93708 |  | 0 | 93708
PRC 3352514PA2906 | 2024-09-17 | Inv. 9283.00-01 |  | 93708 | 59411.74 | 59411.74 | 34296.26 | 3126.93
PRC 3352514PB2906 | 2024-09-27 | Inv. 9283.00-02 |  | 93708 | 28660.87 | 88072.61 | 5635.39 | 4635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  |  |  | 93708 |  | 88072.61 | 5635.39
|  | Totals: | 93708 |  | 88072.61 |  | 5635.39

## #9283.00 Communication Innovato
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Communication Innovators |  |  | Vendor: 00002119160
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#928300-02
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524142803 | 2024-05-21 | PO Procore (Unencumbered) |  | 0 |  |  | 0 |  | FY24
PO 33525142803 | 2024-08-26 | Roll to FY25 | 0 | 0 |  | 0 | 0
PO 33525142803A | 2024-10-21 | PO Procore- Move to Encumbered | 369438 | 369438 |  | 0 | 369438
PO 33525142803A | 2025-02-21 | CO #1 | 12095 | 381533 |  | 0 | 381533
PO 33525142803A | 2025-04-29 | CO #2 | 19235 | 400768 |  | 0 | 400768
PRC 3352514PA2803A | 2025-05-29 | Inv. 9283.00-01 |  | 400768 | 211280 | 211280 | 189488 | 11120
PRC 3352514PB2803A | 2025-06-10 | Inv. 9283.00-02 |  | 400768 | 35625 | 246905 | 153863 | 12995
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  |  |  | 400768 |  | 246905 | 153863
|  | Totals: | 400768 |  | 246905 |  | 153863

## #9283.00 Holmes Murphy
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Holmes Murphy |  |  | Vendor: 00002110543
Acct. Codes-0506-335-DA22-9255 |  |  | 24143
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524151904 | 2024-05-30 | DO Procore | 15234 | 15234 |  |  | 15234
PRC 3352415PA1904 | 2024-05-31 | Inv. 772416 |  | 15234 | 15234 | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  |  |  | 15234 |  | 15234 | 0
|  | Totals: | 15234 |  | 15234 |  | 0

## #9283.00 Shumacher Elevator CO.
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
Schumacher Elevator CO. |  |  | Vendor: 00002108471
Acct. Codes-0506-335-DA22-9255 |  |  | RFB#928300-02
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524157802 | 2024-06-05 | PO Procore (Unencumbered) |  | 0 |  |  | 0 |  | FY24
PO 33525157802 | 2024-08-26 | Roll to FY25 | 0 | 0 |  | 0 | 0
PO 33525157802A | 2024-10-21 | PO Procore- Move to Encumbered | 184917 | 184917 |  | 0 | 184917
PO 3352515PA7802A | 2025-02-05 | Inv. 90637480 |  | 184917 | 87562.54 | 87562.54 | 97354.46 | 4608.56
PO 3352515PB7802A | 2025-03-31 | Inv. 90643066 |  | 184917 | 45054.65 | 132617.19 | 52299.81 | 6979.86
PO 33525157802A | 2025-04-15 | CO #1 | 4759.1 | 189676.1 |  | 132617.19 | 57058.91
PO 3352515PC7802A | 2025-04-28 | Inv. 90645953 |  | 189676.1 | 24912.94 | 157530.13 | 32145.97 | 8291.07
PO 3352515PD7802A | 2025-06-03 | Inv. 90648724 |  | 189676.1 | 8191.75 | 165721.88 | 23954.22 | 8722.22
PO 33525157802A | 2025-06-10 | CO #2 | 20379 | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  |  |  | 210055.1 |  | 165721.88 | 44333.22
|  | Totals: | 210055.1 |  | 165721.88 |  | 44333.22

## #9283.00 DCI Group (2)
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525261901 | 2024-09-17 | PO Procore | 1237197.91 | 1237197.91 |  |  | 1237197.91
PRC 3352526PA1901 | 2024-10-23 | Inv. 23-054 CA-01 |  | 1237197.91 | 178776.13 | 178776.13 | 1058421.78
PRC 3352526PB1901 | 2024-12-03 | Inv. 23-054 CA 02 |  | 1237197.91 | 59055.54 | 237831.67 | 999366.24
PRC 3352526PC1901 | 2024-12-18 | Inv. 23-054 CA 03 |  | 1237197.91 | 44346.18 | 282177.85 | 955020.06
PRC 3352526PD1901 | 2025-01-13 | Inv. 23-054 CA 04 |  | 1237197.91 | 59617.89 | 341795.74 | 895402.17
PRC 3352526PE1901 | 2025-02-05 | Inv. 23-054 CA 05 |  | 1237197.91 | 53167.02 | 394962.76 | 842235.15
PRC 3352526PF1901 | 2025-03-17 | Inv. 23-054 CA 06 |  | 1237197.91 | 56731.8 | 451694.56 | 785503.35
PO 33525261901 | 2025-03-25 | CO #1(No Cost CO) | 0 | 1237197.91 |  | 451694.56 | 785503.35
PRC 3352526PG1901 | 2025-04-14 | Inv. 23-054 CA 07 |  | 1237197.91 | 40626.91 | 492321.47 | 744876.44
PRC 3352526PH1901 | 2025-05-29 | Inv. 23-054 CA 08 |  | 1237197.91 | 69996.17 | 562317.64 | 674880.27
PRC 3352526PI1901 | 2025-06-23 | Inv. 23-054 CA 09 |  | 1237197.91 | 72855.11 | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  |  |  | 1237197.91 |  | 635172.75 | 602025.16
|  | Totals: | 1237197.91 |  | 635172.75 |  | 602025.16
|  | CM Staff | 755562.91 |  | 421882.65 |  | 333680.26
|  | CM Fee | 196195.82 |  | 156376.53 |  | 39819.29
|  | CM Reimbursables | 285439.18 |  | 56913.57 |  | 228525.61
|  | CO #1 Moved $11,442.77 from Staff to Fees | 0 |  |  |  | 0
|  | Total: | 1237197.91 |  | 635172.75 |  | 602025.16

## #9283.00 MTS Contracting
DHS CHMHI Voldeng Building 1st Floor Remodel
Project # 9283.00
Program code 928300 |  |  | Major Program 4B02
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0506-335-DA22-9255 |  |  | MA 20243C
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525010901 | 2025-01-10 | PO Procore | 34724 | 34724 |  |  | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  |  |  | 34724 |  | 0 | 34724
|  | Totals: | 34724 |  | 0 |  | 34724

## RECAP #9285.00
DPS P15 Property Disposal
Project # 9285.00
| Program code 928500 |  |  | Major Program 4E12
Recap
Acct. Codes-0506-335-DA22
Project Manager - Barb B.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 956.25
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 956.25 | 956.25 | 0
| Total Project Cost | 956.25 | 956.25 | 956.25 | 0 | 0
Closed 08/17/2023

## #9285.00 Funds Rec'd
DPS P15 Property Disposal
Project # 9285.00
Program code 928500 |  |  | Major Program 4E12
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Barb B.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 030822KPH02ISP | 2022-03-08 | 10000 | 10000
|  |  | Return FY22 Funds to Agency | IET 33522216806 | 2022-08-04 | -9043.75 | -9043.75
|  |  | Received FY23 funds from agency | IET 083122LKG02ISP | 2022-08-31 | 9043.75 | 9043.75
|  |  | MOU #: 22-019 DPS and ICN | IET 092322KPH04ISP | 2022-09-28 | 1496.25 | 1496.25
|  |  | Closing per PM & Return Funds to Agency | IET 33523229926 | 2023-08-17 | -10540 | -10540
| Total Requested | 0 | Total Transferred |  |  | 956.25 | 956.25

## #9285.00 Vendor A
DPS P15 Property Disposal
Project # 9285.00
Program code 928500 |  |  | Major Program 4E12
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Barb B. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9285.00 PM TIME
DPS P15 Property Disposal
Project # 9285.00
Program code 928500 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Barb B. |  |  |  | eDAS 723U
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
IET DAS202305115300001 | 2022-12-07 | 1926-01-03 | PM-July 1-July 29, 2022 9997.23 Disbursement | 536.73 | 536.73 | 536.73 | 536.73 | 0
CDE 33523353209 | 2022-12-21 | 1926-01-03 | Move PM time to 9997.23 MM23 | -536.73 | 0 | -536.73 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9285.00 Misc
DPS P15 Property Disposal
Project # 9285.00
Program code 928500 |  |  |  | Major Program 4E12
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Barb B.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202209115300001 | 2022-04-08 | 2323 |  | DPS Post 15 | DAS2022091153 | 212.5 | 212.5
IET DAS202210115300001 | 2022-05-06 | 2323 |  | DPS Post 15 | DAS2022101153 | 425 | 637.5
IET DAS202211115300001 | 2022-06-07 | 2323 |  | Leasing Services | DAS2022111153 | 233.75 | 871.25
IET DAS202212115300001 | 2022-07-08 | 2323 |  | DPS-Post Meeting | DAS2022121153 | 85 | 956.25
956.25
956.25
956.25
956.25
956.25
956.25
956.25
956.25
|  |  |  | Totals: |  | 956.25

## RECAP #9286.00
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
| Program code 928600 |  |  | Major Program 4E12
Recap
Acct. Codes-0506-335-DA22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 11887.35
C | Boyd Jones Construction |  | 4180.6 | 4180.6 | 0
C | PM TIME |  | 1850 | 1850 | 0
C | Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 5856.75 | 5856.75 | 0
| Total Project Cost | 11887.35 | 11887.35 | 11887.35 | 0 | 0
CLOSED 09/30/2022

## #9286.00 Funds Rec'd
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
Program code 928600 |  |  | Major Program 4E12
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 031022KPH01ISP | 2022-03-11 | 12000 | 12000
|  |  | Return FY22 Funds to Agency | IET 33522216807 | 2022-08-04 | -1212.65 | -1212.65
|  |  | Received FY23 funds from agency | IET 083122LKG03ISP | 2022-08-31 | 1212.65 | 1212.65
|  |  | Return Remaining Funds to Agency | IET 33523257804 | 2022-09-14 | -112.65 | -112.65
| Total Requested | 0 | Total Transferred |  |  | 11887.35 | 11887.35

## #9286.00 PM TIME
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
Program code 928600 |  |  | Major Program 4E12
PM TIME |  |  | Internal documents
Acct. Codes-0506-335-DA22-xxxx |  |  | PM TIME = 9500
Project Manager - James T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget | 1850 | 1850 |  |  | 1850
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 1850 | 300 | 300 | 1550
IET DAS202210115300001 | 2022-05-06 | PM April 1-April 29, 2022 |  | 1850 | 100 | 400 | 1450
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 1850 | 100 | 500 | 1350
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 1850 | 250 | 750 | 1100
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 1850 | 1000 | 1750 | 100
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Credit |  | 1850 | -1000 | 750 | 1100
IET DAS202301115300001 | 2022-09-08 | PM-July 1-July 29, 2022-Reposted correct amount |  | 1850 | 1100 | 1850 | 0
|  |  |  | 1850 |  | 1850 | 0
|  |  |  | 1850 |  | 1850 | 0
|  |  |  | 1850 |  | 1850 | 0
|  |  |  | 1850 |  | 1850 | 0
|  |  |  | 1850 |  | 1850 | 0
|  | Totals: | 1850 |  | 1850 |  | 0
Note on D9: Huggins, Joni [DAS]: PM Time - 9286.00 - DPS Fleet & Supply Level 2 Floor Framing $Joni Trower, James Mar 15, 2022, 3:50 PM (15 hours ago) to me Finance - Please set up $1,000 in PM Time for project 9286.00 - DPS Fleet & Supply Level 2 Floor Framing. Thank you, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9286.00 - DPS DSM Fleet & Supply Level 2 Floor Framing - PM Time Increase $Joni Trower, James 12:22 PM (23 minutes ago) to me Finance - Please increase my PM Time for project 9286.00 by $850.00. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Re: DA22 9283.00 PM Time posting corrections for July Inbox Trower, James 2:17 PM (1 minute ago) to DAS, me Joni - It appears there is $212.65 remaining in funding for the project. Please increase the PM Time by $100. After the PM Time has been processed, this project can be closed and the remaining funds can be returned to the agency. Thanks, James Trower

## #9286.00 Boyd Jones
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
Program code 928600 |  |  | Major Program 4E12
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA22-9255 |  |  | RFP18121335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522076902 | 2022-03-17 | PO Procore | 4415 | 4415 |  |  | 4415
PRC 3352207PA6902 | 2022-05-12 | Inv. 9286.00-05 |  | 4415 | 2918.9 | 2918.9 | 1496.1
PRC 3352207PB6902 | 2022-06-16 | Inv. 9286.00-02 |  | 4415 | 886.7 | 3805.6 | 609.4
PRC 3352207PC6902 | 2022-07-11 | Inv. 9286.00-03 Final | -234.4 | 4180.6 | 375 | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  |  |  | 4180.6 |  | 4180.6 | 0
|  | Totals: | 4180.6 |  | 4180.6 |  | 0
|  | CM Services | 4165 |  | 4165 |  | 0
|  | Reimbursables | 15.6 |  | 15.6 |  | 0
|  | Totals: | 4180.6 |  | 4180.6 |  | 0

## #9286.00 Misc
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
Program code 928600 |  |  |  | Major Program 4E12
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9286.00 Shive Hattery
DPS Fleet & Supply Level 2 Floor Framing
Project # 9286.00
Program code 928600 |  |  | Major Program 4E12
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA22-9260 |  |  | RFP928600-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522115900 | 2022-04-25 | PO Procore | 5868 | 5868 |  |  | 5868
PRC 3352211PA5900 | 2022-06-03 | Inv. 2142202790-1 |  | 5868 | 4397.75 | 4397.75 | 1470.25
PRC 3352211PB5900 | 2022-06-08 | Inv. 2142202790-2 |  | 5868 | 1459 | 5856.75 | 11.25
PO 33522115900 | 2022-06-24 | Inv. 2142202790-2 was the final invoice | -11.25 | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  |  |  | 5856.75 |  | 5856.75 | 0
|  | Totals: | 5856.75 |  | 5856.75 |  | 0
|  | Design Evaulation Report | 5836 |  | 5836 |  | 0
|  | Reimbursables | 20.75 |  | 20.75 |  | 0
|  | Totals: | 5856.75 |  | 5856.75 |  | 0

## RECAP #9289.00
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
| Program code 928900 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 205218.89
C | McGough Construction |  | 20724.14 | 20724.14 | 0
C | PM TIME |  | 10998.4 | 10998.4 | 0
C | Misc. |  | 1098.11 | 1098.11 | 0
C | Genesis Architectural Design |  | 27900 | 27900 | 0
C | McGough Construction |  | 15720.24 | 15720.24 | 0
C | Woodruff Construction |  | 128778 | 128778 | 0
| Total Project Cost | 205218.89 | 205218.89 | 205218.89 | 0 | 0
Closed 07/12/2024

## #9289.00 Funds Rec'd
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25204142201 | 2022-04-14 | 215000 | 215000
|  |  | Return FY22 Funds to Agency | IET 33522216804 | 2022-08-04 | -211235.12 | -211235.12
|  |  | Received FY23 Funds From Agency | IET 25208082201 | 2022-08-09 | 211235.12 | 211235.12
|  |  | Return FY23 Funds to Agency | IET 33523228916 | 2023-08-14 | -171452.21 | -171452.21
|  |  | Received FY24 Funds From Agency | IET 25208172301 | 2023-08-18 | 171452.21 | 171452.21
|  |  | MOU Amendment #1 | IET 25210112305 | 2023-10-12 | 12000 | 12000
|  |  | Return Funds to Agency | IET 33524194900 | 2024-07-12 | -21781.11 | -21781.11
| Total Requested | 0 | Total Transferred |  |  | 205218.89 | 205218.89

## #9289.00 McGough Construction
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-McGough 11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522146800 | 2022-05-26 | PO Procore | 15786.64 | 15786.64 |  |  | 15786.64
PRC 3352214PA6800 | 2022-07-11 | Inv. 9289.001-1 |  | 15786.64 | 1769.88 | 1769.88 | 14016.76 | FY22
PO 33523146800 | 2022-08-10 | Rolled to FY23 | 0 | 15786.64 |  | 1769.88 | 14016.76
PRC 3352314PB6800 | 2022-08-11 | Inv. 9289.00.001-2 |  | 15786.64 | 1360 | 3129.88 | 12656.76
PRC 3352314PC6800 | 2022-09-09 | Inv. 9289.00.001-3 |  | 15786.64 | 330.27 | 3460.15 | 12326.49
PRC 3352314PD6800 | 2022-10-17 | Inv. 9289.00.001-4 |  | 15786.64 | 3285 | 6745.15 | 9041.49
PRC 3352314PE6800 | 2022-11-14 | Inv. 100877.004-5 PC |  | 15786.64 | 5134 | 11879.15 | 3907.49
PRC 3352314PF6800 | 2022-12-09 | Inv. 100877.004-6 |  | 15786.64 | 2842 | 14721.15 | 1065.49
PO 33523146800 | 2023-01-20 | CO 1 | 5069 | 20855.64 |  | 14721.15 | 6134.49
PRC 3352314PG6800 | 2023-02-13 | Inv. 100877.004PC7 |  | 20855.64 | 1160 | 15881.15 | 4974.49
PRC 3352314PH6800 | 2023-03-13 | Inv. 100877.004PC8 |  | 20855.64 | 360 | 16241.15 | 4614.49
PRC 3352314PI6800 | 2023-04-07 | Inv. 100877.004-09 |  | 20855.64 | 37.5 | 16278.65 | 4576.99
PRC 3352314PJ6800 | 2023-06-09 | Inv. 100877.004-10 |  | 20855.64 | 445 | 16723.65 | 4131.99 | FY23
PO 33524146800 | 2023-08-28 | Roll to FY24 | 0 | 20855.64 |  | 16723.65 | 4131.99
PRC 3352414PK6800 | 2023-08-29 | Inv. 100877.004-11 |  | 20855.64 | 2460 | 19183.65 | 1671.99
PRC 3352414PL6800 | 2023-09-14 | Inv. 100877.004-12 |  | 20855.64 | 862.99 | 20046.64 | 809
PRC 3352414PM6800 | 2023-10-11 | Inv. 100877.004-13-Final | -131.5 | 20724.14 | 677.5 | 20724.14 | -2.0464e-12
|  |  |  | 20724.14 |  | 20724.14 | -2.0464e-12
|  | Totals: | 20724.14 |  | 20724.14 |  | 0 | FINAL
|  | CM Services | 15484 |  | 15484 |  | 0
|  | Reimbursables | 302.64 |  | 302.64 |  | 0
|  | CO 1 | 4937.5 |  | 4937.5 |  | 0
|  | Total: | 20724.14 |  | 20724.14 |  | 0

## #9289.00 PM Time
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Jennifer K |  |  |  | eDAS 907P
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10998.4 | 10998.4 |  |  | 10998.4
IET DAS202210115300001 | 2022-05-06 |  | PM April 1-April 29, 2022 |  | 10998.4 | 275 | 275 | 10723.4
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 10998.4 | 175 | 450 | 10548.4
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 10998.4 | 625 | 1075 | 9923.4
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 10998.4 | 775 | 1850 | 9148.4
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Credit |  | 10998.4 | -775 | 1075 | 9923.4
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022-Reposted correct amount |  | 10998.4 | 852.5 | 1927.5 | 9070.9
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 10998.4 | 357.5 | 2285 | 8713.4
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 10998.4 | 302.5 | 2587.5 | 8410.9
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 10998.4 | 1045 | 3632.5 | 7365.9
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 10998.4 | 440 | 4072.5 | 6925.9
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 disbursement | 732 | 11730.4 | 732 | 4804.5 | 6925.9
CDE 33523353209 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -732 | 10998.4 | -732 | 4072.5 | 6925.9
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 330.04 | 11328.44 | 330.04 | 4402.54 | 6925.9
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -330.04 | 10998.4 | -330.04 | 4072.5 | 6925.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 188.82 | 11187.22 | 188.82 | 4261.32 | 6925.9
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -188.82 | 10998.4 | -188.82 | 4072.5 | 6925.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 821.46 | 11819.86 | 821.46 | 4893.96 | 6925.9
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -821.46 | 10998.4 | -821.46 | 4072.5 | 6925.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 440.28 | 11438.68 | 440.28 | 4512.78 | 6925.9
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -440.28 | 10998.4 | -440.28 | 4072.5 | 6925.9
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 10998.4 | 110 | 4182.5 | 6815.9
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 10998.4 | 20.8 | 4203.3 | 6795.1
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 10998.4 | 182.41 | 4385.71 | 6612.69
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September, October 2022 | 172.88 | 11171.28 | 172.88 | 4558.59 | 6612.69
CDE 33523075200 | 2023-03-07 | 2507 | Move PM time to 9997.23 MM23 | -172.88 | 10998.4 | -172.88 | 4385.71 | 6612.69
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 10998.4 | 37.48 | 4423.19 | 6575.21
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 10998.4 | 227.26 | 4650.45 | 6347.95
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 10998.4 | 10.13 | 4660.58 | 6337.82
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 10998.4 | 44.58 | 4705.16 | 6293.24
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 10998.4 | 15.45 | 4720.61 | 6277.79
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 10998.4 | 91.7 | 4812.31 | 6186.09
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 10998.4 | 24.12 | 4836.43 | 6161.97
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 10998.4 | 169.4 | 5005.83 | 5992.57
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 10998.4 | 5.3 | 5011.13 | 5987.27
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 10998.4 | 34.9 | 5046.03 | 5952.37
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 10998.4 | 64.56 | 5110.59 | 5887.81
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 10998.4 | 412.5 | 5523.09 | 5475.31
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 10998.4 | 126.82 | 5649.91 | 5348.49
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 10998.4 | 708.3 | 6358.21 | 4640.19
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 10998.4 | 45.08 | 6403.29 | 4595.11
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 10998.4 | 310.1 | 6713.39 | 4285.01
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 10998.4 | 32.7 | 6746.09 | 4252.31
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 10998.4 | 261.7 | 7007.79 | 3990.61
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10998.4 | 35.24 | 7043.03 | 3955.37
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10998.4 | 266.9 | 7309.93 | 3688.47
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 10998.4 | 12.8 | 7322.73 | 3675.67
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 10998.4 | 93.7 | 7416.43 | 3581.97
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10998.4 | 21.53 | 7437.96 | 3560.44
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10998.4 | 193.8 | 7631.76 | 3366.64
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10998.4 | 78.68 | 7710.44 | 3287.96
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10998.4 | 397.5 | 8107.94 | 2890.46
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10998.4 | 73.29 | 8181.23 | 2817.17
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10998.4 | 553.4 | 8734.63 | 2263.77
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 10998.4 | 127.45 | 8862.08 | 2136.32
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 10998.4 | 1130.7 | 9992.78 | 1005.62
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 10998.4 | 27.35 | 10020.13 | 978.27
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10998.4 | 226.2 | 10246.33 | 752.07
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10998.4 | 74.47 | 10320.8 | 677.6
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10998.4 | 677.6 | 10998.4 | 0
[5 empty] | 10998.4 |  | 10998.4 | 0
|  |  | Totals: | 10998.4 |  | 10998.4 |  | 0
Note on E9: Huggins, Joni [DAS]: DA22 9289.00 PM Budget $Joni Kleene, Jennifer Tue, Apr 19, 3:26 PM (15 hours ago) to me Please create a PM Time budget of $4,000.00 for DA22 project 9289.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time changes $Joni Kleene, Jennifer 1:03 PM (22 minutes ago) to me, Scott Please make the following changes: DA20 9159.00 Increase PM time by $330.00 DA22 9289.00 Increase PM time by $3,300.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Re: PM Time $Joni Kleene, Jennifer Mon, Dec 11, 5:17 PM (14 hours ago) to me Please increase the PM Time budget for 9289.00 by $3,740.00. Please increase the PM time budget for 9279.30 in DA24 by $56,100.00. Please increase the PM time budget for 9244 in MM22 by $3,740.00. Please increase the PM time budget for 9268.01 in R22M by $2,138.40. Regards, Jennifer Jennifer Kleene

## #9289.00 Misc
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523228901 | 2022-08-12 | 9500 | CNST | ATC V#(00002134218) | Inv. 2444613 | 915 | 915
PRC 33523012800 | 2023-01-12 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV026746 | 183.11 | 1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
1098.11
|  |  |  | Totals: |  | 1098.11

## #9289.00 Genesis Architectural
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  | Major Program 4B01
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA22-9260 |  |  | RFP/B#: 928900-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522159800 | 2022-06-08 | PO Procore | 27900 | 27900 |  |  | 27900
PRC 3352215PA9800 | 2022-07-13 | Inv. 2205-01 |  | 27900 | 920 | 920 | 26980 | FY22
PO 33523159800 | 2022-08-10 | Rolled to FY23 | 0 | 27900 |  | 920 | 26980
PRC 3352315PB9800 | 2022-09-28 | Inv. 2205-02 |  | 27900 | 16080 | 17000 | 10900
PRC 3352315PC9800 | 2022-12-20 | Inv. 2205-03 |  | 27900 | 3200 | 20200 | 7700
PRC 3352315PD9800 | 2023-02-23 | Inv. 2205-04 |  | 27900 | 480 | 20680 | 7220 | FY23
PO 33524159800 | 2023-08-28 | Rolled to FY24 | 0 | 27900 |  | 20680 | 7220
PRC 3352415PE9800 | 2023-12-05 | Inv. 2205-05 |  | 27900 | 475 | 21155 | 6745
PRC 3352415PF9800 | 2024-02-15 | Inv. 2205-06 |  | 27900 | 1633 | 22788 | 5112
PRC 3352415PG9800 | 2024-04-04 | Inv. 2205-07 |  | 27900 | 2627 | 25415 | 2485
PRC 3352415PH9800 | 2024-06-24 | Inv. 2205-08 Final |  | 27900 | 2485 | 27900 | 0
|  |  |  | 27900 |  | 27900 | 0
|  |  |  | 27900 |  | 27900 | 0
|  | Totals: | 27900 |  | 27900 |  | 0 | FINAL
|  | Design Development Documents | 9200 |  | 9200 |  | 0
|  | Construction Documents | 10400 |  | 10400 |  | 0
|  | Bidding Phase | 1200 |  | 1200 |  | 0
|  | Construction Phase | 7100 |  | 7100 |  | 0
|  | Total: | 27900 |  | 27900 |  | 0

## #9289.00 McGough Constructi (2)
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-McGough 11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524278901 | 2023-10-04 | PO Procore | 27887.62 | 27887.62 |  |  | 27887.62
PRC 3352427PA8901 | 2023-11-13 | Inv. 100877.004CA - 1 |  | 27887.62 | 1083.87 | 1083.87 | 26803.75
PRC 3352427PB8901 | 2023-12-12 | Inv. 100877.004CA - 2 |  | 27887.62 | 598.33 | 1682.2 | 26205.42
PRC 3352427PC8901 | 2023-01-12 | Inv. 100877.004CA - 3 |  | 27887.62 | 558.61 | 2240.81 | 25646.81
PRC 3352427PD8901 | 2024-02-06 | Inv. 100877.004CA - 4 |  | 27887.62 | 2004.84 | 4245.65 | 23641.97
PRC 3352427PE8901 | 2024-03-08 | Inv. 100877.004CA - 5 |  | 27887.62 | 2038.87 | 6284.52 | 21603.1
PRC 3352427PF8901 | 2024-04-04 | Inv. 100877.004CA - 6 |  | 27887.62 | 4684.6 | 10969.12 | 16918.5
PRC 3352427PG8901 | 2024-05-14 | Inv. 100877.004CA - 7 |  | 27887.62 | 3475.05 | 14444.17 | 13443.45
PRC 3352427PH8901 | 2024-06-12 | Inv. 100877.004CA - 8 |  | 27887.62 | 925.02 | 15369.19 | 12518.43
PRC 3352427PI8901 | 2024-06-28 | Inv. 100877.004CA - 9 FINAL | -12167.38 | 15720.24 | 351.05 | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  |  |  | 15720.24 |  | 15720.24 | 12167.38
|  | Totals: | 15720.24 |  | 15720.24 |  | 0 | FINAL
|  | CM Services | 15102.24 |  | 15102.24 |  | 0
|  | Reimbursables | 618 |  | 618 |  | 0
|  | Total: | 15720.24 |  | 15720.24 |  | 0

## #9289.00 Woodruff Construction
DOC FDCF Bldg H Gym Loft and Concessions
Project # 9289.00
Program code 928900 |  |  | Major Program 4B01
Woodruff Construction |  |  | Vendor: 00002142754
Acct. Codes-0506-335-DA22-9255 |  |  | RFQ928900-02
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524293800 | 2023-10-20 | PO Procore | 127675 | 127675 |  |  | 127675
PO 33524293800 | 2024-03-18 | CO #1 | 1840 | 129515 |  | 0 | 129515
PRC 3352429PA3800 | 2024-03-18 | Inv. Pay App #1 February 2024 |  | 129515 | 57415.62 | 57415.62 | 72099.38 | 3021.88
PRC 3352429PB3800 | 2024-04-18 | Inv. Pay App #2 March 2024 |  | 129515 | 31100.62 | 88516.24 | 40998.76 | 4658.76
PO 33524293800 | 2024-04-29 | CO #2 | -737 | 128778 |  | 88516.24 | 40261.76
PRC 3352429PC3800 | 2024-05-10 | Inv. Pay App #3 April 2024 |  | 128778 | 32611.6 | 121127.84 | 7650.16 | 6375.16
PRC 3352429PD3800 | 2024-06-13 | Inv. Pay App #4 May 2024 100% |  | 128778 | 1211.25 | 122339.09 | 6438.91 | 6438.91
PRC 3352429PE3800 | 2024-06-21 | Inv. Pay App #5 - Final - Retainage |  | 128778 | 6438.91 | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  |  |  | 128778 |  | 128778 | 0
|  | Totals: | 128778 |  | 128778 |  | 0 | FINAL

## RECAP #9295.00
DOC NCF BAS Panel Upgrade
Project # 9295.00
| Program code 929500 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 190689.63
C | Samuels Group |  | 13429.78 | 13429.78 | 0
C | PM TIME |  | 19766.45 | 19766.45 | 0
C | Misc. |  | 27414.56 | 27414.56 | 0
C | Siemens Industry |  | 119935.64 | 119935.64 | 0
C | Samuels Group #141 CA |  | 10143.2 | 10143.2 | 0
| Total Project Cost | 190689.63 | 190689.63 | 190689.63 | 0 | 0
Closed 08/13/2024

## #9295.00 Funds Rec'd
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA22-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25563A23001 | 2022-08-09 | 208954 | 208954
|  |  | Funds transferred without program code | CDR 33523222900 | 2022-08-10 | 0 | 0
|  |  | Return FY23 Funds to Agency | IET 33523228919 | 2023-08-14 | -142510.03 | -142510.03
|  |  | Received FY24 Funds from Agency | IET 25563A24001 | 2023-09-26 | 142510.03 | 142510.03
|  |  | Funds recevied without program code | CDR 33524270900 | 2023-09-27 | 0 | 0
|  |  | Return Funds to Agency | IET 33524226901 | 2024-08-13 | -18264.37 | -18264.37
| Total Requested | 0 | Total Transferred |  |  | 190689.63 | 190689.63

## #9295.00 PM Time
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - Brad T. |  |  |  | eDAS 907W
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 19766.45 | 19766.45 |  |  | 19766.45
IET DAS202301115300001 | 2022-09-08 | 9500 | PM-August 1-August 31, 2022 |  | 19766.45 | 605 | 605 | 19161.45
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 19766.45 | 110 | 715 | 19051.45
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 19766.45 | 357.5 | 1072.5 | 18693.95
IET DAS202305115300001 | 2022-12-19 | 9500 | PM Time-November 1- Novemer 30, 2022 |  | 19766.45 | 467.5 | 1540 | 18226.45
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 623.9 | 20390.35 | 623.9 | 2163.9 | 18226.45
CDE 33523353210 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -623.9 | 19766.45 | -623.9 | 1540 | 18226.45
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sept 9997.23 disbursement | 99.29 | 19865.74 | 99.29 | 1639.29 | 18226.45
CDE 33523353211 | 2022-12-21 | 9500 | Move PM time to 9997.23 MM23 | -99.29 | 19766.45 | -99.29 | 1540 | 18226.45
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 404.73 | 20171.18 | 404.73 | 1944.73 | 18226.45
CDE 33523353207 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -404.73 | 19766.45 | -404.73 | 1540 | 18226.45
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 414.47 | 20180.92 | 414.47 | 1954.47 | 18226.45
CDE 33523353208 | 2022-12-22 | 9500 | Move PM time to 9997.23 MM23 | -414.47 | 19766.45 | -414.47 | 1540 | 18226.45
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 19766.45 | 440 | 1980 | 17786.45
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 19766.45 | 158.83 | 2138.83 | 17627.62
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 19766.45 | 1392.48 | 3531.31 | 16235.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 19766.45 | 120.34 | 3651.65 | 16114.8
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 19766.45 | 729.74 | 4381.39 | 15385.06
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 19766.45 | 185.1 | 4566.49 | 15199.96
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 19766.45 | 814.18 | 5380.67 | 14385.78
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 19766.45 | 132.69 | 5513.36 | 14253.09
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 19766.45 | 779 | 6292.36 | 13474.09
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 19766.45 | 102.62 | 6394.98 | 13371.47
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 19766.45 | 720.5 | 7115.48 | 12650.97
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 19766.45 | 109.87 | 7225.35 | 12541.1
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 19766.45 | 943.2 | 8168.55 | 11597.9
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 19766.45 | 98.79 | 8267.34 | 11499.11
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 19766.45 | 629.1 | 8896.44 | 10870.01
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 19766.45 | 158 | 9054.44 | 10712.01
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 19766.45 | 881 | 9935.44 | 9831.01
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 19766.45 | 134.97 | 10070.41 | 9696.04
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 19766.45 | 936.9 | 11007.31 | 8759.14
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 19766.45 | 122.34 | 11129.65 | 8636.8
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 19766.45 | 985.1 | 12114.75 | 7651.7
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 19766.45 | 159.43 | 12274.18 | 7492.27
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 19766.45 | 1202.5 | 13476.68 | 6289.77
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 19766.45 | 165.06 | 13641.74 | 6124.71
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 19766.45 | 1213.3 | 14855.04 | 4911.41
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 19766.45 | 57.64 | 14912.68 | 4853.77
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 19766.45 | 512.6 | 15425.28 | 4341.17
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 19766.45 | 151.92 | 15577.2 | 4189.25
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 19766.45 | 766 | 16343.2 | 3423.25
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 19766.45 | 79.14 | 16422.34 | 3344.11
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 19766.45 | 603.6 | 17025.94 | 2740.51
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 19766.45 | 62.75 | 17088.69 | 2677.76
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 19766.45 | 558.5 | 17647.19 | 2119.26
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 19766.45 | 104.4 | 17751.59 | 2014.86
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 19766.45 | 872.3 | 18623.89 | 1142.56
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 19766.45 | 112.76 | 18736.65 | 1029.8
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 19766.45 | 1029.8 | 19766.45 | -6.1391e-12
[5 empty] | 19766.45 |  | 19766.45 | -6.1391e-12
[5 empty] | 19766.45 |  | 19766.45 | -6.1391e-12
[5 empty] | 19766.45 |  | 19766.45 | -6.1391e-12
|  |  | Totals: | 19766.45 |  | 19766.45 |  | 0
Note on E9: Huggins, Joni [DAS]: 9295.00 - DOC NCF BAS Panel Upgrade $Joni Tonyan, Brad 2:15 PM (50 minutes ago) to Jennifer, me, Scott, Brad Jennifer, I see that project 9295.00(DA22) has been funded by the MOU now and was wondering if you could set up the PM budget please. PM Time - $8,500 Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. PM Time / Budget Adjustments $Joni Tonyan, Brad 1:33 PM (32 minutes ago) to me, Scott, Brad Finance, Please make the following adjustments/set ups: DA22: 9295.00 - Increase PM Time by $5K 9239.01 - Increase PM Time by $5K

## #9295.00 Samuels Group
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523312900 | 2022-11-08 | PO Procore | 9234.52 | 9234.52 |  |  | 9234.52
PRC 3352331PA2900 | 2023-01-17 | Inv. 7449.01929500 |  | 9234.52 | 1596.17 | 1596.17 | 7638.35
PRC 3352331PB2900 | 2023-02-14 | Inv. 7449.02929500 |  | 9234.52 | 2614.36 | 4210.53 | 5023.99
PO 33523312900 | 2023-03-02 | CO #1 | 5228.72 | 14463.24 |  | 4210.53 | 10252.71
PRC 3352331PC2900 | 2023-03-09 | Inv. 7449.03929500 |  | 14463.24 | 2570.36 | 6780.89 | 7682.35
PRC 3352331PD2900 | 2023-05-08 | Inv. 7449.04929500 |  | 14463.24 | 2641.27 | 9422.16 | 5041.08
PRC 3352331PE2900 | 2023-06-09 | Inv. 7449.05929500 |  | 14463.24 | 4007.62 | 13429.78 | 1033.46 | FY23
PO 33524312900 | 2023-08-28 | Roll to FY24 | 0 | 14463.24 |  | 13429.78 | 1033.46
PO 33524312900 | 2023-09-06 | Close PO Per PM & Vendor | -1033.46 | 13429.78 |  | 13429.78 | 0
|  |  |  | 13429.78 |  | 13429.78 | 0
|  |  |  | 13429.78 |  | 13429.78 | 0
|  |  |  | 13429.78 |  | 13429.78 | 0
|  |  |  | 13429.78 |  | 13429.78 | 0
|  | Totals: | 13429.78 |  | 13429.78 |  | 0
|  | CM Services | 9058.52 |  | 9058.52 |  | 0
|  | Reimbursables | 132 |  | 132 |  | 0
|  | CO #1 | 4239.26 |  | 4239.26 |  | 0
|  | Total: | 13429.78 |  | 13429.78 |  | 0

## #9295.00 Misc
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 33523160808 | 2023-06-09 | 9500 | CNST | Processing CDE to move expense from project 9295.00 to NCF purchased material with P-card | Inv. MISC-1-Final | 18675.51 | 18675.51
CDE 33524285800 | 2023-10-12 | 9500 | CNST | Processing CDE to move expense from project 9295.00 to NCF purchased material with P-card | Inv. 5331075257/113398 | 1822.22 | 20497.73
GAX 33524208903 | 2024-07-26 | 9500 | CNST | Siemens Industry V#(00002089900) | Inv. 5331071738 | 186.2 | 20683.93
GAX 33524220905 | 2024-08-07 | 9500 | CNST | Siemens Industry V#(00002089900) | Inv. 5331504500R | 6730.63 | 27414.56
27414.56
27414.56
27414.56
27414.56
27414.56
27414.56
27414.56
27414.56
|  |  |  | Totals: |  | 27414.56

## #9295.00 Siemens Industry
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  | Major Program 4B01
Siemens Industry |  |  | Vendor: 00002089900
Acct. Codes-0506-335-DA22-9255 |  |  | MA 005 20358
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523334900 | 2022-11-30 | PO Procore | 101076.6 | 101076.6 |  |  | 101076.6
PO 33523334900 | 2023-01-24 | CO #1 | 429.58 | 101506.18 |  | 0 | 101506.18
PO 33523334900 | 2023-03-22 | CO #2 | 6671.63 | 108177.81 |  | 0 | 108177.81
PRC 3352333PA4900 | 2023-07-17 | Inv. 5330982750 |  | 108177.81 | 26170.13 | 26170.13 | 82007.68 | 1377.38 | FY23
PO 33524334900 | 2023-08-28 | Roll to FY24 | 0 | 108177.81 |  | 26170.13 | 82007.68
PO 33524334900 | 2023-11-16 | CO #3 | 4413.36 | 112591.17 |  | 26170.13 | 86421.04
PO 33524334900 | 2023-12-21 | CO #4 | 4100 | 116691.17 |  | 26170.13 | 90521.04
PO 33524334900 | 2024-01-03 | CO #5 | 1215.91 | 117907.08 |  | 26170.13 | 91736.95
PO 33524334900 | 2024-02-21 | CO #6 | 2028.56 | 119935.64 |  | 26170.13 | 93765.51
PRC 3352433PB4900 | 2024-04-09 | Inv. 5331121038 |  | 119935.64 | 66321.9 | 92492.03 | 27443.61 | 4868.01
PRC 3352433PC4900 | 2024-06-11 | Inv. 5331354874 |  | 119935.64 | 21446.81 | 113938.84 | 5996.8 | 5996.8
PRC 3352433PD4900 | 2024-06-17 | Inv. 5331288841 Retainage |  | 119935.64 | 5996.8 | 119935.64 | 0
|  |  |  | 119935.64 |  | 119935.64 | 0
|  | Totals: | 119935.64 |  | 119935.64 |  | 0 | FINAL

## #9295.00 Samuels Group #141 CA
DOC NCF BAS Panel Upgrade
Project # 9295.00
Program code 929500 |  |  | Major Program 4B01
Samuels Group #141 CA |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523178801 | 2023-06-27 | PO Procore | 7870.32 | 7870.32 |  |  | 7870.32 | FY23
PO 33524178801 | 2023-08-28 | Roll to FY24 | 0 | 7870.32 |  | 0 | 7870.32
PRC 3352417PA8801 | 2023-09-27 | Inv. 7520.50 CA |  | 7870.32 | 3869.72 | 3869.72 | 4000.6
PRC 3352417PB8801 | 2023-10-11 | Inv. 7520.51 CA |  | 7870.32 | 3529.44 | 7399.16 | 471.16
PO 33524178801 | 2023-11-09 | CO #1 | 2501.48 | 10371.8 |  | 7399.16 | 2972.64
PRC 3352417PC8801 | 2023-12-12 | Inv. 7520.52 CA |  | 10371.8 | 1975.47 | 9374.63 | 997.17
PRC 3352417PD8801 | 2024-02-08 | Inv. 7520.53CA |  | 10371.8 | 422.18 | 9796.81 | 574.99
PRC 3352417PE8801 | 2024-07-08 | Inv. 7520.54 CA FINAL | -228.6 | 10143.2 | 346.39 | 10143.2 | 0
|  |  |  | 10143.2 |  | 10143.2 | 0
|  |  |  | 10143.2 |  | 10143.2 | 0
|  |  |  | 10143.2 |  | 10143.2 | 0
|  |  |  | 10143.2 |  | 10143.2 | 0
|  |  |  | 10143.2 |  | 10143.2 | 0
|  | Totals: | 10143.2 |  | 10143.2 |  | 0 | FINAL
|  | CM Services | 7620.32 |  | 7620.32 |  | 0
|  | Reimbursables | 44 |  | 44 |  | 0
|  | Fee | 0 |  |  |  | 0
|  | CO #1 | 2478.88 |  | 2478.88 |  | 0
|  | Total: | 10143.2 |  | 10143.2 |  | 0

## #9268.02 Funds Rec'd Error
DAS CC Tunnel Drain Line Repair
Project # 9268.02
Program code 926802 |  |  | Major Program 4E17
Funds Rec'd
Acct Code: 0506-335-DA23-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Received FY24 funds from agency | IET 00524PROJ926802 | 2023-08-24 | 13633.34 | 13633.34
|  |  | Move Revenue from DA22 to DA23 | CDR 33524237801 | 2023-08-25 | -13633.34 | -13633.34
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #xxxx.xx Funds Rec'd incorrect
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-DA22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU Funds Recv'd Incorrect Unit | IET DASPROJECTS 092524 | 2024-09-26 | 617486.63 | 617486.63
|  |  | Move funds to correct unit - DA22 to DA24 | CDR 33525271900 | 2024-09-27 | -617486.63 | -617486.63
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-DA22
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #xxxx.xx Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-DA22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #xxxx.xx Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Labor | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #xxxx.xx PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents | .
Acct. Codes-0506-335-DA22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #xxxx.xx Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Acct. Codes-0506-335-DA22-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - xxxxxxxxxxxxxxxxxxx
Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0