## Language
Approp 838, until expended - IA Code 8A.330.2

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 363337.39
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 363337.39
|  | Less: Total Assigned |  | 121896.89
|  | Total Unassigned / Unallocated |  | 241440.5
R22M (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| XXXX.XX | Overhead |  | 0 | 62871.17 | 62871.17 | 62871.17 | 62871.17 | 0 | 0
| 9159.00 | DAS CC Redundant Power Distribution | Jennifer K | 0 | 7507 | 7507 | 7507 | 7507 | 0 | 0
C | 9268.01 | DAS CC Tunnel System Infiltration Mitigation | Jennifer K. | 0 | 50159.42 | 50159.42 | 50159.42 | 50159.42 | 0 | 0
| 9277.00 | CC Main Switchgear Master Control Replacement | Jennifer K | 0 | 1359.3 | 1359.3 | 1359.3 | 0 | 1359.3 | 0
|  | R22M (MOU) Totals |  | 0 | 121896.89 | 121896.89 | 121896.89 | 120537.59 | 1359.3 | 0
242799.8

## Funds Rec'd
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | #REF!
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| 335FY22DAS | 363337.39 |  |  | 2021-09-22 | 363337.39 | 363337.39
|  |  | Funds Allocated to 9268.01 |  | 2023-01-13 | -60000 | -60000
|  |  | Funds Allocated to 9159.00 |  | 2023-06-20 | -7507 | -7507
|  |  | Funds allocated to Overhead |  | 2023-06-14 | -5331.5 | -5331.5
|  |  | Funds allocated to Overhead |  | 2023-06-14 | -31080.78 | -31080.78
|  |  | Funds Allocated from R21M to R22M |  | 2023-06-23 | -23450.56 | -23450.56
|  |  | Funds Returned from 9268.01 |  | 2024-04-12 | 9840.58 | 9840.58
| Total Requested | 363337.39 | Total Transferred |  |  | 245808.13 | 245808.13

## RECAP #Overhead
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-R22M
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 62871.17
VendorA |  | 62871.17 | 62871.17 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 62871.17 | 62871.17 | 62871.17 | 0 | 0

## #Overhead Funds Rec'd
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds allocated from R22M |  | 2023-06-14 | 5331.5 | 5331.5
|  |  | Funds allocated from R22M |  | 2023-06-14 | 31080.78 | 31080.78
|  |  | Funds allocated from R22M |  | 2023-06-23 | 23450.56 | 23450.56
|  |  | Funds allocated from R22M |  | 2023-07-11 | 16466.13 | 16466.13
|  |  | Funds allocated from R22M |  | 2023-08-24 | -3182 | -3182
|  |  | Funds allocated from R22M |  | 2023-07-11 | -23450.56 | -23450.56
|  |  | Funds allocated from R22M |  | 2023-08-21 | -31080.78 | -31080.78
|  |  | Funds allocated from R22M |  | 2023-08-21 | -5331.5 | -5331.5
|  |  | Funds allocated from R22M |  | 2024-07-24 | 48887.04 | 48887.04
|  |  | Funds allocated from R22M |  | 2024-08-09 | 500 | 500
|  |  | Funds allocated from R22M |  | 2024-08-16 | 200 | 200
| Total Requested | 0 | Total Transferred |  |  | 62871.17 | 62871.17

## #Overhead
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget | 62871.17 | 62871.17 |  |  | 62871.17
CDE 005235330TOR22MH | 2023-06-14 | CDE to move expense from 5330 to R22M FY23 |  | 62871.17 | 5331.5 | 5331.5 | 57539.67
CDE 005235330TOR22MG | 2023-06-14 | CDE to move expense from 5330 to R22M FY23 |  | 62871.17 | 31080.78 | 36412.28 | 26458.89
CDE 00523R21MTOR22M | 2023-06-14 | CDE to move expense from R21M to R22M FY23 |  | 62871.17 | 23450.56 | 59862.84 | 3008.33
CDE 00523THILTOR22M | 2023-07-11 | CDE to move expense from THIL to R22M FY23 |  | 62871.17 | 16466.13 | 76328.97 | -13457.8
CDE 00523R22MTO5330 | 2023-08-21 | CDE to move expense from 5330 to R22M FY23 |  | 62871.17 | -23450.56 | 52878.41 | 9992.76
CDE 00523R22MTO5330A | 2023-08-21 | CDE to move expense from 5330 to R22M FY23 |  | 62871.17 | -31080.78 | 21797.63 | 41073.54
CDE 00523R22MTO5330B | 2023-08-21 | CDE to move expense from 5330 to R22M FY23 |  | 62871.17 | -5331.5 | 16466.13 | 46405.04
CDE 00523R22MTOTHIL | 2023-08-24 | CDE to move expense from R22M to THIL FY23 |  | 62871.17 | -3182 | 13284.13 | 49587.04
CDE 00524GSERMFUNDS | 2024-07-24 | Move Geothermal Exp |  | 62871.17 | 48887.04 | 62171.17 | 700
CDE 00524THILRMFUNDS1 | 2024-08-09 | CDE to move expense from R22M to THIL FY24 |  | 62871.17 | 500 | 62671.17 | 200
CDE 00524THILRMFUNDS2 | 2024-08-16 | CDE to move expense from R22M to THIL FY24 |  | 62871.17 | 200 | 62871.17 | 7.276e-12
|  |  |  | 62871.17 |  | 62871.17 | 7.276e-12
|  | Totals | 62871.17 |  | 62871.17 |  | 0

## RECAP #9159.00
DAS CC Redundant Power Distribution
Project # 9159.00
| Program code 915900 |  |  | Major Program 4E06
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 7507
| Baker Group |  | 7507 | 7507 | 0
C | PM TIME |  | 0 | 0 | 0
| Misc. |  | 0 | 0 | 0
| Total Project Cost | 7507 | 7507 | 7507 | 0 | 0

## #9159.00 Funds Rec'd
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  | Major Program 4E06
Funds Rec'd
Acct Code: 0506-335-R22M-0285
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Allocated from R21M |  | 2023-06-20 | 7507 | 7507
0
| Total Requested | 0 | Total Transferred |  |  | 7507 | 7507

## #9159.00 Baker Group
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  | Major Program 4E06
Baker Group |  |  | Vendor: 00002108328
Acct. Codes-0506-335-R22M-9255 |  |  | RFB915900-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
CDE 33523171900 | 2023-06-20 | Moving Expenses From DA20 | 7507 | 7507 | 7507 | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  | Totals | 7507 |  | 7507 |  | 0

## #9159.00 PM TIME
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  |  | Major Program 4E06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E26W
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9159.00 Misc
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  |  | Major Program 4E06
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9268.01
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
| Program code 926801 |  |  | Major Program 4E17
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 50159.42
C | DCI Group |  | 3440.17 | 3440.17 | 0
C | PM TIME |  | 4319.25 | 4319.25 | 0
C | Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 42400 | 42400 | 0
| Total Project Cost | 50159.42 | 50159.42 | 50159.42 | 0 | 0
Closed 04/12/24

## #9268.01 Funds Rec'd
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
Funds Rec'd
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Allocated from R22M |  | 2023-01-13 | 60000 | 60000
|  |  | Funds returned to R22M |  | 2024-04-12 | -9840.58 | -9840.58
| Total Requested | 0 | Total Transferred |  |  | 50159.42 | 50159.42

## #9268.01 DCI Group
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0506-335-R22M-9255 |  |  | RFP1821335228-DCI11012021
Project Manager Jennifer K. |  |  | Activity code:CMGR
Split with MM23 and DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523013801 | 2023-01-13 | PO Procore | 3470.85 | 3470.85 |  |  | 3470.85
PRC 3352301PA3801 | 2023-03-20 | Inv. 22-009.1 PC-01(Split with MM23) |  | 3470.85 | 323.2 | 323.2 | 3147.65
PRC 3352301PB3801 | 2023-04-25 | Inv. 22-009.1 PC-02(100% to MM23) |  | 3470.85 | 0 | 323.2 | 3147.65
PRC 3352301PC3801 | 2023-07-06 | Inv. 22-009.1 PC-03 (100% to MM23) |  | 3470.85 | 0 | 323.2 | 3147.65
PO 33523013801 | 2023-07-12 | CO #2 (100% to DA23) | 0 | 3470.85 |  | 323.2 | 3147.65
PRC 3352301PD3801 | 2023-07-28 | Inv. 22-009.1 PC 04 (Split between MM23 and DA23) |  | 3470.85 | 0 | 323.2 | 3147.65 | FY23
PO 33524013801 | 2023-08-25 | Roll to FY24 | 0 | 3470.85 |  | 323.2 | 3147.65
PRC 3352401PE3801 | 2023-11-13 | Inv. 22-009.1 PC-05 (Split between MM23 and R22M) |  | 3470.85 | 3116.97 | 3440.17 | 30.68
PRC 3352401PF3801 | 2023-11-16 | Inv. 22-009.1 PC-06 (100% to MM23) |  | 3470.85 | 0 | 3440.17 | 30.68
PRC 3352401PG3801 | 2023-12-21 | Inv. 22-009.1 PC 07 FINAL | -30.68 | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  | Totals | 3440.17 |  | 3440.17 |  | 0 | FINAL
|  | DA23 (Closed 07/28/23) | 2250.46 |  | 2250.46 |  | 0
|  | MM23(Closed 12/21) | 38550.17 |  | 38550.17 |  | 0
|  | Total Contract: | 44240.8 |  | 44240.8 |  | 0

## #9268.01 PM TIME
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  |  | Major Program 4E17
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E25E
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 4319.25 | 4319.25 |  |  | 4319.25
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 4319.25 | 53.98 | 53.98 | 4265.27
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 4319.25 | 473.29 | 527.27 | 3791.98
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 4319.25 | 125.65 | 652.92 | 3666.33
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 4319.25 | 762.01 | 1414.93 | 2904.32
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 4319.25 | 10.13 | 1425.06 | 2894.19
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 4319.25 | 44.58 | 1469.64 | 2849.61
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 4319.25 | 7.83 | 1477.47 | 2841.78
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 4319.25 | 57.2 | 1534.67 | 2784.58
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 4319.25 | 31.33 | 1566 | 2753.25
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 4319.25 | 279.8 | 1845.8 | 2473.45
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 4319.25 | 58.71 | 1904.51 | 2414.74
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 4319.25 | 372.1 | 2276.61 | 2042.64
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 4319.25 | 75.74 | 2352.35 | 1966.9
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 4319.25 | 424.1 | 2776.45 | 1542.8
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 4319.25 | 48.72 | 2825.17 | 1494.08
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 4319.25 | 391.2 | 3216.37 | 1102.88
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 4319.25 | 91.92 | 3308.29 | 1010.96
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 4319.25 | 695.4 | 4003.69 | 315.56
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 4319.25 | 12.8 | 4016.49 | 302.76
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 4319.25 | 93.7 | 4110.19 | 209.06
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 4319.25 | 24.06 | 4134.25 | 185
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 4319.25 | 185 | 4319.25 | 0
[5 empty] | 4319.25 |  | 4319.25 | 0
[5 empty] | 4319.25 |  | 4319.25 | 0
|  |  | Totals | 4319.25 |  | 4319.25 |  | 0
Note on E9: Huggins, Joni [DAS]: 9268.01 PM Time $Joni Herman, Josh Jan 18, 2023, 10:05 AM (23 hours ago) to me Please set PM Time for the following in 9268.01 MM23 $11,000 R22M $2,750 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Kleene, Jennifer 3:24 PM (10 minutes ago) to me Please make the following changes: 9326.00 MM21 - increase by $2,100.00 9054.03 MM22 - increase by $5,000.00 9262.00 MM22 - increase by $8,000.00 9290.00 MM22 - increase by $3,200.00 9268.01 R22M - increase by $1,000.00 Regards, Jennifer Re: PM Time $Joni Kleene, Jennifer Dec 11, 2023, 5:17 PM (14 hours ago) to me Please increase the PM Time budget for 9289.00 by $3,740.00. Please increase the PM time budget for 9279.30 in DA24 by $56,100.00. Please increase the PM time budget for 9244 in MM22 by $3,740.00. Please increase the PM time budget for 9268.01 in R22M by $2,138.40. Regards, Jennifer

## #9268.01 Misc
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  |  | Major Program 4E17
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9268.01 Shive Hattery
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-R22M-9260 |  |  | RFP9268.00-02
Project Manager Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523045903 | 2023-02-14 | PO Procore | 42400 | 42400 |  |  | 42400
PO 33523045903 | 2023-07-06 | CO #1 (100% to DA23) | 0 | 42400 |  | 0 | 42400
PRC 3352304PA5903 | 2023-07-17 | Inv. 2142201940-101 (Split Between MM23, DA23, and R22M) |  | 42400 | 30155 | 30155 | 12245 | FY23
PO 33524045903 | 2023-08-25 | Roll to FY24 | 0 | 42400 |  | 30155 | 12245
PO 33524045903 | 2023-08-29 | CO #2 (No Cost) | 0 | 42400 |  | 30155 | 12245
PRC 3352404PB5903 | 2023-08-30 | Inv. 2142201940-102 (Split Between MM23 and R22M) |  | 42400 | 11795 | 41950 | 450
PRC 3352404PC5903 | 2023-10-12 | Inv. 2142201940-103 (Split Between MM23, DA23, and R22M) |  | 42400 | 360 | 42310 | 90
PRC 3352404PD5903 | 2023-12-13 | Inv. 2142201940-104 (Split Between MM23 and DA23) |  | 42400 | 0 | 42310 | 90
PO 33524045903 | 2024-02-09 | CO #3 (100% to MM23) | 0 | 42400 |  | 42310 | 90
PRC 3352404PE5903 | 2024-03-18 | Inv. 2142201940-105 (Split Between MM23 and R22M) |  | 42400 | 90 | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  | Totals | 42400 |  | 42400 |  | 0
|  | Investigation/Design Development | 14100 |  | 14100 |  | 0
|  | 50% Report | 16900 |  | 16900 |  | 0
|  | 95% Report | 9600 |  | 9600 |  | 0
|  | 100% Report | 1800 |  | 1800 |  | 0
|  | Totals: | 42400 |  | 42400 |  | 0
|  | 9268.02 DA23 | 6860 |  | 6860 |  | 0
|  | 9268.01 MM23 | 0 |  | 10179.88 |  | 16062.12
|  | Total Contract: | 49260 |  | 59439.88 |  | 16062.12

## RECAP #9277.00
CC Main Switchgear Master Control Replacement
Project # 9277.00
| Program code 927700 |  |  | Major Program 4F08
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1359.3
| Cummins Inc. |  | 1359.3 | 0 | 1359.3
C | PM TIME |  | 0 | 0 | 0
| Misc. |  | 0 | 0 | 0
| Total Project Cost | 1359.3 | 1359.3 | 0 | 1359.3 | 0
Note on C8: Huggins, Joni [DAS]: Re: Draft MOU for 9277.00, CC Main Switchgear Master Control Replacement and New Project Set-up FY22 Jusic, Mirela Attachments Jul 21, 2022, 7:53 AM (6 days ago) to me, Jennifer, Scott, Jennifer Attached, thanks On Thu, Jul 21, 2022 at 7:31 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Attached is the completed MOU, ready for signatures On Wed, Jul 20, 2022 at 5:09 PM Kleene, Jennifer <jennifer.kleene@iowa.gov> wrote: Please review the draft MOU and let me know if you have any questions. Please also set-up a third 9277.00 project - this will be in R21M for $28,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9277.00 Funds Rec'd
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Funds Rec'd
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
[6 empty] | 1359.3 | 1359.3
0
| Total Requested | 0 | Total Transferred |  |  | 1359.3 | 1359.3

## #9277.00 Cummins
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Cummins Inc. |  |  | Vendor: 00003104792
Acct. Codes-0506-335-R22M-9255 |  |  | MA21233A
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split with MM22 & DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524234800 | 2024-07-24 | CO update to Transfer R21M to R22M | 1359.3 | 1359.3 |  |  | 1359.3 | 1359.3 | FY24
PO 33525234800 | 2024-08-26 | Roll to FY25 |  | 1359.3 |  | 0 | 1359.3
PO 33525234800 | 2024-08-30 | CO #2(No Cost CO-100% to MM22) | 0 | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  | Totals | 1359.3 |  | 0 |  | 1359.3
|  | MM22 | 383990 |  | 265442.35 |  | 118547.65
|  | DA23 | 108744 |  | 103306.8 |  | 5437.2
|  | R21M (Closed 07/24/24) | 25826.7 |  | 25826.7 |  | 0
|  | Total Contract: | 519920 |  | 394575.85 |  | 125344.15

## #9277.00 PM TIME
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9277.00 Misc
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-R22M
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #xxxx.xx Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #xxxx.xx Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #xxxx.xx PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #xxxx.xx Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0