## Language
Approp 838, until expended - IA Code 8A.330.2

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 363337.39
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 363337.39
|  | Less: Total Assigned |  | 224274.61
|  | Total Unassigned / Unallocated |  | 139062.78
R22M (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| XXXX.XX | Overhead |  | 0 | 165248.89 | 165248.89 | 165248.89 | 165248.89 | 0 | 0
C | 9159.00 | DAS CC Redundant Power Distribution | Jennifer K | 0 | 7507 | 7507 | 7507 | 7507 | 0 | 0
C | 9268.01 | DAS CC Tunnel System Infiltration Mitigation | Jennifer K. | 0 | 50159.42 | 50159.42 | 50159.42 | 50159.42 | 0 | 0
| 9277.00 | CC Main Switchgear Master Control Replacement | Jennifer K | 0 | 1359.3 | 1359.3 | 1359.3 | 0 | 1359.3 | 0
|  | R22M (MOU) Totals |  | 0 | 224274.61 | 224274.61 | 224274.61 | 222915.31 | 1359.3 | 0
140422.08
Note on F15: Jurgenson, John [DAS]: Kleene, Jennifer 8:33 AM (1 hour ago) to me, Matthew Sorry, I guess I should have looked at the financials first (I didn't see any project #s in the email)! R22M 9159.00 can close, but I'd prefer 9277.00 stay open as we still need some work to be done and closeout items before we should pay that retainage. That work was delayed due to MidAmerican and we're hoping it will be done this fall. Regards, Jennifer

## Funds Rec'd
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | #REF!
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| 335FY22DAS | 363337.39 |  |  | 2021-09-22 | 363337.39 | 363337.39
|  |  | Funds Allocated to 9268.01 |  | 2023-01-13 | -60000 | -60000
|  |  | Funds Allocated to 9159.00 |  | 2023-06-20 | -7507 | -7507
|  |  | Funds allocated to Overhead |  | 2023-06-14 | -5331.5 | -5331.5
|  |  | Funds allocated to Overhead |  | 2023-06-14 | -31080.78 | -31080.78
|  |  | Funds Allocated from R21M to R22M |  | 2023-06-23 | -23450.56 | -23450.56
|  |  | Funds Returned from 9268.01 |  | 2024-04-12 | 9840.58 | 9840.58
| Total Requested | 363337.39 | Total Transferred |  |  | 245808.13 | 245808.13

## RECAP #Overhead
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-R22M
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 165248.89
VendorA |  | 165248.89 | 165248.89 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 165248.89 | 165248.89 | 165248.89 | 0 | 0

## #Overhead Funds Rec'd
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds allocated from R22M |  | 2023-06-14 | 5331.5 | 5331.5
|  |  | Funds allocated from R22M |  | 2023-06-14 | 31080.78 | 31080.78
|  |  | Funds allocated from R22M |  | 2023-06-23 | 23450.56 | 23450.56
|  |  | Funds allocated from R22M |  | 2023-07-11 | 16466.13 | 16466.13
|  |  | Funds allocated from R22M |  | 2023-08-24 | -3182 | -3182
|  |  | Funds allocated from R22M |  | 2023-07-11 | -23450.56 | -23450.56
|  |  | Funds allocated from R22M |  | 2023-08-21 | -31080.78 | -31080.78
|  |  | Funds allocated from R22M |  | 2023-08-21 | -5331.5 | -5331.5
|  |  | Funds allocated from R22M |  | 2024-07-24 | 48887.04 | 48887.04
|  |  | Funds allocated from R22M |  | 2024-08-09 | 500 | 500
|  |  | Funds allocated from R22M |  | 2024-08-16 | 200 | 200
|  |  | Funds allocated from R22M |  | 2025-06-23 | 102308.4 | 102308.4
|  |  | Funds allocated from R22M |  | 2025-07-03 | 69.32 | 69.32
| Total Requested | 0 | Total Transferred |  |  | 165248.89 | 165248.89

## #Overhead
Overhead
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget | 165248.89 | 165248.89 |  |  | 165248.89
CDE 005235330TOR22MH | 2023-06-14 | CDE to move expense from 5330 to R22M FY23 |  | 165248.89 | 5331.5 | 5331.5 | 159917.39
CDE 005235330TOR22MG | 2023-06-14 | CDE to move expense from 5330 to R22M FY23 |  | 165248.89 | 31080.78 | 36412.28 | 128836.61
CDE 00523R21MTOR22M | 2023-06-14 | CDE to move expense from R21M to R22M FY23 |  | 165248.89 | 23450.56 | 59862.84 | 105386.05
CDE 00523THILTOR22M | 2023-07-11 | CDE to move expense from THIL to R22M FY23 |  | 165248.89 | 16466.13 | 76328.97 | 88919.92
CDE 00523R22MTO5330 | 2023-08-21 | CDE to move expense to 5330 From R22M FY23 |  | 165248.89 | -23450.56 | 52878.41 | 112370.48
CDE 00523R22MTO5330A | 2023-08-21 | CDE to move expense to 5330 From R22M FY23 |  | 165248.89 | -31080.78 | 21797.63 | 143451.26
CDE 00523R22MTO5330B | 2023-08-21 | CDE to move expense to 5330 From R22M FY23 |  | 165248.89 | -5331.5 | 16466.13 | 148782.76
CDE 00523R22MTOTHIL | 2023-08-24 | CDE to move expense to R22M from THIL FY23 |  | 165248.89 | -3182 | 13284.13 | 151964.76
CDE 00524GSERMFUNDS | 2024-07-24 | Move Geothermal Exp |  | 165248.89 | 48887.04 | 62171.17 | 103077.72
CDE 00524THILRMFUNDS1 | 2024-08-09 | CDE to move expense from R22M to THIL FY24 |  | 165248.89 | 500 | 62671.17 | 102577.72
CDE 00524THILRMFUNDS2 | 2024-08-16 | CDE to move expense from R22M to THIL FY24 |  | 165248.89 | 200 | 62871.17 | 102377.72
CDE 00525GSERMFUNDS | 2025-06-24 | CDE to move expense from R22M to Ceremonial GSE FY25 |  | 165248.89 | 102308.4 | 165179.57 | 69.32
CDE 335525184912 | 2025-07-03 | CDE to move expense from DA20 to R22M for Ceremonial |  |  | 69.32 |  | 6.9917e-12
|  | Totals | 165248.89 |  | 165248.89 |  | 0

## RECAP #9159.00
DAS CC Redundant Power Distribution
Project # 9159.00
| Program code 915900 |  |  | Major Program 4E06
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 7507
C | Baker Group |  | 7507 | 7507 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 7507 | 7507 | 7507 | 0 | 0
Closed 06/24/25

## #9159.00 Funds Rec'd
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  | Major Program 4E06
Funds Rec'd
Acct Code: 0506-335-R22M-0285
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Allocated from R21M |  | 2023-06-20 | 7507 | 7507
0
| Total Requested | 0 | Total Transferred |  |  | 7507 | 7507

## #9159.00 Baker Group
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  | Major Program 4E06
Baker Group |  |  | Vendor: 00002108328
Acct. Codes-0506-335-R22M-9255 |  |  | RFB915900-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
CDE 33523171900 | 2023-06-20 | Moving Expenses From DA20 | 7507 | 7507 | 7507 | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  |  |  | 7507 |  | 7507 | 0
|  | Totals | 7507 |  | 7507 |  | 0

## #9159.00 PM TIME
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  |  | Major Program 4E06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E26W
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9159.00 Misc
DAS CC Redundant Power Distribution
Project # 9159.00
Program code 915900 |  |  |  | Major Program 4E06
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9268.01
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
| Program code 926801 |  |  | Major Program 4E17
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 50159.42
C | DCI Group |  | 3440.17 | 3440.17 | 0
C | PM TIME |  | 4319.25 | 4319.25 | 0
C | Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 42400 | 42400 | 0
| Total Project Cost | 50159.42 | 50159.42 | 50159.42 | 0 | 0
Closed 04/12/24

## #9268.01 Funds Rec'd
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
Funds Rec'd
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Allocated from R22M |  | 2023-01-13 | 60000 | 60000
|  |  | Funds returned to R22M |  | 2024-04-12 | -9840.58 | -9840.58
| Total Requested | 0 | Total Transferred |  |  | 50159.42 | 50159.42

## #9268.01 DCI Group
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0506-335-R22M-9255 |  |  | RFP1821335228-DCI11012021
Project Manager Jennifer K. |  |  | Activity code:CMGR
Split with MM23 and DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523013801 | 2023-01-13 | PO Procore | 3470.85 | 3470.85 |  |  | 3470.85
PRC 3352301PA3801 | 2023-03-20 | Inv. 22-009.1 PC-01(Split with MM23) |  | 3470.85 | 323.2 | 323.2 | 3147.65
PRC 3352301PB3801 | 2023-04-25 | Inv. 22-009.1 PC-02(100% to MM23) |  | 3470.85 | 0 | 323.2 | 3147.65
PRC 3352301PC3801 | 2023-07-06 | Inv. 22-009.1 PC-03 (100% to MM23) |  | 3470.85 | 0 | 323.2 | 3147.65
PO 33523013801 | 2023-07-12 | CO #2 (100% to DA23) | 0 | 3470.85 |  | 323.2 | 3147.65
PRC 3352301PD3801 | 2023-07-28 | Inv. 22-009.1 PC 04 (Split between MM23 and DA23) |  | 3470.85 | 0 | 323.2 | 3147.65 | FY23
PO 33524013801 | 2023-08-25 | Roll to FY24 | 0 | 3470.85 |  | 323.2 | 3147.65
PRC 3352401PE3801 | 2023-11-13 | Inv. 22-009.1 PC-05 (Split between MM23 and R22M) |  | 3470.85 | 3116.97 | 3440.17 | 30.68
PRC 3352401PF3801 | 2023-11-16 | Inv. 22-009.1 PC-06 (100% to MM23) |  | 3470.85 | 0 | 3440.17 | 30.68
PRC 3352401PG3801 | 2023-12-21 | Inv. 22-009.1 PC 07 FINAL | -30.68 | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  |  |  | 3440.17 |  | 3440.17 | 2.9132e-13
|  | Totals | 3440.17 |  | 3440.17 |  | 0 | FINAL
|  | DA23 (Closed 07/28/23) | 2250.46 |  | 2250.46 |  | 0
|  | MM23(Closed 12/21) | 38550.17 |  | 38550.17 |  | 0
|  | Total Contract: | 44240.8 |  | 44240.8 |  | 0

## #9268.01 PM TIME
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  |  | Major Program 4E17
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E25E
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 4319.25 | 4319.25 |  |  | 4319.25
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 4319.25 | 53.98 | 53.98 | 4265.27
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 4319.25 | 473.29 | 527.27 | 3791.98
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 4319.25 | 125.65 | 652.92 | 3666.33
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 4319.25 | 762.01 | 1414.93 | 2904.32
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 4319.25 | 10.13 | 1425.06 | 2894.19
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 4319.25 | 44.58 | 1469.64 | 2849.61
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 4319.25 | 7.83 | 1477.47 | 2841.78
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 4319.25 | 57.2 | 1534.67 | 2784.58
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 4319.25 | 31.33 | 1566 | 2753.25
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 4319.25 | 279.8 | 1845.8 | 2473.45
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 4319.25 | 58.71 | 1904.51 | 2414.74
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 4319.25 | 372.1 | 2276.61 | 2042.64
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 4319.25 | 75.74 | 2352.35 | 1966.9
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 4319.25 | 424.1 | 2776.45 | 1542.8
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 4319.25 | 48.72 | 2825.17 | 1494.08
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 4319.25 | 391.2 | 3216.37 | 1102.88
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 4319.25 | 91.92 | 3308.29 | 1010.96
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 4319.25 | 695.4 | 4003.69 | 315.56
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 4319.25 | 12.8 | 4016.49 | 302.76
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 4319.25 | 93.7 | 4110.19 | 209.06
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 4319.25 | 24.06 | 4134.25 | 185
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 4319.25 | 185 | 4319.25 | 0
[5 empty] | 4319.25 |  | 4319.25 | 0
[5 empty] | 4319.25 |  | 4319.25 | 0
|  |  | Totals | 4319.25 |  | 4319.25 |  | 0
Note on E9: Huggins, Joni [DAS]: 9268.01 PM Time $Joni Herman, Josh Jan 18, 2023, 10:05 AM (23 hours ago) to me Please set PM Time for the following in 9268.01 MM23 $11,000 R22M $2,750 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Kleene, Jennifer 3:24 PM (10 minutes ago) to me Please make the following changes: 9326.00 MM21 - increase by $2,100.00 9054.03 MM22 - increase by $5,000.00 9262.00 MM22 - increase by $8,000.00 9290.00 MM22 - increase by $3,200.00 9268.01 R22M - increase by $1,000.00 Regards, Jennifer Re: PM Time $Joni Kleene, Jennifer Dec 11, 2023, 5:17 PM (14 hours ago) to me Please increase the PM Time budget for 9289.00 by $3,740.00. Please increase the PM time budget for 9279.30 in DA24 by $56,100.00. Please increase the PM time budget for 9244 in MM22 by $3,740.00. Please increase the PM time budget for 9268.01 in R22M by $2,138.40. Regards, Jennifer

## #9268.01 Misc
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  |  | Major Program 4E17
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9268.01 Shive Hattery
DAS CC Tunnel System Infiltration Mitigation
Project 9268.01
Program code 926801 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-R22M-9260 |  |  | RFP9268.00-02
Project Manager Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523045903 | 2023-02-14 | PO Procore | 42400 | 42400 |  |  | 42400
PO 33523045903 | 2023-07-06 | CO #1 (100% to DA23) | 0 | 42400 |  | 0 | 42400
PRC 3352304PA5903 | 2023-07-17 | Inv. 2142201940-101 (Split Between MM23, DA23, and R22M) |  | 42400 | 30155 | 30155 | 12245 | FY23
PO 33524045903 | 2023-08-25 | Roll to FY24 | 0 | 42400 |  | 30155 | 12245
PO 33524045903 | 2023-08-29 | CO #2 (No Cost) | 0 | 42400 |  | 30155 | 12245
PRC 3352404PB5903 | 2023-08-30 | Inv. 2142201940-102 (Split Between MM23 and R22M) |  | 42400 | 11795 | 41950 | 450
PRC 3352404PC5903 | 2023-10-12 | Inv. 2142201940-103 (Split Between MM23, DA23, and R22M) |  | 42400 | 360 | 42310 | 90
PRC 3352404PD5903 | 2023-12-13 | Inv. 2142201940-104 (Split Between MM23 and DA23) |  | 42400 | 0 | 42310 | 90
PO 33524045903 | 2024-02-09 | CO #3 (100% to MM23) | 0 | 42400 |  | 42310 | 90
PRC 3352404PE5903 | 2024-03-18 | Inv. 2142201940-105 (Split Between MM23 and R22M) |  | 42400 | 90 | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  |  |  | 42400 |  | 42400 | 0
|  | Totals | 42400 |  | 42400 |  | 0
|  | Investigation/Design Development | 14100 |  | 14100 |  | 0
|  | 50% Report | 16900 |  | 16900 |  | 0
|  | 95% Report | 9600 |  | 9600 |  | 0
|  | 100% Report | 1800 |  | 1800 |  | 0
|  | Totals: | 42400 |  | 42400 |  | 0
|  | 9268.02 DA23 | 6860 |  | 6860 |  | 0
|  | 9268.01 MM23 | 0 |  | 10179.88 |  | 16062.12
|  | Total Contract: | 49260 |  | 59439.88 |  | 16062.12

## RECAP #9277.00
CC Main Switchgear Master Control Replacement
Project # 9277.00
| Program code 927700 |  |  | Major Program 4F08
Recap
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1359.3
| Cummins Inc. |  | 1359.3 | 0 | 1359.3
C | PM TIME |  | 0 | 0 | 0
| Misc. |  | 0 | 0 | 0
| Total Project Cost | 1359.3 | 1359.3 | 0 | 1359.3 | 0
Note on C9: Huggins, Joni [DAS]: Re: Draft MOU for 9277.00, CC Main Switchgear Master Control Replacement and New Project Set-up FY22 Jusic, Mirela Attachments Jul 21, 2022, 7:53 AM (6 days ago) to me, Jennifer, Scott, Jennifer Attached, thanks On Thu, Jul 21, 2022 at 7:31 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Attached is the completed MOU, ready for signatures On Wed, Jul 20, 2022 at 5:09 PM Kleene, Jennifer <jennifer.kleene@iowa.gov> wrote: Please review the draft MOU and let me know if you have any questions. Please also set-up a third 9277.00 project - this will be in R21M for $28,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9277.00 Funds Rec'd
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Funds Rec'd
Acct. Codes-0506-335-R22M
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
[6 empty] | 1359.3 | 1359.3
0
| Total Requested | 0 | Total Transferred |  |  | 1359.3 | 1359.3

## #9277.00 Cummins
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Cummins Inc. |  |  | Vendor: 00003104792
Acct. Codes-0506-335-R22M-9255 |  |  | MA21233A
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split with MM22 & DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524234800 | 2024-07-24 | CO update to Transfer R21M to R22M | 1359.3 | 1359.3 |  |  | 1359.3 | 1359.3 | FY24
PO 33525234800 | 2024-08-26 | Roll to FY25 | 0 | 1359.3 |  | 0 | 1359.3
PO 33525234800 | 2024-08-30 | CO #2(No Cost CO-100% to MM22) | 0 | 1359.3 |  | 0 | 1359.3
PO 33525234800 | 2024-12-17 | CO #3 (Moving MM22 to MM24) | 0 | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  |  |  | 1359.3 |  | 0 | 1359.3
|  | Totals | 1359.3 |  | 0 |  | 1359.3
|  | MM22(Closed 12/17/24) | 265442.5 |  | 265442.35 |  | 0
|  | DA23 | 108744 |  | 103306.8 |  | 5437.2
|  | R21M (Closed 07/24/24) | 25826.7 |  | 25826.7 |  | 0
|  | MM24 | 118547.65 |  | 0 |  | 118547.65
|  | Total Contract: | 519920.15 |  | 394575.85 |  | 125344.15

## #9277.00 PM TIME
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9277.00 Misc
CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-R22M
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #xxxx.xx Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #xxxx.xx Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #xxxx.xx PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-R22M-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #xxxx.xx Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Acct. Codes-0506-335-R22M-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0