## FINANCIAL
Date DAS Processed | Agency | Document number | Document number for Interest Transfer | Project Mgr. | Vertical Infrastructure Project Allocation | Interest | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation $2,000,000 |  | 2000000
|  | Additional Funds |  | 11969.84
|  | Sales Tax Refunds |  |  | 0
|  | Total Funds & Sales Tax Refunds |  |  | 2011969.84
|  | Less: Total Assigned |  |  | 2003783.96
|  | Total Unassigned / Unallocated |  |  | 8185.88
|  | Routine Maintenance Projects | [9 empty] | Data as of 12/31/2020
[5 empty] | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
2019-10-10 | IPTV | 33520RMIPTV |  |  | 14938.55 | 28.37 | 14966.92 | 0 | 14966.92 | 0 | 0
2019-10-14 | THIL | 33520RMTHIL |  |  | 5041.14 | 9.57 | 5050.71 | 0 | 5050.71 | 0 | 0
2019-10-21 | DPS | 33520RMDPS |  |  | 25995.25 | 49.37 | 26044.62 | 0 | 26044.62 | 0 | 0
2019-10-21 | IVH | 33520RMIVH |  |  | 138210.77 | 262.49 | 138473.26 | 0 | 138473.26 | 0 | 0
2019-10-21 | DVA | 33520RMDVA |  |  | 4594.86 | 8.73 | 4603.59 | 0 | 4603.59 | 0 | 0
2019-10-28 | ILEA | 33520RMILEA |  |  | 7588.68 | 0 | 7588.68 | 0 | 7588.68 | 0 | 0
2019-11-04 | DHS | 33520RMDHS |  |  | 559002.03 | 1061.65 | 560063.68 | 0 | 560063.68 | 0 | 0
2019-11-04 | DCA | 33520RMDCA |  |  | 15801.72 | 30.01 | 15831.73 | 0 | 15831.73 | 0 | 0
2019-11-15 | DOC | 33520RMDOC |  |  | 860154.11 | 1633.59 | 861787.7 | 0 | 861787.7 | 0 | 0
2019-12-04 | DAS | 33520RMDAS |  |  | 368672.89 | 700.18 | 369373.07 | 0 | 369373.07 | 0 | 0
3783.96
|  | ILEA 14.41 |  |  |  | -14.41
|  | Major Maintenance Totals |  |  | 2000000 | 7553.51 | 2003783.96 | 0 | 2003783.96 | 0 | 0
[7 empty] | Total funds not allocated to the projects listed above |  |  |  | 8185.88
|  | For these project the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  |  | Subtotal |  |  |  | 8185.88
[7 empty] | Total funds Available |  |  | 2011969.84
[7 empty] | Total obligated by contract or PO |  |  | -2003783.96 | 8185.88
[7 empty] | Variance |  |  |  | 0

## #Funds Rec'd
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program 4D03
Funds Rec'd
Acct Code: 0090-335-20RM-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | November Interest | JV1INTALL2019352056 | 2019-12-20 | 169.9 | 169.9
|  |  | December Interest | JV1INTALL2020027055 | 2020-01-27 | 1894.41 | 1894.41
|  |  | January Interest | JV1INTALL20200550226 | 2020-02-24 | 1565.18 | 1565.18
|  |  | February Interest | JV1INTALL20200830225 | 2020-03-24 | 157.67 | 157.67
|  |  | March Interest | JV1INTALL2020114055 | 2020-04-23 | 1.21 | 1.21
|  |  | April Interest | JV1INTALL2020147056 | 2020-05-26 | 3.65 | 3.65
|  |  | May Interest | JV1INTALL2020170055 | 2020-06-19 | 3.35 | 3.35 | Recvd | Trans
|  |  | June Interest | JV1INTALL20202050114 | 2020-07-23 | 3 | 3 | 3798.37 | 3783.96 | -14.41
|  |  | July Interest | JV1INTALL2020233054 | 2020-08-20 | 1.96 | 1.96
|  |  | August Interest | JV1INTALL2020268054 | 2020-09-24 | 2.41 | 2.41 |  | 14.41
|  |  | September Interest | JV1INTALL2020296054 | 2020-10-22 | 1.07 | 1.07 |  | 16.35
|  |  | October Interest | JV1INTALL2020324054 | 2020-11-19 | 0.89 | 0.89 |  | 30.76
|  |  | November Interest | JV1INTALL2020352054 | 2020-12-18 | 0.51 | 0.51
|  |  | December Interest | JV1INTALL2021026054 | 2021-01-26 | 0.28 | 0.28
|  |  | January Interest | JV1INTALL2021049054 | 2021-02-23 | 0.17 | 0.17
|  |  | February Interest | JV1INTALL2021081054 | 2021-03-23 | 7.83 | 7.83
|  |  | March Interest | JV1INTALL2021112054 | 2021-04-22 | 0.48 | 0.48
|  |  | April Interest | JV1INTALL2021140054 | 2021-05-20 | 0.35 | 0.35
|  |  | May Interest | JV1INTALL2021173054 | 2021-06-22 | 0.18 | 0.18
|  |  | June Interest | JV1INTALL2021200054 | 2021-07-20 | 0.22 | 0.22 |  | 16.35 | 2021 Interest included on FY22 MOU's
|  |  | July Interest | JV1INTALL2021229054 | 2021-08-19 | 0.14 | 0.14
|  |  | August Interest | JV1INTALL20212650227 | 2021-09-23 | 0.54 | 0.54
|  |  | Interest moved out to 22RM | CDR 00522RMINT | 2021-10-13 | -30.76 | -30.76
|  |  | September Interest | JV1INTALL2021294054 | 2021-10-21 | 7.93 | 7.93
|  |  | October Interest | JV1INTALL2021320054 | 2021-11-22 | 25.67 | 25.67
|  |  | November Interest | JV1INTALL2021349053 | 2021-12-16 | 3.77 | 3.77
|  |  | December Interest | JV1INTALL2022021054 | 2022-01-21 | 10.62 | 10.62
|  |  | January Interest | JV1INTALL2022046054 | 2022-02-16 | 61.58 | 61.58
|  |  | February Interest | JV1INTALL2022080052 | 2022-03-22 | 86.56 | 86.56
|  |  | March Interest | JV1INTALL2022111053 | 2022-04-25 | 1.54 | 1.54 |  | 198.35 | 2022 Interest
|  |  | August Interest | JV1INTALL2022265054 | 2022-09-23 | 0.08 | 0.08
|  |  | Interest moved out to 23RM | CDR 00523RMINT | 2022-10-05 | -198.35 | -198.35
|  |  | September Interest | JV1INSTALL2022292054 | 2022-10-20 | 0.27 | 0.27
|  |  | October Interest | JV1INTALL2022322055 | 11/18/202 | 0.27 | 0.27
|  |  | November Interest | JV1INTALL2022353055 | 2022-12-19 | 492.64 | 492.64
|  |  | December Interest | JVT1INTALL2023023055 | 2023-01-23 | 2333.7 | 2333.7
|  |  | December Interest | JVT1INTCOR2023023055 | 2023-01-23 | -2333.7 | -2333.7
|  |  | December Interest | JV1INTALL2023024055 | 2023-01-24 | 2333.7 | 2333.7
|  |  | January Interest | JV1INTALL2023055055 | 2023-02-24 | 558.28 | 558.28
|  |  | February Interest | JV1INTALL2023082055 | 2023-03-23 | 36.59 | 36.59
|  |  | March Interest | JV1INTALL2023117056 | 2023-04-28 | 8.76 | 8.76
|  |  | April Interest | JV1INTALL2023145055 | 2023-05-31 | 11.1 | 11.1
|  |  | May Interest | JV1INTALL2023179055 | 2023-06-28 | 9.81 | 9.81
|  |  | June Interest | JV1INTALL2023208070 | 2023-07-28 | 11 | 11 |  | 3462.5 | 2023 Interest
|  |  | July Interest | JV1INTALL2023241076 | 2023-08-31 | 11.74 | 11.74
|  |  | Interest moved out to 24RM | CDR 00524RMINT | 2023-09-12 | -3462.5 | -3462.5
|  |  | August Interest | JV1INTALL2023270054 | 2023-09-28 | 12.96 | 12.96
|  |  | September Interest | JV1INTALL2023293054 | 2023-10-20 | 13.24 | 13.24
|  |  | October Interest | JV1INTALL2023324055 | 2023-11-20 | 2578.86 | 2578.86
|  |  | November Interest | JV1INTALL2023354055 | 2023-12-20 | 3439.01 | 3439.01
|  |  | December Interest | JV1INTALL2024029054 | 2024-01-30 | 2690.97 | 2690.97
|  |  | January Interest | JV1INTALL2024058054 | 2024-02-28 | 944.16 | 944.16
|  |  | February Interest | JV1INTALL2024086056 | 2024-03-28 | 30.53 | 30.53
|  |  | March Interest | JV1INTALL20241200229 | 2024-04-30 | 33.01 | 33.01
|  |  | April Interest | JV1INTALL2024145055 | 2024-05-24 | 41.34 | 41.34
|  |  | May Interest | JV1INTALL2024178053 | 2024-06-27 | 34.73 | 34.73
|  |  | June Interest | JV1INTALL2024205053 | 2024-07-24 | 38.35 | 38.35 |  | 9868.9 | 2024 Interest
|  |  | July Interest | JV1INTALL2024240053 | 2024-08-27 | 38.82 | 38.82
|  |  | Interest moved out to 25RM | CDR 00525RMINT | 2024-09-12 | -9868.9 | -9868.9
|  |  | August Interest | JV1INTALL2024270052 | 2024-09-27 | 44.42 | 44.42
|  |  | September Interest | JV1INTALL2024304052 | 2024-10-31 | 1490.22 | 1490.22
|  |  | October Interest | JV1INTALL2024330052 | 2024-11-25 | 3680.46 | 3680.46
|  |  | November Interest | JV1INTALL2024354052 | 2024-12-19 | 2159.94 | 2159.94
|  |  | December Interest | JV1INTALL2025027052 | 2025-01-28 | 692.67 | 692.67
|  |  | January Interest | JV1INTALL2025057052 | 2025-02-27 | 22.91 | 22.91
|  |  | February Interest | CDRINTALL2025086097 | 2025-03-27 | 30.25 | 30.25
|  |  | March Interest | CDRINTALL2025119097 | 2025-04-30 | 26.19 | 26.19
April Interest
May Interest
June Interest
|  |  | July Interest | [6 empty] | 2025 Interest
| Total Requested | 0 | Total Transferred |  |  | 11969.84 | 11969.84

## DHS
DHS SFY 20 Routine Maintenance Fund Allocation Plan
Facility | Project Description | Project Status/ Work Completed | Revenue Source | Cost Estimate | Funds Obligated | Funds Expended | Completion Date
CHK/CCUSO | Monthly elevator inspections | Partially completed | RM | 18804 | 18804 | 9402 | June 30, 2021
CHK/CCUSO | Monthly pest control service | Partially completed | RM | 4080 | 4080 | 2040 | June 30, 2021
CHK/CCUSO | Monthly water treatment & chemicals | Partially completed | RM | 9072 | 9072 | 4536 | June 30, 2021
CHK/CCUSO | Quarterly fire alarm testing | Partially completed | RM | 10800 | 10800 | 5400 | June 30, 2021
CHK/CCUSO | Repair & replace powerhouse switchgear | Not yet started | RM | 20080 | 20080 | 0 | June 30, 2021
CHK/CCUSO | Fire extinguisher inspections & service | Partially completed | RM | 11719 | 11719 | 5859.5 | June 30, 2021
CHK/CCUSO | Softener salt for water systems | Partially completed | RM | 5229 | 5229 | 2614.5 | June 30, 2021
CHK/CCUSO | Replacement of ceiling tiles | Not yet started | RM | 6082.56 | 6082.56 | 0 | June 30, 2021
CHK/CCUSO | Replacement of faucets | Partially completed | RM | 4603.94 | 4603.94 | 4603.94 | March 2020
CHK/CCUSO | Replacement switch covers, outlet covers, junction boxes | Completed | RM | 5400 | 5400 | 5400 | December 2019
CHK/CCUSO | Radiator covers to eliminate ligature risk | Just begun | RM | 174000 | 174000 | 174000 | June 30, 2021
IMHI | Monthly elevator inspections | Partially completed | RM | 8400 | 8400 | 4200 | June 30, 2021
IMHI | Monthly Rentokil service | Partially completed | RM | 3360 | 3360 | 1680 | June 30, 2021
IMHI | Quarterly sprinkler inspections, repairs | Partially completed | RM | 7983.62 | 7983.62 | 3991.81 | June 30, 2021
IMHI | Fire alarm repairs | Completed | RM | 709.16 | 709.16 | 709.16 | November 2019
IMHI | Monthly boiler chemicals | Partially completed | RM | 4800 | 4800 | 2400 | June 30, 2021
IMHI | Kitchen hood cleaning, semi-annual | Partially completed | RM | 1770 | 1770 | 885 | June 30, 2021
IMHI | Nuisance animal control | Completed | RM | 2430 | 2430 | 2430 | Fall 2019
IMHI | Fire rated doors | Completed | RM | 1225 | 1225 | 1225 | July 2019
IMHI | Blower fans | Completed | RM | 1586.92 | 1586.92 | 1586.92 | August 2019
IMHI | Garage doors and repairs | Completed | RM | 2170.26 | 2170.26 | 2170.26 | November 2019
IMHI | Boiler repairs | Completed | RM | 15302.51 | 15302.51 | 15302.51 | September 2019
IMHI | Grounds upkeep, trees, stump removal | Completed | RM | 10280.4 | 10280.4 | 10280.4 | October 2019
IMHI | Storm drain and sidewalk repairs | Completed | RM | 8285.2 | 8285.2 | 8285.2 | September 2019
IMHI | Electrical & lighting supplies | Completed | RM | 5526.34 | 5526.34 | 5526.34 | November 2019
IMHI | Plumbing supplies | Completed | RM | 7049.53 | 7049.53 | 7049.53 | September 2019
IMHI | Building supplies | Completed | RM | 6437.34 | 6437.34 | 6437.34 | August 2019
IMHI | Solar salt | Not yet started | RM | 4380 | 4380 | 0 | June 30, 2021
IMHI | Ceiling tiles | Not yet started | RM | 10000 | 10000 | 0 | June 30, 2021
IMHI | LED lighting conversion | Not yet started | RM | 10000 | 10000 | 0 | June 30, 2021
IMHI | Flooring | Not yet started | RM | 10000 | 10000 | 0 | June 30, 2021
IMHI | Replacement doors and associated hardware | Not yet started | RM | 20000 | 20000 | 0 | June 30, 2021
IMHI | Engergy management upgrade, required | Not yet started | RM | 41700 | 41700 | 0 | June 30, 2021
IMHI | 5 - Ligature resistant drinking fountains | Not yet started | RM | 11000 | 11000 | 0 | June 30, 2021
IMHI | 15 - ligature/vandal resistant toilets | Not yet started | RM | 14488.59 | 14488.59 | 0 | June 30, 2021
IMHI | Heater convector screens | Not yet started | RM | 2400 | 2400 | 0 | June 30, 2021
IMHI | Build walls w/door around air conditioners | Not yet started | RM | 5000 | 5000 | 0 | June 30, 2021
IMHI | Install hard ceiling in patient restrooms | Not yet started | RM | 4500 | 4500 | 0 | June 30, 2021
IMHI | Ligature resistant door hardward | Not yet started | RM | 34274 | 34274 | 0 | June 30, 2021
IJH Toledo | Storm water intake repairs | Not yet started | RM | 34072.16 | 34072.16 | 0 | June 30, 2021
|  | Total Costs Submitted |  | 559001.53 | 559001.53 | 288015.41
|  | Allocation |  | 559002.03
|  | Funding Balance |  | 0.5
559002
| Routine Maintenance Allocation | 559002
| Minus IJH Toledo Repair | 524929.84
| Facility Square Footage | 1180564
| CHK/CCUSO | 564425
| IMHI | 616139
| CHK/CCUSO Allocaiton Based on Square Footage | 250967.7789
| IMHI Allocation Based on Square Footage | 273962.0611

## DCA
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered | Date of Completion/ estimated completion date
|  | Total Allocation $15,801.72 | 15801.72
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 15801.72
|  | Less: Total Assigned |  | 15801.72
|  | Total Unassigned / Unallocated |  | 0
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| n/a | DCA Routine Maintenance - Historic Sites | Michael P. | 15801.72 |  | 15801.72 | 15878.95 | 15878.95 | 0 | -77.23
|  | Routine Maintenance Totals |  | 15801.72 | 0 | 15801.72 | 15878.95 | 15878.95 | 0 | -77.23
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
[6 empty] | Subtotal |  |  |  | -77.23
[6 empty] | Total funds Available |  |  | 15801.72
[6 empty] | Total obligated by contract or PO |  |  | -15878.95 | -77.23
[6 empty] | Variance |  |  |  | 0

## DOC
Department | Date | Vendor Customer | Line Description | Amount
242 | - | - | - | 0
243 | 2019-07-02 | Grainger | Wall Lights | 18012
243 | 2019-07-02 | Black Box/Norstan | Telephone System Agreement | 10767.38
243 | 2019-07-08 | McAleer Water | July 2019 Services | 144
243 | 2019-07-09 | Plumbers Supply | Flush Valve | 4331.7
243 | 2019-07-22 | Menards | Durock & Access Panel | 93.72
243 | 2019-07-23 | Johnson Controls | Annual Maintenance | 9500
243 | 2019-08-19 | United Rental | Scissor Lift Rental | 1642.28
243 | 2019-10-14 | Iowa Dept. of Admin. Services | MOU for PH Water Softener Project 9006.01 | 50000
94491.08
244 | - | - | - | 0
245 | - | - | - | 0
246 | - | - | - | 0
247 | 2019-07-24 | Van Meter | Fence Alarm - Communications & Pull Rope for Fiber Optic Installation | 414.57
247 | 2019-08-19 | Tri-City Electric | Fence Alarm - Balance of Project | 15000
247 | 2019-08-23 | Van Meter | Fence Alarm - Ground Boxes | 882.73
247 | 2019-08-23 | Graybar | Fence Alarm - Project Materials | 3074.91
247 | 2019-09-05 | Graybar | Fence Alarm - Project Materials | 1468.92
247 | 2019-09-25 | Fastenal | Fasteners for Ground Boxes & Security Screws for Air Vents | 201.22
247 | 2019-09-26 | Wirtjers / JW Construction | Fence Alarm - Pea Rock/Gravel | 368.5
247 | 2019-09-26 | Van Meter | Fence Alarm - Miscellaneous Materials | 178.95
247 | 2019-11-18 | Tri-City Electric | Fence Alarm - Balance of Project | 17067.3
247 | 2019-11-22 | IPI | Fence Alarm - Signs | 704
247 | 2019-11-21 | Tim Hildreth | Boilers - Replace 4 Tubes in Boiler & Perform Combustion Checks on 5 of them | 3729.9
247 | 2019-12-12 | Tim Hildreth | Boilers - Replace 4 Tubes in Boiler & Perform Combustion Checks on 5 of them | 936.78
44027.78
248 | - | - | - | 0
249 | 2019-09-17 | Kone | Elevator Maint Coverage 7/1/19 thru 8/31/19 | 601.38
249 | 2019-10-07 | Kone | Elevator Maint Coverage 9/1/19 thru 9/30/19 | 300.69
249 | 2019-10-23 | Kone | Elevator Maint Coverage 10/1/19 thru 10/31/19 | 300.69
249 | 2019-11-07 | Kone | Elevator Maint Coverage 11/1/19 thru 11/30/19 | 300.69
249 | 2019-12-16 | Kone | Elevator Maint Coverage 12/1/19 thru 12/31/19 | 300.69
249 | 2019-12-16 | Johnson Controls | Unit 9 Chiller - Diagnosis of Repairs Neeeded | 758
2562.14
252 | 2019-12-09 | Heritage Food Service | Parts for Combi Oven & Bread Slicer | 2396.25
252 | 2019-12-09 | Heritage Food Service | Parts for Combi Oven | 434.32
2830.57

## DAS
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 345492
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 345492
|  | Less: Total Assigned |  | 345492
|  | Total Unassigned / Unallocated |  | 0
R20M (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9111.00 | DAS CC Grimes Building Elevator Replacements | Brad T | 0 | 345492 | 345492 | 345492 | 345492 | 0 | 0
|  | R20M (MOU) Totals |  | 0 | 345492 | 345492 | 345492 | 345492 | 0 | 0
0

## IVH FY20
IVH Routine Maintenance - FY 2020
| Posting Am | Vendor Customer Name | Doc ID | Line Description | Doc CD | Cycle Date | Object Class | Unit | Sub Unit | Object | Sub Object | Revenue Class | Revenue | Revenue Type
| -138210.77 |  | 33520RMIVH |  | IET | 2019-10-21 |  | RM20 |  |  |  | 234 | 0304
| 218.5 | MJ Breen LLC | PRC031820400 | IVH-inv#1900301035288-7 batteries for emergency lights in Fox & Ulery | PRC | 2020-03-19 | 302 | RM20 |  | 2222
| 392.5 | Sherwin Williams | GAX031720301 | IVH-Inv#7008-1- Qty 1 gallon of Paint (earth smoke)-3/6/2020 | GAX | 2020-03-20 | 302 | RM20 |  | 2223
| 4998.56 | Backflow Prevention Serv Of Iowa Inc | GAX040520400 | IVH-inv#144503-service to replace backflow preventor on cooling tower | GAX | 2020-04-07 | 409 | RM20 |  | 2513
| 204.7 | US BANK CARDMEMBER SERV | PRC040820401 | baomain female quick disconnects vinyl insulated spade wire connectors;heat shrink tubing wire wrap | PRC | 2020-04-13 | 302 | RM20 |  | 2222
| 32.08 | Plumbers Supply Company | PRC042420400 | IVH-inv#S1626015.001-rough brass nipples;2 handle repair kits;4 faucet connectors | PRC | 2020-04-29 | 302 | RM20 |  | 2224
| 200.4 | Plumbers Supply Company | PRC042420400 | IVH-inv#S1626308.001-10 P-traps | PRC | 2020-04-29 | 302 | RM20 |  | 2224
| 875 |  | CDE050420100 | QCA Water Treatment-PRC010720400-monthly water treatment for December | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 448 |  | CDE050420100 | QCA Water Treatment-PRC020620400-boiler sensors | CDE | 2020-05-04 | 303 | RM20 |  | 2230
| 875 |  | CDE050420100 | QCA Water Treatment-PRC020620400-monthly water treatment for January | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC030420400-monthly water treatment for February | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC041320400-monthly water treatment for March | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 160 |  | CDE050420100 | QCA Water Treatment-PRC073019400 flow switch | CDE | 2020-05-04 | 303 | RM20 |  | 2230
| 875 |  | CDE050420100 | QCA Water Treatment-PRC081219400-monthly water treatment for July | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC091219400-monthly water treatment for August | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC100819400-monthly water treatment for September | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC111219400-monthly water treatment for October | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 875 |  | CDE050420100 | QCA Water Treatment-PRC120519400-monthly water treatment for November | CDE | 2020-05-04 | 406 | RM20 |  | 2386
| 1100 |  | CDE050420100 | Trugreen-GAX042920300-lawn services 4/10/20 | CDE | 2020-05-04 | 406 | RM20 |  | 2487
| 2000 |  | CDE050420100 | Trugreen-GAX090519400-lawn services 8/22/19 | CDE | 2020-05-04 | 406 | RM20 |  | 2487
| 1100 |  | CDE050420100 | Trugreen-GAX101819300-lawn services 9/30/19 | CDE | 2020-05-04 | 406 | RM20 |  | 2487
| 2586.01 |  | CDE050520400 | Johnson Controls-PRC042820400 service to add Sheeler to fiber network for Sheeler fire panel | CDE | 2020-05-05 | 409 | RM20 |  | 2519
| 1018.3 | Johnson Controls Inc | PRC050420400 | IVH-inv#86720769-service/repairs to HH fire supression system | PRC | 2020-05-07 | 409 | RM20 |  | 2519
| 2900.04 | Menards Inc | PRC050420400 | IVH-inv#34875-132gal paint | PRC | 2020-05-07 | 302 | RM20 |  | 2223
| 725.28 | Plumbers Supply Company | PRC050620400 | IVH-inv#S1626015.002-6 4" lift spacers for elongated toilet seats | PRC | 2020-05-07 | 302 | RM20 |  | 2224
| 875 | QCA WATER TREATMENT SERVICES LLC | PRC050420400 | IVH-inv#20-120-monthly water treatment chemical flat fee-April | PRC | 2020-05-07 | 406 | RM20 |  | 2386
| 142 | QCA WATER TREATMENT SERVICES LLC | PRC051220400 | IVH-inv#20-139-tower 5 chem controller | PRC | 2020-05-13 | 303 | RM20 |  | 2230
| 209 | QCA WATER TREATMENT SERVICES LLC | PRC051420401 | IVH-inv#20-083 replacement pH/ORP sensor for water testing | PRC | 2020-05-19 | 303 | RM20 |  | 2230
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC011720400 -elevator maintenance-Jan | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC041320400 -elevator maintenance-April | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC041320400 -elevator maintenance-Feb | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC041320400 -elevator maintenance-March | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC072319401 -elevator maintenance-July | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC081919400 -elevator maintenance-August | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC091819400 -elevator maintenance-Sept | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC102819400 -elevator maintenance-Oct | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC111419400 -elevator maintenance-Nov | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 3083.35 | Schumacher Elevator Co | CDE051920300 | Schumacher-PRC121819400 -elevator maintenance-Dec | CDE | 2020-05-19 | 406 | RM20 |  | 2372
| 96.61 | US BANK CARDMEMBER SERV | PRC051520400 | 12 wall switch plates;motor run capacitor;24 electrical boxes | PRC | 2020-05-19 | 302 | RM20 |  | 2224
| 489.84 | US BANK CARDMEMBER SERV | PRC051520400 | 36 toilet vacuum breaker kits;20 flushometer rebuild kits | PRC | 2020-05-19 | 302 | RM20 |  | 2224
| 1371 | US BANK CARDMEMBER SERV | PRC051520400 | 5 room temp sensors | PRC | 2020-05-19 | 503 | RM20 |  | 3300
| 886.7 | US BANK CARDMEMBER SERV | PRC051520401 | 10 room temp sensors | PRC | 2020-05-19 | 303 | RM20 |  | 2230
| 115.39 | US BANK CARDMEMBER SERV | PRC051520401 | 1 pullstation horn cover | PRC | 2020-05-19 | 302 | RM20 |  | 2229
| 67.56 | US BANK CARDMEMBER SERV | PRC051520401 | 6 american standard lavatory faucet handles | PRC | 2020-05-19 | 302 | RM20 |  | 2224
| 613.16 |  | CDE052120300 | Control Installations of IA-PRC013020400-service call to repair Dack slider door | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 159.95 |  | CDE052120300 | Control Installations of IA-PRC021720200-service call to make repairs to Malloy smoke room doo | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 201.6 |  | CDE052120300 | Control Installations of IA-PRC042420400-service call to make repairs to KU north door | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 201.6 |  | CDE052120300 | Control Installations of IA-PRC042420400-service call to repair Malloy LRC slider door | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 1450.52 |  | CDE052120300 | Control Installations of IA-PRC051420401-service call to repair Ulery front entrance door | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 575.73 |  | CDE052120300 | Control Installations of IA-PRC073119401-Service on North exterior door by Malloy Gift Shop | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 284.9 |  | CDE052120300 | Control Installations of IA-PRC092519400-service call to work on Sheeler/Loftus slider repairs | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 278.56 |  | CDE052120300 | Control Installations of IA-PRC110819400-repair to Malloy exterior doors by gift shop | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 448.06 |  | CDE052120300 | Control Installations of IA-PRC111219400-repairs to Malloy west entrance chapel door | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 389.95 |  | CDE052120300 | Control Installations of IA-PRC112219400-repairs to Malloy gift shop & Dack slider doors | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 531.16 |  | CDE052120300 | Control Installations of IA-PRC121819400-breakout switch assy | CDE | 2020-05-21 | 302 | RM20 |  | 2222
| 280 |  | CDE052120300 | Johnson Controls-PRC010720400 -service call to work on Ulery fire panel 12/13/19 | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 1050 |  | CDE052120300 | Johnson Controls-PRC021320400 -service call to fix panel issues between Sheeler & switchboard | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 722.4 |  | CDE052120300 | Johnson Controls-PRC021320400 -service call to work on Malloy fire panel | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 857.4 |  | CDE052120300 | Johnson Controls-PRC081219400 -photo sensors for smoke heads for facility | CDE | 2020-05-21 | 303 | RM20 |  | 2230
| 535 |  | CDE052120300 | Johnson Controls-PRC081219400 -service call to fix supervisory trouble in Fox 2 | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 560 |  | CDE052120300 | Johnson Controls-PRC081219400 -service call to make repairs to smoke head in KU4 | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 578.68 |  | CDE052120300 | Johnson Controls-PRC081619400 -service to remove & replace low air pressure switch in Fox | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 459.14 |  | CDE052120300 | Johnson Controls-PRC082819400 -service call to work on smoke head in KU1 | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 1741.68 |  | CDE052120300 | Johnson Controls-PRC083019400 -service call to make repairs to dietary kitchen hood system | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 822.2 |  | CDE052120300 | Johnson Controls-PRC091119400 -service call to diagnose low air alarm in Fox | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 420 |  | CDE052120300 | Johnson Controls-PRC091219400 -service to repair Malloy fire alarm | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 698.6 |  | CDE052120300 | Johnson Controls-PRC091819400 -service to repair camera system on East side | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 822.2 |  | CDE052120300 | Johnson Controls-PRC100319400 -service call to repair card reader patio door for Fox bldg | CDE | 2020-05-21 | 409 | RM20 |  | 2513
| 409.4 |  | CDE052120300 | Johnson Controls-PRC122419400 -service call to make repairs to fire panel at switchboard | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 215.6 |  | CDE052120301 | Johnson Controls-PRC041420400- service to fix 2 doors | CDE | 2020-05-21 | 409 | RM20 |  | 2512
| 2586.01 |  | CDE052120301 | Johnson Controls-PRC042820400 -service to add Sheeler to fiber network for Sheeler fire panel | CDE | 2020-05-21 | 409 | RM20 |  | 2519
| 11050 |  | CDE052120301 | Ralph & Smith-GAX040320300-Service to provide labor & materials to install flooring in HH | CDE | 2020-05-21 | 409 | RM20 |  | 2512
| 758.7 | Accredited Lock Company | PRC052020400 | IVH-inv#2086053-6 arrow assa leversets w/removable core | PRC | 2020-05-26 | 302 | RM20 |  | 2210
| 23.52 | Standard Bearings | PRC052220400 | IVH-inv#6513526-2 v-belts | PRC | 2020-05-26 | 303 | RM20 |  | 2230
| 875 | QCA WATER TREATMENT SERVICES LLC | PRC060520400 | IVH-inv#20-147 monthly water treatment-May | PRC | 2020-06-08 | 406 | RM20 |  | 2386
| 1100 | Outdoor Home Services Holdings LLC | GAX060920300 | IVH-Inv#120972977-Lawn Services-5/22/2020 | GAX | 2020-06-11 | 406 | RM20 |  | 2487
| 36800 | OMG Midwest Inc | PRC070120400 | IVH-inv#128419-HMA Mill & fill 7 pavement markings IVH NE parking lot resurfacing | PRC | 2020-07-01 | 409 | RM20 |  | 2519
| 540 | Ethington Heat & Cooling | GAX071320301 | IVH-Inv#24551-Qty 6 Radiator actuator-4.9.2020 | GAX | 2020-07-13 | 302 | RM20 |  | 2224
| 5579 |  | CDE081020300 | DH Pace-GAX071320301-Service to replace HH double doors-6.30.2020 | CDE | 2020-08-11 | 409 | RM20 |  | 2512
| 28.26 |  | CDE081020300 | IPI-IET042420401-Air Filters-Inv#088397-6(partial) | CDE | 2020-08-11 | 302 | RM20 |  | 2229
| 565.14 |  | CDE081020300 | IPI-IET042420401-Air Filters-Inv088399 | CDE | 2020-08-11 | 302 | RM20 |  | 2229
| 1951.68 |  | CDE081020300 | Kone Inc-PRC071520400-Elevator Maintenance-June 2020 | CDE | 2020-08-11 | 406 | RM20 |  | 2372
1.296e-11
2.3292e-11