## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 1000000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 1000000
|  | Less: Total Assigned |  | 1000000
|  | Total Unassigned / Unallocated |  | 0
Capitol Security Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
C | 9333.00 | Capitol Complex Phase 2 Camera Install | Charlee C. | 556007.42 |  | 556007.42 | 556007.42 | 556007.42 | 0 | 0
C | 9333.03 | Capitol Complex Camera Project Phase 2 - Missing Views | Jeff S. | 9660.77 |  | 9660.77 | 9660.77 | 9660.77 | 0 | 0
| 9333.05 | Capitol Complex Camera Project Phase 3 | Jeff S. | 234331.81 |  | 234331.81 | 0 | 0 | 0 | 234331.81
| 9421.00 | DAS TH East Gate Replacement | James T. | 200000 |  | 200000 | 111855.18 | 31682 | 80173.18 | 88144.82
|  | Capitol Security Upgrade Totals |  | 1000000 | 0 | 1000000 | 677523.37 | 597350.19 | 80173.18 | 322476.63
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 322476.63
[6 empty] | Total funds Available |  |  | 1000000
[6 empty] | Total obligated by contract or PO |  |  | -677523.37 | 322476.63
[6 empty] | Variance |  |  |  | 0
Note on E14: Jurgenson, John [DAS]: Re: Customer 1153 Construction Services Report[FY2023-13] $John Shannon, Jeff 2:05 PM (6 minutes ago) to me I'm not sure the $397.41 should be charged to CS23, that is not part of my project. $1,742 is correct. Please increase the budget of 9333.00 CS23 by $1,742.13 Thank you. Shannon, Jeff Attachments 2:37 PM (3 minutes ago) to me, James Please increase the budget of CS23, Project 9333.00, by $7,818.91. Once increased, please reimburse DPS $7,818.91 to cover the expenses of the attached invoice they have already paid. Thank you, Jeff Shannon Fwd: Draft email to JW $Joni Shannon, Jeff 9:20 AM (6 hours ago) to me Can you confirm that we still have $29,496.49 available in project 9333.00? All invoices have been paid. If that is the case, we can close the project and put the funds back to CS23. Please let me know if there is anything you would need from me. Thank you, Jeff Shannon Associate Facilities Administrator
Note on E15: Jurgenson, John [DAS]: Re: Project 9333.03 CS23 $John Shannon, Jeff 9:14 AM (2 minutes ago) to me, Charlee, Brent Yes I approved the increase in budget for 9333.03 in CS23 Please increase the total budget $4,794.27. Thank you,
Note on E17: Huggins, Joni [DAS]: 9421.00 - DAS TH East Gate Replacement - CS23 Funds $Joni Trower, James 9:37 AM (1 hour ago) to me, Charlee, Jeff Finance - Please increase the CS23 funding for project 9421.00 by $95,000.00. Thank you, James Trower, Licensed Architect, LEED AP 9421.00 - DAS TH East Gate Replacement - Increase Budget Inbox Trower, James 11:39 AM (4 minutes ago) to me Finance - 9421.00 - DAS TH East Gate Replacement Please increase the project budget by $55,000 (CS.23 funding). Thanks, James Trower, Licensed Architect, LEED AP

## RECAP #9333.00
Capitol Complex Phase 2 Camera Install
Project # 9333.00
| Program code 933300 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - Charlee C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 556007.42
C | Communications Innovators |  | 540281.07 | 540281.07 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 15726.35 | 15726.35 | 0
| Total Project Cost | 556007.42 | 556007.42 | 556007.42 | 0 | 0
Project closed 1/21/25

## #9333.00 Communications Innovat
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  |  | Major Program 4E21
Communications Innovators |  |  |  | Vendor:00002119160
Acct. Codes-0017-335-CS23-xxxx |  |  |  | MA-005-23075
Project Manager - Charlee C. |  |  |  | Activity code:No activity code
Doc # | Date |  | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523354810 | 2022-12-20 |  | DO Procore | 501964.67 | 501964.67 |  |  | 501964.67
PRC 3352335PA4810 | 2023-02-16 |  | Inv. 111086, 111091, 111092 |  | 501964.67 | 28182.25 | 28182.25 | 473782.42
PRC 3352335PB4810 | 2023-04-12 |  | Inv. 111784 & Inv.111783 |  | 501964.67 | 42289.52 | 70471.77 | 431492.9
PRC 3352335PC4810 | 2023-05-02 |  | Inv. 112221, 112219, 112217, 112222 |  | 501964.67 | 30598.14 | 101069.91 | 400894.76
PRC 3352335PD4810 | 2023-05-31 |  | Inv. 112641, 112642, 112669 |  | 501964.67 | 28698.46 | 129768.37 | 372196.3
CDE 33523163800 | 2023-06-12 |  | Move from SC22 to CS23 |  | 501964.67 | 39114.43 | 168882.8 | 333081.87
DO 33523354810 | 2023-06-20 |  | CO 1 | 67812.89 | 569777.56 |  | 168882.8 | 400894.76
PRC 3352335PE4810 | 2023-07-05 |  | Inv. 113042, 113045 |  | 569777.56 | 62584.8 | 231467.6 | 338309.96 | FY23
DO 33524354810 | 2023-08-09 |  | Rolled to FY24 | 0 | 569777.56 |  | 231467.6 | 338309.96
PRC 3352435PF4810 | 2023-08-11 |  | Inv. 113480, 113481 |  | 569777.56 | 72482.28 | 303949.88 | 265827.68
PRC 3352435PG4810 | 2023-11-06 |  | Inv. 114693 |  | 569777.56 | 170105.51 | 474055.39 | 95722.17
PRC 3352435PH4810 | 2023-12-28 |  | Inv. 115187 | -29496.49 | 540281.07 | 66225.68 | 540281.07 | 0
[5 empty] | 540281.07 |  | 540281.07 | 0
|  |  | Totals | 540281.07 |  | 540281.07 |  | 0 | FINAL
| Object code | Object class
| 3911 | 510 | Servers | 0 |  |  |  | 0
| 2674 | 501 | Axis Product and Accessories | 207934.75 |  | 207934.75 |  | 0
| 2464 | 405 | Labor Rates for Install Reg Rate | 210579.5 |  | 210579.5 |  | 0
| 2829 | 701 | Milestone Device License | 16632 |  | 16632 |  | 0
| 2829 | 701 | 1 Year Milestone Care Plus | 0 |  |  |  | 0
| 9210 | 901 | Warranty/Service Contract | 2028 |  | 2028 |  | 0
| 2464 | 405 | Subcontractors | 103106.82 |  | 103106.82 |  | 0
|  |  | Totals | 540281.07 |  | 540281.07 |  | 0

## #9333.00 PM TIME
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-CS23-xxxx
Project Manager - Charlee C. |  |  | eDAS E255
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.00 Misc
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23-xxxx
Project Manager - Charlee C.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202313115300001 | 2023-07-14 | 2507 |  | Electrical Services | DAS2023131153 | 1742.13 | 1742.13
IET 005FY23CS23TODPS | 2023-08-22 | 2674 |  | Transfer expense from DPS |  | 7442.4 | 9184.53
CDE 33524261801 | 2023-09-15 | 4011 |  | Transfer expense from DPS | Inv. INV000039891 | 6541.82 | 15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
|  |  |  | Totals |  | 15726.35

## RECAP #9333.03
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
| Program code 933303 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - Jeff S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 9660.77
C | Communication Innovators |  | 3435.24 | 3435.24 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 6225.53 | 6225.53 | 0
| Total Project Cost | 9660.77 | 9660.77 | 9660.77 | 0 | 0
Closed 08/02/23

## #9333.03 Communication Innovato
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  | Major Program 4E21
Communication Innovators |  |  | Vendor: 00002119160
Acct. Codes-0017-335-CS23-xxxx |  |  | MA# 005-23075
Project Manager - Jeff S. |  |  | Activity code:No activity code
Split with SC22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524129811 | 2024-05-08 | DO IA Advantage | 11912.86 | 11912.86 |  |  | 11912.86
DO 33524129811 | 2024-06-24 | CO #1 (100% to SC22) | 0 | 11912.86 |  | 0 | 11912.86
PRC 3352412PA9811 | 2024-06-21 | Inv. 117675(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
PRC 3352412PB9811 | 2024-06-21 | Inv. 117688(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
PRC 3352412PC9811 | 2024-06-21 | Inv. 117700(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
DO 33524129811 | 2024-06-24 | CO #2 (100% to SC22) | 0 | 11912.86 |  | 0 | 11912.86
PRC 3352412PD9811 | 2024-07-05 | Inv. 117747 |  | 11912.86 | 3435.24 | 3435.24 | 8477.62
DO 33524129811 | 2024-08-02 | Closing DO per PM | -8477.62 | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  | Totals | 3435.24 |  | 3435.24 |  | 0
Object codes
| 2674 | Axis Product and Accessories | 1323.77 |  | 1323.77 |  | 0
| 2464 | Labor Rates for Install Reg Rate | 2111.47 |  | 2111.47 |  | 0
|  | Totals | 3435.24 |  | 3435.24 |  | 0
|  | SC22 Closed 06/24/2024 | 42545.9 |  | 42545.9 |  | 0
|  | Total Contract | 45981.14 |  | 45981.14 |  | 0

## #9333.03 PM TIME
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-CS23 |  |  | eDAS 909K
Project Manager - Jeff S.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.03 Misc
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager - Jeff S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202412115300001 | 2024-07-17 | 2507 |  | Electrical Services June 1-30, 2024 | DAS2024121153 | 6225.53 | 6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
|  |  |  | Totals |  | 6225.53

## RECAP #9333.05
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - Jeff S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 234331.81
Vendor A |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 234331.81 | 0 | 0 | 0 | 234331.81

## #9333.05 Vendor A
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  | Major Program 4E21
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-CS23-xxxx
Project Manager - Jeff S |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.05 PM TIME
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  |  | Major Program 4E21
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-CS23
Project Manager - Jeff S
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #9333.05 Misc
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager - Jeff S
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9421.00
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 200000
Shive Hattery |  | 12100 | 9400 | 2700
PM TIME |  | 8000 | 8166.62 | -166.62
Misc. |  | 0 | 0 | 0
DCI Group |  | 16974.99 | 14115.38 | 2859.61
MidWest Fence & Gate |  | 74780.19 | 0 | 74780.19
Total Project Cost | 200000 | 111855.18 | 31682 | 80173.18 | 88144.82

## #9421.00 Shive Hattery
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-CS23-9260 |  |  | SRVV5
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524162902 | 2024-06-10 | PO Procore | 12100 | 12100 |  |  | 12100 | FY24
PO 33525162902 | 2024-08-02 | Rolled to FY25 |  | 12100 |  | 0 | 12100
PRC 3352516PA2902 | 2024-10-24 | Inv. 2240004580-1 |  | 12100 | 6670 | 6670 | 5430
PRC 3352516PB2902 | 2024-12-10 | Inv. 2240004580-2 |  | 12100 | 2730 | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  | Totals | 12100 |  | 9400 |  | 2700
|  | Limitied Topographic Survey | 1600 |  | 1600 |  | 0
|  | East Gate Design Services | 7800 |  | 7800 |  | 0
|  | Construction Phase Services | 2700 |  |  |  | 2700
|  | Totals | 12100 |  | 9400 |  | 2700

## #9421.00 PM TIME
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  |  | Major Program 4E21
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-CS23 |  |  |  | eDAS E2DI
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8000 | 157.58 | 157.58 | 7842.42
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8000 | 1303.5 | 1461.08 | 6538.92
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8000 | 175.54 | 1636.62 | 6363.38
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8000 | 1605.3 | 3241.92 | 4758.08
CDE 33525229800 | 2024-08-21 | 2507 | Moving PM Expense from 9997.25(Finance Support-July) |  | 8000 | 61.68 | 3303.6 | 4696.4
CDE 33525229800 | 2024-08-21 | 9500 | Moving PM Expense from 9997.25(DAS Services-July) |  | 8000 | 675 | 3978.6 | 4021.4
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8000 | 148.31 | 4126.91 | 3873.09
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8000 | 755.2 | 4882.11 | 3117.89
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8000 | 114.39 | 4996.5 | 3003.5
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8000 | 1023.5 | 6020 | 1980
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 8000 | 136.73 | 6156.73 | 1843.27
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8000 | 914.7 | 7071.43 | 928.57
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 8000 | 47.78 | 7119.21 | 880.79
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 8000 | 318.5 | 7437.71 | 562.29
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 8000 | 66.51 | 7504.22 | 495.78
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 8000 | 662.4 | 8166.62 | -166.62
[5 empty] | 8000 |  | 8166.62 | -166.62
[5 empty] | 8000 |  | 8166.62 | -166.62
[5 empty] | 8000 |  | 8166.62 | -166.62
|  |  | Totals | 8000 |  | 8166.62 |  | -166.62

## #9421.00 Misc
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9421.00 DCI Group
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-CS23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524179903 | 2024-06-27 | PO Procore | 16974.99 | 16974.99 |  |  | 16974.99 | FY24
PO 33525179903 | 2024-08-02 | Rolled to FY25 |  | 16974.99 |  | 0 | 16974.99
PRC 3352517PA9903 | 2024-10-18 | Inv. 24-032 PC 01 |  | 16974.99 | 8920.53 | 8920.53 | 8054.46
PRC 3352517PB9903 | 2024-12-03 | Inv. 24-032 PC 02 |  | 16974.99 | 1135.86 | 10056.39 | 6918.6
PRC 3352517PC9903 | 2025-01-03 | Inv. 24-032 PC 03 |  | 16974.99 | 4058.99 | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  |  |  | 16974.99 |  | 14115.38 | 2859.61
|  | Totals | 16974.99 |  | 14115.38 |  | 2859.61

## #9421.00 Midwest Fence & Gate
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Midwest Fence & Gate |  |  | Vendor: 00002122529
Acct. Codes-0017-335-CS23-9255 |  |  | MA00521284
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362902 | 2025-12-27 | PO Procore | 74780.19 | 74780.19 |  |  | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  | Totals | 74780.19 |  | 0 |  | 74780.19

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  | Major Program
Recap
Acct. Codes-0017-335-CS23
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget
Vendor A |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-CS23-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-CS23
Project Manager -
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  |  | Major Program
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager -
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0