## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 1000000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 1000000
|  | Less: Total Assigned |  | 795164.68
|  | Total Unassigned / Unallocated |  | 204835.32
Capitol Security Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9333.00 | Capitol Complex Phase 2 Camera Install | Charlee C. | 585503.91 |  | 585503.91 | 556007.42 | 556007.42 | 0 | 29496.49
C | 9333.03 | Capitol Complex Camera Project Phase 2 - Missing Views | Jeff S. | 9660.77 |  | 9660.77 | 9660.77 | 9660.77 | 0 | 0
| 9421.00 | DAS TH East Gate Replacement | James T. | 200000 |  | 200000 | 111855.18 | 26894.1 | 84961.08 | 88144.82
|  | Capitol Security Upgrade Totals |  | 795164.68 | 0 | 795164.68 | 677523.37 | 592562.29 | 84961.08 | 117641.31
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 204835.32
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 322476.63
[6 empty] | Total funds Available |  |  | 1000000
[6 empty] | Total obligated by contract or PO |  |  | -677523.37 | 322476.63
[6 empty] | Variance |  |  |  | 0
Note on E14: Jurgenson, John [DAS]: Re: Customer 1153 Construction Services Report[FY2023-13] $John Shannon, Jeff 2:05 PM (6 minutes ago) to me I'm not sure the $397.41 should be charged to CS23, that is not part of my project. $1,742 is correct. Please increase the budget of 9333.00 CS23 by $1,742.13 Thank you. Shannon, Jeff Attachments 2:37 PM (3 minutes ago) to me, James Please increase the budget of CS23, Project 9333.00, by $7,818.91. Once increased, please reimburse DPS $7,818.91 to cover the expenses of the attached invoice they have already paid. Thank you, Jeff Shannon
Note on E15: Jurgenson, John [DAS]: Re: Project 9333.03 CS23 $John Shannon, Jeff 9:14 AM (2 minutes ago) to me, Charlee, Brent Yes I approved the increase in budget for 9333.03 in CS23 Please increase the total budget $4,794.27. Thank you,
Note on E16: Huggins, Joni [DAS]: 9421.00 - DAS TH East Gate Replacement - CS23 Funds $Joni Trower, James 9:37 AM (1 hour ago) to me, Charlee, Jeff Finance - Please increase the CS23 funding for project 9421.00 by $95,000.00. Thank you, James Trower, Licensed Architect, LEED AP 9421.00 - DAS TH East Gate Replacement - Increase Budget Inbox Trower, James 11:39 AM (4 minutes ago) to me Finance - 9421.00 - DAS TH East Gate Replacement Please increase the project budget by $55,000 (CS.23 funding). Thanks, James Trower, Licensed Architect, LEED AP

## RECAP #9333.00
Capitol Complex Phase 2 Camera Install
Project # 9333.00
| Program code 933300 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - Charlee C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 585503.91
C | Communications Innovators |  | 540281.07 | 540281.07 | 0
| PM TIME |  | 0 | 0 | 0
| Misc. |  | 15726.35 | 15726.35 | 0
| Total Project Cost | 585503.91 | 556007.42 | 556007.42 | 0 | 29496.49

## #9333.00 Communications Innovat
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  |  | Major Program 4E21
Communications Innovators |  |  |  | Vendor:00002119160
Acct. Codes-0017-335-CS23-xxxx |  |  |  | MA-005-23075
Project Manager - Charlee C. |  |  |  | Activity code:No activity code
Doc # | Date |  | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523354810 | 2022-12-20 |  | DO Procore | 501964.67 | 501964.67 |  |  | 501964.67
PRC 3352335PA4810 | 2023-02-16 |  | Inv. 111086, 111091, 111092 |  | 501964.67 | 28182.25 | 28182.25 | 473782.42
PRC 3352335PB4810 | 2023-04-12 |  | Inv. 111784 & Inv.111783 |  | 501964.67 | 42289.52 | 70471.77 | 431492.9
PRC 3352335PC4810 | 2023-05-02 |  | Inv. 112221, 112219, 112217, 112222 |  | 501964.67 | 30598.14 | 101069.91 | 400894.76
PRC 3352335PD4810 | 2023-05-31 |  | Inv. 112641, 112642, 112669 |  | 501964.67 | 28698.46 | 129768.37 | 372196.3
CDE 33523163800 | 2023-06-12 |  | Move from SC22 to CS23 |  | 501964.67 | 39114.43 | 168882.8 | 333081.87
DO 33523354810 | 2023-06-20 |  | CO 1 | 67812.89 | 569777.56 |  | 168882.8 | 400894.76
PRC 3352335PE4810 | 2023-07-05 |  | Inv. 113042, 113045 |  | 569777.56 | 62584.8 | 231467.6 | 338309.96 | FY23
DO 33524354810 | 2023-08-09 |  | Rolled to FY24 | 0 | 569777.56 |  | 231467.6 | 338309.96
PRC 3352435PF4810 | 2023-08-11 |  | Inv. 113480, 113481 |  | 569777.56 | 72482.28 | 303949.88 | 265827.68
PRC 3352435PG4810 | 2023-11-06 |  | Inv. 114693 |  | 569777.56 | 170105.51 | 474055.39 | 95722.17
PRC 3352435PH4810 | 2023-12-28 |  | Inv. 115187 | -29496.49 | 540281.07 | 66225.68 | 540281.07 | 0
[5 empty] | 540281.07 |  | 540281.07 | 0
|  |  | Totals | 540281.07 |  | 540281.07 |  | 0 | FINAL
| Object code | Object class
| 3911 | 510 | Servers | 0 |  |  |  | 0
| 2674 | 501 | Axis Product and Accessories | 207934.75 |  | 207934.75 |  | 0
| 2464 | 405 | Labor Rates for Install Reg Rate | 210579.5 |  | 210579.5 |  | 0
| 2829 | 701 | Milestone Device License | 16632 |  | 16632 |  | 0
| 2829 | 701 | 1 Year Milestone Care Plus | 0 |  |  |  | 0
| 9210 | 901 | Warranty/Service Contract | 2028 |  | 2028 |  | 0
| 2464 | 405 | Subcontractors | 103106.82 |  | 103106.82 |  | 0
|  |  | Totals | 540281.07 |  | 540281.07 |  | 0

## #9333.00 PM TIME
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-CS23-xxxx
Project Manager - Charlee C. |  |  | eDAS E255
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.00 Misc
Capitol Complex Phase 2 Camera Install
Project # 9333.00
Program code 933300 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23-xxxx
Project Manager - Charlee C.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202313115300001 | 2023-07-14 | 2507 |  | Electrical Services | DAS2023131153 | 1742.13 | 1742.13
IET 005FY23CS23TODPS | 2023-08-22 | 2674 |  | Transfer expense from DPS |  | 7442.4 | 9184.53
CDE 33524261801 | 2023-09-15 | 4011 |  | Transfer expense from DPS | Inv. INV000039891 | 6541.82 | 15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
15726.35
|  |  |  | Totals |  | 15726.35

## RECAP #9333.03
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
| Program code 933303 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - Jeff S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 9660.77
C | Communication Innovators |  | 3435.24 | 3435.24 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 6225.53 | 6225.53 | 0
| Total Project Cost | 9660.77 | 9660.77 | 9660.77 | 0 | 0
Closed 08/02/23

## #9333.03 Communication Innovato
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  | Major Program 4E21
Communication Innovators |  |  | Vendor: 00002119160
Acct. Codes-0017-335-CS23-xxxx |  |  | MA# 005-23075
Project Manager - Jeff S. |  |  | Activity code:No activity code
Split with SC22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524129811 | 2024-05-08 | DO IA Advantage | 11912.86 | 11912.86 |  |  | 11912.86
DO 33524129811 | 2024-06-24 | CO #1 (100% to SC22) | 0 | 11912.86 |  | 0 | 11912.86
PRC 3352412PA9811 | 2024-06-21 | Inv. 117675(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
PRC 3352412PB9811 | 2024-06-21 | Inv. 117688(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
PRC 3352412PC9811 | 2024-06-21 | Inv. 117700(100% to SC22) |  | 11912.86 | 0 | 0 | 11912.86
DO 33524129811 | 2024-06-24 | CO #2 (100% to SC22) | 0 | 11912.86 |  | 0 | 11912.86
PRC 3352412PD9811 | 2024-07-05 | Inv. 117747 |  | 11912.86 | 3435.24 | 3435.24 | 8477.62
DO 33524129811 | 2024-08-02 | Closing DO per PM | -8477.62 | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  |  |  | 3435.24 |  | 3435.24 | 0
|  | Totals | 3435.24 |  | 3435.24 |  | 0
Object codes
| 2674 | Axis Product and Accessories | 1323.77 |  | 1323.77 |  | 0
| 2464 | Labor Rates for Install Reg Rate | 2111.47 |  | 2111.47 |  | 0
|  | Totals | 3435.24 |  | 3435.24 |  | 0
|  | SC22 Closed 06/24/2024 | 42545.9 |  | 42545.9 |  | 0
|  | Total Contract | 45981.14 |  | 45981.14 |  | 0

## #9333.03 PM TIME
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-CS23 |  |  | eDAS 909K
Project Manager - Jeff S.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.03 Misc
Capitol Complex Camera Project Phase 2 - Missing Views
Project # 9333.03
Program code 933303 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager - Jeff S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202412115300001 | 2024-07-17 | 2507 |  | Electrical Services June 1-30, 2024 | DAS2024121153 | 6225.53 | 6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
6225.53
|  |  |  | Totals |  | 6225.53

## RECAP #9421.00
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-CS23
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 200000
Shive Hattery |  | 12100 | 9400 | 2700
PM TIME |  | 8000 | 7437.71 | 562.29
Misc. |  | 0 | 0 | 0
DCI Group |  | 16974.99 | 10056.39 | 6918.6
MidWest Fence & Gate |  | 74780.19 | 0 | 74780.19
Total Project Cost | 200000 | 111855.18 | 26894.1 | 84961.08 | 88144.82

## #9421.00 Shive Hattery
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-CS23-9260 |  |  | SRVV5
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524162902 | 2024-06-10 | PO Procore | 12100 | 12100 |  |  | 12100 | FY24
PO 33525162902 | 2024-08-02 | Rolled to FY25 |  | 12100 |  | 0 | 12100
PRC 3352516PA2902 | 2024-10-24 | Inv. 2240004580-1 |  | 12100 | 6670 | 6670 | 5430
PRC 3352516PB2902 | 2024-12-10 | Inv. 2240004580-2 |  | 12100 | 2730 | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  |  |  | 12100 |  | 9400 | 2700
|  | Totals | 12100 |  | 9400 |  | 2700
|  | Limitied Topographic Survey | 1600 |  | 1600 |  | 0
|  | East Gate Design Services | 7800 |  | 7800 |  | 0
|  | Construction Phase Services | 2700 |  |  |  | 2700
|  | Totals | 12100 |  | 9400 |  | 2700

## #9421.00 PM TIME
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  |  | Major Program 4E21
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-CS23 |  |  |  | eDAS E2DI
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8000 | 157.58 | 157.58 | 7842.42
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8000 | 1303.5 | 1461.08 | 6538.92
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8000 | 175.54 | 1636.62 | 6363.38
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8000 | 1605.3 | 3241.92 | 4758.08
CDE 33525229800 | 2024-08-21 | 2507 | Moving PM Expense from 9997.25(Finance Support-July) |  | 8000 | 61.68 | 3303.6 | 4696.4
CDE 33525229800 | 2024-08-21 | 9500 | Moving PM Expense from 9997.25(DAS Services-July) |  | 8000 | 675 | 3978.6 | 4021.4
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8000 | 148.31 | 4126.91 | 3873.09
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8000 | 755.2 | 4882.11 | 3117.89
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8000 | 114.39 | 4996.5 | 3003.5
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8000 | 1023.5 | 6020 | 1980
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 8000 | 136.73 | 6156.73 | 1843.27
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8000 | 914.7 | 7071.43 | 928.57
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 8000 | 47.78 | 7119.21 | 880.79
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 8000 | 318.5 | 7437.71 | 562.29
[5 empty] | 8000 |  | 7437.71 | 562.29
|  |  | Totals | 8000 |  | 7437.71 |  | 562.29

## #9421.00 Misc
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9421.00 DCI Group
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-CS23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524179903 | 2024-06-27 | PO Procore | 16974.99 | 16974.99 |  |  | 16974.99 | FY24
PO 33525179903 | 2024-08-02 | Rolled to FY25 |  | 16974.99 |  | 0 | 16974.99
PRC 3352517PA9903 | 2024-10-18 | Inv. 24-032 PC 01 |  | 16974.99 | 8920.53 | 8920.53 | 8054.46
PRC 3352517PB9903 | 2024-12-03 | Inv. 24-032 PC 02 |  | 16974.99 | 1135.86 | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  |  |  | 16974.99 |  | 10056.39 | 6918.6
|  | Totals | 16974.99 |  | 10056.39 |  | 6918.6

## #9421.00 Midwest Fence & Gate
DAS TH East Gate Replacement
Project # 9421.00
Program code 942100 |  |  | Major Program 4E21
Midwest Fence & Gate |  |  | Vendor: 00002122529
Acct. Codes-0017-335-CS23-9255 |  |  | MA00521284
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362902 | 2025-12-27 | PO Procore | 74780.19 | 74780.19 |  |  | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  |  |  | 74780.19 |  | 0 | 74780.19
|  | Totals | 74780.19 |  | 0 |  | 74780.19

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  | Major Program
Recap
Acct. Codes-0017-335-CS23
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget
Vendor A |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-CS23-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-CS23
Project Manager -
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXX.XX |  |  |  | Major Program
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-CS23
Project Manager -
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0