## Language
Approp R52, final reversion FY2024 - 2018 Ia Acts, ch 1162, sec 1.1; 2020 Ia Acts, ch 1120, sec 7

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 20000000
|  | Additional Funds | 1855849.35
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 21855849.35
| . | Less: Total Assigned |  | 21674792.28
|  | Total Unassigned / Unallocated |  | 181057.07
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
|  | Funds Received |  |  | 1058062.34
C | 9997.22 | Project Management Time | NA | 526230 |  | 526230 | 526230 | 526230 | 0 | 0
C | 8983.02 | DAS CC SHB Roof and Skylight Replacement FY22 | Jennie E. | 3077863.62 | 25000 | 3102863.62 | 3102863.62 | 3102863.62 | 0 | 0
C | 9054.03 | DOC IMCC Boilers #2 and #3 Replacement | Jennifer K | 1053139.46 |  | 1053139.46 | 1053139.46 | 1053139.46 | 0 | 0
C | 9099.00 | DHS CHMHI Patient Restroom Safety Improvements | Jennie E. | 91006.93 |  | 91006.93 | 91006.93 | 91006.93 | 0 | 0
| 9180.01 | DOC IMCC Hot Water Piping Replacement | Jennifer K | 150000 |  | 150000 | 141508.42 | 124862.71 | 16645.71 | 8491.58 | 590.54
C | 9199.00 | DHS IMHI Reynolds Water Main Replacement | Jennie E. | 150737.42 |  | 150737.42 | 150737.42 | 150737.42 | 0 | 0
C | 9217.00 | DHS WRC Main Transformer Replacement | Jennifer K | 117671.8 |  | 117671.8 | 117671.8 | 117671.8 | 0 | 0
C | 9218.00 | DHS STS Kitchen Storage Roof Replacement | Jennifer K | 86054.48 |  | 86054.48 | 86054.48 | 86054.48 | 0 | 0
C | 9219.00 | DHS STS Maintenance Main Building Tuckpointing | Jennifer K | 121952.44 |  | 121952.44 | 121952.44 | 121952.44 | 0 | 0
C | 9226.00 | DCA MON Main House Site Work and Outbuilding Repairs | James T | 207100.61 |  | 207100.61 | 207100.61 | 207100.61 | 0 | 0
C | 9227.00 | DHS GRC 212-214 and 717-Main Road Tunnel Repairs | Doug C | 72267.06 |  | 72267.06 | 72267.06 | 72267.06 | 0 | 0
C | 9228.00 | DCA PGR Plum Grove Roof Replacement | James T | 71478.53 |  | 71478.53 | 71478.53 | 71478.53 | 0 | 0
C | 9229.00 | DOC NCCF R&D Floor Replacement | James T | 99268.95 |  | 99268.95 | 99268.95 | 99268.95 | 0 | 0
C | 9230.00 | DHS GRC Powerhouse Parking Lot Repair | Jennie E. | 294537.52 |  | 294537.52 | 294537.52 | 294537.52 | 0 | 0
C | 9231.00 | DAS CC Jessie Parker Water Infiltration Repair | James T | 259505.97 |  | 259505.97 | 259505.97 | 259505.97 | 0 | 0
C | 9232.00 | DCA TMVC Siding Replacement | James T | 84802.21 |  | 84802.21 | 84802.21 | 84802.21 | 0 | 0
C | 9233.00 | DHS GRC Building 105, 111 and 703 Tuckpointing | Doug C | 33179.1 |  | 33179.1 | 33179.1 | 33179.1 | 0 | 0
C | 9234.00 | DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs | Brad T | 453120.21 |  | 453120.21 | 453120.21 | 453120.21 | 0 | 0
C | 9235.00 | DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing | Brad T | 481175.96 |  | 481175.96 | 481175.96 | 481175.96 | 0 | 0
C | 9236.00 | DOC NCCF Food Warehouse Walk-in Freezer Replacement (Moved to MM20) | James T | 0 |  | 0 | 0 | 0 | 0 | 0
C | 9237.00 | DAS CC Hoover East Side Paver Repairs | James T | 255120.34 |  | 255120.34 | 255120.34 | 255120.34 | 0 | 0
| 9244.00 | IPBS JOH 6450 Corporate Dr. Roof Replacement | Jennifer K | 1077238.62 |  | 1077238.62 | 1062516.44 | 1021282.64 | 41233.8 | 14722.18 | 1923.69
C | 9245.00 | DOC CCF CTC NW and SW Porch Repairs | Brad T | 530800.84 |  | 530800.84 | 530800.84 | 530800.84 | 0 | 0
C | 9246.00 | DOC CCF Precast Walls and Window Sealing | Brad T | 451172.62 |  | 451172.62 | 451172.62 | 451172.62 | 0 | 0
C | 9247.00 | DHS IMHI Storage Bldg Roof Replacement | Jennie E. | 170176.39 |  | 170176.39 | 170176.39 | 170176.39 | 0 | 0
C | 9248.00 | DHS WRC Administration, Birches and Linden Court Tuckpointing | Jennifer K | 183186.71 |  | 183186.71 | 183186.71 | 183186.71 | 0 | 0
C | 9249.00 | DOC MPCF Front Steps Repair | James T | 500102.67 |  | 500102.67 | 500102.67 | 500102.67 | 0 | 0
C | 9250.00 | DOC MPCF Building 18 Roof Replacement | Brandon A | 152815.88 |  | 152815.88 | 152815.88 | 152815.88 | 0 | 0
C | 9251.00 | DPS P09 Parking Lot Replacement | James T | 269266.16 |  | 269266.16 | 269266.16 | 269266.16 | 0 | 0
C | 9252.00 | DPS P09 Window Replacement | James T | 80991.18 |  | 80991.18 | 80991.18 | 80991.18 | 0 | 0
C | 9253.00 | DOC FDCF Floyd and Bldg K Roof Replacement | Jennifer K | 0 |  | 0 | 0 | 0 | 0 | 0
C | 9254.00 | DHS GRC 712-714-716 Lacey Roof Replacements | Doug C | 1800 |  | 1800 | 1800 | 1800 | 0 | 0
C | 9255.00 | DOC NCF Bldg K and CRC Roof Replacement | Brad T | 0 |  | 0 | 0 | 0 | 0 | 0
C | 9256.00 | DOC ASP Vacuum Condensate System Replacement | Jennie E. | 319823.75 |  | 319823.75 | 319823.75 | 319823.75 | 0 | 0
C | 9257.00 | DAS CC Historical Building Floor Repair | Jennie E. | 778007.97 |  | 778007.97 | 778007.97 | 778007.97 | 0 | 0
C | 9258.00 | DAS CC Hoover East Side Ice Mitigation | James T | 42460.74 |  | 42460.74 | 42460.74 | 42460.74 | 0 | 0
C | 9259.00 | DAS CC Finkbine St Paving and Parking Lot 5 Replacement | Doug C | 688485.9 |  | 688485.9 | 688485.9 | 688485.9 | 0 | 0
| 9262.00 | DHS WRC Medical Center New Sprinkler System | Jennifer K | 837665.11 |  | 837665.11 | 821605.63 | 812568.54 | 9037.09 | 16059.48 | 1563.72
C | 9263.00 | DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214 | Jennie E. | 851050.11 |  | 851050.11 | 851050.11 | 851050.11 | 0 | 0
C | 9264.00 | DPS P10 Front Entrance Repair | James T | 29183.1 |  | 29183.1 | 29183.1 | 29183.1 | 0 | 0
C | 9265.00 | DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs | Jennie E. | 274134.78 |  | 274134.78 | 274134.78 | 274134.78 | 0 | 0
C | 9271.00 | DVA IVH Pedestrian Tunnel Water Infiltration | Brad T | 526030.69 |  | 526030.69 | 526030.69 | 526030.69 | 0 | 0
C | 9272.00 | DOC NCF CRC Facility Window Replacements | Brad T | 268187.55 |  | 268187.55 | 268187.55 | 268187.55 | 0 | 0
C | 9273.00 | DOC IMCC SNU Building Tuckpointing | Jennifer K | 14823.07 |  | 14823.07 | 14823.07 | 14823.07 | 0 | 0
C | 9274.00 | DHS WRC Myers Hall Chiller Replacement | Jennifer K | 269198.56 | 1562.3 | 270760.86 | 270760.86 | 270760.86 | 0 | 0 | 0
C | 9275.00 | DPS P12 Window Replacement | James T | 188608.81 |  | 188608.81 | 188608.81 | 188608.81 | 0 | 0
C | 9276.00 | DPS P12 Driveway Repairs | James T | 60799.39 |  | 60799.39 | 60799.39 | 60799.39 | 0 | 0
C | 9277.00 | DAS CC Main Switchgear Master Control Replacement | Jennifer K | 336796.33 |  | 336796.33 | 336796.33 | 336796.33 | 0 | 0
C | 9278.00 | DOC MPCF Elevator D | James T | 0 |  | 0 | 0 | 0 | 0 | 0
| 9279.00 | DHS WRC Campus Utility Decentralization Phase 1 | Jennifer K | 386023.27 |  | 386023.27 | 386023.27 | 380878.51 | 5144.76 | 0 | 789.76
| 9279.30 | DHS WRC Campus Utility Decentralization Phase 3 | Jennifer K | 266000 |  | 266000 | 265872.67 | 262717.17 | 3155.5 | 127.33 | 0
C | 9290.00 | DOC FDCF Bldg C Water Heater Replacement (29C20) | Jennifer K | 0 | 152210.17 | 152210.17 | 152210.17 | 152210.17 | 0 | 0
C | 9291.00 | DOC CCF Condensate Tank Replacement (29C20) | Brad T | 0 | 259551.33 | 259551.33 | 259551.33 | 259551.33 | 0 | 0
C | 9292.00 | DOC CCF CTC Roof Storm Damage 2022 (29C20) | Brad T | 0 | 359463.21 | 359463.21 | 359463.21 | 359463.21 | 0 | 0
C | 9299.00 | DAS ANK SHL Ductwork Replacement | Jennifer K | 1280.52 |  | 1280.52 | 1280.52 | 1280.52 | 0 | -1.0459e-11
C | 9302.00 | DOC ICIW Unit 9 Chiller Replacement | Brandon A | 258205.98 |  | 258205.98 | 258205.98 | 258205.98 | 0 | 0
C | 9303.00 | DOC NCCF Kitchen Grease Pit Replacement | James T | 295591.3 |  | 295591.3 | 295591.3 | 295591.3 | 0 | 0
| 9306.00 | DOC CCF Metal Roof Replacement | Brad T | 1175000 |  | 1175000 | 1175000 | 1116250 | 58750 | 0
| 9354.00 | DOC ASP LUC Plumbing Repairs Design | Jennie E. | 200000 |  | 200000 | 154800.57 | 139352.33 | 15448.24 | 45199.43 | 48.24
| 9364.00 | DAS MEBS House Structural Repairs | James T. | 186000 |  | 186000 | 35698.14 | 33698.14 | 2000 | 150301.86 | 0
C | 9365.00 | DAS MON Front Porch Column Repair/Replacement | James T. | 4044.57 |  | 4044.57 | 4044.57 | 4044.57 | 0 | 0
| 9366.00 | DOC NCCF IPI Sally Port Vehicle Gate | Jennie E. | 403000 |  | 403000 | 365243.02 | 68380.07 | 296862.95 | 37756.98 | 2163.13
| 9367.00 | DOE IPBS JOH 6535 Corporate Dr Roof Replacement | Brandon A. | 305000 |  | 305000 | 269939.24 | 265055.91 | 4883.33 | 35060.76 | 797.32
| 9368.00 | HHS IMHI Reynolds Bldg North Annex Roof Replacement | Jennie E. | 210000 |  | 210000 | 180758.13 | 58835.02 | 121923.11 | 29241.87 | 6.57
C | 9369.00 | HHS IMHI Plant Oberations Bldg Window Replacement | Jennie E. | 147783.65 |  | 147783.65 | 147783.65 | 147783.65 | 0 | 0
| 9387.00 | DOC MPCF IPI Building Stormwater Management | Brandon A. | 254000 |  | 254000 | 244248.03 | 216162.02 | 28086.01 | 9751.97 | 1169.76
| 9407.00 | DAS TH Carriage House Exterior Stair Replacement | James T. | 65442.13 |  | 65442.13 | 58442.13 | 52575.21 | 5866.92 | 7000 | 2366.53
C | 9420.00 | DAS CC Capitol West & Surrounding Landings Repairs | James T. | 130614.31 |  | 130614.31 | 130614.31 | 130614.31 | 0 | 0
|  | Major Maintenance Totals |  | 20877005.27 | 1855849.35 | 21674792.28 | 21321078.84 | 20712041.42 | 609037.42 | 353713.44
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 181057.07
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 534770.51
[6 empty] | Total funds Available |  |  | 21855849.35
[6 empty] | Total obligated by contract or PO |  |  | -21321078.84 | 534770.51
[6 empty] | Variance |  |  |  | 0
Note on E15: Huggins, Joni [DAS]: Re: 9997.22 Closing Inbox Gustafson, Scott 2:40 PM (14 minutes ago) to me Joni, Yes, please move Emily's August time to 9997.23, close 9997.22 and return any unused funds to MM22. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Tue, Aug 9, 2022 at 2:14 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good afternoon Scott, We need to close down 9997.22. Emily has time recorded in 8/1, 8/2 & 8/3. I believe this should be in 9997.23. 1) May I move Emily's time to 9997.23? 2) May I close 9997.22 and move the funds to MM22 pool? Thank you ~Joni
Note on E16: Jenkins, Jennifer [DAS]: Fwd: New MM Project Request Jennifer Kleene, Jennifer Thu, Aug 12, 4:39 PM (4 days ago) to me, Scott We would like to add funding to 9215.00 in a different fund and add funding to 8983.02 as shown below. Please let me know if you have any questions. Create a new 9215.00 DAS CC Grimes Lighting Replacement in MM20 for $925,000.00 Increase the budget for MM22 project 8983.02 by $1,400,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative2) Recently Jennifer had Finance add $1.4MM in funding to 8983.02 in MM22. Please return this $1.4MM in funding to the MM22 fund but allocate $1,000.000 in MM21 to 8983.02. Future CO's will be added to this fund. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services ---------- Forwarded message --------- From: Elliott, Jennie <jennie.elliott@iowa.gov> Date: Mon, Jun 12, 2023 at 1:35 PM Subject: Fwd: 8983.02 - SHB Roof and Skylight Replacement - Additional Funds To: DAS Finance Payables <das.finance.payables@iowa.gov> Cc: Gustafson, Scott [DAS] <scott.gustafson@iowa.gov> Please see the email string below. Per email please add an additional $160,000 to project 8983.02 - SHB Roof and Skylight Replacement in MM22. This will bring the total budget of that project to $3,170,592.36. Thank you, 8983.02 - Project Closeout - SHB Roof and Skylight Replacement (Smoke Purge) $Joni Elliott, Jennie Jan 28, 2024, 1:03 PM (18 hours ago) to me, Scott Can you please make the following changes and close out project 8983.02 in the following funds. MM21 - 8983.02 Please change PM Time Budget in "Contracted" line to $48,168.18 Please close the project and return $100,575.43 to the MM21 Fund MM22 - 8983.02 Please change PM Time Budget in "Contracted" line to $61,234.80 Please change eDAS Budget in "Contracted" line to $13,172.57 Please close the project and return $92,728.74 to the MM22 Fund
Note on E17: Jenkins, Jennifer [DAS]: Please also increase the budget for MM22 9054.03 by $300,000.00. MM22 Budget Changes Inbox Kleene, Jennifer 12:09 PM (9 minutes ago) to me, Scott MM22 Project 9054.03 - Please decrease the budget by $65,000.00 MM22 Project 9248.00 - Please decrease the budget by $20,000.00 Regards, Jennifer Regards, Jennifer Jennifer Kleene, Owner’s RepresentativeRe: MM22 Budget Changes Inbox Kleene, Jennifer 9:44 AM (0 minutes ago) to me, Scott Yes, I did, sorry! Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov On Wed, Jun 15, 2022 at 9:43 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Do you mean 9054.03 in MM22? ~Joni On Wed, Jun 15, 2022 at 8:48 AM Kleene, Jennifer <jennifer.kleene@iowa.gov> wrote: Please make the following changes: Decrease overall budget for 9054.02 by $175,000.00 Decrease overall budget for 9217.00 by $260,000.00 Decrease overall budget for 9218.00 by $18,000.00 Decrease overall budget for 9219.00 by $50,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E19: Huggins, Joni [DAS]: Budget Increase for MM22 9180.01 $Joni Kleene, Jennifer 8:57 AM (1 hour ago) to me, Scott Please increase the budget for MM22 9180.01 by $10,000.00 and let me know if you have any questions. Regards, Jennifer Jennifer Kleene Owner’s Representative MM22 9180.01 Budget Increase $Joni Kleene, Jennifer Mon, Nov 4, 12:53 PM (18 hours ago) to me, Scott Please increase the budget for MM22 9180.01 by $15,000.00. Regards, Jennifer
Note on E21: Huggins, Joni [DAS]: MM22 Budget Changes $Joni Kleene, Jennifer 8:48 AM (54 minutes ago) to me, Scott Please make the following changes: Decrease overall budget for 9054.02 by $175,000.00 Decrease overall budget for 9217.00 by $260,000.00 Decrease overall budget for 9218.00 by $18,000.00 Decrease overall budget for 9219.00 by $50,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Budget Changes FY23 Kleene, Jennifer 7:44 AM (41 minutes ago) to me, Scott Please decrease the PM Time for MM20 Project 9064.00 by $52.50 and then reduce the overall project budget by $8,451.83. Please decrease the budget for MM22 Project 9217.00 by $30,000.00. Please decrease the budget for MM22 Project 9248.00 by $65,000.00 Please decrease the budget for MM22 Project 9274.00 by $10,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 9217.00 Budget Reduction $Joni Kleene, Jennifer 7:56 AM (25 minutes ago) to me, Scott Please reduce the budget for MM22 9217.00 by $67,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 12:42 PM (31 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer
Note on E22: Huggins, Joni [DAS]: MM22 Budget Changes $Joni Kleene, Jennifer 8:48 AM (54 minutes ago) to me, Scott Please make the following changes: Decrease overall budget for 9054.02 by $175,000.00 Decrease overall budget for 9217.00 by $260,000.00 Decrease overall budget for 9218.00 by $18,000.00 Decrease overall budget for 9219.00 by $50,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.govRe: Please close MM22 Project 9218.00 Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> (sent by selma.durakovic@iowa.gov) Aug 4, 2022, 10:31 AM (7 days ago) to Jennifer, Scott Project #9218.00 has been closed & removed from the billing file. Thank you, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov On Tue, Jul 26, 2022 at 10:44 AM Kleene, Jennifer <jennifer.kleene@iowa.gov> wrote: All invoices have been paid and all PM time has posted, so please close project 9218.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E23: Huggins, Joni [DAS]: MM22 Budget Changes $Joni Kleene, Jennifer 8:48 AM (54 minutes ago) to me, Scott Please make the following changes: Decrease overall budget for 9054.02 by $175,000.00 Decrease overall budget for 9217.00 by $260,000.00 Decrease overall budget for 9218.00 by $18,000.00 Decrease overall budget for 9219.00 by $50,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Budget Adjustments $Joni Kleene, Jennifer 11:34 AM (2 hours ago) to me, Scott MM20 Project #9215.00 Please decrease the budget by $30,000 MM22 Project #9219.00 Please decrease the budget by $20,000 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close MM22 Project 9219.00 $Joni Kleene, Jennifer 9:07 AM (1 hour ago) to me, Scott All DAS costs have been posted and all invoices have been paid, so please closeout MM22 project 9219.00 and remove it from the billing sheet. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E24: Huggins, Joni [DAS]: 9226.00 - DCA MON Main House Site Work & Outbuilding Repairs - MM22 $Joni Trower, James Mar 12, 2025, 6:31 PM (12 hours ago) to me Finance - 1. Reduce MM22 PM Time $4,142.36 and return to the MM22 Pool Fund 2. Transfer $69,476.47 MM2 to the MM22 Pool Fund Thanks, James Trower, Licensed Architect, LEED AP
Note on E25: Huggins, Joni [DAS]: Project 9227.00 and 9259.00 - MM22 $Joni Carper, Douglas Wed, Jun 29, 2:48 PM (16 hours ago) to me, Scott Reduce the budget of 9227.00 by $300,000.00. Increase the budget of 9259.00 by $300,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Project 9227.00 and 9265.00 - MM22 $Joni Carper, Douglas 8:57 AM (2 minutes ago) to me, Scott 9227.00 - Decrease the budget by $40,000.00. 9265.00 - Increase the budget by $40,000.00 Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov MM22 Funding $Joni Carper, Douglas 7:16 AM (3 minutes ago) to me, Scott Project 9227.00: Decrease funding by $200,000.00. Project 9230.00: Increase funding by $40,000.00. Project 9256.00: Increase funding by $160,000.00. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.govMM22 Funding Inbox Carper, Douglas 8:46 AM (30 minutes ago) to me, Scott Project 9227.00: Decrease funding by $225,000.00. Project 9247.00: Increase funding by $225,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov MM22 Project 9227.00 DHS GRC 212-214 and 717-Main Road Tunnel Repairs $Joni Carper, Douglas Aug 12, 2022, 1:01 PM (3 days ago) to me, Scott This project can be closed and the balance of funds returned to MM22. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Re: MM22 9227.00 PM Time Corrections $Joni Carper, Douglas 2:53 PM (1 minute ago) to me If you can add the $10 to the budget and then close it would be great. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov On Mon, Sep 12, 2022 at 2:47 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi Doug In this project we are $10 short in PM Time to post the July correction that came through. Please advise Thank you ~Joni Will do, thanks!Will do.Done.
Note on E26: Huggins, Joni [DAS]: 9228.00 - DCA PGR Plum Grove Roof Replacement $Joni Trower, James Apr 7, 2022, 9:25 PM (9 hours ago) to me Finance - Please transfer $5,000 from project 9228.00 - DCA PGR Plum Grove Roof Replacement to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E27: Huggins, Joni [DAS]: Re: 9229.00 - DOC NCCF R&D Floor Replacement - Additional Project Funding (MM22) $Joni Trower, James 9:03 AM (5 minutes ago) to me Finance - Please increase funding by $24,000 in MM22 funds for project 9229.00 - DOC NCCF R&D Floor Replacement. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9229.00 - DOC NCCF R&D Floor Replacement - Close $Joni Trower, James Feb 25, 2023, 7:45 AM (2 days ago) to me Finance - Reduce PM Time by $664.53. Close project and return on funding to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E28: Huggins, Joni [DAS]: MM22 Funding $Joni Carper, Douglas 7:16 AM (5 minutes ago) to me, Scott Project 9227.00: Decrease funding by $200,000.00. Project 9230.00: Increase funding by $40,000.00. Project 9256.00: Increase funding by $160,000.00. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9230.00 - DHS GRC Powerhouse Parking Lot Repair FY24 Elliott, Jennie Sun, Sep 10, 5:04 PM (18 hours ago) to me, Scott Please Reduce PM Time to match the expended amount of $17,775.69 in project 9230.00. Upon completion, please close out the project and return any remaining funds to MM22. Thank you,
Note on E29: Huggins, Joni [DAS]: 9231.00 - DAS CC Jessie Parker Water Infiltration Repair - Increase Funding $Joni Trower, James Mon, Oct 3, 3:26 PM (18 hours ago) to me Finance - Please increase funding for project 9231.00 - DAS CC Jessie Parker Water Infiltration Repair by $80,000 (MM22). Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Close Projects $John Trower, James 3:23 PM (21 minutes ago) to me Finance - 9231.00 - DAS CC Jessie Parker Water Infiltration Repair Reduce PM Time by $272.71. Return all remaining MM22 funding to the MM22 pool fund. Close Project 9251.00 - DPS P09 Parking Lot Replacement Reduce PM Time by $509.40 Return all remaining MM22 funding to the MM22 pool fund. Close Project 9252.00 - DPS P09 Window Replacement Reduce PM Time by $750.18 Return all remaining MM22 funding to the MM22 pool fund. Close Project
Note on E30: Huggins, Joni [DAS]: 9232.00 - DCA TMVC Toolesboro Mounds Visitor Center Siding Replacement $Joni Trower, James Thu, Apr 7, 9:35 PM (9 hours ago) to me Finance - Please increase the MM22 funding for project 9232.00 - DCA TMVC Toolesboro Mounds Visitor Center Siding Replacement by $7,000. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E31: Huggins, Joni [DAS]: MM22 9233.00 DHS GRC Bldgs. 111, 703 & 705 Tuckpointing $Joni Carper, Douglas Aug 12, 2022, 11:24 AM (3 days ago) to me, Scott This project can be closed and the balance of funds returned to MM22. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov
Note on E32: Huggins, Joni [DAS]: Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov
Note on E33: Huggins, Joni [DAS]: Fwd: MM22 - Budget Increase Needed for 9235.00 - Newton CRC Tuckpointing $Joni Tonyan, Brad 11:08 AM (20 minutes ago) to me, Mirela, Scott, Brad DAS Finance, Please put an additional $250,000 into the following project 9235.00 under MM22. Thank you and please let me know when this is complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov ---------- Forwarded message --------- From: Gustafson, Scott <scott.gustafson@iowa.gov> Date: Thu, May 26, 2022 at 11:06 AM Subject: Re: MM22 - Budget Increase Needed for 9235.00 - Newton CRC Tuckpointing To: Tonyan, Brad <brad.tonyan@iowa.gov> Cc: Jennifer Kleene <jennifer.kleene@iowa.gov> Brad, You are ok to proceed with the additional $250,000. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Tue, May 24, 2022 at 2:11 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: Scott, The bids (4 - Bi-States, E&H, Pullman and TNT) came in pretty close to what we expected on project 9235.00 and I would like to include the base bid and (2) alternates which were low by Bi-States Masonry. To accept the low bid with alternates and include roughly a 5% construction contingency we would need an additional $240,000 but it might be wise to raise it by $250,000 or make the overall budget $500,000. Please confirm this is acceptable and I will request the shift with finance and have procurement issue the NOI. About to take the Denver State Capitol tour for the next few hours with NASFA. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Thu, Apr 28, 2022 at 11:56 AM Gustafson, Scott <scott.gustafson@iowa.gov> wrote: Brad, Per our discussion, we'll wait until we receive bids to adjust the budget. Let me know if you have any questions. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Mon, Apr 25, 2022 at 1:31 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: All, The following tuckpointing project at Newton was originally estimated by Ryan Companies with budget of roughly $600K and then Samuels estimated it lower. Anyways we feel the current budget of $250K needs to be raised to at least $400K but would rather it be $425K. It appears we have the funds available in MM22 and was looking for approval on an additional $175K to support the full scope prior to bid. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget a FF Tonyan, Brad Jul 17, 2023, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. Fwd: DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing: Action Required for Contract # MISC-9235.00-007 - 33523244901: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Jul 17, 2023, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general orgWith that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank you, Tonyan, Brad Jul 17, 2023, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank you, Tonyan, Brad Jul 17, 2023, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank you,wd: DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing: Action Required for Contract # MISC-9235.00-007 - 33523244901: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Mon, Jul 17, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank you,Fwd: DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing: Action Required for Contract # MISC-9235.00-007 - 33523244901: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Mon, Jul 17, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank youwd: DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing: Action Required for Contract # MISC-9235.00-007 - 33523244901: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Mon, Jul 17, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank youdjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Fwd: DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing: Action Required for Contract # MISC-9235.00-007 - 33523244901: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Mon, Jul 17, 3:28 PM (19 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $15,264.71 back to MM22 general org. Thank you
Note on E35: Durakovic, Selma [DAS]: Re: 9237.00 - Seedorff Masonry Inc. - 802 $Selma Trower, James 1:20 PM (45 minutes ago) to me Finance - Please add $130,000 in MM22 funds to project 9237.00. Thanks, James Project 9237.00 - Close $Joni Trower, James Tue, Jan 17, 9:11 PM (9 hours ago) to me Finance - Reduce PM Time by $2,600 and return to MM22 pool fund. Please close the project and return all remaining funds to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E36: Huggins, Joni [DAS]: Budget Reduction for MM22 9244.00 $Joni Kleene, Jennifer Oct 11, 2022, 3:30 PM (18 hours ago) to me, Scott Please reduce the overall budget for MM22 9244.00 by $140,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E37: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Project Budget Adjustments $Joni Herman, Josh Nov 21, 2022, 3:51 PM (15 hours ago) to me, Scott, Jennifer Please adjust the budget of the following projects: 9269.00 MM20 Give back $15,000 9245.00 MM22 Add $150,000 9257.00 MM22 Add $50,000 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov MM Project Additional Funding $Joni Re: MM Project Additional Funding $Joni Herman, Josh Dec 22, 2022, 1:01 PM (6 days ago) to me Finance Please add $250,000 instead of the $300,000 originally requested. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Budget Shifts / Adjustments $Joni Tonyan, Brad 11:36 AM (5 minutes ago) to me, Brad, Scott, Jennifer Finance, MM22 - Reduce budget $15K from project 9245.00 back to general fund org MM22. Fwd: DOC CCF CTC NE and SW Porch Repairs: State Change on Subcontractor Invoice #1: State of Iowa - Department of Administrative Services $Joni Tonyan, Brad 12:57 PM (36 minutes ago) to me, Brad Finance, I just processed the final PM time invoice balancing invoice in Procore to balance with the DAS billables. You can now please close out the entire project 9245.00 and return the remaining balance to MM22 funding org. All invoices are closed and paid in full. Thank you and let me know when this is done. Brad Tonyan, CPM, LEED G
Note on E38: Huggins, Joni [DAS]: 9246.00 Project Funding - MM22 Inbox Herman, Josh 3:10 PM (13 minutes ago) to me, Jennifer, Scott Please increase project funding to $500,000 total. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Fwd: DOC CCF Precast Walls and Window Sealing: Action Required for Contract #MISC-9246.00-007: Miscellaneous - DAS Costs - PM Time FY23 Tonyan, Brad Mon, Jul 17, 3:55 PM (18 hours ago) to me, Scott, Brad Finance, I am doing a "Dummy" invoice for time that has already hit in the Finance billables to update Procore for PM time on Project 9246.00. With that said all invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $40,991.11 back to MM22 general org.
Note on E39: Huggins, Joni [DAS]: MM22 Funding Inbox Carper, Douglas 8:46 AM (30 minutes ago) to me, Scott Project 9227.00: Decrease funding by $225,000.00. Project 9247.00: Increase funding by $225,000.00. Sincerely, Doug Douglas L. Carper, PE, Project Closeout - 9247.00 DHS IMHI Storage Bldg Roof Replacement - MM22 $Joni Elliott, Jennie Jan 7, 2024, 1:47 PM (17 hours ago) to me, Scott, Jennifer Please reduce PM Time in project 9247.00 to a total Contracted amount of $11,724.46. Following this please close out the project and return remaining funds to the Total Unassigned/Unallocated line for MM22. Total of returned funds should be $132,038.49. Thank you, Jennie Elliott
Note on E40: Huggins, Joni [DAS]: Budget Changes FY23 Kleene, Jennifer 7:44 AM (41 minutes ago) to me, Scott Please decrease the PM Time for MM20 Project 9064.00 by $52.50 and then reduce the overall project budget by $8,451.83. Please decrease the budget for MM22 Project 9217.00 by $30,000.00. Please decrease the budget for MM22 Project 9248.00 by $65,000.00 Please decrease the budget for MM22 Project 9274.00 by $10,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 Budget Changes Inbox Kleene, Jennifer 12:09 PM (9 minutes ago) to me, Scott MM22 Project 9054.03 - Please decrease the budget by $65,000.00 MM22 Project 9248.00 - Please decrease the budget by $20,000.00 Regards, Jennifer Please close MM22 9248.00 $John Kleene, Jennifer 9:57 AM (2 hours ago) to me, Scott All invoices have been paid and all DAS costs have posted, so please close Project 9248.00, remove from my billing sheet and return the remaining funds. Regards, Jennifer
Note on E41: Jurgenson, John [DAS]: 9249.00 - DOC MPCF Front Steps Repair Inbox Trower, James 12:50 PM (0 minutes ago) to me Finance - Please make the following changes to project 9249.00: 1. Return $300,000 in MM23 funding to the MM23 pool fund. 2. Increase the MM22 funding by $310,000.
Note on E42: Huggins, Joni [DAS]: Trower, James 11:36 AM (1 hour ago) to me Finance - Please see the below modifications for project 9250.00: MM22: Reduce PM Time by 5,755.92 Return $50,000 to the MM22 pool fund MM23: Increase project budget by $145,000 Thanks,
Note on E43: Huggins, Joni [DAS]: Fwd: 9251.00 - DPS P09 Parking Lot Replacement - Increase In Funding $Joni Trower, James Aug 17, 2022, 2:33 PM (17 hours ago) to me Finance - Please add $76,000 in MM22 funding to project 9251.00 - DPS P09 Parking Lot Replacement. Thanks, James Trower ---------- Forwarded message --------- From: Trower, James <james.trower@iowa.gov> Date: Tue, Aug 16, 2022 at 4:14 PM Subject: 9251.00 - DPS P09 Parking Lot Replacement - Increase In Funding To: Scott Gustafson <scott.gustafson@iowa.gov> Cc: Jennifer Kleene <jennifer.kleene@iowa.gov> Scott - Shive Hattery's cost opinion is for the construction budget is $223,000, and the low bid is $183,500. Samuels Group provided a quick MM total project budget (construction budget & soft costs) of $200,000. To enter a contract with the low bidder, Woodruff Construction, and have a 10% construction contingency, I will need an additional $76,000 in MM22 funding. Please let me know if this is acceptable, and I will transfer the funding. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Close Projects $John Trower, James 3:23 PM (21 minutes ago) to me Finance - 9231.00 - DAS CC Jessie Parker Water Infiltration Repair Reduce PM Time by $272.71. Return all remaining MM22 funding to the MM22 pool fund. Close Project 9251.00 - DPS P09 Parking Lot Replacement Reduce PM Time by $509.40 Return all remaining MM22 funding to the MM22 pool fund. Close Project 9252.00 - DPS P09 Window Replacement Reduce PM Time by $750.18 Return all remaining MM22 funding to the MM22 pool fund. Close Project
Note on E44: Huggins, Joni [DAS]: 9252.00 - DPS P09 Window Replacement - Increase Funding (MM22) $Joni Trower, James 10:39 AM (32 minutes ago) to me DAS Finance - Please increase funding for project 9252.00 - DPS P09 Window Replacement by $28,000 (MM22 Funding). Thanks, Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Close Projects $John Trower, James 3:23 PM (21 minutes ago) to me Finance - 9231.00 - DAS CC Jessie Parker Water Infiltration Repair Reduce PM Time by $272.71. Return all remaining MM22 funding to the MM22 pool fund. Close Project 9251.00 - DPS P09 Parking Lot Replacement Reduce PM Time by $509.40 Return all remaining MM22 funding to the MM22 pool fund. Close Project 9252.00 - DPS P09 Window Replacement Reduce PM Time by $750.18 Return all remaining MM22 funding to the MM22 pool fund. Close Project
Note on E45: Durakovic, Selma [DAS]: Budget Change for MM22 Projects 9253.00 and 9255.00 $Selma Kleene, Jennifer Jan 13, 2022, 2:53 PM (23 hours ago) to me, Scott, Brad We need to postpone MM22 projects 9253.00 (DOC FDCF Floyd and Grove Roof Replacement) and 9255.00 (DOC NCF Bldg K and CRC Roof Replacement) because roof materials are in short supply currently and would likely not be available for at least a year. We'd like to decrease the budget for both to $0 but keep the projects open as they will likely be funded again in FY23 if market conditions improve and we get the currently anticipated major maintenance appropriation. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E47: Durakovic, Selma [DAS]: Budget Change for MM22 Projects 9253.00 and 9255.00 $Selma Kleene, Jennifer Jan 13, 2022, 2:53 PM (23 hours ago) to me, Scott, Brad We need to postpone MM22 projects 9253.00 (DOC FDCF Floyd and Grove Roof Replacement) and 9255.00 (DOC NCF Bldg K and CRC Roof Replacement) because roof materials are in short supply currently and would likely not be available for at least a year. We'd like to decrease the budget for both to $0 but keep the projects open as they will likely be funded again in FY23 if market conditions improve and we get the currently anticipated major maintenance appropriation. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E48: Huggins, Joni [DAS]: MM22 Funding $Joni Carper, Douglas 7:16 AM (6 minutes ago) to me, Scott Project 9227.00: Decrease funding by $200,000.00. Project 9230.00: Increase funding by $40,000.00. Project 9256.00: Increase funding by $160,000.00. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov
Note on E49: Huggins, Joni [DAS]: Project Budget Adjustments $Joni Herman, Josh Nov 21, 2022, 3:51 PM (15 hours ago) to me, Scott, Jennifer Please adjust the budget of the following projects: 9269.00 MM20 Give back $15,000 9245.00 MM22 Add $150,000 9257.00 MM22 Add $50,000 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Herman, Josh 9:35 AM (3 minutes ago) to me, Jennie Add the $100,000 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov On Tue, Feb 21, 2023 at 9:31 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Josh I have this projects budget at $650,915.99 So would you like me to increase that to $750,000.00 or add $100,000.00 for a new total of $750,915.99? Thanks John On Tue, Feb 21, 2023 at 8:54 AM Herman, Josh <josh.herman@iowa.gov> wrote: Finance Please increase the overall project budget for 9257 in MM22 by $100,000 for an overall total of $750,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov ---------- Forwarded message --------- From: Gustafson, Scott <scott.gustafson@iowa.gov> Date: Tue, Feb 21, 2023 at 8:11 AM Subject: Re: Additional Funds - 9257.00 - State Historical Building Atrium Flooring To: Elliott, Jennie <jennie.elliott@iowa.gov> Cc: Herman, Josh [DAS] <josh.herman@iowa.gov>, Jennifer Kleene <jennifer.kleene@iowa.gov> Jennie, I spoke with Josh this morning. Please proceed with the additional funds to keep the project moving forward. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Wed, Feb 15, 2023 at 11:16 AM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Scott, We received the alternative funding prices back from the vendors for the "Select Grade, Plain Sawn, White Oak" wood flooring. It appears with this new information that we would still need an additional $101,000.00 in MM funding. This project is in funding source MM22 which currently has $236,562.29 unallocated. Are you okay with adding the additionally needed funds coming from MM22? Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-423-6383 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number will be 515-745-3244 beginning February 17, 2023 Fwd: Historical Building Flooring Additional Funds Request $Joni Elliott, Jennie Mon, Jun 5, 7:18 PM (18 hours ago) to me Per the email below please increase funding to Project 9257.00 DAS CC Historical Building Floor Repair in MM22 by $30,000. This will bring the total project budget 9257.00 - Historical Building Floor Repair Inbox Elliott, Jennie 3:23 PM (0 minutes ago) to me, Scott, Jennifer Please transfer an additional $10,000 in MM22 funding into project 9257.00 DAS CC Historical Building Floor Repair for a total budget of $790,641.44. Thank you,9257.00 - Historical Building Floor Repair Inbox Elliott, Jennie 3:23 PM (0 minutes ago) to me, Scott, Jennifer Please transfer an additional $10,000 in MM22 funding into project 9257.00 DAS CC Historical Building Floor Repair for a total budget of $790,641.44. le: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov o me, Scott, Jennifer Please transfer an additional $10,000 in MM22 funding into project 9257.00 DAS CC Historical Building Floor Repair for a total budget of $790,641.44. Thank you,
Note on E50: Jurgenson, John [DAS]: Trower, James 1:44 PM (22 minutes ago) to me Finance - See below changes for project 9258.00 - DAS CC Hoover East Side Ice Mitigation: 1. Return $67,653.31 in MM22 funding to the MM22 pool fund. 2. Set up MM21 funding for project 9258.00 - DAS CC Hoover East Side Ice Mitigation with $116,000 in MM21 funding. 3. Set up MM21 funding PM Time in the amount of $5,000. Please add the MM21 PM Time to my February billables spreadsheet. If you have any questions, please let me know. Trower, James 1:56 PM (0 minutes ago) to me John - Please increase the project budget for 9258.00 by $10,000 in MM22 funds. 9258.00 - DAS CC Hoover East Side Ice Mitigation - Close $Joni Trower, James Mon, May 27, 9:15 AM (22 hours ago) to me Finance - 9258.00 - DAS CC Hoover East Side Ice Mitigation MM21: Close project and return all MM21 funds to the MM21 pool fund MM22: Approve Invoice# 6 for Contract #DP-9258.00-002 Close project and return all MM22 funds to the MM22 pool fund
Note on E51: Huggins, Joni [DAS]: Project 9227.00 and 9259.00 - MM22 $Joni Carper, Douglas Wed, Jun 29, 2:48 PM (16 hours ago) to me, Scott Reduce the budget of 9227.00 by $300,000.00. Increase the budget of 9259.00 by $300,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9259.00 - Finkbine $Joni Elliott, Jennie Mar 27, 2023, 3:58 PM (17 hours ago) to me, Scott Can you please re-open project 9259.00 in fund MM22 and move $134.25 to that project. Unfortunately, an unpaid miscellaneous invoice has come up from work completed in November. I do not plan to charge any PM time to process this invoice. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov
Note on E52: Huggins, Joni [DAS]: Budget Changes $Joni Kleene, Jennifer 10:35 AM (4 minutes ago) to me, Scott For MM22 Project 9262.00, please increase the budget by $385,000.00. For MM22 Project 9274.00, please increase the budget by $75,000.00. For MM21 Project 8982.01, please increase the budget by $23,000.00. For MM20 Project 8982.01, please decrease the budget by $23,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 9262.00 Budget Reduction $Joni Kleene, Jennifer 7:45 AM (13 minutes ago) to me, Scott Please decrease the budget for MM22 9262.00 by $50,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E53: Huggins, Joni [DAS]: Project 9263.00 MM22 $Joni Carper, Douglas 10:22 AM (1 hour ago) to me, Scott, Jennifer Please decrease the budget for this project by $250,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9263.00 - DHS GRC New Fire Sprinkler Systems in Bldgs 105, 110, 111, & 214 $Joni Elliott, Jennie 8:48 AM (2 hours ago) to me, Scott Please Reduce PM Time to match the expended amount of $26,428.44 in project 9263.00. Upon completion, please close out the project and return any remaining funds to MM22. Thank you,
Note on E54: Huggins, Joni [DAS]: 9264.00 - DPS P10 Front Entrance Repair - Increase Funding $Joni Trower, James Dec 16, 2022, 12:30 PM (3 days ago) to me Finance - Please increase MM22 funding for project 9264.00 - DPS P10 Front Entrance Repair by $6,000. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9264.00 - DPS P10 Front Entrance Repair (MM22) $John Trower, James Attachments Apr 20, 2023, 3:28 PM (19 hours ago) to me Finance - See below items for 9264.00 - DPS P10 Front Entrance Repair (MM22): 1. Samuels Group #111CA invoiced their final invoice per invoice# 7390.52926400 Final Can you please close this contract? 2. Reduce PM Time by $1,302.58 3. If you are in agreement with item 1, please close this project and return on MM22 funding to the MM22 pool fund. Thanks,
Note on E55: Huggins, Joni [DAS]: Project 9227.00 and 9265.00 - MM22 $Joni Carper, Douglas 8:57 AM (2 minutes ago) to me, Scott 9227.00 - Decrease the budget by $40,000.00. 9265.00 - Increase the budget by $40,000.00 Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9265.00 - DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs - Project Closeout $John Elliott, Jennie 2:22 PM (11 minutes ago) to me, Scott Please close the PM Time line item in project 9265.00 - DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs - MM22 and return the remaining funds to the "unassigned/unallocated" line. Returned funds should be $28,515.20. Thank you, Jennie Elliott
Note on E56: Durakovic, Selma [DAS]: Re: RFB927100-01 - DVA IVH Pedestrian Tunnel Water Infiltration $Selma Tonyan, Brad 10:56 AM (1 hour ago) to me, Scott Sorry, It is project 9271.00 and is MM22. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Aug 30, 2022 at 10:48 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Brad, 9271.00 is in MM22, not MM21 as indicated in your email below. 9270.00 is in MM21 but it's Doug's project. Please advise. I just want to be sure we are increasing the budget in the correct project # as well as unit. Respectfully, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.go https://das.iowa.gov On Tue, Aug 30, 2022 at 9:25 AM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: Finance, Please increase the budget on project 9271.00 within MM21 by $80,000 which will make the new overall budget on this project $555,000. Thank you and please let me know when this is completed. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise obile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov From: Gustafson, Scott <scott.gustafson@iowa.gov> Date: Tue, Aug 30, 2022 at 9:23 AM Subject: Re: RFB927100-01 - DVA IVH Pedestrian Tunnel Water Infiltration To: Tonyan, Brad <brad.tonyan@iowa.gov> Cc: Michael Steen - Senior Project Manager <michaels@dcigroup-us.com> Brad, I am ok with proceeding with this based on the bids. Please request the budget increase from Finance. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.govttps://das.iowa.gov On Tue, Aug 30, 2022 at 9:15 AM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: Scott, Project 9271.00 - DVA IVH Pedestrian Tunnel Water Infiltration project bid this past Friday and was very close to the expected budget put forth by DCI Group and Shive Hattery. DCI Group and myself feel we shall award both scopes for the Courtyard and Laundry tunnel as the combined scope is a much better deal than just accepting one phase. Please see cost details below but in short we need another $66,400 for construction and $10,000 for CMCA as DCI Group, I am requesting an additional $80,000 to fully fund this project and hold roughly a 10% contingency. Procore Current Budget for Construction - $322,000: Shive Hattery 100% CD Estimate - Total project which includes Laundry Tunnel and Courtyard Tunnel - $407,450 total (Courtyard $207,100) (Laundry $200,350). TriCon - Apparent low bidder - both phase's - $388,400 - Courtyard only - $271,400 - Laundry area - $117,000 Thank you and reach out with any questions. Once you provide direction I will send finance an email to provide additional funding and have procurement issue an NOI. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov om: Construction Procurement, CPE <construction.procurementProject Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. ad Tonyan, CPM, LEED Green Associate, Owner Representative 9271.00 - IVH Pedestrian Tunnel Water Infiltration $Joni Tonyan, Brad Jul 17, 2023, 4:22 PM (16 hours ago) to me, Scott, Brad FinanceAll invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $21,221.64 back to MM22 general org. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Ju9271.00 - IVH Pedestrian Tunnel Water Infiltration $Joni Tonyan, Brad Jul 17, 2023, 4:22 PM (16 hours ago) to me, Scott, Brad Finance, All invoices have been paid on this project and finance can close the financials on this project and return the unspent funds of $21,221.64 back to MM22 general org. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov n 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov rprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov @iowa.gov> Date: Thu, Aug 25, 2022 at 3:07 PM Subject: RFB927100-01 - DVA IVH Pedestrian Tunnel Water Infiltration To: Michael Steen <michaels@dcigroup-us.com>, Brad Tonyan <brad.tonyan@iowa.gov> Good afternoon. Attached are the Bids we received for the aforementioned project and the Bid Summary. Please let me know when a decision has been made regarding the lowest responsible bidder. Thank you. Jeff -- Central Procurement Iowa Department of Administrative Services Hoover Building, 3rd Floor construction.procurement@iowa.gov
Note on E57: Huggins, Joni [DAS]: MM22 - 9272.00 - DOC NCF CRC Facility Window Replacements $Joni Tonyan, Brad 1:52 PM (16 minutes ago) to me, Scott, Jennifer, Brad Finance, Please increase the project budget on 9272.00 in MM22 from $450,000 to $750,000 as we are going to re-bid this project in the Winter-Spring 2023 time-frame. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Fwd: DOC NCF CRC Facility Window Replacements: State Change on Subcontractor Invoice #1: State of Iowa - Department of Administrative Services $John Tonyan, Brad 2:44 PM (5 minutes ago) to me, Brad Finance, Please close the PM time financials and the overall project on MM22 project 9272.00. I have just done the final pm time invoice in Procore to match that in the DAS financials. Please shift the remaining project balance of $9,467.33 back to the general fund org MM22 and close the financials for this project. Thank you,
Note on E58: Huggins, Joni [DAS]: Please close MM22 Project 9273.00 $Joni Kleene, Jennifer 11:31 AM (6 minutes ago) to me, Scott All invoices have been paid and all PM time has posted, so please close project 9273.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov
Note on E59: Huggins, Joni [DAS]: Budget Changes $Joni Kleene, Jennifer 10:35 AM (5 minutes ago) to me, Scott For MM22 Project 9262.00, please increase the budget by $385,000.00. For MM22 Project 9274.00, please increase the budget by $75,000.00. For MM21 Project 8982.01, please increase the budget by $23,000.00. For MM20 Project 8982.01, please decrease the budget by $23,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Budget Changes FY23 Kleene, Jennifer 7:44 AM (41 minutes ago) to me, Scott Please decrease the PM Time for MM20 Project 9064.00 by $52.50 and then reduce the overall project budget by $8,451.83. Please decrease the budget for MM22 Project 9217.00 by $30,000.00. Please decrease the budget for MM22 Project 9248.00 by $65,000.00 Please decrease the budget for MM22 Project 9274.00 by $10,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 9274.00 Budget Increase $Joni Kleene, Jennifer 10:41 AM (14 minutes ago) to me, Scott Please increase the budget for MM22 9274.00 by $5,000.00. Please also increase the PM Time budget by $2,300.00. Regards, Jennifer
Note on E60: Huggins, Joni [DAS]: Funding Transfers $Joni Trower, James Thu, Dec 22, 1:45 PM (6 days ago) to me Finance - 9276.00 - DPS P12 Driveway Repairs Transfer $200,000 in MM22 funds from project 9276.00 - DPS P12 Driveway Repairs to the MM22 pool fund. Set up MM23 funds in the amount of $700,000 from the MM23 pool fund. 9275.00 - DPS P12 Window Replacement Increase MM22 funds by $125,000 from the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9275.00 - DPS P12 Window Replacement $John Trower, James 10:35 AM (6 minutes ago) to me Finance - Project 9275.00: please return $45,000 in MM22 to the MM22 pool fund. Thanks, 9275.00 - DPS P12 Window Replacement - Close Project $Joni Trower, James Aug 13, 2024, 8:13 PM (11 hours ago) to me Finance - MM22 Funding for project 9275.00: 1. Reduce PM Time $1,085.69 and close PM Time 2. Return all remaining MM22 funds from project 9275.00 to the MM22 pool 3. Close Project Thanks, James Trower, Licensed Architect, LEED AP
Note on E61: Huggins, Joni [DAS]: Funding Transfers $Joni Trower, James Dec 22, 2022, 1:45 PM (6 days ago) to me Finance - 9276.00 - DPS P12 Driveway Repairs Transfer $200,000 in MM22 funds from project 9276.00 - DPS P12 Driveway Repairs to the MM22 pool fund. Set up MM23 funds in the amount of $700,000 from the MM23 pool fund. 9275.00 - DPS P12 Window Replacement Increase MM22 funds by $125,000 from the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James Mar 10, 2023, 4:39 PM (3 days ago) to me Finance - See below changes for project 9276.00 - DPS P12 Driveway Repairs: 1. Return $700,000 in MM23 funding to the MM23 pool fund (this funding source can be closed for project 9276.00). 2. Set up $470,000 in MM21 funding 3. Return $53,000 in MM22 funding to the MM22 pool fund. Thanks,
Note on E62: Huggins, Joni [DAS]: MM22 Project 9277.00 Budget Increase $Joni Kleene, Jennifer Mon, Aug 8, 1:21 PM (17 hours ago) to me, Scott Please increase the budget for MM22 Project 9277.00 by $150,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.govBudget Increase for MM22 9277.00 $Joni Kleene, Jennifer Mon, Mar 18, 4:28 PM (14 hours ago) to me, Scott Please increase the total budget for MM22 9277.00 by $15,000.00. Regards, Jennifer https://das.iowa.gov Split Project 9277.00 $Joni Kleene, Jennifer Fri, Dec 13, 12:30 PM (4 days ago) to me, Scott We have delayed the completion of MM22 project 9277.00 until sometime in Summer 2025, so we need to create a new 9277.00 in MM24 for $130,000.00. Once this is set up, please: Create a new PM Time budget of $1,500.00 in MM24 9277.00. Move remaining $147.82 in DCI Group CA PO#33525256901 to the new MM24 9277.00. Move remaining $732.80 in the Siemens-BAS Integration DO#33525320801 to the new MM24 9277.00. I will be sending through a change order for Cummins that will include moving the balance of their PO to the new MM24 9277.00. When all these changes are completed, the MM22 9277.00 project can be closed. Please let me know if you have any questions. Regards, Jennifer
Note on E63: Huggins, Joni [DAS]: Projects 9278.00 & 9224.00 Funding Modifications $Joni Trower, James Sep 27, 2022, 2:01 PM (2 days ago) to me Finance: Please see the below modifications that are needed: 1. Please close project 9278.00 - DOC MPCF Elevator D and transfer $487,500 in MM22 funds to the MM22 pool fund. 2. Please set up $1,845,000.00 in MM23 funds for project 9224.00 - DOC MPCF Elevator B C & D Replacements. 3. Please transfer $795,066.92 in MM21 funds from project 9224.00 - DOC MPCF Elevator B C & D Replacements to the MM21 pool fund. If you have any questions, please let me know. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E64: Jurgenson, John [DAS]: Budget Change and 2 New Projects Inbox Kleene, Jennifer 11:46 AM (48 minutes ago) to me, Scott Please decrease the budget for MM22 Project 9279.00 by $300,000.00. Once that is done, please set-up the following two new projects: Facility Project Title Budget OR Fund WRC DHS WRC Campus Utility Decentralization Phase 3 $200,000 JK MM22 Please use Project # 9279.30 WRC DHS WRC Fire Alarm System Replacement Phase 2 $100,000 JK MM21 Please use Project # 9294.01 Regards, Jennifer MM22 Budget Changes $John Kleene, Jennifer 9:07 AM (39 minutes ago) to me, Scott Please reduce the budget for MM22 9279.00 by $70,894.21. Please reduce the PM Time budget for MM22 9279.30 by $3,101.35 and remove it from my billables. Then please reduce the overall budget for MM22 9279.30 by $54,000.00. Regards, Jennifer
Note on E65: Jurgenson, John [DAS]: Budget Change and 2 New Projects Inbox Kleene, Jennifer 11:46 AM (54 minutes ago) to me, Scott Please decrease the budget for MM22 Project 9279.00 by $300,000.00. Once that is done, please set-up the following two new projects: Facility Project Title Budget OR Fund WRC DHS WRC Campus Utility Decentralization Phase 3 $200,000 JK MM22 Please use Project # 9279.30 WRC DHS WRC Fire Alarm System Replacement Phase 2 $100,000 JK MM21 Please use Project # 9294.01 Regards, Jennifer MM22 9279.30 Budget Increase Inbox Kleene, Jennifer 2:49 PM (1 minute ago) to me, Scott Please increase the budget for decentralization project 9279.30 by $120,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 Budget Changes $John Kleene, Jennifer 9:07 AM (39 minutes ago) to me, Scott Please reduce the budget for MM22 9279.00 by $70,894.21. Please reduce the PM Time budget for MM22 9279.30 by $3,101.35 and remove it from my billables. Then please reduce the overall budget for MM22 9279.30 by $54,000.00. Regards, Jennifer
Note on E67: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9291.00 MM22 Overall Budget $Joni Herman, Josh 11:28 AM (6 minutes ago) to me, Scott, Jennifer Please increase from $200,000 to $350,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Fwd: DOC CCF CTC Condensation Tank Replacement: State Change on Subcontractor Invoice #1: State of Iowa - Department of Administrative Services $Joni Tonyan, Brad Jun 11, 2024, 1:08 PM (19 hours ago) to me, Scott, Jennifer, Brad Finance, Now that project 9291.00 "DOC CCF Condensate Tank Replacement (29C20)" is complete and Final PM Time posted can you please complete the following tasks: 1. Funding Source MM22 - Please close the PM time and Misc. categories but leave the project open as we need to compile the overall costs so CCF can submit the 29C20 for reimbursement. Project to be closed once reimbursement is received. 2. Please return the remaining balance to the general funding org MM22 which is roughly $18,346.55 3. Compile financial backup and invoices for 29C20 submission Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E68: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9292.00 MM22 Increase $Joni Herman, Josh 10:47 AM (27 minutes ago) to me, Scott, Jennifer Finance Please increase funding of 9292.00 in MM22 to $375,000 total. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9292.00 - 29C20 Backup Invoice Compilation & PM Time $John Tonyan, Brad 12:39 PM (18 minutes ago) to me, Scott, Brad, Christopher Finance, Please shift remaining unspent funds of I believe $18,541.56 back to the general fund org MM22 once the PM is fixed.
Note on E70: Huggins, Joni [DAS]: 9302.00 Budget $Joni Herman, Josh 8:03 AM (36 minutes ago) to me Please add $70,000 to the budget for 9302.00 in MM22. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Project Budget Adjustments Inbox Adams, Brandon 11:50 AM (27 minutes ago) to me, Jennifer Finance, Please make the following adjustments; 9302.00 - MM22 Please reduce budget by $15,000 and put back into general MM22 org Thank you and please let me know when these adjustments are completed. 9302.00 MM22 Budget Increase Inbox Adams, Brandon 12:58 PM (0 minutes ago) to me, Jennifer, Scott Finance, Please increase the budget for 9302.00 MM22 DOC ICIW Unit 9 Chiller Replacement by $8,500. Regards, Brandon Adams
Note on E71: Huggins, Joni [DAS]: 9303.00 - DOC NCCF Kitchen Grease Pit Replacement $Joni Trower, James Wed, Nov 1, 6:01 PM (21 hours ago) to me Finance - Please increase the budget for project 9303.00 (MM22) by $24,000.
Note on E72: Huggins, Joni [DAS]: Moving funds between MM24 and MM22 $Joni Kleene, Jennifer Jan 27, 2025, 4:09 PM (18 hours ago) to me, Scott, Brad We would like to make some changes to move some expenses for project 9306.00 from MM24 to MM22. To accomplish this, please create a new 9306.00 in MM22 for $1,175,000.00 and split the existing Modern Buildings PO 33525292802 to move $1,175,000.00 in FY25 expenses from MM24 to MM22. Once the PO is split/expenses are moved, please decrease the MM24 budget for 9306.00 by $1,175,000.00. Brad will do a change order through Docusign to reflect this change in Procore as well. Please let me know if you have any questions or concerns with this plan. Regards, Jennifer
Note on E76: Huggins, Joni [DAS]: 9366.00 - DOC NCCF IPI Sally Port Vehicle Gate - MM22 Additional Funds $Joni Elliott, Jennie Fri, Dec 13, 9:20 AM (3 days ago) to me, Scott Please transfer an additional $125,000.00 from the Total Unassigned/Unallocated line in MM22 to project 9366.00 - DOC NCCF IPI Sally Port Vehicle Gate. Thank you, Jennie Elliott
Note on E77: Huggins, Joni [DAS]: 9367.00 MM22 DOE IPBS JOH 6535 Corporate Dr Roof Replacement $Joni Adams, Brandon 2:06 PM (12 minutes ago) to me, Jennifer Finance, Please reduce the budget for MM22 9367.00 DOE IPBS JOH 6535 Corporate Dr Roof Replacement by $175,000. Regards, Brandon Adams
Note on E78: Huggins, Joni [DAS]: MM22 - Project 9368.00 - HHS IMHI Reynolds Bldg North Annex Roof Replacement $Joni Elliott, Jennie Jan 25, 2025, 5:20 PM (2 days ago) to me, Scott, Jennifer Please return $290,000 from Project 9368.00 - HHS IMHI Reynolds Bldg North Annex Roof Replacement to the "Total Unassigned/Unallocated" line in Major Maintenance 2022. Thank you, Jennie Elliott
Note on E79: Huggins, Joni [DAS]: Re: 9369.00 - IMHI Plant Ops Windows - Timekey Enterprise, LLC - 802 - FY25 Inbox Elliott, Jennie 9:46 AM (0 minutes ago) to me, Jennifer, Scott Sorry about that. It looks like I emailed Scott and Jennifer and updated my budget in Procore, but forgot to email finance! Please increase budget for 9369.00 in MM22 by $105,000.00 for a total budget of $155,000.00 Thank you, Jennie Elliott
Note on E81: Huggins, Joni [DAS]: 9407.00 - DAS TH Carriage House Exterior Stair Replacement - Increase Budget $Joni Trower, James Fri, Oct 18, 6:16 PM (3 days ago) to me Finance - Please increase MM22 budget by $110,000.00. Thanks, James Trower, Licensed Architect, LEED AP 9407.00 - DAS TH Carriage House Exterior Stair Replacement - Funding $Joni Trower, James 11:50 AM (27 minutes ago) to me Finance - MM22 Funding: Return $ 169,557.87 to the MM22 pool fund. MM24 Funding: Set up $170,000 for project 9407.00 Set up $5,000 in PM Time The total amount in MM24 funding should be 170,000.00. Thanks, James Trower, Licensed Architect, LEED AP
Note on E82: Huggins, Joni [DAS]: 9420.00 - DAS CC Capitol West Stairs & Surrounding Landings Repairs $Joni Trower, James Thu, Jun 13, 4:53 PM (14 hours ago) to me Finance - Please increase the MM22 budget by $75,000. Increase PM Time by $6,000. Thanks, James Trower, Licensed Architect, LEED AP Trower, James 9:04 AM (35 minutes ago) to me Joni - Please increase the MM22 funds by 13,126.50 for project 9420.00. 9420.00 - DAS CC Capitol West Stairs & Surrounding Landings Repairs $Joni Trower, James 1:18 PM (2 hours ago) to me Finance - Please increase the MM22 budget for project 9420.00 by $18,720.00. Thanks, James Trower, Licensed Architect, LEED AP

## MM22 Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct. Codes-0017-335-MM22
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | 29C20 payment for IVH Fox water damage Project 9196.00 | IET010522100 | 2022-01-06 | 561522.6 | 561522.6
|  |  | Funds transferred with incorrect unit code | CDR 33522012800 | 2022-01-12 | -561522.6 | -561522.6
|  |  | IVH Roof Replacement-VA Payment Reimbursement 8965.01 for $383,906.23 and 9074.00 for 674,156.11 | JV1011122100 | 2022-01-11 | 1058062.34 | 1058062.34
| Total Requested | 0 | Total Transferred |  |  | 1058062.34 | 1058062.34

## RECAP #9997.22
Project Management Time
Project # 9997.22
| Program code 999722 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - NA
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 526230
C | PM TIME |  | 526230 | 526230 | 0
| Total Project Cost | 526230 | 526230 | 526230 | 0 | 0
Closed 08/09/22

## #9997.22 PM TIME
Project Management Time
Project # 9997.22
Program code 999722 |  |  | Major Program 3E01
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - NA
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
| 2021-07-01 | Budget amount | 526230 | 526230 |  |  | 526230
CDE 33522347904 | 2021-12-10 | Moving PM time expense from 9997.21 MM21 |  | 526230 | 222550 | 222550 | 303680
CDE 33522363900 | 2021-12-29 | Moving PM Time expense to MM22 9997.22 |  | 526230 | 25 | 222575 | 303655
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 526230 | 39100 | 261675 | 264555
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 526230 | 42400 | 304075 | 222155
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 526230 | 39950 | 344025 | 182205
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 526230 | 38025 | 382050 | 144180
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 526230 | 47450 | 429500 | 96730
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 526230 | 49480 | 478980 | 47250
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 526230 | 47250 | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  |  |  | 526230 |  | 526230 | 0
|  | Totals: | 526230 |  | 526230 |  | 0
Note on D9: Huggins, Joni [DAS]: Re: 9997.22 Closing Inbox Gustafson, Scott 2:40 PM (13 minutes ago) to me Joni, Yes, please move Emily's August time to 9997.23, close 9997.22 and return any unused funds to MM22. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Tue, Aug 9, 2022 at 2:14 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good afternoon Scott, We need to close down 9997.22. Emily has time recorded in 8/1, 8/2 & 8/3. I believe this should be in 9997.23. 1) May I move Emily's time to 9997.23? 2) May I close 9997.22 and move the funds to MM22 pool? Thank you ~Joni

## RECAP #8983.02
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
| Program code 898302 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 3077863.62
| Additional Funds Recv'd | 25000
C | Ball Team, LLC |  | 2799554.88 | 2799554.88 | 0
C | PM TIME |  | 61234.8 | 61234.8 | 0
C | eDAS |  | 13172.57 | 13172.57 | 0
C | Misc. |  | 0 | 0 | 0
C | Waldinger Corporation |  | 6595.51 | 6595.51 | 0
C | Holmes Murphy |  | 8566 | 8566 | 0
C | Ryan Companies |  | 137813.25 | 137813.25 | 0
C | Neumann Monson |  | 39301.44 | 39301.44 | 0
C | W.W. Grainger |  | 576.66 | 576.66 | 0
C | ATC Group Services LLC |  | 0 | 0 | 0
C | Terracon Consultants |  | 7007.5 | 7007.5 | 0
C | Waldinger Corporation (2) |  | 19712.2 | 19712.2 | 0
C | Midwest Caulking |  | 4000 | 4000 | 0
C | Baker Group |  | 5328.81 | 5328.81 | 0
| Total Project Cost | 3102863.62 | 3102863.62 | 3102863.62 | 0 | 0
Closed 01/29/2024

## #8983.02 Funds Rec'd
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Funds Received
Acct Codes 0017-335-MM22-0657
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Reimbursements from Neumann Monson | CR 00524199101 | 2023-07-18 | 25000 | 25000
| Total Requested | 0 | Total Transferred |  |  | 25000 | 25000

## #8983.02 Ball Team
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Ball Team, LLC |  |  | Vendor: 00003090419
Acct. Codes-0017-335-MM22-9255 |  |  | RFB 1820335002
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split w/ MM21 & R20M
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522161200 | 2021-07-14 | Rolled to FY22 and moved from MM19, MM20 and MM21 | 2568365.33 | 2568365.33 |  |  | 2568365.33
PO 33522161200 | 2021-09-09 | Reallocate between MM19 & MM22 | -111517.45 | 2456847.88 |  | 0 | 2456847.88
PRC 3352216PA1200 | 2021-09-28 | Inv. 21-040 - 1 (Split betwwen MM19, MM20 & MM22) |  | 2456847.88 | 27118.7 | 27118.7 | 2429729.18
PO 33522161200 | 2021-10-15 | CO 1 (100% to MM22) | -84486 | 2372361.88 |  | 27118.7 | 2345243.18
PRC 3352216PB1200 | 2021-10-22 | Inv. 21-040-2 (Split between DA18, MM19, MM20 & MM22) |  | 2372361.88 | 27812.2 | 54930.9 | 2317430.98
PRC 3352216PC1200 | 2021-11-22 | Inv. 21-040-3 (Split between DA18, MM19, MM20 & MM22) |  | 2372361.88 | 178517.35 | 233448.25 | 2138913.63
PO 33522161200 | 2021-11-23 | CO 2 (100% to MM22) | 4651 | 2377012.88 |  | 233448.25 | 2143564.63
PRC 3352216PD1200 | 2021-12-17 | Inv. 21-040-4 (Split between DA18, MM19, MM20 & MM22) |  | 2377012.88 | 116554.64 | 350002.89 | 2027009.99
PO 33522161200 | 2022-01-20 | CO 3 (100% to MM22) | 98303 | 2475315.88 |  | 350002.89 | 2125312.99
PRC 3352216PE1200 | 2022-01-20 | Inv. 21-040-5 (Split Between MM19, MM20, MM22) |  | 2475315.88 | 103659.85 | 453662.74 | 2021653.14
PO 33522161200 | 2022-02-24 | CO 4 (Split between MM22, MM21 & R20M) | 24474 | 2499789.88 |  | 453662.74 | 2046127.14
PRC 3352216PF1200 | 2022-02-26 | Inv. 21-040-6 (Split Between MM19, MM20, MM22) |  | 2499789.88 | 167923.95 | 621586.69 | 1878203.19
PO 33522161200 | 2022-03-16 | CO 5 (100% to MM22) | 51275 | 2551064.88 |  | 621586.69 | 1929478.19
PRC 3352216PG1200 | 2022-03-23 | Inv. 21-040-7 (Split Between MM19, MM20, MM22) |  | 2551064.88 | 114535.9 | 736122.59 | 1814942.29
PO 33522161200 | 2022-04-06 | CO 6 (100% to MM22) | 32117 | 2583181.88 |  | 736122.59 | 1847059.29
PRC 3352216PH1200 | 2022-05-02 | Inv. 21-040-8 (Split Between MM19, MM20, MM22) |  | 2583181.88 | 199680.93 | 935803.52 | 1647378.36
PO 33522161200 | 2022-05-10 | CO 7 (Split between MM19 & MM22) | -67732 | 2515449.88 |  | 935803.52 | 1579646.36
PRC 3352216PI1200 | 2022-05-19 | Inv. 21-040-9 (Split Between MM19, MM20, MM22) |  | 2515449.88 | 38073.15 | 973876.67 | 1541573.21
PRC 3352216PJ1200 | 2022-06-18 | Inv. 8983.02-10 (Split between MM20 & MM22) |  | 2515449.88 | 200853.9 | 1174730.57 | 1340719.31
PO 33522161200 | 2022-06-28 | CO #8 (100% to MM22) | 44728.5 | 2560178.38 |  | 1174730.57 | 1385447.81
PRC 3352216PK1200 | 2022-07-22 | Inv. 8983.02-11 (Split between MM20, MM21 & MM22) |  | 2560178.38 | 163864.39 | 1338594.96 | 1221583.42 | FY22
PO 33523161200 | 2022-08-10 | Rolled to FY23 | 0 | 2560178.38 |  | 1338594.96 | 1221583.42
PRC 3352316PL1200 | 2022-08-23 | Inv. 8983.02-12 (Split between MM20 & MM22) |  | 2560178.38 | 160210.63 | 1498805.59 | 1061372.79
PO 33523161200 | 2022-08-31 | CO #9 (100% to MM22) | 10768.5 | 2570946.88 |  | 1498805.59 | 1072141.29
PO 33523161200 | 2022-09-16 | CO #10 (Split between MM21 & MM22) | 6289 | 2577235.88 |  | 1498805.59 | 1078430.29
PRC 3352316PM1200 | 2022-09-23 | Inv. 8983.02-13 (Split between MM20 & MM22) |  | 2577235.88 | 222835.73 | 1721641.32 | 855594.56
PO 33523161200 | 2022-10-05 | CO #11 (100% to MM22) | 6638 | 2583873.88 |  | 1721641.32 | 862232.56
PRC 3352316PN1200 | 2022-10-27 | Inv. 8983.02-14 (Split between MM20 & MM22) |  | 2583873.88 | 234859.91 | 1956501.23 | 627372.65
PRC 3352316PO1200 | 2022-11-16 | Inv. 8983.02-15 (Split between MM20 & MM22) |  | 2583873.88 | 206531.34 | 2163032.57 | 420841.31
PO 33523161200 | 2022-12-15 | CO #12 (Split between (MM21 & MM22) | 2807 | 2586680.88 |  | 2163032.57 | 423648.31
PRC 3352316PP1200 | 2022-12-15 | Inv. 8983.02-16 (Split between MM20 & MM22) |  | 2586680.88 | 45036.35 | 2208068.92 | 378611.96
PRC 3352316PQ1200 | 2023-01-27 | Inv. 8983.02-17(Split between MM20, MM21, MM22, R20M) |  | 2586680.88 | 156436.69 | 2364505.61 | 222175.27
PO 33523161200 | 2023-02-03 | CO #13 (100% to MM22) | -332 | 2586348.88 |  | 2364505.61 | 221843.27
PRC 3352316PR1200 | 2023-02-17 | Inv. 8983.02-18(Split between MM20, MM21, MM22) |  | 2586348.88 | 85127.95 | 2449633.56 | 136715.32
PRC 3352316PS1200 | 2023-03-09 | Inv. 8983.02-19(Split between MM21 & MM22) |  | 2586348.88 | 33667.95 | 2483301.51 | 103047.37
PO 33523161200 | 2023-03-22 | CO #14 (100% to MM21) | 0 | 2586348.88 |  | 2483301.51 | 103047.37
PRC 3352316PT1200 | 2023-04-18 | Inv. 8983.02-20 (100% to MM21) |  | 2586348.88 | 0 | 2483301.51 | 103047.37
PO 33523161200 | 2023-04-20 | CO #15 (100% to MM21) | 0 | 2586348.88 |  | 2483301.51 | 103047.37
PRC 3352316PU1200 | 2023-05-15 | Inv. 8983.02-21 (100% to MM21) |  | 2586348.88 | 0 | 2483301.51 | 103047.37
PO 33523161200 | 2023-05-17 | CO #16 (100% to MM22) | 5996 | 2592344.88 |  | 2483301.51 | 109043.37
PO 33523161200 | 2023-06-12 | CO #17 (Split between MM21 and R20M) | 0 | 2592344.88 |  | 2483301.51 | 109043.37
PRC 3352316PV1200 | 2023-06-12 | Inv. 8983.02-22 (Split between MM21 and MM22) |  | 2592344.88 | 40633.2 | 2523934.71 | 68410.17
PO 33523161200 | 2023-06-19 | CO #18(100% to MM22) | 207210 | 2799554.88 |  | 2523934.71 | 275620.17
PO 33523161200 | 2023-06-30 | CO #19(100% to MM21) | 0 | 2799554.88 |  | 2523934.71 | 275620.17
PRC 3352316PW1200 | 2023-08-02 | Inv. 8983.02-23 (Split between MM21, MM22 & R20M) |  | 2799554.88 | 17697 | 2541631.71 | 257923.17 | FY23
PO 33524161200 | 2023-08-18 | Roll to FY24 | 0 | 2799554.88 |  | 2541631.71 | 257923.17
PRC 3352416PX1200 | 2023-08-22 | Inv. 8983.02-24 (Split between MM21 and MM22) |  | 2799554.88 | 228201.17 | 2769832.88 | 29722
PRC 3352416PY1200 | 2023-09-18 | Inv. 8983.02-25 (Split between MM21 and MM22) |  | 2799554.88 | 18931 | 2788763.88 | 10791
PO 33524161200 | 2023-10-11 | CO #20 (100% to MM21) | 0 | 2799554.88 |  | 2788763.88 | 10791
PO 33524161200 | 2023-10-26 | CO #21 (100% to MM21) | 0 | 2799554.88 |  | 2788763.88 | 10791
PRC 3352416PZ1200 | 2024-01-08 | Inv. 8983.02-26_Final (Split between MM21 and MM22 &R20M) |  | 2799554.88 | 10791 | 2799554.88 | -4.3656e-10
|  | Totals: | 2799554.88 |  | 2799554.88 |  | 0
|  | 8983.01 DA18 (Closed 12/21/2021) | 550000 |  | 550000 |  | 0
|  | 8983.02 MM19 (Closed 05/19/2022) | 1340558.12 |  | 1340558.12 |  | 0
|  | 8983.02 MM20(Closed 02/17/2023) | 3300000 |  | 3300000 |  | 0
|  | 8983.02 R20M | 19166 |  | 19166 |  | 0
|  | 8983.02 MM21 | 659337.59 |  | 659337.59 |  | 0
|  | Total Contract: | 8668616.59 |  | 8668616.59 |  | 0
***Stored Materials Breakdown. Current store materials are subtracted from the invoice totals****
|  |  | Store Materials | Store Materials | C**+E**-D**
|  | Total Payment | Previous Invoice | Current Invoice | Actual Payment
3352216PA1200 | 2021-09-28 | 508570.15 | 0 | 71250 | 579820.15
3352216PB1200 | 2021-10-22 | 394679.55 | 71250 | 71250 | 394679.55
3352216PC1200 | 2021-11-22 | 529669.65 | 71250 | 133000 | 591419.65
3352216PD1200 | 2021-12-17 | 824176.29 | 133000 | 99750 | 790926.29
3352216PE1200 | 2022-01-20 | 445093.65 | 99750 | 0 | 345343.65
3352216PF1200 | 2022-02-26 | 446448.72 | 0 | 79583.4 | 526032.12
3352216PG1200 | 2022-03-23 | 362618.9 | 79583.4 | 349079.4 | 632114.9
3352216PH1200 | 2022-05-02 | 654657.42 | 349079.4 | 531586.26 | 837164.28
3352216PI1200 | 2022-05-19 | 303631.95 | 531586.26 | 599382.06 | 371427.75
3352216PJ1200 | 2022-06-18 | 830844.41 | 599382.06 | 165580.71 | 397043.06
3352216PK1200 | 2022-07-22 | 445224.5 | 165580.71 | 232978.95 | 512622.74
3352316PL1200 | 2022-08-23 | 293685.63 | 232978.95 | 232978.95 | 293685.63
3352316PM1200 | 2022-09-23 | 641842.83 | 232978.95 | 20622.15 | 429486.03
3352316PN1200 | 2022-10-27 | 396281.01 | 20622.15 | 5637.3 | 381296.16
3352316PO1200 | 2022-11-16 | 265604.24 | 5637.3 | 3685.05 | 263651.99
3352316PP1200 | 2022-12-15 | 72990.3 | 3685.05 | 0 | 69305.25
3352316PQ1200 | 2023-01-27 | 176523.69 | 0 | 61952.35 | 238476.04
3352316PR1200 | 2023-02-17 | 205082.69 | 61952.35 | 40908.35 | 184038.69
3352316PS1200 | 2023-03-09 | 153082.08 | 40908.35 | 22624 | 134797.73
3352316PT1200 | 2023-04-18 | 78843.73 | 22624 | 22624 | 78843.73
3352316PU1200 | 2023-05-15 | 110554.35 | 22624 | 22624 | 110554.35
3352316PV1200 | 2023-06-12 | 178976.3 | 22624 | 0 | 156352.3
3352416PX1200 | 2023-08-22 | 228201.17 | 0 |  | 228201.17
3352416PY1200 | 2023-09-18 |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0

## #8983.02 PM TIME
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 861D
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 50642.44 | 50642.44 |  |  | 50642.44
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 50642.44 | 1900 | 1900 | 48742.44
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 50642.44 | 2900 | 4800 | 45842.44
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 50642.44 | 3325 | 8125 | 42517.44
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 50642.44 | 2677.5 | 10802.5 | 39839.94
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 50642.44 | 3500 | 14302.5 | 36339.94
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 50642.44 | 1325 | 15627.5 | 35014.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 50642.44 | -1325 | 14302.5 | 36339.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 50642.44 | 1457.5 | 15760 | 34882.44
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 50642.44 | 2777.5 | 18537.5 | 32104.94
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 50642.44 | 1980 | 20517.5 | 30124.94
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 50642.44 | 2090 | 22607.5 | 28034.94
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 50642.44 | 3107.5 | 25715 | 24927.44
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 758.5 | 51400.94 | 758.5 | 26473.5 | 24927.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 2114.82 | 53515.76 | 2114.82 | 28588.32 | 24927.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 1265.68 | 54781.44 | 1265.68 | 29854 | 24927.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1316.03 | 56097.47 | 1316.03 | 31170.03 | 24927.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 2133.17 | 58230.64 | 2133.17 | 33303.2 | 24927.44
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 58230.64 | 5586.17 | 38889.37 | 19341.27
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 58230.64 | 318.52 | 39207.89 | 19022.75
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 58230.64 | 2792.41 | 42000.3 | 16230.34
CDE 33523044800 | 2023-02-13 | 9500 | Move PM time expense from MM20 to MM22 8983.02 |  | 58230.64 | 547.82 | 42548.12 | 15682.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 179.97 | 58410.61 | 179.97 | 42728.09 | 15682.52
CDE 33523075202 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 692.16 | 59102.77 | 692.16 | 43420.25 | 15682.52
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 518.31 | 59621.08 | 518.31 | 43938.56 | 15682.52
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 220.05 | 59841.13 | 220.05 | 44158.61 | 15682.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 557.95 | 60399.08 | 557.95 | 44716.56 | 15682.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 835.72 | 61234.8 | 835.72 | 45552.28 | 15682.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 61234.8 | 960.89 | 46513.17 | 14721.63
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 61234.8 | 5826.9 | 52340.07 | 8894.73
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 61234.8 | 906.2 | 53246.27 | 7988.53
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 61234.8 | 517.47 | 53763.74 | 7471.06
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 61234.8 | 26.45 | 53790.19 | 7444.61
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 61234.8 | 184.8 | 53974.99 | 7259.81
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 61234.8 | 138.03 | 54113.02 | 7121.78
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 61234.8 | 1239.6 | 55352.62 | 5882.18
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 61234.8 | 448.67 | 55801.29 | 5433.51
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 61234.8 | 2505.8 | 58307.09 | 2927.71
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 61234.8 | 167.25 | 58474.34 | 2760.46
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 61234.8 | 1160.6 | 59634.94 | 1599.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 61234.8 | 94.64 | 59729.58 | 1505.22
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 61234.8 | 757.8 | 60487.38 | 747.42
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 61234.8 | 89.82 | 60577.2 | 657.6
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 61234.8 | 657.6 | 61234.8 | 5.5707e-12
[5 empty] | 61234.8 |  | 61234.8 | 5.5707e-12
[5 empty] | 61234.8 |  | 61234.8 | 5.5707e-12
[5 empty] | 61234.8 |  | 61234.8 | 5.5707e-12
|  |  | Totals: | 61234.8 |  | 61234.8 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Adjustment $Joni Herman, Josh Fri, Feb 18, 8:28 AM (3 days ago) to me 8983.02 in MM21 Please increase from $5,000 to $10,000. 8983.02 in MM22 Please create for $20,000 Thank you, Josh PM Time Updates $Joni From: Elliott, Jennie <jennie.elliott@iowa.gov> Date: Tue, Mar 21, 2023 at 10:40 AM Subject: Re: 8983.02 MM22 PM time budget To: Caldwell, Jennifer <jennifer.jenkins@iowa.gov>, DAS Finance Payables Infrastructure <dasfinanceinfrastructure@iowa.gov> lease increase the PM time in MM22 for project 8983.02 to $75,000. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244! Thu, Dec 1, 10:33 AM (23 Please update the following: 8983.02 MM22 Add $4,500 to $30,000 total 9223.00 DA22 Add $5,000 for $30,000 total Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Josh Herman CPM, Owner Representative Iowa Department of Administrative Services eneral Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time for September $Joni Herman, Josh 8:53 AM (5 hours ago) to me 8983.02 in MM22 Please add $5,500. 9306.00 in MM23 Please set at $8,800 9313.00 in DA23 Please set at $4,200. 9246.00 in MM22 Please change to $10,000 total. 9245.00 in MM22 Please change to $10,000 total. 9287.00 in MM21 Please change to $10,000 total. 9268.00 in MM20 Please add $1,100. Thank you, Josh Josh Herman CPM, Owner Representative General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov Re: PM Time for September $Joni Herman, Josh 8:53 AM (5 hours ago) 8983.02 in MM22 Please add $5,500. 9306.00 in MM23 Please set at $8,800 9313.00 in DA23 Please set at $4,200. 9246.00 in MM22 Please change to $10,000 total. 9245.00 in MM22 Please change to $10,000 total. 9287.00 in MM21 Please change to $10,000 total. 9268.00 in MM20 Please add $1,100. Thank you, Josh sh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov PM Time Updates $Joni Herman, Josh Thu, Dec 1, 10:33 AM Please update the following: 8983.02 MM22 Add $4,500 to $30,000 total 9223.00 DA22 Add $5,000 for $30,000 total Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: MM22 PM Time 8983.02 FY23 Herman, Josh Wed, Jan 18, 8:43 PM (14 hours ago) to me Please increase the eDAS tab by $2,500 and the PM Time by $7,500. Thank you, Josh Josh Herman CPM, Owner Representative https://das.iowa.gov 21, 10:40 AM (2 days ago) to Jennifer, me Please increase the PM time in MM22 for project 8983.02 to $75,000. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244! Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: 8983.02 MM22 PM time budget $Joni FY23 Elliott, Jennie Tue, Mar 21, 10:40 AM (2 days ago) to Jennifer, me Please increase the PM time in MM22 for project 8983.02 to $75,000. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244! 8983.02 CC SHB Roof and Skylight - MM22 $Joni Elliott, Jennie 9:40 AM (20 minutes ago) to me Can we please reduce the PM time budget in 8983.02 CC SHB Roof and Skylight - MM22 from $85,592.36 to $65,592.36. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov 8983.02 - Project Closeout - SHB Roof and Skylight Replacement (Smoke Purge) $Joni Elliott, Jennie Sun, Jan 28, 1:03 PM (18 hours ago) to me, Scott Can you please make the following changes and close out project 8983.02 in the following funds. MM21 - 8983.02 Please change PM Time Budget in "Contracted" line to $48,168.18 Please close the project and return $100,575.43 to the8983.02 - Project Closeout - SHB Roof and Skylight Replacement (Smoke Purge) $Joni Elliott, Jennie Jan 28, 2024, 1:03 PM (18 hours ago) to me, Scott Can you please make the following changes and close out project 8983.02 in the following funds. MM21 - 8983.02 Please change PM Time Budget in "Contracted" line to $48,168.18 Please close the project and return $100,575.43 to the MM21 Fund MM22 - 8983.02 Please change PM Time Budget in "Contracted" line to $61,234.80 Please change eDAS Budget in "Contracted" line to $13,172.57 Please close the project and return $92,728.74 to the MM22 Fund MM21 Fund MM22 - 8983.02 Please change PM Time Budget in "Contracted" line to $61,234.80 Please change eDAS Budget in "Contracted" line to $13,172.57 Please close the project and return $92,728.74 to the MM22 Fund

## #8983.02 eDAS
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  |  | Major Program 4E02
eDAS |  |  |  | Internal documents
eDAS
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13172.57 | 13172.57 |  |  | 13172.57
IET DAS202202115300001 | 2021-09-08 | 2507 | Electrical Order #207125004 Inv. DAS2022021153 |  | 13172.57 | 62.01 | 62.01 | 13110.56
IET DAS202203115300001 | 2021-10-07 | 2507 | Locksmith Order #207125935 Inv. DAS2022031153 |  | 13172.57 | 54.86 | 116.87 | 13055.7
IET DAS202203115300001 | 2021-10-07 | 2507 | Fire Watc Order #207125050 Inv. DAS2022031153 |  | 13172.57 | 478.24 | 595.11 | 12577.46
IET DAS202203115300001 | 2021-10-07 | 2507 | Space Planning Services Inv. DAS2022031153 |  | 13172.57 | 42.5 | 637.61 | 12534.96
IET DAS202204115300001 | 2021-11-05 | 2507 | Fire Watch Service Order #207125464 |  | 13172.57 | 59.78 | 697.39 | 12475.18
IET DAS202204115300001 | 2021-11-05 | 2507 | Locksmith & Key Services Order #207125021 |  | 13172.57 | 490.6 | 1187.99 | 11984.58
IET DAS202204115300001 | 2021-11-05 | 2507 | Locksmith & Key Services Order #207125140 |  | 13172.57 | 1006.14 | 2194.13 | 10978.44
IET DAS202204115300001 | 2021-11-05 | 2507 | Electrical Services Order #207125236 |  | 13172.57 | 73.77 | 2267.9 | 10904.67
IET DAS202204115300001 | 2021-11-05 | 2507 | Carpentry Order #207125207 |  | 13172.57 | 1076.74 | 3344.64 | 9827.93
IET 335FY22898302 | 2022-01-17 | 9500 | ICN Iowa Communications Network Invoice #631096 |  | 13172.57 | 420 | 3764.64 | 9407.93
IET DAS202208115300001 | 2022-03-07 | 2507 | Firewatch #207128592 & 207129061 Inv. DAS2022081153 |  | 13172.57 | 986.37 | 4751.01 | 8421.56
IET DAS202209115300001 | 2022-04-08 | 2507 | SHB-HA Key order #207130897 Inv. DAS2022091153 |  | 13172.57 | 35.75 | 4786.76 | 8385.81
IET DAS202211115300001 | 2022-06-07 | 2507 | Firewatch #207132278 Inv. DAS20220111153 |  | 13172.57 | 1016.26 | 5803.02 | 7369.55
IET DAS202212115300001 | 2022-07-08 | 2507 | Tape Plastic up on Level 2. #207132446 DAS2022121153 |  | 13172.57 | 109.72 | 5912.74 | 7259.83
IET DAS202301115300001 | 2022-08-10 | 2507 | Firewatch-Skylight Replacement #20713610 |  | 13172.57 | 89.67 | 6002.41 | 7170.16
IET DAS202302115300001 | 2022-09-08 | 2507 | Firewatch-Skylight Replacement #207134173 |  | 13172.57 | 298.9 | 6301.31 | 6871.26
IET DAS202304115300001 | 2022-11-08 | 2507 | East Atrium Door #207135765 |  | 13172.57 | 573.46 | 6874.77 | 6297.8
IET DAS202305115300001 | 2022-12-07 | 2507 | Space Planning-Barbara Bendon DAS2023051153 |  | 13172.57 | 47.5 | 6922.27 | 6250.3
IET DAS202305115300001 | 2022-12-07 | 2507 | Carpentry Order#207137302 DAS2023051153 |  | 13172.57 | 584.03 | 7506.3 | 5666.27
IET DAS202306115300001 | 2023-01-09 | 2507 | SHB 2nd Floor Gallery wall painting #207135683 DAS2023061153 |  | 13172.57 | 4063.65 | 11569.95 | 1602.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Carpentry |  | 13172.57 | 119.85 | 11689.8 | 1482.77
IET DAS202310115300001 | 2023-05-07 | 2507 | Space Planning Services |  | 13172.57 | 95 | 11784.8 | 1387.77
IET DAS202311115300001 | 2023-06-07 | 2507 | Historical Bldg Smoke control Doors |  | 13172.57 | 503.53 | 12288.33 | 884.24
IET DAS202311115300001 | 2023-06-07 | 2507 | Firewatch |  | 13172.57 | 884.24 | 13172.57 | 0
[5 empty] | 13172.57 |  | 13172.57 | 0
[5 empty] | 13172.57 |  | 13172.57 | 0
[5 empty] | 13172.57 |  | 13172.57 | 0
|  |  | Totals: | 13172.57 |  | 13172.57 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: MM22 PM Time 8983.02 FY23 Herman, Josh Wed, Jan 18, 8:43 PM (14 hours ago) to me Please increase the eDAS tab by $2,500 and the PM Time by $7,500. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time/eDAS $John Elliott, Jennie 8:29 AM (22 minutes ago) to me Please increase eDAS time by $2,500 for a total of $15,000 in the contracted line. Thank you

## #8983.02 Misc
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #8983.02 Waldinger
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: MA 20452
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522229801 | 2021-08-16 | DO Procore | 5903.48 | 5903.48 |  |  | 5903.48
DO 33522229801 | 2022-06-21 | CO 1 | 692.03 | 6595.51 |  | 0 | 6595.51
DO 33522229801 | 2022-06-21 | Edit to CO1 (processed incorrectly in I/3) | 0 | 6595.51 |  | 0 | 6595.51
PRC 3352222PA9801 | 2022-06-21 | Inv. 60870E-001 |  | 6595.51 | 6595.51 | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  |  |  | 6595.51 |  | 6595.51 | 0
|  | Totals: | 6595.51 |  | 6595.51 |  | 0 | Final Invoice
|  | Line 1 - Labor | 2445.28 |  | 2445.28 |  | 0
|  | Line 2 - Materials & Equipment | 4150.23 |  | 4150.23 |  | 0
|  | Total: | 6595.51 |  | 6595.51 |  | 0

## #8983.02 Holmes Murphy
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Holmes Murphy |  |  | Vendor: 00002110543
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 18142C
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522251500 | 2021-09-07 | DO Procore | 8566 | 8566 |  |  | 8566
PRC 3352225PA1500 | 2021-09-08 | Inv. 609819 |  | 8566 | 8566 | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  |  |  | 8566 |  | 8566 | 0
|  | Totals: | 8566 |  | 8566 |  | 0

## #8983.02 Ryan Companies 4729CA
DAS CC SHB Roof and Skylight Replacement FY19
Project #8983.02
Program code 898302 |  |  | Major Program 4E02
Ryan Companies (#4729 CA) |  |  | Vendor # 00003035285
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Ryan9112015
Project Manager - Jennie E. |  |  | Activity Code: CMGR
Split w/ MM21
Doc# | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522099200 | 2021-09-15 | CO #2 (Split with MM19) | 125000.01 | 125000.01 |  | 0 | 125000.01
PRC 3352209PL9200 | 2021-12-20 | Inv. 4729CA-12 (100% to MM19) |  | 125000.01 | 0 | 0 | 125000.01
PRC 3352209PM9200 | 2022-01-18 | Inv. 4729CA-13 (100% to MM19) |  | 125000.01 | 0 | 0 | 125000.01
PO 33522099200 | 2022-02-10 | CO #3 (Split between MM21 &DA22) | 0 | 125000.01 |  | 0 | 125000.01
PRC 3352209PN9200 | 2022-02-15 | Inv. 4729-14 (100% to MM19) |  | 125000.01 | 0 | 0 | 125000.01
PRC 3352209PM9200 | 2022-03-28 | Inv. 47290-015 (Split between MM19, MM21, & DA22) |  | 125000.01 | 0 | 0 | 125000.01
PRC 3352209PP9200 | 2022-04-15 | Inv. 47290-016 (Split between MM19, MM21 & DA22) |  | 125000.01 | 0 | 0 | 125000.01
PO 33522099200 | 2022-05-05 | CO #4 (Split between MM19 & MM22) | 57000 | 182000.01 |  | 0 | 182000.01
PRC 3352209PQ9200 | 2022-05-13 | Inv. 4729CA-17 (Split between MM19 & MM22) |  | 182000.01 | 4346.84 | 4346.84 | 177653.17
PO 33522099200 | 2022-06-15 | CO #5 (100% to MM21) | 0 | 182000.01 |  | 4346.84 | 177653.17
PRC 3352209PR9200 | 2022-06-15 | Inv. 4729CA-18 (Split between MM19 & MM22) |  | 182000.01 | 4228.5 | 8575.34 | 173424.67
PO 33522099200 | 2022-06-21 | CO #6 (100% to MM22) $0.00 CO | 0 | 182000.01 |  | 8575.34 | 173424.67
PRC 3352209PS9200 | 2022-07-20 | Inv. 4729CA-19 (Split between DA22 & MM22) |  | 182000.01 | 25640.17 | 34215.51 | 147784.5 | FY22
PO 33523099200 | 2022-08-09 | Rolled to FY23 | 0 | 182000.01 |  | 34215.51 | 147784.5
PRC 3352309PT9200 | 2022-08-31 | Inv. 4729CA-20 (100% to MM22) |  | 182000.01 | 15446.03 | 49661.54 | 132338.47
PRC 3352309PU9200 | 2022-09-11 | Inv. 4729CA-21 (Split between MM21 & MM22) |  | 182000.01 | 11986.45 | 61647.99 | 120352.02
PRC 3352309PV9200 | 2022-10-12 | Inv. 4729CA-22 (100% to MM22) |  | 182000.01 | 16330.71 | 77978.7 | 104021.31
PO 33523099200 | 2022-11-17 | CO #7 (100% to MM21) | 0 | 182000.01 |  | 77978.7 | 104021.31
PRC 3352309PW9200 | 2022-12-06 | Inv. 4729CA-23 (Split between MM21 & MM22) |  | 182000.01 | 5350.95 | 83329.65 | 98670.36
PO 33523099200 | 2022-12-13 | CO 8(No Cost CO) | 0 | 182000.01 |  | 83329.65 | 98670.36
PRC 3352309PX9200 | 2022-12-14 | Inv. 4729CA-24 (Split between MM21 & MM22) |  | 182000.01 | 42838.13 | 126167.78 | 55832.23
PRC 3352309PY9200 | 2023-01-14 | Inv. 4729CA-25 (Split between MM21 & MM22) |  | 182000.01 | 9021.06 | 135188.84 | 46811.17
PRC 3352309PZ9200 | 2023-02-09 | Inv. 4729CA-26 (Split between MM21 & MM22) |  | 182000.01 | 2624.41 | 137813.25 | 44186.76
PRC 3352309PAA9200 | 2023-03-07 | Inv. 4729CA-27 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352309PAB9200 | 2023-04-12 | Inv. 4729CA-28 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352309PAC9200 | 2023-05-15 | Inv. 4729CA-29 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352309PAD9200 | 2023-06-12 | Inv. 4729CA-30 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352309PAE9200 | 2023-07-13 | Inv. 4729CA-31 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76 | FY23
PO 33524099200 | 2023-08-03 | Roll to FY24 | 0 | 182000.01 |  | 137813.25 | 44186.76
PRC 3352409PAF9200 | 2023-08-11 | Inv. 4729CA-32 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352409PAG9200 | 2023-09-18 | Inv. 4729CA-33 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352409PAH9200 | 2023-10-06 | Inv. 4729CA-34 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352409PAI9200 | 2023-11-08 | Inv. 4729CA-35 (100% to MM21) |  | 182000.01 | 0 | 137813.25 | 44186.76
PRC 3352409PAJ9200 | 2023-12-20 | Inv. 4729CA-36 FINAL | -44186.76 | 137813.25 | 0 | 137813.25 | 0
|  |  |  | 137813.25 |  | 137813.25 | 0
|  |  |  | 137813.25 |  | 137813.25 | 0
|  |  |  | 137813.25 |  | 137813.25 | 0
|  | Totals: | 137813.25 |  | 137813.25 |  | 0 | FINAL
|  | R528 (Closed 10/29/20) | 155603.38 |  | 155603.38 |  | 0
|  | MM19 (Closed 06/15/22) | 563476.99 |  | 563476.99 |  | 0
|  | MM21 | 68715.28 |  | 68715.28 |  | 0
|  | DA22 (Closed 07/20/22) | 24577.6 |  | 24577.6 |  | 0
|  | Total contract: | 950186.5 |  | 950186.5 |  | 0

## #8983.02 Neumann Monson
DAS CC SHB Roof and Skylight Replacement FY19
Project #8983.02
Program code 898302 |  |  | Major Program 4E02
Neumann Monson Architects |  |  | Vendor: 00002116371
Acct. Codes-0017-335-MM22-9260 |  |  | RFP0215335040
Project Manager - Josh H. |  |  | Activity code: DSGN
Split with MM21
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522263200 | 2021-09-23 | CO #4 (Split between MM19, MM21 & MM22) | 41517.44 | 41517.44 |  | 0 | 41517.44
PO 33522263200 | 2021-10-13 | CO to update correct open PO amount (100% to MM19) | 0 | 41517.44 |  | 0 | 41517.44
PRC 3352226PI3200 | 2021-10-21 | Inv. 8983.02-09 (100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PRC 3352226PJ3200 | 2021-11-17 | Inv. 8983.02-10 (100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PRC 3352226PK3200 | 2021-12-07 | Inv. 8983.02-11 (100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PRC 3352226PL3200 | 2022-01-06 | Inv. 8983.02-12 (100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PRC 3352226PM3200 | 2022-02-07 | Inv. 8983.02-13 (100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PO 33522263200 | 2022-02-14 | CO 5 (Split between MM21&DA18) | 0 | 41517.44 |  | 0 | 41517.44
PRC 3352226PN3200 | 2022-03-09 | Inv. 8983.02-14 (Split between MM19 & MM21) |  | 41517.44 | 0 | 0 | 41517.44
PO 33522263200 | 2022-03-16 | CO 6 (100% to MM21) | 0 | 41517.44 |  | 0 | 41517.44
PRC 3352226PO3200 | 2022-04-04 | Inv. 8983.02-15(100% to MM19) |  | 41517.44 | 0 | 0 | 41517.44
PRC 3352226PP3200 | 2022-05-16 | Inv. 8983.02-16 (Split between MM21, MM22, & DA18) |  | 41517.44 | 5931.07 | 5931.07 | 35586.37
PRC 3352226PQ3200 | 2022-06-06 | Inv. 8983.02-17 (Split between MM21 & MM22) |  | 41517.44 | 5931.07 | 11862.14 | 29655.3
PRC 3352226PR3200 | 2022-07-12 | Inv. 8983.02-18 (Split between MM21 & MM22) |  | 41517.44 | 5931.06 | 17793.2 | 23724.24 | FY22
PO 33523263200 | 2022-08-09 | Rolled to FY23 | 0 | 41517.44 |  | 17793.2 | 23724.24
PRC 3352326PS3200 | 2022-08-11 | Inv. 8983.02-19 (100% to MM22) |  | 41517.44 | 5931.06 | 23724.26 | 17793.18
PRC 3352326PT3200 | 2022-09-11 | Inv. 8983.02-20 (100% to MM22) |  | 41517.44 | 5931.06 | 29655.32 | 11862.12
PRC 3352326PU3200 | 2022-10-12 | Inv. 8983.02-21 (100% to MM22) |  | 41517.44 | 5931.06 | 35586.38 | 5931.06
PO 33523263200 | 2022-12-13 | CO 7 (100% to MM22) | -2216 | 39301.44 |  | 35586.38 | 3715.06
PRC 3352326PV3200 | 2022-12-15 | Inv. 8983.02-22 (100% to MM22) |  | 39301.44 | 3715.06 | 39301.44 | 0
|  |  |  | 39301.44 |  | 39301.44 | 0
|  |  |  | 39301.44 |  | 39301.44 | 0
|  |  |  | 39301.44 |  | 39301.44 | 0
|  |  |  | 39301.44 |  | 39301.44 | 0
|  | Totals: | 39301.44 |  | 39301.44 |  | 0
|  | DA18 8983.01 (Closed 5/16/22) | 37577 |  | 37577 |  | 0
|  | MM19 (Closed 4/22/22) | 392419.56 |  | 392419.56 |  | 0
|  | MM21 | 111016 |  | 92246 |  | 18770
|  | Total contract: | 580314 |  | 561544 |  | 18770

## #8983.02 W.W. Grainger
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
W.W. Grainger |  |  | Vendor: 00002099406
Acct. Codes-0017-335-MM22-9255 |  |  | MA 18298A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522281500 | 2021-10-08 | DO Procore | 576.66 | 576.66 |  |  | 576.66
PRC 3352228PA1500 | 2021-11-01 | Inv. 9081297591 |  | 576.66 | 576.66 | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  |  |  | 576.66 |  | 576.66 | 0
|  | Totals: | 576.66 |  | 576.66 |  | 0

## #8983.02 ATC Group Services
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
ATC Group Services LLC |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: MA 20262A
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522281803 | 2021-10-08 | DO Procore | 1735 | 1735 |  |  | 1735
DO 33522281803 | 2022-05-25 | Closing DO @ the request of PM & vendor | -1735 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Line 2 - Asbestos Per Sample Fee (60 samples at $10/sample) | 0 |  |  |  | 0
|  | Line 5 - Administrative (1 hour at $45/hour) | 0 |  |  |  | 0
|  | Line 7 - Field Technician (12 hours at $75/hour) | 0 |  |  |  | 0
|  | Line 8 - Hygienist (2 hours at $95/hour) | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #8983.02 Terracon Consultants
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0017-335-MM22-9255 |  |  | RFQQ898300.02-01
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522298804 | 2021-10-25 | PO Procore | 13479.5 | 13479.5 |  |  | 13479.5
PRC 3352229PA8804 | 2022-01-05 | Inv. TG06906 |  | 13479.5 | 1008.75 | 1008.75 | 12470.75
PRC 3352229PB8804 | 2022-01-05 | Inv. TG16478 |  | 13479.5 | 458.75 | 1467.5 | 12012
PRC 3352229PC8804 | 2022-06-08 | Inv. TG40144 |  | 13479.5 | 612.5 | 2080 | 11399.5
PRC 3352229PD8804 | 2022-06-08 | Inv. TG66333 |  | 13479.5 | 760 | 2840 | 10639.5
PRC 3352229PE8804 | 2022-06-08 | Inv. TG80891 |  | 13479.5 | 2567.5 | 5407.5 | 8072
PRC 3352229PF8804 | 2022-08-05 | Inv. TH13443 |  | 13479.5 | 648.75 | 6056.25 | 7423.25 | FY22
PO 33523298804 | 2022-08-10 | Rolled to FY23 | 0 | 13479.5 |  | 6056.25 | 7423.25
PRC 3352329PG8804 | 2022-08-26 | Inv. TH22468 |  | 13479.5 | 218.75 | 6275 | 7204.5
PRC 3352329PH8804 | 2022-09-20 | Inv. TH34022 |  | 13479.5 | 388.75 | 6663.75 | 6815.75
PRC 3352329PI8804 | 2022-10-26 | Inv. TH49466 |  | 13479.5 | 343.75 | 7007.5 | 6472
PO 33523298804 | 2023-06-29 | Close PO per PM | -6472 | 7007.5 |  | 7007.5 | 0
|  |  |  | 7007.5 |  | 7007.5 | 0
|  |  |  | 7007.5 |  | 7007.5 | 0
|  |  |  | 7007.5 |  | 7007.5 | 0
|  |  |  | 7007.5 |  | 7007.5 | 0
|  |  |  | 7007.5 |  | 7007.5 | 0
|  | Totals: | 7007.5 |  | 7007.5 |  | 0 | FINAL

## #8983.02 Waldinger (2)
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Waldinger Corporation (2) |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: MA20452
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522319800 | 2021-11-12 | DO Procore | 25285 | 25285 |  |  | 25285
DO 33522319800 | 2022-06-21 | CO 1 | -5572.8 | 19712.2 |  | 0 | 19712.2
PRC 3352231PA9800 | 2022-06-21 | Inv. 62358E-001 |  | 19712.2 | 19712.2 | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  |  |  | 19712.2 |  | 19712.2 | 0
|  | Totals: | 19712.2 |  | 19712.2 |  | 0
|  | Line 1 - Labor Regular Time | 7548.28 |  | 7548.28 |  | 0
|  | Line 2 - Materials | 12163.92 |  | 12163.92 |  | 0
|  | Total: | 19712.2 |  | 19712.2 |  | 0

## #8983.02 Midwest Caulking
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Midwest Caulking |  |  | Vendor: 00002121632
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522069901 | 2022-03-10 | PO Procore | 4000 | 4000 |  |  | 4000
PRC 3352206PA9901 | 2022-06-09 | Inv. 9999 |  | 4000 | 4000 | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  |  |  | 4000 |  | 4000 | 0
|  | Totals: | 4000 |  | 4000 |  | 0

## #8983.02 Baker Group
DAS CC SHB Roof and Skylight Replacement FY22
Project # 8983.02
Program code 898302 |  |  | Major Program 4E02
Baker Group |  |  | Vendor: 00002109043
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523280900 | 2022-10-07 | PO Procore | 6580 | 6580 |  |  | 6580
PRC 3352328PA0900 | 2023-04-06 | Inv. 242399-FINAL | -1251.19 | 5328.81 | 5328.81 | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  |  |  | 5328.81 |  | 5328.81 | 0
|  | Totals: | 5328.81 |  | 5328.81 |  | 0 | FINAL

## RECAP #9054.03
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
| Program code 905403 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1053139.46
C | Samuels Group |  | 16195.78 | 16195.78 | 0
C | PM TIME |  | 16550.45 | 16550.45 | 0
C | Misc. |  | 1617.85 | 1617.85 | 0
C | Shive Hattery |  | 75770 | 75770 | 0
C | Denovo LLC |  | 15080 | 15080 | 0
C | S & S Plumbing |  | 833183.49 | 833183.49 | 0
C | Samuels Group #113CA |  | 94741.89 | 94741.89 | 0
| Total Project Cost | 1053139.46 | 1053139.46 | 1053139.46 | 0 | 0
Closed 07/12/2024

## #9054.03 Samuels Group
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522251501 | 2021-09-08 | PO Procore | 16518.62 | 16518.62 |  |  | 16518.62
PRC 3352225PA1501 | 2021-10-07 | Inv. 7283.9 PC |  | 16518.62 | 1959.16 | 1959.16 | 14559.46
PRC 3352225PB1501 | 2021-11-02 | Inv. 7283.10 PC |  | 16518.62 | 1477.5 | 3436.66 | 13081.96
PRC 3352225PC1501 | 2021-12-13 | Inv. 7283.21 B23PC |  | 16518.62 | 834.54 | 4271.2 | 12247.42
PRC 3352225PD1501 | 2022-01-07 | Inv. 7283.24 B23PC |  | 16518.62 | 2701.51 | 6972.71 | 9545.91
PRC 3352225PE1501 | 2022-02-09 | Inv. 7283.25 B23PC |  | 16518.62 | 3836.08 | 10808.79 | 5709.83
PRC 3352225PF1501 | 2022-03-09 | Inv. 7283.26 B23PC |  | 16518.62 | 5018.97 | 15827.76 | 690.86
PRC 3352225PG1501 | 2022-04-14 | Inv. 7283.27 B23PC - Final | -322.84 | 16195.78 | 368.02 | 16195.78 | -2.1032e-12
|  |  |  | 16195.78 |  | 16195.78 | -2.1032e-12
|  |  |  | 16195.78 |  | 16195.78 | -2.1032e-12
|  |  |  | 16195.78 |  | 16195.78 | -2.1032e-12
|  |  |  | 16195.78 |  | 16195.78 | -2.1032e-12
|  |  |  | 16195.78 |  | 16195.78 | -2.1032e-12
|  | Totals: | 16195.78 |  | 16195.78 |  | 0 | Final
|  | CM Services | 16013.26 |  | 16013.26 |  | 0
|  | Reimbursables | 182.52 |  | 182.52 |  | 0
|  | Total: | 16195.78 |  | 16195.78 |  | 0

## #9054.03 PM TIME
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 905Z
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15995.5 | 15995.5 |  |  | 15995.5
IET DAS202202115300001 | 2021-09-08 |  | PM-Jul. 23-Aug. 19, 2021 |  | 15995.5 | 125 | 125 | 15870.5
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 15995.5 | 650 | 775 | 15220.5
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 15995.5 | 875 | 1650 | 14345.5
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 15995.5 | 225 | 1875 | 14120.5
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 15995.5 | 1175 | 3050 | 12945.5
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 15995.5 | 400 | 3450 | 12545.5
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 15995.5 | 1400 | 4850 | 11145.5
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 15995.5 | 400 | 5250 | 10745.5
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 15995.5 | 175 | 5425 | 10570.5
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 15995.5 | 175 | 5600 | 10395.5
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 15995.5 | 125 | 5725 | 10270.5
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 15995.5 | 75 | 5800 | 10195.5
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 15995.5 | -75 | 5725 | 10270.5
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 15995.5 | 82.5 | 5807.5 | 10188
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 15995.5 | 137.5 | 5945 | 10050.5
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 15995.5 | 165 | 6110 | 9885.5
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 15995.5 | 137.5 | 6247.5 | 9748
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 86.78 | 16082.28 | 86.78 | 6334.28 | 9748
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 126.95 | 16209.23 | 126.95 | 6461.23 | 9748
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 102.99 | 16312.22 | 102.99 | 6564.22 | 9748
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 108.08 | 16420.3 | 108.08 | 6672.3 | 9748
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16420.3 | 15.6 | 6687.9 | 9732.4
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16420.3 | 136.81 | 6824.71 | 9595.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 19.08 | 16439.38 | 19.08 | 6843.79 | 9595.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 52.41 | 16491.79 | 52.41 | 6896.2 | 9595.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 42.8 | 16534.59 | 42.8 | 6939 | 9595.59
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 15.86 | 16550.45 | 15.86 | 6954.86 | 9595.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 16550.45 | 14.99 | 6969.85 | 9580.6
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 16550.45 | 90.9 | 7060.75 | 9489.7
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 16550.45 | 81.08 | 7141.83 | 9408.62
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 16550.45 | 356.62 | 7498.45 | 9052
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 16550.45 | 139.67 | 7638.12 | 8912.33
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 16550.45 | 821.6 | 8459.72 | 8090.73
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 16550.45 | 64.54 | 8524.26 | 8026.19
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 16550.45 | 454.3 | 8978.56 | 7571.89
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 16550.45 | 47.21 | 9025.77 | 7524.68
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 16550.45 | 392.9 | 9418.67 | 7131.78
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 16550.45 | 71.51 | 9490.18 | 7060.27
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 16550.45 | 454.5 | 9944.68 | 6605.77
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 16550.45 | 143.94 | 10088.62 | 6461.83
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 16550.45 | 803.4 | 10892.02 | 5658.43
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 16550.45 | 134.55 | 11026.57 | 5523.88
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 16550.45 | 931.4 | 11957.97 | 4592.48
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 16550.45 | 54.14 | 12012.11 | 4538.34
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 16550.45 | 436 | 12448.11 | 4102.34
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 16550.45 | 56.67 | 12504.78 | 4045.67
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 16550.45 | 427.4 | 12932.18 | 3618.27
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 16550.45 | 63.55 | 12995.73 | 3554.72
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 16550.45 | 465.8 | 13461.53 | 3088.92
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 16550.45 | 27.63 | 13489.16 | 3061.29
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 16550.45 | 242.4 | 13731.56 | 2818.89
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 16550.45 | 174.79 | 13906.35 | 2644.1
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 16550.45 | 882.3 | 14788.65 | 1761.8
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 16550.45 | 18.22 | 14806.87 | 1743.58
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 16550.45 | 138.1 | 14944.97 | 1605.48
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 16550.45 | 35.57 | 14980.54 | 1569.91
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 16550.45 | 316.4 | 15296.94 | 1253.51
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 16550.45 | 65.88 | 15362.82 | 1187.63
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 16550.45 | 542.5 | 15905.32 | 645.13
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 16550.45 | 63.63 | 15968.95 | 581.5
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 16550.45 | 581.5 | 16550.45 | 0
|  |  | Totals: | 16550.45 |  | 16550.45 |  | 0
Note on E9: Wray, Ronda [DAS]: PM Time Budgets $Ronda Kleene, Jennifer Aug 7, 2021, 1:16 PM (5 days ago) to me Please create the following PM Time budgets: MM22 9054.03 $4,000.00 MM22 9219.00 $4,000.00 Please increase the PM Time Budget for MM20 8982.01 by $800.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative PM Time Increase $Joni Kleene, Jennifer Mon, Feb 28, 3:43 PM (2 days ago) to me, Scott Please increase the PM Time budget for MM22 project 9054.03 by $6,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 3:24 PM (10 minutes ago) to me Please make the following changes: 9326.00 MM21 - increase by $2,100.00 9054.03 MM22 - increase by $5,000.00 9262.00 MM22 - increase by $8,000.00 9290.00 MM22 - increase by $3,200.00 9268.01 R22M - increase by $1,000.00 Regards, Jennifer

## #9054.03 Misc
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522047903 | 2022-02-16 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2404232-Final | 1010 | 1010
PRC 33522049901 | 2022-02-21 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV018221 | 607.85 | 1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
1617.85
|  |  |  | Totals: |  | 1617.85

## #9054.03 Shive Hattery
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 905401-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522259801 | 2021-09-14 | PO Procore | 75000 | 75000 |  |  | 75000
PRC 3352225PA9801 | 2021-12-14 | Inv. 1217670-1 |  | 75000 | 19000 | 19000 | 56000
PRC 3352225PB9801 | 2021-12-23 | Inv. 1217670-2 |  | 75000 | 29500 | 48500 | 26500
PRC 3352225PC9801 | 2022-01-28 | Inv. 1217670-3 |  | 75000 | 9500 | 58000 | 17000
PRC 3352225PD9801 | 2022-03-04 | Inv. 1217670-4 |  | 75000 | 2000 | 60000 | 15000
PRC 3352225PE9801 | 2022-03-31 | Inv. 1217670-5 |  | 75000 | 1500 | 61500 | 13500
PRC 3352225PF9801 | 2022-05-11 | Inv. 1217670-6 |  | 75000 | 1500 | 63000 | 12000
PRC 3352225PG9801 | 2022-06-20 | Inv. 1217670-7 |  | 75000 | 1500 | 64500 | 10500
PRC 3352225PH9801 | 2022-07-12 | Inv. 1217670-8 |  | 75000 | 1500 | 66000 | 9000 | FY22
PO 33523259801 | 2022-08-08 | Rolled to FY23 | 0 | 75000 |  | 66000 | 9000
PRC 3352325PI9801 | 2023-03-22 | Inv. 1217670-9 |  | 75000 | 1500 | 67500 | 7500
PRC 3352325PJ9801 | 2023-05-05 | Inv. 1217670-10 |  | 75000 | 1500 | 69000 | 6000
PRC 3352325PK9801 | 2023-06-09 | Inv. 1217670-11 |  | 75000 | 1500 | 70500 | 4500
PRC 3352325PL9801 | 2023-07-11 | Inv. 1217670-12 |  | 75000 | 3000 | 73500 | 1500 | FY23
PO 33524259801 | 2023-07-25 | Roll to FY24 | 0 | 75000 |  | 73500 | 1500
PRC 3352425PM9801 | 2023-08-04 | Inv. 9054.03-13 |  | 75000 | 750 | 74250 | 750
PO 33524259801 | 2023-09-12 | CO #1 | 770 | 75770 |  | 74250 | 1520
PRC 3352425PN9801 | 2023-12-08 | Inv. 9054.03-14 |  | 75770 | 1070 | 75320 | 450
PRC 3352425PO9801 | 2024-06-05 | Inv. 9054.03-15Final |  | 75770 | 450 | 75770 | 0
|  |  |  | 75770 |  | 75770 | 0
|  | Totals: | 75770 |  | 75770 |  | 0 | FINAL
|  | Schematic Design Documents | 19000 |  | 19000 |  | 0
|  | Design Development Documents | 20000 |  | 20000 |  | 0
|  | Construction Documents | 19000 |  | 19000 |  | 0
|  | Bidding Assistance | 2000 |  | 2000 |  | 0
|  | Construction Phase | 15000 |  | 15000 |  | 0
|  | CO #1 | 770 |  | 770 |  | 0
|  | Total: | 75770 |  | 75770 |  | 0

## #9054.03 Denovo LLC
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  | Major Program 4E01
Denovo LLC |  |  | Vendor: 00003187582
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B: 905403-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522298801 | 2021-10-22 | PO Procore | 15080 | 15080 |  |  | 15080
PRC 3352229PA8801 | 2022-01-14 | Inv. 21.0025.01 |  | 15080 | 3540 | 3540 | 11540 | FY22
PO 33523298801 | 2022-08-08 | Rolled to FY23 | 0 | 15080 |  | 3540 | 11540
PRC 3352329PB8801 | 2023-07-13 | Inv. 21.0025.02 |  | 15080 | 3200 | 6740 | 8340 | FY23
PO 33524298801 | 2023-07-25 | Roll to FY24 | 0 | 15080 |  | 6740 | 8340
PRC 3352429PC8801 | 2023-10-03 | Inv. AR000100 |  | 15080 | 3200 | 9940 | 5140
PRC 3352429PD8801 | 2024-03-20 | Inv. AR000186 |  | 15080 | 3200 | 13140 | 1940
PRC 3352429PE8801 | 2024-05-31 | Inv. 9054.03-05 - Final |  | 15080 | 1940 | 15080 | 0
|  |  |  | 15080 |  | 15080 | 0
|  |  |  | 15080 |  | 15080 | 0
|  |  |  | 15080 |  | 15080 | 0
|  |  |  | 15080 |  | 15080 | 0
|  |  |  | 15080 |  | 15080 | 0
|  | Totals: | 15080 |  | 15080 |  | 0 | FINAL
|  | Design Review | 3540 |  | 3540 |  | 0
|  | Construction Commissioning | 9600 |  | 9600 |  | 0
|  | Close Out/Final Report | 1940 |  | 1940 |  | 0
|  | Total: | 15080 |  | 15080 |  | 0

## #9054.03 S & S Plumbing
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  | Major Program 4E01
S & S Plumbing |  |  | Vendor: 00003036947
Acct. Codes-0017-335-MM22-9255 |  |  | 905403-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522067900 | 2022-03-08 | PO Procore | 832715 | 832715 |  |  | 832715 |  | FY22
PO 33523067900 | 2022-08-08 | Rolled to FY23 | 0 | 832715 |  | 0 | 832715
PO 33523067900 | 2022-10-19 | CO 1 ($0 CO) | 0 | 832715 |  | 0 | 832715
PRC 3352306PA7900 | 2023-03-13 | Inv. 9054.03-01 |  | 832715 | 410509.25 | 410509.25 | 422205.75 | 21605.75
PO 33523067900 | 2023-06-27 | CO 2 | -650 | 832065 |  | 410509.25 | 421555.75
PRC 3352306PB7900 | 2023-07-11 | Inv. 9054.03-02 |  | 832065 | 225340 | 635849.25 | 196215.75 | 33465.75 | FY23
PO 33524067900 | 2023-07-25 | Roll to FY24 | 0 | 832065 |  | 635849.25 | 196215.75
PO 33524067900 | 2023-08-31 | CO 3 | -1171.65 | 830893.35 |  | 635849.25 | 195044.1
PO 33524067900 | 2023-10-04 | CO 4 | -940.29 | 829953.06 |  | 635849.25 | 194103.81
PO 33524067900 | 2023-11-06 | CO 5 | -2419.57 | 827533.49 |  | 635849.25 | 191684.24
PRC 3352406PC7900 | 2023-12-06 | Inv. 9054.03-03 |  | 827533.49 | 111120.06 | 746969.31 | 80564.18 | 39314.18
PO 33524067900 | 2023-12-15 | CO 6 | 5650 | 833183.49 |  | 746969.31 | 86214.18
PRC 3352406PD7900 | 2024-05-29 | Inv. 9054.03-04 |  | 833183.49 | 44555 | 791524.31 | 41659.18 | 41659.18
PRC 3352406PE7900 | 2024-06-04 | Inv. 9054.03-05-Retainage |  | 833183.49 | 41659.18 | 833183.49 | 0
|  |  |  | 833183.49 |  | 833183.49 | 0
|  | Totals: | 833183.49 |  | 833183.49 |  | 0

## #9054.03 Samuels Group #113CA
DOC IMCC Boilers #2 and #3 Replacement
Project # 9054.03
Program code 905403 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522076901 | 2022-03-16 | PO Procore | 89826.63 | 89826.63 |  |  | 89826.63
PRC 3352207PA6901 | 2022-04-14 | Inv. 7398C1.10 CA |  | 89826.63 | 1329.75 | 1329.75 | 88496.88
PRC 3352207PB6901 | 2022-05-06 | Inv. 7398C1.11 CA |  | 89826.63 | 1625.25 | 2955 | 86871.63
PRC 3352207PC6901 | 2022-06-02 | Inv. 7398C1.12 CA |  | 89826.63 | 5561.96 | 8516.96 | 81309.67
PRC 3352207PD6901 | 2022-07-08 | Inv. 7398C1.13 CA |  | 89826.63 | 1202.56 | 9719.52 | 80107.11 | FY22
PO 33523076901 | 2022-08-08 | Rolled to FY23 | 0 | 89826.63 |  | 9719.52 | 80107.11
PRC 3352307PE6901 | 2022-09-09 | Inv. 7398C1.14 CA |  | 89826.63 | 1788.14 | 11507.66 | 78318.97
PRC 3352307PF6901 | 2023-01-06 | Inv. 7398C1.15 CA |  | 89826.63 | 1547.1 | 13054.76 | 76771.87
PRC 3352307PG6901 | 2023-02-03 | Inv. 7398C1.16 CA |  | 89826.63 | 1177.31 | 14232.07 | 75594.56
PRC 3352307PH6901 | 2023-03-07 | Inv. 7398C1.17 CA |  | 89826.63 | 1127.33 | 15359.4 | 74467.23
PRC 3352307PI6901 | 2023-04-07 | Inv. 7398C1.18 CA |  | 89826.63 | 3002.39 | 18361.79 | 71464.84
PRC 3352307PJ6901 | 2023-05-08 | Inv. 7398C1.19 CA |  | 89826.63 | 9437.01 | 27798.8 | 62027.83
PRC 3352307PK6901 | 2023-06-06 | Inv. 7398C1.20 CA |  | 89826.63 | 9427.32 | 37226.12 | 52600.51
PRC 3352307PL6901 | 2023-07-13 | Inv. 7398C1.21 CA |  | 89826.63 | 31124.4 | 68350.52 | 21476.11 | FY23
PO 33524076901 | 2023-07-25 | Roll to FY24 | 0 | 89826.63 |  | 68350.52 | 21476.11
PRC 3352407PM6901 | 2023-08-07 | Inv. 7398C1.22 CA |  | 89826.63 | 8449.9 | 76800.42 | 13026.21
PO 33524076901 | 2023-09-07 | CO #1 | 2501.65 | 92328.28 |  | 76800.42 | 15527.86
PRC 3352407PN6901 | 2023-09-15 | Inv. 7398C1.23 CA |  | 92328.28 | 5693.33 | 82493.75 | 9834.53
PRC 3352407PO6901 | 2023-10-12 | Inv. 7398C1.24 CA |  | 92328.28 | 4174.49 | 86668.24 | 5660.04
PO 33524076901 | 2023-11-06 | CO #2 | 2419.57 | 94747.85 |  | 86668.24 | 8079.61
PRC 3352407PP6901 | 2023-11-13 | Inv. 7398C1.25 CA |  | 94747.85 | 1904.3 | 88572.54 | 6175.31
PRC 3352407PQ6901 | 2023-12-13 | Inv. 7398C1.26 CA |  | 94747.85 | 3379.6 | 91952.14 | 2795.71
PRC 3352407PR6901 | 2024-01-05 | Inv. 7398C1.27 CA |  | 94747.85 | 846.6 | 92798.74 | 1949.11
PRC 3352407PS6901 | 2024-06-10 | Inv. 7398C1.28 CA FINAL | -5.96 | 94741.89 | 1943.15 | 94741.89 | -6.7848e-12
|  |  |  | 94741.89 |  | 94741.89 | -6.7848e-12
|  |  |  | 94741.89 |  | 94741.89 | -6.7848e-12
|  | Totals: | 94741.89 |  | 94741.89 |  | 0 | FINAL
|  | CM Services | 45190.88 |  | 45190.88 |  | 0
|  | Reimbursables | 3000 |  | 3000 |  | 0
|  | Fee | 41635.75 |  | 41635.75 |  | 0
|  | CO #1 | 2501.65 |  | 2501.65 |  | 0
|  | CO #2 | 2413.61 |  | 2413.61 |  | 0
|  | Total: | 94741.89 |  | 94741.89 |  | 0

## RECAP #9099.00
DHS CHMHI Patient Restroom Safety Improvements
Project #9099.00
| Program code 909900 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 91006.93
C | Story Construction |  | 5555 | 5555 | 0
C | PM TIME |  | 1431.95 | 1431.95 | 0
C | Misc. |  | 0 | 0
C | Haselhoff Construction |  | 84019.98 | 84019.98 | 0
| Total Project Cost | 91006.93 | 91006.93 | 91006.93 | 0 | 0
Closed 01/13/25

## #9099.00 Story Construction
DHS CHMHI Patient Restroom Safety Improvements
Project #9099.00
Program code 909900 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524020900 | 2024-07-05 | Moving PO From MM21 | 7859.35 | 7859.35 |  |  | 7859.35
PRC 3352402PAC0900 | 2024-07-17 | Inv. 34435 |  | 7859.35 | 4350 | 4350 | 3509.35 | FY24
PO 335250209900 | 2024-07-18 | Roll to FY25 |  | 7859.35 |  | 4350 | 3509.35
PRC 3352502PB09900 | 2024-12-20 | Inv. 34653 FINAL | -2304.35 | 5555 | 1205 | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  |  |  | 5555 |  | 5555 | 0
|  | Totals: | 5555 |  | 5555 |  | 0 | FINAL
|  | Reimburseables | 0 |  |  |  | 0
|  | CMCA Fee 5% | 3540 |  | 3540 |  | 0
|  | CO #3 | 2015 |  | 2015 |  | 0
|  | Total | 5555 |  | 5555 |  | 0
|  | MM21 Closed 07/05/2024 | 152211.65 |  | 152211.65 |  | 0
|  | DA23 Closed 04/22/2024 | 36138 |  | 36138 |  | 0
|  | Total Contract | 193904.65 |  | 193904.65 |  | 0

## #9099.00 PM TIME
DHS CHMHI Patient Restroom Safety Improvements
Project #9099.00
Program code 909900 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 909R
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 1431.95 | 1431.95 |  |  | 1431.95
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 1431.95 | 30.84 | 30.84 | 1401.11
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 1431.95 | 339.4 | 370.24 | 1061.71
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 1431.95 | 31.55 | 401.79 | 1030.16
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 1431.95 | 162.2 | 563.99 | 867.96
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 1431.95 | 11.52 | 575.51 | 856.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 1431.95 | 77 | 652.51 | 779.44
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 1431.95 | 40.33 | 692.84 | 739.11
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 1431.95 | 266.6 | 959.44 | 472.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 1431.95 | 43.31 | 1002.75 | 429.2
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 1431.95 | 429.2 | 1431.95 | 0
[5 empty] | 1431.95 |  | 1431.95 | 0
[5 empty] | 1431.95 |  | 1431.95 | 0
|  |  | Totals: | 1431.95 |  | 1431.95 |  | 0
Note on E9: Huggins, Joni [DAS]: 9099.00 - HHS CHMHI Restroom Safety Improvements - Close Out - MM22 & DA23 External $Joni Elliott, Jennie Sun, Jan 12, 11:36 AM (21 hours ago) to me, Scott, Chris Finance, Please reduce the PM time budget to $1,431.95 and close out project 9099.00 in MM22. This should return $8,993.07 to the Total Unassigned/Unallocated line in MM22. Please reduce the PM time budget to 1,712.42 and close out project 9099.00 in DA23. This should return $2,692.15 to HHS. Thank you, Jennie Elliott

## #9099.00 Misc
DHS CHMHI Patient Restroom Safety Improvements
Project #9099.00
Program code 909900 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9099.00 Haselhoff Construction
DHS CHMHI Patient Restroom Safety Improvements
Project #9099.00
Program code 909900 |  |  | Major Program 4B02
Hasselhoff Construction |  |  | Vendor: 00002118715
Acct. Codes-0017-335-MM22-9255 |  |  | 909900-03
Project Manager - Jennie E. |  |  | Activity code: BRIN
Split w/DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524032900 | 2024-07-05 | Moving PO From MM21 | 84019.98 | 84019.98 |  |  | 84019.98 | 71019.98 | FY24
PO 33525032900 | 2024-08-26 | Roll to FY25 |  | 84019.98 |  | 0 | 84019.98
PRC 3352503PS2900 | 2024-12-03 | Inv. 9099.00-19(100% to MM22) |  | 84019.98 | 12350 | 12350 | 71669.98 | 71669.98
PRC 3352503PT2900 | 2024-12-16 | Inv. 9099.00-20(Split to DA23) |  | 84019.98 | 71669.98 | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  |  |  | 84019.98 |  | 84019.98 | 0
|  | Totals: | 84019.98 |  | 84019.98 |  | 0
|  | MM21 Closed 07/05/2024 | 1349375.33 |  | 1349375.33
|  | DA23 | 18484.43 |  | 18484.43 |  | 0
|  | Totals: | 1451879.74 |  | 1451879.74 |  | 0
***Stored Materials Breakdown. Current store materials are subtracted from the invoice totals****
|  |  | Store Materials | Store Materials | D**+F**-E**
|  | Total Payment | Previous Invoice | Current Invoice | Actual Payment
PRC 3352203PA2900 | 2022-03-21 | 9545 | 0 | 0 | 9067.75
PRC 3352203PB2900 | 2022-04-29 | 14819.76 | 0 | 0 | 14078.77
PRC 3352203PC2900 | 2022-06-14 | 46886.91 | 0 | 0 | 44542.56
PRC 3352203PD2900 | 2022-07-18 | 58664.87 | 0 | 25771.68 | 80214.71
PRC 3352303PE2900 | 2022-09-14 | 165990.6 | 25771.68 | 55885.18 | 186298.84
PRC 3352303PF2900 | 2022-12-06 | 349174.39 | 55885.18 | 59885.18 | 335515.67
PRC 3352303PG2900 | 2023-01-10 | 25983.3 | 59885.18 | 59885.18 | 24683.63
PRC 3352303PH2900 | 2023-02-07 | 40517.16 | 59885.18 | 59885.18 | 38491.29
PRC 3352303PI2900 | 2023-04-12 | 125369.54 | 59885.18 | 67886.38 | 126702.19
PRC 3352303PJ2900 | 2023-05-05 | 37188.56 | 67886.38 | 67886.38 | 35329.13
PRC 3352303PK2900 | 2023-06-20 | 30605.85 | 67886.38 | 67886.38 | 29075.56
PRC 3352303PL2900 | 2023-07-07 | 34943.04 | 67886.38 | 67886.38 | 33195.88
PRC 3352403PM2900 | 2023-10-11 | 104481.87 | 67886.38 | 67886.38 | 99257.75
PRC 3352403PN2900 | 2023-11-09 | 96010.04 | 67886.38 | 67886.38 | 91209.51
PRC 3352403PO2900 | 2023-12-20 | 19836.96 | 67886.38 | 67886.38 | 18845.12
PRC 3352403PP2900 | 2024-03-18 | 70047.22 | 67886.38 | 67886.38 | 66629.31
PRC 3352403PQ2900 | 2024-04-08 | 61678.95 | 67886.38 | 67886.38 | 58594.99
PRC 3352403PR2900 | 2024-06-28 | 75277.36 | 67886.38 | 67886.38 | 75277.36
Begin in MM22 | 2024-07-05 |  | 67886.38 | 67886.38 | 0
PRC 3352503PS2900 | 2024-12-03 | 12350 | 67886.38 | 67886.38 | 12350
PRC 3352503PT2900 | 2024-12-16 | 67886.38 | 67886.38 | 0 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0

## RECAP #9180.01
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
| Program code 918001 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 150000
| Samuels Group |  | 20343.07 | 14354.9 | 5988.17
| PM TIME |  | 7400 | 6809.46 | 590.54
| Misc. |  | 0 | 0 | 0
C | S & S Plumbing, HVAC |  | 101448.35 | 101448.35 | 0
| KFI Engineers |  | 4500 | 2250 | 2250
| S & S Plumbing, HVAC |  | 7817 | 0 | 7817
| Total Project Cost | 150000 | 141508.42 | 124862.71 | 16645.71 | 8491.58

## #9180.01 Samuels Group
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010903 | 2024-04-10 | Moving PO From MM21 | 10603.93 | 10603.93 |  |  | 10603.93
PRC 3352401PD0903 | 2024-05-09 | Inv. 7667.04 PC |  | 10603.93 | 2296.74 | 2296.74 | 8307.19
PRC 3352401PE0903 | 2024-05-29 | Inv. 7667.05 PC |  | 10603.93 | 4254.72 | 6551.46 | 4052.47
PO 33524010903 | 2024-06-19 | CO #1 | 4745.82 | 15349.75 |  | 6551.46 | 8798.29
PRC 3352401PF0903 | 2024-07-05 | Inv. 7667.06 PC |  | 15349.75 | 471.5 | 7022.96 | 8326.79 | FY24
PO 33525010903 | 2024-07-18 | Rolled to FY25 |  | 15349.75 |  | 7022.96 | 8326.79
PRC 3352501PG0903 | 2024-08-15 | Inv. 7667.07 PC |  | 15349.75 | 2710.58 | 9733.54 | 5616.21
PO 33525010903 | 2024-09-23 | CO #2 | 4993.32 | 20343.07 |  | 9733.54 | 10609.53
PRC 3352501PH0903 | 2024-12-06 | Inv. 7667.08 PC |  | 20343.07 | 3460.69 | 13194.23 | 7148.84
PRC 3352501PI0903 | 2025-01-07 | Inv. 7667.09 PC |  | 20343.07 | 1160.67 | 14354.9 | 5988.17
|  |  |  | 20343.07 |  | 14354.9 | 5988.17
|  |  |  | 20343.07 |  | 14354.9 | 5988.17
|  |  |  | 20343.07 |  | 14354.9 | 5988.17
|  | Totals: | 20343.07 |  | 14354.9 |  | 5988.17
|  | MM21 Closed 04/10/24 | 3525.77 |  | 3525.77 |  | 0
|  | Total | 23868.84 |  | 17880.67 |  | 5988.17

## #9180.01 PM TIME
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2CS
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7400 | 7400 |  |  | 7400
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 7400 | 163.03 | 163.03 | 7236.97
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 7400 | 1447.7 | 1610.73 | 5789.27
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 7400 | 27.35 | 1638.08 | 5761.92
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 7400 | 226.2 | 1864.28 | 5535.72
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 7400 | 47.61 | 1911.89 | 5488.11
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 7400 | 435.7 | 2347.59 | 5052.41
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 7400 | 11.83 | 2359.42 | 5040.58
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 7400 | 128.8 | 2488.22 | 4911.78
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 7400 | 313.38 | 2801.6 | 4598.4
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 7400 | 1595.6 | 4397.2 | 3002.8
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 7400 | 62.55 | 4459.75 | 2940.25
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 7400 | 553 | 5012.75 | 2387.25
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 7400 | 59.44 | 5072.19 | 2327.81
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 7400 | 396.7 | 5468.89 | 1931.11
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 7400 | 75.05 | 5543.94 | 1856.06
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 7400 | 499.9 | 6043.84 | 1356.16
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 7400 | 41.07 | 6084.91 | 1315.09
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 7400 | 410.1 | 6495.01 | 904.99
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 7400 | 7.6 | 6502.61 | 897.39
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 7400 | 84.2 | 6586.81 | 813.19
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 7400 | 41.85 | 6628.66 | 771.34
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 7400 | 180.8 | 6809.46 | 590.54
[5 empty] | 7400 |  | 6809.46 | 590.54
[5 empty] | 7400 |  | 6809.46 | 590.54
[5 empty] | 7400 |  | 6809.46 | 590.54
|  |  | Totals: | 7400 |  | 6809.46 |  | 590.54

## #9180.01 Misc
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9180.01 S & S Plumbing, HVAC
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  | Major Program 4E01
S & S Plumbing HVAC |  |  | Vendor: 00003036947
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ918001-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524103915 | 2024-04-12 | PO Procore | 66318 | 66318 |  |  | 66318
PO 33524103915 | 2024-06-21 | CO #1 | 35130.35 | 101448.35 |  | 0 | 101448.35
PRC 3352410PA3915 | 2024-07-15 | Inv. 9180.01-01 |  | 101448.35 | 62052.1 | 62052.1 | 39396.25 | 3265.9 | FY24
PO 33525103915 | 2024-07-18 | Roll to FY25 |  | 101448.35 |  | 62052.1 | 39396.25
PRC 3352510PB3915 | 2024-12-04 | Inv. 9180.01-02 |  | 101448.35 | 34323.83 | 96375.93 | 5072.42 | 5072.42
PRC 3352510PC3915 | 2024-12-05 | Inv. 9180.01-03 Retainage |  | 101448.35 | 5072.42 | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  |  |  | 101448.35 |  | 101448.35 | 0
|  | Totals: | 101448.35 |  | 101448.35 |  | 0

## #9180.01 KFI Engineers
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  | Major Program 4E01
KFI Engineers |  |  | Vendor: VS000002170
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525242900 | 2024-08-29 | PO Procore | 4500 | 4500 |  |  | 4500
PRC 3352524PA2900 | 2024-12-18 | Inv. 68182 |  | 4500 | 2250 | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  |  |  | 4500 |  | 2250 | 2250
|  | Totals: | 4500 |  | 2250 |  | 2250

## #9180.01 S & S Plumbing, HV (2)
DOC IMCC Hot Water Piping Replacement
Project # 9180.01
Program code 918001 |  |  | Major Program 4E01
S & S Plumbing HVAC (2) |  |  | Vendor: 00003036947
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525310908 | 2024-11-05 | PO Procore | 7817 | 7817 |  |  | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  |  |  | 7817 |  | 0 | 7817
|  | Totals: | 7817 |  | 0 |  | 7817

## RECAP #9199.00
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
| Program code 919900 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 150737.42
C | Watersmith Engineering |  | 5387.5 | 5387.5 | 0
C | PM TIME |  | 2841.08 | 2841.08 | 0
C | Misc. |  | 1047.5 | 1047.5 | 0
C | Samuels Group CA |  | 13014.34 | 13014.34 | 0
C | Proctor Mechanical |  | 128447 | 128447 | 0
| Total Project Cost | 150737.42 | 150737.42 | 150737.42 | 0 | 0
Closed 01/13/25

## #9199.00 Watersmith Engineering
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
Program code 919900 |  |  | Major Program 4B02
Watersmith Engineering |  |  | Vendor: VS000000493
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524292501 | 2024-03-27 | Moved PO from MM21 | 5387.5 | 5387.5 |  |  | 5387.5
PRC 3352429PK2501 | 2024-07-11 | Inv. 1270106 |  | 5387.5 | 187.5 | 187.5 | 5200 | FY24
PO 33525292501A | 2024-07-15 | Roll to FY25 |  | 5387.5 |  | 187.5 | 5200
PRC 3352529PL2501A | 2024-09-06 | Inv. 1270107 |  | 5387.5 | 1774 | 1961.5 | 3426
PRC 3352529PM2501A | 2024-10-09 | Inv. 1270108 |  | 5387.5 | 2466 | 4427.5 | 960
PRC 3352529PN2501A | 2024-12-06 | Inv. 1270109 FINAL |  | 5387.5 | 960 | 5387.5 | 0
|  | Totals: | 5387.5 |  | 5387.5 |  | 0 | FINAL
|  | MM21(Closed 03/27/2024) | 15778.5 |  | 15778.5 |  | 0
|  | Total | 21166 |  | 21166 |  | 0

## #9199.00 PM TIME
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
Program code 919900 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 909I
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 2841.08 | 2841.08 |  |  | 2841.08
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 2841.08 | 35.14 | 35.14 | 2805.94
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 2841.08 | 314.8 | 349.94 | 2491.14
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 2841.08 | 40.47 | 390.41 | 2450.67
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 2841.08 | 334.9 | 725.31 | 2115.77
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 2841.08 | 4.32 | 729.63 | 2111.45
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 2841.08 | 43.7 | 773.33 | 2067.75
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 2841.08 | 10.28 | 783.61 | 2057.47
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 2841.08 | 113.5 | 897.11 | 1943.97
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 2841.08 | 71.41 | 968.52 | 1872.56
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 2841.08 | 363.7 | 1332.22 | 1508.86
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 2841.08 | 57.34 | 1389.56 | 1451.52
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 2841.08 | 510.4 | 1899.96 | 941.12
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 2841.08 | 28.94 | 1928.9 | 912.18
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 2841.08 | 193.6 | 2122.5 | 718.58
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 2841.08 | 32.47 | 2154.97 | 686.11
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 2841.08 | 213.6 | 2368.57 | 472.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 2841.08 | 43.31 | 2411.88 | 429.2
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 2841.08 | 429.2 | 2841.08 | 0
[5 empty] | 2841.08 |  | 2841.08 | 0
|  |  | Totals: | 2841.08 |  | 2841.08 |  | 0
Note on E9: Huggins, Joni [DAS]: Elliott, Jennie <jennie.elliott@iowa.gov> Wed, Mar 27, 2024 at 10:41 AM To: DAS Finance Payables Infrastructure <dasfinanceinfrastructure@iowa.gov> I need to move project 9199.00 from MM21 to MM22 and add additional funding. Per the email string below please: Open new project 9199.00 DHS IMHI Reynolds Water Main Replacement in MM22 for $173,000.00 Close Watersmith Engineering in MM21 and move remaining contract value of $5,387.50 to MM22 Close PM Time in MM21 and open new PM Time for $5,000 in MM22 Close Samuels Group CA in MM21 and move remaining contract value of $13,721.13 to MM22 Return remaining funds ($97,201.75) in 9199.00 MM21 to unallocated funds for MM21 Thank you, Jennie Elliott 9199.00 - DHS IMHI Reynolds Bldg Water Main Repl. and Witte Bldg. Water Main - Close Out $Joni Elliott, Jennie Jan 12, 2025, 1:05 PM (20 hours ago) to me, Scott Finance, Please reduce the PM time budget to $2,841.08 and close out project 9199.00 in MM22. This should return $22,262.58 to the Total Unassigned/Unallocated line in MM22. Thank you, Jennie Elliott

## #9199.00 Misc
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
Program code 919900 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524114910 | 2024-04-23 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2562470 | 1212.5 | 1212.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -165 | 1047.5
1047.5
1047.5
1047.5
1047.5
1047.5
1047.5
1047.5
|  |  |  | Totals: |  | 1047.5

## #9199.00 Samuels Group CA
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
Program code 919900 |  |  | Major Program 4B02
Samuels Group CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524143903 | 2024-03-27 | Moved PO from MM21 | 13721.13 | 13721.13 |  |  | 13721.13
PRC 3352414PP3903 | 2024-04-04 | Inv. 7412.25 CA |  | 13721.13 | 687.35 | 687.35 | 13033.78
PRC 3352414PQ3903 | 2024-05-13 | Inv. 7412.26 CA |  | 13721.13 | 473.58 | 1160.93 | 12560.2
PRC 3352414PR3903 | 2024-06-01 | Inv. 7412.27 CA |  | 13721.13 | 316.62 | 1477.55 | 12243.58
PRC 3352414PS3903 | 2024-07-11 | Inv. 7412.28 CA |  | 13721.13 | 156.96 | 1634.51 | 12086.62 | FY24
PO 33525143903 | 2024-07-15 | Roll to FY25 |  | 13721.13 |  | 1634.51 | 12086.62
PRC 3352514PT3903 | 2024-09-09 | Inv. 7412.29 CA |  | 13721.13 | 4731.6 | 6366.11 | 7355.02
PRC 3352514PU3903 | 2024-09-30 | Inv. 7412.30 CA |  | 13721.13 | 5343.7 | 11709.81 | 2011.32
PRC 3352514PV3903 | 2024-12-04 | Inv. 7412.31 CA - FINAL | -706.79 | 13014.34 | 1304.53 | 13014.34 | 0
|  | Totals: | 13014.34 |  | 13014.34 |  | 0 | FINAL
|  | MM21(Closed 03/27/2024) | 20562.15 |  | 20562.15 |  | 0
|  | Total | 33576.49 |  | 33576.49 |  | 0
|  | CM Services: | 20349.76 |  | 20349.76 |  | 0
|  | Reimbursables: | 931.28 |  | 931.28 |  | 0
|  | CO #1 | 12295.45 |  | 12295.45 |  | 0
|  | Total: | 33576.49 |  | 33576.49 |  | 0

## #9199.00 Proctor Mechanical
DHS IMHI Reynolds Water Main Replacement
Project # 9199.00
Program code 919900 |  |  | Major Program 4B02
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM22-9255 |  |  | MA 21010A
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524123901 | 2024-05-02 | PO Procore | 119500 | 119500 |  |  | 119500 | FY24
PO 33525123901 | 2024-07-18 | Roll to FY25 |  | 119500 |  | 0 | 119500
PO 33525123901 | 2024-09-12 | CO #1 | 8947 | 128447 |  | 0 | 128447
PRC 3352512PA3901 | 2024-10-17 | Inv. 7605.01 |  | 128447 | 121074.65 | 121074.65 | 7372.35 | 6372.35
PRC 3352512PB3901 | 2024-11-14 | Inv. 7605.02-Closeout |  | 128447 | 950 | 122024.65 | 6422.35 | 6422.35
PRC 3352512PC3901 | 2024-12-06 | Inv. 7605.03-Retainage |  | 128447 | 6422.35 | 128447 | 0
|  | Totals: | 128447 |  | 128447 |  | 0 | FINAL

## RECAP #9217.00
DHS WRC Main Transformer Replacement
Project # 9217.00
| Program code 921700 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 117671.8
C | Story Construction |  | 13575.16 | 13575.16 | 0
C | PM TIME |  | 8074.8 | 8074.8 | 0
C | Misc. |  | 194.15 | 194.15 | 0
C | Bluestone Engineering |  | 45912 | 45912 | 0
C | Story Construction (2) |  | 16705.5 | 16705.5 | 0
C | Waldinger Corporation |  | 33210.19 | 33210.19 | 0
| Total Project Cost | 117671.8 | 117671.8 | 117671.8 | 0 | 0
Closed 04/20/23

## #9217.00 Story Construction PC
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  | Major Program 4B02
Story Construction PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522204800 | 2021-07-23 | PO Procore | 14485.1 | 14485.1 |  |  | 14485.1
PRC 3352220PA4800 | 2021-09-15 | Inv. 32752 |  | 14485.1 | 2249.09 | 2249.09 | 12236.01
PRC 3352220PB4800 | 2021-10-18 | Inv. 32799 |  | 14485.1 | 768.5 | 3017.59 | 11467.51
PRC 3352220PC4800 | 2021-11-22 | Inv. 32841 |  | 14485.1 | 1419.01 | 4436.6 | 10048.5
PRC 3352220PD4800 | 2021-12-20 | Inv. 32894 |  | 14485.1 | 3375.96 | 7812.56 | 6672.54
PRC 3352220PE4800 | 2022-01-18 | Inv. 32937 |  | 14485.1 | 1969.93 | 9782.49 | 4702.61
PRC 3352220PF4800 | 2022-02-17 | Inv. 32979 |  | 14485.1 | 3546.97 | 13329.46 | 1155.64
PRC 3352220PG4800 | 2022-03-22 | Inv. 33021 |  | 14485.1 | 245.7 | 13575.16 | 909.94
PO 33522204800 | 2022-06-24 | Close PO per Vendor - final invoiced | -909.94 | 13575.16 |  | 13575.16 | 0
|  |  |  | 13575.16 |  | 13575.16 | 0
|  |  |  | 13575.16 |  | 13575.16 | 0
|  |  |  | 13575.16 |  | 13575.16 | 0
|  |  |  | 13575.16 |  | 13575.16 | 0
|  | Totals: | 13575.16 |  | 13575.16 |  | 0
|  | CM Services | 13562.29 |  | 13562.29 |  | 0
|  | Reimbursables | 12.87 |  | 12.87 |  | 0
|  | Total: | 13575.16 |  | 13575.16 |  | 0

## #9217.00 PM TIME
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906A
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 6765.94 | 6765.94 |  |  | 6765.94
IET DAS202201115300001 | 2021-08-06 |  | PM-July 01-July 22, 2021 |  | 6765.94 | 275 | 275 | 6490.94
IET DAS202202115300001 | 2021-09-08 |  | PM-Jul. 23-Aug. 19, 2021 |  | 6765.94 | 300 | 575 | 6190.94
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 6765.94 | 700 | 1275 | 5490.94
IET DAS202204115300001 | 2021-11-08 |  | PM-Oct 1-Oct 29, 2021 |  | 6765.94 | 375 | 1650 | 5115.94
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 6765.94 | 225 | 1875 | 4890.94
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 6765.94 | 125 | 2000 | 4765.94
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 6765.94 | 850 | 2850 | 3915.94
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 6765.94 | 250 | 3100 | 3665.94
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 6765.94 | 200 | 3300 | 3465.94
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 6765.94 | 250 | 3550 | 3215.94
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 6765.94 | 200 | 3750 | 3015.94
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 6765.94 | 50 | 3800 | 2965.94
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 6765.94 | 300 | 4100 | 2665.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 6765.94 | -300 | 3800 | 2965.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 6765.94 | 330 | 4130 | 2635.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 6765.94 | 165 | 4295 | 2470.94
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 6765.94 | 165 | 4460 | 2305.94
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 6765.94 | 165 | 4625 | 2140.94
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 6765.94 | 330 | 4955 | 1810.94
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 126.01 | 6891.95 | 126.01 | 5081.01 | 1810.94
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 152.33 | 7044.28 | 152.33 | 5233.34 | 1810.94
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 102.99 | 7147.27 | 102.99 | 5336.33 | 1810.94
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 129.71 | 7276.98 | 129.71 | 5466.04 | 1810.94
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 330.21 | 7607.19 | 330.21 | 5796.25 | 1810.94
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 7607.19 | 661.23 | 6457.48 | 1149.71
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 7607.19 | 62.42 | 6519.9 | 1087.29
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 7607.19 | 547.22 | 7067.12 | 540.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 76.33 | 7683.52 | 76.33 | 7143.45 | 540.07
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 89.84 | 7773.36 | 89.84 | 7233.29 | 540.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 42.8 | 7816.16 | 42.8 | 7276.09 | 540.07
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 89.43 | 7905.59 | 89.43 | 7365.52 | 540.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 70.29 | 7975.88 | 70.29 | 7435.81 | 540.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 98.92 | 8074.8 | 98.92 | 7534.73 | 540.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 8074.8 | 29.98 | 7564.71 | 510.09
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 8074.8 | 181.81 | 7746.52 | 328.28
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 8074.8 | 60.81 | 7807.33 | 267.47
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 8074.8 | 267.47 | 8074.8 | 0
|  |  | Totals: | 8074.8 |  | 8074.8 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: MM22 Project 9217.00 Jennifer Kleene, Jennifer Aug 3, 2021, 7:57 AM (1 day ago) to me Please create a PM Time budget of $4,000.00 for project 9217.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative PM Time Budget Increases $Joni Kleene, Jennifer Wed, Jun 1, 4:55 PM (16 hours ago) to me, Scott Please increase the PM Time budget for MM19 9064.00 by $1,000.00. Please increase the PM Time budget for MM19 9180.00 by $1,000.00. Please increase the PM Time budget for MM22 9217.00 by $2,500.00. Please increase the PM Time budget for DA20 9159.00 by $1,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes $Joni Kleene, Jennifer Fri, Feb 3, 4:46 PM (3 days ago) to me, Scott Please increase the PM Time budget for DA22 9216.00 by $10,000.00. Please increase the PM Time budget for MM22 9217.00 by $1,100.00. Please increase the PM Time budget for MM22 9279.00 by $4,400.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 12:42 PM (31 minutes ago) to me, Scott, Clinton All invoices have been paid and all DAS Services costs have been posted, so please close both projects. For DA22 9217.01, please return the remaining balance of $41,100.97 to WRC. Regards, Jennifer

## #9217.00 Misc
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522041900 | 2022-02-10 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 419088-0 | 194.15 | 194.15
194.15
194.15
194.15
194.15
194.15
194.15
194.15
194.15
194.15
194.15
194.15
|  |  |  | Totals: |  | 194.15

## #9217.00 Bluestone Engineering
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  | Major Program 4B02
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0017-335-MM22-9260 |  |  | IRFP921700-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Split with 9217.01 DA22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522238802 | 2021-08-24 | PO Procore | 45912 | 45912 |  |  | 45912
PRC 3352223PA8802 | 2021-09-08 | Inv. 11255 |  | 45912 | 3500 | 3500 | 42412
PRC 3352223PB8802 | 2021-10-07 | Inv. 11290 |  | 45912 | 10070.5 | 13570.5 | 32341.5
PO 33522238802 | 2021-10-08 | CO 1 (100% to DA22) | 0 | 45912 |  | 13570.5 | 32341.5
PRC 3352223PC8802 | 2021-11-17 | Inv. 11349 (100% to MM22) |  | 45912 | 13531 | 27101.5 | 18810.5
PRC 3352223PD8802 | 2021-12-09 | Inv. 11416 (split between MM22 & DA22) |  | 45912 | 4503.75 | 31605.25 | 14306.75
PRC 3352223PE8802 | 2021-01-24 | Inv. 11506 (100% to MM22) |  | 45912 | 4503.75 | 36109 | 9803
PO 33522238802 | 2022-02-08 | CO 2(100% to DA22) | 0 | 45912 |  | 36109 | 9803
PRC 3352223PF8802 | 2022-02-09 | Inv. 11558(split between DA22 & MM22) |  | 45912 | 1496.25 | 37605.25 | 8306.75
PRC 3352223PG8802 | 2022-03-22 | Inv. 11600(split between DA22 & MM22) |  | 45912 | 498.75 | 38104 | 7808
PRC 3352223PH8802 | 2022-07-26 | Inv. 11872(100% to MM22) |  | 45912 | 1171.2 | 39275.2 | 6636.8 | FY22
PO 33523238802 | 2022-08-30 | Rolled to FY23 | 0 | 45912 |  | 39275.2 | 6636.8
PRC 3352323PI8802 | 2022-08-31 | Inv. 11963 (100% to MM22) |  | 45912 | 780.8 | 40056 | 5856
PRC 3352323PJ8802 | 2022-10-06 | Inv. 11989 (Split between DA22 & MM22) |  | 45912 | 2732.8 | 42788.8 | 3123.2
PRC 3352323PK8802 | 2023-01-19 | Inv. 12201 (Split between DA22 & MM22) |  | 45912 | 2732.8 | 45521.6 | 390.4
PRC 3352323PL8802 | 2023-02-22 | Inv. 12310 - FINAL (Split between DA22 & MM22) |  | 45912 | 390.4 | 45912 | 0
|  |  |  | 45912 |  | 45912 | 0
|  |  |  | 45912 |  | 45912 | 0
|  |  |  | 45912 |  | 45912 | 0
|  |  |  | 45912 |  | 45912 | 0
|  |  |  | 45912 |  | 45912 | 0
|  | Totals: | 45912 |  | 45912 |  | 0 | FINAL
|  | Site survey & Design Development Document Phase | 18094 |  | 18094 |  | 0
|  | Construction Document Phase | 18015 |  | 18015 |  | 0
|  | Bidding | 1995 |  | 1995 |  | 0
|  | Construction Phase | 7808 |  | 7808 |  | 0
|  | Total: | 45912 |  | 45912 |  | 0
|  | 9217.01 DA22 | 17458 |  | 17458 |  | 2.2737e-13
|  | Total Contract: | 63370 |  | 63370 |  | 2.2737e-13

## #9217.00 Story Construction CA
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  | Major Program 4B02
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522115800 | 2022-04-22 | PO Procore | 16985.08 | 16985.08 |  |  | 16985.08
PRC 3352211PA5800 | 2022-06-21 | Inv. 33159 |  | 16985.08 | 1515 | 1515 | 15470.08
PRC 3352211PB5800 | 2022-07-20 | Inv. 33210 |  | 16985.08 | 238.5 | 1753.5 | 15231.58 | FY22
PO 33523115800 | 2022-08-08 | Rolled to FY23 | 0 | 16985.08 |  | 1753.5 | 15231.58
PRC 3352311PC5800 | 2022-08-24 | Inv. 33267 |  | 16985.08 | 1458 | 3211.5 | 13773.58
PRC 3352311PD5800 | 2022-09-26 | Inv. 33332 |  | 16985.08 | 1203 | 4414.5 | 12570.58
PRC 3352311PE5800 | 2022-10-18 | Inv. 33391 |  | 16985.08 | 2028 | 6442.5 | 10542.58
PRC 3352311PF5800 | 2022-11-21 | Inv. 33449 |  | 16985.08 | 1514.5 | 7957 | 9028.08
PRC 3352311PG5800 | 2022-12-19 | Inv. 33505 |  | 16985.08 | 2588 | 10545 | 6440.08
PRC 3352311PH5800 | 2023-01-20 | Inv. 33573 |  | 16985.08 | 1896 | 12441 | 4544.08
PRC 3352311PI5800 | 2023-02-16 | Inv. 33625 |  | 16985.08 | 4026 | 16467 | 518.08
PRC 3352311PJ5800 | 2023-03-22 | Inv. 33677 - FINAL | -279.58 | 16705.5 | 238.5 | 16705.5 | 1.7621e-12
|  |  |  | 16705.5 |  | 16705.5 | 1.7621e-12
|  | Totals: | 16705.5 |  | 16705.5 |  | 0 | FINAL
|  | CM Services | 16685.5 |  | 16685.5 |  | 0
|  | Reimbursables | 20 |  | 20 |  | 0
|  | Total: | 16705.5 |  | 16705.5 |  | 0

## #9217.00 Waldinger Corporation
DHS WRC Main Transformer Replacement
Project # 9217.00
Program code 921700 |  |  | Major Program 4B02
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | 005 20452
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522143902 | 2022-05-20 | PO Procore | 91777 | 91777 |  |  | 91777 | FY22
PO 33523143902 | 2022-08-08 | Rolled to FY23 | 0 | 91777 |  | 0 | 91777
PO 33523143902 | 2022-10-31 | CO 1(No cost CO) | 0 | 91777 |  | 0 | 91777
PRC 3352314PA3902 | 2022-12-22 | Inv. 65201E-001 |  | 91777 | 14003.33 | 14003.33 | 77773.67 | 737.01
PO 33523143902 | 2022-12-29 | CO #2 | -58566.81 | 33210.19 |  | 14003.33 | 19206.86
PRC 3352314PB3902 | 2023-02-07 | Inv. 65201E-002 |  | 33210.19 | 17546.36 | 31549.69 | 1660.5 | 1660.5
PRC 3352314PC3902 | 2023-02-20 | Inv. 65201E-003-Retainage |  | 33210.19 | 1660.5 | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  |  |  | 33210.19 |  | 33210.19 | 0
|  | Totals: | 33210.19 |  | 33210.19 |  | 0

## RECAP #9218.00
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
| Program code 921800 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 86054.48
C | Story Construction PC |  | 5938.28 | 5938.28 | 0
C | PM TIME |  | 2125 | 2125 | 0
C | Misc. |  | 2140.2 | 2140.2 | 0
C | Genesis Architectural Design |  | 13750 | 13750 | 0
C | Academy Roofing |  | 39300 | 39300 | 0
C | Story Construction CA |  | 22801 | 22801 | 0
| Total Project Cost | 86054.48 | 86054.48 | 86054.48 | 0 | 0
Closed 08/04/22

## #9218.00 Story Construction PC
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  | Major Program 4E02
Story Construction PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522223800 | 2021-08-06 | PO Procore | 14603.04 | 14603.04 |  |  | 14603.04
PRC 3352222PA3800 | 2021-10-19 | Inv. 32800 |  | 14603.04 | 1542.72 | 1542.72 | 13060.32
PRC 3352222PB3800 | 2021-11-17 | Inv. 32842 |  | 14603.04 | 1589.48 | 3132.2 | 11470.84
PRC 3352222PC3800 | 2021-12-16 | Inv. 32895 |  | 14603.04 | 1705.3 | 4837.5 | 9765.54
PRC 3352222PD3800 | 2022-01-18 | Inv. 32938-Final | -8664.76 | 5938.28 | 1100.78 | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  |  |  | 5938.28 |  | 5938.28 | 0
|  | Totals: | 5938.28 |  | 5938.28 |  | 0 | Final Invoice
|  | CM Services | 5919.56 |  | 5919.56 |  | 0
|  | Reimbursables | 18.72 |  | 18.72 |  | 0
|  | Total: | 5938.28 |  | 5938.28 |  | 0

## #9218.00 PM TIME
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 2152.5 | 2152.5 |  |  | 2152.5
IET DAS202201115300001 | 2021-08-06 | PM-July 01-July 22, 2021 |  | 2152.5 | 50 | 50 | 2102.5
IET DAS202202115300001 | 2021-09-08 | PM-Jul. 23-Aug. 19, 2021 |  | 2152.5 | 75 | 125 | 2027.5
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 2152.5 | 475 | 600 | 1552.5
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 2152.5 | 350 | 950 | 1202.5
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 2152.5 | 200 | 1150 | 1002.5
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 2152.5 | 75 | 1225 | 927.5
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 2152.5 | 175 | 1400 | 752.5
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 2152.5 | 100 | 1500 | 652.5
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 2152.5 | 25 | 1525 | 627.5
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 2152.5 | 125 | 1650 | 502.5
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 2152.5 | 150 | 1800 | 352.5
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 2152.5 | 325 | 2125 | 27.5
IET DAS202201115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 2152.5 | 25 | 2150 | 2.5
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 2152.5 | -25 | 2125 | 27.5
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 2152.5 | 27.5 | 2152.5 | 0
CDE 33523236904 | 2022-08-24 | Moving PM Time to 9219.00 | -27.5 | 2125 | -27.5 | 2125 | 0
|  |  |  | 2125 |  | 2125 | 0
|  |  |  | 2125 |  | 2125 | 0
|  | Totals: | 2125 |  | 2125 |  | 0
Note on D9: Jenkins, Jennifer [DAS]: MM22 9218.00 PM Time Budget Jennifer Kleene, Jennifer 8:57 PM (1 hour ago) to me Please create a PM Time budget for $3,000.00 for 9218.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative MM22 9218.00 PM Time budget change $Joni Kleene, Jennifer Mon, Jun 20, 4:09 PM (15 hours ago) to me, Scott Please reduce the PM time budget by $300.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Re: Please close MM22 Project 9218.00 Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> (sent by selma.durakovic@iowa.gov) Aug 4, 2022, 10:31 AM (7 days ago) to Jennifer, Scott Project #9218.00 has been closed & removed from the billing file. Thank you, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov On Tue, Jul 26, 2022 at 10:44 AM Kleene, Jennifer <jennifer.kleene@iowa.gov> wrote: All invoices have been paid and all PM time has posted, so please close project 9218.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9218.00 Misc
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522347903 | 2021-12-13 | 9500 | CMGR | ATC Group V#(00002134218) | Inv. 2387664 | 816.25 | 816.25
GAX 33522173804 | 2022-06-22 | 9500 | CNST | Controlled Asbestos V#00002118118 | Inv. 0010386-IN | 1323.95 | 2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
2140.2
|  |  |  | Totals: |  | 2140.2

## #9218.00 Genesis Design
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  | Major Program 4E02
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 921800-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522272802 | 2021-09-29 | PO Procore | 13750 | 13750 |  |  | 13750
PRC 3352227PA2802 | 2021-10-22 | Inv. 2112.01-01 |  | 13750 | 3780 | 3780 | 9970
PRC 3352227PB2802 | 2021-11-30 | Inv. 2112.01-02 |  | 13750 | 4420 | 8200 | 5550
PRC 3352227PC2802 | 2022-02-08 | Inv. 2112.01-03 |  | 13750 | 1250 | 9450 | 4300
PRC 3352227PD2802 | 2022-06-23 | Inv. 2112.01-04 |  | 13750 | 4300 | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  |  |  | 13750 |  | 13750 | 0
|  | Totals: | 13750 |  | 13750 |  | 0 | Final Invoice
|  | Design Development | 4200 |  | 4200 |  | 0
|  | Construction Documents | 4000 |  | 4000 |  | 0
|  | Bid Phase | 1250 |  | 1250 |  | 0
|  | Construction Phase | 4300 |  | 4300 |  | 0
|  | Total: | 13750 |  | 13750 |  | 0

## #9218.00 Academy Roofing
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  | Major Program 4E02
Academy Roofing |  |  | Vendor: 00003010234
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ921800-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522013900 | 2022-01-12 | PO Procore | 39300 | 39300 |  |  | 39300
PO 33522013900 | 2022-01-27 | Edit from DA21 to MM22 as per procore | 0 | 39300 |  | 0 | 39300
PRC 3352201PA3900 | 2022-05-13 | Inv. 122216901 |  | 39300 | 36385 | 36385 | 2915 | 1915
PRC 3352201PB3900 | 2022-06-16 | Inv. 122216902 |  | 39300 | 950 | 37335 | 1965 | 1965
PRC 3352201PC3900 | 2022-06-20 | Inv. 122216999-Retainage |  | 39300 | 1965 | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  |  |  | 39300 |  | 39300 | 0
|  | Totals: | 39300 |  | 39300 |  | 0

## #9218.00 Story Construction CA
DHS STS Kitchen Storage Roof Replacement
Project # 9218.00
Program code 921800 |  |  | Major Program 4E02
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522021900 | 2022-01-21 | PO Procore | 23147.52 | 23147.52 |  |  | 23147.52
PO 33522021900 | 2022-01-25 | Edit from DA22 to MM22 | 0 | 23147.52 |  | 0 | 23147.52
PRC 3352202PA1900 | 2022-03-23 | Inv. 33023 |  | 23147.52 | 5891.25 | 5891.25 | 17256.27
PRC 3352202PB1900 | 2022-04-28 | Inv. 33070 |  | 23147.52 | 1104 | 6995.25 | 16152.27
PRC 3352202PC1900 | 2022-05-20 | Inv. 33113 |  | 23147.52 | 3734.75 | 10730 | 12417.52
PRC 3352202PD1900 | 2022-06-20 | Inv. 33160 |  | 23147.52 | 10424 | 21154 | 1993.52
PRC 3352202PE1900 | 2022-07-20 | Inv. 33211(Final) | -346.52 | 22801 | 1647 | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  |  |  | 22801 |  | 22801 | 0
|  | Totals: | 22801 |  | 22801 |  | 0
|  | CM Services | 22801 |  | 22801 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 22801 |  | 22801 |  | 0

## RECAP #9219.00
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
| Program code 921900 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 121952.44
C | Story Construction PC |  | 8295.4 | 8295.4 | 0
C | PM TIME |  | 5418.47 | 5418.47 | 0
C | Misc. |  | 1112.5 | 1112.5 | 0
C | Genesis Architectural |  | 15500 | 15500 | 0
C | Story Construction CA |  | 22224 | 22224 | 0
C | Controlled Asbestos |  | 3529.63 | 3529.63 | 0
C | E & H Restoration |  | 65872.44 | 65872.44 | 0
| Total Project Cost | 121952.44 | 121952.44 | 121952.44 | 0 | 0
Closed 02/17/2023

## #9219.00 Story Construction PC
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
Story Construction PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522224800 | 2021-08-12 | PO Procore | 15157.23 | 15157.23 |  |  | 15157.23
PRC 3352222PA4800 | 2021-09-24 | Inv. 32753 |  | 15157.23 | 145.04 | 145.04 | 15012.19
PRC 3352222PB4800 | 2021-10-18 | Inv. 32801 |  | 15157.23 | 1386 | 1531.04 | 13626.19
PRC 3352222PC4800 | 2021-11-22 | Inv. 32843 |  | 15157.23 | 1127.31 | 2658.35 | 12498.88
PRC 3352222PD4800 | 2021-12-16 | Inv. 32896 |  | 15157.23 | 996.33 | 3654.68 | 11502.55
PRC 3352222PE4800 | 2022-01-18 | Inv. 32939 |  | 15157.23 | 900 | 4554.68 | 10602.55
PRC 3352222PF4800 | 2022-02-17 | Inv. 32981 |  | 15157.23 | 3047.45 | 7602.13 | 7555.1
PRC 3352222PG4800 | 2022-03-23 | Inv. 33024-Final PC | -6861.83 | 8295.4 | 693.27 | 8295.4 | 0
|  |  |  | 8295.4 |  | 8295.4 | 0
|  |  |  | 8295.4 |  | 8295.4 | 0
|  |  |  | 8295.4 |  | 8295.4 | 0
|  |  |  | 8295.4 |  | 8295.4 | 0
|  |  |  | 8295.4 |  | 8295.4 | 0
|  | Totals: | 8295.4 |  | 8295.4 |  | 0
|  | CM Services | 8295.4 |  | 8295.4 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 8295.4 |  | 8295.4 |  | 0

## #9219.00 PM TIME
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx |  |  | eDAS 906C
Project Manager - Jennifer K
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 4328.54 | 4328.54 |  |  | 4328.54
IET DAS202202115300001 | 2021-09-08 | PM-Jul. 23-Aug. 19, 2021 |  | 4328.54 | 150 | 150 | 4178.54
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 4328.54 | 950 | 1100 | 3228.54
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 4328.54 | 175 | 1275 | 3053.54
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 4328.54 | 250 | 1525 | 2803.54
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 4328.54 | 75 | 1600 | 2728.54
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 4328.54 | 225 | 1825 | 2503.54
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 4328.54 | 300 | 2125 | 2203.54
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 4328.54 | 75 | 2200 | 2128.54
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 4328.54 | 25 | 2225 | 2103.54
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 4328.54 | 100 | 2325 | 2003.54
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 4328.54 | 25 | 2350 | 1978.54
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 4328.54 | 100 | 2450 | 1878.54
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 4328.54 | -100 | 2350 | 1978.54
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 4328.54 | 110 | 2460 | 1868.54
CDE 33523236904 | 2022-08-24 | Moving PM Time from 9218.00 MM22 |  | 4328.54 | 27.5 | 2487.5 | 1841.04
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 4328.54 | 110 | 2597.5 | 1731.04
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 4328.54 | 192.5 | 2790 | 1538.54
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 4328.54 | 577.5 | 3367.5 | 961.04
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30,2022 |  | 4328.54 | 385 | 3752.5 | 576.04
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 28.99 | 4357.53 | 28.99 | 3781.49 | 576.04
IET DAS202205115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 101.56 | 4459.09 | 101.56 | 3883.05 | 576.04
IET DAS202205115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 120.16 | 4579.25 | 120.16 | 4003.21 | 576.04
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 453.97 | 5033.22 | 453.97 | 4457.18 | 576.04
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 385.25 | 5418.47 | 385.25 | 4842.43 | 576.04
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 5418.47 | 220.41 | 5062.84 | 355.63
IET DAS202307115300001 | 2023-02-07 | Finance Support for: January 1-31, 2023 |  | 5418.47 | 36.42 | 5099.26 | 319.21
IET DAS202307115300001 | 2023-02-07 | DAS Services For: January 1-31, 2023 |  | 5418.47 | 319.21 | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  |  |  | 5418.47 |  | 5418.47 | 0
|  | Totals: | 5418.47 |  | 5418.47 |  | 0
Note on D9: Wray, Ronda [DAS]: PM Time Budgets $Ronda Kleene, Jennifer Please close MM22 Project 9219.00 $Joni Kleene, Jennifer 9:07 AM (1 hour ago) to me, Scott All DAS costs have been posted and all invoices have been paid, so please closeout MM22 project 9219.00 and remove it from the billing sheet. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Aug 7, 2021, 1:16 PM (5 days ago) to me Please create the following PM Time budgets: MM22 9054.03 $4,000.00 MM22 9219.00 $4,000.00 Please increase the PM Time Budget for MM20 8982.01 by $800.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative PM Time Budget Changes $Joni Kleene, Jennifer Fri, Jan 6, 4:07 PM (3 days ago) to me, Scott Please make the following changes: MM22 Project 9219.00 - increase PM time by $770.00. DA22 Project 9217.01 - increase PM time by $550.00. DA20 Project 9159.00 - increase PM time by $550.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close MM22 Project 9219.00 $Joni Kleene, Jennifer 9:07 AM (1 hour ago) to me, Scott All DAS costs have been posted and all invoices have been paid, so please closeout MM22 project 9219.00 and remove it from the billing sheet. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9219.00 Misc
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522349901 | 2021-12-15 | 9500 | CMGR | ATC Group V#(00002134218) | Inv. 2387674-Final | 552.5 | 552.5
GAX 33522038901 | 2022-02-04 | 9500 | CNST | MTS Contracting V#(00003067019) | Inv. 21-4001 | 560 | 1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
1112.5
|  |  |  | Totals: |  | 1112.5

## #9219.00 Genesis Architectural
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | 921800-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522272502 | 2021-09-29 | PO Procore | 15500 | 15500 |  |  | 15500
PRC 3352227PA2502 | 2021-10-22 | Inv. 2112.02-01 |  | 15500 | 1960 | 1960 | 13540
PRC 3352227PB2502 | 2021-11-30 | Inv. 2112.02-02 |  | 15500 | 3710 | 5670 | 9830
PRC 3352227PC2502 | 2021-12-16 | Inv. 2112.02-03 |  | 15500 | 2310 | 7980 | 7520
PRC 3352227PD2502 | 2022-02-08 | Inv. 2112.02-04 |  | 15500 | 2020 | 10000 | 5500
PRC 3352227PE2502 | 2022-07-14 | Inv. 2112.02-05 |  | 15500 | 440 | 10440 | 5060 | FY22
PO 33523272502 | 2022-08-08 | Rolled to FY23 | 0 | 15500 |  | 10440 | 5060
PRC 3352327PF2502 | 2022-09-28 | Inv. 2112.02-06 |  | 15500 | 3135 | 13575 | 1925
PRC 3352327PG2502 | 2023-01-04 | Inv. 2112.02-07 FINAL |  | 15500 | 1925 | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  |  |  | 15500 |  | 15500 | 0
|  | Totals: | 15500 |  | 15500 |  | 0 | Final
|  | Design Development | 4900 |  | 4900 |  | 0
|  | Construction Documents | 3850 |  | 3850 |  | 0
|  | Bid Phase | 1250 |  | 1250 |  | 0
|  | Construction Phase | 5500 |  | 5500 |  | 0
|  | Total: | 15500 |  | 15500 |  | 0

## #9219.00 Story Construction CA
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522042902 | 2022-09-10 | PO Procore | 24678.6 | 24678.6 |  |  | 24678.6
PRC 3352204PA2902 | 2022-03-23 | Inv. 33025 |  | 24678.6 | 1629.25 | 1629.25 | 23049.35
PRC 3352204PB2902 | 2022-04-28 | Inv. 33071 |  | 24678.6 | 2145 | 3774.25 | 20904.35
PRC 3352204PC2902 | 2022-05-19 | Inv. 33114 |  | 24678.6 | 891.75 | 4666 | 20012.6
PRC 3352204PD2902 | 2022-06-20 | Inv. 33161 |  | 24678.6 | 5207 | 9873 | 14805.6
PRC 3352204PE2902 | 2022-07-18 | Inv. 33212 |  | 24678.6 | 4585.5 | 14458.5 | 10220.1 | FY22
PO 33523042902 | 2022-08-08 | Rolled to FY23 | 0 | 24678.6 |  | 14458.5 | 10220.1
PRC 3352304PF2902 | 2022-08-24 | Inv. 33268 |  | 24678.6 | 2340 | 16798.5 | 7880.1
PRC 3352304PG2902 | 2022-09-20 | Inv. 33333 |  | 24678.6 | 2521.5 | 19320 | 5358.6
PRC 3352304PH2902 | 2022-10-17 | Inv. 33392 |  | 24678.6 | 1485 | 20805 | 3873.6
PRC 3352304PI2902 | 2022-11-21 | Inv. 33450 |  | 24678.6 | 978 | 21783 | 2895.6
PRC 3352304PJ2902 | 2022-12-19 | Inv. 33506 |  | 24678.6 | 252 | 22035 | 2643.6
PRC 3352304PK2902 | 2023-01-23 | Inv. 33574-FINAL | -2454.6 | 22224 | 189 | 22224 | 0
|  |  |  | 22224 |  | 22224 | 0
|  |  |  | 22224 |  | 22224 | 0
|  |  |  | 22224 |  | 22224 | 0
|  |  |  | 22224 |  | 22224 | 0
|  | Totals: | 22224 |  | 22224 |  | 0 | Final
|  | CM Services | 22224 |  | 22224 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 22224 |  | 22224 |  | 0

## #9219.00 Controlled Asbestos
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | MA00521060
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522045902 | 2022-02-14 | DO Procore | 5366.26 | 5366.26 |  |  | 5366.26
PRC 3352204PA5902 | 2022-07-28 | Inv. 0010394-IN |  | 5366.26 | 3529.63 | 3529.63 | 1836.63 | FY22
DO 33523045902 | 2022-08-08 | Rolled to FY23 | 0 | 5366.26 |  | 3529.63 | 1836.63
DO 33523045902 | 2022-12-09 | Closing per PM Request | -1836.63 | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  |  |  | 3529.63 |  | 3529.63 | 0
|  | Totals: | 3529.63 |  | 3529.63 |  | 0
|  | Contract Line 1: Asbestos Abatement Services (84hrs x $58/hr) | 3190 |  | 3190 |  | 0
|  | Contract Line 7: Materials | 166.47 |  | 166.47 |  | 0
|  | Contract Line 11: Non-Friable Disposal Fee | 0 |  |  |  | 0
|  | Contract Line 12: Mileage (592 miles x $0.39/mile) | 173.16 |  | 173.16 |  | 0
|  | Total: | 3529.63 |  | 3529.63 |  | 0

## #9219.00 E & H Restoration
DHS STS Maintenance Main Building Tuckpointing
Project # 9219.00
Program code 921900 |  |  | Major Program 4E10
E & H Restoration |  |  | Vendor: 00002101642
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ921900-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522052900 | 2022-02-18 | PO Procore | 66792 | 66792 |  |  | 66792 | FY22
PO 33523052900 | 2022-08-08 | Rolled to FY23 | 0 | 66792 |  | 0 | 66792
PO 33523052900 | 2022-10-28 | CO 1 | -919.56 | 65872.44 |  | 0 | 65872.44
PRC 3352305PA2900 | 2022-11-17 | Inv. 22052-002 |  | 65872.44 | 59449.86 | 59449.86 | 6422.58 | 3128.96
PRC 3352305PB2900 | 2022-12-15 | Inv. 22052R - 002 |  | 65872.44 | 3128.92 | 62578.78 | 3293.66 | 3293.66
PRC 3352305PC2900 | 2022-12-21 | Inv. 22078-002-retainage |  | 65872.44 | 3293.66 | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  |  |  | 65872.44 |  | 65872.44 | 0
|  | Totals: | 65872.44 |  | 65872.44 |  | 0

## RECAP #9226.00
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
| Program code 922600 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 207100.61
C | Story Construction PC |  | 23961.42 | 23961.42 | 0
C | PM TIME |  | 27499.2 | 27499.2 | 0
C | Misc. |  | 4531.62 | 4531.62 | 0
C | Genesis Architectural Design |  | 41803 | 41803 | 0
C | Bi-State Masonry |  | 69050 | 69050 | 0
C | Story Construction CA |  | 21302.42 | 21302.42 | 0
C | Wapsi Valley Archeology |  | 6917.48 | 6917.48 | 0
C | Controlled Asbestos |  | 1516.57 | 1516.57 | 0
C | Boyd Jones |  | 6752.49 | 6752.49 | 0
C | DCI Group |  | 3766.41 | 3766.41 | 0
| Total Project Cost | 207100.61 | 207100.61 | 207100.61 | 0 | 0
Closed 03/25/25

## #9226.00 Story Construction PC
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Story Construction PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522270800 | 2021-09-24 | PO Procore | 13323.86 | 13323.86 |  |  | 13323.86
PRC 3352227PA0800 | 2021-11-18 | Inv. 32846 |  | 13323.86 | 3054.67 | 3054.67 | 10269.19
PRC 3352227PB0800 | 2021-12-17 | Inv. 32901 |  | 13323.86 | 1404.94 | 4459.61 | 8864.25
PRC 3352227PC0800 | 2022-01-17 | Inv. 32944 |  | 13323.86 | 1398.44 | 5858.05 | 7465.81
PRC 3352227PD0800 | 2022-02-17 | Inv. 32986 |  | 13323.86 | 484.91 | 6342.96 | 6980.9
PRC 3352227PE0800 | 2022-03-25 | Inv. 33030 |  | 13323.86 | 1339.99 | 7682.95 | 5640.91
PRC 3352227PF0800 | 2022-04-28 | Inv. 33076 |  | 13323.86 | 3349.96 | 11032.91 | 2290.95
PRC 3352227PG0800 | 2022-05-19 | Inv. 33119 |  | 13323.86 | 1702.59 | 12735.5 | 588.36
PO 33522270800 | 2022-06-10 | CO 1 | 13920.18 | 27244.04 |  | 12735.5 | 14508.54
PRC 3352227PH0800 | 2022-07-18 | Inv. 33217 |  | 27244.04 | 2499.57 | 15235.07 | 12008.97 | FY22
PO 33523270800 | 2022-08-08 | Rolled to FY23 | 0 | 27244.04 |  | 15235.07 | 12008.97
PRC 3352327PI0800 | 2022-08-26 | Inv. 33273 |  | 27244.04 | 1097.53 | 16332.6 | 10911.44
PRC 3352327PJ0800 | 2022-09-20 | Inv. 33338 |  | 27244.04 | 694.89 | 17027.49 | 10216.55
PRC 3352327PK0800 | 2022-10-20 | Inv. 33397 |  | 27244.04 | 1069.39 | 18096.88 | 9147.16
PRC 3352327PL0800 | 2022-11-28 | Inv. 33455 |  | 27244.04 | 1034.95 | 19131.83 | 8112.21
PRC 3352327PM0800 | 2022-12-22 | Inv. 33510 |  | 27244.04 | 173.18 | 19305.01 | 7939.03
PRC 3352327PN0800 | 2023-02-19 | Inv. 33627 |  | 27244.04 | 1517.5 | 20822.51 | 6421.53
PRC 3352327PO0800 | 2023-03-17 | Inv. 33678 |  | 27244.04 | 1969.94 | 22792.45 | 4451.59
PRC 3352327PP0800 | 2023-04-17 | Inv. 33725 |  | 27244.04 | 952.49 | 23744.94 | 3499.1
PRC 3352327PQ0800 | 2023-07-17 | Inv. 33887 |  | 27244.04 | 216.48 | 23961.42 | 3282.62
PO 33523270800 | 2023-08-03 | Close Per PM & Vendor | -3282.62 | 23961.42 |  | 23961.42 | 0
|  |  |  | 23961.42 |  | 23961.42 | 0
|  | Totals: | 23961.42 |  | 23961.42 |  | 0 | Final
|  | CM Services | 12672.56 |  | 12672.56 |  | 0
|  | Reimbursables | 187.98 |  | 187.98 |  | 0
|  | CO #1 | 11100.88 |  | 11100.88 |  | 0
|  | Total: | 23961.42 |  | 23961.42 |  | 0

## #9226.00 PM TIME
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906K
Project Manager - James T
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 24857.64 | 24857.64 |  |  | 24857.64
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 24857.64 | 700 | 700 | 24157.64
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 24857.64 | 1050 | 1750 | 23107.64
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 24857.64 | 850 | 2600 | 22257.64
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 24857.64 | 675 | 3275 | 21582.64
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 24857.64 | 300 | 3575 | 21282.64
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 24857.64 | 650 | 4225 | 20632.64
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 24857.64 | 700 | 4925 | 19932.64
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 24857.64 | 1025 | 5950 | 18907.64
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 24857.64 | 1150 | 7100 | 17757.64
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 24857.64 | 925 | 8025 | 16832.64
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 24857.64 | 450 | 8475 | 16382.64
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 24857.64 | -450 | 8025 | 16832.64
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 24857.64 | 495 | 8520 | 16337.64
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 24857.64 | 687.5 | 9207.5 | 15650.14
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 24857.64 | 742.5 | 9950 | 14907.64
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 24857.64 | 907.5 | 10857.5 | 14000.14
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 24857.64 | 275 | 11132.5 | 13725.14
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 202.39 | 25060.03 | 202.39 | 11334.89 | 13725.14
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 584.6 | 25644.63 | 584.6 | 11919.49 | 13725.14
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 399.6 | 26044.23 | 399.6 | 12319.09 | 13725.14
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 662.63 | 26706.86 | 662.63 | 12981.72 | 13725.14
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 210.81 | 26917.67 | 210.81 | 13192.53 | 13725.14
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 26917.67 | 422.7 | 13615.23 | 13302.44
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 26917.67 | 196.98 | 13812.21 | 13105.46
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 26917.67 | 1726.87 | 15539.08 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 98.42 | 27016.09 | 98.42 | 15637.5 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 533.05 | 27549.14 | 533.05 | 16170.55 | 11378.59
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | -533.05 | 27016.09 | -533.05 | 15637.5 | 11378.59
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 72.03 | 27088.12 | 72.03 | 15709.53 | 11378.59
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 182.39 | 27270.51 | 182.39 | 15891.92 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 113.73 | 27384.24 | 113.73 | 16005.65 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 51.72 | 27435.96 | 51.72 | 16057.37 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 63.24 | 27499.2 | 63.24 | 16120.61 | 11378.59
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 27499.2 | 88.19 | 16208.8 | 11290.4
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 27499.2 | 534.79 | 16743.59 | 10755.61
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 27499.2 | 150.19 | 16893.78 | 10605.42
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 27499.2 | 660.63 | 17554.41 | 9944.79
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 27499.2 | 34.49 | 17588.9 | 9910.3
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 27499.2 | 204.7 | 17793.6 | 9705.6
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 27499.2 | 16.29 | 17809.89 | 9689.31
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 27499.2 | 114.4 | 17924.29 | 9574.91
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 27499.2 | 20.96 | 17945.25 | 9553.95
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 27499.2 | 180 | 18125.25 | 9373.95
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 27499.2 | 61.09 | 18186.34 | 9312.86
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 27499.2 | 388.5 | 18574.84 | 8924.36
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 27499.2 | 70.57 | 18645.41 | 8853.79
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 27499.2 | 393.5 | 19038.91 | 8460.29
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 27499.2 | 85.16 | 19124.07 | 8375.13
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 27499.2 | 588.5 | 19712.57 | 7786.63
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 27499.2 | 42.45 | 19755.02 | 7744.18
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 27499.2 | 338.2 | 20093.22 | 7405.98
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 27499.2 | 30.92 | 20124.14 | 7375.06
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 27499.2 | 233.6 | 20357.74 | 7141.46
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 27499.2 | 20.17 | 20377.91 | 7121.29
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 27499.2 | 149.6 | 20527.51 | 6971.69
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 27499.2 | 85.27 | 20612.78 | 6886.42
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 27499.2 | 755 | 21367.78 | 6131.42
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 27499.2 | 164.89 | 21532.67 | 5966.53
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 27499.2 | 829.9 | 22362.57 | 5136.63
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 27499.2 | 129.9 | 22492.47 | 5006.73
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 27499.2 | 981.3 | 23473.77 | 4025.43
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 27499.2 | 59.96 | 23533.73 | 3965.47
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 27499.2 | 527.9 | 24061.63 | 3437.57
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 27499.2 | 50.81 | 24112.44 | 3386.76
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 27499.2 | 419.6 | 24532.04 | 2967.16
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 27499.2 | 53.03 | 24585.07 | 2914.13
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 27499.2 | 486.5 | 25071.57 | 2427.63
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 27499.2 | 32.81 | 25104.38 | 2394.82
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 27499.2 | 356.9 | 25461.28 | 2037.92
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 27499.2 | 33.1 | 25494.38 | 2004.82
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 27499.2 | 168.2 | 25662.58 | 1836.62
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 27499.2 | 13.67 | 25676.25 | 1822.95
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 27499.2 | 123.5 | 25799.75 | 1699.45
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 27499.2 | 16.72 | 25816.47 | 1682.73
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 27499.2 | 114.6 | 25931.07 | 1568.13
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 27499.2 | 11.94 | 25943.01 | 1556.19
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 27499.2 | 79.2 | 26022.21 | 1476.99
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 27499.2 | 20.53 | 26042.74 | 1456.46
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 27499.2 | 207.5 | 26250.24 | 1248.96
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 27499.2 | 69.47 | 26319.71 | 1179.49
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 27499.2 | 744.5 | 27064.21 | 434.99
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 27499.2 | 81.59 | 27145.8 | 353.4
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 27499.2 | 353.4 | 27499.2 | -3.638e-12
[5 empty] | 27499.2 |  | 27499.2 | -3.638e-12
|  |  | Totals: | 27499.2 |  | 27499.2 |  | 0
Note on E9: please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative PM Time - James Trower $Joni Trower, James Mar 31, 2022, 6:21 PM (19 hours ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Please set up $6,000 in PM Time for the MM21 funds 9212.00 - DIA CC Wallace 3rd Floor Renovation (2021): Please increase PM Time by $1,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs: Please increase PM Time by $4,000 9228.00 - DCA PGR Plum Grove Roof Replacement: Please increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement: Please increase PM Time by $2,000 9251.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 9252.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 Thanks, James James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov PM Time - James Trower $Joni Trower, James 3:10 PM (2 minutes ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Increase PM Time by $5,000 9201.00 - DAS CC Ola Babcock Miller Tuckpointing (MM20): Increase PM Time by $1,100 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22): Increase PM Time by $6,000 9249.00 - DOC MPCF Front Steps Repair (MM22): Increase PM Time by $6,000 9251.00 - DPS P09 Parking Lot Replacement (MM22): Increase PM Time by $3,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James 2:58 PM (19 minutes ago) to me Finance - See below modifications in RED. MM21 9342.00 3,890.70 Can not post will put PM time over budget - Increase PM Time by $8,000 MM22 9226.00 59226.00 - DCA MON M House Site Work & Outbuilding Repairs - MM22 Finance - 1. Reduce MM22 PM Time $4,142.36 and return to the MM22 Pool Fund 2. Transfer $69,476.47 MM2 to the MM22 Pool Fund Thanks, James Trower, Licensed Architect, LEED AP59226.00 - DCA MON Main House Site Work & Outbuilding Repairs - MM22 $Joni Trower, James Wed, Mar 12, 6:31 PM (12 hours ago) to me Finance - 1. Reduce MM22 PM Time $4,142.36 and return to the MM22 Pool Fund 2. Transfer $69,476.47 MM2 to the MM22 Pool Fund Thanks, James Trower, Licensed Architect, LEED AP5.50 Can not post will put PM time over budget - Increase PM Time by $6,000 MM23 9250.00 1,112.10 Can not post will put PM time over budget - Increase PM Time by $10,000 MM23 9304.00 1,069.20 Can not post will put PM time over budget - Increase PM Time by $5,000 Thanks, James Fwd: PM Time Posted $Joni Trower, James 10:41 AM (5 minutes ago) to me Thanks, James Finance Payables nfrastructure, DAS <dasfinanceinfrastructure@iowa.gov> Date: Thu, Sep 19, 2024 at 9:45 AM Subject: PM Time Posted To: James Trower <james.trower@iowa.gov> Good morning Pm Time posted and the following projects need attention: DA23 9346.00 -745.45 Increase PM Time by $2,000 DA24 9412.00 -480.35 Increase PM Time by $2,000 MM22 9226.00 -21.02 Increase PM Time by $6,000 PARK 9411.00 -1557.83 Increase PM Time by $10,000 9226.00 - DCA MON Main House Site Work & Outbuilding Repairs - MM22 $Joni Trower, James Wed, Mar 12, 6:31 PM (12 hours ago) to me Finance - 1. Reduce MM22 PM Time $4,142.36 and return to the MM22 Pool Fund 2. Transfer $69,476.47 MM2 to the MM22 Pool Fund Thanks, James Trower, Licensed Architect, LEED AP

## #9226.00 Misc
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522097901 | 2022-04-06 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2412334-Final | 1612.5 | 1612.5
PRC 33522131801 | 2022-05-11 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 419479-0 | 89.12 | 1701.62
GAX 33523257801 | 2022-08-26 | 9500 | CNST | Ground Penetrating Radar Systems V#(00003035582) | Inv. 505696 | 1975 | 3676.62
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2024 | DAS2024071153 | 137.5 | 3814.12
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 82.5 | 3896.62
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 110 | 4006.62
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -330 | 3676.62
GAX 33524204901 | 2024-07-22 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2586056 | 855 | 4531.62
4531.62
4531.62
4531.62
4531.62
|  |  |  | Totals: |  | 4531.62

## #9226.00 Genesis Architectural
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B: 922500-01
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522347801 | 2021-12-13 | PO Procore | 33500 | 33500 |  |  | 33500
PRC 3352234PA7801 | 2022-02-09 | Inv. 2114.02-01 |  | 33500 | 14120 | 14120 | 19380
PO 33522347801 | 2022-02-15 | CO 1 | 500 | 34000 |  | 14120 | 19880
PRC 3352234PB7801 | 2022-03-13 | Inv. 2114.02-02 |  | 34000 | 6370 | 20490 | 13510
PO 33522347801 | 2022-04-01 | CO 2 | 800 | 34800 |  | 20490 | 14310
PRC 3352234PC7801 | 2022-04-22 | Inv. 2114.02-03 |  | 34800 | 2860 | 23350 | 11450
PRC 3352234PD7801 | 2022-07-14 | Inv. 2114.02-04 |  | 34800 | 1190 | 24540 | 10260 | FY22
PO 33523347801 | 2022-08-08 | Rolled to FY23 | 0 | 34800 |  | 24540 | 10260
PRC 3352334PE7801 | 2022-09-27 | Inv. 2114.02-05 |  | 34800 | 5940 | 30480 | 4320
PRC 3352334PF7801 | 2022-12-20 | Inv. 2114.02-06 |  | 34800 | 1215 | 31695 | 3105 | FY23
PO 33524347801 | 2023-08-11 | Rolled to FY24 | 0 | 34800 |  | 31695 | 3105
PO 33524347801 | 2024-03-19 | CO 3 | 18050 | 52850 |  | 31695 | 21155
PRC 3352434PG7801 | 2024-05-06 | Inv. 2402-01 |  | 52850 | 5415 | 37110 | 15740
PRC 3352434PH7801 | 2024-07-05 | Inv. 2402-02 |  | 52850 | 4693 | 41803 | 11047 | FY24
PO 33525347801 | 2024-07-19 | Roll to FY25 |  | 52850 |  | 41803 | 11047
PO 33525347801 | 2025-03-21 | CO #4 (Moving PO to MM24) | -11047 | 41803 |  | 41803 | 0
|  |  |  | 41803 |  | 41803 | 0
|  | Totals: | 41803 |  | 41803 |  | 0
|  | Design Development Phase | 12300 |  | 12300 |  | 0
|  | Construction Documents | 9100 |  | 9100 |  | 0
|  | Bid Phase | 1300 |  | 1300 |  | 0
|  | Constructon Phase | 7695 |  | 7695 |  | 0
|  | CO 1 | 500 |  | 500 |  | 0
|  | CO 2 | 800 |  | 800 |  | 0
|  | CO 3 | 10108 |  | 10108 |  | 0
|  | Total: | 41803 |  | 41803 |  | 0
|  | MM24 | 11047
|  | Total: | 52850 |  | 41803 |  | 11047

## #9226.00 BiState Masonry
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 922500-01
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522133800 | 2022-05-13 | PO Procore | 69050 | 69050 |  |  | 69050 |  | FY22
PO 33523133800 | 2022-08-08 | Rolled to FY23 | 0 | 69050 |  | 0 | 69050
PRC 3352313PA3800 | 2022-09-08 | Inv. 5375 |  | 69050 | 47505.9 | 47505.9 | 21544.1 | 2500.35
PRC 3352313PB3800 | 2022-10-21 | Inv. 5401 |  | 69050 | 16666.5 | 64172.4 | 4877.6 | 3377.6
PRC 3352313PC3800 | 2022-12-02 | Inv. 5428 |  | 69050 | 1425 | 65597.4 | 3452.6 | 3452.6
PRC 3352313PD3800 | 2022-12-12 | Inv. 5440 Retainage |  | 69050 | 3452.6 | 69050 | 0
|  | Totals: | 69050 |  | 69050 |  | 0

## #9226.00 Story Construction CA
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522144900 | 2022-05-17 | PO Procore | 24446.3 | 24446.3 |  |  | 24446.3
PRC 3352214PA4900 | 2022-07-18 | Inv. 33218 |  | 24446.3 | 6717.5 | 6717.5 | 17728.8 | FY22
PO 33523144900 | 2022-08-08 | Rolled to FY23 | 0 | 24446.3 |  | 6717.5 | 17728.8
PRC 3352314PB4900 | 2022-08-26 | Inv. 33274 |  | 24446.3 | 1190 | 7907.5 | 16538.8
PRC 3352314PC4900 | 2022-09-20 | Inv. 33339 |  | 24446.3 | 6410.79 | 14318.29 | 10128.01
PRC 3352314PD4900 | 2022-10-20 | Inv. 33398 |  | 24446.3 | 3650.13 | 17968.42 | 6477.88
PRC 3352314PE4900 | 2022-11-21 | Inv. 33456 |  | 24446.3 | 2214 | 20182.42 | 4263.88
PRC 3352314PF4900 | 2022-12-20 | Inv. 33511 |  | 24446.3 | 914.5 | 21096.92 | 3349.38
PRC 3352314PG4900 | 2023-01-20 | Inv. 33578-Final | -3143.88 | 21302.42 | 205.5 | 21302.42 | 0
|  | Totals: | 21302.42 |  | 21302.42 |  | 0 | Final
|  | CM Services | 20999 |  | 20999 |  | 0
|  | Reimbursables | 303.42 |  | 303.42 |  | 0
|  | Total: | 21302.42 |  | 21302.42 |  | 0

## #9226.00 Wapsi Valley
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Wapsi Valley Archaeology |  |  | Vendor: 00002136542
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: TSB
Project Manager - James T |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522157802 | 2022-06-03 | PO Procore | 5950 | 5950 |  |  | 5950
PO 33522157802 | 2022-07-07 | CO 1 | 967.48 | 6917.48 |  | 0 | 6917.48 | FY22
PO 33523157802 | 2022-08-08 | Rolled to FY23 | 0 | 6917.48 |  | 0 | 6917.48
PO 3352315PA7802 | 2022-10-28 | Inv. WVA1266 |  | 6917.48 | 6917.48 | 6917.48 | 0
|  | Totals: | 6917.48 |  | 6917.48 |  | 0

## #9226.00 Controlled Asbestos
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: MA21060
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522159802 | 2022-06-08 | DO Procore | 5447.06 | 5447.06 |  |  | 5447.06 | FY22
DO 33523159802 | 2022-08-08 | Rolled to FY23 | 0 | 5447.06 |  | 0 | 5447.06
PRC 3352315PA9802 | 2022-11-10 | Inv. 10426 FINAL | -3930.49 | 1516.57 | 1516.57 | 1516.57 | 0
|  | Totals: | 1516.57 |  | 1516.57 |  | 0 | FINAL
|  | Line 1: Labor (48 Hours x $58.00) | 928 |  | 928 |  | 0
|  | Line 1: Drive Time (3 Hours x 3 Trips x 2 Employees x $58.00) | 348 |  | 348 |  | 0
|  | Line 7: Air Monitoring | 43.99 |  | 43.99 |  | 0
|  | Line 11: Waste Disposal | 48.38 |  | 48.38 |  | 0
|  | Line 12: Mileage (380 Miles x 4 Trips x $.39) | 148.2 |  | 148.2 |  | 0
|  | Total: | 1516.57 |  | 1516.57 |  | 0

## #9226.00 Boyd Jones
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524009901 | 2024-01-09 | PO Procore | 9709.76 | 9709.76 |  |  | 9709.76
PRC 3352400PA9901 | 2024-02-29 | Inv. 9226.00-001 |  | 9709.76 | 966.95 | 966.95 | 8742.81
PRC 3352400PB9901 | 2024-03-18 | Inv. 9226.00-002 |  | 9709.76 | 834.57 | 1801.52 | 7908.24
PRC 3352400PC9901 | 2024-04-09 | Inv. 9226.00-003 |  | 9709.76 | 1669.14 | 3470.66 | 6239.1
PRC 3352400PD9901 | 2024-05-06 | Inv. 9226.00-004 |  | 9709.76 | 3281.83 | 6752.49 | 2957.27
PO 33524009901 | 2024-07-22 | Close per PM & Vendor | -2957.27 | 6752.49 |  | 6752.49 | 0
|  | Totals: | 6752.49 |  | 6752.49 |  | 0
|  | CM Services | 6548.49 |  | 6548.49 |  | 0
|  | Reimbursables | 204 |  | 204 |  | 0
|  | Total: | 6752.49 |  | 6752.49 |  | 0

## #9226.00 DCI Group
DCA MON Main House Site Work and Outbuilding Repairs
Project # 9226.00
Program code 922600 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524159902 |  | PO Procore | 14060 | 14060 |  |  | 14060
PRC 3352415PA9902 | 2024-07-17 | Inv. 24-021 PC 01 |  | 14060 | 2244.87 | 2244.87 | 11815.13 | FY24
PO 33525159902 | 2024-07-19 | Roll to FY25 |  | 14060 |  | 2244.87 | 11815.13
PRC 3352515PB9902 | 2025-02-12 | Inv. 24-021 PC 02 |  | 14060 | 1521.54 | 3766.41 | 10293.59
PO 33525159902 | 2025-03-19 | CO #1 (Moving to MM24) | -10293.59 | 3766.41 |  | 3766.41 | 0
|  |  |  | 3766.41 |  | 3766.41 | 0
|  |  |  | 3766.41 |  | 3766.41 | 0
|  |  |  | 3766.41 |  | 3766.41 | 0
|  |  |  | 3766.41 |  | 3766.41 | 0
|  |  |  | 3766.41 |  | 3766.41 | 0
|  | Totals: | 3766.41 |  | 3766.41 |  | 0
|  | CM Services | 3766.41 |  | 3766.41 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 3766.41 |  | 3766.41 |  | 0

## RECAP #9227.00
DHS GRC 212-214 and 717-Main Road Tunnel Repairs
Project # 9227.00
| Program code 922700 |  |  | Major Program 4E17
Recap
Acct. Codes-0017-335-MM22
Project Manager - Doug C
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 72267.06
C | Samuels Group |  | 9030.81 | 9030.81 | 0
C | PM TIME |  | 6460 | 6460 | 0
C | Misc. |  | 1176.25 | 1176.25 | 0
C | Shive Hattery |  | 55600 | 55600 | 0
| Total Project Cost | 72267.06 | 72267.06 | 72267.06 | 0 | 0
Closed 08/12/2022

## #9227.00 Samuels Group
DHS GRC 212-214 and 717-Main Road Tunnel Repairs
Project # 9227.00
Program code 922700 |  |  | Major Program 4E17
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: Samuels9112015
Project Manager - Doug C |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522279800 | 2021-10-06 | PO Procore | 13984.68 | 13984.68 |  |  | 13984.68
PRC 3352227PA9800 | 2021-11-08 | Inv. 7363.01922700 |  | 13984.68 | 194.29 | 194.29 | 13790.39
PRC 3352227PB9800 | 2021-12-09 | Inv. 7363.02922700 |  | 13984.68 | 292.79 | 487.08 | 13497.6
PRC 3352227PC9800 | 2022-01-04 | Inv. 7363.03922700 |  | 13984.68 | 1291.2 | 1778.28 | 12206.4
PRC 3352227PD9800 | 2022-02-09 | Inv. 7363.04922700 |  | 13984.68 | 1928.74 | 3707.02 | 10277.66
PRC 3352227PE9800 | 2022-03-09 | Inv. 7363.05922700 |  | 13984.68 | 788 | 4495.02 | 9489.66
PRC 3352227PF9800 | 2022-04-14 | Inv. 7363.06922700 |  | 13984.68 | 834.54 | 5329.56 | 8655.12
PRC 3352227PG9800 | 2022-05-05 | Inv. 7363.07922700 |  | 13984.68 | 2130.67 | 7460.23 | 6524.45
PRC 3352227PH9800 | 2022-06-02 | Inv. 7363.08922700 |  | 13984.68 | 1500.77 | 8961 | 5023.68
PRC 3352227PI9800 | 2022-06-30 | Inv. 7363.09922700 |  | 13984.68 | 69.81 | 9030.81 | 4953.87
PO 33522279800 | 2022-07-15 | Closing PO per Vendor & PM | -4953.87 | 9030.81 |  | 9030.81 | 0
|  |  |  | 9030.81 |  | 9030.81 | 0
|  |  |  | 9030.81 |  | 9030.81 | 0
|  | Totals: | 9030.81 |  | 9030.81 |  | 0
|  | CM Services | 8692.33 |  | 8692.33 |  | 0
|  | Reimbursables | 338.48 |  | 338.48 |  | 0
|  | Total: | 9030.81 |  | 9030.81 |  | 0

## #9227.00 PM TIME
DHS GRC 212-214 and 717-Main Road Tunnel Repairs
Project # 9227.00
Program code 922700 |  |  | Major Program 4E17
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 6460 | 6460 |  |  | 6460
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 6460 | 400 | 400 | 6060
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 6460 | 750 | 1150 | 5310
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 6460 | 500 | 1650 | 4810
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 6460 | 950 | 2600 | 3860
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 6460 | 1000 | 3600 | 2860
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 6460 | 500 | 4100 | 2360
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 6460 | 900 | 5000 | 1460
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 6460 | 750 | 5750 | 710
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 6460 | 400 | 6150 | 310
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 6460 | 200 | 6350 | 110
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 6460 | 100 | 6450 | 10
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 6460 | -100 | 6350 | 110
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 6460 | 110 | 6460 | 0
|  |  |  | 6460 |  | 6460 | 0
|  | Totals: | 6460 |  | 6460 |  | 0
Note on D9: Durakovic, Selma [DAS]: Re: URGENT: 9227.00 MM22 PM time $Selma Carper, Douglas 8:18 AM (1 minute ago) to me Set PM Time budget to $15,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov

## #9227.00 Misc
DHS GRC 212-214 and 717-Main Road Tunnel Repairs
Project # 9227.00
Program code 922700 |  |  |  | Major Program 4E17
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522181900 | 2022-06-29 | 9500 | CNST | ATC Group V#00002134218 | Inv. 2428973-Final | 1176.25 | 1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
1176.25
|  |  |  | Totals |  | 1176.25

## #9227.00 Shive Hattery
DHS GRC 212-214 and 717-Main Road Tunnel Repairs
Project # 9227.00
Program code 922700 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 922700-01
Project Manager - Doug C |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522025901 | 2022-01-25 | PO Procore | 69912 | 69912 |  |  | 69912
PRC 3352202PA5901 | 2022-04-04 | Inv. 4217780-1 |  | 69912 | 48705 | 48705 | 21207
PRC 3352202PB5901 | 2022-06-08 | Inv. 4217780-2 |  | 69912 | 6895 | 55600 | 14312
PO 33522025901 | 2022-07-18 | Close project per vendor request | -14312 | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  |  |  | 55600 |  | 55600 | 0
|  | Totals | 55600 |  | 55600 |  | 0
|  | Schematic Design | 19500 |  | 19500 |  | 0
|  | Design Development Documents | 16400 |  | 16400 |  | 0
|  | Construction Documents | 19700 |  | 19700 |  | 0
|  | Bidding Assistance | 0 |  |  |  | 0
|  | Construction Phase | 0 |  |  |  | 0
|  | Total: | 55600 |  | 55600 |  | 0

## RECAP #9228.00
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
| Program code 922800 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 71478.53
C | Samuels Group PC |  | 7343.21 | 7343.21 | 0
C | PM TIME |  | 7565.63 | 7565.63 | 0
C | Misc. |  | 0 | 0 | 0
C | Horizon Architecture |  | 4470 | 4470 | 0
C | Premier Plus Siding & Windows |  | 39954.6 | 39954.6 | 0
C | Samuels Group CA |  | 12145.09 | 12145.09 | 0
| Total Project Cost | 71478.53 | 71478.53 | 71478.53 | 0 | 0
Closed 12/31/22

## #9228.00 Samuels Group
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522267504 | 2021-09-24 | PO Procore | 7601.63 | 7601.63 |  |  | 7601.63
PRC 3352226PA7504 | 2021-12-10 | Inv. 7362.20PC |  | 7601.63 | 814.54 | 814.54 | 6787.09
PRC 3352226PB7504 | 2022-02-08 | Inv. 7362.21PC |  | 7601.63 | 749.59 | 1564.13 | 6037.5
PRC 3352226PC7504 | 2022-03-09 | Inv. 7362.22PC |  | 7601.63 | 3595.26 | 5159.39 | 2442.24
PRC 3352226PD7504 | 2022-04-11 | Inv. 7362.23 PC Final | -258.42 | 7343.21 | 2183.82 | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  |  |  | 7343.21 |  | 7343.21 | 0
|  | Totals | 7343.21 |  | 7343.21 |  | 0
|  | CM Services | 7295.63 |  | 7295.63 |  | 0
|  | Reimbursables | 47.58 |  | 47.58 |  | 0
|  | Total: | 7343.21 |  | 7343.21 |  | 0

## #9228.00 PM TIME
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 5915 | 5915 |  |  | 5915
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 5915 | 650 | 650 | 5265
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 5915 | 525 | 1175 | 4740
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 5915 | 350 | 1525 | 4390
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 5915 | 375 | 1900 | 4015
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 5915 | 300 | 2200 | 3715
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 5915 | 275 | 2475 | 3440
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 5915 | 250 | 2725 | 3190
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 5915 | 350 | 3075 | 2840
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 5915 | 175 | 3250 | 2665
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 5915 | 300 | 3550 | 2365
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 5915 | 350 | 3900 | 2015
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 5915 | -350 | 3550 | 2365
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 5915 | 385 | 3935 | 1980
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 5915 | 495 | 4430 | 1485
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 5915 | 550 | 4980 | 935
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 5915 | 935 | 5915 | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 251.01 | 6166.01 | 251.01 | 6166.01 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 420.91 | 6586.92 | 420.91 | 6586.92 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 296 | 6882.92 | 296 | 6882.92 | 0
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 682.71 | 7565.63 | 682.71 | 7565.63 | 0
|  |  |  | 7565.63 |  | 7565.63 | 0
|  | Totals: | 7565.63 |  | 7565.63 |  | 0
Note on D9: Wray, Ronda [DAS]: PM TIME - James Trower $Ronda Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Finance - Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative PM Time - James Trower $Joni Trower, James Mar 31, 2022, 6:21 PM (19 hours ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Please set up $6,000 in PM Time for the MM21 funds 9212.00 - DIA CC Wallace 3rd Floor Renovation (2021): Please increase PM Time by $1,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs: Please increase PM Time by $4,000 9228.00 - DCA PGR Plum Grove Roof Replacement: Please increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement: Please increase PM Time by $2,000 9251.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 9252.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 Thanks, James James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Project 9228.00 (MM22) $Joni Trower, James Dec 31, 2022, 10:42 PM (4 days ago) to me Finance - Reduce PM Time by $85.00 and return to the MM22 pool fund. Close the project and return remaining funds to the MM22 pool funds. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9228.00 Misc
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9228.00 Horizon Architecture
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  | Major Program 4E02
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: TSB
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522274801 | 2021-10-01 | PO Procore | 4470 | 4470 |  |  | 4470
PRC 3352227PA4801 | 2022-01-24 | Inv. 9228.00-01 |  | 4470 | 2440 | 2440 | 2030
PRC 3352227PB4801 | 2022-05-05 | Inv. 9228.00-02 |  | 4470 | 710 | 3150 | 1320 | FY22
PO 33523274801 | 2022-08-08 | Rolled to FY23 | 0 | 4470 |  | 3150 | 1320
PRC 3352327PC4801 | 2022-10-04 | Inv. 9228.00-03 FINAL |  | 4470 | 1320 | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  | Totals: | 4470 |  | 4470 |  | 0
|  | Design & Documentation | 2440 |  | 2440 |  | 0
|  | Bidding Assistance | 710 |  | 710 |  | 0
|  | Construction Administration | 1320 |  | 1320 |  | 0
|  | Total: | 4470 |  | 4470 |  | 0

## #9228.00 Premier Plus
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  | Major Program 4E02
Premier Plus Siding & Windows |  |  | Vendor: 00003196527
Acct. Codes-0017-335-MM22-9255 |  |  | 922800-01
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522098901 | 2022-04-08 | PO Procore | 39954.6 | 39954.6 |  |  | 39954.6
PO 33522098901 | 2022-06-10 | CO #1 (no cost) | 0 | 39954.6 |  | 0 | 39954.6 |  | FY22
PO 33523098901 | 2022-08-08 | Rolled to FY23 | 0 | 39954.6 |  | 0 | 39954.6
PRC 3352309PA8901 | 2022-08-25 | Inv. 2110 |  | 39954.6 | 37006.87 | 37006.87 | 2947.73 | 1947.73
PRC 3352309PB8901 | 2022-09-30 | Inv. 2110-2 |  | 39954.6 | 950 | 37956.87 | 1997.73 | 1997.73
PRC 3352309PC8901 | 2022-10-04 | Inv. 2110-3 Retainage |  | 39954.6 | 1997.73 | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  |  |  | 39954.6 |  | 39954.6 | 0
|  | Totals: | 39954.6 |  | 39954.6 |  | 0

## #9228.00 Samuels Group CA
DCA PGR Plum Grove Roof Replacement
Project # 9228.00
Program code 922800 |  |  | Major Program 4E02
Samuels Group CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522110800 | 2022-04-13 | PO Procore | 12470.14 | 12470.14 |  |  | 12470.14
PRC 3352211PA0800 | 2022-05-11 | Inv. 7403.10 CA |  | 12470.14 | 1167.9 | 1167.9 | 11302.24
PRC 3352211PB0800 | 2022-06-02 | Inv. 7403.11 CA |  | 12470.14 | 373.44 | 1541.34 | 10928.8
PRC 3352211PC0800 | 2022-07-07 | Inv. 7403.12 CA |  | 12470.14 | 376.15 | 1917.49 | 10552.65 | FY22
PO 33523110800 | 2022-08-08 | Rolled to FY23 | 0 | 12470.14 |  | 1917.49 | 10552.65
PRC 3352311PD0800 | 2022-08-11 | Inv. 7403.13 CA |  | 12470.14 | 4001.6 | 5919.09 | 6551.05
PRC 3352311PE0800 | 2022-09-09 | Inv. 7403.14CA |  | 12470.14 | 4245.14 | 10164.23 | 2305.91
PRC 3352311PF0800 | 2022-10-07 | Inv. 7403.15CA FINAL | -325.05 | 12145.09 | 1980.86 | 12145.09 | 0
|  |  |  | 12145.09 |  | 12145.09 | 0
|  |  |  | 12145.09 |  | 12145.09 | 0
|  |  |  | 12145.09 |  | 12145.09 | 0
|  |  |  | 12145.09 |  | 12145.09 | 0
|  |  |  | 12145.09 |  | 12145.09 | 0
|  | Totals: | 12145.09 |  | 12145.09 |  | 0
|  | CM Services | 11812.03 |  | 11812.03 |  | 0
|  | Reimbursables | 333.06 |  | 333.06 |  | 0
|  | Total: | 12145.09 |  | 12145.09 |  | 0

## RECAP #9229.00
DOC NCCF R&D Floor Replacement
Project # 9229.00
| Program code 922900 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 99268.95
C | Story Construction PC |  | 8230.1 | 8230.1 | 0
C | PM TIME |  | 8284.67 | 8284.67 | 0
C | Misc. |  | 642.5 | 642.5 | 0
C | SPECcetra |  | 11400 | 11400 | 0
C | Story Construction CA |  | 22014.68 | 22014.68 | 0
C | Phillips Floors |  | 48697 | 48697 | 0
| Total Project Cost | 99268.95 | 99268.95 | 99268.95 | 0 | 0
Closed 02/27/2023

## #9229.00 Story Construction PC
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  | Major Program 4B01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522277801 | 2021-10-01 | PO Procore | 9410.5 | 9410.5 |  |  | 9410.5
PRC 3352227PA7801 | 2021-12-17 | Inv. 32898 |  | 9410.5 | 1262.6 | 1262.6 | 8147.9
PRC 3352227PB7801 | 2022-01-18 | Inv. 32941 |  | 9410.5 | 552.02 | 1814.62 | 7595.88
PRC 3352227PC7801 | 2022-02-22 | Inv. 32983 |  | 9410.5 | 1189.54 | 3004.16 | 6406.34
PRC 3352227PD7801 | 2022-03-25 | Inv. 33027 |  | 9410.5 | 851.84 | 3856 | 5554.5
PRC 3352227PE7801 | 2022-04-28 | Inv. 33073 |  | 9410.5 | 2423.65 | 6279.65 | 3130.85
PRC 3352227PF7801 | 2022-05-19 | Inv. 33116-Final | -1180.4 | 8230.1 | 1950.45 | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  |  |  | 8230.1 |  | 8230.1 | 0
|  | Totals: | 8230.1 |  | 8230.1 |  | 0
|  | CM Services | 8198.51 |  | 8198.51 |  | 0
|  | Reimbursables | 31.59 |  | 31.59 |  | 0
|  | Total: | 8230.1 |  | 8230.1 |  | 0

## #9229.00 PM TIME
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  | Major Program 4B01
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx |  |  | eDAS 906N
Project Manager - James T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 6835.47 | 6835.47 |  |  | 6835.47
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 6835.47 | 500 | 500 | 6335.47
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 6835.47 | 325 | 825 | 6010.47
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 6835.47 | 250 | 1075 | 5760.47
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 6835.47 | 350 | 1425 | 5410.47
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 6835.47 | 425 | 1850 | 4985.47
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 6835.47 | 350 | 2200 | 4635.47
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 6835.47 | 450 | 2650 | 4185.47
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 6835.47 | 325 | 2975 | 3860.47
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 6835.47 | 475 | 3450 | 3385.47
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 6835.47 | 150 | 3600 | 3235.47
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 6835.47 | 250 | 3850 | 2985.47
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 6835.47 | -250 | 3600 | 3235.47
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 6835.47 | 275 | 3875 | 2960.47
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 6835.47 | 55 | 3930 | 2905.47
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 6835.47 | 440 | 4370 | 2465.47
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 6835.47 | 412.5 | 4782.5 | 2052.97
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30,2022 |  | 6835.47 | 440 | 5222.5 | 1612.97
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 527.13 | 7362.6 | 527.13 | 5749.63 | 1612.97
IET DAS202205115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 46.78 | 7409.38 | 46.78 | 5796.41 | 1612.97
IET DAS202205115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 236.8 | 7646.18 | 236.8 | 6033.21 | 1612.97
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 301.2 | 7947.38 | 301.2 | 6334.41 | 1612.97
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 337.29 | 8284.67 | 337.29 | 6671.7 | 1612.97
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 8284.67 | 563.6 | 7235.3 | 1049.37
IET DAS202307115300001 | 2023-02-07 | Finance Support for: January 1-31, 2023 |  | 8284.67 | 107.44 | 7342.74 | 941.93
IET DAS202307115300001 | 2023-02-07 | DAS Services For: January 1-31, 2023 |  | 8284.67 | 941.93 | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  |  |  | 8284.67 |  | 8284.67 | 0
|  | Totals | 8284.67 |  | 8284.67 |  | 0
Note on D9: Wray, Ronda [DAS]: PM TIME - James Trower $Ronda Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Finance - Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative PM Time - James Trower $Joni Trower, James Mar 31, 2022, 6:21 PM (19 hours ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Please set up $6,000 in PM Time for the MM21 funds 9212.00 - DIA CC Wallace 3rd Floor Renovation (2021): Please increase PM Time by $1,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs: Please increase PM Time by $4,000 9228.00 - DCA PGR Plum Grove Roof Replacement: Please increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement: Please increase PM Time by $2,000 9251.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 9252.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 Thanks, James James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov PM Time Increases $Joni Trower, James Dec 22, 2022, 1:00 PM (6 days ago) to me Finance: Please see the below items: 9197.00 - 5th Judicial DSM 5JD FT DM 70 South Restroom Remodel Increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement Increase PM Time by $2,000 9237.00 - DAS CC Hoover East Side Paver Repairs Increase PM Time by $1,100 9264.00 - DPS P10 Front Entrance Repair Increase PM Time by $1,100 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9229.00 - DOC NCCF R&D Floor Replacement - Close $Joni Trower, James Sat, Feb 25, 7:45 AM (2 days ago) to me Finance - Reduce PM Time by $664.53. Close project and return on funding to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9229.00 Misc
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522096800 | 2022-04-06 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2412329-Final | 642.5 | 642.5
642.5
642.5
642.5
642.5
642.5
642.5
642.5
642.5
642.5
642.5
642.5
|  |  |  | Totals |  | 642.5

## #9229.00 SPECcetera
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  | Major Program 4B01
SPECcetera |  |  | Vendor: VS000002708
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522026900 | 2022-01-26 | PO Procore | 12000 | 12000 |  |  | 12000
PRC 3352202PA6900 | 2022-07-08 | Inv. 9229.00-01 |  | 12000 | 7200 | 7200 | 4800 | FY22
PO 33523026900 | 2022-08-08 | Rolled to FY23 | 0 | 12000 |  | 7200 | 4800
PRC 3352302PB6900 | 2022-10-17 | Inv. 9229.00-02 |  | 12000 | 500 | 7700 | 4300
PRC 3352302PC6900 | 2022-11-28 | Inv. 9229.00-03 |  | 12000 | 2200 | 9900 | 2100
PRC 3352302PD6900 | 2022-01-03 | Inv. 9229.00-04 |  | 12000 | 1500 | 11400 | 600
PO 33523026900 | 2023-01-18 | Closing PO Per PM & Vendor | -600 | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  |  |  | 11400 |  | 11400 | 0
|  | Totals | 11400 |  | 11400 |  | 0
|  | Design Phase | 5850 |  | 5850 |  | 0
|  | Bid Phase | 1350 |  | 1350 |  | 0
|  | Construction Phase | 4200 |  | 4200 |  | 0
|  | Total: | 11400 |  | 11400 |  | 0

## #9229.00 Story Construction CA
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  | Major Program 4B01
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522119900 | 2022-04-29 | PO Procore | 22171.08 | 22171.08 |  |  | 22171.08
PRC 3352211PA9900 | 2022-06-17 | Inv. 33163 |  | 22171.08 | 4640 | 4640 | 17531.08
PRC 3352211PB9900 | 2022-07-18 | Inv. 33214 |  | 22171.08 | 928.68 | 5568.68 | 16602.4 | FY22
PO 33523119900 | 2022-08-08 | Rolled to FY23 | 0 | 22171.08 |  | 5568.68 | 16602.4
PRC 3352311PC9900 | 2022-08-26 | Inv. 33270 |  | 22171.08 | 1196.5 | 6765.18 | 15405.9
PRC 3352311PD9900 | 2022-09-20 | Inv. 33335 |  | 22171.08 | 421 | 7186.18 | 14984.9
PRC 3352311PE9900 | 2022-10-17 | Inv. 33394 |  | 22171.08 | 325 | 7511.18 | 14659.9
PRC 3352311PF9900 | 2022-11-21 | Inv. 33452 |  | 22171.08 | 1485 | 8996.18 | 13174.9
PRC 3352311PG9900 | 2022-12-28 | Inv. 33507 |  | 22171.08 | 9121.5 | 18117.68 | 4053.4
PRC 3352311PH9900 | 2023-01-20 | Inv. 33575 |  | 22171.08 | 3645 | 21762.68 | 408.4
PRC 3352311PI9900 | 2023-02-16 | Inv. 33626-Final | -156.4 | 22014.68 | 252 | 22014.68 | 1.4495e-12
|  |  |  | 22014.68 |  | 22014.68 | 1.4495e-12
|  |  |  | 22014.68 |  | 22014.68 | 1.4495e-12
|  | Totals: | 22014.68 |  | 22014.68 |  | 0
|  | CM Services | 21780.5 |  | 21780.5 |  | 0
|  | Reimbursables | 234.18 |  | 234.18 |  | 0
|  | Total: | 22014.68 |  | 22014.68 |  | 0

## #9229.00 Phillips Flooring
DOC NCCF R&D Floor Replacement
Project # 9229.00
Program code 922900 |  |  | Major Program 4B01
Phillips Flooring |  |  | Vendor: 00002121889
Acct. Codes-0017-335-MM22-9255 |  |  | 922900-01
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522130900 | 2022-05-10 | PO Procore | 48697 | 48697 |  |  | 48697 |  | FY22
PO 33523130900 | 2022-08-08 | Rolled to FY23 | 0 | 48697 |  | 0 | 48697
PRC 3352313PA0900 | 2022-09-01 | Inv. 9229.00-01 |  | 48697 | 3363 | 3363 | 45334 | 177
PRC 3352313PB0900 | 2022-11-08 | Inv. 9229.00-02 |  | 48697 | 25713.65 | 29076.65 | 19620.35 | 1530.35
PRC 3352313PC0900 | 2022-12-09 | Inv. 9229.00-03 |  | 48697 | 16235.5 | 45312.15 | 3384.85 | 2384.85
PRC 3352313PD0900 | 2023-01-23 | Inv. 9229.00-005.4 |  | 48697 | 950 | 46262.15 | 2434.85 | 2434.85
PRC 3352313PE0900 | 2023-01-26 | Inv. 9229.00-005.5-Retainage |  | 48697 | 2434.85 | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  |  |  | 48697 |  | 48697 | 0
|  | Totals | 48697 |  | 48697 |  | 0

## RECAP #9230.00
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
| Program code 923000 |  |  | Major Program 3G01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 294537.52
C | Samuels Group |  | 11773.18 | 11773.18 | 0
C | PM TIME |  | 17775.69 | 17775.69 | 0
C | Misc. |  | 160.78 | 160.78 | 0
C | Shive Hattery |  | 28277 | 28277 | 0
C | Samuels Group CA |  | 20258.37 | 20258.37 | 0
C | Minturn, Inc |  | 187807 | 187807 | 0
C | MTS Contracting |  | 20208 | 20208 | 0
C | MTS Contracting (2) |  | 8277.5 | 8277.5 | 0
| Total Project Cost | 294537.52 | 294537.52 | 294537.52 | 0 | 0
Closed 09/10/2023

## #9230.00 Samuels Group
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522281501 | 2021-10-08 | PO Procore | 11773.9 | 11773.9 |  |  | 11773.9
PRC 3352228PA1501 | 2021-11-02 | Inv. 7364.10 |  | 11773.9 | 741.95 | 741.95 | 11031.95
PRC 3352228PB1501 | 2022-02-08 | Inv. 7364.20 PC |  | 11773.9 | 1359.42 | 2101.37 | 9672.53
PRC 3352228PC1501 | 2022-03-08 | Inv. 7364.21 PC |  | 11773.9 | 871.36 | 2972.73 | 8801.17
PRC 3352228PD1501 | 2022-04-12 | Inv. 7364.22 PC |  | 11773.9 | 871.36 | 3844.09 | 7929.81
PRC 3352228PE1501 | 2022-05-05 | Inv. 7364.23 PC |  | 11773.9 | 2895.24 | 6739.33 | 5034.57
PRC 3352228PF1501 | 2022-06-02 | Inv. 7364.24 PC |  | 11773.9 | 752.3 | 7491.63 | 4282.27
PRC 3352228PG1501 | 2022-07-06 | Inv. 7364.25 PC |  | 11773.9 | 4035.67 | 11527.3 | 246.6 | FY22
PO 33523281501 | 2022-08-08 | Rolled to FY23 | 0 | 11773.9 |  | 11527.3 | 246.6
PRC 3352328PH1501 | 2022-08-19 | Inv. 7364.26 PC FINAL | -0.72 | 11773.18 | 245.88 | 11773.18 | -1.4506e-12
|  |  |  | 11773.18 |  | 11773.18 | -1.4506e-12
|  |  |  | 11773.18 |  | 11773.18 | -1.4506e-12
|  |  |  | 11773.18 |  | 11773.18 | -1.4506e-12
|  | Totals: | 11773.18 |  | 11773.18 |  | 0
|  | CM Services | 11473.48 |  | 11473.48 |  | 0
|  | Reimbursables | 299.7 |  | 299.7 |  | 0
|  | Total: | 11773.18 |  | 11773.18 |  | 0

## #9230.00 PM TIME
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  |  | Major Program 3G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906O
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13079.69 | 13079.69 |  |  | 13079.69
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 13079.69 | 450 | 450 | 12629.69
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 13079.69 | 350 | 800 | 12279.69
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 13079.69 | 200 | 1000 | 12079.69
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 13079.69 | 650 | 1650 | 11429.69
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 13079.69 | 900 | 2550 | 10529.69
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 13079.69 | 350 | 2900 | 10179.69
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 13079.69 | 650 | 3550 | 9529.69
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 13079.69 | 600 | 4150 | 8929.69
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 13079.69 | 550 | 4700 | 8379.69
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 13079.69 | 1050 | 5750 | 7329.69
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 13079.69 | 850 | 6600 | 6479.69
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 13079.69 | -850 | 5750 | 7329.69
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 13079.69 | 935 | 6685 | 6394.69
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 13079.69 | 550 | 7235 | 5844.69
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 13079.69 | 1210 | 8445 | 4634.69
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 13079.69 | 1320 | 9765 | 3314.69
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 13079.69 | 825 | 10590 | 2489.69
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 652.76 | 13732.45 | 652.76 | 11242.76 | 2489.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 474.31 | 14206.76 | 474.31 | 11717.07 | 2489.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 803.17 | 15009.93 | 803.17 | 12520.24 | 2489.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 928.28 | 15938.21 | 928.28 | 13448.52 | 2489.69
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 661.76 | 16599.97 | 661.76 | 14110.28 | 2489.69
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16599.97 | 1261.44 | 15371.72 | 1228.25
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16599.97 | 9.5 | 15381.22 | 1218.75
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16599.97 | 83.34 | 15464.56 | 1135.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 216.96 | 16816.93 | 216.96 | 15681.52 | 1135.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 145.01 | 16961.94 | 145.01 | 15826.53 | 1135.41
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 321.49 | 17283.43 | 321.49 | 16148.02 | 1135.41
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 145.25 | 17428.68 | 145.25 | 16293.27 | 1135.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 158.29 | 17586.97 | 158.29 | 16451.56 | 1135.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 188.72 | 17775.69 | 188.72 | 16640.28 | 1135.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 17775.69 | 7.61 | 16647.89 | 1127.8
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 17775.69 | 46.13 | 16694.02 | 1081.67
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 17775.69 | 42.54 | 16736.56 | 1039.13
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 17775.69 | 247.3 | 16983.86 | 791.83
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 17775.69 | 6.56 | 16990.42 | 785.27
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 17775.69 | 46.2 | 17036.62 | 739.07
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 17775.69 | 73.67 | 17110.29 | 665.4
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 17775.69 | 665.4 | 17775.69 | 0
[5 empty] | 17775.69 |  | 17775.69 | 0
[5 empty] | 17775.69 |  | 17775.69 | 0
|  |  | Totals: | 17775.69 |  | 17775.69 |  | 0
Note on E9: Durakovic, Selma [DAS]: Re: PM Time Budget $Selma Carper, Douglas 9:12 AM (3 hours ago) to me MM19: 9123.00 - Increase PM time to $8,700.00. 9169.01 - Increase PM time to $6,000.00. 9178.00 - Increase PM time to $5,000.00. MM20: 9108.00 - Increase PM time to $6,200.00. 9137.00 - Put time to 9139.00 9139.00 - Increase PM time to $15,000.00. 9140.00 - Increase PM time to 12,000.00. 9141.00 - Move to MM21 MM21: 9099.00 - Set PM time budget to $12,000.00. 9141.00 - Set PM time budget $6,000.00. MM22: 9230.00 - Set PM time budget to $9,000.00. 9233.00 - Set PM time budget to $15,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov PM Time $Joni Carper, Douglas Oct 7, 2022, 3:27 PM (3 days ago) to me, Joni MM21 9270.00 Increase PM Time to $10,000.00. MM22 9247.00 Increase PM Time to $7,000.00. MM22 9230.00 Increase PM Time to $12,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.go 9230.00 DHS BRC Powerhouse Parking Lot Repair $Joni Elliott, Jennie 8:50 AM (24 minutes ago) to me Please increase PM time contracted to a total of $25,000 in project 9230.00 DHS BRC Powerhouse Parking Lot Repair. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov 9230.00 - DHS GRC Powerhouse Parking Lot Repair $Joni Elliott, Jennie Sun, Sep 10, 5:04 PM (18 hours ago) to me, Scott Please Reduce PM Time to match the expended amount of $17,775.69 in project 9230.00. Upon completion, please close out the project and return any remaining funds to MM22. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov

## #9230.00 Misc
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  |  | Major Program 3G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523203805 | 2022-07-15 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. 022237 | 160.78 | 160.78
160.78
160.78
160.78
160.78
160.78
160.78
160.78
160.78
160.78
160.78
160.78
|  |  |  | Totals |  | 160.78

## #9230.00 Shive Hattery
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 922700-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522025800 | 2022-01-25 | PO Procore | 28277 | 28277 |  |  | 28277
PRC 3352202PA5800 | 2022-03-30 | Inv. 4217781-1 |  | 28277 | 17210 | 17210 | 11067
PRC 3352202PB5800 | 2022-05-19 | Inv. 4217781-2 |  | 28277 | 2590 | 19800 | 8477
PRC 3352202PC5800 | 2022-07-07 | Inv. 4217781-3 |  | 28277 | 2100 | 21900 | 6377 | FY22
PO 33523025800 | 2022-08-08 | Rolled to FY23 | 0 | 28277 |  | 21900 | 6377
PRC 3352302PD5800 | 2022-08-31 | Inv. 4217781-4 |  | 28277 | 2423.26 | 24323.26 | 3953.74
PRC 3352302PE5800 | 2022-11-28 | Inv. 4217781-5 |  | 28277 | 3698.66 | 28021.92 | 255.08
PRC 3352302PF5800 | 2022-12-14 | Inv. 4217781-6Final |  | 28277 | 255.08 | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  |  |  | 28277 |  | 28277 | 0
|  | Totals: | 28277 |  | 28277 |  | 0
|  | Site Investigation/Schematic Design | 6500 |  | 6500 |  | 0
|  | Design Development Documents | 5900 |  | 5900 |  | 0
|  | Construction Documents | 7400 |  | 7400 |  | 0
|  | Bidding Assistance | 2100 |  | 2100 |  | 0
|  | Construction Phase | 6377 |  | 6377 |  | 0
|  | Total: | 28277 |  | 28277 |  | 0

## #9230.00 Samuels Group CA
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
Samuels Group CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523200905 | 2022-07-18 | PO Procore | 23138.6 | 23138.6 |  |  | 23138.6
PRC 3352320PA0905 | 2022-08-11 | Inv. 7423.10CA |  | 23138.6 | 1481.19 | 1481.19 | 21657.41
PRC 3352320PB0905 | 2022-09-08 | Inv. 7423.11CA |  | 23138.6 | 1060.79 | 2541.98 | 20596.62
PRC 3352320PC0905 | 2022-10-07 | Inv. 7423.12CA |  | 23138.6 | 2530.66 | 5072.64 | 18065.96
PRC 3352320PD0905 | 2022-11-04 | Inv. 7423.13CA |  | 23138.6 | 10799.14 | 15871.78 | 7266.82
PRC 3352320PE0905 | 2022-12-01 | Inv. 7423.14CA |  | 23138.6 | 2946.93 | 18818.71 | 4319.89
PRC 3352320PF0905 | 2023-01-04 | Inv. 7423.15 CA |  | 23138.6 | 281.44 | 19100.15 | 4038.45
PRC 3352320PG0905 | 2023-05-05 | Inv. 7423.16 CA |  | 23138.6 | 156.96 | 19257.11 | 3881.49
PRC 3352320PH0905 | 2023-06-21 | Inv. 7423.17 FINAL | -2880.23 | 20258.37 | 1001.26 | 20258.37 | 0
|  |  |  | 20258.37 |  | 20258.37 | 0
|  |  |  | 20258.37 |  | 20258.37 | 0
|  |  |  | 20258.37 |  | 20258.37 | 0
|  |  |  | 20258.37 |  | 20258.37 | 0
|  | Totals: | 20258.37 |  | 20258.37 |  | 0 | FINAL
|  | CM Services | 19159.04 |  | 19159.04 |  | 0
|  | Reimbursables | 1099.33 |  | 1099.33 |  | 0
|  | Total: | 20258.37 |  | 20258.37 |  | 0

## #9230.00 Minturn, Inc
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
Minturn, Inc |  |  | Vendor: VS000002177
Acct. Codes-0017-335-MM22-9255 |  |  | 923000-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523203900 | 2022-07-22 | PO Procore | 186900 | 186900 |  |  | 186900
PO 33523203900 | 2022-10-31 | CO 1 | 907 | 187807 |  | 0 | 187807
PRC 3352320PA3900 | 2022-11-02 | Inv. 9230.00-001 |  | 187807 | 175779.45 | 175779.45 | 12027.55 | 9251.55
PRC 3352320PB3900 | 2022-12-21 | Inv. 9230.00-002 |  | 187807 | 2637.2 | 178416.65 | 9390.35 | 9390.35
PRC 3352320PC3900 | 2023-01-03 | Inv. 9230.00-003-Retainage |  | 187807 | 9390.35 | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  |  |  | 187807 |  | 187807 | 0
|  | Totals: | 187807 |  | 187807 |  | 0

## #9230.00 MTS Contracting
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM22-9255 |  |  | MA 20243A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523203804 | 2022-07-18 | DO Procore | 20208 | 20208 |  |  | 20208
PRC 3352320PA3804 | 2022-09-27 | Inv. D22-4414 |  | 20208 | 20208 | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  |  |  | 20208 |  | 20208 | 0
|  | Totals: | 20208 |  | 20208 |  | 0 | Final
|  | Line 1: 132mh x $81.50 | 10758 |  | 10758 |  | 0
|  | Line 3: Materials ($7200 x 12.5%) | 8100 |  | 8100 |  | 0
|  | Line 4: Equipment ($1200 x 12.5%) | 1350 |  | 1350 |  | 0
|  | Total: | 20208 |  | 20208 |  | 0

## #9230.00 MTS Contracting (2)
DHS GRC Powerhouse Parking Lot Repair
Project # 9230.00
Program code 923000 |  |  | Major Program 3G01
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM22-9255 |  |  | MA 20243A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523228902 | 2022-08-14 | DO Procore | 8277.5 | 8277.5 |  |  | 8277.5
PRC 3352322PA8902 | 2022-10-28 | Inv. 22-4443 |  | 8277.5 | 8277.5 | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  |  |  | 8277.5 |  | 8277.5 | 0
|  | Totals: | 8277.5 |  | 8277.5 |  | 0
|  | Line 1: 85hrs x $81.50/hr | 6927.5 |  | 6927.5 |  | 0
|  | Line 3: Materials | 1350 |  | 1350 |  | 0
|  | Totals: | 8277.5 |  | 8277.5 |  | 0

## RECAP #9231.00
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
| Program code 923100 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 259505.97
C | Horizon Architecture |  | 24710 | 24710 | 0
C | PM TIME |  | 24483.15 | 24483.15 | 0
C | Misc. |  | 4073.61 | 4073.61 | 0
C | DCI Group |  | 7497.9 | 7497.9 | 0
C | Bergstrom Construction |  | 27262 | 27262 | 0
C | Iowa Contracting |  | 93536.5 | 93536.5 | 0
C | Cable Glass DBA Forman Ford |  | 13025 | 13025 | 0
C | DCI Group |  | 29671.24 | 29671.24 | 0
C | Controlled Asbestos |  | 9580.74 | 9580.74 | 0
C | Waldinger Corp -Electrical |  | 6190.15 | 6190.15 | 0
C | Waldinger Corp -Plumbing |  | 17654.1 | 17654.1 | 0
C | Johnson Controls |  | 1821.58 | 1821.58 | 0
| Total Project Cost | 259505.97 | 259505.97 | 259505.97 | 0 | 0
Closed 09/15/23

## #9231.00 Horizon Architecture
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522292502 | 2021-10-19 | PO Procore | 9910 | 9910 |  |  | 9910
PRC 3352229PA2502 | 2022-02-07 | Inv. 9231.00-01 |  | 9910 | 2745 | 2745 | 7165
PRC 3352229PB2502 | 2022-07-19 | Inv. 9231.00-02 |  | 9910 | 2435 | 5180 | 4730 | FY22
PO 33523292502 | 2022-08-08 | Rolled to FY23 | 0 | 9910 |  | 5180 | 4730
PO 33523292502 | 2022-10-04 | CO 1 | 14800 | 24710 |  | 5180 | 19530
PRC 3352329PC2502 | 2022-11-14 | Inv. 9231.00-03 |  | 24710 | 11840 | 17020 | 7690
PRC 3352329PD2502 | 2022-12-22 | Inv. 9231.00-04 |  | 24710 | 5325 | 22345 | 2365
PO 33523292502 | 2023-01-25 | CO 2 (No Cost) | 0 | 24710 |  | 22345 | 2365
PRC 3352329PE2502 | 2023-07-21 | Inv. 9231.00-05 - Final |  | 24710 | 2365 | 24710 | 0
|  |  |  | 24710 |  | 24710 | 0
|  |  |  | 24710 |  | 24710 | 0
|  |  |  | 24710 |  | 24710 | 0
|  |  |  | 24710 |  | 24710 | 0
|  | Totals: | 24710 |  | 24710 |  | 0 | FINAL
|  | Survey, Design and Documentation | 3660 |  | 3660 |  | 0
|  | Bidding Assistance | 1520 |  | 1520 |  | 0
|  | Construction Administration | 4730 |  | 4730 |  | 0
|  | CO 1 | 14800 |  | 14800 |  | 0
|  | Total: | 24710 |  | 24710 |  | 0

## #9231.00 PM TIME
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906P
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 19727.29 | 19727.29 |  |  | 19727.29
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 19727.29 | 875 | 875 | 18852.29
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 19727.29 | 650 | 1525 | 18202.29
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 19727.29 | 725 | 2250 | 17477.29
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 19727.29 | 725 | 2975 | 16752.29
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 19727.29 | 525 | 3500 | 16227.29
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 19727.29 | 775 | 4275 | 15452.29
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 19727.29 | 375 | 4650 | 15077.29
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 19727.29 | 225 | 4875 | 14852.29
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 19727.29 | 350 | 5225 | 14502.29
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 19727.29 | 450 | 5675 | 14052.29
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 19727.29 | 750 | 6425 | 13302.29
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 19727.29 | -750 | 5675 | 14052.29
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 19727.29 | 825 | 6500 | 13227.29
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 19727.29 | 1732.5 | 8232.5 | 11494.79
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 19727.29 | 1540 | 9772.5 | 9954.79
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 19727.29 | 990 | 10762.5 | 8964.79
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 19727.29 | 852.5 | 11615 | 8112.29
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 424.75 | 20152.04 | 424.75 | 12039.75 | 8112.29
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1473.17 | 21625.21 | 1473.17 | 13512.92 | 8112.29
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 828.8 | 22454.01 | 828.8 | 14341.72 | 8112.29
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 722.87 | 23176.88 | 722.87 | 15064.59 | 8112.29
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 653.51 | 23830.39 | 653.51 | 15718.1 | 8112.29
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 23830.39 | 774.96 | 16493.06 | 7337.33
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 23830.39 | 137.29 | 16630.35 | 7200.04
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 23830.39 | 1203.58 | 17833.93 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 65.61 | 23896 | 65.61 | 17899.54 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 129.66 | 24025.66 | 129.66 | 18029.2 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 135.1 | 24160.76 | 135.1 | 18164.3 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 46.11 | 24206.87 | 46.11 | 18210.41 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 160.34 | 24367.21 | 160.34 | 18370.75 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 115.94 | 24483.15 | 115.94 | 18486.69 | 5996.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 24483.15 | 160.35 | 18647.04 | 5836.11
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 24483.15 | 972.34 | 19619.38 | 4863.77
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 24483.15 | 262.85 | 19882.23 | 4600.92
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 24483.15 | 1156.1 | 21038.33 | 3444.82
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 24483.15 | 147.07 | 21185.4 | 3297.75
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 24483.15 | 866.9 | 22052.3 | 2430.85
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 24483.15 | 65.6 | 22117.9 | 2365.25
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 24483.15 | 458.7 | 22576.6 | 1906.55
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 24483.15 | 77.48 | 22654.08 | 1829.07
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 24483.15 | 669.7 | 23323.78 | 1159.37
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 24483.15 | 24.49 | 23348.27 | 1134.88
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 24483.15 | 155.5 | 23503.77 | 979.38
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 24483.15 | 148.68 | 23652.45 | 830.7
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 24483.15 | 830.7 | 24483.15 | 0
[5 empty] | 24483.15 |  | 24483.15 | 0
|  |  | Totals | 24483.15 |  | 24483.15 |  | 0
Note on E9: Trower, James Jul 12, 2023, 4:17 PM (15 Please make the below changes in red: 9231.00 MM22 amount to post is 590.70 Increase PM Time by $1,000 Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 Owner’s Representative Trower, James 9:09 AM (1 hour ago) to me Joni - My billables to 9278.00 should have been billed to project 9224.00 - DOC MPCF Elevator B C & D. Can you please change billing to 9224.00? Please increase the PM Time to project 9231.00 by $4,500. Thank you, James -- James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov James Trower - PM Time $Joni Trower, James 1:08 PM (47 minutes ago) to me Finance - See below items: 9203.00 - DOC NCCF Treatment Center EIFS Replacement: Increase PM Time by $5,000 (MM21) 9231.00 - DAS CC Jessie Parker Water: Increase PM Time by $4,000 (MM22) 9250.00 - DOC MPCF Building 18 Roof Replacement: Increase PM Time by $5,000 (MM22) 9297.00 - DOC MPCF Gym Floor Repair: Set up $6,000 in PM Time (MM21) 9300.00 - DOC MPFC Storage Bunker Repair: Set up $6,000 in PM Time (MM21) 9301.00 - DPS DSM Fleet & Supply 2nd Floor Structural: Set up $4,000 in PM Time (MM21) 9305.00 - DAS CC Capitol South Stair Repair:Set up $6,000 in PM Time (MM23) 9308.00 - DOC NCCF Generator System Control Replacement: Set up $6,000 in PM Time (MM23) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov James Trower - PM Time $Joni Trower, James 1:08 PM (50 minutes ago) to me Finance - See below items: 9203.00 - DOC NCCF Treatment Center EIFS Replacement: Increase PM Time by $5,000 (MM21) 9231.00 - DAS CC Jessie Parker Water: Increase PM Time by $4,000 (MM22) 9250.00 - DOC MPCF Building 18 Roof Replacement: Increase PM Time by $5,000 (MM22) 9297.00 - DOC MPCF Gym Floor Repair: Set up $6,000 in PM Time (MM21) 9300.00 - DOC MPFC Storage Bunker Repair: Set up $6,000 in PM Time (MM21) 9301.00 - DPS DSM Fleet & Supply 2nd Floor Structural: Set up $4,000 in PM Time 9305.00 - DAS CC Capitol South Stair Repair:Set up $6,000 in PM Time (MM23) 9308.00 - DOC NCCF GeeraPm Time Increases $Joni Trower, James Thu, Aug 31, 2:05 PM (6 days ago) to me Finance - Please make the below increases to PM Time: 9203.00 - Treatment Center EIFS Replacement (MM21) - Increase PM Time by $5,000 9231.00 - Jessie Parker Water Infiltration Repair (MM22) - Increase PM Time by $1,000 9251.00 - DPS P09 Parking Lot Replacement (MM22) - Increase PM Time by $1,000 9252.00 - Window Replacement (MM22) - Increase PM Time by $1,000 9305.00 - DAS CC Capitol North and South Stair Repair (MM23) - Increase PM Time by $6,000 9334.00 - DPS Post 9 Interior Renovation (DA23) - Increase PM Time by $3,000 9336.00 - DPS Post 8 Water Damage Repair (DA23) - Increase PM Time by $3tor System Control Replacement: Set up $6,000 in PM Time (MM23) Thanks, James Trower, Licensed Architect/LEED A Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James 3:20 PM (32 minutes ago) to me, John John - Re: PM Time I Trower, James Jul 12, 2023, 4:17 PM (15 hours ago) to me Finance - Please make the below changes in red: 9249.00 MM23 amount to post is 1198.68 Increase PM Time by $5,000 9250.00 MM23 amount to post is 915.35 Increase PM Time by $5,000 9342.00 MM21 amount to post is 4679.40 Increase PM Time by $5,000 9231.00 MM22 amount to post is 590.70 Increase PM Time by $1,000 9304.00 MM23 amount to post is 2684.00 Increase PM Time by $6,000 Thanks, Jamesnbox Trower, James 2:58 PM (8 minutes ago) to me John - See below: 9258.00 MM22: Please increase PM Time by $5,000 9231.00 MM22 Please increase PM Time by $3,000 Please see below in red: On Fri, Feb 10, 2023 at 3:14 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi James MM21-9203.00 is short by $19.11 when posting $1,282.57 Increase PM Time by $2,000 MM21-9224.00 is short by $128.25 when posting $291.49 Increase PM Time by $5,000 MM22-9231.00 is short by $712.15 when posting $1,340.87 Increase PM Time by $2,000 MM22-9250.00 is short by $1,007.49 when posting $2,914.93 Increase PM Time by $3,00

## #9231.00 Misc
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522123901 | 2022-05-02 | 9500 | CNST | ATC Group V# (00002134218) | Inv. 2422833-Final | 1412.5 | 1412.5
IET DAS202303115300001 | 2022-10-07 | 2507 |  | #207134146 Moving Parking Signs | Inv. DAS2023031153 | 91.2 | 1503.7
GAX 33523307904 | 2022-11-01 | 9500 | DSGN | Bolton&MenkV#00002104085 | Inv. 0299897 | 2000 | 3503.7
IET DAS202305115300001 | 2022-12-07 | 2507 |  | Fire Watch Service #207137173 | DAS2023051153 | 136.99 | 3640.69
IET DAS202306115300001 | 2023-01-09 | 2507 |  | Remove ADA signs & reinstall #207136494 | DAS2023061153 | 120.76 | 3761.45
IET DAS202308115300001 | 2023-03-07 | 2507 |  | Locksmith & Key Services | DAS2023081153 | 212.88 | 3974.33
IET DAS202311115300001 | 2023-06-07 | 2507 |  | ADA Signs | DAS2023111153 | 99.28 | 4073.61
4073.61
4073.61
4073.61
4073.61
4073.61
|  |  |  | Totals: |  | 4073.61

## #9231.00 DCI Group
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-CM Firm-DCI 9112015
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522293801 | 2021-10-20 | PO Procore | 7499.97 | 7499.97 |  |  | 7499.97
PRC 3352229PA3801 | 2021-11-23 | Inv. 21-039 PC-01 |  | 7499.97 | 956.84 | 956.84 | 6543.13
PRC 3352229PB3801 | 2021-12-20 | Inv. 21-039 PC-02 |  | 7499.97 | 1729.16 | 2686 | 4813.97
PRC 3352229PC3801 | 2022-01-12 | Inv. 21-039 PC-03 |  | 7499.97 | 1441.24 | 4127.24 | 3372.73
PRC 3352229PD3801 | 2022-02-24 | Inv. 21-039 PC-04 |  | 7499.97 | 1398.48 | 5525.72 | 1974.25
PRC 3352229PE3801 | 2022-03-28 | Inv. 21-039 PC-05 |  | 7499.97 | 1480.22 | 7005.94 | 494.03
PRC 3352229PF3801 | 2022-04-25 | Inv. 21-039 PC-06 Final | -2.07 | 7497.9 | 491.96 | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  |  |  | 7497.9 |  | 7497.9 | 4.4809e-13
|  | Totals: | 7497.9 |  | 7497.9 |  | 0

## #9231.00 Bergstrom Construction
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFQ923100-02
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522181802 | 2022-06-29 | PO Procore | 19998 | 19998 |  |  | 19998 |  | FY22
PO 33523181802 | 2022-08-08 | Rolled to FY23 | 0 | 19998 |  | 0 | 19998
PO 33523181802 | 2022-10-21 | CO 1 | 6839 | 26837 |  | 0 | 26837
PO 33523181802 | 2022-12-13 | CO 2(No Cost CO) | 0 | 26837 |  | 0 | 26837
PRC 3352318PA1802 | 2023-03-14 | Inv. 9231.00-01 |  | 26837 | 23570.59 | 23570.59 | 3266.41 | 1240.56
PO 33523181802 | 2023-03-29 | CO 3 | 425 | 27262 |  | 23570.59 | 3691.41
PRC 3352318PB1802 | 2023-05-02 | Inv. 8448-2 |  | 27262 | 2328.31 | 25898.9 | 1363.1 | 1363.1025
PRC 3352318PC1802 | 2023-07-17 | Inv. 8448 retainage |  | 27262 | 1363.1 | 27262 | 0
|  |  |  | 27262 |  | 27262 | 0
|  |  |  | 27262 |  | 27262 | 0
|  |  |  | 27262 |  | 27262 | 0
|  |  |  | 27262 |  | 27262 | 0
|  |  |  | 27262 |  | 27262 | 0
|  | Totals: | 27262 |  | 27262 |  | 0 | FINAL

## #9231.00 Iowa Contracting
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Iowa Contracting |  |  | Vendor: 00003106386
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ923100-03
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523203801 | 2022-07-13 | PO Procore | 28200 | 28200 |  |  | 28200
PO 33523203801 | 2022-11-22 | CO 1 | 64436.5 | 92636.5 |  | 0 | 92636.5
PO 33523203801 | 2022-12-13 | CO 2(No cost CO) | 0 | 92636.5 |  | 0 | 92636.5
PRC 3352320PA3801 | 2023-01-16 | Inv. 9231.00-01 |  | 92636.5 | 75993.1 | 75993.1 | 16643.4 | 3999.65
PO 33523203801 | 2023-03-23 | CO 3 | 900 | 93536.5 |  | 75993.1 | 17543.4
PRC 3352320PB3801 | 2023-07-17 | Inv. 9231.00-02 |  | 93536.5 | 12866.56 | 88859.66 | 4676.84 | 4676.84
PRC 3352320PC3801 | 2023-07-20 | Inv. 9231.00-03 - RETAINAGE |  | 93536.5 | 4676.84 | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  |  |  | 93536.5 |  | 93536.5 | 0
|  | Totals: | 93536.5 |  | 93536.5 |  | 0 | FINAL

## #9231.00 Cable Glass
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Cable Glass DBA Forman Ford |  |  | Vendor: 00002090996
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ923100-02
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523203802 | 2022-07-13 | PO Procore | 7892 | 7892 |  |  | 7892
PO 33523203802 | 2022-10-28 | CO 1 | 4493 | 12385 |  | 0 | 12385
PO 33523203802 | 2022-11-21 | CO 2(No Cost CO) | 0 | 12385 |  | 0 | 12385
PO 33523203802 | 2022-12-20 | CO 3 | 640 | 13025 |  | 0 | 13025
PRC 3352320PA3802 | 2023-03-14 | Inv. S6516-1 |  | 13025 | 12373.75 | 12373.75 | 651.25 | 651.25
PRC 3352320PB3802 | 2023-07-17 | Inv. S6516 Retainage |  | 13025 | 651.25 | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  |  |  | 13025 |  | 13025 | 0
|  | Totals: | 13025 |  | 13025 |  | 0 | FINAL

## #9231.00 DCI Group CA
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523210901 | 2022-07-28 | PO Procore | 21783.05 | 21783.05 |  |  | 21783.05
PRC 3352321PA0901 | 2022-09-21 | Inv. 21-039 CA-01 |  | 21783.05 | 11959.86 | 11959.86 | 9823.19
PO 33523210901 | 2022-10-21 | CO 1 | 5747.37 | 27530.42 |  | 11959.86 | 15570.56
PRC 3352321PB0901 | 2022-11-07 | Inv. 21-039 CA-02 |  | 27530.42 | 3822.82 | 15782.68 | 11747.74
PRC 3352321PC0901 | 2022-11-14 | Inv. 21-039 CA-03 |  | 27530.42 | 3803.72 | 19586.4 | 7944.02
PRC 3352321PD0901 | 2023-02-07 | Inv. 21-039 CA-04 |  | 27530.42 | 2388.85 | 21975.25 | 5555.17
PO 33523210901 | 2023-02-07 | CO 2 | 500 | 28030.42 |  | 21975.25 | 6055.17
PRC 3352321PE0901 | 2023-03-28 | Inv. 21-039 CA-05 |  | 28030.42 | 3703.73 | 25678.98 | 2351.44
PRC 3352321PF0901 | 2023-04-25 | Inv. 21-039 CA-06 |  | 28030.42 | 1629.17 | 27308.15 | 722.27
PO 33523210901 | 2023-05-19 | CO 3 | 2000 | 30030.42 |  | 27308.15 | 2722.27
PRC 3352321PG0901 | 2023-06-23 | Inv. 21-039 CA-07 Final | -359.18 | 29671.24 | 2363.09 | 29671.24 | -1.9895e-12
|  |  |  | 29671.24 |  | 29671.24 | -1.9895e-12
|  |  |  | 29671.24 |  | 29671.24 | -1.9895e-12
|  | Totals: | 29671.24 |  | 29671.24 |  | 0 | FINAL
|  | Construction Management | 16262.05 |  | 16262.05 |  | 0
|  | Reimbursables | 5521 |  | 5521 |  | 0
|  | CO 1 | 5613.25 |  | 5613.25 |  | 0
|  | CO 2 | 500 |  | 500 |  | 0
|  | CO 3 | 1774.94 |  | 1774.94 |  | 0
|  | Total: | 29671.24 |  | 29671.24 |  | 0

## #9231.00 Controlled Asbestos
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | MA21060
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523229904 | 2022-08-16 | DO Procore | 6888.76 | 6888.76 |  |  | 6888.76
DO 33523229904 | 2023-03-02 | CO #1 | 2887.84 | 9776.6 |  | 0 | 9776.6
PRC 3352322PA9904 | 2023-04-17 | Inv. 0010529-IN FINAL | -195.86 | 9580.74 | 9580.74 | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  |  |  | 9580.74 |  | 9580.74 | 0
|  | Totals: | 9580.74 |  | 9580.74 |  | 0 | FINAL
|  | Line 1 Asbestos abatement Services 104hrs@$58/hr | 6032 |  | 6032 |  | 0
|  | Line 1 Asbestos abatement Services .5hrsX7trips=3.5hrsX58 | 203 |  | 203 |  | 0
|  | Line 7 Abatement Remediation (Lump Sum) | 419.85 |  | 419.85 |  | 0
|  | Line 7 DNR Fee | 100 |  | 100 |  | 0
|  | Line 11 Friable Disposal Fee 1.01 tons @$64/ton | 64.64 |  | 64.64 |  | 0
|  | Line12 Travel Expenses 84 miles @ 0.39/mile | 32.76 |  | 32.76 |  | 0
|  | CO #1 | 2728.49 |  | 2728.49 |  | 0
|  | Total: | 9580.74 |  | 9580.74 |  | 0

## #9231.00 Waldinger Electrical
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Waldinger Corp-Electrical |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | MA20452
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523283901 | 2022-10-10 | PO Procore | 7475.2 | 7475.2 |  |  | 7475.2
PRC 3352328PA3901 | 2023-05-10 | Inv. 68585E-001 |  | 7475.2 | 6190.15 | 6190.15 | 1285.05
PO 33523283901 | 2023-08-15 | Closing PO Per PM & Vendor | -1285.05 | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  |  |  | 6190.15 |  | 6190.15 | 0
|  | Totals: | 6190.15 |  | 6190.15 |  | 0

## #9231.00 Waldinger Plumbing
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Waldinger Corp-Plumbing |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | MA21012
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523283902 | 2022-10-10 | PO Procore | 19654.8 | 19654.8 |  |  | 19654.8
PO 33523283902 | 2023-04-10 | CO #1 (No Cost) | 0 | 19654.8 |  | 0 | 19654.8
PRC 3352328PA3902 | 2023-05-10 | Inv. 68585P-001 |  | 19654.8 | 17654.1 | 17654.1 | 2000.7
PO 33523283902 | 2023-08-15 | Closing PO Per PM & Vendor | -2000.7 | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  |  |  | 17654.1 |  | 17654.1 | 0
|  | Totals: | 17654.1 |  | 17654.1 |  | 0

## #9231.00 Johnson Controls
DAS CC Jessie Parker Water Infiltration Repair
Project # 9231.00
Program code 923100 |  |  | Major Program 4F04
Johnson Controls |  |  | Vendor: 00002139022
Acct. Codes-0017-335-MM22-9255 |  |  | MA20003A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523299902 | 10/25/22 | DO Procore | 5674 | 5674 |  |  | 5674
PRC 3352329PA9902 | 2023-08-29 | Inv. 51166555 | -3852.42 | 1821.58 | 1821.58 | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  |  |  | 1821.58 |  | 1821.58 | 0
|  | Totals: | 1821.58 |  | 1821.58 |  | 0 | FINAL

## RECAP #9232.00
DCA TMVC Siding Replacement
Project # 9232.00
| Program code 923200 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 84802.21
C | Samuels Group PC |  | 7378.31 | 7378.31 | 0
C | PM TIME |  | 10105.51 | 10105.51 | 0
C | Misc. |  | 0 | 0 | 0
C | Horizon Architecture |  | 5720 | 5720 | 0
C | Premier Plus Siding & Windows |  | 46729.17 | 46729.17 | 0
C | Samuels Group CA |  | 14869.22 | 14869.22 | 0
| Total Project Cost | 84802.21 | 84802.21 | 84802.21 | 0 | 0
Closed 01/17/2023

## #9232.00 Samuels Group PC
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  | Major Program 4E19
Samuels Group PC |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522267505 | 2021-09-24 | PO Procore | 7615.63 | 7615.63 |  |  | 7615.63
PRC 3352226PA7505 | 2021-12-10 | Inv. 7361.20PC |  | 7615.63 | 1001.26 | 1001.26 | 6614.37
PRC 3352226PB7505 | 2022-02-08 | Inv. 7361.21PC |  | 7615.63 | 874.07 | 1875.33 | 5740.3
PRC 3352226PC7505 | 2022-03-09 | Inv. 7361.22PC |  | 7615.63 | 3630.36 | 5505.69 | 2109.94
PRC 3352226PD7505 | 2022-04-11 | Inv. 7361.23 PC Final | -237.32 | 7378.31 | 1872.62 | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  |  |  | 7378.31 |  | 7378.31 | 0
|  | Totals: | 7378.31 |  | 7378.31 |  | 0
|  | CM Services | 7295.63 |  | 7295.63 |  | 0
|  | Reimbursables | 82.68 |  | 82.68 |  | 0
|  | Total: | 7378.31 |  | 7378.31 |  | 0

## #9232.00 PM TIME
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  | Major Program 4E19
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 7913.6 | 7913.6 |  |  | 7913.6
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 7913.6 | 675 | 675 | 7238.6
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 7913.6 | 475 | 1150 | 6763.6
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 7913.6 | 350 | 1500 | 6413.6
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 7913.6 | 400 | 1900 | 6013.6
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 7913.6 | 275 | 2175 | 5738.6
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 7913.6 | 800 | 2975 | 4938.6
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 7913.6 | 450 | 3425 | 4488.6
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 7913.6 | 400 | 3825 | 4088.6
IET DAS2022011115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 7913.6 | 200 | 4025 | 3888.6
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 7913.6 | 300 | 4325 | 3588.6
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 7913.6 | 325 | 4650 | 3263.6
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 7913.6 | -325 | 4325 | 3588.6
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 7913.6 | 357.5 | 4682.5 | 3231.1
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 7913.6 | 1265 | 5947.5 | 1966.1
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 7913.6 | 550 | 6497.5 | 1416.1
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 7913.6 | 550 | 7047.5 | 866.1
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30,2022 |  | 7913.6 | 302.5 | 7350 | 563.6
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 186.77 | 8100.37 | 186.77 | 7536.77 | 563.6
IET DAS202205115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 1075.65 | 9176.02 | 1075.65 | 8612.42 | 563.6
IET DAS202205115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 296 | 9472.02 | 296 | 8908.42 | 563.6
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 401.59 | 9873.61 | 401.59 | 9310.01 | 563.6
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 231.9 | 10105.51 | 231.9 | 9541.91 | 563.6
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 10105.51 | 563.6 | 10105.51 | 0
|  |  |  | 10105.51 |  | 10105.51 | 0
|  |  |  | 10105.51 |  | 10105.51 | 0
|  | Totals: | 10105.51 |  | 10105.51 |  | 0
Note on D9: Wray, Ronda [DAS]: PM TIME - James Trower $Ronda Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Finance - Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative PM Time - Increase Request $Selma Trower, James Fri, Jun 17, 2:47 PM (3 days ago) to me Finance - Please increase PM Time for the following projects: 9232.00 - DCA TMVC Toolesboro Mounds Visitor Center Siding Replacement: Increase PM Time by $3,000 9237.00 - DAS CC Hoover East Side Paver Repairs: Increase PM Time by $4,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Project 9232.00 - Close Project $Joni Trower, James 1:54 PM (22 minutes ago) to me Finance - Reduce PM Time by $86.40 and return to MM22 pool fund. Please close the project and return all remaining funds to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9232.00 Misc
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9232.00 Horizon Architecture
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  | Major Program 4E19
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522038900 | 2022-02-04 | PO Procore | 5720 | 5720 |  |  | 5720
PRC 3352203PA8900 | 2022-02-11 | Inv. 9232.00-01 |  | 5720 | 3050 | 3050 | 2670
PRC 3352203PB8900 | 2022-05-05 | Inv. 9232.00-02 |  | 5720 | 980 | 4030 | 1690 | FY22
PO 33523038900 | 2022-08-08 | Rolled to FY23 | 0 | 5720 |  | 4030 | 1690
PRC 3352303PC8900 | 2022-11-28 | Inv. 9232.00-03-Final |  | 5720 | 1690 | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  |  |  | 5720 |  | 5720 | 0
|  | Totals: | 5720 |  | 5720 |  | 0
|  | Design & Documentation | 3050 |  | 3050 |  | 0
|  | Bidding Assistance | 980 |  | 980 |  | 0
|  | Construction Administration | 1690 |  | 1690 |  | 0
|  | Total: | 5720 |  | 5720 |  | 0

## #9232.00 Premier Plus
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  | Major Program 4E19
Premier Plus Siding & Windows |  |  | Vendor: 00003196527
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ923200-01
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522101800 | 2022-04-08 | PO Procore | 46153.85 | 46153.85 |  |  | 46153.85 |  | FY22
PO 33523101800 | 2022-08-08 | Rolled to FY23 | 0 | 46153.85 |  | 0 | 46153.85
PO 33523101800 | 2022-08-11 | CO #1 (no cost) | 0 | 46153.85 |  | 0 | 46153.85
PRC 3352310PA1800 | 2022-08-25 | Inv. 2111 |  | 46153.85 | 40667.28 | 40667.28 | 5486.57 | 2140.39
PO 33523101800 | 2022-09-12 | CO #2 | 575.32 | 46729.17 |  | 40667.28 | 6061.89
PRC 3352310PB1800 | 2022-10-25 | Inv. 2111-2 |  | 46729.17 | 2775.43 | 43442.71 | 3286.46 | 2286.46
PRC 3352310PC1800 | 2022-11-13 | Inv. 2122 |  | 46729.17 | 950 | 44392.71 | 2336.46 | 2336.46
PRC 3352310PD1800 | 2022-11-28 | Inv. 2111-retainage |  | 46729.17 | 2336.46 | 46729.17 | 0
|  |  |  | 46729.17 |  | 46729.17 | 0
|  |  |  | 46729.17 |  | 46729.17 | 0
|  |  |  | 46729.17 |  | 46729.17 | 0
|  |  |  | 46729.17 |  | 46729.17 | 0
|  |  |  | 46729.17 |  | 46729.17 | 0
|  | Totals: | 46729.17 |  | 46729.17 |  | 0

## #9232.00 Samuels Group CA
DCA TMVC Siding Replacement
Project # 9232.00
Program code 923200 |  |  | Major Program 4E19
Samuels Group CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522110801 | 2022-04-13 | PO Procore | 16074.22 | 16074.22 |  |  | 16074.22
PRC 3352211PA0801 | 2022-05-10 | Inv. 7405.10 CA |  | 16074.22 | 1413.44 | 1413.44 | 14660.78
PRC 3352211PB0801 | 2022-06-05 | Inv. 7405.11 CA |  | 16074.22 | 497.92 | 1911.36 | 14162.86
PRC 3352211PC0801 | 2022-07-06 | Inv. 7405.12 CA |  | 16074.22 | 500.63 | 2411.99 | 13662.23 | FY22
PO 33523110801 | 2022-08-08 | Rolled to FY23 | 0 | 16074.22 |  | 2411.99 | 13662.23
PRC 3352311PD0801 | 2022-08-12 | Inv. 7405.13 CA |  | 16074.22 | 687.35 | 3099.34 | 12974.88
PRC 3352311PE0801 | 2022-09-09 | Inv. 7405.13CA |  | 16074.22 | 6069.55 | 9168.89 | 6905.33
PRC 3352311PF0801 | 2022-10-11 | Inv. 7405.15 CA |  | 16074.22 | 1371.99 | 10540.88 | 5533.34
PRC 3352311PG0801 | 2022-11-04 | Inv. 7405.16 CA |  | 16074.22 | 2071.44 | 12612.32 | 3461.9
PRC 3352311PH0801 | 2022-12-01 | Inv. 7405.17 CA FINAL | -1205 | 14869.22 | 2256.9 | 14869.22 | 0
|  |  |  | 14869.22 |  | 14869.22 | 0
|  |  |  | 14869.22 |  | 14869.22 | 0
|  |  |  | 14869.22 |  | 14869.22 | 0
|  | Total: | 14869.22 |  | 14869.22 |  | 0 | FINAL
|  | CM Services | 14252.96 |  | 14252.96 |  | 0
|  | Reimbursables | 616.26 |  | 616.26 |  | 0
|  | Total: | 14869.22 |  | 14869.22 |  | 0

## RECAP #9233.00
DHS GRC Building 105, 111 and 703 Tuckpointing
Project # 9233.00
| Program code 923300 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM22
Project Manager - Doug C
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 33179.1
C | Samuels Group PC |  | 10529.1 | 10529.1 | 0
C | PM TIME |  | 5165 | 5165 | 0
C | Misc. |  | 1785 | 1785 | 0
C | Genesis Design |  | 15700 | 15700 | 0
| Total Project Cost | 33179.1 | 33179.1 | 33179.1 | 0 | 0
Closed 08/12/2022

## #9233.00 Samuels Group PC
DHS GRC Building 105, 111 and 703 Tuckpointing
Project # 9233.00
Program code 923300 |  |  | Major Program 4E10
Samuels Group PC |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - Doug C |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522281502 | 2021-10-08 | PO Procore | 15313.44 | 15313.44 |  |  | 15313.44
PRC 3352228PA1502 | 2021-11-02 | Inv. 7368.10 |  | 15313.44 | 741.95 | 741.95 | 14571.49
PRC 3352228PB1502 | 2022-01-05 | Inv. 7368.20PC |  | 15313.44 | 2414.79 | 3156.74 | 12156.7
PRC 3352228PC1502 | 2022-02-08 | Inv. 7368.21PC |  | 15313.44 | 2308.3 | 5465.04 | 9848.4
PRC 3352228PD1502 | 2022-03-08 | Inv. 7368.22PC |  | 15313.44 | 746.88 | 6211.92 | 9101.52
PRC 3352228PE1502 | 2022-04-11 | Inv. 7368.23 PC |  | 15313.44 | 1431.52 | 7643.44 | 7670
PRC 3352228PF1502 | 2022-05-06 | Inv. 7368.24 PC |  | 15313.44 | 2382.32 | 10025.76 | 5287.68
PRC 3352228PG1502 | 2022-07-15 | Inv. 7368.25 PC FINAL | -4784.34 | 10529.1 | 503.34 | 10529.1 | 0
|  |  |  | 10529.1 |  | 10529.1 | 0
|  |  |  | 10529.1 |  | 10529.1 | 0
|  |  |  | 10529.1 |  | 10529.1 | 0
|  |  |  | 10529.1 |  | 10529.1 | 0
|  |  |  | 10529.1 |  | 10529.1 | 0
|  | Totals: | 10529.1 |  | 10529.1 |  | 0 | Final Invoice
|  | CM Services | 10256.1 |  | 10256.1 |  | 0
|  | Reimbursables | 273 |  | 273 |  | 0
|  | Total: | 10529.1 |  | 10529.1 |  | 0

## #9233.00 PM TIME
DHS GRC Building 105, 111 and 703 Tuckpointing
Project # 9233.00
Program code 923300 |  |  | Major Program 4E10
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 5165 | 5165 |  |  | 5165
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 5165 | 400 | 400 | 4765
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 5165 | 400 | 800 | 4365
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 5165 | 350 | 1150 | 4015
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 5165 | 800 | 1950 | 3215
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 5165 | 1000 | 2950 | 2215
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 5165 | 450 | 3400 | 1765
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 5165 | 600 | 4000 | 1165
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 5165 | 900 | 4900 | 265
IET DAS2022012115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 5165 | 100 | 5000 | 165
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 5165 | 150 | 5150 | 15
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 5165 | -150 | 5000 | 165
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 5165 | 165 | 5165 | 0
|  | Totals: | 5165 |  | 5165 |  | 0
Note on D9: Durakovic, Selma [DAS]: Re: PM Time Budget $Selma Carper, Douglas 9:12 AM (3 hours ago) to me MM19: 9123.00 - Increase PM time to $8,700.00. 9169.01 - Increase PM time to $6,000.00. 9178.00 - Increase PM time to $5,000.00. MM20: 9108.00 - Increase PM time to $6,200.00. 9137.00 - Put time to 9139.00 9139.00 - Increase PM time to $15,000.00. 9140.00 - Increase PM time to 12,000.00. 9141.00 - Move to MM21 MM21: 9099.00 - Set PM time budget to $12,000.00. 9141.00 - Set PM time budget $6,000.00. MM22: 9230.00 - Set PM time budget to $9,000.00. 9233.00 - Set PM time budget to $15,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov

## #9233.00 Misc
DHS GRC Building 105, 111 and 703 Tuckpointing
Project # 9233.00
Program code 923300 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522166902 | 2022-06-15 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2417292-Final | 1785 | 1785
1785
1785
1785
1785
1785
1785
1785
1785
1785
1785
1785
|  |  |  | Totals: |  | 1785

## #9233.00 Genesis Design
DHS GRC Building 105, 111 and 703 Tuckpointing
Project # 9233.00
Program code 923300 |  |  | Major Program 4E10
Genesis Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RPF/B: 923300-01
Project Manager - Doug C |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522020902 | 2022-01-20 | PO Procore | 29900 | 29900 |  |  | 29900
PRC 3352202PA0902 | 2022-02-07 | Inv. 2201-01 |  | 29900 | 1350 | 1350 | 28550
PRC 3352202PB0902 | 2022-03-09 | Inv. 2201-02 |  | 29900 | 4050 | 5400 | 24500
PRC 3352202PC0902 | 2022-04-26 | Inv. 2201-03 |  | 29900 | 10300 | 15700 | 14200
PO 33522020902 | 2022-07-15 | Closing PO per vendor and PM | -14200 | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  |  |  | 15700 |  | 15700 | 0
|  | Totals: | 15700 |  | 15700 |  | 0
|  | Schematic Design Phase | 5400 |  | 5400 |  | 0
|  | Design Development Phase | 5200 |  | 5200 |  | 0
|  | Construction Documents | 5100 |  | 5100 |  | 0
|  | Bid Phase | 0 |  | 0 |  | 0
|  | Construction Phase | 0 |  | 0 |  | 0
|  | Total: | 15700 |  | 15700 |  | 0

## RECAP #9234.00
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
| Program code 923400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 453120.21
C | Samuels Group |  | 12565.61 | 12565.61 | 0
C | PM TIME |  | 25461.19 | 25461.19 | 0
C | Misc. |  | 1148.63 | 1148.63 | 0
C | Genesis Architectural Design |  | 23800 | 23800 | 0
C | Samuels Group |  | 50544.78 | 50544.78 | 0
C | MTS Contracting |  | 339600 | 339600 | 0
| Total Project Cost | 453120.21 | 453120.21 | 453120.21 | 0 | 0
Closed 09/14/23

## #9234.00 Samuels Group
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522272501 | 2021-09-29 | PO Procore | 12619.75 | 12619.75 |  |  | 12619.75
PRC 3352227PA2501 | 2021-11-05 | Inv. 7365.01923400 |  | 12619.75 | 1032.87 | 1032.87 | 11586.88
PRC 3352227PB2501 | 2021-12-09 | Inv. 7365.02923400 |  | 12619.75 | 1389.15 | 2422.02 | 10197.73
PRC 3352227PC2501 | 2022-01-04 | Inv. 7365.03923400 |  | 12619.75 | 1309.75 | 3731.77 | 8887.98
PRC 3352227PD2501 | 2022-02-09 | Inv. 7365.04923400 |  | 12619.75 | 562.87 | 4294.64 | 8325.11
PRC 3352227PE2501 | 2022-03-09 | Inv. 7365.05923400 |  | 12619.75 | 746.88 | 5041.52 | 7578.23
PRC 3352227PF2501 | 2022-04-17 | Inv. 7365.06923400 |  | 12619.75 | 1060.79 | 6102.31 | 6517.44
PRC 3352227PG2501 | 2022-05-05 | Inv. 7365.07923400 |  | 12619.75 | 2781.88 | 8884.19 | 3735.56
PRC 3352227PH2501 | 2022-05-31 | Inv. 7365.08923400 FINAL | -54.14 | 12565.61 | 3681.42 | 12565.61 | 3.2685e-13
|  |  |  | 12565.61 |  | 12565.61 | 3.2685e-13
|  |  |  | 12565.61 |  | 12565.61 | 3.2685e-13
|  |  |  | 12565.61 |  | 12565.61 | 3.2685e-13
|  |  |  | 12565.61 |  | 12565.61 | 3.2685e-13
|  | Totals: | 12565.61 |  | 12565.61 |  | 0
|  | CM Services | 12469.69 |  | 12469.69 |  | 0
|  | Reimbursables | 95.92 |  | 95.92 |  | 0
|  | Total: | 12565.61 |  | 12565.61 |  | 0

## #9234.00 PM TIME
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906S
Project Manager - Brad T
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 19966.31 | 19966.31 |  |  | 19966.31
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 19966.31 | 200 | 200 | 19766.31
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 19966.31 | 350 | 550 | 19416.31
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 19966.31 | 175 | 725 | 19241.31
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 19966.31 | 775 | 1500 | 18466.31
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 19966.31 | 375 | 1875 | 18091.31
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 19966.31 | 525 | 2400 | 17566.31
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 19966.31 | 575 | 2975 | 16991.31
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 19966.31 | 800 | 3775 | 16191.31
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 19966.31 | 875 | 4650 | 15316.31
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 19966.31 | 975 | 5625 | 14341.31
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 19966.31 | 725 | 6350 | 13616.31
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 19966.31 | -725 | 5625 | 14341.31
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 19966.31 | 797.5 | 6422.5 | 13543.81
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 19966.31 | 907.5 | 7330 | 12636.31
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 19966.31 | 605 | 7935 | 12031.31
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 19966.31 | 990 | 8925 | 11041.31
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 19966.31 | 1045 | 9970 | 9996.31
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 736.59 | 20702.9 | 736.59 | 10706.59 | 9996.31
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 935.84 | 21638.74 | 935.84 | 11642.43 | 9996.31
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 546.04 | 22184.78 | 546.04 | 12188.47 | 9996.31
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1120.8 | 23305.58 | 1120.8 | 13309.27 | 9996.31
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 926.47 | 24232.05 | 926.47 | 14235.74 | 9996.31
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 24232.05 | 1480.93 | 15716.67 | 8515.38
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 24232.05 | 34.75 | 15751.42 | 8480.63
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 24232.05 | 304.6 | 16056.02 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 216.53 | 24448.58 | 216.53 | 16272.55 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 260.96 | 24709.54 | 260.96 | 16533.51 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 183.81 | 24893.35 | 183.81 | 16717.32 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 136.38 | 25029.73 | 136.38 | 16853.7 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 209.9 | 25239.63 | 209.9 | 17063.6 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 221.56 | 25461.19 | 221.56 | 17285.16 | 8176.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 25461.19 | 33.42 | 17318.58 | 8142.61
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 25461.19 | 202.71 | 17521.29 | 7939.9
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 25461.19 | 176.29 | 17697.58 | 7763.61
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 25461.19 | 775.41 | 18472.99 | 6988.2
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 25461.19 | 208.65 | 18681.64 | 6779.55
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 25461.19 | 1229.4 | 19911.04 | 5550.15
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 25461.19 | 257.09 | 20168.13 | 5293.06
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 25461.19 | 1799.6 | 21967.73 | 3493.46
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for: June 1-30, 2023 |  | 25461.19 | 165.13 | 22132.86 | 3328.33
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for: June 1-30, 2023 |  | 25461.19 | 1360.2 | 23493.06 | 1968.13
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 25461.19 | 154.03 | 23647.09 | 1814.1
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 25461.19 | 982.7 | 24629.79 | 831.4
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 25461.19 | 126.4 | 24756.19 | 705
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 25461.19 | 705 | 25461.19 | 0
[5 empty] | 25461.19 |  | 25461.19 | 0
|  |  | Totals: | 25461.19 |  | 25461.19 |  | 0
Note on E9: Wray, Ronda [DAS]: PM Time Set up on New Projects $Ronda Tonyan, Bradley 8:51 AM (1 hour ago) to me, Scott Finance, Can you please set up the following PM time budgets on the following projects below: - MM22 - 9234.00 - DOC NCF A, B, C, D, E, H, K, L, J Pre-cast Joint Repairs - $16,000 - MM22 - 9235.00 - DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing - $8,000 Thank you, Brad Tonyan, Owner Representative Re: MM22 9234.00 Inbox Tonyan, Brad 10:35 AM (17 minutes ago) to me Please raise 472.85 to cover. On Fri, Jun 16, 2023, 10:32 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: I have to have a specific amount to change PM Time. ~Joni Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. Tonyan, Brad 2:24 PM (1 minute ago) to me John and Finance. Please raise the PM time budget $660.00 to cover the added PM time. Thank you,

## #9234.00 Misc
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522081901 | 2022-03-21 | 9500 | CNST | ATC Group V# (00002134218) | Inv. 2413280-Final | 797.5 | 797.5
PRC 33522153904 | 2022-06-01 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV021003 | 351.13 | 1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
1148.63
|  |  |  | Totals: |  | 1148.63

## #9234.00 Genesis
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  | Major Program 4B01
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 923400-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522350902 | 2021-12-14 | PO Procore | 23800 | 23800 |  |  | 23800
PRC 3352235PA0902 | 2022-02-10 | Inv. 2115-01 |  | 23800 | 5900 | 5900 | 17900
PRC 3352235PB0902 | 2022-03-09 | Inv. 2115-02 |  | 23800 | 5250 | 11150 | 12650
PRC 3352235PC0902 | 2022-04-25 | Inv. 2115-03 |  | 23800 | 3350 | 14500 | 9300
PRC 3352235PD0902 | 2022-06-06 | Inv. 2115-04 |  | 23800 | 1500 | 16000 | 7800
PRC 3352235PE0902 | 2022-07-12 | Inv. 2115-05 |  | 23800 | 390 | 16390 | 7410 | FY22
PO 33523350902 | 2022-08-08 | Rolled to FY23 | 0 | 23800 |  | 16390 | 7410
PRC 3352335PF0902 | 2022-12-14 | Inv. 2115-06 |  | 23800 | 1365 | 17755 | 6045
PRC 3352335PG0902 | 2023-06-07 | Inv. 2115-07 |  | 23800 | 3315 | 21070 | 2730
PRC 3352335PH0902 | 2023-06-30 | Inv. 2115-08 |  | 23800 | 936 | 22006 | 1794 | FY23
PO 33524350902 | 2023-08-03 | Roll to FY24 | 0 | 23800 |  | 22006 | 1794
PRC 3352435PI0902 | 2023-08-09 | Inv. 2115-09 |  | 23800 | 1014 | 23020 | 780
PRC 3352435PJ0902 | 2023-09-12 | Inv. 2115-10 - FINAL |  | 23800 | 780 | 23800 | 0
|  | Totals: | 23800 |  | 23800 |  | 0 | FINAL
|  | Schematice Design | 4000 |  | 4000 |  | 0
|  | Design Development | 3800 |  | 3800 |  | 0
|  | Construction Documents | 6700 |  | 6700 |  | 0
|  | Bidding Assistance | 1500 |  | 1500 |  | 0
|  | Construction Phase | 7800 |  | 7800 |  | 0
|  | Total: | 23800 |  | 23800 |  | 0

## #9234.00 Samuels Group (2)
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522151901 | 2022-05-31 | PO Procore | 52020.79 | 52020.79 |  |  | 52020.79
PRC 3352215PA1901 | 2022-06-30 | Inv. 7365.51923400 |  | 52020.79 | 1217.75 | 1217.75 | 50803.04 | FY22
PO 33523151901 | 2022-08-08 | Rolled to FY23 | 0 | 52020.79 |  | 1217.75 | 50803.04
PRC 3352315PB1901 | 2022-08-01 | Inv. 7365.52923400 |  | 52020.79 | 1125.74 | 2343.49 | 49677.3
PRC 3352315PC1901 | 2022-09-08 | Inv. 7365.53923400 |  | 52020.79 | 817.25 | 3160.74 | 48860.05
PRC 3352315PD1901 | 2022-09-30 | Inv. 7365.54923400 |  | 52020.79 | 1401.76 | 4562.5 | 47458.29
PRC 3352315PE1901 | 2022-11-07 | Inv. 7365.55923400 |  | 52020.79 | 1605.42 | 6167.92 | 45852.87
PRC 3352315PF1901 | 2022-12-02 | Inv. 7365.56923400 |  | 52020.79 | 3379.98 | 9547.9 | 42472.89
PRC 3352315PG1901 | 2023-01-04 | Inv. 7365.57923400 |  | 52020.79 | 2962.56 | 12510.46 | 39510.33
PRC 3352315PH1901 | 2023-04-06 | Inv. 7365.58923400 |  | 52020.79 | 4370.41 | 16880.87 | 35139.92
PRC 3352315PI1901 | 2023-05-08 | Inv. 7365.41 |  | 52020.79 | 6652.67 | 23533.54 | 28487.25
PO 33523151901 | 2023-06-09 | CO #1 | 800 | 52820.79 |  | 23533.54 | 29287.25
PRC 3352315PJ1901 | 2023-06-12 | Inv. 7365.42 |  | 52820.79 | 7002.13 | 30535.67 | 22285.12
PRC 3352315PK1901 | 2023-07-06 | Inv. 7365.43 CA |  | 52820.79 | 6441.24 | 36976.91 | 15843.88 | FY23
PO 33524151901 | 2023-08-03 | Roll to FY24 | 0 | 52820.79 |  | 36976.91 | 15843.88
PRC 3352415PL1901 | 2023-08-07 | Inv. 7365.44 |  | 52820.79 | 9476.24 | 46453.15 | 6367.64
PRC 3352415PM1901 | 2023-09-12 | Inv. 7365.45 CA FINAL | -2276.01 | 50544.78 | 4091.63 | 50544.78 | 0
|  |  |  | 50544.78 |  | 50544.78 | 0
|  | Totals: | 50544.78 |  | 50544.78 |  | 0 | FINAL
|  | CM Services | 48944.78 |  | 48944.78 |  | 0
|  | Reimbursables | 800 |  | 800 |  | 0
|  | CO #1 | 800 |  | 800 |  | 0
|  | Total: | 50544.78 |  | 50544.78 |  | 0

## #9234.00 MTS Contracting
DOC NCF A, B, C, D, E, H, K, L, J Pre-Cast Joint Repairs
Project # 9234.00
Program code 923400 |  |  | Major Program 4B01
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM22-9255 |  |  | 923400-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522153901 | 2022-06-01 | PO Procore | 342525 | 342525 |  |  | 342525 |  | FY22
PO 33523153901 | 2022-08-08 | Rolled to FY23 | 0 | 342525 |  | 0 | 342525
PRC 3352315PA3901 | 2023-01-17 | Inv. 22-4293A |  | 342525 | 73261.15 | 73261.15 | 269263.85 | 3855.85
PRC 3352315PB3901 | 2023-04-28 | Inv. 22-4293B |  | 342525 | 48287.55 | 121548.7 | 220976.3 | 6397.3
PO 33523153901 | 2023-05-31 | CO #1 | 2200 | 344725 |  | 121548.7 | 223176.3
PRC 3352315PC3901 | 2023-06-09 | Inv. 22-4293C |  | 344725 | 74978.75 | 196527.45 | 148197.55 | 10343.55
PO 33523153901 | 2023-06-29 | CO #2 | -125 | 344600 |  | 196527.45 | 148072.55
PRC 3352315PD3901 | 2023-06-30 | Inv. 22-4293D |  | 344600 | 83512.6 | 280040.05 | 64559.95 | 14738.95 | FY23
PO 33524153901 | 2023-08-03 | Roll to FY24 | 0 | 344600 |  | 280040.05 | 64559.95
PO 33524153901 | 2023-08-04 | CO #3 | -5000 | 339600 |  | 280040.05 | 59559.95
PRC 3352415PE3901 | 2023-08-31 | Inv. 22-4293E |  | 339600 | 42579.95 | 322620 | 16980 | 16980
PRC 3352415PF3901 | 2023-09-11 | Inv. 22-4293Retainage |  | 339600 | 16980 | 339600 | 0
|  |  |  | 339600 |  | 339600 | 0
|  | Totals: | 339600 |  | 339600 |  | 0 | FINAL

## RECAP #9235.00
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
| Program code 923500 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 481175.96
C | Samuels Group |  | 9263.05 | 9263.05 | 0
C | PM TIME |  | 24596.61 | 24596.61 | 0
C | Misc. |  | 1027.45 | 1027.45 | 0
C | Shive Hattery |  | 32400 | 32400 | 0
C | Samuels Group (2) |  | 41277.75 | 41277.75 | 0
C | Bi-State Masonry |  | 369028 | 369028 | 0
C | Controlled Asbestos |  | 3583.1 | 3583.1 | 0
| Total Project Cost | 481175.96 | 481175.96 | 481175.96 | 0 | 0
Closed 07/17/23

## #9235.00 Samuels Group
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  | Major Program 4E10
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | Samuels9112015
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522272503 | 2021-09-29 | PO Procore | 9361.63 | 9361.63 |  |  | 9361.63
PRC 3352227PA2503 | 2021-11-05 | Inv. 7366.01923500 |  | 9361.63 | 687.35 | 687.35 | 8674.28
PRC 3352227PB2503 | 2021-12-09 | Inv. 7366.02923500 |  | 9361.63 | 1451.39 | 2138.74 | 7222.89
PRC 3352227PC2503 | 2022-01-04 | Inv. 7366.03923500 |  | 9361.63 | 876.78 | 3015.52 | 6346.11
PRC 3352227PD2503 | 2022-02-08 | Inv. 7366.04923500 |  | 9361.63 | 597.19 | 3612.71 | 5748.92
PRC 3352227PE2503 | 2022-03-09 | Inv. 7366.05923500 |  | 9361.63 | 746.88 | 4359.59 | 5002.04
PRC 3352227PF2503 | 2022-04-17 | Inv. 7366.06923500 |  | 9361.63 | 2370.54 | 6730.13 | 2631.5
PRC 3352227PG2503 | 2022-05-05 | Inv. 7366.07923500 |  | 9361.63 | 1840.15 | 8570.28 | 791.35
PRC 3352227PH2503 | 2022-05-31 | Inv. 7366.08923500 Final | -98.58 | 9263.05 | 692.77 | 9263.05 | -1.89e-12
|  |  |  | 9263.05 |  | 9263.05 | -1.89e-12
|  |  |  | 9263.05 |  | 9263.05 | -1.89e-12
|  |  |  | 9263.05 |  | 9263.05 | -1.89e-12
|  |  |  | 9263.05 |  | 9263.05 | -1.89e-12
|  | Totals: | 9263.05 |  | 9263.05 |  | 0
|  | CM Services | 9211.57 |  | 9211.57 |  | 0
|  | Reimbursables | 51.48 |  | 51.48 |  | 0
|  | Total: | 9263.05 |  | 9263.05 |  | 0

## #9235.00 PM TIME
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 906T
Project Manager - Brad T
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18155.94 | 18155.94 |  |  | 18155.94
IET DAS202203115300001 | 2021-10-07 |  | PM-Aug. 20-Sept. 30, 2021 |  | 18155.94 | 200 | 200 | 17955.94
IET DAS202204115300001 | 2021-11-05 |  | PM-Oct 1-Oct 29, 2021 |  | 18155.94 | 275 | 475 | 17680.94
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 18155.94 | 125 | 600 | 17555.94
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 18155.94 | 650 | 1250 | 16905.94
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 18155.94 | 525 | 1775 | 16380.94
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 18155.94 | 400 | 2175 | 15980.94
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 18155.94 | 350 | 2525 | 15630.94
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 18155.94 | 550 | 3075 | 15080.94
IET DAS202201115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 18155.94 | 900 | 3975 | 14180.94
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 18155.94 | 850 | 4825 | 13330.94
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 18155.94 | 575 | 5400 | 12755.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 18155.94 | -575 | 4825 | 13330.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 18155.94 | 632.5 | 5457.5 | 12698.44
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 18155.94 | 770 | 6227.5 | 11928.44
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 18155.94 | 1705 | 7932.5 | 10223.44
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 18155.94 | 1567.5 | 9500 | 8655.94
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 18155.94 | 632.5 | 10132.5 | 8023.44
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 399.59 | 18555.53 | 399.59 | 10532.09 | 8023.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 794.06 | 19349.59 | 794.06 | 11326.15 | 8023.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 1538.84 | 20888.43 | 1538.84 | 12864.99 | 8023.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1774.6 | 22663.03 | 1774.6 | 14639.59 | 8023.44
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 560.75 | 23223.78 | 560.75 | 15200.34 | 8023.44
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 23223.78 | 793.36 | 15993.7 | 7230.08
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 23223.78 | 49.64 | 16043.34 | 7180.44
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 23223.78 | 435.15 | 16478.49 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 171.74 | 23395.52 | 171.74 | 16650.23 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 221.42 | 23616.94 | 221.42 | 16871.65 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 518.02 | 24134.96 | 518.02 | 17389.67 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 215.92 | 24350.88 | 215.92 | 17605.59 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 127.04 | 24477.92 | 127.04 | 17732.63 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 118.69 | 24596.61 | 118.69 | 17851.32 | 6745.29
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 24596.61 | 26.74 | 17878.06 | 6718.55
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 24596.61 | 162.17 | 18040.23 | 6556.38
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 24596.61 | 88.15 | 18128.38 | 6468.23
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 24596.61 | 387.7 | 18516.08 | 6080.53
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 24596.61 | 306.85 | 18822.93 | 5773.68
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 24596.61 | 1801.5 | 20624.43 | 3972.18
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 24596.61 | 333.68 | 20958.11 | 3638.5
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 24596.61 | 2339.7 | 23297.81 | 1298.8
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 24596.61 | 146.5 | 23444.31 | 1152.3
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 24596.61 | 1152.3 | 24596.61 | 0
[5 empty] | 24596.61 |  | 24596.61 | 0
[5 empty] | 24596.61 |  | 24596.61 | 0
[5 empty] | 24596.61 |  | 24596.61 | 0
[5 empty] | 24596.61 |  | 24596.61 | 0
[5 empty] | 24596.61 |  | 24596.61 | 0
|  |  | Totals: | 24596.61 |  | 24596.61 |  | 0
Note on E9: Wray, Ronda [DAS]: PM Time Set up on New Projects $Ronda Tonyan, Bradley 8:51 AM (1 hour ago) to me, Scott Finance, Can you please set up the following PM time budgets on the following projects below: - MM22 - 9234.00 - DOC NCF A, B, C, D, E, H, K, L, J Pre-cast Joint Repairs - $16,000 - MM22 - 9235.00 - DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing - $8,000 Thank you, Brad Tonyan, Owner Representative DAS PM Time Adjustments $Joni Tonyan, Brad 2:57 PM (25 minutes ago) to me, Jennifer, Brad, Scott Finance, Please see the following projects below that need PM Time budget adjustments. 9172.00 - DA21 - Increase PM time budget by $10,000 9235.00 - MM22 - Please set up PM time budget at $4,000 Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Billables and PM Time Adjustments $Joni Tonyan, Brad Feb 23, 2023, 4:15 PM (17 hours ago) to me, Scott, Brad Finance, Please make the following changes with Josh moving on and Doug retiring as some of the projects are not on my billables sheet. While I am on it I have made some PM time adjustments to cover some of the billing changes or construction oversight. - DA20 - 9118.00 - Raise PM time budget $3,000 - MM21 - 9204.00 - Raise PM time budget $2,000 - MM22 - 9235.00 - Raise PM time budget $5,000 - DA22 - 9239.00 - Raise PM time budget $2,500 - DA22 - 9242.00 - Raise PM time budget $15,000 - DA22 - 9280.00 - Add this project to my billables as I took from Doug - DA22 - 9281.00 - Add this project to my billables as I took from Doug Thank you and I think that is all for now. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed.

## #9235.00 Misc
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522081900 | 2022-03-21 | 9500 | CNST | ATC Group V# (00002134218) | Inv. 2413298-Final | 807.5 | 807.5
PRC 33522153903 | 2022-06-01 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV021009 | 219.95 | 1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
1027.45
|  |  |  | Totals: |  | 1027.45

## #9235.00 Shive Hattery
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  | Major Program 4E10
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 923500-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522351902 | 2021-12-15 | PO Procore | 32400 | 32400 |  |  | 32400
PRC 3352235PA1902 | 2022-01-31 | Inv. 4217200-1 |  | 32400 | 3534 | 3534 | 28866
PRC 3352235PB1902 | 2022-02-28 | Inv. 4217200-2 |  | 32400 | 9986 | 13520 | 18880
PRC 3352235PC1902 | 2022-04-05 | Inv. 4217200-3 |  | 32400 | 9260 | 22780 | 9620
PRC 3352235PD1902 | 2022-05-02 | Inv. 4217200-4 |  | 32400 | 320 | 23100 | 9300
PRC 3352235PE1902 | 2022-05-27 | Inv. 4217200-5 |  | 32400 | 1300 | 24400 | 8000
PRC 3352235PF1902 | 2022-07-02 | Inv. 4217200-6 |  | 32400 | 800 | 25200 | 7200 | FY22
PO 33523351902 | 2022-08-08 | Rolled to FY23 | 0 | 32400 |  | 25200 | 7200
PRC 3352335PG1902 | 2022-08-12 | Inv. 4217200-7 |  | 32400 | 400 | 25600 | 6800
PRC 3352335PH1902 | 2022-09-29 | Inv. 4217200-8 |  | 32400 | 1200 | 26800 | 5600
PRC 3352335PI1902 | 2023-05-30 | Inv. 4217200-9 |  | 32400 | 4800 | 31600 | 800
PRC 3352335PJ1902 | 2023-06-28 | Inv. 4217200-10 FINAL |  | 32400 | 800 | 32400 | 0
|  |  |  | 32400 |  | 32400 | 0
|  |  |  | 32400 |  | 32400 | 0
|  |  |  | 32400 |  | 32400 | 0
|  |  |  | 32400 |  | 32400 | 0
|  |  |  | 32400 |  | 32400 | 0
|  | Totals: | 32400 |  | 32400 |  | 0 | FINAL
|  | Schematic Design Docs | 11400 |  | 11400 |  | 0
|  | Design Development Docs | 5300 |  | 5300 |  | 0
|  | Construction Design | 6400 |  | 6400 |  | 0
|  | Bidding Assistance | 1300 |  | 1300 |  | 0
|  | Construction Phase | 8000 |  | 8000 |  | 0
|  | Total: | 32400 |  | 32400 |  | 0

## #9235.00 Samuels Group (2)
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  | Major Program 4E10
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522151800 | 2022-05-31 | PO Procore | 41299.36 | 41299.36 |  |  | 41299.36
PO 3352215PA1800 | 2022-06-30 | Inv. 7366.51923500 |  | 41299.36 | 1834.73 | 1834.73 | 39464.63 | FY22
PO 33523151800 | 2022-08-08 | Rolled to FY23 | 0 | 41299.36 |  | 1834.73 | 39464.63
PRC 3352315PB1800 | 2022-08-01 | Inv. 7366.52923500 |  | 41299.36 | 811.83 | 2646.56 | 38652.8
PRC 3352315PC1800 | 2022-09-08 | Inv. 7366.53923500 |  | 41299.36 | 719.83 | 3366.39 | 37932.97
PRC 3352315PD1800 | 2022-09-30 | Inv. 7366.54923500 |  | 41299.36 | 7124.45 | 10490.84 | 30808.52
PRC 3352315PE1800 | 2022-11-07 | Inv. 7366.55923500 |  | 41299.36 | 7858.61 | 18349.45 | 22949.91
PRC 3352315PF1800 | 2022-12-02 | Inv. 7366.56923500 |  | 41299.36 | 3701.54 | 22050.99 | 19248.37
PRC 3352315PG1800 | 2023-01-04 | Inv. 7366.57923500 |  | 41299.36 | 790.18 | 22841.17 | 18458.19
PRC 3352315PH1800 | 2023-04-06 | Inv. 7366.58923500 |  | 41299.36 | 1215.04 | 24056.21 | 17243.15
PRC 3352315PI1800 | 2023-05-08 | Inv. 7366.59923500 |  | 41299.36 | 6177.93 | 30234.14 | 11065.22
PRC 3352315PJ1800 | 2023-06-01 | Inv. 7366.60923500 |  | 41299.36 | 4971.09 | 35205.23 | 6094.13
PRC 3352315PK1800 | 2023-07-06 | Inv. 7366.99 FINAL | -21.61 | 41277.75 | 6072.52 | 41277.75 | -1.0331e-11
|  | Totals: | 41277.75 |  | 41277.75 |  | 0 | FINAL
|  | CM Services | 40677.75 |  | 40677.75 |  | 0
|  | Reimbursables | 600 |  | 600 |  | 0
|  | Total: | 41277.75 |  | 41277.75 |  | 0

## #9235.00 Bi-State Masonry
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  | Major Program 4E10
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM22-9255 |  |  | 923500-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522153902 | 2022-06-01 | PO Procore | 361350 | 361350 |  |  | 361350 |  | FY22
PO 33523153902 | 2022-08-08 | Rolled to FY23 | 0 | 361350 |  | 0 | 361350
PRC 3352315PA3902 | 2022-09-30 | Inv. 9235.00-01 |  | 361350 | 69682.83 | 69682.83 | 291667.17 | 3667.52
PRC 3352315PB3902 | 2022-10-28 | Inv. 2-5432 |  | 361350 | 161697.18 | 231380.01 | 129969.99 | 12177.92
PO 33523153902 | 2022-11-10 | CO 1(No Cost CO) | 0 | 361350 |  | 231380.01 | 129969.99
PRC 3352315PC3902 | 2022-12-01 | Inv. 5486 |  | 361350 | 40468.02 | 271848.03 | 89501.97 | 14307.82
PO 33523153902 | 2023-01-23 | CO 2 | 14028 | 375378 |  | 271848.03 | 103529.97
PRC 3352315PD3902 | 2023-05-08 | Inv. 5550 |  | 375378 | 63895.7 | 335743.73 | 39634.27 | 17670.77
PO 33523153902 | 2023-05-18 | CO 3 | -6350 | 369028 |  | 335743.73 | 33284.27
PRC 3352315PE3902 | 2023-06-21 | Inv. 5615 |  | 369028 | 14832.82 | 350576.55 | 18451.45 | 18451.45
PRC 3352315PF3902 | 2023-06-28 | Inv. 5615-Retainage |  | 369028 | 18451.45 | 369028 | 0
|  |  |  | 369028 |  | 369028 | 0
|  |  |  | 369028 |  | 369028 | 0
|  | Totals: | 369028 |  | 369028 |  | 0 | FINAL

## #9235.00 Controlled Asbestos
DOC NCF CRC Dorms 1 & 2 and RVP 3, 4, and 5 Tuckpointing
Project # 9235.00
Program code 923500 |  |  | Major Program 4E10
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | MA 005 21060
Project Manager - Brad T |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523244900 | 2022-09-01 | DO Procore | 10410.5 | 10410.5 |  |  | 10410.5
PRC 3352324PA4900 | 2023-06-20 | Inv. 10583-IN- Final | -6827.4 | 3583.1 | 3583.1 | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  |  |  | 3583.1 |  | 3583.1 | 0
|  | Totals: | 3583.1 |  | 3583.1 |  | 0 | Final
|  | Line 1 Asbestos abatement Services 142.5hrs@$58/hr | 2610 |  | 2610 |  | 0
|  | Line 7 Air Monitoring, Landfill fees, DNR fee, Lift rental | 791.2 |  | 791.2 |  | 0
|  | Line 10 Waste Disposal | 6.4 |  | 6.4 |  | 0
|  | Line12 Travel Expenses 90 x 15 trips @ 0.39/mile | 175.5 |  | 175.5 |  | 0
|  | Total: | 3583.1 |  | 3583.1 |  | 0

## RECAP #9236.00
DOC NCCF Food Warehouse Walk-in Freezer Replacement
Project # 9236.00
| Program code 923600 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
C | Story Construction |  | 0 | 0 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 0 | 0 | 0
| Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 03/04/2022
Moved to MM20

## #9236.00 Story Construction
DOC NCCF Food Warehouse Walk-in Freezer Replacement
Project # 9236.00
Program code 923600 |  |  | Major Program 4B01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-Story9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522277800 | 2021-10-01 | PO Procore | 9410.5 | 9410.5 |  |  | 9410.5
PRC 3352227PA7800 | 2021-12-21 | Inv. 32899 |  | 9410.5 | 1262.6 | 1262.6 | 8147.9
PRC 3352227PB7800 | 2022-01-22 | Inv. 32942 |  | 9410.5 | 1596.52 | 2859.12 | 6551.38
PRC 3352227PC7800 | 2022-02-18 | Inv. 32984 |  | 9410.5 | 716.54 | 3575.66 | 5834.84
PO 33522277800 | 2022-03-04 | Moved to MM20 | -5834.84 | 3575.66 |  | 3575.66 | 0
CDE 33522063901 | 2022-03-04 | Moving expenses to MM20 | -3575.66 | 0 | -3575.66 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 3575.66 |  | 3575.66 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 3575.66 |  | 3575.66 |  | 0

## #9236.00 PM TIME
DOC NCCF Food Warehouse Walk-in Freezer Replacement
Project # 9236.00
Program code 923600 |  |  | Major Program 4B01
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 2500 | 2500 |  |  | 2500
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 2500 | 525 | 525 | 1975
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 2500 | 250 | 775 | 1725
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 2500 | 250 | 1025 | 1475
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 2500 | 425 | 1450 | 1050
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 2500 | 475 | 1925 | 575
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb28, 2022 |  | 2500 | 575 | 2500 | 0
CDE 33522073901 | 2022-03-14 | Moving expenses to MM20 | -1925 | 575 | -1925 | 575 | 0
CDE 33522075900 | 2022-03-15 | Move PM Time to MM20 | -575 | 0 | -575 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0
Note on D9: Wray, Ronda [DAS]: PM TIME - James Trower $Ronda Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Finance - Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative ames Trower - PM Time $Joni Trower, James Feb 15, 2022, 11:06 AM (23 hours ago) to me Finance - Please see the below items: 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement: Add $2,500 to PM Time 9275.00 - DPS P12 Window Replacement: Setup $6,000 in PM Time 9276.00 - DPS P12 Driveway Repairs: Setup $6,000 in PM Time Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Office: 515-725-4150 Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9236.00 Misc
DOC NCCF Food Warehouse Walk-in Freezer Replacement
Project # 9236.00
Program code 923600 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9236.00 Shive Hattery
DOC NCCF Food Warehouse Walk-in Freezer Replacement
Project # 9236.00
Program code 923600 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 922900-01
Project Manager - James T |  |  | Activity Code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522361900 | 2021-12-27 | PO Procore | 26902 | 26902 |  |  | 26902
PRC 3352236PA1900 | 2022-02-01 | Inv. 4217300-1 |  | 26902 | 3768.6 | 3768.6 | 23133.4
PRC 3352236PB1900 | 2022-03-03 | Inv. 4217300-2 |  | 26902 | 9827.4 | 13596 | 13306
PO 33522361900 | 2022-03-04 | Moving to MM20 | -13306 | 13596 |  | 13596 | 0
CDE 33522063902 | 2022-03-04 | Moving expense to MM20 | -13596 | 0 | -13596 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0
|  | Design Development Phase | 6281 |  | 6281 |  | 0
|  | Construction Documents Phase | 7315 |  | 7315 |  | 0
|  | Bidding Phase | 0 |  |  |  | 0
|  | Construction Phase | 0 |  |  |  | 0
|  | Total: | 13596 |  | 13596 |  | 0

## RECAP #9237.00
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
| Program code 923700 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 255120.34
C | DCI Group |  | 4527.19 | 4527.19 | 0
C | PM TIME |  | 8403.35 | 8403.35 | 0
C | Misc. |  | 1991.68 | 1991.68 | 0
C | MA Architecture |  | 14240 | 14240 | 0
C | Seedorff Masonry |  | 201383.94 | 201383.94 | 0
C | DCI Group |  | 24574.18 | 24574.18 | 0
| Total Project Cost | 255120.34 | 255120.34 | 255120.34 | 0 | 0
Closed 01/17/2023

## #9237.00 DCI Group
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP0215335062-CM Firm-DCI 9112015
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522293800 | 2021-10-20 | PO Procore | 4546.08 | 4546.08 |  |  | 4546.08
PRC 3352229PA3800 | 2021-11-23 | Inv. 21-040 PC-01 |  | 4546.08 | 622.38 | 622.38 | 3923.7
PRC 3352229PB3800 | 2021-12-20 | Inv. 21-040 PC-02 |  | 4546.08 | 877.3 | 1499.68 | 3046.4
PRC 3352229PC3800 | 2022-01-12 | Inv. 21-040 PC-03 |  | 4546.08 | 1198.22 | 2697.9 | 1848.18
PRC 3352229PD3800 | 2022-02-24 | Inv. 21-040 PC-04 |  | 4546.08 | 995.82 | 3693.72 | 852.36
PRC 3352229PE3800 | 2022-03-28 | Inv. 21-040 PC-05 |  | 4546.08 | 603.99 | 4297.71 | 248.37
PRC 3352229PF3800 | 2022-05-11 | Inv. 21-040 PC-06 FINAL | -18.89 | 4527.19 | 229.48 | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  |  |  | 4527.19 |  | 4527.19 | -4.4054e-13
|  | Totals: | 4527.19 |  | 4527.19 |  | 0

## #9237.00 PM TIME
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  | Major Program 4E19
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx |  |  | eDAS 906V
Project Manager - James T
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 6500 | 6500 |  |  | 6500
IET DAS202203115300001 | 2021-10-07 | PM-Aug. 20-Sept. 30, 2021 |  | 6500 | 450 | 450 | 6050
IET DAS202204115300001 | 2021-11-05 | PM-Oct 1-Oct 29, 2021 |  | 6500 | 600 | 1050 | 5450
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 6500 | 425 | 1475 | 5025
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 6500 | 625 | 2100 | 4400
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 6500 | 50 | 2150 | 4350
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 6500 | 550 | 2700 | 3800
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 6500 | 400 | 3100 | 3400
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 6500 | 225 | 3325 | 3175
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 6500 | 200 | 3525 | 2975
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 6500 | 500 | 4025 | 2475
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 6500 | 600 | 4625 | 1875
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 6500 | -600 | 4025 | 2475
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 6500 | 660 | 4685 | 1815
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 6500 | 742.5 | 5427.5 | 1072.5
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 6500 | 577.5 | 6005 | 495
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 6500 | 275 | 6280 | 220
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30,2022 |  | 6500 | 220 | 6500 | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 591.75 | 7091.75 | 591.75 | 7091.75 | 0
IET DAS202305115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 631.35 | 7723.1 | 631.35 | 7723.1 | 0
IET DAS202305115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 310.8 | 8033.9 | 310.8 | 8033.9 | 0
IET DAS202305115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 200.8 | 8234.7 | 200.8 | 8234.7 | 0
IET DAS202305115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 168.65 | 8403.35 | 168.65 | 8403.35 | 0
|  |  |  | 8403.35 |  | 8403.35 | 0
|  |  |  | 8403.35 |  | 8403.35 | 0
|  | Totals: | 8403.35 |  | 8403.35 |  | 0
Note on D9: Wray, Ronda [DAS]: PM TIME - James Trower $Ronda Trower, James Sep 13, 2021, 9:13 PM (13 hours ago) to me, Josh Finance - Please set up PM Time for the below projects as indicated (Josh Herman and I will both be working on project 9224.00): 9224.00 - DOC MPCF Elevator B, C and D Replacements (MM21) PM Time (James Trower): $15,000 PM Time (Josh Herman): $2,500 9225.00 - DCA CLE Clermont Museum Masonry Repairs (MM20) PM Time (James Trower): $7,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22) PM Time (James Trower): $7,000 9228.00 - DCA PGR Plum Grove Roof Replacement (MM22) PM Time (James Trower): $4,000 9229.00 - DOC NCCF R&D Floor Replacement (MM22) PM Time (James Trower): $3,500 9231.00 - DAS CC Jessie Parker Water Infiltration Repair (MM22) PM Time (James Trower): $4,500 9232.00 - DCA TMVC Siding Replacement (MM22) PM Time (James Trower): $5,000 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement (MM22) PM Time (James Trower): $3,500 9237.00 - DAS CC Hoover East Side Paver Repairs (MM22) PM Time (James Trower): $4,000 Thank you, James Trower, AIA, LEED AP Owner’s Representative PM Time - Increase Request $Selma Trower, James Fri, Jun 17, 2:47 PM (3 days ago) to me Finance - Please increase PM Time for the following projects: 9232.00 - DCA TMVC Toolesboro Mounds Visitor Center Siding Replacement: Increase PM Time by $3,000 9237.00 - DAS CC Hoover East Side Paver Repairs: Increase PM Time by $4,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov PM Time Increases $Joni Trower, James Dec 22, 2022, 1:00 PM (6 days ago) to me Finance: Please see the below items: 9197.00 - 5th Judicial DSM 5JD FT DM 70 South Restroom Remodel Increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement Increase PM Time by $2,000 9237.00 - DAS CC Hoover East Side Paver Repairs Increase PM Time by $1,100 9264.00 - DPS P10 Front Entrance Repair Increase PM Time by $1,100 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Project 9237.00 - Close $Joni Trower, James Tue, Jan 17, 9:11 PM (9 hours ago) to me Finance - Reduce PM Time by $2,600 and return to MM22 pool fund. Please close the project and return all remaining funds to the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov

## #9237.00 Misc
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522096900 | 2022-04-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV019225 | 102.61 | 102.61
PRC 33522153905 | 2022-06-02 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV021000 | 74.95 | 177.56
GAX 33523272900 | 2022-09-27 | 9500 | BRUM | Neumann Brothers V#(00002106354) | Inv. 54660 | 1673.28 | 1850.84
IET DAS202303115300001 | 2022-10-07 | 2507 |  | #207133863 Moving Parking Signs | Inv. DAS2023031153 | 140.84 | 1991.68
1991.68
1991.68
1991.68
1991.68
1991.68
1991.68
1991.68
1991.68
|  |  |  | Totals: |  | 1991.68

## #9237.00 MA Architecture
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  | Major Program 4E19
MA Architecture |  |  | Vendor: 00003166868
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B: TSB
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522313801 | 2021-11-09 | PO Procore | 14240 | 14240 |  |  | 14240
PRC 3352231PA3801 | 2022-01-20 | Inv. 9237.00-1 |  | 14240 | 1392 | 1392 | 12848
PRC 3352231PB3801 | 2022-02-24 | Inv. 200050 |  | 14240 | 7424 | 8816 | 5424
PRC 3352231PC3801 | 2022-05-17 | Inv. 9237.00-3 |  | 14240 | 960 | 9776 | 4464
PRC 3352231PD3801 | 2022-07-18 | Inv. 2044 |  | 14240 | 744 | 10520 | 3720 | FY22
PO 33523313801 | 2022-08-08 | Rolled to FY23 | 0 | 14240 |  | 10520 | 3720
PRC 3352331PE3801 | 2022-09-08 | Inv. 1031 |  | 14240 | 3472 | 13992 | 248
PRC 3352331PF3801 | 2022-10-24 | Inv. 9237.00-6-Final |  | 14240 | 248 | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  |  |  | 14240 |  | 14240 | 0
|  | Totals: | 14240 |  | 14240 |  | 0
|  | Construction Documents | 9280 |  | 9280 |  | 0
|  | Bidding & Construction Administration | 4960 |  | 4960 |  | 0
|  | Total: | 14240 |  | 14240 |  | 0

## #9237.00 Seedorff Masonry
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  | Major Program 4E19
Seedorff Masonry |  |  | Vendor: 00002108955
Acct. Codes-0017-335-MM22-9255 |  |  | RFB923700-02
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522171800 | 2022-06-17 | PO Procore | 198880 | 198880 |  |  | 198880 | FY22
PO 33523171800 | 2022-08-08 | Rolled to FY23 | 0 | 198880 |  | 0 | 198880
PRC 3352317PA1800 | 2022-08-26 | Inv. 22042-1 |  | 198880 | 14924 | 14924 | 183956
PO 33523171800 | 2022-08-31 | CO 1 | 2503.94 | 201383.94 |  | 14924 | 186459.94
PRC 3352317PB1800 | 2022-09-11 | Inv. 22042-2 |  | 201383.94 | 184469.94 | 199393.94 | 1990
PRC 3352317PC1800 | 2022-10-20 | Inv. 22042-7 |  | 201383.94 | 1990 | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  |  |  | 201383.94 |  | 201383.94 | 0
|  | Totals: | 201383.94 |  | 201383.94 |  | 0

## #9237.00 DCI Group CA
DAS CC Hoover East Side Paver Repairs
Project # 9237.00
Program code 923700 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523202901 | 2022-07-21 | PO Procore | 26553.56 | 26553.56 |  |  | 26553.56
PRC 3352320PA2901 | 2022-09-27 | Inv. 21-040 CA-01 |  | 26553.56 | 20268.4 | 20268.4 | 6285.16
PRC 3352320PB2901 | 2022-11-07 | Inv. 21-040 CA-02 |  | 26553.56 | 3799.36 | 24067.76 | 2485.8
PRC 3352320PC2901 | 2022-11-14 | Inv. 21-040 CA-03-FINAL | -1979.38 | 24574.18 | 506.42 | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  |  |  | 24574.18 |  | 24574.18 | 0
|  | Totals: | 24574.18 |  | 24574.18 |  | 0 | FINAL
|  | Construction Management | 24367.4 |  | 24367.4 |  | 0
|  | Reimbursables | 206.78 |  | 206.78 |  | 0
|  | Total: | 24574.18 |  | 24574.18 |  | 0

## RECAP #9244.00
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
| Program code 924400 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1077238.62
| Additional Funds Recv'd | 0
C | McGough Construction |  | 13857.2 | 13857.2 | 0
| PM TIME |  | 35172.62 | 33248.93 | 1923.69
| Misc. |  | 4532.5 | 4532.5 | 0
C | SystemWorks |  | 6467.5 | 6467.5 | 0
| Terracon Consultants |  | 67856 | 66551 | 1305
| McGough Construction(2) |  | 145364.16 | 107976.11 | 37388.05
C | Bi-State Masonry |  | 112334 | 112334 | 0
C | Hopkins Roofing |  | 666561.75 | 666561.75 | 0
| Hopkins Roofing (2) |  | 10370.71 | 9753.65 | 617.06
| Total Project Cost | 1077238.62 | 1062516.44 | 1021282.64 | 41233.8 | 14722.18

## #9244.00 Funds Rec'd
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
Funds Received
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Terracon refund | IET 3359244270 | 2023-09-28 | 2000 | 2000
|  |  | Terracon refund | IET 3359244270A | 2023-10-12 | -200 | -200
|  |  | Terracon refund | IET 3359244270B | 2023-10-12 | 400 | 400
|  |  | Terracon refund allocated to vendor tab | PO 33524126900 | 2024-01-26 | -2200 | -2200
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9244.00 McGough Construction
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP 1821335228
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522005900 | 2022-01-03 | PO Procore | 13857.2 | 13857.2 |  |  | 13857.2
PRC 3352200PA5900 | 2022-04-11 | Inv. 9244.00-01 |  | 13857.2 | 1312 | 1312 | 12545.2
PRC 3352200PB5900 | 2022-05-27 | Inv. 9244.00-001.2 |  | 13857.2 | 1414.53 | 2726.53 | 11130.67
PRC 3352200PC5900 | 2022-06-13 | Inv. 9244.00-001.3 |  | 13857.2 | 1249.5 | 3976.03 | 9881.17
PRC 3352200PD5900 | 2022-07-11 | Inv. 9244.00-001.4 |  | 13857.2 | 734.92 | 4710.95 | 9146.25 | FY22
PO 33523005900 | 2022-08-10 | Rolled to FY23 | 0 | 13857.2 |  | 4710.95 | 9146.25
PRC 3352300PE5900 | 2022-08-12 | Inv. 9244.001.5 |  | 13857.2 | 877 | 5587.95 | 8269.25
PRC 3352300PF5900 | 2022-09-09 | Inv. 9244.00-001.6 |  | 13857.2 | 6241 | 11828.95 | 2028.25
PO 33523005900 | 2022-09-12 | CO 1 | 0 | 13857.2 |  | 11828.95 | 2028.25
PRC 3352300PG5900 | 2022-10-07 | Inv. 9244.00-001.7 FINAL |  | 13857.2 | 2028.25 | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  |  |  | 13857.2 |  | 13857.2 | 0
|  | Totals: | 13857.2 |  | 13857.2 |  | 0
|  | CM Services | 13793.32 |  | 13793.32 |  | 0
|  | Reimbursables | 63.88 |  | 63.88 |  | 0
|  | Total: | 13857.2 |  | 13857.2 |  | 0

## #9244.00 PM TIME
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1Z8
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 31090 | 31090 |  |  | 31090
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 31090 | 75 | 75 | 31015
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 31090 | 475 | 550 | 30540
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 31090 | 225 | 775 | 30315
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 31090 | 150 | 925 | 30165
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 31090 | 675 | 1600 | 29490
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 31090 | 650 | 2250 | 28840
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 31090 | 525 | 2775 | 28315
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 31090 | 525 | 3300 | 27790
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 31090 | 400 | 3700 | 27390
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 31090 | -400 | 3300 | 27790
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 31090 | 440 | 3740 | 27350
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 31090 | 1210 | 4950 | 26140
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 31090 | 715 | 5665 | 25425
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 31090 | 797.5 | 6462.5 | 24627.5
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 31090 | 632.5 | 7095 | 23995
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 335.1 | 31425.1 | 335.1 | 7430.1 | 23995
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1117.1 | 32542.2 | 1117.1 | 8547.2 | 23995
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 446.3 | 32988.5 | 446.3 | 8993.5 | 23995
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 626.9 | 33615.4 | 626.9 | 9620.4 | 23995
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 632.9 | 34248.3 | 632.9 | 10253.3 | 23995
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 34248.3 | 440.81 | 10694.11 | 23554.19
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 34248.3 | 36.42 | 10730.53 | 23517.77
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 34248.3 | 319.21 | 11049.74 | 23198.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 101.77 | 34350.07 | 101.77 | 11151.51 | 23198.56
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 344.42 | 34694.49 | 344.42 | 11495.93 | 23198.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 185.45 | 34879.94 | 185.45 | 11681.38 | 23198.56
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 92.02 | 34971.96 | 92.02 | 11773.4 | 23198.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 134.72 | 35106.68 | 134.72 | 11908.12 | 23198.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 65.94 | 35172.62 | 65.94 | 11974.06 | 23198.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 35172.62 | 112.44 | 12086.5 | 23086.12
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 35172.62 | 681.79 | 12768.29 | 22404.33
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 35172.62 | 243.23 | 13011.52 | 22161.1
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 35172.62 | 1069.89 | 14081.41 | 21091.21
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 35172.62 | 186.22 | 14267.63 | 20904.99
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 35172.62 | 1096.2 | 15363.83 | 19808.79
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 35172.62 | 186.42 | 15550.25 | 19622.37
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 35172.62 | 1305.7 | 16855.95 | 18316.67
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 35172.62 | 130.84 | 16986.79 | 18185.83
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 35172.62 | 1086.1 | 18072.89 | 17099.73
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 35172.62 | 149.29 | 18222.18 | 16950.44
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 35172.62 | 950.5 | 19172.68 | 15999.94
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 35172.62 | 143.94 | 19316.62 | 15856
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 35172.62 | 803.4 | 20120.02 | 15052.6
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 35172.62 | 141.24 | 20261.26 | 14911.36
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 35172.62 | 982.3 | 21243.56 | 13929.06
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 35172.62 | 146.82 | 21390.38 | 13782.24
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 35172.62 | 1175.2 | 22565.58 | 12607.04
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 35172.62 | 113.34 | 22678.92 | 12493.7
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 35172.62 | 855.9 | 23534.82 | 11637.8
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 35172.62 | 101.51 | 23636.33 | 11536.29
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 35172.62 | 745.3 | 24381.63 | 10790.99
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 35172.62 | 88.32 | 24469.95 | 10702.67
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 35172.62 | 776.3 | 25246.25 | 9926.37
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 35172.62 | 26.08 | 25272.33 | 9900.29
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 35172.62 | 131.6 | 25403.93 | 9768.69
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 35172.62 | 121.42 | 25525.35 | 9647.27
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 35172.62 | 921.8 | 26447.15 | 8725.47
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 35172.62 | 65.97 | 26513.12 | 8659.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 35172.62 | 587.5 | 27100.62 | 8072
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 35172.62 | 76.63 | 27177.25 | 7995.37
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 35172.62 | 633.2 | 27810.45 | 7362.17
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 35172.62 | 21.44 | 27831.89 | 7340.73
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 35172.62 | 194.4 | 28026.29 | 7146.33
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 35172.62 | 35.2 | 28061.49 | 7111.13
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 35172.62 | 386.9 | 28448.39 | 6724.23
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 35172.62 | 285.07 | 28733.46 | 6439.16
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 35172.62 | 1450.9 | 30184.36 | 4988.26
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 35172.62 | 87.06 | 30271.42 | 4901.2
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 35172.62 | 774.9 | 31046.32 | 4126.3
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 35172.62 | 111.86 | 31158.18 | 4014.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 35172.62 | 747.1 | 31905.28 | 3267.34
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 35172.62 | 56.36 | 31961.64 | 3210.98
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 35172.62 | 374.8 | 32336.44 | 2836.18
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 35172.62 | 27.01 | 32363.45 | 2809.17
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 35172.62 | 272.5 | 32635.95 | 2536.67
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 35172.62 | 42.89 | 32678.84 | 2493.78
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 35172.62 | 459.2 | 33138.04 | 2034.58
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 35172.62 | 20.79 | 33158.83 | 2013.79
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 35172.62 | 90.1 | 33248.93 | 1923.69
[5 empty] | 35172.62 |  | 33248.93 | 1923.69
[5 empty] | 35172.62 |  | 33248.93 | 1923.69
[5 empty] | 35172.62 |  | 33248.93 | 1923.69
|  |  | Totals: | 35172.62 |  | 33248.93 |  | 1923.69
Note on E9: Huggins, Joni [DAS]: Re: PM Time DA23 9277.00 $Joni Kleene, Jennifer 8:14 AM (3 hours ago) to me Sorry, I didn't realize they wouldn't be transferring the funds until after 8/15. Would you please move that time to the MM22 9277.00 project? Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov On Thu, Aug 11, 2022 at 6:48 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good morning Jennifer, There isn't sufficient funds in this project to post $25 PM Time. Please advise Thank you ~Joni PM Time Increases $John Kleene, Jennifer Fri, Apr 7, 3:41 PM (3 days ago) to me, Scott Please increase the PM Time for the following projects: DA21 9207.00, please increase the PM time by $4,675.00 MM22 9244.00, please increase the PM time by $9,350.00 MM22 9277.00, please increase the PM time by $4,675.00 Regards, Jennifer Re: PM Time $Joni Kleene, Jennifer Dec 11, 2023, 5:17 PM (14 hours ago) to me Please increase the PM Time budget for 9289.00 by $3,740.00. Please increase the PM time budget for 9279.30 in DA24 by $56,100.00. Please increase the PM time budget for 9244 in MM22 by $3,740.00. Please increase the PM time budget for 9268.01 in R22M by $2,138.40. Regards, Jennifer PM Time Changes $Joni Kleene, Jennifer 11:59 AM (27 minutes ago) to me, Scott For MM22 9244.00, please increase the PM Time budget by $4,000.00 For MM23 9268.01, please increase the PM Time budget by $8,800.00 For DA22 9216.00, please increase the PM Time budget by $4,000.00 For DA23 9293.00, please increase the PM Time budget by $3,500.00 For DA24 9377.00, please increase the PM Time budget by $4,400.00 Re: November PM Time $Joni Kleene, Jennifer Dec 10, 2024, 5:20 PM (13 hours ago) to Scott, me OK. In that case, please increase the PM Time budgets as follows: MM22 9244.00 Increase by $1,000 MM23 9268.01 Increase by $2,000 Regards, Jennifer PM Time Budget Changes $Joni Kleene, Jennifer 10:13 AM (1 hour ago) to me, Scott Please increase the PM Time Budgets as follows: MM23 9294.01 increase by $3,740.00 DA25 9424.00 increase by $2,000.00 MM22 9244.00 increase by $2,000.00 MM22 9274.00 increase by $600.00 X674 9379.00 increase by $8,800.00 MM24 9391.00 increase by $8,800.00 Regards, Jennifer

## #9244.00 Misc
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522175900 | 2022-06-23 | 9500 | CNST | Terracon V#(00002116512) | Inv. TG92847 | 2500 | 2500
PRC 33523273902 | 2022-09-29 | 9500 | CNST | BeeLine&Blue V#(00002108204) | Inv. INV024190 | 74.95 | 2574.95
PRC 33524289800 | 2023-10-16 | 9500 | CNST | System Works LLC V#(00002144353) | Inv. 11414 - Final | 1417.5 | 3992.45
GAX 33524120914 | 2024-04-29 | 9500 | CNST | CK Fairco V#(00002125989) | Inv. 24042505 | 540.05 | 4532.5
4532.5
4532.5
4532.5
4532.5
4532.5
4532.5
4532.5
4532.5
|  |  |  | Totals: |  | 4532.5

## #9244.00 SystemWorks
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM22-9255 |  |  | MA00521396
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522034900 | 2022-02-03 | DO Procore | 4810 | 4810 |  |  | 4810
DO 33522034900 | 2022-04-25 | Discarded initial DO to correct quantity amount | 0 | 4810 |  | 0 | 4810
DO 33522034900A | 2022-04-25 | DO Procore - Rebuilding DO with same amount | 0 | 4810 |  | 0 | 4810
DO 33522034900A | 2022-04-25 | CO #1 | 1657.5 | 6467.5 |  | 0 | 6467.5
PRC 3352203PA4900A | 2022-05-16 | Inv. 10710 |  | 6467.5 | 6467.5 | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  |  |  | 6467.5 |  | 6467.5 | 0
|  | Totals: | 6467.5 |  | 6467.5 |  | 0

## #9244.00 Terracon Consultants
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0017-335-MM22-9260 |  |  | 924400-001
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522126900 | 2022-05-06 | PO Procore | 61186 | 61186 |  |  | 61186
PRC 3352212PA6900 | 2022-06-20 | Inv. TG79986 |  | 61186 | 3400 | 3400 | 57786
PRC 3352212PB6900 | 2022-07-05 | Inv. TG97353 |  | 61186 | 24783 | 28183 | 33003 | FY22
PO 33523126900 | 2022-08-10 | Rolled to FY23 | 0 | 61186 |  | 28183 | 33003
PRC 3352312PC6900 | 2022-08-25 | Inv. 9244.00-03 |  | 61186 | 14032 | 42215 | 18971
PRC 3352312PD6900 | 2022-10-17 | Inv. 9244.00-04 |  | 61186 | 3361 | 45576 | 15610
PO 33523126900 | 2022-10-18 | CO #1 | 1200 | 62386 |  | 45576 | 16810
PRC 3352312PE6900 | 2022-12-13 | Inv. 9244.00-05 |  | 62386 | 3400 | 48976 | 13410
PRC 3352312PF6900 | 2023-04-03 | Inv. 9244.00-06 |  | 62386 | 2200 | 51176 | 11210
PRC 3352312PG6900 | 2023-05-08 | Inv. 9244.00-07 |  | 62386 | 4500 | 55676 | 6710
PO 33523126900 | 2023-05-25 | CO #2 (100% to DA23) | 0 | 62386 |  | 55676 | 6710
PRC 3352312PH6900 | 2023-07-06 | Inv. 9244.00-08 (100% to MM22) |  | 62386 | 3000 | 58676 | 3710
PRC 3352312PI6900 | 2023-07-17 | Inv. 9244.00-09 (Split with DA23) |  | 62386 | 200 | 58876 | 3510 | FY23
PO 33524126900 | 2023-07-25 | Roll to FY24 | 0 | 62386 |  | 58876 | 3510
PRC 3352412PJ6900 | 2023-08-24 | Inv. 9244.00-10 (100% to MM22) |  | 62386 | 800 | 59676 | 2710
PRC 3352412PK6900 | 2023-10-16 | Inv. 9244.00-11 (100% to MM22) |  | 62386 | 425 | 60101 | 2285
PRC 3352412PL6900 | 2023-11-15 | Inv. TK26190 (100% to MM22) |  | 62386 | 500 | 60601 | 1785
PO 33524126900 | 2024-01-25 | Terracon refund allocated to vendor tab |  | 62386 | -2200 | 58401 | 3985
PRC 3352412PM6900 | 2024-07-18 | Inv. TK61110 |  | 62386 | 3700 | 62101 | 285 | FY24
PO 33525126900 | 2024-07-22 | Roll to FY25 |  | 62386 |  | 62101 | 285
PO 33525126900 | 2024-08-20 | CO #3 | 3470 | 65856 |  | 62101 | 3755
PO 33525126900 | 2024-10-17 | CO #4 | 2000 | 67856 |  | 62101 | 5755
PRC 3352512PN6900 | 2024-11-05 | Inv. TM81442 |  | 67856 | 2350 | 64451 | 3405
PRC 3352512PO6900 | 2025-01-03 | Inv. TM97121 |  | 67856 | 1000 | 65451 | 2405
PRC 3352512PP6900 | 2025-01-14 | Inv. TN21927 |  | 67856 | 1100 | 66551 | 1305
|  |  |  | 67856 |  | 66551 | 1305
|  | Totals: | 67856 |  | 66551 |  | 1305
|  | DA23(Closed 07/17/23) | 277.5 |  | 277.5 |  | 0
|  | Total Contract | 68133.5 |  | 66828.5 |  | 1305
Vendor skipped Invoice 14

## #9244.00 McGough Constructi (2)
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Split with DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523290900 | 2022-10-14 | PO Procore | 150183 | 150183 |  |  | 150183
PRC 3352329PA0900 | 2022-11-14 | Inv. 9244.00-001.1 CA (100% to MM22) |  | 150183 | 1123 | 1123 | 149060
PRC 3352329PB0900 | 2022-12-13 | Inv. 100877.001-CA2 (100% to MM22) |  | 150183 | 940 | 2063 | 148120
PRC 3352329PC0900 | 2023-01-12 | Inv. 100877.001-CA3 (100% to MM22) |  | 150183 | 547.5 | 2610.5 | 147572.5
PRC 3352329PD0900 | 2023-02-10 | Inv. 100877.001-CA4 (100% to MM22) |  | 150183 | 730 | 3340.5 | 146842.5
PRC 3352329PE0900 | 2023-03-13 | Inv. 100877.001-CA5 (100% to MM22) |  | 150183 | 1173.75 | 4514.25 | 145668.75
PO 33523290900 | 2023-03-22 | CO #1 | 716.16 | 150899.16 |  | 4514.25 | 146384.91
PRC 3352329PF0900 | 2023-04-17 | Inv. 100877.001-CA6 (Split between MM22 and DA23) |  | 150899.16 | 30533.65 | 35047.9 | 115851.26
PRC 3352329PG0900 | 2023-05-11 | Inv. 100877.001-CA7 (Split between MM22 and DA23) |  | 150899.16 | 13080.78 | 48128.68 | 102770.48
PO 33523290900 | 2023-05-30 | CO #2 (100% to DA23) | 0 | 150899.16 |  | 48128.68 | 102770.48
PRC 3352329PH0900 | 2023-06-14 | Inv. 100877.001-CA8 (Split between MM22 and DA23) |  | 150899.16 | 11474.69 | 59603.37 | 91295.79
PRC 3352329PI0900 | 2023-07-12 | Inv. 100877.001-09 (Split between MM22 and DA23) |  | 150899.16 | 6040 | 65643.37 | 85255.79 | FY23
PO 33524290900 | 2023-08-23 | Roll to FY24 | 0 | 150899.16 |  | 65643.37 | 85255.79
PRC 3352429PJ0900 | 2023-08-24 | Inv. 100877.001-10 (100% to MM22) |  | 150899.16 | 6642.75 | 72286.12 | 78613.04
PRC 3352429PK0900 | 2023-09-15 | Inv. 100877.001-11 (100% to MM22) |  | 150899.16 | 4965 | 77251.12 | 73648.04
PRC 3352429PL0900 | 2023-10-10 | Inv. 100877.001-12 (100% to MM22) |  | 150899.16 | 2515.5 | 79766.62 | 71132.54
PRC 3352429PM0900 | 2023-11-17 | Inv. 100877.001-13 (100% to MM22) |  | 150899.16 | 4393 | 84159.62 | 66739.54
PRC 3352429PN0900 | 2023-12-13 | Inv. 100877.001-14 (100% to MM22) |  | 150899.16 | 2428.75 | 86588.37 | 64310.79
PRC 3352429PO0900 | 2024-01-17 | Inv. 100877.001-15 (100% to MM22) |  | 150899.16 | 2366 | 88954.37 | 61944.79
PRC 3352429PP0900 | 2024-02-08 | Inv. 100877.001-16 (100% to MM22) |  | 150899.16 | 1990 | 90944.37 | 59954.79
PRC 3352429PQ0900 | 2024-03-08 | Inv. 100877.001-17 (100% to MM22) |  | 150899.16 | 2000 | 92944.37 | 57954.79
PRC 3352429PR0900 | 2024-04-10 | Inv. 100877.001-18 (100% to MM22) |  | 150899.16 | 3107.5 | 96051.87 | 54847.29
PRC 3352429PS0900 | 2024-05-13 | Inv. 100877.001-19 (Split with DA23) |  | 150899.16 | 1817.41 | 97869.28 | 53029.88
PRC 3352429PT0900 | 2024-06-10 | Inv. 100877.001-20 (100% to MM22) |  | 150899.16 | 2639.5 | 100508.78 | 50390.38
PRC 3352429PU0900 | 2024-07-05 | Inv. 100877.001-21 (100% to MM22) |  | 150899.16 | 2042.5 | 102551.28 | 48347.88 | FY24
PO 33525290900 | 2024-08-19 | Roll to FY25 |  | 150899.16 |  | 102551.28 | 48347.88
PO 33525290900 | 2024-08-20 | CO #3(Split with DA23) | -5535 | 145364.16 |  | 102551.28 | 42812.88
PRC 3352529PV0900 | 2024-09-04 | Inv. 100877.001-22 (100% to MM22) |  | 145364.16 | 611.5 | 103162.78 | 42201.38
PRC 3352529PW0900 | 2024-09-11 | Inv. 100877.001-23 (100% to MM22) |  | 145364.16 | 1183.5 | 104346.28 | 41017.88
CDE 33525281900 | 2024-10-07 | Move Expenses from MM22 to DA23 |  | 145364.16 | -5535 | 98811.28 | 46552.88
PRC 3352529PX0900 | 2024-10-07 | Inv. 100877.001-24 (100% to MM22) |  | 145364.16 | 3296.75 | 102108.03 | 43256.13
PRC 3352529PY0900 | 2024-11-13 | Inv. 100877.001-25 (100% to MM22) |  | 145364.16 | 2654 | 104762.03 | 40602.13
PRC 3352529PZ0900 | 2024-12-13 | Inv. 100877.001-26 (100% to MM22) |  | 145364.16 | 1348 | 106110.03 | 39254.13
PO 33525290900 | 2025-01-08 | Closing to correct PO Total after CDE |  | 145364.16 |  | 106110.03 | 39254.13
PO 33525290900A | 2025-01-08 | Opening PO with correct total after CDE |  | 145364.16 |  | 106110.03 | 39254.13
PRC 3352529PAA0900A | 2025-01-08 | Inv. 100877.001-27 (Split between MM22 and DA23) |  | 145364.16 | 1325.58 | 107435.61 | 37928.55
PRC 3352529PAB0900A | 2025-02-06 | Inv. 100877.001-28 |  | 145364.16 | 540.5 | 107976.11 | 37388.05
|  |  |  | 145364.16 |  | 107976.11 | 37388.05
|  |  |  | 145364.16 |  | 107976.11 | 37388.05
|  | Totals: | 145364.16 |  | 107976.11 |  | 37388.05
|  | CM Services | 111643.2 |  | 74325.5 |  | 37317.7
|  | Reimbursables | 912.6 |  | 842.25 |  | 70.35
|  | Base Bid Fee | 37627.2 |  | 37627.2 |  | 0
|  | CO #1 | 716.16 |  | 716.16 |  | 0
|  | CO #3 | -5535 |  | -5535 |  | 0
|  | Total: | 145364.16 |  | 107976.11 |  | 37388.05
|  | DA23 Closed 01/08/25 | 34647.7 |  | 34647.7 |  | 0
|  | Total Contract | 180011.86 |  | 142623.81 |  | 37388.05

## #9244.00 Bi-State Masonry
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM22-9255 |  |  | 924400-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split with DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523290902 | 2022-10-14 | PO Procore | 103794 | 103794 |  |  | 103794
PO 33523290902 | 2023-03-01 | CO 1 (Split between MM22 & DA23) | 6125 | 109919 |  | 0 | 109919
PRC 3352329PA0902 | 2023-04-17 | Inv. 5531 (Split between MM22 & DA23) |  | 109919 | 71409.6 | 71409.6 | 38509.4 | 3758.42
PRC 3352329PB0902 | 2023-05-04 | Inv. 5560R (Split between MM22 and DA23) |  | 109919 | 16067.38 | 87476.98 | 22442.02 | 4604.07
PO 33523290902 | 2023-05-25 | CO 2 (Split between MM22 & DA23) | 2880 | 112799 |  | 87476.98 | 25322.02
PRC 3352329PC0902 | 2023-06-08 | Inv. 5585 (Split between MM22 and DA23) |  | 112799 | 15958.05 | 103435.03 | 9363.97 | 5443.97
PO 33523290902 | 2023-06-20 | CO 3 (100% to DA23) | 0 | 112799 |  | 103435.03 | 9363.97
PRC 3352329PD0902 | 2023-07-07 | Inv. 5617 (Split between MM22 and DA23) |  | 112799 | 2736 | 106171.03 | 6627.97 | 5587.97 | FY23
PO 33524290902 | 2023-08-22 | Roll to FY24 | 0 | 112799 |  | 106171.03 | 6627.97
PO 33524290902 | 2023-08-29 | CO 4 (No Cost) | 0 | 112799 |  | 106171.03 | 6627.97
PRC 3352429PE0902 | 2023-12-05 | Inv. 5715 (100% to DA23) |  | 112799 | 0 | 106171.03 | 6627.97 | 5587.97 | FY24
PO 33525290902 | 2024-08-19 | Roll to FY25 |  | 112799 |  | 106171.03 | 6627.97
PO 33525290902 | 2024-08-19 | CO #5 | -465 | 112334 |  | 106171.03 | 6162.97
PRC 3352529PF0902 | 2024-12-19 | Inv. 5808(100% to MM22) |  | 112334 | 546.25 | 106717.28 | 5616.72 | 5616.72
PRC 3352529PG0902 | 2025-01-03 | Inv. 5844 (Split between MM22 and DA23) |  | 112334 | 5616.72 | 112334 | 0
|  | Totals: | 112334 |  | 112334 |  | 0 | FINAL
|  | DA23 | 582759 |  | 582759 |  | 0
|  | Total Contract | 695093 |  | 695093 |  | 0

## #9244.00 Hopkins Roofing
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
Hopkins Roofing |  |  | Vendor: 00003054888
Acct. Codes-0017-335-MM22-9255 |  |  | 924400-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split with DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523290903 | 2022-10-14 | PO Procore | 648750 | 648750 |  |  | 648750
PO 33523290903 | 2023-02-24 | CO #1 | 7874.08 | 656624.08 |  | 0 | 656624.08
PRC 3352329PA0903 | 2023-04-17 | Inv. 9244.00-01 |  | 656624.08 | 354397.5 | 354397.5 | 302226.58 | 18652.5
PRC 3352329PB0903 | 2023-05-22 | Inv. 9244.00-02 |  | 656624.08 | 111589.37 | 465986.87 | 190637.21 | 24525.63
PO 33523290903 | 2023-06-02 | CO #2 (100% to DA23) | 0 | 656624.08 |  | 465986.87 | 190637.21
PRC 3352329PC0903 | 2023-06-13 | Inv. 9244.00-03 (100% to MM22) |  | 656624.08 | 68329.67 | 534316.54 | 122307.54 | 28121.93
PO 33523290903 | 2023-06-28 | CO #3 (100% to MM22) | 3304.47 | 659928.55 |  | 534316.54 | 125612.01
PRC 3352329PD0903 | 2023-07-17 | Inv. 9244.00-04 (100% to MM22) |  | 659928.55 | 31350 | 565666.54 | 94262.01 | 29771.93 | FY23
PO 33524290903 | 2023-08-22 | Roll to FY24 | 0 | 659928.55 |  | 565666.54 | 94262.01
PRC 3352429PE0903 | 2023-08-23 | Inv. 9244.00-05 (100% to MM22) |  | 659928.55 | 44175 | 609841.54 | 50087.01 | 32096.93
PO 33524290903 | 2023-09-14 | CO #4 (100% to MM22) | 9968.2 | 669896.75 |  | 609841.54 | 60055.21
PRC 3352429PF0903 | 2023-10-11 | Inv. 9244.00-06 (100% to MM22) |  | 669896.75 | 3139.25 | 612980.79 | 56915.96 | 32262.15
PO 33524290903 | 2023-12-13 | CO #5 (100% to MM22) | -3335 | 666561.75 |  | 612980.79 | 53580.96
PRC 3352429PG0903 | 2024-04-10 | Inv. 9244.00-07 (Split between MM22 and DA23) |  | 666561.75 | 20252.86 | 633233.65 | 33328.1 | 33328.1
PRC 3352429PH0903 | 2024-04-29 | Inv. 9244.00-08-Retainage (Split between MM22 and DA23) |  | 666561.75 | 33328.1 | 666561.75 | 0
|  |  |  | 666561.75 |  | 666561.75 | 0
|  |  |  | 666561.75 |  | 666561.75 | 0
|  |  |  | 666561.75 |  | 666561.75 | 0
|  | Totals: | 666561.75 |  | 666561.75 |  | 0
|  | DA23 | 7085 |  | 7085 |  | 0
|  | Total Contract | 673646.75 |  | 673646.75 |  | 0

## #9244.00 Hopkins Roofing (2)
IPBS JOH 6450 Corporate Dr. Roof Replacement
Project # 9244.00
Program code 924400 |  |  | Major Program 4E02
Hopkins Roofing |  |  | Vendor: 00003054888
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV2
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525291900 | 2024-10-17 | PO Procore | 10370.71 | 10370.71 |  |  | 10370.71
PRC 3352529PA1900 | 2025-02-06 | Inv. 1584 |  | 10370.71 | 9753.65 | 9753.65 | 617.06 | 513.35
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
|  |  |  | 10370.71 |  | 9753.65 | 617.06
9753.65
|  | Totals: | 10370.71 |  | 9753.65 |  | 617.06

## RECAP #9245.00
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
| Program code 924500 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 530800.84
C | Samuels Group |  | 11632.2 | 11632.2 | 0
C | PM TIME |  | 23466.42 | 23466.42 | 0
C | Misc. |  | 274.37 | 274.37 | 0
C | MA Architecture |  | 24985 | 24985 | 0
C | ATC Group |  | 1132.5 | 1132.5 | 0
C | Samuels Group #098CA |  | 50130.35 | 50130.35 | 0
C | Stevens Brothers Construction |  | 419180 | 419180 | 0
| Total Project Cost | 530800.84 | 530800.84 | 530800.84 | 0 | 0
Closed 12/17/24
Note on C8: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #9245.00 Samuels Group
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522356802 | 2021-12-22 | PO Procore | 7844.64 | 7844.64 |  |  | 7844.64
PRC 3352235PA6802 | 2022-02-10 | Inv. 7359.01924500 |  | 7844.64 | 248.96 | 248.96 | 7595.68
PRC 3352235PB6802 | 2022-03-09 | Inv. 7359.02924500 |  | 7844.64 | 1244.8 | 1493.76 | 6350.88
PO 33522356802 | 2022-04-05 | CO 1 | 1132.72 | 8977.36 |  | 1493.76 | 7483.6
PRC 3352235PC6802 | 2022-04-14 | Inv. 7359.03924500 |  | 8977.36 | 1944.55 | 3438.31 | 5539.05
PRC 3352235PD6802 | 2022-05-05 | Inv. 7359.04924500 |  | 8977.36 | 281.44 | 3719.75 | 5257.61
PRC 3352235PE6802 | 2022-06-03 | Inv. 7359.05924500 |  | 8977.36 | 627.82 | 4347.57 | 4629.79
PRC 3352235PF6802 | 2022-06-30 | Inv. 7359.06924500 |  | 8977.36 | 2038.32 | 6385.89 | 2591.47 | FY22
PO 33523356802 | 2022-08-10 | Rolled to FY23 | 0 | 8977.36 |  | 6385.89 | 2591.47
PRC 3352335PG6802 | 2022-08-12 | Inv. 7359.07924500 |  | 8977.36 | 503.34 | 6889.23 | 2088.13
PRC 3352335PH6802 | 2022-09-12 | Inv. 7359.08924500 |  | 8977.36 | 811.83 | 7701.06 | 1276.3
PRC 3352335PI6802 | 2022-10-04 | Inv. 7359.09924500 |  | 8977.36 | 1001.26 | 8702.32 | 275.04
PO 33523356802 | 2022-11-22 | CO 2 | 2654.92 | 11632.28 |  | 8702.32 | 2929.96
PRC 3352335PJ6802 | 2022-12-09 | Inv. 7359.10924500 |  | 11632.28 | 2080.15 | 10782.47 | 849.81
PRC 3352335PK6802 | 2023-07-06 | Inv. 7359.11924500 |  | 11632.28 | 849.73 | 11632.2 | 0.08
PO 33523356802 | 2023-08-04 | Closing Per PM & Vendor | -0.08 | 11632.2 |  | 11632.2 | 8.3673e-13
|  |  |  | 11632.2 |  | 11632.2 | 8.3673e-13
|  | Total: | 11632.2 |  | 11632.2 |  | 0
|  | CM Services | 7544.64 |  | 7544.64 |  | 0
|  | Reimbursables | 300 |  | 300 |  | 0
|  | CO 1 | 1132.72 |  | 1132.72 |  | 0
|  | CO 2 | 2654.84 |  | 2654.84 |  | 0
|  | Total: | 11632.2 |  | 11632.2 |  | 0

## #9245.00 PM TIME
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1Z9
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 21439.51 | 21439.51 |  |  | 21439.51
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 21439.51 | 50 | 50 | 21389.51
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 21439.51 | 225 | 275 | 21164.51
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 21439.51 | 150 | 425 | 21014.51
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 21439.51 | 350 | 775 | 20664.51
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 21439.51 | 375 | 1150 | 20289.51
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 21439.51 | 650 | 1800 | 19639.51
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 21439.51 | 425 | 2225 | 19214.51
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 21439.51 | 950 | 3175 | 18264.51
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 21439.51 | 350 | 3525 | 17914.51
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 21439.51 | -350 | 3175 | 18264.51
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 21439.51 | 385 | 3560 | 17879.51
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 21439.51 | 605 | 4165 | 17274.51
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 21439.51 | 137.5 | 4302.5 | 17137.01
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 21439.51 | 275 | 4577.5 | 16862.01
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 21439.51 | 357.5 | 4935 | 16504.51
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 638.62 | 22078.13 | 638.62 | 5573.62 | 16504.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 460.65 | 22538.78 | 460.65 | 6034.27 | 16504.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 87.89 | 22626.67 | 87.89 | 6122.16 | 16504.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 173.17 | 22799.84 | 173.17 | 6295.33 | 16504.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 245.41 | 23045.25 | 245.41 | 6540.74 | 16504.51
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 23045.25 | 187.78 | 6728.52 | 16316.73
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 107.39 | 23152.64 | 107.39 | 6835.91 | 16316.73
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 150.77 | 23303.41 | 150.77 | 6986.68 | 16316.73
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 35.99 | 23339.4 | 35.99 | 7022.67 | 16316.73
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 34.74 | 23374.14 | 34.74 | 7057.41 | 16316.73
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 64.19 | 23438.33 | 64.19 | 7121.6 | 16316.73
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 28.09 | 23466.42 | 28.09 | 7149.69 | 16316.73
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 23466.42 | 42.35 | 7192.04 | 16274.38
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 23466.42 | 256.78 | 7448.82 | 16017.6
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 23466.42 | 13.96 | 7462.78 | 16003.64
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 23466.42 | 81.9 | 7544.68 | 15921.74
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 23466.42 | 8.89 | 7553.57 | 15912.85
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 23466.42 | 60.5 | 7614.07 | 15852.35
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 23466.42 | 55.26 | 7669.33 | 15797.09
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 23466.42 | 494.9 | 8164.23 | 15302.19
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 23466.42 | 92.52 | 8256.75 | 15209.67
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 23466.42 | 589.3 | 8846.05 | 14620.37
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 23466.42 | 126.4 | 8972.45 | 14493.97
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 23466.42 | 705 | 9677.45 | 13788.97
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 23466.42 | 33.8 | 9711.25 | 13755.17
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 23466.42 | 234.1 | 9945.35 | 13521.07
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 23466.42 | 109.81 | 10055.16 | 13411.26
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 23466.42 | 881.3 | 10936.46 | 12529.96
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 23466.42 | 79.38 | 11015.84 | 12450.58
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 23466.42 | 602.6 | 11618.44 | 11847.98
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 23466.42 | 132.11 | 11750.55 | 11715.87
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 23466.42 | 971.1 | 12721.65 | 10744.77
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 23466.42 | 105.95 | 12827.6 | 10638.82
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 23466.42 | 930.8 | 13758.4 | 9708.02
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 23466.42 | 89.43 | 13847.83 | 9618.59
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 23466.42 | 451 | 14298.83 | 9167.59
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 23466.42 | 89.99 | 14388.82 | 9077.6
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 23466.42 | 683.3 | 15072.12 | 8394.3
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 23466.42 | 130.67 | 15202.79 | 8263.63
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 23466.42 | 1160.2 | 16362.99 | 7103.43
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 23466.42 | 104.4 | 16467.39 | 6999.03
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 23466.42 | 872.3 | 17339.69 | 6126.73
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 23466.42 | 92.43 | 17432.12 | 6034.3
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 23466.42 | 842.5 | 18274.62 | 5191.8
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 23466.42 | 78.29 | 18352.91 | 5113.51
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 23466.42 | 856.2 | 19209.11 | 4257.31
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 23466.42 | 188.17 | 19397.28 | 4069.14
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 23466.42 | 955.6 | 20352.88 | 3113.54
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 23466.42 | 113.54 | 20466.42 | 3000
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 23466.42 | 1010.4 | 21476.82 | 1989.6
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 23466.42 | 114.8 | 21591.62 | 1874.8
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 23466.42 | 767.8 | 22359.42 | 1107
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 23466.42 | 144.9 | 22504.32 | 962.1
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 23466.42 | 962.1 | 23466.42 | 0
[5 empty] | 23466.42 |  | 23466.42 | 0
[5 empty] | 23466.42 |  | 23466.42 | 0
[5 empty] | 23466.42 |  | 23466.42 | 0
[5 empty] | 23466.42 |  | 23466.42 | 0
[5 empty] | 23466.42 |  | 23466.42 | 0
|  |  | Totals: | 23466.42 |  | 23466.42 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time Setup $Selma Herman, Josh Wed, Nov 24, 9:38 AM (5 days ago) to me Please set up $5,000 of PM Time in project 9245.00 in MM22. Please set up $5,000 of PM Time in project 9246.00 in MM22. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time for September $Joni Herman, Josh 8:53 AM (5 hours ago) to me 8983.02 in MM22 Please add $5,500. 9306.00 in MM23 Please set at $8,800 9313.00 in DA23 Please set at $4,200. 9246.00 in MM22 Please change to $10,000 total. 9245.00 in MM22 Please change to $10,000 total. 9287.00 in MM21 Please change to $10,000 total. 9268.00 in MM20 Please add $1,100. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Re: PM Time $John Tonyan, Brad 11:29 AM (59 minutes ago) to me, John John, Please raise the PM Time budget to an even $20,000 in this project 9245.00. Thank you, Joni, Please raise the PM time budget by $1,000 to cover this and the final month of time to hit in November. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative PM Time Budget Increases Inbox Tonyan, Brad 2:56 PM (1 minute ago) to me, Brad Finance, Please make the following adjustments to ensure coverage on November PM time: MM22 - 9245.00 - Increase PM Time $2,000 MM24 - 9306.00 - Increase PM Time $10,000 MM24 - 9376.00 - Increase PM Time $2,500 DA24 - 9362.00 - Increase PM Time $2,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Fwd: DOC CCF CTC NE and SW Porch Repairs: State Change on Subcontractor Invoice #1: State of Iowa - Department of Administrative Services $Joni Tonyan, Brad 12:57 PM (36 minutes ago) to me, Brad Finance, I just processed the final PM time invoice balancing invoice in Procore to balance with the DAS billables. You can now please close out the entire project 9245.00 and return the remaining balance to MM22 funding org. All invoices are closed and paid in full. Thank you and let me know when this is done. Brad Tonyan, CPM, LEED G

## #9245.00 Misc
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523332901 | 2022-11-28 | 9500 | CNST | BeeLine&Blue V#(00002108204) | Inv. INV025470 | 199.42 | 199.42
PRC 33523199901 | 2023-07-17 | 9500 | CNST | BeeLine&Blue V#(00002108204) | Inv. INV031624 | 74.95 | 274.37
274.37
274.37
274.37
274.37
274.37
274.37
274.37
274.37
274.37
274.37
|  |  |  | Totals: |  | 274.37

## #9245.00 MA Architecture
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  | Major Program 4B01
MA Architecture |  |  | Vendor: 00003166868
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522063903 | 2022-03-04 | PO Procore | 24985 | 24985 |  |  | 24985
PRC 3352206PA3903 | 2022-04-28 | Inv. 9245-1 |  | 24985 | 2717.5 | 2717.5 | 22267.5
PRC 3352206PB3903 | 2022-07-07 | Inv. 1888 |  | 24985 | 6892.5 | 9610 | 15375 | FY22
PO 33523063903 | 2022-08-10 | Rolled to FY23 | 0 | 24985 |  | 9610 | 15375
PRC 3352306PC3903 | 2022-08-25 | Inv. 7764 |  | 24985 | 4797.5 | 14407.5 | 10577.5
PRC 3352306PD3903 | 2022-10-28 | Inv. 467 |  | 24985 | 252.5 | 14660 | 10325
PO 33523063903 | 2022-12-02 | CO #1 (No Cost) | 0 | 24985 |  | 14660 | 10325
PRC 3352306PE3903 | 2023-07-06 | Inv. 468 |  | 24985 | 4430 | 19090 | 5895 | FY23
PO 33524063903 | 2023-08-03 | Roll to FY24 | 0 | 24985 |  | 19090 | 5895
PRC 3352406PF3903 | 2024-05-09 | Inv. 469 |  | 24985 | 3551.25 | 22641.25 | 2343.75
PRC 3352406PG3903 | 2024-07-08 | Inv. 1132 |  | 24985 | 937.5 | 23578.75 | 1406.25 | FY24
PO 33525063903 | 2024-07-18 | Roll To FY25 |  | 24985 |  | 23578.75 | 1406.25
PRC 3352506PH3903 | 2024-11-20 | Inv. 1133 FINAL |  | 24985 | 1406.25 | 24985 | 0
|  | Total: | 24985 |  | 24985 |  | 0 | FINAL
|  | Schematic Design Docs | 5435 |  | 5435 |  | 0
|  | Design Development Docs | 4175 |  | 4175 |  | 0
|  | Construction Docs | 5050 |  | 5050 |  | 0
|  | Bidding Assistance | 950 |  | 950 |  | 0
|  | Construction Phase | 9375 |  | 9375 |  | 0
|  | Total: | 24985 |  | 24985 |  | 0

## #9245.00 ATC Group
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  | Major Program 4B01
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA 20262A
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522087900 | 2022-03-25 | DO Procore | 2060 | 2060 |  |  | 2060
PRC 3352208PA7900 | 2022-07-13 | Inv. 2423017 - Final | -927.5 | 1132.5 | 1132.5 | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  |  |  | 1132.5 |  | 1132.5 | 0
|  | Total: | 1132.5 |  | 1132.5 |  | 0 | Final Invoice
|  | Contract Line 7 Field Tech 14hrs@ $75 | 675 |  | 675 |  | 0
|  | Contract Line 8 Hygienist 2 hrs@ $95 | 190 |  | 190 |  | 0
|  | Contract Line 5 Admin Time 1hr@ $45 | 22.5 |  | 22.5 |  | 0
|  | Contract Line 2 Abestos Per Sample Fee 40 Samples@ $10 | 20 |  | 20 |  | 0
|  | Contract Line 3 Lead Based Paint Per Sample Fee 25 Samples@ $15.00 | 225 |  | 225 |  | 0
|  | Total: | 1132.5 |  | 1132.5 |  | 0

## #9245.00 Samuels Group 098 CA
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  | Major Program 4B01
Samuels Group #098CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524216803 | 2023-08-04 | PO Procore | 53440.64 | 53440.64 |  |  | 53440.64
PRC 3352421PA6803 | 2023-09-14 | Inv. 7516.01924500 |  | 53440.64 | 2732.7 | 2732.7 | 50707.94
PRC 3352421PB6803 | 2023-10-05 | Inv. 7516.02924500 |  | 53440.64 | 1561.78 | 4294.48 | 49146.16
PRC 3352421PC6803 | 2023-11-07 | Inv. 7516.03924500 |  | 53440.64 | 619.85 | 4914.33 | 48526.31
PRC 3352421PD6803 | 2023-12-11 | Inv. 7516.04924500 |  | 53440.64 | 1745.47 | 6659.8 | 46780.84
PRC 3352421PE6803 | 2024-01-05 | Inv. 7516.05924500 |  | 53440.64 | 849.67 | 7509.47 | 45931.17
PRC 3352421PF6803 | 2024-02-02 | Inv. 7516.06924500 |  | 53440.64 | 837.93 | 8347.4 | 45093.24
PRC 3352421PG6803 | 2024-03-05 | Inv. 7516.07924500 |  | 53440.64 | 1366.35 | 9713.75 | 43726.89
PRC 3352421PH6803 | 2024-04-08 | Inv. 7516.08924500 |  | 53440.64 | 4859.92 | 14573.67 | 38866.97
PRC 3352421PI6803 | 2024-05-06 | Inv. 7516.09924500 |  | 53440.64 | 6863.11 | 21436.78 | 32003.86
PRC 3352421PJ6803 | 2024-05-30 | Inv. 7516.10924500 |  | 53440.64 | 5462.79 | 26899.57 | 26541.07
PRC 3352421PK6803 | 2024-07-08 | Inv. 7516.11924500 |  | 53440.64 | 7126.6 | 34026.17 | 19414.47 | FY24
PO 33525216803 | 2024-07-18 | Roll to FY25 |  | 53440.64 |  | 34026.17 | 19414.47
PRC 3352521PL6803 | 2024-08-09 | Inv. 7516.12924500 |  | 53440.64 | 4036.97 | 38063.14 | 15377.5
PRC 3352521PM6803 | 2024-11-06 | Inv. 7516.13924500 |  | 53440.64 | 5762.31 | 43825.45 | 9615.19
PRC 3352521PN6803 | 2024-12-03 | Inv. 7516.14924500-FINAL | -3310.29 | 50130.35 | 6304.9 | 50130.35 | 0
|  |  |  | 50130.35 |  | 50130.35 | 0
|  | Total: | 50130.35 |  | 50130.35 |  | 0 | FINAL
|  | CM Services | 46440.64 |  | 46440.64 |  | 0
|  | Reimbursables | 3689.71 |  | 3689.71 |  | 0
|  | Total: | 50130.35 |  | 50130.35 |  | 0

## #9245.00 Stevens Brothers
DOC CCF CTC NW and SW Porch Repairs
Project # 9245.00
Program code 924500 |  |  | Major Program 4B01
Stevens Brother Construction |  |  | Vendor: 00002091978
Acct. Codes-0017-335-MM22-9255 |  |  | RFB924500-02
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524221906 | 2023-08-09 | PO Procore | 419860 | 419860 |  |  | 419860
PO 33524221906 | 2024-03-18 | CO #1 | 1035 | 420895 |  | 0 | 420895
PRC 3352422PA1906 | 2024-04-19 | Inv. 9245.00-01 |  | 420895 | 94145.95 | 94145.95 | 326749.05 | 4955.05
PO 33524221906 | 2024-04-29 | CO #2 | -2637 | 418258 |  | 94145.95 | 324112.05
PRC 3352422PB1906 | 2024-06-11 | Inv. 1686 |  | 418258 | 146581.2 | 240727.15 | 177530.85 | 12669.85
PO 33524221906 | 2024-06-26 | CO #3(No Cost CO) | 0 | 418258 |  | 240727.15 | 177530.85
PRC 3352422PC1906 | 2024-07-12 | Inv. 9245.00-03 |  | 418258 | 53912.5 | 294639.65 | 123618.35 | 15507.35 | FY24
PO 33525221906 | 2024-07-18 | Roll to FY25 |  | 418258 |  | 294639.65 | 123618.35
PO 33525221906 | 2024-09-30 | CO #4 | 922 | 419180 |  | 294639.65 | 124540.35
PRC 3352522PD1906 | 2024-11-06 | Inv. 9245.00-04 |  | 419180 | 99592.68 | 394232.33 | 24947.67 | 20749.07
PRC 3352522PE1906 | 2024-11-20 | Inv. 9245.00-05 |  | 419180 | 3988.67 | 398221 | 20959 | 20959
PRC 3352522PF1906 | 2024-11-22 | Inv. 9245.00-06 retainage |  | 419180 | 20959 | 419180 | 0
|  |  |  | 419180 |  | 419180 | 0
|  | Total: | 419180 |  | 419180 |  | 0

## RECAP #9246.00
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
| Program code 924600 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 451172.62
C | Samuels Group |  | 13623.38 | 13623.38 | 0
C | PM TIME |  | 14309.33 | 14309.33 | 0
C | Misc. |  | 241.3 | 241.3 | 0
C | Genesis Architectural Design |  | 27500 | 27500 | 0
C | ATC Group Services |  | 1153.75 | 1153.75 | 0
C | Bi-State Masonry |  | 351134.19 | 351134.19 | 0
C | Samuels Group CA |  | 43210.67 | 43210.67 | 0
| Total Project Cost | 451172.62 | 451172.62 | 451172.62 | 0 | 0
Closed 07/17/23

## #9246.00 Samuels Group
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: Samuels9112015
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522012801 | 2022-01-11 | PO Procore | 13743.94 | 13743.94 |  |  | 13743.94
PRC 3352201PA2801 | 2022-02-10 | Inv. 7382.01924600 |  | 13743.94 | 497.92 | 497.92 | 13246.02
PRC 3352201PB2801 | 2022-03-09 | Inv. 7382.02924600 |  | 13743.94 | 2489.6 | 2987.52 | 10756.42
PRC 3352201PC2801 | 2022-04-14 | Inv. 7382.03924600 |  | 13743.94 | 1060.79 | 4048.31 | 9695.63
PRC 3352201PD2801 | 2022-05-05 | Inv. 7382.04924600 |  | 13743.94 | 595.35 | 4643.66 | 9100.28
PRC 3352201PE2801 | 2022-06-03 | Inv. 7382.05924600 |  | 13743.94 | 2135.49 | 6779.15 | 6964.79
PRC 3352201PF2801 | 2022-06-30 | Inv. 7382.06924600 |  | 13743.94 | 2188.13 | 8967.28 | 4776.66 | FY22
PO 33523012801 | 2022-08-10 | Rolled to FY23 | 0 | 13743.94 |  | 8967.28 | 4776.66
PRC 3352301PG2801 | 2022-08-16 | Inv. 7382.07924600 |  | 13743.94 | 2154.06 | 11121.34 | 2622.6
PRC 3352301PH2801 | 2022-09-01 | Inv. 7382.08924600 Final | -120.56 | 13623.38 | 2502.04 | 13623.38 | 8.5265e-13
|  |  |  | 13623.38 |  | 13623.38 | 8.5265e-13
|  |  |  | 13623.38 |  | 13623.38 | 8.5265e-13
|  |  |  | 13623.38 |  | 13623.38 | 8.5265e-13
|  | Total: | 13623.38 |  | 13623.38 |  | 0 | Final
|  | CM Services | 13422.27 |  | 13422.27 |  | 0
|  | Reimbursables | 201.11 |  | 201.11 |  | 0
|  | Total: | 13623.38 |  | 13623.38 |  | 0

## #9246.00 PM TIME
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZA
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12145.6 | 12145.6 |  |  | 12145.6
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 12145.6 | 50 | 50 | 12095.6
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 12145.6 | 25 | 75 | 12070.6
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 12145.6 | 225 | 300 | 11845.6
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 12145.6 | 950 | 1250 | 10895.6
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 12145.6 | 200 | 1450 | 10695.6
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 12145.6 | 250 | 1700 | 10445.6
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 12145.6 | 1225 | 2925 | 9220.6
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 12145.6 | 225 | 3150 | 8995.6
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 12145.6 | 700 | 3850 | 8295.6
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 12145.6 | -700 | 3150 | 8995.6
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 12145.6 | 770 | 3920 | 8225.6
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 12145.6 | 385 | 4305 | 7840.6
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12145.6 | 687.5 | 4992.5 | 7153.1
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12145.6 | 330 | 5322.5 | 6823.1
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 12145.6 | 165 | 5487.5 | 6658.1
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 505.11 | 12650.71 | 505.11 | 5992.61 | 6658.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 293.14 | 12943.85 | 293.14 | 6285.75 | 6658.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 439.48 | 13383.33 | 439.48 | 6725.23 | 6658.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 207.8 | 13591.13 | 207.8 | 6933.03 | 6658.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 113.27 | 13704.4 | 113.27 | 7046.3 | 6658.1
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 13704.4 | 140.83 | 7187.13 | 6517.27
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 13704.4 | 37.79 | 7224.92 | 6479.48
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 13704.4 | 331.3 | 7556.22 | 6148.18
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 214.78 | 13919.18 | 214.78 | 7771 | 6148.18
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 95.94 | 14015.12 | 95.94 | 7866.94 | 6148.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 208.77 | 14223.89 | 208.77 | 8075.71 | 6148.18
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 34.74 | 14258.63 | 34.74 | 8110.45 | 6148.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 29.63 | 14288.26 | 29.63 | 8140.08 | 6148.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 21.07 | 14309.33 | 21.07 | 8161.15 | 6148.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 14309.33 | 114.78 | 8275.93 | 6033.4
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 14309.33 | 696.04 | 8971.97 | 5337.36
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 14309.33 | 114.58 | 9086.55 | 5222.78
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 14309.33 | 504.01 | 9590.56 | 4718.77
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 14309.33 | 223.25 | 9813.81 | 4495.52
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 14309.33 | 1311.3 | 11125.11 | 3184.22
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 14309.33 | 265.34 | 11390.45 | 2918.88
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 14309.33 | 1860.1 | 13250.55 | 1058.78
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for: June 1-30, 2023 |  | 14309.33 | 118.98 | 13369.53 | 939.8
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for: June 1-30, 2023 |  | 14309.33 | 939.8 | 14309.33 | 0
[5 empty] | 14309.33 |  | 14309.33 | 0
[5 empty] | 14309.33 |  | 14309.33 | 0
[5 empty] | 14309.33 |  | 14309.33 | 0
|  |  | Totals: | 14309.33 |  | 14309.33 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time Setup $Selma Herman, Josh Wed, Nov 24, 9:38 AM (5 days ago) to me Please set up $5,000 of PM Time in project 9245.00 in MM22. Please set up $5,000 of PM Time in project 9246.00 in MM22. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time for September $Joni Herman, Josh 8:53 AM (5 hours ago) to me 8983.02 in MM22 Please add $5,500. 9306.00 in MM23 Please set at $8,800 9313.00 in DA23 Please set at $4,200. 9246.00 in MM22 Please change to $10,000 total. 9245.00 in MM22 Please change to $10,000 total. 9287.00 in MM21 Please change to $10,000 total. 9268.00 in MM20 Please add $1,100. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM time $John Tonyan, Brad 3:41 PM (19 minutes ago) to me Finance, Please increase all as needed to cover. Thanks, On Thu, Jun 8, 2023, 3:38 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Brad When trying to post pm time for May we have the following that need budget increases in order to post. DA21 Proj. 9172.00 Amount 1139.60 Balance 651.03 MM22 Proj. 9246.00 Amount 1860.10 Balance 773.28 Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed.

## #9246.00 Misc
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523250800 | 2022-09-06 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. 022333 | 241.3 | 241.3
241.3
241.3
241.3
241.3
241.3
241.3
241.3
241.3
241.3
241.3
241.3
|  |  |  | Totals: |  | 241.3

## #9246.00 Genesis Architectural
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  | Major Program 4B01
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | 924600-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522064900 | 2022-03-01 | PO Procore | 27500 | 27500 |  |  | 27500
PRC 3352206PA4900 | 2022-05-09 | Inv. 2203-01 |  | 27500 | 5000 | 5000 | 22500
PRC 3352206PB4900 | 2022-06-08 | Inv. 2203-02 |  | 27500 | 8000 | 13000 | 14500
PRC 3352206PC4900 | 2022-07-13 | Inv. 2203-03 |  | 27500 | 3000 | 16000 | 11500 | FY22
PO 33523064900 | 2022-08-10 | Rolled to FY23 | 0 | 27500 |  | 16000 | 11500
PRC 3352306PD4900 | 2022-09-28 | Inv. 2203-04 |  | 27500 | 3140 | 19140 | 8360
PRC 3352306PE4900 | 2022-12-19 | Inv. 2203-05 |  | 27500 | 1710 | 20850 | 6650
PO 33523064900 | 2023-05-23 | CO #1 (No Cost) | 0 | 27500 |  | 20850 | 6650
PRC 3352306PF4900 | 2023-06-09 | Inv. 2203-06 |  | 27500 | 4275 | 25125 | 2375
PRC 3352306PG4900 | 2023-06-30 | Inv. 2203-07 - Final |  | 27500 | 2375 | 27500 | 0
|  |  |  | 27500 |  | 27500 | 0
|  |  |  | 27500 |  | 27500 | 0
|  |  |  | 27500 |  | 27500 | 0
|  | Total: | 27500 |  | 27500 |  | 0
|  | Schematic Design Docs | 5000 |  | 5000 |  | 0
|  | Design Development Docs | 5000 |  | 5000 |  | 0
|  | Construction Docs | 6000 |  | 6000 |  | 0
|  | Bidding Assistance | 2000 |  | 2000 |  | 0
|  | Construction Phase | 9500 |  | 9500 |  | 0
|  | Total: | 27500 |  | 27500 |  | 0

## #9246.00 ATC Group
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  | Major Program 4B01
ATC Group Services |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | 20262A
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522069900 | 2022-03-09 | DO Procore | 1610 | 1610 |  |  | 1610
PRC 3352206PA9900 | 2022-07-13 | Inv. 2422998 - Final | -456.25 | 1153.75 | 1153.75 | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  |  |  | 1153.75 |  | 1153.75 | 0
|  | Total: | 1153.75 |  | 1153.75 |  | 0 | Final Invoice
|  | Line 7-Field Technician(13hrs @$75 | 731.25 |  | 731.25 |  | 0
|  | Line 8-Hygenist(2hrs @$95) | 190 |  | 190 |  | 0
|  | Line 5-Administrative Time (1hrs@45) | 22.5 |  | 22.5 |  | 0
|  | Line 2-Field Technician(40 Samples@$10) | 210 |  | 210 |  | 0
|  | Total: | 1153.75 |  | 1153.75 |  | 0

## #9246.00 Bi-State Masonry
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  | Major Program 4B01
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM22-9255 |  |  | RFB#924600-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523223803 | 2022-08-11 | PO Procore | 368100 | 368100 |  |  | 368100
PRC 3352322PA3803 | 2023-01-11 | Inv. 1-5433 |  | 368100 | 108202.09 | 108202.09 | 259897.91 | 5694.86
PO 33523223803 | 2023-01-18 | CO #1 | 384.19 | 368484.19 |  | 108202.09 | 260282.1
PRC 3352322PB3803 | 2023-05-11 | Inv. 5549 |  | 368484.19 | 161087.26 | 269289.35 | 99194.84 | 14173.15
PRC 3352322PC3803 | 2023-06-06 | Inv. 5601 |  | 368484.19 | 60791.14 | 330080.49 | 38403.7 | 17372.7
PO 33523223803 | 2023-06-08 | CO #2 | -17350 | 351134.19 |  | 330080.49 | 21053.7
PRC 3352322PD3803 | 2023-06-30 | Inv. 5611 |  | 351134.19 | 3496.95 | 333577.44 | 17556.75 | 17556.75
PRC 3352322PE3803 | 2023-07-10 | Inv. 9246.00-05-Retainage |  | 351134.19 | 17556.75 | 351134.19 | 0
|  |  |  | 351134.19 |  | 351134.19 | 0
|  |  |  | 351134.19 |  | 351134.19 | 0
|  |  |  | 351134.19 |  | 351134.19 | 0
|  |  |  | 351134.19 |  | 351134.19 | 0
|  |  |  | 351134.19 |  | 351134.19 | 0
|  | Total: | 351134.19 |  | 351134.19 |  | 0

## #9246.00 Samuels Group CA
DOC CCF Precast Walls and Window Sealing
Project # 9246.00
Program code 924600 |  |  | Major Program 4B01
Samuels Group CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523227900 | 2022-08-15 | PO Procore | 51591.9 | 51591.9 |  |  | 51591.9
PRC 3352322PA7900 | 2022-09-11 | Inv. 7382.51924600 |  | 51591.9 | 698.19 | 698.19 | 50893.71
PRC 3352322PB7900 | 2022-10-04 | Inv. 7382.52924600 |  | 51591.9 | 1197.69 | 1895.88 | 49696.02
PRC 3352322PC7900 | 2022-11-08 | Inv. 7382.53924600 |  | 51591.9 | 4516 | 6411.88 | 45180.02
PRC 3352322PD7900 | 2022-12-12 | Inv. 7382.54924600 |  | 51591.9 | 2274.04 | 8685.92 | 42905.98
PRC 3352322PE7900 | 2023-04-04 | Inv. 7382.55924600 |  | 51591.9 | 2252.86 | 10938.78 | 40653.12
PRC 3352322PF7900 | 2023-05-08 | Inv. 7382.56924600 |  | 51591.9 | 7830.52 | 18769.3 | 32822.6
PRC 3352322PG7900 | 2023-06-05 | Inv. 7382.57924600 |  | 51591.9 | 11662.57 | 30431.87 | 21160.03
PRC 3352322PH7900 | 2023-07-06 | Inv. 7382.58924600 FINAL | -8381.23 | 43210.67 | 12778.8 | 43210.67 | 0
|  |  |  | 43210.67 |  | 43210.67 | 0
|  |  |  | 43210.67 |  | 43210.67 | 0
|  |  |  | 43210.67 |  | 43210.67 | 0
|  |  |  | 43210.67 |  | 43210.67 | 0
|  | Total: | 43210.67 |  | 43210.67 |  | 0 | FINAL
|  | CM Services | 41024.26 |  | 41024.26 |  | 0
|  | Reimbursables | 2186.41 |  | 2186.41 |  | 0
|  | Total: | 43210.67 |  | 43210.67 |  | 0

## RECAP #9247.00
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
| Program code 924700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 170176.39
C | Boyd Jones Construction |  | 15034.96 | 15034.96 | 0
C | PM TIME |  | 12471.88 | 12471.88 | 0
C | Misc. |  | 74.95 | 74.95 | 0
C | Horizon Architecture |  | 13700 | 13700 | 0
C | Boyd Jones Construction 2 |  | 17794.6 | 17794.6 | 0
C | Koopman Roofing AKA Hopkins |  | 52400 | 52400 | 0
C | Advanced Environmental Inc. |  | 58700 | 58700 | 0
| Total Project Cost | 170176.39 | 170176.39 | 170176.39 | 0 | 0
CLOSED 01/08/2024

## #9247.00 Boyd Jones Constructio
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  | Major Program 4E02
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522117800 | 2022-04-27 | PO Procore | 16493.95 | 16493.95 |  |  | 16493.95
PRC 3352211PA7800 | 2022-06-15 | Inv. 9247.00-01 |  | 16493.95 | 2336.38 | 2336.38 | 14157.57
PRC 3352211PB7800 | 2022-06-22 | Inv. 9247.00-02 |  | 16493.95 | 990 | 3326.38 | 13167.57
PRC 3352211PC7800 | 2022-07-15 | Inv. 9247.00-03 |  | 16493.95 | 2367.32 | 5693.7 | 10800.25 | FY22
PO 33523117800 | 2022-08-09 | Rolled to FY23 | 0 | 16493.95 |  | 5693.7 | 10800.25
PRC 3352311PD7800 | 2022-08-22 | Inv. 9247.00-04 |  | 16493.95 | 1565 | 7258.7 | 9235.25
PRC 3352311PE7800 | 2022-09-14 | Inv. 9247.00-05 |  | 16493.95 | 1405 | 8663.7 | 7830.25
PRC 3352311PF7800 | 2022-10-12 | Inv. 9247.00-06 |  | 16493.95 | 2155 | 10818.7 | 5675.25
PRC 3352311PG7800 | 2022-11-08 | Inv. 9247.00-07 |  | 16493.95 | 1366.14 | 12184.84 | 4309.11
PRC 3352311PH7800 | 2022-12-07 | Inv. 9247.00-08 |  | 16493.95 | 1240.4 | 13425.24 | 3068.71
PRC 3352311PI7800 | 2023-01-10 | Inv. 9247.00-09 |  | 16493.95 | 1609.72 | 15034.96 | 1458.99
PO 33523117800 | 2023-06-28 | Close PO per PM | -1458.99 | 15034.96 |  | 15034.96 | 0
|  |  |  | 15034.96 |  | 15034.96 | 0
|  | Totals: | 15034.96 |  | 15034.96 |  | 0 | FINAL

## #9247.00 PM TIME
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZB
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11004.43 | 11004.43 |  |  | 11004.43
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 11004.43 | 100 | 100 | 10904.43
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 11004.43 | 100 | 200 | 10804.43
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 11004.43 | 50 | 250 | 10754.43
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 11004.43 | 600 | 850 | 10154.43
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 11004.43 | 100 | 950 | 10054.43
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 11004.43 | 100 | 1050 | 9954.43
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 11004.43 | 450 | 1500 | 9504.43
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 11004.43 | 200 | 1700 | 9304.43
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 11004.43 | -200 | 1500 | 9504.43
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 11004.43 | 220 | 1720 | 9284.43
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 11004.43 | 550 | 2270 | 8734.43
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 11004.43 | 220 | 2490 | 8514.43
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 11004.43 | 110 | 2600 | 8404.43
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 11004.43 | 55 | 2655 | 8349.43
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 293.02 | 11297.45 | 293.02 | 2948.02 | 8349.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 474.31 | 11771.76 | 474.31 | 3422.33 | 8349.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 146.03 | 11917.79 | 146.03 | 3568.36 | 8349.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 77.36 | 11995.15 | 77.36 | 3645.72 | 8349.43
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 44.12 | 12039.27 | 44.12 | 3689.84 | 8349.43
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 12039.27 | 360.41 | 4050.25 | 7989.02
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 12039.27 | 152.1 | 4202.35 | 7836.92
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 12039.27 | 1333.4 | 5535.75 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 51.05 | 12090.32 | 51.05 | 5586.8 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 246.51 | 12336.83 | 246.51 | 5833.31 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 379.94 | 12716.77 | 379.94 | 6213.25 | 6503.52
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | -379.94 | 12336.83 | -379.94 | 5833.31 | 6503.52
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 58.46 | 12395.29 | 58.46 | 5891.77 | 6503.52
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 12.11 | 12407.4 | 12.11 | 5903.88 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 10.56 | 12417.96 | 10.56 | 5914.44 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 53.92 | 12471.88 | 53.92 | 5968.36 | 6503.52
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 12471.88 | 174.99 | 6143.35 | 6328.53
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 12471.88 | 1061.12 | 7204.47 | 5267.41
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 12471.88 | 147.05 | 7351.52 | 5120.36
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 12471.88 | 646.84 | 7998.36 | 4473.52
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 12471.88 | 84.01 | 8082.37 | 4389.51
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 12471.88 | 495.7 | 8578.07 | 3893.81
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 12471.88 | 85.49 | 8663.56 | 3808.32
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 12471.88 | 599.5 | 9263.06 | 3208.82
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 12471.88 | 64.78 | 9327.84 | 3144.04
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 12471.88 | 539.3 | 9867.14 | 2604.74
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 12471.88 | 78.62 | 9945.76 | 2526.12
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 12471.88 | 500.9 | 10446.66 | 2025.22
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 12471.88 | 157.57 | 10604.23 | 1867.65
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 12471.88 | 878.8 | 11483.03 | 988.85
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 12471.88 | 30.33 | 11513.36 | 958.52
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 12471.88 | 211.1 | 11724.46 | 747.42
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 12471.88 | 89.82 | 11814.28 | 657.6
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 12471.88 | 657.6 | 12471.88 | 0
[5 empty] | 12471.88 |  | 12471.88 | 0
|  |  | Totals: | 12471.88 |  | 12471.88 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: PM Time Budget $Joni Carper, Douglas 11:49 AM (2 hours ago) to me 9247.00 PM Budget $3,000.00 9254.00 PM Budget $7,500.00 9256.00 PM Budget $4,800.00 9259.00 PM Budget $15,000.00 9261.00 PM Budget $10,000.00 Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative PM Time $Joni Carper, Douglas Oct 7, 2022, 3:27 PM (3 days ago) to me, Joni MM21 9270.00 Increase PM Time to $10,000.00. MM22 9247.00 Increase PM Time to $7,000.00. MM22 9230.00 Increase PM Time to $12,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9247.00 - DHS IMHI Storage Bldg Roof Replacement $Joni Elliott, Jennie 8:53 AM (16 minutes ago) to me Please increase PM time in contracted to a total of $20,000 in project 9247.00 - DHS IMHI Storage Bldg Roof Replacement. Project Closeout - 9247.00 DHS IMHI Storage Bldg Roof Replacement - MM22 $Joni Elliott, Jennie Jan 7, 2024, 1:47 PM (17 hours ago) to me, Scott, Jennifer Please reduce PM Time in project 9247.00 to a total Contracted amount of $11,724.46. Following this please close out the project and return remaining funds to the Total Unassigned/Unallocated line for MM22. Total of returned funds should be $132,038.49. Thank you, Jennie Elliott

## #9247.00 Misc
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523032800 | 2023-02-01 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV027153 | 74.95 | 74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
74.95
|  |  |  | Totals: |  | 74.95

## #9247.00 Horizon Architecture
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  | Major Program 4E02
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP924700-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523203803 | 2022-07-15 | PO Procore | 14650 | 14650 |  |  | 14650
PRC 3352320PA3803 | 2022-09-12 | Inv. 9247.00-01 |  | 14650 | 3280 | 3280 | 11370
PRC 3352320PB3803 | 2022-10-04 | Inv. 9247.00-02 |  | 14650 | 4600 | 7880 | 6770
PRC 3352320PC3803 | 2023-04-19 | Inv. 9247.00-03 |  | 14650 | 1020 | 8900 | 5750
PRC 3352320PD3803 | 2023-08-08 | Inv. 9247.00-04 |  | 14650 | 3600 | 12500 | 2150 | FY23
PO 33524203803 | 2023-08-14 | Roll to FY24 | 0 | 14650 |  | 12500 | 2150
PRC 3352420PE3803 | 2023-12-04 | Inv. 9247.00-05 - Final | -950 | 13700 | 1200 | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  |  |  | 13700 |  | 13700 | 0
|  | Totals: | 13700 |  | 13700 |  | 0 | Final
|  | Design Development Documents | 3280 |  | 3280 |  | 0
|  | Construction Documentation | 4600 |  | 4600 |  | 0
|  | Bidding/Negotiation Assistance | 1020 |  | 1020 |  | 0
|  | Construction Phase | 4800 |  | 4800 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Total: | 13700 |  | 13700 |  | 0

## #9247.00 Boyd Jones Constru (2)
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  | Major Program 4E02
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523355905 | 2022-12-20 | PO Procore | 19000.37 | 19000.37 |  |  | 19000.37
PRC 3352335PA5905 | 2023-02-14 | Inv. 9247.00-01A |  | 19000.37 | 2724.04 | 2724.04 | 16276.33
PRC 3352335PB5905 | 2023-03-20 | Inv. 9247.00-02A |  | 19000.37 | 1535.6 | 4259.64 | 14740.73
PRC 3352335PC5905 | 2023-04-12 | Inv. 9247.00-03A |  | 19000.37 | 2462.25 | 6721.89 | 12278.48
PRC 3352335PD5905 | 2023-05-22 | Inv. 9247.00-04A |  | 19000.37 | 2901.74 | 9623.63 | 9376.74
PRC 3352335PE5905 | 2023-06-28 | Inv. 9247.00-05A |  | 19000.37 | 3834.34 | 13457.97 | 5542.4
PRC 3352335PF5905 | 2023-07-11 | Inv. 9247.00-06A |  | 19000.37 | 2043.84 | 15501.81 | 3498.56 | FY23
PO 33524355905 | 2023-07-26 | Rolled to FY24 | 0 | 19000.37 |  | 15501.81 | 3498.56
PRC 3352435PG5905 | 2023-08-21 | Inv. 9247.00-07A |  | 19000.37 | 1207.29 | 16709.1 | 2291.27
PRC 3352435PH5905 | 2023-09-29 | Inv. 9247.00-08A - Final | -1205.77 | 17794.6 | 1085.5 | 17794.6 | 0
|  |  |  | 17794.6 |  | 17794.6 | 0
|  |  |  | 17794.6 |  | 17794.6 | 0
|  |  |  | 17794.6 |  | 17794.6 | 0
|  | Totals: | 17794.6 |  | 17794.6 |  | 0 | FINAL

## #9247.00 Koopman Roofing
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  | Major Program 4E02
Koopman Roofing/Hopkins |  |  | Vendor: 00003054888
Acct. Codes-0017-335-MM22-9255 |  |  | RFB924700 01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523095901 | 2023-04-04 | PO Procore | 52400 | 52400 |  |  | 52400
PRC 3352309PA5901 | 2023-06-01 | Inv. 9247.00-01 |  | 52400 | 49779.99 | 49779.99 | 2620.01 | 2620.01
PRC 3352309PB5901 | 2023-08-31 | Inv. 9247.00-02 - Retainage |  | 52400 | 2620.01 | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  |  |  | 52400 |  | 52400 | 0
|  | Totals: | 52400 |  | 52400 |  | 0 | FINAL

## #9247.00 Advanced Environmental
DHS IMHI Storage Bldg Roof Replacement
Project # 9247.00
Program code 924700 |  |  | Major Program 4E02
Advanced Environmental Inc. |  |  | Vendor: 00002125877
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ924700-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523111804 | 2023-04-21 | PO Procore | 58700 | 58700 |  |  | 58700
PRC 3352311PA1804 | 2023-07-21 | Inv. 9247.00-001 |  | 58700 | 55765 | 55765 | 2935 | 2935
PRC 3352311PB1804 | 2023-08-31 | Inv. 9247.00-002 - Retainage |  | 58700 | 2935 | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  |  |  | 58700 |  | 58700 | 0
|  | Totals: | 58700 |  | 58700 |  | 0 | FINAL

## RECAP #9248.00
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
| Program code 924800 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 183186.71
C | Story Construction |  | 26420.64 | 26420.64 | 0
C | PM TIME |  | 16291.46 | 16291.46 | 0
C | Misc. |  | 1875.04 | 1875.04 | 0
C | Shive Hattery |  | 53232 | 53232 | 0
C | Story Construction(2) |  | 35142.02 | 35142.02 | 0
C | MTS Contracting |  | 50225.55 | 50225.55 | 0
| Total Project Cost | 183186.71 | 183186.71 | 183186.71 | 0 | 0
Closed 03/08/24

## #9248.00 Story Construction
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  | Major Program 4E10
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B: RFP0215335062-Story9112015
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522350901 | 2021-12-14 | PO Procore | 12670.1 | 12670.1 |  |  | 12670.1
PRC 3352235PA0901 | 2022-01-18 | Inv. 32947 |  | 12670.1 | 390 | 390 | 12280.1
PRC 3352235PB0901 | 2022-03-22 | Inv. 33033 |  | 12670.1 | 1190 | 1580 | 11090.1
PRC 3352235PC0901 | 2022-04-28 | Inv. 33079 |  | 12670.1 | 925 | 2505 | 10165.1
PRC 3352235PD0901 | 2022-05-19 | Inv. 33122 |  | 12670.1 | 785 | 3290 | 9380.1
PRC 3352235PE0901 | 2022-06-20 | Inv. 33167 |  | 12670.1 | 1365 | 4655 | 8015.1
PO 33522350901 | 2022-07-26 | CO #1 | 3741.5 | 16411.6 |  | 4655 | 11756.6
PRC 3352235PF0901 | 2022-08-01 | Inv. 33233 |  | 16411.6 | 5396.5 | 10051.5 | 6360.1 | FY22
PO 33523350901 | 2022-08-09 | Rolled to FY23 | 0 | 16411.6 |  | 10051.5 | 6360.1
PO 3352335PG0901 | 2022-08-24 | Inv. 33277 |  | 16411.6 | 2215 | 12266.5 | 4145.1
PO 33523350901 | 2022-09-01 | CO #2 | 3853.01 | 20264.61 |  | 12266.5 | 7998.11
PO 3352335PH0901 | 2022-09-20 | Inv. 33342 |  | 20264.61 | 2055.14 | 14321.64 | 5942.97
PO 3352335PI0901 | 2022-10-17 | Inv. 33401 |  | 20264.61 | 2135 | 16456.64 | 3807.97
PO 33523350901 | 2022-11-18 | CO #3 | 6389 | 26653.61 |  | 16456.64 | 10196.97
PRC 3352335PJ0901 | 2022-11-21 | Inv. 33458 |  | 26653.61 | 3575 | 20031.64 | 6621.97
PRC 3352335PK0901 | 2022-12-20 | Inv. 33513-Final | -232.97 | 26420.64 | 6389 | 26420.64 | 1.1653e-12
|  |  |  | 26420.64 |  | 26420.64 | 1.1653e-12
|  |  |  | 26420.64 |  | 26420.64 | 1.1653e-12
|  | Totals: | 26420.64 |  | 26420.64 |  | 0 | Final
|  | CM Services | 12440 |  | 12440 |  | 0
|  | Reimbursables | 10.14 |  | 10.14 |  | 0
|  | CO #1 | 3741.5 |  | 3741.5 |  | 0
|  | CO #2 | 3840 |  | 3840 |  | 0
|  | CO #3 | 6389 |  | 6389 |  | 0
|  | Total: | 26420.64 |  | 26420.64 |  | 0

## #9248.00 PM TIME
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZC
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12827.73 | 12827.73 |  |  | 12827.73
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 12827.73 | 400 | 400 | 12427.73
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 12827.73 | 200 | 600 | 12227.73
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 12827.73 | 175 | 775 | 12052.73
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 12827.73 | 475 | 1250 | 11577.73
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 12827.73 | 375 | 1625 | 11202.73
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 12827.73 | 375 | 2000 | 10827.73
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 12827.73 | 325 | 2325 | 10502.73
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 12827.73 | 425 | 2750 | 10077.73
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 12827.73 | 450 | 3200 | 9627.73
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 12827.73 | -450 | 2750 | 10077.73
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 12827.73 | 495 | 3245 | 9582.73
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 12827.73 | 1265 | 4510 | 8317.73
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12827.73 | 302.5 | 4812.5 | 8015.23
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12827.73 | 1100 | 5912.5 | 6915.23
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 12827.73 | 165 | 6077.5 | 6750.23
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 439.09 | 13266.82 | 439.09 | 6516.59 | 6750.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1167.88 | 14434.7 | 1167.88 | 7684.47 | 6750.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 188.82 | 14623.52 | 188.82 | 7873.29 | 6750.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 864.7 | 15488.22 | 864.7 | 8737.99 | 6750.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 165.11 | 15653.33 | 165.11 | 8903.1 | 6750.23
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 15653.33 | 220.41 | 9123.51 | 6529.82
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 15653.33 | 5.2 | 9128.71 | 6524.62
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 15653.33 | 45.6 | 9174.31 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 114.5 | 15767.83 | 114.5 | 9288.81 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 329.44 | 16097.27 | 329.44 | 9618.25 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 78.46 | 16175.73 | 78.46 | 9696.71 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 47.6 | 16223.33 | 47.6 | 9744.31 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 35.15 | 16258.48 | 35.15 | 9779.46 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 32.98 | 16291.46 | 32.98 | 9812.44 | 6479.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 16291.46 | 104.94 | 9917.38 | 6374.08
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 16291.46 | 636.33 | 10553.71 | 5737.75
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 16291.46 | 70.95 | 10624.66 | 5666.8
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 16291.46 | 312.05 | 10936.71 | 5354.75
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 16291.46 | 23.28 | 10959.99 | 5331.47
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 16291.46 | 137 | 11096.99 | 5194.47
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 16291.46 | 16.29 | 11113.28 | 5178.18
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 16291.46 | 113.3 | 11226.58 | 5064.88
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 16291.46 | 31.33 | 11257.91 | 5033.55
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 16291.46 | 275.6 | 11533.51 | 4757.95
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 16291.46 | 26.01 | 11559.52 | 4731.94
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 16291.46 | 164.8 | 11724.32 | 4567.14
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 16291.46 | 25.33 | 11749.65 | 4541.81
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 16291.46 | 142.1 | 11891.75 | 4399.71
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 16291.46 | 112.01 | 12003.76 | 4287.7
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 16291.46 | 776.1 | 12779.86 | 3511.6
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 16291.46 | 114.12 | 12893.98 | 3397.48
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 16291.46 | 914.6 | 13808.58 | 2482.88
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 16291.46 | 134.1 | 13942.68 | 2348.78
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 16291.46 | 1015.8 | 14958.48 | 1332.98
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 16291.46 | 32.11 | 14990.59 | 1300.87
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 16291.46 | 234 | 15224.59 | 1066.87
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 16291.46 | 49.16 | 15273.75 | 1017.71
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 16291.46 | 436.2 | 15709.95 | 581.51
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 16291.46 | 96.11 | 15806.06 | 485.4
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 16291.46 | 485.4 | 16291.46 | 0
[5 empty] | 16291.46 |  | 16291.46 | 0
[5 empty] | 16291.46 |  | 16291.46 | 0
[5 empty] | 16291.46 |  | 16291.46 | 0
|  |  | Totals: | 16291.46 |  | 16291.46 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Changes Inbox Kleene, Jennifer 12:20 PM (1 hour ago) to me, Scott MM23 9268.01 Please increase the PM Time budget by $7,480.00. MM22 9248.00 Please increase the PM Time budget by $2,992.00. MM22 9279.30 Please increase the PM Time budget by $7,480.00. Regards, Jennifer PM Time Budget Increases $Joni Kleene, Jennifer 11:04 AM (5 minutes ago) to me, Scott Please make the following changes to the PM Time Budgets MM22 Project 9248.00 increase the PM time by $1,200.00 MM21 Project 9326.00 increase the PM time by $400.00 DA23 Project 9345.00 increase the PM time by $5.000.00 Regards,

## #9248.00 Misc
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523249802 | 2022-09-06 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2447933 - Final | 1708.75 | 1708.75
GAX 33523336811 | 2022-12-05 | 9500 | CNST | Rapid Reproductions V# (00002111375) | Inv. 420234-0 | 166.29 | 1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
1875.04
|  |  |  | Totals: |  | 1875.04

## #9248.00 Shive Hattery
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  | Major Program 4E10
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 924800-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522088902 | 2022-03-29 | PO Procore | 54432 | 54432 |  |  | 54432
PRC 3352208PA8902 | 2022-05-04 | Inv. 2142202230-1 |  | 54432 | 11852.5 | 11852.5 | 42579.5
PRC 3352208PB8902 | 2022-05-31 | Inv. 2142202230-2 |  | 54432 | 16099.7 | 27952.2 | 26479.8
PRC 3352208PC8902 | 2022-06-30 | Inv. 2142202230-3 |  | 54432 | 4573 | 32525.2 | 21906.8 | FY22
PO 33523088902 | 2022-08-09 | Rolled to FY23 | 0 | 54432 |  | 32525.2 | 21906.8
PRC 3352308PD8902 | 2022-08-11 | Inv. 2142202230-4 |  | 54432 | 6402.2 | 38927.4 | 15504.6
PRC 3352308PE8902 | 2022-09-30 | Inv. 2142202230-5 |  | 54432 | 914.6 | 39842 | 14590
PRC 3352308PF8902 | 2022-10-28 | Inv. 2142202230-6 |  | 54432 | 3540 | 43382 | 11050
PRC 3352308PG8902 | 2023-03-03 | Inv. 2142202230-7 |  | 54432 | 1105 | 44487 | 9945
PO 33523088902 | 2023-03-13 | CO #1 | -1200 | 53232 |  | 44487 | 8745
PRC 3352308PH8902 | 2023-03-23 | Inv. 2142202230-8 |  | 53232 | 1105 | 45592 | 7640
PRC 3352308PI8902 | 2023-06-05 | Inv. 2142202230-9 |  | 53232 | 1105 | 46697 | 6535 | FY23
PO 33524088902 | 2023-07-25 | Roll to FY24 | 0 | 53232 |  | 46697 | 6535
PRC 3352408PJ8902 | 2023-10-03 | Inv. 2142202230-10 |  | 53232 | 126 | 46823 | 6409
PRC 3352408PK8902 | 2023-11-07 | Inv. 2142202230-11 |  | 53232 | 1436.5 | 48259.5 | 4972.5
PRC 3352408PL8902 | 2023-12-06 | Inv. 2142202230-12 |  | 53232 | 1105 | 49364.5 | 3867.5
PRC 3352408PM8902 | 2024-01-04 | Inv. 2142202230-13 |  | 53232 | 3315 | 52679.5 | 552.5
PRC 3352408PN8902 | 2024-02-15 | Inv. 2142202230-14FINAL |  | 53232 | 552.5 | 53232 | 0
|  |  |  | 53232 |  | 53232 | 0
|  | Totals: | 53232 |  | 53232 |  | 0 | FINAL
|  | Design Development Documents | 21550 |  | 21550 |  | 0
|  | Construction Documents | 18292 |  | 18292 |  | 0
|  | Bidding Phase | 3540 |  | 3540 |  | 0
|  | Construction Phase | 11050 |  | 11050 |  | 0
|  | CO #1 | -1200 |  | -1200 |  | 0
|  | Total: | 53232 |  | 53232 |  | 0

## #9248.00 Story Construction (2)
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  | Major Program 4E10
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523299901 | 2022-10-25 | PO Procore | 47561.81 | 47561.81 |  |  | 47561.81
PRC 3352329PA9901 | 2022-12-20 | Inv. 33514 |  | 47561.81 | 3527.98 | 3527.98 | 44033.83
PRC 3352329PB9901 | 2023-03-20 | Inv. 33681 |  | 47561.81 | 3412.94 | 6940.92 | 40620.89
PRC 3352329PC9901 | 2023-04-19 | Inv. 33727 |  | 47561.81 | 1758.44 | 8699.36 | 38862.45
PRC 3352329PD9901 | 2023-05-22 | Inv. 33782 |  | 47561.81 | 2106.3 | 10805.66 | 36756.15
PRC 3352329PE9901 | 2023-06-21 | Inv. 33831 |  | 47561.81 | 687.81 | 11493.47 | 36068.34
PRC 3352329PF9901 | 2023-07-19 | Inv. 33889 |  | 47561.81 | 2484.38 | 13977.85 | 33583.96 | FY23
PO 33524299901 | 2023-07-25 | Roll to FY24 | 0 | 47561.81 |  | 13977.85 | 33583.96
PRC 3352429PG9901 | 2023-08-21 | Inv. 33947 |  | 47561.81 | 1758.44 | 15736.29 | 31825.52
PRC 3352429PH9901 | 2023-09-18 | Inv. 34001 |  | 47561.81 | 1302.54 | 17038.83 | 30522.98
PRC 3352429PI9901 | 2023-10-13 | Inv. 34062 |  | 47561.81 | 2153.99 | 19192.82 | 28368.99
PRC 3352429PJ9901 | 2023-11-17 | Inv. 34115 |  | 47561.81 | 6529.55 | 25722.37 | 21839.44
PRC 3352429PK9901 | 2023-12-15 | Inv. 34156 |  | 47561.81 | 3596.33 | 29318.7 | 18243.11
PRC 3352429PL9901 | 2024-01-18 | Inv. 34203 |  | 47561.81 | 3751.97 | 33070.67 | 14491.14
PRC 3352429PM9901 | 2024-02-19 | Inv. 34245-Final | -12419.79 | 35142.02 | 2071.35 | 35142.02 | 0
|  |  |  | 35142.02 |  | 35142.02 | 0
|  |  |  | 35142.02 |  | 35142.02 | 0
|  |  |  | 35142.02 |  | 35142.02 | 0
|  | Totals: | 35142.02 |  | 35142.02 |  | 0 | FINAL
|  | CM Services | 35112.52 |  | 35112.52 |  | 0
|  | Reimbursables | 29.5 |  | 29.5 |  | 0
|  | Total: | 35142.02 |  | 35142.02 |  | 0

## #9248.00 MTS Contracting
DHS WRC Administration, Birches and Linden Court Tuckpointing
Project # 9248.00
Program code 924800 |  |  | Major Program 4E10
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM22-9255 |  |  | 924800-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523307902 | 2022-10-31 | PO Procore | 423180 | 423180 |  |  | 423180
PRC 3352330PA7902 | 2023-07-21 | Inv. 22-4612A |  | 423180 | 50225.55 | 50225.55 | 372954.45 | 2643.45 | FY23
PO 33524307902 | 2023-07-25 | Roll to FY24 | 0 | 423180 |  | 50225.55 | 372954.45
PRC 3352430PB7902 | 2023-08-14 | Inv. 22-4612B |  | 423180 | 11658.87 | 61884.42 | 361295.58 | 3257.08
PRC 3352430PC7902 | 2023-09-15 | Inv. 22-4612C |  | 423180 | 82063.85 | 143948.27 | 279231.73 | 7576.23
PRC 33524307902 | 2023-11-03 | CO #1 | 1960 | 425140 |  | 143948.27 | 281191.73
PRC 3352430PD7902 | 2023-11-16 | Inv. 22-4612D |  | 425140 | 246812.85 | 390761.12 | 34378.88 | 20566.38
PRC 3352430PE7902 | 2024-01-04 | Inv. 22-4612E |  | 425140 | 9103.37 | 399864.49 | 25275.51 | 21045.51
PRC 3352430PF7902 | 2024-02-02 | Inv. 22-4612F |  | 425140 | 4018.5 | 403882.99 | 21257.01 | 21257.01
PRC 3352430PG7902 | 2024-02-12 | Inv. 22-4612Retainage |  | 425140 | 21257.01 | 425140 | 0
CDE 33524135905 | 2024-05-14 | Moving Expennses from MM22 to MM21 | -374914.45 | 50225.55 | -374914.45 | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  |  |  | 50225.55 |  | 50225.55 | 0
|  | Totals: | 50225.55 |  | 50225.55 |  | 0

## RECAP #9249.00
DOC MPCF Front Steps Repair
Project # 9249.00
| Program code 924900 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 500102.67
C | McGough Construction |  | 19642.9 | 19642.9 | 0
C | PM TIME |  | 32416.36 | 32416.36 | 0
C | Misc. |  | 946.18 | 946.18 | 0
C | Shive Hattery |  | 65854 | 65854 | 0
C | Controlled Asbestos |  | 0 | 0 | 0
C | Tricon General |  | 314772.73 | 314772.73 | 0
C | McGough CA |  | 64736 | 64736 | 0
C | Terracon Consultants |  | 1734.5 | 1734.5 | 0
| Total Project Cost | 500102.67 | 500102.67 | 500102.67 | 0 | 0
Closed 03/07/25

## #9249.00 McGough Construction
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522363800 | 2021-12-27 | PO Procore | 19702.01 | 19702.01 |  |  | 19702.01
PRC 3352236PA3800 | 2022-04-12 | Inv. 9249.00-01 |  | 19702.01 | 1495 | 1495 | 18207.01
PRC 3352236PB3800 | 2022-05-27 | Inv. 9249.00.001-2 |  | 19702.01 | 713.56 | 2208.56 | 17493.45
PRC 3352236PC3800 | 2022-06-10 | Inv. 9249.00-001-3 |  | 19702.01 | 1382.5 | 3591.06 | 16110.95
PRC 3352236PD3800 | 2022-07-11 | Inv. 9249.00-001-4 |  | 19702.01 | 765.29 | 4356.35 | 15345.66 | FY22
PO 33523363800 | 2022-08-09 | Rolled to FY23 | 0 | 19702.01 |  | 4356.35 | 15345.66
PRC 3352336PE3800 | 2022-08-11 | Inv. 9249.00-001-5 |  | 19702.01 | 1255 | 5611.35 | 14090.66
PRC 3352336PF3800 | 2022-09-08 | Inv. 9249.00-001.6 |  | 19702.01 | 475 | 6086.35 | 13615.66
PRC 3352336PG3800 | 2022-10-10 | Inv. 9249.00.001-7 |  | 19702.01 | 2600.05 | 8686.4 | 11015.61
PRC 3352336PH3800 | 2022-11-13 | Inv. 9249.00.001-8 |  | 19702.01 | 515 | 9201.4 | 10500.61
PRC 3352336PI3800 | 2022-12-09 | Inv. 100877.002-9 |  | 19702.01 | 1074 | 10275.4 | 9426.61
PRC 3352336PJ3800 | 2023-01-16 | Inv. 100877.002PC10 |  | 19702.01 | 477.5 | 10752.9 | 8949.11
PRC 3352336PK3800 | 2023-03-13 | Inv. 100877.002PC11 |  | 19702.01 | 1781.5 | 12534.4 | 7167.61
PRC 3352336PL3800 | 2023-04-07 | Inv. 100877.002-12 |  | 19702.01 | 427.5 | 12961.9 | 6740.11
PRC 3352336PM3800 | 2023-05-08 | Inv. 100877.002-13 |  | 19702.01 | 1154.5 | 14116.4 | 5585.61
PRC 3352336PN3800 | 2023-06-15 | Inv. 100877.002-14 |  | 19702.01 | 1166.5 | 15282.9 | 4419.11
PRC 3352336PO3800 | 2023-07-02 | Inv. 100877.002-15 |  | 19702.01 | 2800 | 18082.9 | 1619.11 | FY23
PO 33524363800 | 2023-08-11 | Rolled to FY24 | 0 | 19702.01 |  | 18082.9 | 1619.11
PRC 3352436PP3800 | 2023-08-21 | Inv. 100877.016 FINAL | -59.11 | 19642.9 | 1560 | 19642.9 | -3.0553e-12
|  |  |  | 19642.9 |  | 19642.9 | -3.0553e-12
|  |  |  | 19642.9 |  | 19642.9 | -3.0553e-12
|  | Total: | 19642.9 |  | 19642.9 |  | 0 | FINAL
|  | CM Services | 19162.5 |  | 19162.5 |  | 0
|  | Reimbursables | 480.4 |  | 480.4 |  | 0
|  | Total: | 19642.9 |  | 19642.9 |  | 0

## #9249.00 PM TIME
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZD
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount (James Trower: $6,000 & Josh Herman: $2,000) | 30362.11 | 30362.11 |  |  | 30362.11
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 30362.11 | 575 | 575 | 29787.11
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 30362.11 | 500 | 1075 | 29287.11
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 30362.11 | 900 | 1975 | 28387.11
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 30362.11 | 1050 | 3025 | 27337.11
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 30362.11 | 500 | 3525 | 26837.11
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 30362.11 | 450 | 3975 | 26387.11
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 30362.11 | 725 | 4700 | 25662.11
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 30362.11 | 750 | 5450 | 24912.11
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 30362.11 | 575 | 6025 | 24337.11
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 30362.11 | -575 | 5450 | 24912.11
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 30362.11 | 632.5 | 6082.5 | 24279.61
CDE 33523230900 | 2022-08-18 | 9500 | Moving PM Time expense from DA22 9243.00 |  | 30362.11 | 125 | 6207.5 | 24154.61
CDE 33523236901 | 2022-08-24 | 9500 | Moving PM Time expense from DA22 9243.00 |  | 30362.11 | 12.5 | 6220 | 24142.11
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 30362.11 | 302.5 | 6522.5 | 23839.61
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 30362.11 | 275 | 6797.5 | 23564.61
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 30362.11 | 385 | 7182.5 | 23179.61
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 30362.11 | 247.5 | 7430 | 22932.11
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 433.44 | 30795.55 | 433.44 | 7863.44 | 22932.11
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 257.22 | 31052.77 | 257.22 | 8120.66 | 22932.11
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 148 | 31200.77 | 148 | 8268.66 | 22932.11
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 281.11 | 31481.88 | 281.11 | 8549.77 | 22932.11
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 189.73 | 31671.61 | 189.73 | 8739.5 | 22932.11
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 31671.61 | 774.96 | 9514.46 | 22157.15
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 31671.61 | 77.6 | 9592.06 | 22079.55
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 31671.61 | 680.28 | 10272.34 | 21399.27
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 262.46 | 31934.07 | 262.46 | 10534.8 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 194.49 | 32128.56 | 194.49 | 10729.29 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 94.57 | 32223.13 | 94.57 | 10823.86 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 30.74 | 32253.87 | 30.74 | 10854.6 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 46.55 | 32300.42 | 46.55 | 10901.15 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 115.94 | 32416.36 | 115.94 | 11017.09 | 21399.27
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 32416.36 | 160.35 | 11177.44 | 21238.92
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 32416.36 | 972.34 | 12149.78 | 20266.58
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 32416.36 | 112.65 | 12262.43 | 20153.93
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 32416.36 | 495.48 | 12757.91 | 19658.45
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 32416.36 | 147.07 | 12904.98 | 19511.38
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 32416.36 | 866.9 | 13771.88 | 18644.48
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 32416.36 | 82.31 | 13854.19 | 18562.17
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 32416.36 | 573.1 | 14427.29 | 17989.07
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 32416.36 | -43.2 | 14384.09 | 18032.27
CDE 33523195800 | 2023-07-14 | 2507 | Finance Support for June 1-30, 2023 (Move Expense from MM23) |  | 32416.36 | 118.98 | 14503.07 | 17913.29
CDE 33523195800 | 2023-07-14 | 9500 | DAS Services for June 1-30, 2023 (Move Expense from MM23) |  | 32416.36 | 1079.7 | 15582.77 | 16833.59
CDE 33524222806 | 2023-08-10 | 2507 | Finance Support for July 1-31, 2023 (Move Expense to MM23) |  | 32416.36 | 42.45 | 15625.22 | 16791.14
CDE 33524222806 | 2023-08-10 | 9500 | DAS Services for July 1-31, 2023 (Move Expense to MM23) |  | 32416.36 | 271.7 | 15896.92 | 16519.44
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 32416.36 | 124.87 | 16021.79 | 16394.57
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 32416.36 | 700.1 | 16721.89 | 15694.47
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 32416.36 | 51.77 | 16773.66 | 15642.7
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 32416.36 | 362.6 | 17136.26 | 15280.1
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 32416.36 | 37.03 | 17173.29 | 15243.07
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 32416.36 | 295.6 | 17468.89 | 14947.47
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 32416.36 | 24.65 | 17493.54 | 14922.82
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 32416.36 | 186.7 | 17680.24 | 14736.12
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 32416.36 | 81.77 | 17762.01 | 14654.35
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 32416.36 | 600.6 | 18362.61 | 14053.75
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 32416.36 | 45.68 | 18408.29 | 14008.07
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 32416.36 | 399.6 | 18807.89 | 13608.47
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 32416.36 | 129.73 | 18937.62 | 13478.74
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 32416.36 | 654.1 | 19591.72 | 12824.64
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 32416.36 | 67.87 | 19659.59 | 12756.77
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 32416.36 | 511.4 | 20170.99 | 12245.37
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 32416.36 | 137.37 | 20308.36 | 12108
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 32416.36 | 1222.5 | 21530.86 | 10885.5
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 32416.36 | 150.05 | 21680.91 | 10735.45
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 32416.36 | 1255.1 | 22936.01 | 9480.35
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 32416.36 | 148.26 | 23084.27 | 9332.09
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 32416.36 | 1356.3 | 24440.57 | 7975.79
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 32416.36 | 123.34 | 24563.91 | 7852.45
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 32416.36 | 1349.5 | 25913.41 | 6502.95
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 32416.36 | 292.25 | 26205.66 | 6210.7
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 32416.36 | 1486.4 | 27692.06 | 4724.3
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 32416.36 | 118.75 | 27810.81 | 4605.55
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 32416.36 | 1057.4 | 28868.21 | 3548.15
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 32416.36 | 164.27 | 29032.48 | 3383.88
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 32416.36 | 1094.8 | 30127.28 | 2289.08
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 32416.36 | 84.04 | 30211.32 | 2205.04
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 32416.36 | 560 | 30771.32 | 1645.04
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 32416.36 | 25.87 | 30797.19 | 1619.17
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 32416.36 | 259.9 | 31057.09 | 1359.27
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 32416.36 | 61.87 | 31118.96 | 1297.4
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 32416.36 | 653.8 | 31772.76 | 643.6
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 32416.36 | 120.9 | 31893.66 | 522.7
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 32416.36 | 522.7 | 32416.36 | -2.6148e-12
[5 empty] | 32416.36 |  | 32416.36 | -2.6148e-12
|  |  | Totals: | 32416.36 |  | 32416.36 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: Fwd: MM22 PM Time Inbox Trower, James 9:31 AM (4 minutes ago) to me, Scott, Josh Jennifer - I want to clarify that I am requesting DAS Finance to set up PM Time for the following new projects (Josh Herman and I will both have PM Time on 9249.00 and 9250.00): 9249.00 - DOC MPCF Front Steps Repair: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9250.00 - DOC MPCF Building 18 Roof Replacement: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9251.00 - DPS P09 Parking Lot Replacement: $4,000 (James Trower: $4,000) 9252.00 - DPS P09 Window Replacement: $4,000 (James Trower: $4,000) 9258.00 - DAS CC Hoover East Side Ice Mitigation: $4,000 (James Trower: $4,000) Please call me at 515-380-8049 when you have a moment. Thanks, James PM Time - James Trower $Joni Trower, James 3:10 PM (3 minutes ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Increase PM Time by $5,000 9201.00 - DAS CC Ola Babcock Miller Tuckpointing (MM20): Increase PM Time by $1,100 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22): Increase PM Time by $6,000 9249.00 - DOC MPCF Front Steps Repair (MM22): Increase PM Time by $6,000 9251.00 - DPS P09 Parking Lot Replacement (MM22): Increase PM Time by $3,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Re: PM Time $John Trower, James Jul 13, 2023, 4:36 PM (16 hours ago) to me, John John - The PM Time billed for project 9249.00 should have been billed to MM22. Please increase the MM22 PM Time by $5,000. There should be zero funding in MM23 for this project. Thanks, James Adams, Brandon 1:42 PM (0 minutes ago) to me Finance, Please increase the follow PM Time, 9249.00 in MM22 increase by $4,000 9224.00 in MM23 increase by $1,000 9370.00 in MM23 increase by $3,000 Regards Re: PM Time Inbox Adams, Brandon 7:46 AM (59 minutes ago) to me Please increase PM Time budget $5000 for 9249.00 MM22. Regards, From: Adams, Brandon <brandon.adams@iowa.gov> Date: Tue, Nov 12, 2024 at 11:19 AM Subject: Re: October PM Time Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Please increase my PM Time on the following projects: DA24 9414.00 $5,000 DA24 9423.00 $5,000 MM22 9429.00 $2,000 MM22 9387.00 $4,000 MM23 9317.00 $4,000

## #9249.00 Misc
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522033904 | 2022-02-02 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV017595 | 14.75 | 14.75
GAX 33523258902 | 2022-09-14 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2447763-Final | 797.5 | 812.25
PRC 33523187900 | 2023-06-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV031129 | 133.93 | 946.18
946.18
946.18
946.18
946.18
946.18
946.18
946.18
946.18
946.18
|  |  |  | Totals: |  | 946.18

## #9249.00 Shive Hattery
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP 924900-002
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522157803 | 2022-06-06 | PO Procore | 46314 | 46314 |  |  | 46314
PRC 3352215PA7803 | 2022-07-07 | Inv. 2142203500-1 |  | 46314 | 2952 | 2952 | 43362 | FY22
PO 33523157803 | 2022-08-09 | Rolled to FY23 | 0 | 46314 |  | 2952 | 43362
PRC 3352315PB7803 | 2022-09-15 | Inv. 2142203500-2 |  | 46314 | 14819.4 | 17771.4 | 28542.6
PRC 3352315PC7803 | 2022-10-07 | Inv. 2142203500-3 |  | 46314 | 6857 | 24628.4 | 21685.6
PO 33523157803 | 2022-11-17 | CO #1 | 19540 | 65854 |  | 24628.4 | 41225.6
PRC 3352315PD7803 | 2023-02-03 | Inv. 2142203500-4 |  | 65854 | 21700.2 | 46328.6 | 19525.4
PO 33523157803 | 2023-03-24 | CO #2 (No Cost) | 0 | 65854 |  | 46328.6 | 19525.4
PRC 3352315PE7803 | 2023-04-12 | Inv. 2142203500-5 |  | 65854 | 3325.4 | 49654 | 16200
PRC 3352315PF7803 | 2023-07-10 | Inv. 2142203500-6 |  | 65854 | 2600 | 52254 | 13600 | FY23
PO 33524157803 | 2023-08-10 | Rolled to FY24 | 0 | 65854 |  | 52254 | 13600
PRC 3352415PG7803 | 2023-11-03 | Inv. 2142203500-7 |  | 65854 | 1632 | 53886 | 11968
PRC 3352415PH7803 | 2024-03-18 | Inv. 2142203500-8 |  | 65854 | 952 | 54838 | 11016
PRC 3352415PI7803 | 2024-04-25 | Inv. 2142203500-9 |  | 65854 | 1088 | 55926 | 9928
PRC 3352415PJ7803 | 2024-06-07 | Inv. 2142203500-10 |  | 65854 | 3536 | 59462 | 6392
PRC 3352415PK7803 | 2024-07-08 | Inv. 2142203500-11 |  | 65854 | 3536 | 62998 | 2856 | FY24
PO 33525157803 | 2024-07-19 | Roll to FY25 |  | 65854 |  | 62998 | 2856
PRC 3352515PL7803 | 2024-09-13 | Inv. 2142203500-12 |  | 65854 | 680 | 63678 | 2176
PRC 3352515PM7803 | 2024-10-25 | Inv. 2142203500-13 |  | 65854 | 1632 | 65310 | 544
PRC 3352515PN7803 | 2025-02-24 | Inv. 2142203500-14-FINAL |  | 65854 | 544 | 65854 | 0
|  |  |  | 65854 |  | 65854 | 0
|  |  |  | 65854 |  | 65854 | 0
|  | Total: | 65854 |  | 65854 |  | 0 | FINAL
|  | Design Development | 16400 |  | 16400 |  | 0
|  | Construction Documents | 13714 |  | 13714 |  | 0
|  | Bidding Assistance (2022) | 2600 |  | 2600 |  | 0
|  | Construction Phase (2023) | 13600 |  | 13600 |  | 0
|  | CO #1 | 19540 |  | 19540 |  | 0
|  | Total: | 65854 |  | 65854 |  | 0

## #9249.00 Controlled Asbestos
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | MA21060
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523055902 | 2023-02-24 | DO Procore(Discard PO in I-3) | 0 | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Total: | 0 |  | 0 |  | 0
|  | Line 5 2m X 2d = 32hrs x 58 | 0 |  |  |  | 0
|  | Line 5 Drive 2m x 5hrs/day x 2d=20 hrs 58 | 0 |  |  |  | 0
|  | Line 11 Landfill | 0 |  |  |  | 0
|  | Line 12 Mileage 280 Miles RT x 2 Trips x.39 | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9249.00 Tricon General
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Tricon General |  |  | Vendor: 00002124028
Acct. Codes-0017-335-MM22-9255 |  |  | RFP 924900-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523187909 | 2023-06-30 | PO Procore | 307000 | 307000 |  |  | 307000 |  | FY23
PO 33524187909 | 2023-08-11 | Rolled to FY24 | 0 | 307000 |  | 0 | 307000
PRC 3352418PA7909 | 2024-04-02 | Inv. 9249.00 AIA #1 |  | 307000 | 5055.9 | 5055.9 | 301944.1 | 266.1
PO 33524187909 | 2024-05-03 | CO #1 | 5028.41 | 312028.41 |  | 5055.9 | 306972.51
PRC 3352418PB7909 | 2024-05-13 | Inv. 9249.00 AIA #2 |  | 312028.41 | 32879.23 | 37935.13 | 274093.28 | 1996.28
PRC 3352418PC7909 | 2024-05-20 | Overpayment of Invoice 2 by $6 this one balances it in Procore |  | 312028.41 | 0 | 37935.13 | 274093.28 | 1996.28
PRC 3352418PD7909 | 2024-07-16 | Inv. 9249.00 AIA #3R |  | 312028.41 | 156636.49 | 194571.62 | 117456.79 | 10240.33 | FY24
PO 33525187909 | 2024-07-19 | Roll to FY25 |  | 312028.41 |  | 194571.62 | 117456.79
PO 33525187909 | 2024-08-09 | CO #2 | 1534.34 | 313562.75 |  | 194571.62 | 118991.13
PRC 3352518PE7909 | 2024-09-06 | Inv. 9249.00 AIA #4 |  | 313562.75 | 60867.63 | 255439.25 | 58123.5 | 13443.9
PO 33525187909 | 2024-10-15 | CO #3 | 1209.98 | 314772.73 |  | 255439.25 | 59333.48
PRC 3352518PF7909 | 2025-02-17 | Inv. 9249.00 AIA #5 |  | 314772.73 | 43595.08 | 299034.33 | 15738.4 | 15738.4
PRC 3352518PG7909 | 2025-02-19 | Inv. 9249.00 AIA #7 - Retainage |  | 314772.73 | 15738.4 | 314772.73 | 0
|  | Total: | 314772.73 |  | 314772.73 |  | 0 | FINAL
Vendor has used AIA #1 for another project- Please follow this invoice format
Vendor skipped invoice #6

## #9249.00 McGough CA
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524208805 | 2023-07-27 | PO Procore | 64845.11 | 64845.11 |  |  | 64845.11
PRC 3352420PA8805 | 2023-08-02 | Inv. 100877.002-01 |  | 64845.11 | 784.71 | 784.71 | 64060.4
PRC 3352420PB8805 | 2023-09-14 | Inv. 100877.002-02 |  | 64845.11 | 1471.46 | 2256.17 | 62588.94
PRC 3352420PC8805 | 2023-10-05 | Inv. 100877.002-03 |  | 64845.11 | 689.93 | 2946.1 | 61899.01
PRC 3352420PD8805 | 2023-11-13 | Inv. 100877.002-04 |  | 64845.11 | 1730.91 | 4677.01 | 60168.1
PRC 3352420PE8805 | 2023-12-12 | Inv. 100877.002-05 |  | 64845.11 | 717.46 | 5394.47 | 59450.64
PRC 3352420PF8805 | 2024-01-12 | Inv. 100877.002-06 |  | 64845.11 | 1331.15 | 6725.62 | 58119.49
PRC 3352420PG8805 | 2024-02-08 | Inv. 100877.002-07 |  | 64845.11 | 980.09 | 7705.71 | 57139.4
PRC 3352420PH8805 | 2024-03-18 | Inv. 100877.002-08 |  | 64845.11 | 757.18 | 8462.89 | 56382.22
PRC 3352420PI8805 | 2024-04-08 | Inv. 100877.002-09 |  | 64845.11 | 1309.97 | 9772.86 | 55072.25
PRC 3352420PJ8805 | 2024-05-08 | Inv. 100877.002-10 |  | 64845.11 | 6231.9 | 16004.76 | 48840.35
PRC 3352420PK8805 | 2024-06-12 | Inv. 100877.002-11 |  | 64845.11 | 8355.85 | 24360.61 | 40484.5
PRC 3352420PL8805 | 2024-07-08 | Inv. 100877.002-12A |  | 64845.11 | 9594.87 | 33955.48 | 30889.63 | FY24
PO 33525208805A | 2024-07-15 | Roll to FY25 |  | 64845.11 |  | 33955.48 | 30889.63
PRC 3352520PM8805A | 2024-08-09 | Inv. 100877.002-13A |  | 64845.11 | 4683.55 | 38639.03 | 26206.08
PRC 3352520PN8805A | 2024-09-12 | Inv. 100877.002-14A |  | 64845.11 | 9350.66 | 47989.69 | 16855.42
PRC 3352520PO8805A | 2024-10-09 | Inv. 100877.002-15A |  | 64845.11 | 11246.74 | 59236.43 | 5608.68
PRC 3352520PP8805A | 2024-11-12 | Inv. 100877.002-16 |  | 64845.11 | 1490 | 60726.43 | 4118.68
PRC 3352520PQ8805A | 2024-12-19 | Inv. 100877.002-17 |  | 64845.11 | 3224.86 | 63951.29 | 893.82
PO 33525208805A | 2025-01-03 | CO #1 | 732.82 | 65577.93 |  | 63951.29 | 1626.64
PRC 3352520PR8805A | 2025-01-14 | Inv. 100877.002-18 |  | 65577.93 | 525.26 | 64476.55 | 1101.38
PRC 3352520PS8805A | 2025-03-04 | Inv. 100877.002-19 FINAL | -841.93 | 64736 | 259.45 | 64736 | 0
|  | Total: | 64736 |  | 64736 |  | 0 | FINAL
`
|  | CM Services | 60225.11 |  | 60225.11 |  | 0
|  | Reimbursables | 3779.5 |  | 3779.5 |  | 0
|  | CO #1 | 731.39 |  | 731.39 |  | 0
|  | Total: | 64736 |  | 64736 |  | 0
*Vendor used Inv. 100877.002-XX on another tab in this project, please continue format
Inv. 100877.002-XXA through Inv. 15

## #9249.00 Terracon
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - Brandon A. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524038800 | 2024-02-07 | PO Procore | 1811 | 1811 |  |  | 1811
PRC 3352403PA8800 | 2024-06-24 | Inv. TM21541 |  | 1811 | 1734.5 | 1734.5 | 76.5
PO 33524038800 | 2024-07-11 | Clsoing PO Per PM Request | -76.5 | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  |  |  | 1734.5 |  | 1734.5 | 0
|  | Total: | 1734.5 |  | 1734.5 |  | 0

## RECAP #9250.00
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
| Program code 925000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 152815.88
C | McGough Construction |  | 23818.69 | 23818.69 | 0
C | PM TIME |  | 20779.86 | 20779.86 | 0
C | Misc. |  | 977.33 | 977.33 | 0
C | MA Architecture |  | 96015 | 96015 | 0
C | Terracon Constultants |  | 11225 | 11225 | 0
| Total Project Cost | 152815.88 | 152815.88 | 152815.88 | 0 | 0
Closed 03/26/25

## #9250.00 McGough Construction
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522006900 | 2022-01-05 | PO Procore | 13000.23 | 13000.23 |  |  | 13000.23
PRC 3352200PA6900 | 2022-04-12 | Inv. 9250.00-01 |  | 13000.23 | 1425 | 1425 | 11575.23
PRC 3352200PB6900 | 2022-05-27 | Inv. 9250.00.001-2 |  | 13000.23 | 678.56 | 2103.56 | 10896.67
PRC 3352200PC6900 | 2022-06-10 | Inv. 9250.00.001-3 |  | 13000.23 | 1242.5 | 3346.06 | 9654.17
PRC 3352200PD6900 | 2022-07-14 | Inv. 9250.00.001-4 |  | 13000.23 | 315.63 | 3661.69 | 9338.54 | FY22
PO 33523006900 | 2022-08-09 | Rolled to FY23 | 0 | 13000.23 |  | 3661.69 | 9338.54
PRC 3352300PE6900 | 2022-08-11 | Inv. 9250.00.001-5 |  | 13000.23 | 185 | 3846.69 | 9153.54
PRC 3352300PF6900 | 2022-09-08 | Inv. 9250.00.001-6 |  | 13000.23 | 1070 | 4916.69 | 8083.54
PRC 3352300PG6900 | 2022-10-10 | Inv. 9250.00.001-7 |  | 13000.23 | 1200 | 6116.69 | 6883.54
PRC 3352300PH6900 | 2022-11-15 | Inv. 100877.003 PC-8 |  | 13000.23 | 2863 | 8979.69 | 4020.54
PRC 3352300PI6900 | 2022-12-13 | Inv. 100877.003-9 |  | 13000.23 | 260 | 9239.69 | 3760.54
PRC 3352300PJ6900 | 2023-01-16 | Inv. 100877.003PC10 |  | 13000.23 | 2222.5 | 11462.19 | 1538.04
PO 33523006900 | 2023-01-19 | CO 1 | 5702 | 18702.23 |  | 11462.19 | 7240.04
PRC 3352300PK6900 | 2023-02-10 | Inv. 100877.003PC11 |  | 18702.23 | 865 | 12327.19 | 6375.04
PRC 3352300PL6900 | 2023-03-13 | Inv. 100877.003PC12 |  | 18702.23 | 595 | 12922.19 | 5780.04
PRC 3352300PM6900 | 2023-04-07 | Inv. 100877.003-13 |  | 18702.23 | 750 | 13672.19 | 5030.04
PRC 3352300PN6900 | 2023-05-08 | Inv. 100877.003-14 |  | 18702.23 | 607.5 | 14279.69 | 4422.54
PRC 3352300PO6900 | 2023-06-14 | Inv. 100877.003-015 |  | 18702.23 | 1755 | 16034.69 | 2667.54
PRC 3352300PP6900 | 2023-07-02 | Inv. 100877.003-016 |  | 18702.23 | 2304 | 18338.69 | 363.54
PO 33523006900 | 2023-07-28 | CO 2 | 5212 | 23914.23 |  | 18338.69 | 5575.54 | FY23
PO 33524006900 | 2023-08-11 | Rolled to FY24 | 0 | 23914.23 |  | 18338.69 | 5575.54
PRC 3352400PQ6900 | 2023-08-21 | Inv. 100877.003-017 |  | 23914.23 | 2055 | 20393.69 | 3520.54
PRC 3352400PR6900 | 2023-09-13 | Inv. 100877.003-018 |  | 23914.23 | 3425 | 23818.69 | 95.54
PO 33524006900 | 2024-07-02 | Closing PO Per Vendor | -95.54 | 23818.69 |  | 23818.69 | 8.6686e-13
|  |  |  | 23818.69 |  | 23818.69 | 8.6686e-13
|  |  |  | 23818.69 |  | 23818.69 | 8.6686e-13
|  | Totals: | 23818.69 |  | 23818.69 |  | 0 | FINAL
|  | CM Services | 12588 |  | 12588 |  | 0
|  | Reimbursables | 412.23 |  | 412.23 |  | 0
|  | CO 1 | 5702 |  | 5702 |  | 0
|  | CO 2 | 5116.46 |  | 5116.46 |  | 0
|  | Total: | 23818.69 |  | 23818.69 |  | 0

## #9250.00 PM TIME
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZE
Project Manager - Brandon A
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount (James Trower: $6,000 & Josh Herman: $2,000) | 18244.08 | 18244.08 |  |  | 18244.08
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 18244.08 | 500 | 500 | 17744.08
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 18244.08 | 525 | 1025 | 17219.08
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 18244.08 | 1475 | 2500 | 15744.08
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 18244.08 | 1675 | 4175 | 14069.08
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 18244.08 | 375 | 4550 | 13694.08
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 18244.08 | 500 | 5050 | 13194.08
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 18244.08 | 850 | 5900 | 12344.08
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 18244.08 | 350 | 6250 | 11994.08
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 18244.08 | 450 | 6700 | 11544.08
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 18244.08 | -450 | 6250 | 11994.08
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 18244.08 | 495 | 6745 | 11499.08
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 18244.08 | 275 | 7020 | 11224.08
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 18244.08 | 880 | 7900 | 10344.08
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 18244.08 | 302.5 | 8202.5 | 10041.58
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 18244.08 | 467.5 | 8670 | 9574.08
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 378.3 | 18622.38 | 378.3 | 9048.3 | 9574.08
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 233.84 | 18856.22 | 233.84 | 9282.14 | 9574.08
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 473.6 | 19329.82 | 473.6 | 9755.74 | 9574.08
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 220.88 | 19550.7 | 220.88 | 9976.62 | 9574.08
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 358.37 | 19909.07 | 358.37 | 10334.99 | 9574.08
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 19909.07 | 2747.57 | 13082.56 | 6826.51
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 19909.07 | 298.46 | 13381.02 | 6528.05
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 19909.07 | 2616.47 | 15997.49 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 150.91 | 20059.98 | 150.91 | 16148.4 | 3911.58
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 36.02 | 20096 | 36.02 | 16184.42 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 141.85 | 20237.85 | 141.85 | 16326.27 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 43.03 | 20280.88 | 43.03 | 16369.3 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 87.93 | 20368.81 | 87.93 | 16457.23 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 411.05 | 20779.86 | 411.05 | 16868.28 | 3911.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 20779.86 | 168.36 | 17036.64 | 3743.22
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 20779.86 | 1020.96 | 18057.6 | 2722.26
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 20779.86 | 237.81 | 18295.41 | 2484.45
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 20779.86 | 1046 | 19341.41 | 1438.45
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 20779.86 | 164.85 | 19506.26 | 1273.6
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 20779.86 | 967.9 | 20474.16 | 305.7
CDE 33523128800 | 2023-05-07 | 9500 | Finance Support for: April 1-30, 2023 |  | 20779.86 | 8.89 | 20483.05 | 296.81
CDE 33523128800 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 20779.86 | 51.3 | 20534.35 | 245.51
CDE 33523135800 | 2023-05-15 | 9500 | Finance Support for: April 1-30, 2023 |  | 20779.86 | -8.89 | 20525.46 | 254.4 | `
CDE 33523135800 | 2023-05-15 | 9500 | DAS Services for: April 1-30, 2023 |  | 20779.86 | -51.3 | 20474.16 | 305.7
CDE 33523135800 | 2023-05-15 | 2507 | Finance Support for: April 1-30, 2023 |  | 20779.86 | 8.89 | 20483.05 | 296.81
CDE 33523135800 | 2023-05-15 | 9500 | DAS Services for: April 1-30, 2023 |  | 20779.86 | 51.3 | 20534.35 | 245.51
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 20779.86 | 33.01 | 20567.36 | 212.5
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 20779.86 | 229.9 | 20797.26 | -17.4
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 20779.86 | -17.4 | 20779.86 | 2.2098e-12
|  |  | Totals: | 20779.86 |  | 20779.86 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: Fwd: MM22 PM Time Inbox Trower, James 9:31 AM (5 minutes ago) to me, Scott, Josh Jennifer - I want to clarify that I am requesting DAS Finance to set up PM Time for the following new projects (Josh Herman and I will both have PM Time on 9249.00 and 9250.00): 9249.00 - DOC MPCF Front Steps Repair: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9250.00 - DOC MPCF Building 18 Roof Replacement: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9251.00 - DPS P09 Parking Lot Replacement: $4,000 (James Trower: $4,000) 9252.00 - DPS P09 Window Replacement: $4,000 (James Trower: $4,000) 9258.00 - DAS CC Hoover East Side Ice Mitigation: $4,000 (James Trower: $4,000) Please call me at 515-380-8049 when you have a moment. Thanks, James James Trower, AIA, LEED AP James Trower - PM Time $Joni Trower, James 1:08 PM (50 minutes ago) to me Finance - See below items: 9203.00 - DOC NCCF Treatment Center EIFS Replacement: Increase PM Time by $5,000 (MM21) 9231.00 - DAS CC Jessie Parker Water: Increase PM Time by $4,000 (MM22) 9250.00 - DOC MPCF Building 18 Roof Replacement: Increase PM Time by $5,000 (MM22) 9297.00 - DOC MPCF Gym Floor Repair: Set up $6,000 in PM Time (MM21) 9300.00 - DOC MPFC Storage Bunker Repair: Set up $6,000 in PM Time (MM21) 9301.00 - DPS DSM Fleet & Supply 2nd Floor Structural: Set up $4,000 in PM Time (MM21) 9305.00 - DAS CC Capitol South Stair Repair:Set up $6,000 in PM Time (MM23) 9308.00 - DOC NCCF Generator System Control Replacement: Set up $6,000 in PM Time (MM23) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James 3:20 PM (32 minutes ago) to me, John John - Please see below in red: On Fri, Feb 10, 2023 at 3:14 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi James MM21-9203.00 is short by $19.11 when posting $1,282.57 Increase PM Time by $2,000 MM21-9224.00 is short by $128.25 when posting $291.49 Increase PM Time by $5,000 MM22-9231.00 is short by $712.15 when posting $1,340.87 Increase PM Time by $2,000 MM22-9250.00 is short by $1,007.49 when posting $2,914.93 Increase PM Time by $3,000 ADD PM Time $Joni Trower, James Mar 31, 2023, 4:50 PM (4 days ago) to me Finance - Please see the below additional pm time that is needed: 9203.00 - DOC NCCF Treatment Center EIFS Replacement Add PM Time: $3,000 (MM21) 9300.00 - DOC MPFC Storage Bunker Repair Add PM Time: $1,500 (MM21) 9250.00 - DOC MPCF Building 18 Roof Replacement Add PM Time: $8,000 (MM22) 9252.00 - DPS P09 Window Replacement Add PM Time: $2,000 (MM22) 9264.00 - DPS P10 Front Entrance Repair Add PM Time: $1,500 (MM22) 9275.00 - DPS P12 Window Replacement Add PM Time: $3,000 (MM22) 9276.00 - DPS P12 Driveway Repairs Add PM Time: $3,000 (MM22) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James 11:36 AM (1 hour ago) to me Finance - Please see the below modifications for project 9250.00: MM22: Reduce PM Time by 5,755.92 Return $50,000 to the MM22 pool fund MM23: Increase project budget by $145,000 Thanks,

## #9250.00 Misc
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522033902 | 2022-02-02 | 9500 | CMGR | ATC Group Services V# (00002134218) | Inv. 2401761-Final | 70 | 70
GAX 33523258903 | 2022-09-14 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2447721-Final | 732.5 | 802.5
PRC 33524256803 | 2023-09-13 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV033217 | 174.83 | 977.33
977.33
977.33
977.33
977.33
977.33
977.33
977.33
977.33
977.33
|  |  |  | Totals: |  | 977.33

## #9250.00 MA Architecture
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
MA Architecture |  |  | Vendor: 00003166868
Acct. Codes-0017-335-MM22-9260 |  |  | RFP925000-02
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523290901 | 2022-10-14 | PO Procore | 78565 | 78565 |  |  | 78565
PRC 3352329PA0901 | 2022-11-08 | Inv. 1021 |  | 78565 | 2689.5 | 2689.5 | 75875.5
PRC 3352329PB0901 | 2022-12-06 | Inv. 1022 |  | 78565 | 15217.5 | 17907 | 60658
PRC 3352329PC0901 | 2023-01-18 | Inv. 1023 |  | 78565 | 8988 | 26895 | 51670
PO 33523290901 | 2023-01-20 | CO 1 | 1280 | 79845 |  | 26895 | 52950
PO 33523290901 | 2023-03-24 | CO 2 (No Cost) | 0 | 79845 |  | 26895 | 52950
PO 33523290901 | 2023-03-30 | CO 3 | 10820 | 90665 |  | 26895 | 63770
PRC 3352329PD0901 | 2023-05-22 | Inv. 1024 |  | 90665 | 12355 | 39250 | 51415
PRC 3352329PE0901 | 2023-06-12 | Inv. 1025 |  | 90665 | 9967.5 | 49217.5 | 41447.5
PRC 3352329PF0901 | 2023-06-22 | Inv. 1026 |  | 90665 | 1107.5 | 50325 | 40340 | FY23
PO 33524290901 | 2023-08-14 | Roll to FY24 | 0 | 90665 |  | 50325 | 40340
PRC 3352429PG0901 | 2023-08-22 | Inv. 1027 |  | 90665 | 3435 | 53760 | 36905
PRC 3352429PH0901 | 2023-10-12 | Inv. 1028 |  | 90665 | 1145 | 54905 | 35760
PRC 3352429PI0901 | 2024-01-04 | Inv. 1029 |  | 90665 | 3576 | 58481 | 32184
PRC 3352429PJ0901 | 2024-05-08 | Inv. 1030 |  | 90665 | 14304 | 72785 | 17880
PO 33524290901 | 2024-06-26 | CO 4 | 5350 | 96015 |  | 72785 | 23230
PRC 3352429PK0901 | 2024-07-08 | Inv. 2022 |  | 96015 | 8926 | 81711 | 14304 | FY24
PO 33525290901 | 2024-07-18 | Roll to FY25 |  | 96015 |  | 81711 | 14304
PRC 3352529PL0901 | 2024-08-23 | Inv. 2023 |  | 96015 | 10728 | 92439 | 3576
PRC 3352529PM0901 | 2025-03-24 | Inv. 2024FINAL |  | 96015 | 3576 | 96015 | 0
|  | Totals: | 96015 |  | 96015 |  | 0 | FINAL
|  | Gutter, DwnSpout, & Low Slope Roof Evaluation | 9910 |  | 9910 |  | 0
|  | Design Development | 16985 |  | 16985 |  | 0
|  | Construction Documents | 11330 |  | 11330 |  | 0
|  | Bidding/Negotiation Assistance | 4580 |  | 4580 |  | 0
|  | Construction Administration | 35760 |  | 35760 |  | 0
|  | CO 1 | 1280 |  | 1280 |  | 0
|  | CO 3 | 10820 |  | 10820 |  | 0
|  | CO 4 | 5350 |  | 5350 |  | 0
|  | Total: | 96015 |  | 96015 |  | 0

## #9250.00 Terracon Consultants
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
TerraconConsultants |  |  | Vendor: 00002116512
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523107800 | 2023-04-17 | PO Procore | 11225 | 11225 |  |  | 11225
PRC 3352310PA7800 | 2023-06-23 | Inv. TJ53206 |  | 11225 | 4450 | 4450 | 6775 | FY23
PO 33524107800 | 2023-08-24 | Roll to FY24 | 0 | 11225 |  | 4450 | 6775
PRC 3352410PB7800 | 2023-09-15 | Inv. TJ96931 |  | 11225 | 996.2 | 5446.2 | 5778.8
PRC 3352410PC7800 | 2023-12-11 | Inv. TK39371 |  | 11225 | 380 | 5826.2 | 5398.8
PRC 3352410PD7800 | 2024-07-12 | Inv. TM02873 |  | 11225 | 5398.8 | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  |  |  | 11225 |  | 11225 | 0
|  | Totals: | 11225 |  | 11225 |  | 0 | FINAL
|  | Design Services | 4450 |  | 4450 |  | 0
|  | Bidding Adminstrative Services | 1050 |  | 1050 |  | 0
|  | Construction Adminstrative Services-Project Adminstration: | 1325 |  | 1325 |  | 0
|  | Construction Adminstrative Services-Abatement Oversight: | 4400 |  | 4400 |  | 0
|  | Total: | 11225 |  | 11225 |  | 0

## RECAP #9251.00
DPS P09 Parking Lot Replacement
Project # 9251.00
| Program code 925100 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 269266.16
C | Boyd Jones Construction |  | 11881.48 | 11881.48 | 0
C | PM TIME |  | 13710.21 | 13710.21 | 0
C | Misc. |  | 3644.63 | 3644.63 | 0
C | Shive Hattery |  | 28546 | 28546 | 0
C | Woodruff Construction |  | 189357.3 | 189357.3 | 0
C | Boyd Jones Construction(2) |  | 22126.54 | 22126.54 | 0
| Total Project Cost | 269266.16 | 269266.16 | 269266.16 | 0 | 0
Closed 09/15/23

## #9251.00 Boyd Jones Constr
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  | Major Program 4G01
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522019900 | 2022-01-19 | PO Procore | 12357.5 | 12357.5 |  |  | 12357.5
PRC 3352201PA9900 | 2022-05-10 | Inv. 9251.00-01 |  | 12357.5 | 4973.6 | 4973.6 | 7383.9
PRC 3352201PB9900 | 2022-06-15 | Inv. 9251.00-02 |  | 12357.5 | 2695 | 7668.6 | 4688.9
PRC 3352201PC9900 | 2022-07-12 | Inv. 9251.00-03 |  | 12357.5 | 2785 | 10453.6 | 1903.9 | FY22
PO 33523019900 | 2022-08-09 | Rolled to FY23 | 0 | 12357.5 |  | 10453.6 | 1903.9
PRC 3352301PD9900 | 2022-08-17 | Inv. 9251.00-04-Final | -476.02 | 11881.48 | 1427.88 | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  |  |  | 11881.48 |  | 11881.48 | 0
|  | Totals: | 11881.48 |  | 11881.48 |  | 0 | Final Invoice
|  | CM Services | 11695 |  | 11695 |  | 0
|  | Reimbursables | 186.48 |  | 186.48 |  | 0
|  | Total: | 11881.48 |  | 11881.48 |  | 0

## #9251.00 PM TIME
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZF
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11490.6 | 11490.6 |  |  | 11490.6
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 11490.6 | 225 | 225 | 11265.6
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 11490.6 | 300 | 525 | 10965.6
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 11490.6 | 975 | 1500 | 9990.6
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 11490.6 | 350 | 1850 | 9640.6
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 11490.6 | 975 | 2825 | 8665.6
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 11490.6 | 400 | 3225 | 8265.6
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 11490.6 | 625 | 3850 | 7640.6
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 11490.6 | 575 | 4425 | 7065.6
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 11490.6 | 425 | 4850 | 6640.6
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 11490.6 | -425 | 4425 | 7065.6
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 11490.6 | 467.5 | 4892.5 | 6598.1
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 11490.6 | 742.5 | 5635 | 5855.6
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 11490.6 | 605 | 6240 | 5250.6
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 11490.6 | 302.5 | 6542.5 | 4948.1
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 11490.6 | 302.5 | 6845 | 4645.6
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 369.96 | 11860.56 | 369.96 | 7214.96 | 4645.6
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 631.35 | 12491.91 | 631.35 | 7846.31 | 4645.6
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 325.6 | 12817.51 | 325.6 | 8171.91 | 4645.6
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 220.88 | 13038.39 | 220.88 | 8392.79 | 4645.6
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 231.9 | 13270.29 | 231.9 | 8624.69 | 4645.6
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 13270.29 | 563.6 | 9188.29 | 4082
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 13270.29 | 71.63 | 9259.92 | 4010.37
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 13270.29 | 627.96 | 9887.88 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 118.1 | 13388.39 | 118.1 | 10005.98 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 79.24 | 13467.63 | 79.24 | 10085.22 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 67.55 | 13535.18 | 67.55 | 10152.77 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 33.82 | 13569 | 33.82 | 10186.59 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 56.89 | 13625.89 | 56.89 | 10243.48 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 84.32 | 13710.21 | 84.32 | 10327.8 | 3382.41
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 13710.21 | 64.14 | 10391.94 | 3318.27
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 13710.21 | 388.94 | 10780.88 | 2929.33
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 13710.21 | 50.07 | 10830.95 | 2879.26
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 13710.21 | 220.21 | 11051.16 | 2659.05
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 13710.21 | 34.49 | 11085.65 | 2624.56
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 13710.21 | 204.7 | 11290.35 | 2419.86
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 13710.21 | 57.13 | 11347.48 | 2362.73
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 13710.21 | 402.6 | 11750.08 | 1960.13
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 13710.21 | 77.48 | 11827.56 | 1882.65
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 13710.21 | 673.9 | 12501.46 | 1208.75
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 13710.21 | 73.46 | 12574.92 | 1135.29
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 13710.21 | 466.5 | 13041.42 | 668.79
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 13710.21 | 101.49 | 13142.91 | 567.3
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 13710.21 | 567.3 | 13710.21 | 0
|  |  | Totals: | 13710.21 |  | 13710.21 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: Fwd: MM22 PM Time Inbox Trower, James 9:31 AM (4 minutes ago) to me, Scott, Josh Jennifer - I want to clarify that I am requesting DAS Finance to set up PM Time for the following new projects (Josh Herman and I will both have PM Time on 9249.00 and 9250.00): 9249.00 - DOC MPCF Front Steps Repair: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9250.00 - DOC MPCF Building 18 Roof Replacement: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9251.00 - DPS P09 Parking Lot Replacement: $4,000 (James Trower: $4,000) 9252.00 - DPS P09 Window Replacement: $4,000 (James Trower: $4,000) 9258.00 - DAS CC Hoover East Side Ice Mitigation: $4,000 (James Trower: $4,000) Please call me at 515-380-8049 when you have a moment. Thanks, James James Trower, AIA, LEED AP PM Time - James Trower $Joni Trower, James Mar 31, 2022, 6:21 PM (19 hours ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Please set up $6,000 in PM Time for the MM21 funds 9212.00 - DIA CC Wallace 3rd Floor Renovation (2021): Please increase PM Time by $1,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs: Please increase PM Time by $4,000 9228.00 - DCA PGR Plum Grove Roof Replacement: Please increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement: Please increase PM Time by $2,000 9251.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 9252.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 Thanks, James James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov PM Time - James Trower $Joni Trower, James 3:10 PM (4 minutes ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Increase PM Time by $5,000 9201.00 - DAS CC Ola Babcock Miller Tuckpointing (MM20): Increase PM Time by $1,100 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs (MM22): Increase PM Time by $6,000 9249.00 - DOC MPCF Front Steps Repair (MM22): Increase PM Time by $6,000 9251.00 - DPS P09 Parking Lot Replacement (MM22): Increase PM Time by $3,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Please make the below increases to PM Time: 9203.00 - Treatment Center EIFS Replacement (MM21) - Increase PM Time by $5,000 9231.00 - Jessie Parker Water Infiltration Repair (MM22) - Increase PM Time by $1,000 9251.00 - DPS P09 Parking Lot Replacement (MM22) - Increase PM Time by $1,000

## #9251.00 Misc
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523258800 | 2022-09-14 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV023258 | 102.13 | 102.13
GAX 33523326905 | 2022-11-22 | 9500 | CNST | Terracon V#(00002116512) | Inv. TH70062 | 3542.5 | 3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
3644.63
|  |  |  | Totals: |  | 3644.63

## #9251.00 Shive Hattery
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  | Major Program 4G01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP925100-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522095800 | 2022-04-05 | PO Procore | 28546 | 28546 |  |  | 28546
PRC 3352209PA5800 | 2022-06-28 | Inv. 9251.00-01 |  | 28546 | 23100 | 23100 | 5446 | FY22
PO 33523095800 | 2022-08-09 | Rolled to FY23 | 0 | 28546 |  | 23100 | 5446
PRC 3352309PB5800 | 2022-10-12 | Inv. 2112202970-2 |  | 28546 | 1400 | 24500 | 4046
PRC 3352309PC5800 | 2022-12-27 | Inv. 9251.00-03 |  | 28546 | 4046 | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  |  |  | 28546 |  | 28546 | 0
|  | Totals: | 28546 |  | 28546 |  | 0
|  | 50% Construction Documents | 13500 |  | 13500 |  | 0
|  | 100% Construction Documents | 9600 |  | 9600 |  | 0
|  | Bidding Assistance | 1400 |  | 1400 |  | 0
|  | Construction Phase | 4046 |  | 4046 |  | 0
|  | Total: | 28546 |  | 28546 |  | 0

## #9251.00 Woodruff Construction
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  | Major Program 4G01
Woodruff Construction |  |  | Vendor: 00002142754
Acct. Codes-0017-335-MM22-9255 |  |  | RFB 925100-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523231806 | 2022-08-19 | PO Procore | 183500 | 183500 |  |  | 183500
PRC 3352323PA1806 | 2022-10-13 | Inv. 9251.00-01 |  | 183500 | 33354.02 | 33354.02 | 150145.98 | 1755.48
PO 33523231806 | 2022-10-28 | CO 1 | 4069.3 | 187569.3 |  | 33354.02 | 154215.28
PO 33523231806 | 2022-11-08 | CO 2 | 1788 | 189357.3 |  | 33354.02 | 156003.28
PRC 3352323PB1806 | 2022-11-29 | Inv. 9251.00-02 |  | 189357.3 | 122594.65 | 155948.67 | 33408.63 | 8207.83
PRC 3352323PC1806 | 2022-12-06 | Inv. 9251.00-03 |  | 189357.3 | 16439.55 | 172388.22 | 16969.08 | 9073.08
PRC 3352323PD1806 | 2023-02-09 | Inv. 9251.00-04 |  | 189357.3 | 471.2 | 172859.42 | 16497.88 | 9097.88
PRC 3352323PE1806 | 2023-02-14 | Inv. 9251.00-05-Partial Retainage |  | 189357.3 | 9097.88 | 181957.3 | 7400 | 0
PRC 3352323PF1806 | 2023-05-31 | Inv. 9251.00-06 |  | 189357.3 | 7030 | 188987.3 | 370 | 370
PRC 3352323PG1806 | 2023-06-01 | Inv. 9251.00-07 - Retainage |  | 189357.3 | 370 | 189357.3 | 5.457e-12
|  |  |  | 189357.3 |  | 189357.3 | 5.457e-12
|  |  |  | 189357.3 |  | 189357.3 | 5.457e-12
|  |  |  | 189357.3 |  | 189357.3 | 5.457e-12
|  | Totals: | 189357.3 |  | 189357.3 |  | 0

## #9251.00 Boyd Jones Constr (2)
DPS P09 Parking Lot Replacement
Project # 9251.00
Program code 925100 |  |  | Major Program 4G01
Boyd Jones Construction(2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523257902 | 2022-09-13 | PO Procore | 23533.75 | 23533.75 |  |  | 23533.75
PRC 3352325PA7902 | 2022-10-13 | Inv. 9251.00-01A |  | 23533.75 | 5863.15 | 5863.15 | 17670.6
PRC 3352325PB7902 | 2022-11-13 | Inv. 9251.00-02A |  | 23533.75 | 7376.93 | 13240.08 | 10293.67
PRC 3352325PC7902 | 2022-12-12 | Inv. 9251.00-03A |  | 23533.75 | 4810.92 | 18051 | 5482.75
PRC 3352325PD7902 | 2023-01-12 | Inv. 9251.00-04A |  | 23533.75 | 2533.73 | 20584.73 | 2949.02
PRC 3352325PE7902 | 2023-03-16 | Inv. 9251.00-05A |  | 23533.75 | 487.16 | 21071.89 | 2461.86
PRC 3352325PF7902 | 2023-04-11 | Inv. 9251.00-06A |  | 23533.75 | 524.22 | 21596.11 | 1937.64
PRC 3352325PG7902 | 2023-05-19 | Inv. 9251.00-07A |  | 23533.75 | 402.43 | 21998.54 | 1535.21
PRC 3352325PH7902 | 2023-06-02 | Inv. 9251.00-08A-Final | -1407.21 | 22126.54 | 128 | 22126.54 | 0
|  |  |  | 22126.54 |  | 22126.54 | 0
|  |  |  | 22126.54 |  | 22126.54 | 0
|  |  |  | 22126.54 |  | 22126.54 | 0
|  |  |  | 22126.54 |  | 22126.54 | 0
|  | Totals: | 22126.54 |  | 22126.54 |  | 0 | FINAL
|  | CM Services | 21377.14 |  | 21377.14 |  | 0
|  | Reimbursables | 749.4 |  | 749.4 |  | 0
|  | Total: | 22126.54 |  | 22126.54 |  | 0

## RECAP #9252.00
DPS P09 Window Replacement
Project # 9252.00
| Program code 925200 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 80991.18
C | Boyd Jones Construction |  | 12318.6 | 12318.6 | 0
C | PM TIME |  | 11519.06 | 11519.06 | 0
C | Misc. |  | 837.5 | 837.5 | 0
C | Horizon Architecture |  | 8500 | 8500 | 0
C | Boyd Jones Construction(2) |  | 9526.02 | 9526.02 | 0
C | Cardinal Construction |  | 38290 | 38290 | 0
| Total Project Cost | 80991.18 | 80991.18 | 80991.18 | 0 | 0
Closed 09/15/23

## #9252.00 Boyd Jones Constr
DPS P09 Parking Lot Replacement
Project # 9252.00
Program code 925200 |  |  | Major Program 4E19
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522019800 | 2022-01-19 | PO Procore | 12550 | 12550 |  |  | 12550
PRC 3352201PA9800 | 2022-05-10 | Inv. 9252.00-01 |  | 12550 | 4973.6 | 4973.6 | 7576.4
PRC 3352201PB9800 | 2022-06-17 | Inv. 9252.00-02 |  | 12550 | 2695 | 7668.6 | 4881.4
PRC 3352201PC9800 | 2022-07-11 | Inv. 9252.00-03 |  | 12550 | 2025 | 9693.6 | 2856.4 | FY22
PO 33523019800 | 2022-08-09 | Rolled to FY23 | 0 | 12550 |  | 9693.6 | 2856.4
PRC 3352301PD9800 | 2022-08-23 | Inv. 9252.00-04 - Final | -231.4 | 12318.6 | 2625 | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  |  |  | 12318.6 |  | 12318.6 | 0
|  | Totals: | 12318.6 |  | 12318.6 |  | 0
|  | CM Services | 12225 |  | 12225 |  | 0
|  | Reimbursables | 93.6 |  | 93.6 |  | 0
|  | Total: | 12318.6 |  | 12318.6 |  | 0

## #9252.00 PM TIME
DPS P09 Window Replacement
Project # 9252.00
Program code 925200 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZG
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10249.82 | 10249.82 |  |  | 10249.82
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 10249.82 | 175 | 175 | 10074.82
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 10249.82 | 300 | 475 | 9774.82
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 10249.82 | 975 | 1450 | 8799.82
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 10249.82 | 350 | 1800 | 8449.82
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 10249.82 | 800 | 2600 | 7649.82
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 10249.82 | 500 | 3100 | 7149.82
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 10249.82 | 475 | 3575 | 6674.82
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 10249.82 | 625 | 4200 | 6049.82
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 10249.82 | 425 | 4625 | 5624.82
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 10249.82 | -425 | 4200 | 6049.82
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 10249.82 | 467.5 | 4667.5 | 5582.32
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 10249.82 | 302.5 | 4970 | 5279.82
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 10249.82 | 302.5 | 5272.5 | 4977.32
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 10249.82 | 137.5 | 5410 | 4839.82
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 10249.82 | 137.5 | 5547.5 | 4702.32
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 141.85 | 10391.67 | 141.85 | 5689.35 | 4702.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 257.22 | 10648.89 | 257.22 | 5946.57 | 4702.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 162.8 | 10811.69 | 162.8 | 6109.37 | 4702.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 100.4 | 10912.09 | 100.4 | 6209.77 | 4702.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 105.41 | 11017.5 | 105.41 | 6315.18 | 4702.32
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 11017.5 | 281.8 | 6596.98 | 4420.52
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 11017.5 | 23.87 | 6620.85 | 4396.65
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 11017.5 | 209.32 | 6830.17 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 111.54 | 11129.04 | 111.54 | 6941.71 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 72.03 | 11201.07 | 72.03 | 7013.74 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 216.16 | 11417.23 | 216.16 | 7229.9 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 33.82 | 11451.05 | 33.82 | 7263.72 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 25.86 | 11476.91 | 25.86 | 7289.58 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 42.15 | 11519.06 | 42.15 | 7331.73 | 4187.33
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 11519.06 | 88.19 | 7419.92 | 4099.14
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 11519.06 | 534.79 | 7954.71 | 3564.35
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 11519.06 | 150.19 | 8104.9 | 3414.16
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 11519.06 | 660.63 | 8765.53 | 2753.53
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 11519.06 | 51.84 | 8817.37 | 2701.69
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 11519.06 | 305.7 | 9123.07 | 2395.99
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 11519.06 | 49.3 | 9172.37 | 2346.69
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 11519.06 | 344.3 | 9516.67 | 2002.39
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 11519.06 | 72.82 | 9589.49 | 1929.57
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 11519.06 | 631.2 | 10220.69 | 1298.37
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 11519.06 | 85.58 | 10306.27 | 1212.79
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 11519.06 | 544 | 10850.27 | 668.79
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 11519.06 | 101.49 | 10951.76 | 567.3
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 11519.06 | 567.3 | 11519.06 | 0
[5 empty] | 11519.06 |  | 11519.06 | 0
|  |  | Totals: | 11519.06 |  | 11519.06 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: Fwd: MM22 PM Time Inbox Trower, James 9:31 AM (4 minutes ago) to me, Scott, Josh Jennifer - I want to clarify that I am requesting DAS Finance to set up PM Time for the following new projects (Josh Herman and I will both have PM Time on 9249.00 and 9250.00): 9249.00 - DOC MPCF Front Steps Repair: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9250.00 - DOC MPCF Building 18 Roof Replacement: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9251.00 - DPS P09 Parking Lot Replacement: $4,000 (James Trower: $4,000) 9252.00 - DPS P09 Window Replacement: $4,000 (James Trower: $4,000) 9258.00 - DAS CC Hoover East Side Ice Mitigation: $4,000 (James Trower: $4,000) Please call me at 515-380-8049 when you have a moment. Thanks, James James Trower, AIA, LEED AP PM Time - James Trower $Joni Trower, James Mar 31, 2022, 6:21 PM (19 hours ago) to me Finance - Please see the below items: 9176.00 - DOC NCCF Tunnel Evaluation and Repair (MM21): Please set up $6,000 in PM Time for the MM21 funds 9212.00 - DIA CC Wallace 3rd Floor Renovation (2021): Please increase PM Time by $1,000 9226.00 - DCA MON Main House Site Work and Outbuilding Repairs: Please increase PM Time by $4,000 9228.00 - DCA PGR Plum Grove Roof Replacement: Please increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement: Please increase PM Time by $2,000 9251.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 9252.00 - DPS P09 Window Replacement: Please increase PM Time by $4,000 Thanks, James James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov ADD PM Time $Joni Trower, James Mar 31, 2023, 4:50 PM (4 days ago) to me Finance - Please see the below additional pm time that is needed: 9203.00 - DOC NCCF Treatment Center EIFS Replacement Add PM Time: $3,000 (MM21) 9300.00 - DOC MPFC Storage Bunker Repair Add PM Time: $1,500 (MM21) 9250.00 - DOC MPCF Building 18 Roof Replacement Add PM Time: $8,000 (MM22) 9252.00 - DPS P09 Window Replacement Add PM Time: $2,000 (MM22) 9264.00 - DPS P10 Front Entrance Repair Add PM Time: $1,500 (MM22) 9275.00 - DPS P12 Window Replacement Add PM Time: $3,000 (MM22) 9276.00 - DPS P12 Driveway Repairs Add PM Time: $3,000 (MM22) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Finance - Please make the below increases to PM Time: 9203.00 - Treatment Center EIFS Replacement (MM21) - Increase PM Time by $5,000 9231.00 - Jessie Parker Water Infiltration Repair (MM22) - Increase PM Time by $1,000 9251.00 - DPS P09 Parking Lot Replacement (MM22) - Increase PM Time by $1,000 9252.00 - Window Replacement (MM22) - Increase PM Time by $1,000

## #9252.00 Misc
DPS P09 Window Replacement
Project # 9252.00
Program code 925200 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522192901 | 2022-07-08 | CNST | 9500 | ATC Group V# (00002134218) | Inv. 2435349 | 837.5 | 837.5
837.5
837.5
837.5
837.5
837.5
837.5
837.5
837.5
837.5
837.5
837.5
|  |  |  | Totals: |  | 837.5

## #9252.00 Horizon Architecture
DPS P09 Parking Lot Replacement
Project # 9252.00
Program code 925200 |  |  | Major Program 4E19
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522111800 | 2022-04-14 | PO Procore | 8500 | 8500 |  |  | 8500
PRC 3352211PA1800 | 2022-05-10 | Inv. 9252.00-01 |  | 8500 | 3000 | 3000 | 5500
PRC 3352211PB1800 | 2022-06-30 | Inv. 9252.00-02 |  | 8500 | 1750 | 4750 | 3750 | FY22
PO 33523111800 | 2022-08-09 | Rolled to FY23 | 0 | 8500 |  | 4750 | 3750
PRC 3352311PC1800 | 2023-04-10 | Inv. 9252.00-03 |  | 8500 | 875 | 5625 | 2875
PRC 3352311PD1800 | 2023-08-01 | Inv. 9252.00-04 |  | 8500 | 2875 | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  |  |  | 8500 |  | 8500 | 0
|  | Totals: | 8500 |  | 8500 |  | 0 | FINAL
|  | Survey, Design & Documentation | 4000 |  | 4000 |  | 0
|  | Project Management | 1500 |  | 1500 |  | 0
|  | Bidding Assistance | 500 |  | 500 |  | 0
|  | Construction Administration | 1500 |  | 1500 |  | 0
|  | Closeout | 1000 |  | 1000 |  | 0
|  | Total: | 8500 |  | 8500 |  | 0

## #9252.00 Boyd Jones Constr (2)
DPS P09 Parking Lot Replacement
Project # 9252.00
Program code 925200 |  |  | Major Program 4E19
Boyd Jones Construction (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523257901 | 2022-09-13 | PO Procore | 10019.38 | 10019.38 |  |  | 10019.38
PRC 3352325PA7901 | 2022-09-19 | Inv. 9252.00A-01 |  | 10019.38 | 1070 | 1070 | 8949.38
PRC 3352325PB7901 | 2022-10-10 | Inv. 9252.00A-02 |  | 10019.38 | 1323.75 | 2393.75 | 7625.63
PRC 3352325PC7901 | 2022-11-11 | Inv. 9252.00A-03 |  | 10019.38 | 767.8 | 3161.55 | 6857.83
PRC 3352325PD7901 | 2023-03-16 | Inv. 9252.00A-04 |  | 10019.38 | 365.37 | 3526.92 | 6492.46
PRC 3352325PE7901 | 2023-04-11 | Inv. 9252.00A-05 |  | 10019.38 | 2172.45 | 5699.37 | 4320.01
PRC 3352325PF7901 | 2023-05-19 | Inv. 9252.00A-06 |  | 10019.38 | 2846.52 | 8545.89 | 1473.49
PRC 3352325PG7901 | 2023-06-16 | Inv. 9252.00A-07 Final | -493.36 | 9526.02 | 980.13 | 9526.02 | 0
|  |  |  | 9526.02 |  | 9526.02 | 0
|  |  |  | 9526.02 |  | 9526.02 | 0
|  |  |  | 9526.02 |  | 9526.02 | 0
|  |  |  | 9526.02 |  | 9526.02 | 0
|  |  |  | 9526.02 |  | 9526.02 | 0
|  | Totals: | 9526.02 |  | 9526.02 |  | 0
|  | CM Services | 9136.02 |  | 9136.02 |  | 0
|  | Reimbursables | 390 |  | 390 |  | 0
|  | Total: | 9526.02 |  | 9526.02 |  | 0

## #9252.00 Cardinal Construction
DPS P09 Parking Lot Replacement
Project # 9252.00
Program code 925200 |  |  | Major Program 4E19
Cardinal Construction |  |  | Vendor: 00003035280
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ 925200-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523279900 | 2022-10-06 | PO Procore | 38290 | 38290 |  |  | 38290
PRC 3352327PA9900 | 2023-04-24 | Inv. 9252.00-01 |  | 38290 | 33316.5 | 33316.5 | 4973.5 | 1753.5
PRC 3352327PB9900 | 2023-07-10 | Inv. 9252.00-02 |  | 38290 | 3059 | 36375.5 | 1914.5 | 1914.5
PRC 3352327PC9900 | 2023-07-18 | Inv. 9252.00-03 - Retainage |  | 38290 | 1914.5 | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  |  |  | 38290 |  | 38290 | 0
|  | Totals: | 38290 |  | 38290 |  | 0

## RECAP #9253.00
DOC FDCF Floyd and Bldg K Roof Replacement
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 01/05/2023

## #9253.00 Vendor A
DOC FDCF Floyd and Bldg K Roof Replacement
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9253.00 PM TIME
DOC FDCF Floyd and Bldg K Roof Replacement
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9253.00 Misc
DOC FDCF Floyd and Bldg K Roof Replacement
Project # 9253.00
Program code 925300 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9254.00
DHS GRC 712-714-716 Lacey Roof Replacements
Project # 9254.00
| Program code 925400 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Doug C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1800
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 1800 | 1800 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 1800 | 1800 | 1800 | 0 | 0
Closed 7/14/22
Note on C8: Durakovic, Selma [DAS]: Project 9254.00 MM22 FY22 Carper, Douglas <douglas.carper@iowa.gov> Jul 14, 2022, 11:58 AM to me, Scott This project can be closed and the balance of funds returned to MM22. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov

## #9254.00 Vendor A
DHS GRC 712-714-716 Lacey Roof Replacements
Project # 9254.00
Program code 925400 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9254.00 PM TIME
DHS GRC 712-714-716 Lacey Roof Replacements
Project # 9254.00
Program code 925400 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 1800 | 1800 |  |  | 1800
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 1800 | 150 | 150 | 1650
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 1800 | 400 | 550 | 1250
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 1800 | 250 | 800 | 1000
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 1800 | 600 | 1400 | 400
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 1800 | 250 | 1650 | 150
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 1800 | 50 | 1700 | 100
IET DAS2022011115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 1800 | 100 | 1800 | 0
|  |  |  | 1800 |  | 1800 | 0
|  |  |  | 1800 |  | 1800 | 0
|  |  |  | 1800 |  | 1800 | 0
|  |  |  | 1800 |  | 1800 | 0
|  |  |  | 1800 |  | 1800 | 0
|  | Totals: | 1800 |  | 1800 |  | 0
Note on D9: Huggins, Joni [DAS]: Re: PM Time Budget $Joni Carper, Douglas 11:49 AM (2 hours ago) to me 9247.00 PM Budget $3,000.00 9254.00 PM Budget $7,500.00 9256.00 PM Budget $4,800.00 9259.00 PM Budget $15,000.00 9261.00 PM Budget $10,000.00 Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative

## #9254.00 Misc
DHS GRC 712-714-716 Lacey Roof Replacements
Project # 9254.00
Program code 925400 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9255.00
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 01/05/2023

## #9255.00 Vendor A
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9255.00 PM TIME
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 234.9 | 234.9 | 234.9 | 234.9 | 0
CDE 33523353203 | 2022-12-21 | Move PM Expense to 9997.23 | -234.9 | 0 | -234.9 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9255.00 Misc
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9256.00
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
| Program code 925600 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 319823.75
C | Story Construction |  | 14780.36 | 14780.36 | 0
| PM TIME |  | 16884.13 | 16884.13 | 0
| Misc. |  | 1292.64 | 1292.64 | 0
C | Karges-Faulconbridge Inc. |  | 25968 | 25968 | 0
C | Modern Piping |  | 235874.12 | 235874.12 | 0
C | Story ConstructionCA |  | 25024.5 | 25024.5 | 0
| Total Project Cost | 319823.75 | 319823.75 | 319823.75 | 0 | 0
Closed 01/12/2024

## #9256.00 Story Construction PC
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  | Major Program 4B01
Story Construction PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522033901 | 2022-02-02 | PO Procore | 14885.84 | 14885.84 |  |  | 14885.84
PRC 3352203PA3901 | 2022-03-23 | Inv. 33038 |  | 14885.84 | 1816.5 | 1816.5 | 13069.34
PRC 3352203PB3901 | 2022-04-27 | Inv. 33084 |  | 14885.84 | 2377.71 | 4194.21 | 10691.63
PRC 3352203PC3901 | 2022-05-19 | Inv. 33127 |  | 14885.84 | 2639.71 | 6833.92 | 8051.92
PRC 3352203PD3901 | 2022-06-23 | Inv. 33172 |  | 14885.84 | 2566.48 | 9400.4 | 5485.44
PRC 3352203PE3901 | 2022-07-18 | Inv. 33225 |  | 14885.84 | 5379.96 | 14780.36 | 105.48 | FY22
PO 33523033901 | 2022-08-09 | Rolled to FY23 | 0 | 14885.84 |  | 14780.36 | 105.48
PO 33523033901 | 2023-06-28 | Close PO per PM | -105.48 | 14780.36 |  | 14780.36 | 4.6896e-13
|  |  |  | 14780.36 |  | 14780.36 | 4.6896e-13
|  |  |  | 14780.36 |  | 14780.36 | 4.6896e-13
|  |  |  | 14780.36 |  | 14780.36 | 4.6896e-13
|  |  |  | 14780.36 |  | 14780.36 | 4.6896e-13
|  |  |  | 14780.36 |  | 14780.36 | 4.6896e-13
|  | Totals: | 14780.36 |  | 14780.36 |  | 0 | FINAL
|  | CM Services | 14420 |  | 14420 |  | 0
|  | Reimbursables | 360.36 |  | 360.36 |  | 0
|  | Total: | 14780.36 |  | 14780.36 |  | 0

## #9256.00 PM TIME
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZK
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14711.32 | 14711.32 |  |  | 14711.32
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 14711.32 | 100 | 100 | 14611.32
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 14711.32 | 200 | 300 | 14411.32
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 14711.32 | 250 | 550 | 14161.32
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 14711.32 | 500 | 1050 | 13661.32
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 14711.32 | 900 | 1950 | 12761.32
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 14711.32 | 850 | 2800 | 11911.32
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 14711.32 | 1100 | 3900 | 10811.32
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 14711.32 | 1000 | 4900 | 9811.32
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 14711.32 | 450 | 5350 | 9361.32
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 14711.32 | -450 | 4900 | 9811.32
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 14711.32 | 495 | 5395 | 9316.32
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 14711.32 | 1100 | 6495 | 8216.32
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 14711.32 | 495 | 6990 | 7721.32
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 14711.32 | 220 | 7210 | 7501.32
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 14711.32 | 110 | 7320 | 7391.32
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 132.47 | 14843.79 | 132.47 | 7452.47 | 7391.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 948.62 | 15792.41 | 948.62 | 8401.09 | 7391.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 328.57 | 16120.98 | 328.57 | 8729.66 | 7391.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 154.71 | 16275.69 | 154.71 | 8884.37 | 7391.32
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 88.23 | 16363.92 | 88.23 | 8972.6 | 7391.32
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16363.92 | 540.61 | 9513.21 | 6850.71
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16363.92 | 76.05 | 9589.26 | 6774.66
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16363.92 | 666.7 | 10255.96 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 114.86 | 16478.78 | 114.86 | 10370.82 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 14.5 | 16493.28 | 14.5 | 10385.32 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 131.51 | 16624.79 | 131.51 | 10516.83 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 157.36 | 16782.15 | 157.36 | 10674.19 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 21.1 | 16803.25 | 21.1 | 10695.29 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 80.88 | 16884.13 | 80.88 | 10776.17 | 6107.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 16884.13 | 114.12 | 10890.29 | 5993.84
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 16884.13 | 692.04 | 11582.33 | 5301.8
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 16884.13 | 68.63 | 11650.96 | 5233.17
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 16884.13 | 301.86 | 11952.82 | 4931.31
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 16884.13 | 27.94 | 11980.76 | 4903.37
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 16884.13 | 165.4 | 12146.16 | 4737.97
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 16884.13 | 39.57 | 12185.73 | 4698.4
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 16884.13 | 277.2 | 12462.93 | 4421.2
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 16884.13 | 22.87 | 12485.8 | 4398.33
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 16884.13 | 188.7 | 12674.5 | 4209.63
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 16884.13 | 102.69 | 12777.19 | 4106.94
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 16884.13 | 655.3 | 13432.49 | 3451.64
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 16884.13 | 78.79 | 13511.28 | 3372.85
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 16884.13 | 439.4 | 13950.68 | 2933.45
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 16884.13 | 83.63 | 14034.31 | 2849.82
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 16884.13 | 580.3 | 14614.61 | 2269.52
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 16884.13 | 46.77 | 14661.38 | 2222.75
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 16884.13 | 379.7 | 15041.08 | 1843.05
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 16884.13 | 127.83 | 15168.91 | 1715.22
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 16884.13 | 967.8 | 16136.71 | 747.42
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 16884.13 | 89.82 | 16226.53 | 657.6
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 16884.13 | 657.6 | 16884.13 | 2.3874e-12
[5 empty] | 16884.13 |  | 16884.13 | 2.3874e-12
|  |  | Totals: | 16884.13 |  | 16884.13 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: PM Time Budget $Joni Carper, Douglas 11:49 AM (2 hours ago) to me 9247.00 PM Budget $3,000.00 9254.00 PM Budget $7,500.00 9256.00 PM Budget $4,800.00 9259.00 PM Budget $15,000.00 9261.00 PM Budget $10,000.00 Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative e: PM Time MM22 9256.00 $Joni Carper, Douglas 2:50 PM (5 minutes ago) to me Increase PM budget to $6,000.00. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Re: MM22 9256.00 PM Time corrections $Joni Carper, Douglas 7:26 AM (0 minutes ago) to me Revise the PM Time budget to $9,000.00. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov On Mon, Sep 12, 2022 at 3:08 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi This project is short 495.00 to post the correction Please advise Thank you ~Joni Re: 9256.00 MM22 PM Time budget FY23 Elliott, Jennie 10:42 AM (19 minutes ago) to Jennifer, me Please increase the PM time budget for 9256.00 to $15,000. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Please note that my mobile phone number is 515-745-3244!

## #9256.00 Misc
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522154901 | 2022-06-03 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2428985-Final | 947.5 | 947.5
PRC 33522201903 | 2022-07-20 | 9500 | CNST | Rapid Reproductions V#(00002111375) | Inv. 419748-0 | 345.14 | 1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
1292.64
|  |  |  | Totals |  | 1292.64

## #9256.00 Karges-Faulconbridge
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  | Major Program 4B01
Karges-Faulconbridge Inc. |  |  | Vendor: VS000002170
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 925600-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522101801 | 2022-04-08 | PO Procore | 25968 | 25968 |  |  | 25968
PRC 3352210PA1801 | 2022-05-17 | Inv. 54859 |  | 25968 | 1623 | 1623 | 24345
PRC 3352210PB1801 | 2022-06-10 | Inv. 55317 |  | 25968 | 9143.5 | 10766.5 | 15201.5
PRC 3352210PC1801 | 2022-06-29 | Inv. 55647 |  | 25968 | 5843 | 16609.5 | 9358.5
PO 33523101801 | 2022-08-09 | Rolled to FY23 | 0 | 25968 |  | 16609.5 | 9358.5
PO 33523101801 | 2022-08-15 | Discard FY23 PO to Pay FY22 invoice | 0 | 25968 |  | 16609.5 | 9358.5
PO 33522101801A | 2022-08-15 | Open FY22 PO to Pay FY22 Invoice | 0 | 25968 |  | 16609.5 | 9358.5
PRC 3352210PB1801A | 2022-08-16 | Inv. 55317A |  | 25968 | 270 | 16879.5 | 9088.5 | FY22
PO 33523101801A | 2022-08-16 | Rolled to FY23 | 0 | 25968 |  | 16879.5 | 9088.5
PO 3352310PD1801A | 2022-08-19 | Inv. 56108 |  | 25968 | 1298.5 | 18178 | 7790
PRC 3352310PE1801A | 2022-09-12 | Inv. 56553 |  | 25968 | 1558 | 19736 | 6232
PRC 3352310PF1801A | 2023-02-03 | Inv. 56993 |  | 25968 | 1558 | 21294 | 4674
PRC 3352310PG1801A | 2023-07-25 | Inv. 61040 |  | 25968 | 1558 | 22852 | 3116 | FY23
PO 33524101801A | 2023-07-28 | Rolled to FY24 | 0 | 25968 |  | 22852 | 3116
PRC 3352410PH1801A | 2023-09-18 | Inv. 61551 |  | 25968 | 1558 | 24410 | 1558
PRC 3352410PI1801A | 2024-01-10 | Inv. 63711-Final |  | 25968 | 1558 | 25968 | 0
|  |  |  | 25968 |  | 25968 | 0
|  |  |  | 25968 |  | 25968 | 0
|  | Total: | 25968 |  | 25968 |  | 0
|  | Design Development Documents | 6492 |  | 6492 |  | 0
|  | Construction Documents | 9089 |  | 9089 |  | 0
|  | Bidding Phase | 2597 |  | 2597 |  | 0
|  | Construction Phase | 7790 |  | 7790 |  | 0
|  | Total: | 25968 |  | 25968 |  | 0
Inv. 55317 paid short-Inv. 55317A paid remainder

## #9256.00 Modern Piping
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  | Major Program 4B01
Modern Piping |  |  | Vendor: 00002108094
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 925600-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523200902 | 2022-07-18 | PO Procore | 233490 | 233490 |  |  | 233490
PRC 3352320PA0902 | 2023-03-04 | Inv. 49282 |  | 233490 | 22614.64 | 22614.64 | 210875.36 | 1190.25
PO 33523200902 | 2023-03-23 | CO #1 | 726 | 234216 |  | 22614.64 | 211601.36
PO 33523200902 | 2023-04-21 | CO #2 (No Cost CO) | 0 | 234216 |  | 22614.64 | 211601.36
PO 33523200902 | 2023-06-01 | CO #3 (No Cost CO) | 0 | 234216 |  | 22614.64 | 211601.36 |  | FY23
PO 33524200902 | 2023-08-03 | Roll to FY24 | 0 | 234216 |  | 22614.64 | 211601.36
PO 33524200902 | 2023-08-22 | CO #4 (No Cost CO) | 0 | 234216 |  | 22614.64 | 211601.36
PO 33524200902 | 2023-09-15 | CO #5 | 1658.12 | 235874.12 |  | 22614.64 | 213259.48
PRC 3352420PB0902 | 2023-09-29 | Inv. 62805 |  | 235874.12 | 196250.13 | 218864.77 | 17009.35 | 11519.2
PRC 3352420PC0902 | 2023-12-15 | Inv. 63723 |  | 235874.12 | 2997.48 | 221862.25 | 14011.87 | 11676.97
PRC 3352420PD0902 | 2023-12-20 | Inv. 63723A-Closeout |  | 235874.12 | 2218.15 | 224080.4 | 11793.72 | 11793.72
PRC 3352420PE0902 | 2024-01-03 | Inv. 63724R-Retainage |  | 235874.12 | 11793.72 | 235874.12 | 0
|  |  |  | 235874.12 |  | 235874.12 | 0
|  | Total: | 235874.12 |  | 235874.12 |  | 0

## #9256.00 Story Construction CA
DOC ASP Vacuum Condensate System Replacement
Project # 9256.00
Program code 925600 |  |  | Major Program 4B01
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523200903 | 2022-07-18 | PO Procore | 25641.72 | 25641.72 |  |  | 25641.72
PRC 3352320PA0903 | 2022-09-20 | Inv. 33351 (revised procore to 33346) |  | 25641.72 | 4077 | 4077 | 21564.72
PRC 3352320PB0903 | 2022-10-18 | Inv. 33405 |  | 25641.72 | 441 | 4518 | 21123.72
PRC 3352320PC0903 | 2022-11-28 | Inv. 33462 |  | 25641.72 | 1272 | 5790 | 19851.72
PRC 3352320PD0903 | 2022-12-22 | Inv. 33518 |  | 25641.72 | 570 | 6360 | 19281.72
PRC 3352320PE0903 | 2023-01-23 | Inv. 33585 |  | 25641.72 | 79.5 | 6439.5 | 19202.22
PRC 3352320PF0903 | 2023-02-17 | Inv. 33633 |  | 25641.72 | 1687.5 | 8127 | 17514.72
PRC 3352320PG0903 | 2023-03-20 | Inv. 33686 |  | 25641.72 | 1753.5 | 9880.5 | 15761.22
PRC 3352320PH0903 | 2023-04-18 | Inv. 33731 |  | 25641.72 | 1167 | 11047.5 | 14594.22
PRC 3352320PI0903 | 2023-05-22 | Inv. 33786 |  | 25641.72 | 925 | 11972.5 | 13669.22
PRC 3352320PJ0903 | 2023-06-21 | Inv. 33834 |  | 25641.72 | 285 | 12257.5 | 13384.22
PRC 3352320PK0903 | 2023-07-17 | Inv. 33892 |  | 25641.72 | 2535 | 14792.5 | 10849.22 | FY23
PO 33524200903 | 2023-07-26 | Rolled to FY24 | 0 | 25641.72 |  | 14792.5 | 10849.22
PRC 3352420PL0903 | 2023-08-21 | Inv. 33949 |  | 25641.72 | 4771.5 | 19564 | 6077.72
PRC 3352420PM0903 | 2023-09-18 | Inv. 34003 |  | 25641.72 | 4026.5 | 23590.5 | 2051.22
PRC 3352420PN0903 | 2023-10-17 | Inv. 34064 |  | 25641.72 | 1434 | 25024.5 | 617.22
PO 33524200903 | 2024-01-09 | Closing PO Per PM | -617.22 | 25024.5 |  | 25024.5 | 0
|  |  |  | 25024.5 |  | 25024.5 | 0
|  | Totals: | 25024.5 |  | 25024.5 |  | 0
|  | CM Services | 24892.5 |  | 24892.5 |  | 0
|  | Reimbursables | 132 |  | 132 |  | 0
|  | Total: | 25024.5 |  | 25024.5 |  | 0
Invoice 33351 was replaced in Procore with Invoice 33346. See new invoice below, invoice already paid.

## RECAP #9257.00
DAS CC Historical Building Floor Repair
Project # 9257.00
| Program code 925700 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 778007.97
C | Neumann Monson |  | 20000 | 20000 | 0
C | PM TIME |  | 20847.96 | 20847.96 | 0
C | Misc. |  | 19002.87 | 19002.87 | 0
C | DCI Group |  | 10476.17 | 10476.17 | 0
C | Atlas Group Services(ATC Group) |  | 855 | 855 | 0
C | Ball Team |  | 611708 | 611708 | 0
C | Waldinger Electric |  | 13821.05 | 13821.05 | 0
C | DCI Group (2) |  | 81296.92 | 81296.92 | 0
| Total Project Cost | 778007.97 | 778007.97 | 778007.97 | 0 | 0
Closed 05/20/2024

## #9257.00 Neumann Monson
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
Neumann Monson |  |  | Vendor: 00002116371
Acct. Codes-0017-335-MM22-9260 |  |  | RFP 0215335040
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523319900 | 2022-11-15 | PO Procore | 20000 | 20000 |  |  | 20000
PRC 3352331PA9900 | 2023-01-10 | Inv. 9257.00-01 |  | 20000 | 4000 | 4000 | 16000
PRC 3352331PB9900 | 2023-03-20 | Inv. 9257.00-02 |  | 20000 | 8000 | 12000 | 8000
PRC 3352331PC9900 | 2023-03-29 | Inv. 9257.00-03 |  | 20000 | 2000 | 14000 | 6000
PRC 3352331PD9900 | 2023-06-30 | Inv. 9257.00-04 |  | 20000 | 4000 | 18000 | 2000 | FY23
PO 33524319900 | 2023-07-26 | Rolled to FY24 | 0 | 20000 |  | 18000 | 2000
PO 33524319900 | 2023-08-09 | CO 1 (No Cost CO) | 0 | 20000 |  | 18000 | 2000
PRC 3352431PE9900 | 2024-03-20 | Inv. 9257.00-05 |  | 20000 | 2000 | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  | Totals | 20000 |  | 20000 |  | 0 | FINAL

## #9257.00 PM TIME
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZL
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20206.52 | 20206.52 |  |  | 20206.52
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 20206.52 | 302.5 | 302.5 | 19904.02
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 20206.52 | 275 | 577.5 | 19629.02
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 536.73 | 20743.25 | 536.73 | 1114.23 | 19629.02
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 190.48 | 20933.73 | 190.48 | 1304.71 | 19629.02
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 188.78 | 21122.51 | 188.78 | 1493.49 | 19629.02
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 21122.51 | 844.97 | 2338.46 | 18784.05
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 21122.51 | 161.96 | 2500.42 | 18622.09
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 21122.51 | 1419.86 | 3920.28 | 17202.23
CDE 33523075203 | 2023-03-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | -536.73 | 20585.78 | -536.73 | 3383.55 | 17202.23
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 86.39 | 20672.17 | 86.39 | 3469.94 | 17202.23
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 49.38 | 20721.55 | 49.38 | 3519.32 | 17202.23
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 126.41 | 20847.96 | 126.41 | 3645.73 | 17202.23
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 20847.96 | 305.68 | 3951.41 | 16896.55
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 20847.96 | 1853.69 | 5805.1 | 15042.86
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 20847.96 | 245.1 | 6050.2 | 14797.76
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 20847.96 | 1078.06 | 7128.26 | 13719.7
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 20847.96 | 260.07 | 7388.33 | 13459.63
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 20847.96 | 1529.1 | 8917.43 | 11930.53
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 20847.96 | 210.53 | 9127.96 | 11720
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 20847.96 | 1476.2 | 10604.16 | 10243.8
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 20847.96 | 175.08 | 10779.24 | 10068.72
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 20847.96 | 1476 | 12255.24 | 8592.72
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 20847.96 | 133.03 | 12388.27 | 8459.69
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 20847.96 | 849 | 13237.27 | 7610.69
CDE 33524221801 | 2023-08-09 | 2507 | Move PM time to 9257.00 MM22 - 2507 |  | 20847.96 | 36.18 | 13273.45 | 7574.51
CDE 33524221801 | 2023-08-09 | 9500 | Move PM time to 9257.00 MM22 - 9500 |  | 20847.96 | 230.8 | 13504.25 | 7343.71
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 20847.96 | 118.19 | 13622.44 | 7225.52
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 20847.96 | 660.2 | 14282.64 | 6565.32
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 20847.96 | 159.46 | 14442.1 | 6405.86
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 20847.96 | 1107 | 15549.1 | 5298.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 20847.96 | 56.51 | 15605.61 | 5242.35
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 20847.96 | 455.1 | 16060.71 | 4787.25
CDE 33524312800 | 2023-11-08 | 2507 | Move PM time to 9257.00 MM22 - 2507 |  | 20847.96 | 19.07 | 16079.78 | 4768.18
CDE 33524312800 | 2023-11-08 | 9500 | Move PM time to 9257.00 MM22 - 9500 |  | 20847.96 | 151.9 | 16231.68 | 4616.28
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 20847.96 | 12.11 | 16243.79 | 4604.17
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 20847.96 | 92.8 | 16336.59 | 4511.37
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2024 |  | 20847.96 | 173.55 | 16510.14 | 4337.82
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2024 |  | 20847.96 | 1272.5 | 17782.64 | 3065.32
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 20847.96 | 215.52 | 17998.16 | 2849.8
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 20847.96 | 1084.9 | 19083.06 | 1764.9
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 20847.96 | 159.39 | 19242.45 | 1605.51
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 20847.96 | 1206.7 | 20449.15 | 398.81
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 20847.96 | 40.31 | 20489.46 | 358.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 20847.96 | 358.5 | 20847.96 | -6.6507e-12
[5 empty] | 20847.96 |  | 20847.96 | -6.6507e-12
[5 empty] | 20847.96 |  | 20847.96 | -6.6507e-12
[5 empty] | 20847.96 |  | 20847.96 | -6.6507e-12
[5 empty] | 20847.96 |  | 20847.96 | -6.6507e-12
|  |  | Totals | 20847.96 |  | 20847.96 |  | 0
Note on E9: Huggins, Joni [DAS]: 9257.00 PM Budget MM22 $Joni Herman, Josh 12:18 PM (15 minutes ago) to me Please set to $5,500. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9257.00 - Increase PM Time budget Inbox Elliott, Jennie 12:49 PM (3 minutes ago) to DAS, me Please increase the PM time budget in 9257.00 by $13,858.56 to create a total PM time budget of $20,000 Thank you Re: Completed: 9257.00 - SHB Atrium Flooring - Ball Team, LLC CO #4 $John Elliott, Jennie 2:45 PM (0 minutes ago) to me Sorry, that should be $17,913.79! Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov On Thu, Jul 20, 2023 at 2:43 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Please reduce contracted PM time to $17,913.82 Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Re: PM Time $John Elliott, Jennie 6:50 AM (1 hour ago) to me Please see comments below. Increase PM Time budget to total of $21,855.79 9257.00 - DAS CC Historical Building Floor Repair FY24 Elliott, Jennie 8:26 AM (51 minutes ago) to me Can you please reduce the PM Time budget in 9257.00 - DAS CC Historical Building Floor Repair by $2,000; making the total PM Time Contracted $19,855.79. Thank you, Jennie Elliott

## #9257.00 Misc
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523065900 | 2023-03-04 | 9500 | CNST | Beeline+Blue V#(00002108204) | Inv. INV027724 | 104.49 | 104.49
GAX 33523111900 | 2023-04-21 | 9500 | CNST | Service Master by Rice (AJS) V#(00002116069) | Inv. 16-15905-MLD | 11352.92 | 11457.41
IET DAS202311115300001 | 2023-06-07 | 2507 |  | Swap Smoke Heads to Heat Heads 207140577 | DAS2023111153 | 312.51 | 11769.92
IET DAS202311115300001 | 2023-06-07 | 2507 |  | Head Swap for Phase 2 207141966 | DAS2023111153 | 460.05 | 12229.97
IET DAS202312115300001 | 2023-07-07 | 2507 |  | Heating/Ventilation/Air Conditioning/Plumbing | DAS2023121153 | 2034.59 | 14264.56
GAX 33524011904 | 2024-01-11 | 9500 | CNST | Proctor Mechanical V#(00003166259) | Inv. 901692 | 4738.31 | 19002.87
19002.87
19002.87
19002.87
19002.87
19002.87
19002.87
|  |  |  | Totals |  | 19002.87

## #9257.00 DCI Group
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523326900 | 2022-11-22 | PO Procore | 10476.17 | 10476.17 |  |  | 10476.17
PRC 3352332PA6900 | 2023-01-18 | Inv. 22-041 PC-01 |  | 10476.17 | 4962.32 | 4962.32 | 5513.85
PRC 3352332PB6900 | 2023-03-20 | Inv. 22-041 PC-02 Final |  | 10476.17 | 5513.85 | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  |  |  | 10476.17 |  | 10476.17 | 0
|  | Totals | 10476.17 |  | 10476.17 |  | 0

## #9257.00 Atlas Group Services
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
Atlas Group Services(ATC Group) |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA20262B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523017801 | 2023-01-17 | DO Procore | 855 | 855 |  |  | 855
PRC 3352301PA7801 | 2023-01-27 | Inv. 2476320-final |  | 855 | 855 | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  |  |  | 855 |  | 855 | 0
|  | Totals | 855 |  | 855 |  | 0
|  | Asbestos Per Sample Fee (7 samples @ $10/sample) | 170 |  | 170 |  | 0
|  | Adminstracton Time (1 Hour @ $45/hour) | 45 |  | 45 |  | 0
|  | Field Technician (6 hours @ $75/hour | 450 |  | 450 |  | 0
|  | Hygienist (2 hours @ $95/hour) | 190 |  | 190 |  | 0
|  | Total: | 855 |  | 855 |  | 0

## #9257.00 Ball Team
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
Ball Team |  |  | Vendor: 00003090419
Acct. Codes-0017-335-MM22-9255 |  |  | RFB925700-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523061803 | 2023-03-02 | PO Procore | 558834 | 558834 |  |  | 558834
PRC 3352306PA1803 | 2023-04-26 | Inv. 9257.00-01 |  | 558834 | 142967.4 | 142967.4 | 415866.6 | 7524.6
PRC 3352306PB1803 | 2023-05-08 | Inv. 9257.00-02 |  | 558834 | 93812.5 | 236779.9 | 322054.1 | 12462.1
PRC 3352306PC1803 | 2023-06-13 | Inv. 9257.00-03 |  | 558834 | 95040.85 | 331820.75 | 227013.25 | 17464.25
PO 33523061803 | 2023-06-15 | CO #1 | 17416 | 576250 |  | 331820.75 | 244429.25
PO 33523061803 | 2023-06-21 | CO #2 | 1210 | 577460 |  | 331820.75 | 245639.25
PO 33523061803 | 2023-07-06 | CO #3 (Split between MM22 and DA23) | 34055 | 611515 |  | 331820.75 | 279694.25
PRC 3352306PD1803 | 2023-07-07 | Inv. 9257.00-04 (100% to MM22) |  | 611515 | 106922.5 | 438743.25 | 172771.75 | 23091.75
PO 33523061803 | 2023-07-19 | CO #4 (100% to MM22) | 4135 | 615650 |  | 438743.25 | 176906.75 |  | FY23
PO 33524061803 | 2023-08-22 | Roll to FY24 | 0 | 615650 |  | 438743.25 | 176906.75
PRC 3352406PE1803 | 2023-08-23 | Inv. 9257.00-05 (Split between MM22 and DA23) |  | 615650 | 47038.3 | 485781.55 | 129868.45 | 25567.45
PRC 3352406PF1803 | 2023-09-18 | Inv. 9257.00-06 (Split between MM22 and DA23) |  | 615650 | 90031.5 | 575813.05 | 39836.95 | 30305.95
PO 33524061803 | 2023-09-20 | CO #5 (Voided in Procore) | 0 | 615650 |  | 575813.05 | 39836.95
PO 33524061803 | 2023-09-20 | CO #6 (100% to MM22) | -3942 | 611708 |  | 575813.05 | 35894.95
PRC 3352406PG1803 | 2023-11-21 | Inv. 9257.00-07 (100% to MM22) |  | 611708 | 5308.6 | 581121.65 | 30586.35 | 30585.35
PRC 3352406PH1803 | 2023-12-27 | Inv. 9257.00-08 (100% to MM22) |  | 611708 | 0.95 | 581122.6 | 30585.4 | 30585.4
PRC 3352406PI1803 | 2024-01-03 | Inv. 9257.00-09-Retainage(Split between MM22 &DA23) |  | 611708 | 30585.4 | 611708 | 0
|  |  |  | 611708 |  | 611708 | 0
|  | Totals | 611708 |  | 611708 |  | 0
|  | DA23 | 25000 |  | 25000 |  | 0
|  | Total: | 636708 |  | 636708 |  | 0
***Stored Materials Breakdown. Current store materials are subtracted from the invoice totals****
|  |  | Store Materials | Store Materials | C**+E**-D**
|  | Total Payment | Previous Invoice | Current Invoice | Actual Payment | Less Retainage
3352306PA1803 | 2023-04-26 | 98038 | 0 | 52454.00 | 150492 | 142967.4
3352306PB1803 | 2023-05-08 | 98750 | 52454.00 | 52454.00 | 98750 | 93812.5
3352306PC1803 | 2023-06-13 | 100043 | 52454.00 | 52454.00 | 100043 | 95040.85
3352306PD1803 | 2023-07-07 | 165004 | 52454.00 | 0 | 112550 | 106922.5
3352406PE1803 | 2023-08-23 | 49514 | 0 | 0 | 49514 | 47038.3
3352406PF1803 | 2023-09-18 | 94770 | 0 | 0 | 94770 | 90031.5
3352406PG1803 | 2023-11-21 | 5588 | 0 | 0 | 5588 | 5308.6
3352406PH1803 | 2023-12-27 | 0 | 0 | 0 | 0 | 0

## #9257.00 Waldinger Electric
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
Waldinger Electric |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | MA 20452
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523081802 | 2023-03-22 | PO Procore | 26086 | 26086 |  |  | 26086
PRC 3352308PA1802 | 2023-07-21 | Inv. 71307E-001 |  | 26086 | 10511.25 | 10511.25 | 15574.75 | 553.22 | FY23
PO 33524081802 | 2023-07-26 | Rolled to FY24 | 0 | 26086 |  | 10511.25 | 15574.75
PO 33524081802 | 2023-10-16 | CO #1 (No Cost) | 0 | 26086 |  | 10511.25 | 15574.75
PRC 3352408PB1802 | 2024-01-24 | Inv. 71307E-002 |  | 26086 | 2618.75 | 13130 | 12956 | 691.05
PO 33524081802 | 2024-02-14 | CO #2 | -11573.9 | 14512.1 |  | 13130 | 1382.1
PO 33524081802 | 2024-03-18 | CO #3 | -691.05 | 13821.05 |  | 13130 | 691.05
PRC 3352408PC1802 | 2024-04-23 | Inv. 71307E-003 Retainage |  | 13821.05 | 691.05 | 13821.05 | 0
|  |  |  | 13821.05 |  | 13821.05 | 0
|  |  |  | 13821.05 |  | 13821.05 | 0
|  |  |  | 13821.05 |  | 13821.05 | 0
|  |  |  | 13821.05 |  | 13821.05 | 0
|  |  |  | 13821.05 |  | 13821.05 | 0
|  | Totals | 13821.05 |  | 13821.05 |  | 0 | FINAL

## #9257.00 DCI Group (2)
DAS CC Historical Building Floor Repair
Project # 9257.00
Program code 925700 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523082900 | 2023-03-22 | PO Procore | 73386.44 | 73386.44 |  |  | 73386.44
PRC 3352308PA2900 | 2023-05-15 | Inv. 22-041 CA-01 |  | 73386.44 | 2964.55 | 2964.55 | 70421.89
PO 33523082900 | 2023-06-01 | CO #1 | 2009.48 | 75395.92 |  | 2964.55 | 72431.37
PRC 3352308PB2900 | 2023-06-28 | Inv. 22-041 CA-02 |  | 75395.92 | 36799.52 | 39764.07 | 35631.85
PO 33523082900 | 2023-07-26 | CO #2 | 10000 | 85395.92 |  | 39764.07 | 45631.85
PRC 3352308PC2900 | 2023-07-28 | Inv. 22-041 CA 03 |  | 85395.92 | 21780.44 | 61544.51 | 23851.41 | FY23
PO 33524082900 | 2023-08-03 | Roll to FY24 | 0 | 85395.92 |  | 61544.51 | 23851.41
PRC 3352408PD2900 | 2023-10-06 | Inv. 22-041 CA-04 |  | 85395.92 | 18909.82 | 80454.33 | 4941.59
PRC 3352408PE2900 | 2023-11-21 | Inv. 22-041 CA 05 |  | 85395.92 | 616.57 | 81070.9 | 4325.02
PRC 3352408PF2900 | 2023-12-19 | Inv. 22-041 CA-06 FINAL | -4099 | 81296.92 | 226.02 | 81296.92 | 0
|  |  |  | 81296.92 |  | 81296.92 | 0
|  |  |  | 81296.92 |  | 81296.92 | 0
|  |  |  | 81296.92 |  | 81296.92 | 0
|  | Totals | 81296.92 |  | 81296.92 |  | 0 | FINAL
|  | CM Staff Hours | 36878.69 |  | 36878.69 |  | 0
|  | Project Fee | 30006.36 |  | 30006.36 |  | 0
|  | Reimbursable Expense | 6500 |  | 6500 |  | 0
|  | CO #1 | 2009.48 |  | 2009.48 |  | 0
|  | CO #2 | 5902.39 |  | 5902.39 |  | 0
|  | Total: | 81296.92 |  | 81296.92 |  | 0

## RECAP #9258.00
DAS CC Hoover East Side Ice Mitigation
Project # 9258.00
| Program code 925800 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 42460.74
C | DCI Group |  | 6239.36 | 6239.36 | 0
C | PM TIME |  | 17114.05 | 17114.05 | 0
C | Misc. |  | 955.33 | 955.33 | 0
C | Shive Hattery |  | 18152 | 18152 | 0
C
| Total Project Cost | 42460.74 | 42460.74 | 42460.74 | 0 | 0
CLOSED 05/28/2024

## #9258.00 DCI Group
DAS CC Hoover East Side Ice Mitigation
Project # 9258.00
Program code 925800 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522019802 | 2022-01-19 | PO Procore | 6246.81 | 6246.81 |  |  | 6246.81
PRC 3352201PA9802 | 2022-06-23 | Inv. 21-055 PC-01 |  | 6246.81 | 5466.03 | 5466.03 | 780.78
PRC 3352201PB9802 | 2022-07-19 | Inv. 21-055 PC-02 Final | -7.45 | 6239.36 | 773.33 | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  |  |  | 6239.36 |  | 6239.36 | 6.1373e-13
|  | Totals: | 6239.36 |  | 6239.36 |  | 0

## #9258.00 PM TIME
DAS CC Hoover East Side Ice Mitigation
Project # 9258.00
Program code 925800 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E1ZM
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14947.61 | 14947.61 |  |  | 14947.61
IET DAS202205115300001 | 2021-12-07 |  | PM-Nov 1-Nov 30, 2021 |  | 14947.61 | 125 | 125 | 14822.61
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 14947.61 | 475 | 600 | 14347.61
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 14947.61 | 275 | 875 | 14072.61
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 14947.61 | 300 | 1175 | 13772.61
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 14947.61 | 225 | 1400 | 13547.61
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 14947.61 | 275 | 1675 | 13272.61
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 14947.61 | 375 | 2050 | 12897.61
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 14947.61 | 575 | 2625 | 12322.61
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 14947.61 | 1000 | 3625 | 11322.61
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 14947.61 | -1000 | 2625 | 12322.61
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 14947.61 | 1100 | 3725 | 11222.61
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 14947.61 | 330 | 4055 | 10892.61
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 14947.61 | 577.5 | 4632.5 | 10315.11
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 14947.61 | 247.5 | 4880 | 10067.61
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 14947.61 | 55 | 4935 | 10012.61
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 829.65 | 15777.26 | 829.65 | 5764.65 | 10012.61
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 280.6 | 16057.86 | 280.6 | 6045.25 | 10012.61
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 310.8 | 16368.66 | 310.8 | 6356.05 | 10012.61
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 180.72 | 16549.38 | 180.72 | 6536.77 | 10012.61
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 42.17 | 16591.55 | 42.17 | 6578.94 | 10012.61
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16591.55 | 281.8 | 6860.74 | 9730.81
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16591.55 | 83.57 | 6944.31 | 9647.24
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16591.55 | 732.62 | 7676.93 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 111.54 | 16703.09 | 111.54 | 7788.47 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 194.49 | 16897.58 | 194.49 | 7982.96 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 148.61 | 17046.19 | 148.61 | 8131.57 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 15.37 | 17061.56 | 15.37 | 8146.94 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 10.34 | 17071.9 | 10.34 | 8157.28 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 42.15 | 17114.05 | 42.15 | 8199.43 | 8914.62
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 17114.05 | 152.33 | 8351.76 | 8762.29
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 17114.05 | 923.72 | 9275.48 | 7838.57
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 17114.05 | 225.29 | 9500.77 | 7613.28
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 17114.05 | 990.94 | 10491.71 | 6622.34
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 17114.05 | 77.45 | 10569.16 | 6544.89
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 17114.05 | 458 | 11027.16 | 6086.89
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 17114.05 | 49.3 | 11076.46 | 6037.59
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 17114.05 | 344.3 | 11420.76 | 5693.29
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 17114.05 | 15.66 | 11436.42 | 5677.63
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 17114.05 | 115.1 | 11551.52 | 5562.53
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 17114.05 | 36.61 | 11588.13 | 5525.92
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 17114.05 | 231.9 | 11820.03 | 5294.02
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 17114.05 | 93.7 | 11913.73 | 5200.32
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 17114.05 | 525.2 | 12438.93 | 4675.12
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 17114.05 | 32.7 | 12471.63 | 4642.42
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 17114.05 | 227 | 12698.63 | 4415.42
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 17114.05 | 58.03 | 12756.66 | 4357.39
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 17114.05 | 465.5 | 13222.16 | 3891.89
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 17114.05 | 55.57 | 13277.73 | 3836.32
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 17114.05 | 420.3 | 13698.03 | 3416.02
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 17114.05 | 88.72 | 13786.75 | 3327.3
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 17114.05 | 650.5 | 14437.25 | 2676.8
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 17114.05 | 50.68 | 14487.93 | 2626.12
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 17114.05 | 443.3 | 14931.23 | 2182.82
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 17114.05 | 164.89 | 15096.12 | 2017.93
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 17114.05 | 829.9 | 15926.02 | 1188.03
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 17114.05 | 45.33 | 15971.35 | 1142.7
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 17114.05 | 341.1 | 16312.45 | 801.6
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 17114.05 | 81.3 | 16393.75 | 720.3
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 17114.05 | 720.3 | 17114.05 | 0
[5 empty] | 17114.05 |  | 17114.05 | 0
[5 empty] | 17114.05 |  | 17114.05 | 0
[5 empty] | 17114.05 |  | 17114.05 | 0
|  |  | Totals: | 17114.05 |  | 17114.05 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: Fwd: MM22 PM Time Inbox Trower, James 9:31 AM (6 minutes ago) to me, Scott, Josh Jennifer - I want to clarify that I am requesting DAS Finance to set up PM Time for the following new projects (Josh Herman and I will both have PM Time on 9249.00 and 9250.00): 9249.00 - DOC MPCF Front Steps Repair: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9250.00 - DOC MPCF Building 18 Roof Replacement: $8,000 (James Trower: $6,000 & Josh Herman: $2,000) 9251.00 - DPS P09 Parking Lot Replacement: $4,000 (James Trower: $4,000) 9252.00 - DPS P09 Window Replacement: $4,000 (James Trower: $4,000) 9258.00 - DAS CC Hoover East Side Ice Mitigation: $4,000 (James Trower: $4,000) Please call me at 515-380-8049 when you have a moment. Thanks, James James Trower, AIA, LEED AP James Trower PM Time Increases $Joni Trower, James 2:31 PM (3 minutes ago) to me Finance - Please see the below projects that need PM Time increases: 9201.00 (MM20): Increase PM Time by $2,000 9209.00 (DA21): Increase PM Time by $1,000 9225.00 (MM20): Increase PM Time by $5,000 9258.00 (MM22): Increase PM Time by $3,000 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Re: PM Time Inbox Trower, James 2:58 PM (8 minutes ago) to me John - See below: 9258.00 MM22: Please increase PM Time by $5,000 9231.00 MM22 Please increase PM Time by $3,000

## #9258.00 Misc
DAS CC Hoover East Side Ice Mitigation
Project # 9258.00
Program code 925800 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522208800 | 2022-07-26 | 9500 | BRUM | Elite Glass & Metal V#(00003078283) | Inv. SM17198A | 650 | 650
CDE 33523069903 | 2023-03-10 | 9500 | BRUM | Move Waldinger Inv. 66880E-001 expense from 9259.00 to 9258.00 |  | 305.33 | 955.33
955.33
955.33
955.33
955.33
955.33
955.33
955.33
955.33
955.33
955.33
|  |  |  | Totals |  | 955.33

## #9258.00 Shive Hattery
DAS CC Hoover East Side Ice Mitigation
Project # 9258.00
Program code 925800 |  |  | Major Program 4E19
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | IRFP925800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522143904 | 2022-05-23 | PO Procore | 16668 | 16668 |  |  | 16668
PRC 3352214PA3904 | 2022-06-07 | Inv. 2142203490-1 |  | 16668 | 3960 | 3960 | 12708
PRC 3352214PB3904 | 2022-07-08 | Inv. 2142203490-2 |  | 16668 | 5462.56 | 9422.56 | 7245.44 | FY22
PO 33523143904 | 2022-08-09 | Rolled to FY23 | 0 | 16668 |  | 9422.56 | 7245.44
PO 33523143904 | 2022-10-04 | CO 1 | 1484 | 18152 |  | 9422.56 | 8729.44
PRC 3352314PC3904 | 2022-10-14 | Inv. 2142203490-3 |  | 18152 | 3429.44 | 12852 | 5300
PRC 3352314PD3904 | 2023-07-18 | Inv. 2142203490-4 |  | 18152 | 795 | 13647 | 4505 | FY23
PO 33524143904 | 2023-08-14 | Rolled to FY23 | 0 | 18152 |  | 13647 | 4505
PRC 3352414PE3904 | 2023-10-03 | Inv. 2142203490-5 |  | 18152 | 3445 | 17092 | 1060
PRC 3352414PF3904 | 2024-05-28 | Inv. 2142203490-6FINAL |  | 18152 | 1060 | 18152 | 0
|  |  |  | 18152 |  | 18152 | 0
|  |  |  | 18152 |  | 18152 | 0
|  |  |  | 18152 |  | 18152 | 0
|  | Totals: | 18152 |  | 18152 |  | 0 | FINAL
|  | Design Development | 6600 |  | 6600 |  | 0
|  | Construction Documents | 3068 |  | 3068 |  | 0
|  | Bidding Assistance | 1700 |  | 1700 |  | 0
|  | Construction Phase | 5300 |  | 5300 |  | 0
|  | CO 1 | 1484 |  | 1484 |  | 0
|  | Total: | 18152 |  | 18152 |  | 0

## RECAP #9259.00
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
| Program code 925900 |  |  | Major Program 3G01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Doug C.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 688485.9
C | DCI Group |  | 10353.97 | 10353.97 | 0
C | PM TIME |  | 16438.73 | 16438.73 | 0
C | Misc. |  | 8237.58 | 8237.58 | 0
C | Bolton & Menk |  | 43442 | 43442 | 0
C | DCI Group CA |  | 121193.97 | 121193.97 | 0
C | Iowa Contracting |  | 488819.65 | 488819.65 | 0
| Total Project Cost | 688485.9 | 688485.9 | 688485.9 | 0 | 0
Closed 01/18/2023
Opened 03/27/2023 for misc invoice
Closed 04/07/23

## #9259.00 DCI Group
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Doug C. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522033900 | 2022-02-01 | PO Procore | 10426.88 | 10426.88 |  |  | 10426.88
PRC 3352203PA3900 | 2022-04-25 | Inv. 21-056-01 |  | 10426.88 | 3409.9 | 3409.9 | 7016.98
PRC 3352203PB3900 | 2022-04-25 | Inv. 21-056-02 |  | 10426.88 | 2727.53 | 6137.43 | 4289.45
PRC 3352203PC3900 | 2022-06-23 | Inv. 21-056-03 |  | 10426.88 | 3353.51 | 9490.94 | 935.94
PRC 3352203PD3900 | 2022-07-18 | Inv. 21-056 PC-04 FINAL | -72.91 | 10353.97 | 863.03 | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  |  |  | 10353.97 |  | 10353.97 | -1.279e-12
|  | Totals: | 10353.97 |  | 10353.97 |  | 0

## #9259.00 PM TIME
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx |  |  | eDAS E1ZN
Project Manager - Doug C.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 12796.74 | 12796.74 |  |  | 12796.74
IET DAS202205115300001 | 2021-12-07 | PM-Nov 1-Nov 30, 2021 |  | 12796.74 | 50 | 50 | 12746.74
IET DAS202206115300001 | 2022-01-07 | PM-Dec 1-Dec30, 2021 |  | 12796.74 | 850 | 900 | 11896.74
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 12796.74 | 1000 | 1900 | 10896.74
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 12796.74 | 650 | 2550 | 10246.74
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 12796.74 | 1050 | 3600 | 9196.74
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 12796.74 | 400 | 4000 | 8796.74
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 12796.74 | 800 | 4800 | 7996.74
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 12796.74 | 800 | 5600 | 7196.74
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 12796.74 | 950 | 6550 | 6246.74
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 12796.74 | -950 | 5600 | 7196.74
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 12796.74 | 1045 | 6645 | 6151.74
CDE 33523230901 | 2022-08-18 | Moving PM Time expense from DA22 9259.00 |  | 12796.74 | 100 | 6745 | 6051.74
CDE 33523236902 | 2022-08-01 | Moving PM Time expense from DA22 9259.00 |  | 12796.74 | 10 | 6755 | 6041.74
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 12796.74 | 935 | 7690 | 5106.74
CDE 33523256902 | 2022-09-13 | Moving PM Time Expense From R20M 9259.00 |  | 12796.74 | 55 | 7745 | 5051.74
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 12796.74 | 1265 | 9010 | 3786.74
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 12796.74 | 935 | 9945 | 2851.74
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30,2022 |  | 12796.74 | 1320 | 11265 | 1531.74
IET DAS202305115300001 | 2022-12-07 | PM-July 1-July 29, 2022 9997.23 Disbursement | 279.65 | 13076.39 | 279.65 | 11544.65 | 1531.74
IET DAS202205115300001 | 2022-12-07 | PM Time-Aug 9997.23 disbursement | 806.31 | 13882.7 | 806.31 | 12350.96 | 1531.74
IET DAS202205115300001 | 2022-12-07 | PM Time-Sep 9997.23 disbursement | 839.67 | 14722.37 | 839.67 | 13190.63 | 1531.74
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 657.53 | 15379.9 | 657.53 | 13848.16 | 1531.74
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 1058.83 | 16438.73 | 1058.83 | 14906.99 | 1531.74
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 16438.73 | 1531.74 | 16438.73 | 0
|  |  |  | 16438.73 |  | 16438.73 | 0
|  | Totals: | 16438.73 |  | 16438.73 |  | 0

## #9259.00 Misc
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  |  | Major Program 3G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Doug C.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522180900 | 2022-06-29 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. 021646 | 102.32 | 102.32
PRC 33522181901 | 2022-06-29 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. 021235 | 178.21 | 280.53
GAX 33522217900 | 2022-08-05 | 9500 | BRUM | Waldinger V#(00002116105) | Inv. 66880E-001 | 305.33 | 585.86
GAX 33523318800 | 2022-11-14 | 9500 | CNST | Team Services Inc. V#(00002121153) | Inv. 1812611-0, 1811720-0, 1812188-0 | 7822.8 | 8408.66
CDE 33523069903 | 2023-03-10 | 9500 | BRUM | Move Waldinger Inv. 66880E-001 expense from 9259.00 to 9258.00 |  | -305.33 | 8103.33
GAX 33523094901 | 2023-04-04 | 9500 | CNST | Team Services Inc. V#(00002121153) | Inv. 1813151-0 | 134.25 | 8237.58
8237.58
8237.58
8237.58
8237.58
8237.58
8237.58
|  |  |  | Totals |  | 8237.58

## #9259.00 Bolton & Menk
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
Bolton & Menk |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM22-9255 |  |  | RFP925900-01
Project Manager - Doug C. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522041901 | 2022-02-10 | PO Procore | 43442 | 43442 |  |  | 43442
PRC 3352204PA1901 | 2022-07-19 | Inv. 0285848, 0285850 (Split w/R20M) |  | 43442 | 34494 | 34494 | 8948
PRC 3352204PB1901 | 2022-08-01 | Inv. 0291358,0291359 (Split w/R20M) |  | 43442 | 2000 | 36494 | 6948 | FY22
PO 33523041901 | 2022-08-16 | Rolled to FY23 | 0 | 43442 |  | 36494 | 6948
PRC 3352304PC1901 | 2022-09-07 | Inv. 0295090, 0295091 (split with R20M) |  | 43442 | 1737 | 38231 | 5211
PRC 3352304PD1901 | 2022-10-12 | Inv. 0297906, 0297908(Split with R20M) |  | 43442 | 3474 | 41705 | 1737
PRC 3352304PE1901 | 2022-11-04 | Inv. 0299896 (100% to R20M) |  | 43442 | 0 | 41705 | 1737
PRC 3352304PF1901 | 2022-12-07 | Inv. 0301932 (100% to MM22) |  | 43442 | 1737 | 43442 | 0
|  |  |  | 43442 |  | 43442 | 0
|  |  |  | 43442 |  | 43442 | 0
|  |  |  | 43442 |  | 43442 | 0
|  |  |  | 43442 |  | 43442 | 0
|  |  |  | 43442 |  | 43442 | 0
|  | Totals: | 43442 |  | 43442 |  | 0
|  | Construction Documents 50% | 22596 |  | 22596 |  | 0
|  | Construction Documents 100% | 11898 |  | 11898 |  | 0
|  | Bidding Assistance | 2000 |  | 2000 |  | 0
|  | Construction Phase | 6948 |  | 6948 |  | 0
|  | Total: | 43442 |  | 43442 |  | 0
|  | R20M (Closed) | 3644 |  | 3644 |  | 0
|  | Total Contract: | 47086 |  | 47086 |  | 0

## #9259.00 DCI Group CA
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
DCI Group CA |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Doug C. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523200904 | 2022-07-18 | PO Procore | 121193.97 | 121193.97 |  |  | 121193.97
PRC 3352320PA0904 | 2022-09-20 | Inv. 21-056 CA-01 |  | 121193.97 | 79193.58 | 79193.58 | 42000.39
PRC 3352320PB0904 | 2022-11-08 | Inv. 21-056 CA-02 |  | 121193.97 | 27048.23 | 106241.81 | 14952.16
PRC 3352320PC0904 | 2022-11-14 | Inv. 21-056 CA-03 FINAL |  | 121193.97 | 14952.16 | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  |  |  | 121193.97 |  | 121193.97 | 0
|  | Totals: | 121193.97 |  | 121193.97 |  | 0 | FINAL
|  | Construction Management | 57774.67 |  | 57774.67 |  | 0
|  | Construction Fee | 63419.3 |  | 63419.3 |  | 0
|  | Total: | 121193.97 |  | 121193.97 |  | 0

## #9259.00 Iowa Contracting
DAS CC Finkbine St Paving and Parking Lot 5 Replacement
Project # 9259.00
Program code 925900 |  |  | Major Program 3G01
Iowa Contracting |  |  | Vendor: 00003106386
Acct. Codes-0017-335-MM22-9255 |  |  | RFB925900-02
Project Manager - Doug C. |  |  | Activity code: BRUM
Split with DA22 & R21M
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523206900 | 2022-07-18 | PO Procore | 968386 | 968386 |  |  | 968386
PRC 3352320PA6900 | 2022-09-12 | Inv. 9259.00-001(Split with DA22, MM22, & R21M) |  | 968386 | 489250 | 489250 | 479136 | 25750
PO 33523206900 | 2022-10-19 | CO 1(100% to MM22) | 29963.5 | 998349.5 |  | 489250 | 509099.5
PO 33523206900 | 2022-11-02 | CO 2(100% to MM22) | 15737 | 1014086.5 |  | 489250 | 524836.5
PRC 3352320PB6900 | 2022-11-08 | Inv. 9259.00-002(Split with DA22, MM22, & R21M) |  | 1014086.5 | 447132.36 | 936382.36 | 77704.14 | 49283.28
PRC 3352320PC6900 | 2022-12-12 | Inv. 9259.00-003(100% to MM22) |  | 1014086.5 | 26999.82 | 963382.18 | 50704.32 | 50704.32
PRC 3352320PD6900 | 2022-12-19 | Inv. 9259.00-004 Retainage (Split with DA22, MM22, & R21M) |  | 1014086.5 | 50704.32 | 1014086.5 | 0
CDE 33523164900 | 2023-06-13 | Move Expenses from MM22 | -525266.85 | 488819.65 | -525266.85 | 488819.65 | 0
|  |  |  | 488819.65 |  | 488819.65 | 0
|  |  |  | 488819.65 |  | 488819.65 | 0
|  |  |  | 488819.65 |  | 488819.65 | 0
|  |  |  | 488819.65 |  | 488819.65 | 0
|  |  |  | 488819.65 |  | 488819.65 | 0
|  | Totals: | 488819.65 |  | 488819.65 |  | 0
|  | R21M | 60000 |  | 60000 |  | 0
|  | DA22 | 240000 |  | 240000 |  | 0
|  | Total Contract: | 788819.65 |  | 788819.65 |  | 0

## RECAP #9262.00
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
| Program code 926200 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 837665.11
C | ATC Group Services |  | 4162.5 | 4162.5 | 0
| PM TIME |  | 23063.11 | 21499.39 | 1563.72
| Misc. |  | 2720.81 | 2720.81 | 0
| Shive Hattery |  | 64725 | 59786.75 | 4938.25
C | Story Construction PC |  | 13148.28 | 13148.28 | 0
C | Proctor Mechanical |  | 3858.88 | 3858.88 | 0
C | Story Construction CA |  | 9440.5 | 9440.5 | 0
| Story Construction CA2 |  | 61749.64 | 61257.47 | 492.17
C | Mahoney Fire Sprinkler |  | 564026.29 | 564026.29 | 0
C | Controlled Asbestos |  | 9476.16 | 9476.16 | 0
C | Siemens Industry |  | 43375.46 | 43375.46 | 0
| Kone Inc |  | 21859 | 19816.05 | 2042.95
| Total Project Cost | 837665.11 | 821605.63 | 812568.54 | 9037.09 | 16059.48

## #9262.00 ATC Group Services
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
ATC Group Services |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B: MA20262A
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522350800 | 2021-12-14 | DO Procore | 6860 | 6860 |  |  | 6860
PRC 3352235PA0800 | 2022-02-04 | Inv. 2401760-Final | -2697.5 | 4162.5 | 4162.5 | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  |  |  | 4162.5 |  | 4162.5 | 0
|  | Totals: | 4162.5 |  | 4162.5 |  | 0
|  | Contract Line 2 - Asbestos Per Sample Fee (250 samples at $10/sample) | 890 |  | 890 |  | 0
|  | Contract Line 3 - Lead Paint Per Sample Fee (15 samples at $15/sample) | 0 |  |  |  | 0
|  | Contract Line 5 - Administrative Hourly Rate (1 hour at $45/hour) | 45 |  | 45 |  | 0
|  | Contract Line 7 - Field Technician Hourly Rate (52 hours at $75/hour) | 3037.5 |  | 3037.5 |  | 0
|  | Contract Line 8 - Hygienist Hourly Rate (2 hours at $95/hour) | 190 |  | 190 |  | 0
|  | Total: | 4162.5 |  | 4162.5 |  | 0

## #9262.00 PM TIME
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907E
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20400 | 20400 |  |  | 20400
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 20400 | 275 | 275 | 20125
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 20400 | 800 | 1075 | 19325
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 20400 | 600 | 1675 | 18725
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 20400 | 675 | 2350 | 18050
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 20400 | 125 | 2475 | 17925
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 20400 | 250 | 2725 | 17675
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 20400 | 400 | 3125 | 17275
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 20400 | 400 | 3525 | 16875
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 20400 | -400 | 3125 | 17275
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 20400 | 440 | 3565 | 16835
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 20400 | 440 | 4005 | 16395
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 20400 | 660 | 4665 | 15735
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 20400 | 412.5 | 5077.5 | 15322.5
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 20400 | 192.5 | 5270 | 15130
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 664.05 | 21064.05 | 664.05 | 5934.05 | 15130
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 406.22 | 21470.27 | 406.22 | 6340.27 | 15130
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 411.97 | 21882.24 | 411.97 | 6752.24 | 15130
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 324.26 | 22206.5 | 324.26 | 7076.5 | 15130
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 192.63 | 22399.13 | 192.63 | 7269.13 | 15130
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 22399.13 | 716.33 | 7985.46 | 14413.67
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 22399.13 | 93.64 | 8079.1 | 14320.03
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 22399.13 | 820.85 | 8899.95 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 101.77 | 22500.9 | 101.77 | 9001.72 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 119.8 | 22620.7 | 119.8 | 9121.52 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 78.46 | 22699.16 | 78.46 | 9199.98 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 215.79 | 22914.95 | 215.79 | 9415.77 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 41 | 22955.95 | 41 | 9456.77 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 107.16 | 23063.11 | 107.16 | 9563.93 | 13499.18
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 23063.11 | 164.9 | 9728.83 | 13334.28
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 23063.11 | 999.96 | 10728.79 | 12334.32
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 23063.11 | 101.35 | 10830.14 | 12232.97
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 23063.11 | 445.78 | 11275.92 | 11787.19
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 23063.11 | 46.76 | 11322.68 | 11740.43
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 23063.11 | 274.6 | 11597.28 | 11465.83
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 23063.11 | 89.29 | 11686.57 | 11376.54
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 23063.11 | 624.8 | 12311.37 | 10751.74
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 23063.11 | 88.91 | 12400.28 | 10662.83
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 23063.11 | 758.7 | 13158.98 | 9904.13
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 23063.11 | 116.33 | 13275.31 | 9787.8
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 23063.11 | 743.7 | 14019.01 | 9044.1
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 23063.11 | 219.68 | 14238.69 | 8824.42
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 23063.11 | 1227.5 | 15466.19 | 7596.92
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 23063.11 | 59.56 | 15525.75 | 7537.36
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 23063.11 | 413.5 | 15939.25 | 7123.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 23063.11 | 97.43 | 16036.68 | 7026.43
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 23063.11 | 783.5 | 16820.18 | 6242.93
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 23063.11 | 70.74 | 16890.92 | 6172.19
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 23063.11 | 535.5 | 17426.42 | 5636.69
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 23063.11 | 57.29 | 17483.71 | 5579.4
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 23063.11 | 419.8 | 17903.51 | 5159.6
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 23063.11 | 99.43 | 18002.94 | 5060.17
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 23063.11 | 872.9 | 18875.84 | 4187.27
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 23063.11 | 78.68 | 18954.52 | 4108.59
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 23063.11 | 397.5 | 19352.02 | 3711.09
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 23063.11 | 12.38 | 19364.4 | 3698.71
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 23063.11 | 91.7 | 19456.1 | 3607.01
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 23063.11 | 30.4 | 19486.5 | 3576.61
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 23063.11 | 271.6 | 19758.1 | 3305.01
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 23063.11 | 71.04 | 19829.14 | 3233.97
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 23063.11 | 587.3 | 20416.44 | 2646.67
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 23063.11 | 31.6 | 20448.04 | 2615.07
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 23063.11 | 289.4 | 20737.44 | 2325.67
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 23063.11 | 11.83 | 20749.27 | 2313.84
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 23063.11 | 128.8 | 20878.07 | 2185.04
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 23063.11 | 19.16 | 20897.23 | 2165.88
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 23063.11 | 96.1 | 20993.33 | 2069.78
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 23063.11 | 6.06 | 20999.39 | 2063.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 23063.11 | 55.2 | 21054.59 | 2008.52
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 23063.11 | 6.33 | 21060.92 | 2002.19
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 23063.11 | 44.2 | 21105.12 | 1957.99
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 23063.11 | 18.69 | 21123.81 | 1939.3
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 23063.11 | 125.1 | 21248.91 | 1814.2
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 23063.11 | 22.78 | 21271.69 | 1791.42
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 23063.11 | 227.7 | 21499.39 | 1563.72
[5 empty] | 23063.11 |  | 21499.39 | 1563.72
[5 empty] | 23063.11 |  | 21499.39 | 1563.72
[5 empty] | 23063.11 |  | 21499.39 | 1563.72
|  |  | Totals: | 23063.11 |  | 21499.39 |  | 1563.72
Note on E9: Durakovic, Selma [DAS]: New PM Time Budget $Selma Kleene, Jennifer 12:35 PM (3 hours ago) to me, Scott Please set-up a PM Time budget for MM22 9262.00 for $8,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Re: 9262.00 MM22 PM time budget Inbox Kleene, Jennifer 8:00 AM (39 minutes ago) to me Please increase the PM Time budget for 9262.00 by $4,400.00. Regards, Jennifer Kleene, Jennifer 3:24 PM (10 minutes ago) to me Please make the following changes: 9326.00 MM21 - increase by $2,100.00 9054.03 MM22 - increase by $5,000.00 9262.00 MM22 - increase by $8,000.00 9290.00 MM22 - increase by $3,200.00 9268.01 R22M - increase by $1,000.00 Regards, Jennifer

## #9262.00 Misc
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33522018800 | 2022-01-18 | 9500 | DSGN | Iowa Fire Equipment Company V# (00002109528) | Inv. 332707 | 1090 | 1090
PRC 33522087903 | 2022-03-25 | 9500 | CNST | Rapids Reproductions V# (00002111375) | Inv. 419238-0 | 137.26 | 1227.26
PRC 33523244801 | 2022-09-01 | 9500 | CNST | Rapids Reproductions V# (00002111375) | Inv. 188377-0 | 207.2 | 1434.46
GAX 33523354803 | 2022-12-20 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2470900-Final | 1255 | 2689.46
PRC 33523069803 | 2023-03-10 | 9500 | CNST | Rapids Reproductions V# (00002111375) | Inv. 420562-0 | 31.35 | 2720.81
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 165 | 2885.81
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 82.5 | 2968.31
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -247.5 | 2720.81
2720.81
2720.81
2720.81
2720.81
|  |  |  | Totals: |  | 2720.81

## #9262.00 Shive Hattery
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B: Emergency
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522354801 | 2021-12-17 | PO Procore | 47700 | 47700 |  |  | 47700
PRC 3352235PA4801 | 2022-01-24 | Inv. 4217460-1 |  | 47700 | 17764 | 17764 | 29936
PRC 3352235PB4801 | 2022-02-23 | Inv. 4217460-2 |  | 47700 | 14156 | 31920 | 15780
PO 33522354801 | 2022-06-07 | CO #1 | 8500 | 56200 |  | 31920 | 24280
PRC 3352235PC4801 | 2022-07-07 | Inv. 4217460-3 |  | 56200 | 6745 | 38665 | 17535 | FY22
PO 33523354801 | 2022-08-09 | Rolled to FY23 | 0 | 56200 |  | 38665 | 17535
PRC 3352335PD4801 | 2022-08-12 | Inv. 4217460-4 |  | 56200 | 355 | 39020 | 17180
PRC 3352335PE4801 | 2022-09-30 | Inv. 4217460-5 |  | 56200 | 1220 | 40240 | 15960
PRC 3352335PF4801 | 2022-10-28 | Inv. 4217460-6 |  | 56200 | 1480 | 41720 | 14480
PRC 3352335PG4801 | 2023-01-06 | Inv. 4217460-7 |  | 56200 | 620 | 42340 | 13860
PRC 3352335PH4801 | 2023-03-03 | Inv. 4217460-8 |  | 56200 | 620 | 42960 | 13240
PRC 3352335PI4801 | 2023-05-30 | Inv. 4217460-9 |  | 56200 | 1320 | 44280 | 11920
PRC 3352335PJ4801 | 2023-07-06 | Inv. 4217460-10 |  | 56200 | 1320 | 45600 | 10600 | FY23
PO 33524354801 | 2023-07-25 | Roll to FY24 | 0 | 56200 |  | 45600 | 10600
PRC 3352435PK4801 | 2023-08-04 | Inv. 4217460-11 |  | 56200 | 3100 | 48700 | 7500
PO 33524354801 | 2023-08-25 | CO #2 | 8525 | 64725 |  | 48700 | 16025
PRC 3352435PL4801 | 2023-08-31 | Inv. 4217460-12 |  | 64725 | 2180 | 50880 | 13845
PRC 3352435PM4801 | 2023-10-04 | Inv. 4217460-13 |  | 64725 | 3643.75 | 54523.75 | 10201.25
PRC 3352435PN4801 | 2023-11-03 | Inv. 4217460-14 |  | 64725 | 1278.75 | 55802.5 | 8922.5
PRC 3352435PO4801 | 2023-12-04 | Inv. 4217460-15 |  | 64725 | 852.5 | 56655 | 8070
PRC 3352435PP4801 | 2024-01-30 | Inv. 4217460-16 |  | 64725 | 1278.75 | 57933.75 | 6791.25
PRC 3352435PQ4801 | 2024-07-11 | Inv. 4217460-17 |  | 64725 | 1853 | 59786.75 | 4938.25 | FY24
PO 33525354801 | 2024-07-18 | Roll to FY25 |  | 64725 |  | 59786.75 | 4938.25
|  |  |  | 64725 |  | 59786.75 | 4938.25
|  |  |  | 64725 |  | 59786.75 | 4938.25
|  |  |  | 64725 |  | 59786.75 | 4938.25
|  | Totals: | 64725 |  | 59786.75 |  | 4938.25
|  | Med Center Design | 28800 |  | 28800 |  | 0
|  | Med Center Bid & Construction Admin | 12400 |  | 11904 |  | 496
|  | Med Center Civil Site Survey | 4000 |  |  |  | 4000
|  | WRC Initial Water Service Study | 2500 |  | 2500 |  | 0
|  | CO #1 | 8500 |  | 8484 |  | 16
|  | CO #2 | 8525 |  | 8098.75 |  | 426.25
|  | Total: | 64725 |  | 59786.75 |  | 4938.25

## #9262.00 Story Construction PC
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B: RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522356800 | 2021-12-21 | PO Procore | 16368.04 | 16368.04 |  |  | 16368.04
PRC 3352235PA6800 | 2022-02-07 | Inv. 32988 |  | 16368.04 | 3831 | 3831 | 12537.04
PRC 3352235PB6800 | 2022-03-21 | Inv. 33034 |  | 16368.04 | 5617.78 | 9448.78 | 6919.26
PRC 3352235PC6800 | 2022-04-28 | Inv. 33080-FINAL | -3219.76 | 13148.28 | 3699.5 | 13148.28 | 0
|  | Totals: | 13148.28 |  | 13148.28 |  | 0
|  | CM Services | 13128 |  | 13128 |  | 0
|  | Reimbursables | 20.28 |  | 20.28 |  | 0
|  | Total: | 13148.28 |  | 13148.28 |  | 0

## #9262.00 Proctor Mechanical
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Proctor Mechanical Corporation |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM22-9255 |  |  | MA00521010
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522082900 | 2022-03-23 | DO Procore | 6990.07 | 6990.07 |  |  | 6990.07 | FY22
DO 33523082900 | 2022-08-09 | Rolled to FY23 | 0 | 6990.07 |  | 0 | 6990.07
PRC 3352308PA2900A | 2023-06-21 | Inv. 901584 final | -3131.19 | 3858.88 | 3858.88 | 3858.88 | 0
|  | Totals: | 3858.88 |  | 3858.88 |  | 0 | FINAL
|  | Contract Line 1 Labor 8 Journeyman hrs @60.00 | 735.5 |  | 735.5 |  | 0
|  | Contract Line 2 -Materials | 3123.38 |  | 3123.38 |  | 0
|  | Total: | 3858.88 |  | 3858.88 |  | 0

## #9262.00 Story Construction CA
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Story Construction #003CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522091900 | 2022-04-01 | PO Procore | 28556.16 | 28556.16 |  |  | 28556.16
PRC 3352209PA1900 | 2022-05-19 | Inv. 33123 |  | 28556.16 | 573.5 | 573.5 | 27982.66
PRC 3352209PB1900 | 2022-06-20 | Inv. 33168 |  | 28556.16 | 603 | 1176.5 | 27379.66
PRC 3352209PC1900 | 2022-07-18 | Inv. 33221 |  | 28556.16 | 633 | 1809.5 | 26746.66 | FY22
PO 33523091900 | 2022-08-09 | Rolled to FY23 | 0 | 28556.16 |  | 1809.5 | 26746.66
PRC 3352309PD1900 | 2022-08-24 | Inv. 33278 |  | 28556.16 | 3607 | 5416.5 | 23139.66
PRC 3352309PE1900 | 2022-09-20 | Inv. 33343-Final | -19115.66 | 9440.5 | 4024 | 9440.5 | 0
|  | Totals: | 9440.5 |  | 9440.5 |  | 0 | FINAL
|  | CM Services | 9440.5 |  | 9440.5 |  | 0
|  | Reimbursables | 0 |  | 0 |  | 0
|  | Total: | 9440.5 |  | 9440.5 |  | 0

## #9262.00 Story Construction (2)
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Story Construction #003CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523258904 | 2022-09-15 | PO Procore | 48691.7 | 48691.7 |  |  | 48691.7
PRC 3352325PA8904 | 2022-11-28 | Inv. 33459 |  | 48691.7 | 6805 | 6805 | 41886.7
PRC 3352325PB8904 | 2023-01-20 | Inv. 33581 |  | 48691.7 | 2348.5 | 9153.5 | 39538.2
PRC 3352325PC8904 | 2023-02-16 | Inv. 33629 |  | 48691.7 | 12555.5 | 21709 | 26982.7
PRC 3352325PD8904 | 2023-03-20 | Inv. 33682 |  | 48691.7 | 9674.5 | 31383.5 | 17308.2
PRC 3352325PE8904 | 2023-04-19 | Inv. 33728 |  | 48691.7 | 5306.5 | 36690 | 12001.7
PRC 3352325PF8904 | 2023-05-22 | Inv. 33783 |  | 48691.7 | 5554.5 | 42244.5 | 6447.2
PO 33523258904 | 2023-05-31 | CO 1 | 6890 | 55581.7 |  | 42244.5 | 13337.2
PRC 3352325PG8904 | 2023-06-22 | Inv. 33832 |  | 55581.7 | 390 | 42634.5 | 12947.2
PO 33523258904 | 2023-06-23 | CO 2 | 2995.2 | 58576.9 |  | 42634.5 | 15942.4
PRC 3352325PH8904 | 2023-07-19 | Inv. 33890 |  | 58576.9 | 3095 | 45729.5 | 12847.4 | FY23
PO 33524258904 | 2023-07-24 | Roll to FY24 | 0 | 58576.9 |  | 45729.5 | 12847.4
PRC 3352425PI8904 | 2023-08-21 | Inv. 33948 |  | 58576.9 | 495 | 46224.5 | 12352.4
PRC 3352425PJ8904 | 2023-09-18 | Inv. 34002 |  | 58576.9 | 3475 | 49699.5 | 8877.4
PRC 3352425PK8904 | 2023-10-13 | Inv. 34063 |  | 58576.9 | 725 | 50424.5 | 8152.4
PRC 3352425PL8904 | 2023-11-16 | Inv. 34116 |  | 58576.9 | 1695 | 52119.5 | 6457.4
PRC 3352425PM8904 | 2023-12-15 | Inv. 34157 |  | 58576.9 | 2019.5 | 54139 | 4437.9
PO 33524258904 | 2024-01-03 | CO 3 | 3172.74 | 61749.64 |  | 54139 | 7610.64
PRC 3352425PN8904 | 2024-01-18 | Inv. 34204 |  | 61749.64 | 875 | 55014 | 6735.64
PRC 3352425PO8904 | 2024-02-15 | Inv. 34246 |  | 61749.64 | 1570 | 56584 | 5165.64
PRC 3352425PP8904 | 2024-07-18 | Inv. 34436 |  | 61749.64 | 4336.32 | 60920.32 | 829.32 | FY24
PO 33525258904 | 2024-07-22 | Roll to FY25 |  | 61749.64 |  | 60920.32 | 829.32
PRC 3352525PQ8904 | 2024-12-16 | Inv. 34654 |  | 61749.64 | 337.15 | 61257.47 | 492.17
|  |  |  | 61749.64 |  | 61257.47 | 492.17
|  |  |  | 61749.64 |  | 61257.47 | 492.17
|  |  |  | 61749.64 |  | 61257.47 | 492.17
|  | Totals: | 61749.64 |  | 61257.47 |  | 492.17
|  | CM Services | 18882 |  | 18882 |  | 0
|  | Reimbursables | 460.2 |  | 295 |  | 165.2
|  | Fee (5%) | 29349.5 |  | 29349.5 |  | 0
|  | CO 1 | 6890 |  | 6890 |  | 0
|  | CO 2 | 2995.2 |  | 2702.23 |  | 292.97
|  | CO 3 | 3172.74 |  | 3138.74 |  | 34
|  | Total: | 61749.64 |  | 61257.47 |  | 492.17

## #9262.00 Mahoney Fire
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Mahoney Fire Sprinkler |  |  | Vendor: 00003035382
Acct. Codes-0017-335-MM22-9255 |  |  | 926200-02
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523272901 | 2022-09-27 | PO Procore | 580000 | 580000 |  |  | 580000
PRC 3352327PA2901 | 2022-10-11 | Inv. 9262.00-01 |  | 580000 | 46360 | 46360 | 533640 | 2440
PRC 3352327PB2901 | 2023-01-18 | Inv. 9262.00-02 |  | 580000 | 35150 | 81510 | 498490 | 4290
PO 33523272901 | 2023-01-20 | CO 1 | -16000 | 564000 |  | 81510 | 482490
PO 33523272901 | 2023-02-23 | CO 2 (No Cost) | 0 | 564000 |  | 81510 | 482490
PO 33523272901 | 2023-02-24 | CO 3 | -2070 | 561930 |  | 81510 | 480420
PRC 3352327PC2901 | 2023-03-07 | Inv. 9262.00-03 |  | 561930 | 117800 | 199310 | 362620 | 10490
PRC 3352327PD2901 | 2023-05-17 | Inv. 9262.00-04 |  | 561930 | 140410 | 339720 | 222210 | 17880
PO 33523272901 | 2023-06-20 | CO 4 (No Cost) | 0 | 561930 |  | 339720 | 222210
PRC 3352327PE2901 | 2023-07-17 | Inv. 9262.00-05 |  | 561930 | 93936 | 433656 | 128274 | 22824 | FY23
PO 33524272901 | 2023-07-25 | Roll to FY24 | 0 | 561930 |  | 433656 | 128274
PO 33524272901 | 2023-08-31 | CO #5 (No Cost) | 0 | 561930 |  | 433656 | 128274
PRC 3352427PF2901 | 2023-09-06 | Inv. 9262.00-06 |  | 561930 | 90392.5 | 524048.5 | 37881.5 | 27581.5
PO 33524272901 | 2023-11-15 | CO #6 | 2096.29 | 564026.29 |  | 524048.5 | 39977.79
PRC 3352427PG2901 | 2024-01-04 | Inv. 9262.00-07 |  | 564026.29 | 6266.48 | 530314.98 | 33711.31 | 27911.31
PRC 3352427PH2901 | 2024-02-05 | Inv. 9262.00-08 - Closeout |  | 564026.29 | 5510 | 535824.98 | 28201.31 | 28201.31
PRC 3352427PI2901 | 2024-02-08 | Inv. 9262.00-09 - Retainage |  | 564026.29 | 28201.31 | 564026.29 | 0
|  |  |  | 564026.29 |  | 564026.29 | 0
|  | Totals: | 564026.29 |  | 564026.29 |  | 0

## #9262.00 Controlled Asbestos
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | MA00521060
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523335808 | 2022-12-21 | DO Procore | 11583.6 | 11583.6 |  |  | 11583.6
DO 33523335808 | 2023-06-26 | CO #1 | 2216.72 | 13800.32 |  | 0 | 13800.32
PRC 3352333PA5808 | 2023-08-02 | Inv. 9262.00-01 FINAL | -4324.16 | 9476.16 | 9476.16 | 9476.16 | 0 | .
|  | Totals: | 9476.16 |  | 9476.16 |  | 0 | FINAL
|  | Abestos Abatement Services (122.5 hours at $58.00/hr) | 6395 |  | 6395 |  | 0
|  | Lead Abatement Services (52.5 hours at $58.00/hr) | 2189 |  | 2189 |  | 0
|  | Materials (Lump Sum) | 487.6 |  | 487.6 |  | 0
|  | Friable Disposal Fee (2 tons at $75.00/ton) | 30.94 |  | 30.94 |  | 0
|  | Mileage (1240 miles at $0.39/mile) | 373.62 |  | 373.62 |  | 0
|  | Total: | 9476.16 |  | 9476.16 |  | 0

## #9262.00 Siemens Industry
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Siemens Industry |  |  | Vendor: 00002089900
Acct. Codes-0017-335-MM22-9255 |  |  | MA00520358
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523005800 | 2023-01-05 | PO Procore | 49234.88 | 49234.88 |  |  | 49234.88
PO 33523005800 | 2023-03-21 | CO #1 (No Cost) | 0 | 49234.88 |  | 0 | 49234.88
PO 33523005800 | 2023-06-20 | CO #2 (No Cost) | 0 | 49234.88 |  | 0 | 49234.88
PCR 3352300PA5800 | 2023-08-09 | Inv. 125 |  | 49234.88 | 28469.27 | 28469.27 | 20765.61 | 1498.38 | FY23
PO 33524005800 | 2023-08-14 | Roll to FY24 | 0 | 49234.88 |  | 28469.27 | 20765.61
PRC 3352400PB5800 | 2023-11-17 | Inv. 140 |  | 49234.88 | 11444.74 | 39914.01 | 9320.87 | 2100.7345
PRC 3352400PC5800 | 2024-01-26 | Inv. 141 |  | 49234.88 | 1292.68 | 41206.69 | 8028.19 | 2168.7745
PO 33524005800 | 2024-05-03 | CO #3 | -5859.42 | 43375.46 |  | 41206.69 | 2168.77
PRC 3352400PD5800 | 2024-08-06 | Inv. 142 |  | 43375.46 | 2168.77 | 43375.46 | 0
|  |  |  | 43375.46 |  | 43375.46 | 0
|  |  |  | 43375.46 |  | 43375.46 | 0
|  |  |  | 43375.46 |  | 43375.46 | 0
|  |  |  | 43375.46 |  | 43375.46 | 0
|  | Totals: | 43375.46 |  | 43375.46 |  | 0 | FINAL

## #9262.00 Kone Inc
DHS WRC Medical Center New Sprinkler System
Project # 9262.00
Program code 926200 |  |  | Major Program 4B02
Kone Inc |  |  | Vendor: 00003078866 |  | 2nd address line PO Box 734874
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ926200-02
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524352800 | 2023-12-18 | PO Procore | 21859 | 21859 |  |  | 21859
PO 33524352800 | 2024-04-19 | CO #1 (No Cost CO) | 0 | 21859 |  | 0 | 21859
PO 33524352800 | 2024-05-28 | CO #2 (No Cost CO) | 0 | 21859 |  | 0 | 21859
PRC 3352435PA2800 | 2024-08-06 | Inv. MED07262024 |  | 21859 | 19816.05 | 19816.05 | 2042.95 | 1042.95 | FY24
PO 33525352800 | 2024-08-09 | Roll to FY25 |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  |  |  | 21859 |  | 19816.05 | 2042.95
|  | Totals: | 21859 |  | 19816.05 |  | 2042.95

## RECAP #9263.00
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
| Program code 926300 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 851050.11
C | Shive Hattery |  | 106800 | 106800 | 0
C | PM TIME |  | 26428.44 | 26428.44 | 0
C | Misc. |  | 13222.65 | 13222.65 | 0
C | Samuels Group |  | 18014.28 | 18014.28 | 0
C | Johnson Controls |  | 954 | 954 | 0
C | ATC Group |  | 5482.5 | 5482.5 | 0
C | Plumbrite LLC |  | 99415 | 99415 | 0
C | Mahoney Fire Sprinkler |  | 438900 | 438900 | 0
C | Samuels Group (2) |  | 92364.46 | 92364.46 | 0
C | Utility Equipment |  | 7100 | 7100 | 0
C | Controlled Asbestos |  | 0 | 0 | 0
C | Johnson Controls(2) |  | 42368.78 | 42368.78 | 0
| Total Project Cost | 851050.11 | 851050.11 | 851050.11 | 0 | 0
Closed 09/11/2023

## #9263.00 Shive Hattery
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B: Emergency
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522013901 | 2022-01-12 | PO Procore | 106800 | 106800 |  |  | 106800
PRC 3352201PA3901 | 2022-02-04 | Inv. 4217461-1 |  | 106800 | 15510 | 15510 | 91290
PRC 3352201PB3901 | 2022-02-28 | Inv. 4217461-2 |  | 106800 | 40890 | 56400 | 50400
PRC 3352201PC3901 | 2022-04-07 | Inv. 4217461-3 |  | 106800 | 21615 | 78015 | 28785 | FY22
PO 33523013901 | 2022-08-10 | Rolled to FY23 | 0 | 106800 |  | 78015 | 28785
PRC 3352301PD3901 | 2022-08-04 | Inv. 4217461-4 |  | 106800 | 606 | 78621 | 28179
PRC 3352301PE3901 | 2022-08-30 | Inv. 4217461-5 |  | 106800 | 909 | 79530 | 27270
PRC 3352301PF3901 | 2022-10-27 | Inv. 4217461-6 |  | 106800 | 7850 | 87380 | 19420
PRC 3352301PG3901 | 2022-01-03 | Inv. 4217461-7 |  | 106800 | 5985 | 93365 | 13435
PRC 3352301PH3901 | 2023-03-04 | Inv. 4217461-8 |  | 106800 | 10935 | 104300 | 2500
PRC 3352301PI3901 | 2023-06-01 | Inv. 4217461-9 |  | 106800 | 2197 | 106497 | 303
PRC 3352301PJ3901 | 2023-06-12 | Inv. 4217461-10-FINAL |  | 106800 | 303 | 106800 | 0
|  |  |  | 106800 |  | 106800 | 0
|  | Totals: | 106800 |  | 106800 |  | 0 | FINAL
|  | Meyer Design | 34800 |  | 34800 |  | 0
|  | Meyer Bid & Construction | 14900 |  | 14900 |  | 0
|  | Canteen Design | 9900 |  | 9900 |  | 0
|  | Canteen Bid & Construction Admin | 4300 |  | 4300 |  | 0
|  | Laundry Design | 11200 |  | 11200 |  | 0
|  | Laundry Bid & Construction Admin | 4800 |  | 4800 |  | 0
|  | Building #214 Design | 14600 |  | 14600 |  | 0
|  | Building #214 Bid & Construction Admin | 6300 |  | 6300 |  | 0
|  | GRC Civil Site Surveys | 6000 |  | 6000 |  | 0
|  | Total: | 106800 |  | 106800 |  | 0

## #9263.00 PM TIME
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907F
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20900.46 | 20900.46 |  |  | 20900.46
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 20900.46 | 1600 | 1600 | 19300.46
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 20900.46 | 1150 | 2750 | 18150.46
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 20900.46 | 950 | 3700 | 17200.46
CDE 33522075901 | 2022-03-16 |  | Move PM Time from DA22 | 150 | 21050.46 | 150 | 3850 | 17200.46
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 21050.46 | 950 | 4800 | 16250.46
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 21050.46 | 1050 | 5850 | 15200.46
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 21050.46 | 900 | 6750 | 14300.46
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 21050.46 | 600 | 7350 | 13700.46
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 21050.46 | 1050 | 8400 | 12650.46
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 21050.46 | -1050 | 7350 | 13700.46
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 21050.46 | 1155 | 8505 | 12545.46
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 21050.46 | 1045 | 9550 | 11500.46
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 21050.46 | 1430 | 10980 | 10070.46
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 21050.46 | 1430 | 12410 | 8640.46
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 21050.46 | 880 | 13290 | 7760.46
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 403.01 | 21453.47 | 403.01 | 13693.01 | 7760.46
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 901.18 | 22354.65 | 901.18 | 14594.19 | 7760.46
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 949.2 | 23303.85 | 949.2 | 15543.39 | 7760.46
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1005.64 | 24309.49 | 1005.64 | 16549.03 | 7760.46
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 705.87 | 25015.36 | 705.87 | 17254.9 | 7760.46
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 25015.36 | 1982.26 | 19237.16 | 5778.2
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 25015.36 | 199.63 | 19436.79 | 5578.57
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 25015.36 | 1750.08 | 21186.87 | 3828.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 268.01 | 25283.37 | 268.01 | 21454.88 | 3828.49
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 275.52 | 25558.89 | 275.52 | 21730.4 | 3828.49
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 379.94 | 25938.83 | 379.94 | 22110.34 | 3828.49
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 24.21 | 25963.04 | 24.21 | 22134.55 | 3828.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 168.84 | 26131.88 | 168.84 | 22303.39 | 3828.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 296.56 | 26428.44 | 296.56 | 22599.95 | 3828.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 26428.44 | 152.16 | 22752.11 | 3676.33
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 26428.44 | 922.71 | 23674.82 | 2753.62
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 26428.44 | 137.25 | 23812.07 | 2616.37
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 26428.44 | 603.71 | 24415.78 | 2012.66
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 26428.44 | 70.04 | 24485.82 | 1942.62
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 26428.44 | 412.7 | 24898.52 | 1529.92
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 26428.44 | 104.95 | 25003.47 | 1424.97
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 26428.44 | 738.1 | 25741.57 | 686.87
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 26428.44 | 73.67 | 25815.24 | 613.2
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 26428.44 | 613.2 | 26428.44 | 0
[5 empty] | 26428.44 |  | 26428.44 | 0
[5 empty] | 26428.44 |  | 24415.78 | 0
|  |  | Totals: | 26428.44 |  | 26428.44 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: PM Time Budgets Jennifer Carper, Douglas 8:33 AM (3 hours ago) to me, Scott Please set up the following budgets for PM Time: 9263.00 $15,000.00 9265.00 $7,800.00 9266.00 $4,350.00 9267.00 $7,350.00 Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, 9263.00 - DHS GRC New Sprinkler System at Buildings 105, .... Inbox Elliott, Jennie 2:48 PM (0 minutes ago) to me Please increase the PM Time Budget in 9263.00 - DHS GRC New Sprinkler System at Buildings 105, .... to a total of $35,000 in the Contracted line. Thank you,9263.00 - DHS GRC New Fire Sprinkler Systems in Bldgs 105, 110, 111, & 214 $Joni Elliott, Jennie 8:48 AM (2 hours ago) to me, Scott Please Reduce PM Time to match the expended amount of $26,428.44 in project 9263.00. Upon completion, please close out the project and return any remaining funds to MM22. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov

## #9263.00 Misc
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522118900 | 2022-04-28 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. 019897 | 298.69 | 298.69
PRC 33523166904 | 2023-06-14 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010582-IN-Final | 12923.96 | 13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
13222.65
|  |  |  | Totals: |  | 13222.65

## #9263.00 Samuels Group
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522021901 | 2022-01-12 | PO Procore | 18055.24 | 18055.24 |  |  | 18055.24
PO 33522021901 | 2022-01-25 | Editing PO To MM22 | 0 | 18055.24 |  | 0 | 18055.24
PRC 3352202PA1901 | 2022-03-09 | Inv. 7384.01926300 |  | 18055.24 | 2607.54 | 2607.54 | 15447.7
PRC 3352202PB1901 | 2022-04-14 | Inv. 7384.02926300 |  | 18055.24 | 5688.39 | 8295.93 | 9759.31
PRC 3352202PC1901 | 2022-05-06 | Inv. 7384.03926300 |  | 18055.24 | 3790.25 | 12086.18 | 5969.06
PRC 3352202PD1901 | 2022-06-02 | Inv. 7384.04926300 |  | 18055.24 | 2086.35 | 14172.53 | 3882.71
PRC 3352202PE1901 | 2022-06-30 | Inv. 7384.05926300 |  | 18055.24 | 522.78 | 14695.31 | 3359.93 | FY22
PO 33523021901 | 2022-08-10 | Rolled to FY23 | 0 | 18055.24 |  | 14695.31 | 3359.93
PRC 3352302PF1901 | 2022-09-09 | Inv. 7384.069263 Final | -40.96 | 18014.28 | 3318.97 | 18014.28 | 1.3998e-12
|  |  |  | 18014.28 |  | 18014.28 | 1.3998e-12
|  |  |  | 18014.28 |  | 18014.28 | 1.3998e-12
|  |  |  | 18014.28 |  | 18014.28 | 1.3998e-12
|  |  |  | 18014.28 |  | 18014.28 | 1.3998e-12
|  | Total: | 18014.28 |  | 18014.28 |  | 0 | Final Invoice
|  | CM Services | 17455 |  | 17455 |  | 0
|  | Reimbursables | 559.28 |  | 559.28 |  | 0
|  | Total: | 18014.28 |  | 18014.28 |  | 0

## #9263.00 Johnson Controls
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Johnson Controls |  |  | Vendor: 00002139022
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522045900 | 2022-02-11 | PO Procore | 1858 | 1858 |  |  | 1858
PRC 3352204PA5900 | 2022-08-02 | Inv. 88649195 |  | 1858 | 954 | 954 | 904 | FY22
PO 33523045900 | 2022-08-16 | Rolled to FY23 | 0 | 1858 |  | 954 | 904
PO 33523045900 | 2023-07-03 | Close PO per PM | -904 | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  |  |  | 954 |  | 954 | 0
|  | Totals: | 954 |  | 954 |  | 0 | FINAL
|  | Materials | 50 |  | 50 |  | 0
|  | Labor | 904 |  | 904 |  | 0
|  | Total: | 954 |  | 954 |  | 0

## #9263.00 ATC Group
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA 20262A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522083900 | 2022-03-24 | DO Procore | 8200 | 8200 |  |  | 8200
PRC 3352208PA3900 | 2022-06-30 | Inv. 2428980-Final | -2717.5 | 5482.5 | 5482.5 | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  |  |  | 5482.5 |  | 5482.5 | 0
|  | Totals: | 5482.5 |  | 5482.5 |  | 0
|  | Line 1 Hazardous Material Testing Technician | 3525 |  | 3525 |  | 0
|  | Line 2 Hygenist | 380 |  | 380 |  | 0
|  | Line 3 Administration | 22.5 |  | 22.5 |  | 0
|  | Line 4 Asbestos Sample Analysis | 1300 |  | 1300 |  | 0
|  | Line 5 Lead Based Paint Chip Analysis | 255 |  | 255 |  | 0
|  | Total: | 5482.5 |  | 5482.5 |  | 0

## #9263.00 Plumbrite LLC
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Plumbrite LLC |  |  | Vendor: VS000008037
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 926300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522168801 | 2022-06-17 | PO Procore | 100810 | 100810 |  |  | 100810 |  | FY22
PO 33523168801 | 2022-08-10 | Rolled to FY23 | 0 | 100810 |  | 0 | 100810
PRC 3352316PA8801 | 2022-09-16 | Inv. 16211 |  | 100810 | 63423.14 | 63423.14 | 37386.86 | 3338.06
PO 33523168801 | 2022-10-21 | CO 1 | -1395 | 99415 |  | 63423.14 | 35991.86
PRC 3352316PB8801 | 2022-10-27 | Inv. 16211-1 |  | 99415 | 30063.51 | 93486.65 | 5928.35 | 4920.35
PRC 3352316PC8801 | 2022-12-01 | Inv. 16211-2 |  | 99415 | 957.6 | 94444.25 | 4970.75 | 4970.75
PRC 3352316PD8801 | 2022-12-09 | Inv. 16211-3 -Retainage |  | 99415 | 4970.75 | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  |  |  | 99415 |  | 99415 | 0
|  | Totals: | 99415 |  | 99415 |  | 0

## #9263.00 Mahoney Fire Sprinkler
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Mahoney Fire Sprinkler |  |  | Vendor: 00003035382
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 926300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33522175800 | 2022-06-22 | PO Procore | 435700 | 435700 |  |  | 435700
PRC 3352217PA5800 | 2022-07-14 | Inv. 9263.00-01 |  | 435700 | 4614.15 | 4614.15 | 431085.85 | 242.85 | FY22
PO 33523175800 | 2022-08-10 | Rolled to FY23 | 0 | 435700 |  | 4614.15 | 431085.85
PRC 3352317PB5800 | 2022-08-04 | Inv. 9263.00-02 |  | 435700 | 35150 | 39764.15 | 395935.85 | 2092.85
PRC 3352317PC5800 | 2022-09-06 | Inv. 9263.00-03 |  | 435700 | 23750 | 63514.15 | 372185.85 | 3342.85
PRC 3352317PD5800 | 2022-09-21 | Inv. 9263.00-04 |  | 435700 | 48545 | 112059.15 | 323640.85 | 5897.85
PO 33523175800 | 2022-10-19 | CO 1 | 3200 | 438900 |  | 112059.15 | 326840.85
PRC 3352317PE5800 | 2022-10-27 | Inv. 9263.00-05 |  | 438900 | 69051.7 | 181110.85 | 257789.15 | 9532.15
PRC 3352317PF5800 | 2022-12-02 | Inv. 9263.00-06 |  | 438900 | 155515 | 336625.85 | 102274.15 | 17717.15
PO 33523175800 | 2023-01-06 | CO 2 (No Cost) | 0 | 438900 |  | 336625.85 | 102274.15
PRC 3352317PG5800 | 2023-01-19 | Inv. 9263.00-07 |  | 438900 | 75240 | 411865.85 | 27034.15 | 21677.15
PRC 3352317PH5800 | 2023-01-26 | Inv. 9263.00-08 |  | 438900 | 950 | 412815.85 | 26084.15 | 21727.15
PRC 3352317PI5800 | 2023-05-15 | Inv. 9263.00-09 |  | 438900 | 4139.15 | 416955 | 21945 | 21945
PRC 3352317PJ5800 | 2023-05-22 | Inv. 9263.00-10-Retainage |  | 438900 | 21945 | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  |  |  | 438900 |  | 438900 | 0
|  | Totals: | 438900 |  | 438900 |  | 0

## #9263.00 Samuels Group (2)
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523227801 | 2022-08-01 | PO Procore | 92386.22 | 92386.22 |  |  | 92386.22
PRC 3352322PA7801 | 2022-09-09 | Inv. 7384.50 |  | 92386.22 | 14831.95 | 14831.95 | 77554.27
PRC 3352322PB7801 | 2022-10-07 | Inv. 7384.51 |  | 92386.22 | 14074.57 | 28906.52 | 63479.7
PRC 3352322PC7801 | 2022-11-04 | Inv. 7384.52 |  | 92386.22 | 7506.82 | 36413.34 | 55972.88
PRC 3352322PD7801 | 2022-12-02 | Inv. 7384.53 |  | 92386.22 | 15791.14 | 52204.48 | 40181.74
PRC 3352322PE7801 | 2023-01-04 | Inv. 7384.54 |  | 92386.22 | 9014.91 | 61219.39 | 31166.83
PO 33523227801 | 2023-02-23 | CO 1 (zero cost) | 0 | 92386.22 |  | 61219.39 | 31166.83
PRC 3352322PF7801 | 2023-03-04 | Inv. 7384.55 |  | 92386.22 | 16464.65 | 77684.04 | 14702.18
PRC 3352322PG7801 | 2023-04-07 | Inv. 7384.56 |  | 92386.22 | 7048.77 | 84732.81 | 7653.41
PRC 3352322PH7801 | 2023-05-05 | Inv. 7384.57 |  | 92386.22 | 3036.65 | 87769.46 | 4616.76
PRC 3352322PI7801 | 2023-06-21 | Inv. 7384.58 FINAL | -21.76 | 92364.46 | 4595 | 92364.46 | 3.8547e-12
|  |  |  | 92364.46 |  | 92364.46 | 3.8547e-12
|  |  |  | 92364.46 |  | 92364.46 | 3.8547e-12
|  | Totals: | 92364.46 |  | 92364.46 |  | 0 | FINAL
|  | CM Services | 60138.96 |  | 60138.96 |  | 0
|  | Reimbursables | 5400 |  | 5400 |  | 0
|  | Samuels Group Fee | 26825.5 |  | 26825.5 |  | 0
|  | Total: | 92364.46 |  | 92364.46 |  | 0

## #9263.00 Utility Equipment
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Utility Equipment Co. |  |  | Vendor: 00002109726
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: SRVV5
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523245801 | 2022-09-01 | PO Procore | 7573.44 | 7573.44 |  |  | 7573.44
PRC 3352324PA5801 | 2022-10-07 | Inv. 60005532-000 |  | 7573.44 | 7100 | 7100 | 473.44
PO 33523245801 | 2023-07-26 | Close PO per PM | -473.44 | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  |  |  | 7100 |  | 7100 | 0
|  | Totals: | 7100 |  | 7100 |  | 0 | FINAL
|  | Install 6" Valve | 7100 |  | 7100 |  | 0
|  | Install Valve Stem w/ HD Lid | 0 |  |  |  | 0
|  | Total: | 7100 |  | 7100 |  | 0

## #9263.00 Controlled Asbestos
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM22-9255 |  |  | RFB#926300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523245901 | 2022-08-31 | PO Procore | 21682.24 | 21682.24 |  |  | 21682.24
PO 33523245901 | 2022-09-27 | PO Updated to correct amount | 10000 | 31682.24 |  | 0 | 31682.24
PO 33523245901 | 2023-06-13 | Close per PM | -31682.24 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Labor 32hrs x 58 | 1856 |  |  |  | 1856
|  | Drive 4.5 x 2 trips x 2 empl x 58 | 1044 |  |  |  | 1044
|  | Labor 128hrs x 58 | 7424 |  |  |  | 7424
|  | Drive 4.5 x 16 trips x 2 empl x 58 | 8352 |  |  |  | 8352
|  | Labor OT 80 x 87 | 6960 |  |  |  | 6960
|  | Air monitoring, Bonding expense | 1600 |  |  |  | 1600
|  | Waste disposal | 150 |  |  |  | 150
|  | Mileage 306 miles x 0.39 x 18 x 2 | 4296.24 |  |  |  | 4296.24
|  |  | 31682.24 |  | 0 |  | 31682.24

## #9263.00 Johnson Controls (2)
DHS GRC New Sprinkler Systems at Bldgs 105, 110, 111 & 214
Project # 9263.00
Program code 926300 |  |  | Major Program 4B02
Johnson Controls(2) |  |  | Vendor: 00002139022
Acct. Codes-0017-335-MM22-9255 |  |  | RFB#926300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523257903 | 2022-09-13 | PO Procore | 41818.19 | 41818.19 |  |  | 41818.19
PO 33523257903 | 2022-10-06 | CO 1 (no cost) | 0 | 41818.19 |  | 0 | 41818.19
PO 33523257903 | 2023-02-01 | CO 2 (no cost) | 0 | 41818.19 |  | 0 | 41818.19
PO 33523257903 | 2023-02-15 | CO 3 | 550.59 | 42368.78 |  | 0 | 42368.78
PRC 3352325PA7903 | 2023-03-01 | Inv. 41602295-41621759 |  | 42368.78 | 38777.26 | 38777.26 | 3591.52 | 2040.93
PRC 3352325PB7903 | 2023-05-15 | Inv. 41636817 closeout : 41632665 CO |  | 42368.78 | 1473.06 | 40250.32 | 2118.46 | 2118.46
PRC 3352325PC7903 | 2023-05-22 | Inv. 41636817 -retainage |  | 42368.78 | 2118.46 | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  |  |  | 42368.78 |  | 42368.78 | 0
|  | Totals: | 42368.78 |  | 42368.78 |  | 0
|  | Laundry | 9585.81 |  | 9585.81 |  | 0
|  | Canteen #110 | 8673.63 |  | 8673.63 |  | 0
|  | Building #214 | 11402.36 |  | 11402.36 |  | 0
|  | Meyers#111 | 12019.89 |  | 12019.89 |  | 0
|  | P&P Bonds | 136.5 |  | 136.5 |  | 0
|  | CO 3 | 550.59 |  | 550.59 |  | 0
|  | Total: | 42368.78 |  | 42368.78 |  | 0

## RECAP #9264.00
DPS P10 Front Entrance Repair
Project # 9264.00
| Program code 926400 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 29183.1
C | Samuels Group |  | 3727.87 | 3727.87 | 0
| PM TIME |  | 6611.94 | 6611.94 | 0
| Misc. |  | 0 | 0 | 0
C | Horizon Architecture |  | 3780 | 3780 | 0
C | Horizon Architecture (2) |  | 6210 | 6210 | 0
C | Paulson Electric |  | 4300 | 4300 | 0
| Samuels Group #111CA |  | 4553.29 | 4553.29 | 0
| Total Project Cost | 29183.1 | 29183.1 | 29183.1 | 0 | 0
Closed 04/21/23

## #9264.00 Samuels Group
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  | Major Program 4E12
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522056900 | 2022-02-25 | PO Procore | 3765.36 | 3765.36 |  |  | 3765.36
PRC 3352205PA6900 | 2022-04-15 | Inv. 7390.01926400 |  | 3765.36 | 2315.27 | 2315.27 | 1450.09
PRC 3352205PB6900 | 2022-07-07 | Inv. 7390.02926400 |  | 3765.36 | 346.39 | 2661.66 | 1103.7 | FY22
PO 33523056900 | 2022-08-10 | Rolled to FY23 | 0 | 3765.36 |  | 2661.66 | 1103.7
PRC 3352305PC6900 | 2022-12-16 | Inv. 7390.03926400-Final | -37.49 | 3727.87 | 1066.21 | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  |  |  | 3727.87 |  | 3727.87 | 2.3448e-13
|  | Totals: | 3727.87 |  | 3727.87 |  | 0 | FINAL
|  | CM Services | 3593.71 |  | 3593.71 |  | 0
|  | Reimbursables | 134.16 |  | 134.16 |  | 0
|  | Fee | 0 |  |  |  | 0
|  | Total: | 3727.87 |  | 3727.87 |  | 0

## #9264.00 PM TIME
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907G
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 5297.42 | 5297.42 |  |  | 5297.42
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 5297.42 | 425 | 425 | 4872.42
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 5297.42 | 225 | 650 | 4647.42
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 5297.42 | 325 | 975 | 4322.42
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 5297.42 | 250 | 1225 | 4072.42
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 5297.42 | 25 | 1250 | 4047.42
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 5297.42 | 350 | 1600 | 3697.42
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 5297.42 | 250 | 1850 | 3447.42
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 5297.42 | 175 | 2025 | 3272.42
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 5297.42 | -175 | 1850 | 3447.42
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 5297.42 | 192.5 | 2042.5 | 3254.92
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 5297.42 | 165 | 2207.5 | 3089.92
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 5297.42 | 82.5 | 2290 | 3007.42
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 5297.42 | 165 | 2455 | 2842.42
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 5297.42 | 220 | 2675 | 2622.42
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 345.5 | 5642.92 | 345.5 | 3020.5 | 2622.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 140.31 | 5783.23 | 140.31 | 3160.81 | 2622.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 44.39 | 5827.62 | 44.39 | 3205.2 | 2622.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 120.48 | 5948.1 | 120.48 | 3325.68 | 2622.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 168.65 | 6116.75 | 168.65 | 3494.33 | 2622.42
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 6116.75 | 1056.75 | 4551.08 | 1565.67
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 6116.75 | 59.69 | 4610.77 | 1505.98
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 6116.75 | 523.3 | 5134.07 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 262.46 | 6379.21 | 262.46 | 5396.53 | 982.68
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | -262.46 | 6116.75 | -262.46 | 5134.07 | 982.68
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 114.5 | 6231.25 | 114.5 | 5248.57 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 79.24 | 6310.49 | 79.24 | 5327.81 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 74.3 | 6384.79 | 74.3 | 5402.11 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 27.67 | 6412.46 | 27.67 | 5429.78 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 41.38 | 6453.84 | 41.38 | 5471.16 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 158.1 | 6611.94 | 158.1 | 5629.26 | 982.68
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 6611.94 | 72.15 | 5701.41 | 910.53
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 6611.94 | 437.56 | 6138.97 | 472.97
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 6611.94 | 87.61 | 6226.58 | 385.36
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 6611.94 | 385.36 | 6611.94 | 0
[5 empty] | 6611.94 |  | 6611.94 | 0
[5 empty] | 6611.94 |  | 6611.94 | 0
[5 empty] | 6611.94 |  | 6611.94 | 0
|  |  | Totals: | 6611.94 |  | 6611.94 |  | 0
Note on E9: Durakovic, Selma [DAS]: Re: James Trower - PM Time $Selma Trower, James 8:29 AM (48 minutes ago) to me Sorry, I meant project 9264.00. Thanks, James On Thu, Dec 16, 2021 at 8:01 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: James, It appears we already set up a budget of $5,000 to this project. We posted November PM time in the amount of $50 and our available balance is $4,950. Did you want additional $4,000 added to the budget? Please advise. Thank you, Selma Durakovic, Accounting Technician II Iowa Department of Administrative Services Division of Financial Management Office: 515-725-0097 selma.durakovic@iowa.gov https://das.iowa.gov On Tue, Dec 14, 2021 at 4:08 PM Trower, James <james.trower@iowa.gov> wrote: Finance - Can you please set up $4,000 in PM Time for me for project 9246.00 - DPS P10 Front Entrance Repair. Thanks, James Trower, LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Office: 515-725-4150 Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov -- James Trower, LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Office: 515-725-4150 Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov PM Time Increases $Joni Trower, James Dec 22, 2022, 1:00 PM (6 days ago) to me Finance: Please see the below items: 9197.00 - 5th Judicial DSM 5JD FT DM 70 South Restroom Remodel Increase PM Time by $2,000 9229.00 - DOC NCCF R&D Floor Replacement Increase PM Time by $2,000 9237.00 - DAS CC Hoover East Side Paver Repairs Increase PM Time by $1,100 9264.00 - DPS P10 Front Entrance Repair Increase PM Time by $1,100 Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov ADD PM Time $Joni Trower, James Mar 31, 2023, 4:50 PM (4 days ago) to me Finance - Please see the below additional pm time that is needed: 9203.00 - DOC NCCF Treatment Center EIFS Replacement Add PM Time: $3,000 (MM21) 9300.00 - DOC MPFC Storage Bunker Repair Add PM Time: $1,500 (MM21) 9250.00 - DOC MPCF Building 18 Roof Replacement Add PM Time: $8,000 (MM22) 9252.00 - DPS P09 Window Replacement Add PM Time: $2,000 (MM22) 9264.00 - DPS P10 Front Entrance Repair Add PM Time: $1,500 (MM22) 9275.00 - DPS P12 Window Replacement Add PM Time: $3,000 (MM22) 9276.00 - DPS P12 Driveway Repairs Add PM Time: $3,000 (MM22) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9264.00 - DPS P10 Front Entrance Repair (MM22) $John Trower, James Attachments Apr 20, 2023, 3:28 PM (18 hours ago) to me Finance - See below items for 9264.00 - DPS P10 Front Entrance Repair (MM22): 1. Samuels Group #111CA invoiced their final invoice per invoice# 7390.52926400 Final Can you please close this contract? 2. Reduce PM Time by $1,302.58 3. If you are in agreement with item 1, please close this project and return on MM22 funding to the MM22 pool fund. Thanks,

## #9264.00 Misc
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## #9264.00 Horizon Architecture
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  | Major Program 4E12
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522062902 | 2022-03-02 | PO Procore | 3780 | 3780 |  |  | 3780
PRC 3352206PA2902 | 2022-05-31 | Inv. 9264.00-01 - Final |  | 3780 | 3780 | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  |  |  | 3780 |  | 3780 | 0
|  | Totals: | 3780 |  | 3780 |  | 0
|  | Travel 6hrs@135 | 810 |  | 810 |  | 0
|  | Survey 4hrs@135 | 540 |  | 540 |  | 0
|  | Report Recommendations & Cost Opinion 12hrs@135 | 1620 |  | 1620 |  | 0
|  | Report Presentation & Discussion 2hrs@135 | 270 |  | 270 |  | 0
|  | Revise & Finalize Repost 4hrs@135 | 540 |  | 540 |  | 0
|  | Total: | 3780 |  | 3780 |  | 0

## #9264.00 Horizon Architecture 2
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  | Major Program 4E12
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522168800 | 2022-06-17 | PO Procore | 6210 | 6210 |  |  | 6210 | FY22
PO 33523168800 | 2022-08-10 | Rolled to FY23 | 0 | 6210 |  | 0 | 6210
PRC 3352316PA8800 | 2022-12-16 | Inv. 9264.00-01 |  | 6210 | 4185 | 4185 | 2025
PRC 3352316PB8800 | 2023-03-07 | Inv. 9264.00-02 - Final |  | 6210 | 2025 | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  |  |  | 6210 |  | 6210 | 0
|  | Totals: | 6210 |  | 6210 |  | 0
|  | Design & Documentation | 3240 |  | 3240 |  | 0
|  | Project Management | 540 |  | 540 |  | 0
|  | Bidding Assistance | 270 |  | 270 |  | 0
|  | Construction Administration | 1620 |  | 1620 |  | 0
|  | Closeout/Warranty | 540 |  | 540 |  | 0
|  | Total: | 6210 |  | 6210 |  | 0

## #9264.00 Paulson Electric
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  | Major Program 4E12
Paulson Electric |  |  | Vendor: 00002110214
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: SRVV5
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523336806 | 2022-12-02 | PO Procore | 4300 | 4300 |  |  | 4300
PRC 3352333PA6806 | 2023-03-29 | Inv. #1 Final |  | 4300 | 4300 | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  |  |  | 4300 |  | 4300 | 0
|  | Totals: | 4300 |  | 4300 |  | 0

## #9264.00 Samuels Group #111CA
DPS P10 Front Entrance Repair
Project # 9264.00
Program code 926400 |  |  | Major Program 4E12
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523354804 | 2022-12-20 | PO Procore | 5166.34 | 5166.34 |  |  | 5166.34
PRC 3352335PA4804 | 2023-02-09 | Inv. 7390.51926400 |  | 5166.34 | 3454.6 | 3454.6 | 1711.74
PRC 3352335PB4804 | 2023-03-09 | Inv. 7390.52926400 |  | 5166.34 | 1098.69 | 4553.29 | 613.05
PO 33523354804 | 2023-04-21 | Close Project per PM | -613.05 | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  |  |  | 4553.29 |  | 4553.29 | 0
|  | Totals: | 4553.29 |  | 4553.29 |  | 0
|  | CM Services | 4389.29 |  | 4389.29 |  | 0
|  | Reimbursables | 164 |  | 164 |  | 0
|  | Total: | 4553.29 |  | 4553.29 |  | 0

## RECAP #9265.00
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
| Program code 926500 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 274134.78
C | Story Construction |  | 14460.55 | 14460.55 | 0
C | PM TIME |  | 11323.21 | 11323.21 | 0
C | Misc. |  | 1315 | 1315 | 0
C | Bluestone Engineering |  | 25945 | 25945 | 0
C | Story Construction CA |  | 29591.02 | 29591.02 | 0
C | Haselhoff Construction |  | 191500 | 191500 | 0
| Total Project Cost | 274134.78 | 274134.78 | 274134.78 | 0 | 0
Closed 12/04/23

## #9265.00 Story Construction
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  | Major Program 4B02
Story Construction |  |  | Vendor; 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522020903 | 2022-01-20 | PO Procore | 14694.04 | 14694.04 |  |  | 14694.04
PRC 3352202PA0903 | 2022-03-22 | Inv. 33036 |  | 14694.04 | 2541.72 | 2541.72 | 12152.32
PRC 3352202PB0903 | 2022-04-27 | Inv. 33082 |  | 14694.04 | 969.25 | 3510.97 | 11183.07
PRC 3352202PC0903 | 2022-05-18 | Inv. 33125 |  | 14694.04 | 1342.86 | 4853.83 | 9840.21
PRC 3352202PD0903 | 2022-06-23 | Inv. 33170 |  | 14694.04 | 4052.61 | 8906.44 | 5787.6
PRC 3352202PE0903 | 2022-07-19 | Inv. 33223 |  | 14694.04 | 5554.11 | 14460.55 | 233.49 | FY22
PO 33523020903 | 2022-08-10 | Rolled to FY23 | 0 | 14694.04 |  | 14460.55 | 233.49
PO 33523020903 | 2023-06-28 | Close PO per PM | -233.49 | 14460.55 |  | 14460.55 | 0
|  |  |  | 14460.55 |  | 14460.55 | 0
|  |  |  | 14460.55 |  | 14460.55 | 0
|  |  |  | 14460.55 |  | 14460.55 | 0
|  |  |  | 14460.55 |  | 14460.55 | 0
|  |  |  | 14460.55 |  | 14460.55 | 0
|  | Totals: | 14460.55 |  | 14460.55 |  | 0 | FINAL
|  | CM Services | 14287 |  | 14287 |  | 0
|  | Reimbursables | 173.55 |  | 173.55 |  | 0
|  | Total: | 14460.55 |  | 14460.55 |  | 0

## #9265.00 PM TIME
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907H
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8673.23 | 8673.23 |  |  | 8673.23
IET DAS202206115300001 | 2022-01-07 |  | PM-Dec 1-Dec30, 2021 |  | 8673.23 | 600 | 600 | 8073.23
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 8673.23 | 450 | 1050 | 7623.23
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 8673.23 | 700 | 1750 | 6923.23
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 8673.23 | 350 | 2100 | 6573.23
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 8673.23 | 450 | 2550 | 6123.23
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 8673.23 | 550 | 3100 | 5573.23
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 8673.23 | 650 | 3750 | 4923.23
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 8673.23 | 550 | 4300 | 4373.23
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 8673.23 | -550 | 3750 | 4923.23
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 8673.23 | 605 | 4355 | 4318.23
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 8673.23 | 660 | 5015 | 3658.23
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 8673.23 | 495 | 5510 | 3163.23
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 8673.23 | 330 | 5840 | 2833.23
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 8673.23 | 495 | 6335 | 2338.23
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 370.69 | 9043.92 | 370.69 | 6705.69 | 2338.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 569.17 | 9613.09 | 569.17 | 7274.86 | 2338.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 328.57 | 9941.66 | 328.57 | 7603.43 | 2338.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 232.07 | 10173.73 | 232.07 | 7835.5 | 2338.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 397.05 | 10570.78 | 397.05 | 8232.55 | 2338.23
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 10570.78 | 1171.33 | 9403.88 | 1166.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 140.38 | 10711.16 | 140.38 | 9544.26 | 1166.9
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 174 | 10885.16 | 174 | 9718.26 | 1166.9
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 131.51 | 11016.67 | 131.51 | 9849.77 | 1166.9
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 36.32 | 11052.99 | 36.32 | 9886.09 | 1166.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 94.98 | 11147.97 | 94.98 | 9981.07 | 1166.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 175.24 | 11323.21 | 175.24 | 10156.31 | 1166.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 11323.21 | 7.61 | 10163.92 | 1159.29
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 11323.21 | 46.13 | 10210.05 | 1113.16
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 11323.21 | 68.63 | 10278.68 | 1044.53
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 11323.21 | 301.86 | 10580.54 | 742.67
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 11323.21 | 73.67 | 10654.21 | 669
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 11323.21 | 669 | 11323.21 | 0
|  |  | Totals: | 11323.21 |  | 11323.21 |  | 0
Note on E9: Jenkins, Jennifer [DAS]: PM Time Budgets Jennifer Carper, Douglas 8:33 AM (3 hours ago) to me, Scott Please set up the following budgets for PM Time: 9263.00 $15,000.00 9265.00 $7,800.00 9266.00 $4,350.00 9267.00 $7,350.00 Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, 9265.00 - PM Time Increase Inbox Elliott, Jennie 12:51 PM (2 minutes ago) to DAS, me Please increase PM time budget in project 9265.00 by $4,550.02 for a total PM time budget of $15,000. Thank you,

## #9265.00 Misc
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33522188900 | 2022-07-07 | 9500 | CNST | Rapids Reproductions V# (00002111375) | Inv. 419702-0 | 65 | 65
GAX 33522193800 | 2022-07-07 | 9500 | CNST | Schoon Construction V# (00002110153) | Inv. 74068 | 1250 | 1315
1315
1315
1315
1315
1315
1315
1315
1315
1315
1315
|  |  |  | Totals |  | 1315

## #9265.00 Bluestone Engineering
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  | Major Program 4B02
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 926500-02
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522102801 | 2022-04-12 | PO Procore | 25945 | 25945 |  |  | 25945
PO 3352210PA2801 | 2022-06-29 | Inv. 11856 |  | 25945 | 18210 | 18210 | 7735
PO 33522102801A | 2022-06-30 | PO Accidentally closed on last invoice | 0 | 25945 |  | 18210 | 7735 | FY22
PO 33523102801A | 2022-08-10 | Rolled to FY23 | 0 | 25945 |  | 18210 | 7735
PRC 3352310PB2801A | 2022-10-03 | Inv. 12045 |  | 25945 | 1547 | 19757 | 6188
PRC 3352310PC2801A | 2022-11-04 | Inv. 12092 |  | 25945 | 2320.5 | 22077.5 | 3867.5
PRC 3352310PD2801A | 2022-12-12 | Inv. 12158 |  | 25945 | 1933.75 | 24011.25 | 1933.75
PRC 3352310PE2801A | 2023-01-24 | Inv. 12256 |  | 25945 | 232.05 | 24243.3 | 1701.7
PRC 3352310PF2801A | 2023-02-10 | Inv. 12322 |  | 25945 | 1314.95 | 25558.25 | 386.75
PRC 3352310PG2801A | 2023-04-26 | Inv. 9265.00-07 FINAL |  | 25945 | 386.75 | 25945 | 0
|  |  |  | 25945 |  | 25945 | 0
|  |  |  | 25945 |  | 25945 | 0
|  |  |  | 25945 |  | 25945 | 0
|  | Total: | 25945 |  | 25945 |  | 0
|  | Construction Documents | 15340 |  | 15340 |  | 0
|  | Bidding Phase | 2870 |  | 2870 |  | 0
|  | Construction Phase | 7735 |  | 7735 |  | 0
|  | Total: | 25945 |  | 25945 |  | 0

## #9265.00 Story Construction CA
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  | Major Program 4B02
Story Construction |  |  | Vendor; 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523200901 | 2022-07-18 | PO Procore | 31298.84 | 31298.84 |  |  | 31298.84
PRC 3352320PA0901 | 2022-08-23 | Inv. 33280 |  | 31298.84 | 1107 | 1107 | 30191.84
PRC 3352320PB0901 | 2022-09-22 | Inv. 33344 |  | 31298.84 | 1913.22 | 3020.22 | 28278.62
PRC 3352320PC0901 | 2022-10-19 | Inv. 33403 |  | 31298.84 | 1378.5 | 4398.72 | 26900.12
PRC 3352320PD0901 | 2022-11-28 | Inv. 33460 |  | 31298.84 | 2910.55 | 7309.27 | 23989.57
PRC 3352320PE0901 | 2022-12-20 | Inv. 33516 |  | 31298.84 | 3005.25 | 10314.52 | 20984.32
PRC 3352320PF0901 | 2023-01-20 | Inv. 33583 |  | 31298.84 | 7343.5 | 17658.02 | 13640.82
PRC 3352320PG0901 | 2023-02-17 | Inv. 33631 |  | 31298.84 | 7031 | 24689.02 | 6609.82
PRC 3352320PH0901 | 2023-03-20 | Inv. 33684 |  | 31298.84 | 2644.5 | 27333.52 | 3965.32
PRC 3352320PI0901 | 2023-04-18 | Inv. 33730 |  | 31298.84 | 931.5 | 28265.02 | 3033.82
PRC 3352320PJ0901 | 2023-05-22 | Inv. 33785 |  | 31298.84 | 1326 | 29591.02 | 1707.82
PO 33523200901 | 2023-07-26 | Close PO per PM | -1707.82 | 29591.02 |  | 29591.02 | 0
|  |  |  | 29591.02 |  | 29591.02 | 0
|  | Totals: | 29591.02 |  | 29591.02 |  | 0 | FINAL
|  | CM Services | 29231.25 |  | 29231.25 |  | 0
|  | Reimbursables | 359.77 |  | 359.77 |  | 0
|  | Total: | 29591.02 |  | 29591.02 |  | 0

## #9265.00 Haselhoff Construction
DHS CHMHI CCUSO Fire Sprinkler Dry Stack Pipe Repairs
Project # 9265.00
Program code 926500 |  |  | Major Program 4B02
Haselhoff Construction |  |  | Vendor: 00002118715
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 926500-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523223802 | 2022-08-11 | PO Procore | 191500 | 191500 |  |  | 191500
PO 33523223802 | 2022-12-09 | CO 1 (No cost CO) | 0 | 191500 |  | 0 | 191500
PRC 3352322PA3802 | 2022-12-13 | Inv. 9265.00-01 |  | 191500 | 106705.67 | 106705.67 | 84794.33 | 5616.09
PRC 3352322PB3802 | 2023-01-10 | Inv. 9265.00-02 |  | 191500 | 68063.09 | 174768.76 | 16731.24 | 9198.36
PRC 3352322PC3802 | 2023-03-29 | Inv. 9265.00-03 |  | 191500 | 7156.24 | 181925 | 9575 | 9575
PRC 3352322PD3802 | 2023-04-19 | Inv. 9265.00-04 FINAL |  | 191500 | 9575 | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  |  |  | 191500 |  | 191500 | 0
|  | Totals: | 191500 |  | 191500 |  | 0

## RECAP #9271.00
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
| Program code 927100 |  |  | Major Program 4E17
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 526030.69
C | DCI Group |  | 11682.35 | 11682.35 | 0
C | PM TIME |  | 23075.88 | 23075.88 | 0
C | Misc. |  | 2519.07 | 2519.07 | 0
C | Shive Hattery |  | 62263 | 62263 | 0
C | TriCon General Construction |  | 396556.45 | 396556.45 | 0
C | DCI Group #22-003 CA |  | 29933.94 | 29933.94 | 0
| Total Project Cost | 526030.69 | 526030.69 | 526030.69 | 0 | 0
Closed 07/17/2023

## #9271.00 DCI Group
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  | Major Program 4E17
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522062903 | 2022-03-02 | PO Procore | 11689.18 | 11689.18 |  |  | 11689.18
PRC 3352206PA2903 | 2022-04-25 | Inv. 22-003 PC-01 |  | 11689.18 | 3062.27 | 3062.27 | 8626.91
PRC 3352206PB2903 | 2022-07-08 | Inv. 22-003 PC-02 |  | 11689.18 | 3828.15 | 6890.42 | 4798.76
PRC 3352206PC2903 | 2022-07-14 | Inv. 22-003 PC-03 |  | 11689.18 | 1521.55 | 8411.97 | 3277.21 | FY22
PO 33523062903 | 2022-08-10 | Rolled to FY23 | 0 | 11689.18 |  | 8411.97 | 3277.21
PRC 3352306PD2903 | 2022-09-26 | Inv. 22-003 PC-04 FINAL | -6.83 | 11682.35 | 3270.38 | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  |  |  | 11682.35 |  | 11682.35 | -7.2831e-14
|  | Totals: | 11682.35 |  | 11682.35 |  | 0

## #9271.00 PM TIME
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  |  | Major Program 4E17
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E20X
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15823.55 | 15823.55 |  |  | 15823.55
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 15823.55 | 150 | 150 | 15673.55
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 15823.55 | 400 | 550 | 15273.55
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 15823.55 | 675 | 1225 | 14598.55
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 15823.55 | 875 | 2100 | 13723.55
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 15823.55 | 625 | 2725 | 13098.55
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 15823.55 | 850 | 3575 | 12248.55
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 15823.55 | 775 | 4350 | 11473.55
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 15823.55 | -775 | 3575 | 12248.55
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 15823.55 | 852.5 | 4427.5 | 11396.05
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 15823.55 | 1127.5 | 5555 | 10268.55
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 15823.55 | 1072.5 | 6627.5 | 9196.05
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 15823.55 | 1127.5 | 7755 | 8068.55
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 15823.55 | 1210 | 8965 | 6858.55
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 1160.18 | 16983.73 | 1160.18 | 10125.18 | 6858.55
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1162.72 | 18146.45 | 1162.72 | 11287.9 | 6858.55
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 967.98 | 19114.43 | 967.98 | 12255.88 | 6858.55
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1276.47 | 20390.9 | 1276.47 | 13532.35 | 6858.55
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 1072.76 | 21463.66 | 1072.76 | 14605.11 | 6858.55
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 21463.66 | 2221.41 | 16826.52 | 4637.14
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 21463.66 | 134.02 | 16960.54 | 4503.12
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 21463.66 | 1174.9 | 18135.44 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 231.47 | 21695.13 | 231.47 | 18366.91 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 324.22 | 22019.35 | 324.22 | 18691.13 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 325.85 | 22345.2 | 325.85 | 19016.98 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 155.32 | 22500.52 | 155.32 | 19172.3 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 243.03 | 22743.55 | 243.03 | 19415.33 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 332.33 | 23075.88 | 332.33 | 19747.66 | 3328.22
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 23075.88 | 93.59 | 19841.25 | 3234.63
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 23075.88 | 567.57 | 20408.82 | 2667.06
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 23075.88 | 114.58 | 20523.4 | 2552.48
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 23075.88 | 504.01 | 21027.41 | 2048.47
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 23075.88 | 139.67 | 21167.08 | 1908.8
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 23075.88 | 819.4 | 21986.48 | 1089.4
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 23075.88 | 146 | 22132.48 | 943.4
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 23075.88 | 1020.8 | 23153.28 | -77.4
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 23075.88 | -77.4 | 23075.88 | 1.0516e-12
|  |  | Totals: | 23075.88 |  | 23075.88 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time-Budget Updates $Selma Tonyan, Brad 10:04 AM (3 hours ago) to me, Scott Finance, Please see the following new projects and one project that needs PM Time budget adjustment. 9204.00 - MM21 - Increase PM time budget by $5,000 9271.00 - MM22 - Please set up PM time budget at $15,000 9272.00 - MM22 - Please set up PM time budget at $15,000 Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Re: MM22 9271.00 PM Time $Joni Tonyan, Brad 8:31 AM (3 minutes ago) to me Please increase the PM time as needed as we have extra money in the 9271.00 funding. Please do foe all of my projects if money left in contingency as it's hard to know how much additional finance time hitting projects. Thank you, On Fri, Jun 16, 2023, 8:28 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good Morning Brad, In this project, PM Time is short -900.95 for posting $1020.80 Please advise. ~Joni Re: MM22 9271.00 PM Time $Joni Tonyan, Brad 8:31 AM (2 hours ago) to me Please increase the PM time as needed as we have extra money in the 9271.00 funding. Please do foe all of my projects if money left in contingency as it's hard to know how much additional finance time hitting projects. Thank you, Fwd: DVA IVH Pedestrian Tunnel Water Infiltration: Action Required for Contract #MISC-9271.00-007: Miscellaneous - DAS Costs - PM Time Inbox Tonyan, Brad 10:20 AM (5 minutes ago) to me Finance, I am doing a "Dummy" invoice to post all the funds spent on PM Time that is showing on the DAS Financial log. Please also close the PM time financial in project 9271.00 as we have already closed it on the Billable log. Thank you,

## #9271.00 Misc
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  |  | Major Program 4E17
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523245800 | 2022-09-01 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV023555 | 205.41 | 205.41
GAX 33523027900 | 2023-01-27 | 9500 | CNST | Team Services V#(00002121153) | Inv. 1813522-2/1813858-2 | 2313.66 | 2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
2519.07
|  |  |  | Totals: |  | 2519.07

## #9271.00 Shive Hattery
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP927100-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522112800 | 2022-04-15 | PO Procore | 62263 | 62263 |  |  | 62263
PRC 3352211PA2800 | 2022-05-05 | Inv. 2142201690-1 |  | 62263 | 4713.75 | 4713.75 | 57549.25
PRC 3352211PB2800 | 2022-06-07 | Inv. 2142201690-2 |  | 62263 | 24616.05 | 29329.8 | 32933.2
PRC 3352211PC2800 | 2022-07-14 | Inv. 2142201690-3 |  | 62263 | 14664.72 | 43994.52 | 18268.48 | FY22
PO 33523112800 | 2022-08-26 | Rolled to FY23 | 0 | 62263 |  | 43994.52 | 18268.48
PRC 3352311PD2800 | 2022-08-25 | Inv. 2142201690-4 |  | 62263 | 5832.48 | 49827 | 12436
PRC 3352311PE2800 | 2022-09-26 | Inv. 2142201690-5 |  | 62263 | 696 | 50523 | 11740
PRC 3352311PF2800 | 2022-11-07 | Inv. 2142201690-6 |  | 62263 | 4109 | 54632 | 7631
PRC 3352311PG2800 | 2023-01-06 | Inv. 2142201690-7 |  | 62263 | 6574.4 | 61206.4 | 1056.6
PRC 3352311PH2800 | 2023-06-22 | Inv. 2142201690-8 Final |  | 62263 | 1056.6 | 62263 | 0
|  |  |  | 62263 |  | 62263 | 0
|  |  |  | 62263 |  | 62263 | 0
|  |  |  | 62263 |  | 62263 | 0
|  | Totals: | 62263 |  | 62263 |  | 0
|  | Site Investigation/Schematic Design | 18855 |  | 18855 |  | 0
|  | Construction Documents | 29928 |  | 29928 |  | 0
|  | Bidding Assistance | 1740 |  | 1740 |  | 0
|  | Construction Phase | 11740 |  | 11740 |  | 0
|  | Total: | 62263 |  | 62263 |  | 0

## #9271.00 TriCon General Constr.
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  | Major Program 4E17
TriCon General Construction |  |  | Vendor: 00002124028
Acct. Codes-0017-335-MM22-9255 |  |  | RFB927100-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523250801 | 2022-09-07 | PO Procore | 388400 | 388400 |  |  | 388400
PO 33523250801 | 2022-12-13 | CO #1 | 4389.59 | 392789.59 |  | 0 | 392789.59
PO 33523250801 | 2023-03-23 | CO #2 | 9516.47 | 402306.06 |  | 0 | 402306.06
PRC 3352325PA0801 | 2023-04-21 | Inv. 9271.00-AIA #1 |  | 402306.06 | 350436.05 | 350436.05 | 51870.01 | 18444
PO 33523250801 | 2023-06-02 | CO #3 | -5749.64 | 396556.42 |  | 350436.05 | 46120.37
PO 33523250801 | 2023-06-23 | Correction to CO #3 | 0.03 | 396556.45 |  | 350436.05 | 46120.4
PRC 3352325PB0801 | 2023-06-23 | Inv. 9271.00-AIA #2 |  | 396556.45 | 22602.78 | 373038.83 | 23517.62 | 19633.62
PRC 3352325PC0801 | 2023-06-30 | Inv. 9271.00-AIA #3 |  | 396556.45 | 3689.8 | 376728.63 | 19827.82 | 19827.82
PRC 3352325PD0801 | 2023-07-13 | Inv. 9271.00-AIA #4 Retainage |  | 396556.45 | 19827.82 | 396556.45 | 0
|  |  |  | 396556.45 |  | 396556.45 | 0
|  |  |  | 396556.45 |  | 396556.45 | 0
|  |  |  | 396556.45 |  | 396556.45 | 0
|  |  |  | 396556.45 |  | 396556.45 | 0
|  | Totals: | 396556.45 |  | 396556.45 |  | 0 | FINAL

## #9271.00 DCI Group #022-003 CA
DVA IVH Pedestrian Tunnel Water Infiltration
Project # 9271.00
Program code 927100 |  |  | Major Program 4E17
DCI Group #22-003 CA |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523251801 | 2022-09-08 | PO Procore | 29959.5 | 29959.5 |  |  | 29959.5
PRC 3352325PA1801 | 2022-11-07 | Inv. 22-003 CA-01 |  | 29959.5 | 9146.4 | 9146.4 | 20813.1
PRC 3352325PB1801 | 2022-11-14 | Inv. 22-003 CA-02 |  | 29959.5 | 9293.84 | 18440.24 | 11519.26
PRC 3352325PC1801 | 2023-01-17 | Inv. 22-003 CA-03 |  | 29959.5 | 9226.15 | 27666.39 | 2293.11
PRC 3352325PD1801 | 2023-03-15 | Inv. 22-003 CA-04 |  | 29959.5 | 628.85 | 28295.24 | 1664.26
PRC 3352325PE1801 | 2023-04-25 | Inv. 22-003 CA-05 |  | 29959.5 | 533.6 | 28828.84 | 1130.66
PRC 3352325PF1801 | 2023-06-22 | Inv. 22-003 CA-06 |  | 29959.5 | 819.35 | 29648.19 | 311.31
PRC 3352325PG1801 | 2023-06-30 | Inv. 22-003 CA-07 FINAL | -25.56 | 29933.94 | 285.75 | 29933.94 | -1.0765e-12
|  |  |  | 29933.94 |  | 29933.94 | -1.0765e-12
|  |  |  | 29933.94 |  | 29933.94 | -1.0765e-12
|  |  |  | 29933.94 |  | 29933.94 | -1.0765e-12
|  |  |  | 29933.94 |  | 29933.94 | -1.0765e-12
|  |  |  | 29933.94 |  | 29933.94 | -1.0765e-12
|  | Totals: | 29933.94 |  | 29933.94 |  | 0 | FINAL

## RECAP #9272.00
DOC NCF CRC Facility Window Replacements
Project # 9272.00
| Program code 927200 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 268187.55
C | Boyd Jones Construction |  | 15430.7 | 15430.7 | 0
C | PM TIME |  | 26067.14 | 26067.14 | 0
C | Misc. |  | 5966.45 | 5966.45 | 0
C | Genesis Architectural |  | 23800 | 23800 | 0
C | Boyd Jones Construction (2) |  | 23907.07 | 23907.07 | 0
C | Voss Services dba Pella Glass |  | 173016.19 | 173016.19 | 0
| Total Project Cost | 268187.55 | 268187.55 | 268187.55 | 0 | 0
Closed 01/29/2024

## #9272.00 Boyd Jones
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  | Major Program 4B01
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522076900 | 2022-03-16 | PO Procore | 15559.6 | 15559.6 |  |  | 15559.6
PRC 3352207PA6900 | 2022-05-09 | Inv. 9272.00-04 |  | 15559.6 | 4817.1 | 4817.1 | 10742.5
PRC 3352207PB6900 | 2022-06-15 | Inv. 9272.00-02 |  | 15559.6 | 3182.3 | 7999.4 | 7560.2
PRC 3352207PC6900 | 2022-07-11 | Inv. 9272.00-03 |  | 15559.6 | 3162.76 | 11162.16 | 4397.44 | FY22
PO 33523076900 | 2022-08-10 | Rolled to FY23 | 0 | 15559.6 |  | 11162.16 | 4397.44
PRC 3352307PD6900 | 2022-08-17 | Inv. 9272.00-04.1 |  | 15559.6 | 4268.54 | 15430.7 | 128.9
PO 33523076900 | 2023-06-01 | Closing PO Per vendor & Pm Request | -128.9 | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  |  |  | 15430.7 |  | 15430.7 | 0
|  | Totals: | 15430.7 |  | 15430.7 |  | 0
|  | CM Staff Hours | 15282.5 |  | 15282.5 |  | 0
|  | CM Reimbursable Expenses(Mileage) | 148.2 |  | 148.2 |  | 0
|  | Total: | 15430.7 |  | 15430.7 |  | 0

## #9272.00 PM TIME
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E20Y
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 23412.26 | 23412.26 |  |  | 23412.26
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 23412.26 | 175 | 175 | 23237.26
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 23412.26 | 725 | 900 | 22512.26
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 23412.26 | 550 | 1450 | 21962.26
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 23412.26 | 1075 | 2525 | 20887.26
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 23412.26 | 775 | 3300 | 20112.26
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 23412.26 | 1125 | 4425 | 18987.26
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 23412.26 | 1225 | 5650 | 17762.26
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 23412.26 | -1225 | 4425 | 18987.26
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 23412.26 | 1347.5 | 5772.5 | 17639.76
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 23412.26 | 935 | 6707.5 | 16704.76
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 23412.26 | 165 | 6872.5 | 16539.76
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 23412.26 | 55 | 6927.5 | 16484.76
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 781.26 | 24193.52 | 781.26 | 7708.76 | 16484.76
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 964.21 | 25157.73 | 964.21 | 8672.97 | 16484.76
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 148.92 | 25306.65 | 148.92 | 8821.89 | 16484.76
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 48.77 | 25355.42 | 48.77 | 8870.66 | 16484.76
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 25355.42 | 105.77 | 8976.43 | 16378.99
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 25355.42 | 24.81 | 9001.24 | 16354.18
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 25355.42 | 217.58 | 9218.82 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 365.86 | 25721.28 | 365.86 | 9584.68 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 268.86 | 25990.14 | 268.86 | 9853.54 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 50.13 | 26040.27 | 50.13 | 9903.67 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 11.04 | 26051.31 | 11.04 | 9914.71 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 15.83 | 26067.14 | 15.83 | 9930.54 | 16136.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 26067.14 | 93.59 | 10024.13 | 16043.01
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 26067.14 | 567.57 | 10591.7 | 15475.44
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 26067.14 | 211.55 | 10803.25 | 15263.89
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 26067.14 | 930.49 | 11733.74 | 14333.4
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 26067.14 | 174.16 | 11907.9 | 14159.24
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 26067.14 | 1024.7 | 12932.6 | 13134.54
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 26067.14 | 239.73 | 13172.33 | 12894.81
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 26067.14 | 1679.7 | 14852.03 | 11215.11
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 26067.14 | 155.6 | 15007.63 | 11059.51
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 26067.14 | 1286.2 | 16293.83 | 9773.31
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 26067.14 | 159.88 | 16453.71 | 9613.43
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 26067.14 | 1021.4 | 17475.11 | 8592.03
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 26067.14 | 197.4 | 17672.51 | 8394.63
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 26067.14 | 1101.8 | 18774.31 | 7292.83
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 26067.14 | 216.22 | 18990.53 | 7076.61
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 26067.14 | 1499.7 | 20490.23 | 5576.91
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 26067.14 | 355.59 | 20845.82 | 5221.32
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 26067.14 | 2852 | 23697.82 | 2369.32
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 26067.14 | 173.92 | 23871.74 | 2195.4
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 26067.14 | 1313.3 | 25185.04 | 882.1
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 26067.14 | 106.1 | 25291.14 | 776
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 26067.14 | 776 | 26067.14 | 0
[5 empty] | 26067.14 |  | 26067.14 | 0
[5 empty] | 26067.14 |  | 26067.14 | 0
[5 empty] | 26067.14 |  | 26067.14 | 0
|  |  | Totals: | 26067.14 |  | 26067.14 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time-Budget Updates $Selma Tonyan, Brad 10:04 AM (3 hours ago) to me, Scott Finance, Please see the following new projects and one project that needs PM Time budget adjustment. 9204.00 - MM21 - Increase PM time budget by $5,000 9271.00 - MM22 - Please set up PM time budget at $15,000 9272.00 - MM22 - Please set up PM time budget at $15,000 Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Re: PM Time $John Tonyan, Brad 2:13 PM (15 minutes ago) to me, John John, Please increase the exact amount needed to post for each project. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Jan 9, 2024 at 2:12 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Brad I need specific amounts that you need each to be increased by for our audit...unless you are wanting each project increased by the exact amount i need to post? John On Tue, Jan 9, 2024 at 12:35 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: John and Finance, Please increase the PM time as needed from the project's contingency funds to cover for the following. DA21 9172.00 Amt. $654.50 MM22 9272.00 Amt. $748.00 MM23 9255.00 Amt. $513.70 MM23 9310.00 Amt. $981.20 MM23 9324.00 Amt. $1449.80 Thank you,

## #9272.00 Misc
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523236802 | 2022-08-24 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV023259 | 109.38 | 109.38
PRC 33523166801 | 2023-06-15 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV030061 | 95.36 | 204.74
PRC 33524312801 | 2023-11-08 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010662-IN | 5749.11 | 5953.85
PRC 33524341902 | 2023-12-07 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. Misc-0010693-IN | 12.6 | 5966.45
5966.45
5966.45
5966.45
5966.45
5966.45
5966.45
5966.45
5966.45
|  |  |  | Totals: |  | 5966.45

## #9272.00 Genesis Architectural
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  | Major Program 4B01
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP927200-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522129900 | 2022-05-06 | PO Procore | 23800 | 23800 |  |  | 23800
PRC 3352212PA9900 | 2022-06-08 | Inv. 2204-01 |  | 23800 | 3500 | 3500 | 20300
PRC 3352212PB9900 | 2022-07-13 | Inv. 2204-02 |  | 23800 | 11005 | 14505 | 9295 | FY22
PO 33523129900 | 2022-08-10 | Rolled to FY23 | 0 | 23800 |  | 14505 | 9295
PRC 3352312PC9900 | 2022-09-29 | Inv. 2204-03 |  | 23800 | 1895 | 16400 | 7400
PRC 3352312PD9900 | 2023-06-30 | Inv. 2204-04 |  | 23800 | 222 | 16622 | 7178 | FY23
PO 33524129900 | 2023-08-03 | Roll to FY24 | 0 | 23800 |  | 16622 | 7178
PRC 3352412PE9900 | 2023-08-22 | Inv. 2204-05 |  | 23800 | 518 | 17140 | 6660
PRC 3352412PF9900 | 2023-10-11 | Inv. 2204-06 |  | 23800 | 1850 | 18990 | 4810
PRC 3352412PG9900 | 2023-11-28 | Inv. 2204-07 |  | 23800 | 3700 | 22690 | 1110
PRC 3352412PH9900 | 2024-01-22 | Inv. 2204-08 |  | 23800 | 1110 | 23800 | 0
|  |  |  | 23800 |  | 23800 | 0
|  |  |  | 23800 |  | 23800 | 0
|  | Totals: | 23800 |  | 23800 |  | 0
|  | Design Development Phase | 7000 |  | 7000 |  | 0
|  | Construction Documents | 7900 |  | 7900 |  | 0
|  | Bid Phase | 1500 |  | 1500 |  | 0
|  | Construction Phase | 7400 |  | 7400 |  | 0
|  | Total: | 23800 |  | 23800 |  | 0

## #9272.00 Boyd Jones (2)
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  | Major Program 4B01
Boyd Jones Construction |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523138900 | 2023-05-18 | PO Procore | 25158.62 | 25158.62 |  |  | 25158.62
PRC 3352313PA8900 | 2023-06-12 | Inv. 9272.00-001 |  | 25158.62 | 2022.76 | 2022.76 | 23135.86
PRC 3352313PB8900 | 2023-07-11 | Inv. 9272.00-002 |  | 25158.62 | 1779.18 | 3801.94 | 21356.68 | FY23
PO 33524138900 | 2023-08-03 | Roll to FY24 | 0 | 25158.62 |  | 3801.94 | 21356.68
PRC 3352413PC8900 | 2023-08-22 | Inv. 9272.00-003 |  | 25158.62 | 1572.66 | 5374.6 | 19784.02
PRC 3352413PD8900 | 2023-09-25 | Inv. 9272.00-004 |  | 25158.62 | 2260.52 | 7635.12 | 17523.5
PRC 3352413PE8900 | 2023-10-12 | Inv. 9272.00-005 |  | 25158.62 | 3718.82 | 11353.94 | 13804.68
PRC 3352413PF8900 | 2023-11-14 | Inv. 9272.00-006 |  | 25158.62 | 7354.95 | 18708.89 | 6449.73
PRC 3352413PG8900 | 2024-01-08 | Inv. 9272.00-007 |  | 25158.62 | 3887.33 | 22596.22 | 2562.4
PRC 3352413PH8900 | 2024-01-22 | Inv. 9272.00-008 - Final | -1251.55 | 23907.07 | 1310.85 | 23907.07 | 0
|  |  |  | 23907.07 |  | 23907.07 | 0
|  |  |  | 23907.07 |  | 23907.07 | 0
|  |  |  | 23907.07 |  | 23907.07 | 0
|  | Totals: | 23907.07 |  | 23907.07 |  | 0 | FINAL
|  | CM Services | 23533.07 |  | 23533.07 |  | 0
|  | CM Reimbursable | 374 |  | 374 |  | 0
|  | Total: | 23907.07 |  | 23907.07 |  | 0

## #9272.00 Voss Services
DOC NCF CRC Facility Window Replacements
Project # 9272.00
Program code 927200 |  |  | Major Program 4B01
Voss Services dba Pella Glass |  |  | Vendor: 00003179688
Acct. Codes-0017-335-MM22-9255 |  |  | RFP927200-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523150900 | 2023-05-29 | PO Procore | 173016.19 | 173016.19 |  |  | 173016.19 |  | FY23
PO 33524150900 | 2023-08-03 | Roll to FY24 | 0 | 173016.19 |  | 0 | 173016.19
PRC 3352415PA0900 | 2023-09-06 | Inv. 9272.00-0001 |  | 173016.19 | 45863.15 | 45863.15 | 127153.04 | 2413.85
PRC 3352415PB0900 | 2023-10-16 | Inv. 9272.00-0002 |  | 173016.19 | 39840.15 | 85703.3 | 87312.89 | 4510.7
PRC 3352415PC0900 | 2023-11-21 | Inv. 9272.00-0003 |  | 173016.19 | 77034.52 | 162737.82 | 10278.37 | 8565.15
PRC 3352415PD0900 | 2024-01-05 | Inv. 9272.00-0004 |  | 173016.19 | 1627.56 | 164365.38 | 8650.81 | 8650.81
PRC 3352415PE0900 | 2024-01-22 | Inv. 9272.00-0005 - Retainage |  | 173016.19 | 8650.81 | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  |  |  | 173016.19 |  | 173016.19 | 0
|  | Totals: | 173016.19 |  | 173016.19 |  | 0
|  | Base Bid 01 | 170766.19 |  | 170766.19 |  | 0
|  | Alternate 01 | 2250 |  | 2250 |  | 0
|  | Total: | 173016.19 |  | 173016.19 |  | 0

## RECAP #9273.00
DOC IMCC SNU Building Tuckpointing
Project # 9273.00
| Program code 927300 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 14823.07
C | Samules Group |  | 5035.01 | 5035.01 | 0
C | PM TIME |  | 2655 | 2655 | 0
C | Misc. |  | 674.14 | 674.14 | 0
C | System Works |  | 6458.92 | 6458.92 | 0
| Total Project Cost | 14823.07 | 14823.07 | 14823.07 | 0 | 0
Closed 10/19/2022

## #9273.00 Samuels Group
DOC IMCC SNU Building Tuckpointing
Project # 9273.00
Program code 927300 |  |  | Major Program 4E10
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522073900 | 2022-03-14 | PO Procore | 19036.45 | 19036.45 |  |  | 19036.45
PRC 3352207PA3900 | 2022-05-06 | Inv. 7397P1.10PC |  | 19036.45 | 841.6 | 841.6 | 18194.85
PRC 3352207PB3900 | 2022-06-02 | Inv. 7397P1.11PC |  | 19036.45 | 1679.74 | 2521.34 | 16515.11
PRC 3352207PC3900 | 2022-07-11 | Inv. 7397P1.12PC |  | 19036.45 | 1512.4 | 4033.74 | 15002.71 | FY22
PO 33523073900 | 2022-08-10 | Rolled to FY23 | 0 | 19036.45 |  | 4033.74 | 15002.71
PRC 3352307PD3900 | 2022-08-10 | Inv. 7397P1.13PC |  | 19036.45 | 595.35 | 4629.09 | 14407.36
PRC 3352307PE3900 | 2022-09-16 | Inv. 7397P1.14PC-Final | -14001.44 | 5035.01 | 405.92 | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  |  |  | 5035.01 |  | 5035.01 | 0
|  | Totals: | 5035.01 |  | 5035.01 |  | 0 | Final
|  | CM Services | 4843.91 |  | 4843.91 |  | 0
|  | Reimbursables | 191.1 |  | 191.1 |  | 0
|  | Total: | 5035.01 |  | 5035.01 |  | 0

## #9273.00 PM TIME
DOC IMCC SNU Building Tuckpointing
Project # 9273.00
Program code 927300 |  |  | Major Program 4E10
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 2655 | 2655 |  |  | 2655
IET DAS202207115300001 | 2022-02-08 | PM-Jan 1-Jan 31, 2022 |  | 2655 | 175 | 175 | 2480
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 2655 | 75 | 250 | 2405
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 2655 | 100 | 350 | 2305
IET DAS202210115300001 | 2022-05-06 | PM-April 1-April 29, 2022 |  | 2655 | 25 | 375 | 2280
IET DAS202211115300001 | 2022-06-07 | PM-May 2-May 31, 2022 |  | 2655 | 725 | 1100 | 1555
IET DAS202212115300001 | 2022-07-08 | PM June1-June30, 2022 |  | 2655 | 950 | 2050 | 605
IET DAS202301115300001 | 2022-08-10 | PM-July 1-July 29, 2022 |  | 2655 | 250 | 2300 | 355
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Credit |  | 2655 | -250 | 2050 | 605
IET DAS202302115300001 | 2022-09-08 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 2655 | 275 | 2325 | 330
IET DAS202302115300001 | 2022-09-08 | PM Time-August 1-August 31, 2022 |  | 2655 | 27.5 | 2352.5 | 302.5
IET DAS202303115300001 | 2022-10-07 | PM Time-September 1-September 30, 2022 |  | 2655 | 302.5 | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  |  |  | 2655 |  | 2655 | 0
|  | Totals: | 2655 |  | 2655 |  | 0
Note on D9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Mon, Jan 31, 4:12 PM (22 hours ago) to me Would you please create the following PM Time Budgets? MM22 9273.00 for $4.000.00 MM22 9274.00 for $4,500.00 MM22 9277.00 for $4,000.00 MM22 9279.00 for $16,875.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please close MM22 Project 9273.00 $Joni Kleene, Jennifer 11:31 AM (2 minutes ago) to me, Scott All invoices have been paid and all PM time has posted, so please close project 9273.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9273.00 Misc
DOC IMCC SNU Building Tuckpointing
Project # 9273.00
Program code 927300 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 33523291900 | 2022-10-14 | 9500 | CNST | Processing CDE to Move expenses from project 9273.00 to DAS | Inv. 22-141-DRBM | 674.14 | 674.14
674.14
674.14
674.14
674.14
674.14
674.14
674.14
674.14
674.14
674.14
674.14
|  |  |  | Totals: |  | 674.14

## #9273.00 System Works
DOC IMCC SNU Building Tuckpointing
Project # 9273.00
Program code 927300 |  |  | Major Program 4E10
System Works |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM22-9255 |  |  | MA21396
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33522124800 | 2022-05-04 | DO Procore | 7820 | 7820 |  |  | 7820
PRC 3352212PA4800 | 2022-07-20 | Inv. 10846 |  | 7820 | 6068.92 | 6068.92 | 1751.08 | FY22
DO 33523124800 | 2022-08-15 | Rolled to FY23 | 0 | 7820 |  | 6068.92 | 1751.08
PRC 3352312PB4800 | 2022-09-14 | Inv. 10914 FINAL | -1361.08 | 6458.92 | 390 | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  |  |  | 6458.92 |  | 6458.92 | 0
|  | Totals: | 6458.92 |  | 6458.92 |  | 0

## RECAP #9274.00
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
| Program code 927400 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 269198.56
| Additional funds | 1562.3
C | Story Construction |  | 11826.81 | 11826.81 | 0
C | PM TIME |  | 12138.6 | 12138.6 | 0
C | Misc. |  | 2386.2 | 2386.2 | 0
C | Shive Hattery |  | 31000 | 31000 | 0
C | Story Construction |  | 30717.25 | 30717.25 | 0
C | Waldinger Corporation |  | 182692 | 182692 | 0
| Total Project Cost | 270760.86 | 270760.86 | 270760.86 | 0 | 0
Closed 03/31/25

## #9274.00 Funds Rec'd
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  | Major Program 4B02
Funds Received
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  |  | IET REBATEMM22 927400 | 2025-02-14 | 1562.3 | 1562.3
| Total Requested | 0 | Total Transferred |  |  | 1562.3 | 1562.3

## #9274.00 Story Construction
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522110802 | 2022-04-19 | PO Procore | 13621.07 | 13621.07 |  |  | 13621.07
PRC 3352211PA0802 | 2022-06-20 | Inv. 33176 |  | 13621.07 | 900 | 900 | 12721.07
PO 33522110802 | 2022-07-26 | CO 1 | 1204 | 14825.07 |  | 900 | 13925.07
PRC 3352211PB0802 | 2022-08-01 | Inv. 33229 |  | 14825.07 | 2394 | 3294 | 11531.07 | FY22
PO 33523110802 | 2022-08-10 | Rolled to FY23 | 0 | 14825.07 |  | 3294 | 11531.07
PRC 3352311PC0802 | 2022-08-24 | Inv. 33285 |  | 14825.07 | 1225 | 4519 | 10306.07
PRC 3352311PD0802 | 2022-09-20 | Inv. 33350 |  | 14825.07 | 3961.31 | 8480.31 | 6344.76
PO 33523110802 | 2022-09-21 | CO 2 | 3346 | 18171.07 |  | 8480.31 | 9690.76
PO 33523110802 | 2022-09-27 | CO 2 Correction | 0.5 | 18171.57 |  | 8480.31 | 9691.26
PRC 3352311PE0802 | 2022-09-28 | Inv. 33360 FINAL | -6344.76 | 11826.81 | 3346.5 | 11826.81 | 0
|  |  |  | 11826.81 |  | 11826.81 | 0
|  |  |  | 11826.81 |  | 11826.81 | 0
|  |  |  | 11826.81 |  | 11826.81 | 0
|  | Totals: | 11826.81 |  | 11826.81 |  | 0
|  | CM Services | 7265 |  | 7265 |  | 0
|  | Reimbursables | 11.31 |  | 11.31 |  | 0
|  | CO #1 | 1204 |  | 1204 |  | 0
|  | CO #2 | 3346.5 |  | 3346.5 |  | 0
|  | Total: | 11826.81 |  | 11826.81 |  | 0

## #9274.00 PM TIME
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E210
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10165.07 | 10165.07 |  |  | 10165.07
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 10165.07 | 50 | 50 | 10115.07
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 10165.07 | 75 | 125 | 10040.07
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 10165.07 | 75 | 200 | 9965.07
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 10165.07 | 50 | 250 | 9915.07
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 10165.07 | 175 | 425 | 9740.07
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 10165.07 | 425 | 850 | 9315.07
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 10165.07 | -425 | 425 | 9740.07
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 10165.07 | 467.5 | 892.5 | 9272.57
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 10165.07 | 660 | 1552.5 | 8612.57
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 10165.07 | 605 | 2157.5 | 8007.57
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 10165.07 | 220 | 2377.5 | 7787.57
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 10165.07 | 55 | 2432.5 | 7732.57
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 311.08 | 10476.15 | 311.08 | 2743.58 | 7732.57
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 609.33 | 11085.48 | 609.33 | 3352.91 | 7732.57
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 377.64 | 11463.12 | 377.64 | 3730.55 | 7732.57
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 172.94 | 11636.06 | 172.94 | 3903.49 | 7732.57
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 55.03 | 11691.09 | 55.03 | 3958.52 | 7732.57
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 11691.09 | 440.81 | 4399.33 | 7291.76
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 11691.09 | 5.2 | 4404.53 | 7286.56
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 11691.09 | 45.6 | 4450.13 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 108.13 | 11799.22 | 108.13 | 4558.26 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 179.7 | 11978.92 | 179.7 | 4737.96 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 57.06 | 12035.98 | 57.06 | 4795.02 | 7240.96
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 24.96 | 12060.94 | 24.96 | 4819.98 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 11.72 | 12072.66 | 11.72 | 4831.7 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 65.94 | 12138.6 | 65.94 | 4897.64 | 7240.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 12138.6 | 37.48 | 4935.12 | 7203.48
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 12138.6 | 227.26 | 5162.38 | 6976.22
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 12138.6 | 40.54 | 5202.92 | 6935.68
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 12138.6 | 178.31 | 5381.23 | 6757.37
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 12138.6 | 23.28 | 5404.51 | 6734.09
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 12138.6 | 137 | 5541.51 | 6597.09
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 12138.6 | 24.12 | 5565.63 | 6572.97
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 12138.6 | 169.4 | 5735.03 | 6403.57
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 12138.6 | 67.54 | 5802.57 | 6336.03
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 12138.6 | 604 | 6406.57 | 5732.03
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 12138.6 | 58.71 | 6465.28 | 5673.32
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 12138.6 | 372.1 | 6837.38 | 5301.22
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 12138.6 | 17.12 | 6854.5 | 5284.1
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 12138.6 | 95.1 | 6949.6 | 5189
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 12138.6 | 66.94 | 7016.54 | 5122.06
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 12138.6 | 464.9 | 7481.44 | 4657.16
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2024 |  | 12138.6 | 43.29 | 7524.73 | 4613.87
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2024 |  | 12138.6 | 347.5 | 7872.23 | 4266.37
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12138.6 | 5.84 | 7878.07 | 4260.53
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12138.6 | 46.4 | 7924.47 | 4214.13
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 12138.6 | 15.76 | 7940.23 | 4198.37
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 12138.6 | 136.1 | 8076.33 | 4062.27
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 12138.6 | 65.88 | 8142.21 | 3996.39
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12138.6 | 542.5 | 8684.71 | 3453.89
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 12138.6 | 26.18 | 8710.89 | 3427.71
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12138.6 | 241.9 | 8952.79 | 3185.81
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 12138.6 | 86.6 | 9039.39 | 3099.21
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12138.6 | 946.8 | 9986.19 | 2152.41
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12138.6 | 75.78 | 10061.97 | 2076.63
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12138.6 | 386.6 | 10448.57 | 1690.03
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12138.6 | 6.06 | 10454.63 | 1683.97
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12138.6 | 55.2 | 10509.83 | 1628.77
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12138.6 | 26 | 10535.83 | 1602.77
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12138.6 | 175.8 | 10711.63 | 1426.97
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12138.6 | 28.39 | 10740.02 | 1398.58
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12138.6 | 187.4 | 10927.42 | 1211.18
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12138.6 | 22.78 | 10950.2 | 1188.4
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12138.6 | 227.7 | 11177.9 | 960.7
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12138.6 | 15.18 | 11193.08 | 945.52
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12138.6 | 166.7 | 11359.78 | 778.82
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12138.6 | 146.32 | 11506.1 | 632.5
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12138.6 | 632.5 | 12138.6 | 0
[5 empty] | 12138.6 |  | 12138.6 | 0
[5 empty] | 12138.6 |  | 12138.6 | 0
[5 empty] | 12138.6 |  | 12138.6 | 0
|  |  | Totals: | 12138.6 |  | 12138.6 |  | 0
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Mon, Jan 31, 4:12 PM (22 hours ago) to me Would you please create the following PM Time Budgets? MM22 9273.00 for $4.000.00 MM22 9274.00 for $4,500.00 MM22 9277.00 for $4,000.00 MM22 9279.00 for $16,875.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes Inbox Kleene, Jennifer 3:04 PM (19 minutes ago) to me, Scott Please increase the PM Time budget for DA21 9207.00 by $1,870.00. Please increase the PM Time budget for DA23 9328.00 by $2,000.00. Please increase the PM Time budget for MM22 9274.00 by $2,100.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM22 9274.00 Budget Increase $Joni Kleene, Jennifer 10:41 AM (13 minutes ago) to me, Scott Please increase the budget for MM22 9274.00 by $5,000.00. Please also increase the PM Time budget by $2,300.00. Regards, Jennifer Jennifer Kleene PM Time Budget Changes $Joni Kleene, Jennifer 10:13 AM (1 hour ago) to me, Scott Please increase the PM Time Budgets as follows: MM23 9294.01 increase by $3,740.00 DA25 9424.00 increase by $2,000.00 MM22 9244.00 increase by $2,000.00 MM22 9274.00 increase by $600.00 X674 9379.00 increase by $8,800.00 MM24 9391.00 increase by $8,800.00 Regards, Jennifer Please close MM22 Project 9274.00 $Joni Kleene, Jennifer Sat, Mar 29, 1:12 PM (2 days ago) to me All invoices have been paid and all DAS Costs have posted, so please close MM22 Project 9274.00. Regards, Jennifer

## #9274.00 Misc
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523249801 | 2022-09-06 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2447931 - Final | 512.5 | 512.5
GAX 33523336810 | 2022-12-05 | 9500 | CNST | Rapid Reproductions V# (00002111375) | Inv. 420232-0 | 199.65 | 712.15
GAX 33523347811 | 2022-12-13 | 9500 | CNST | August Enterprises LLC V# (00002140874) | Inv. 2022-104 | 1090.3 | 1802.45
GAX 33523188800 | 2023-07-07 | 9500 | CNST | ATC Group Services V# (00002134218) | Inv. 2507889 | 583.75 | 2386.2
2386.2
2386.2
2386.2
2386.2
2386.2
2386.2
2386.2
2386.2
|  |  |  | Totals: |  | 2386.2

## #9274.00 Shive Hattery
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522166800 | 2022-06-15 | PO Procore | 31000 | 31000 |  |  | 31000
PRC 3352216PA6800 | 2022-06-30 | Inv. 2142203391-1 |  | 31000 | 465 | 465 | 30535 | FY22
PO 33523166800 | 2022-08-10 | Rolled to FY23 | 0 | 31000 |  | 465 | 30535
PRC 3352316PB6800 | 2022-08-12 | Inv. 2142203391-2 |  | 31000 | 17010 | 17475 | 13525
PRC 3352316PC6800 | 2022-08-29 | Inv. 2142203391-3 |  | 31000 | 2725 | 20200 | 10800
PRC 3352316PD6800 | 2022-09-28 | Inv. 2142203391-4 |  | 31000 | 2500 | 22700 | 8300
PRC 3352316PE6800 | 2022-10-28 | Inv. 2142203391-5 |  | 31000 | 1245 | 23945 | 7055
PRC 3352316PF6800 | 2023-04-24 | Inv. 2142203391-6 |  | 31000 | 1660 | 25605 | 5395
PRC 3352316PG6800 | 2023-05-30 | Inv. 2142203391-7 |  | 31000 | 2490 | 28095 | 2905
PRC 3352316PH6800 | 2023-07-06 | Inv. 2142203391-8 |  | 31000 | 1245 | 29340 | 1660 | FY23
PO 33524166800 | 2023-07-25 | Roll to FY24 | 0 | 31000 |  | 29340 | 1660
PO 33524166800 | 2023-10-26 | CO #1 (No Cost) | 0 | 31000 |  | 29340 | 1660 | FY24
PO 33525166800A | 2024-07-22 | Roll to FY25 |  | 31000 |  | 29340 | 1660
PRC 3352516PI6800A | 2024-10-30 | Inv. 2142203391-10 |  | 31000 | 1328 | 30668 | 332
PRC 3352516PJ6800A | 2025-02-24 | Inv. 2142203391-11 |  | 31000 | 332 | 31000 | 0
|  | Totals: | 31000 |  | 31000 |  | 0 | FINAL
|  | Design Development Documents | 9300 |  | 9300 |  | 0
|  | Construction Documents | 10900 |  | 10900 |  | 0
|  | Bidding/Negotiation | 2500 |  | 2500 |  | 0
|  | Construction Phase | 8300 |  | 8300 |  | 0
|  | Total: | 31000 |  | 31000 |  | 0
Vendor skipped Invoice 9

## #9274.00 Story Construction CA
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  | Major Program 4B02
Story Construction CA |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523257900 | 2022-09-13 | PO Procore | 20535.09 | 20535.09 |  |  | 20535.09
PRC 3352325PA7900 | 2022-11-21 | Inv. 33466 |  | 20535.09 | 4438.5 | 4438.5 | 16096.59
PRC 3352325PB7900 | 2022-12-19 | Inv. 33521 |  | 20535.09 | 1070.5 | 5509 | 15026.09
PRC 3352325PC7900 | 2023-01-20 | Inv. 33588 |  | 20535.09 | 693 | 6202 | 14333.09
PRC 3352325PD7900 | 2023-02-17 | Inv. 33635 |  | 20535.09 | 835 | 7037 | 13498.09
PRC 3352325PE7900 | 2023-03-20 | Inv. 33689 |  | 20535.09 | 527 | 7564 | 12971.09
PRC 3352325PF7900 | 2023-04-19 | Inv. 33734 |  | 20535.09 | 1597 | 9161 | 11374.09
PRC 3352325PG7900 | 2023-05-22 | Inv. 33790 |  | 20535.09 | 4742.5 | 13903.5 | 6631.59
PO 33523257900 | 2023-06-09 | CO #1 | 6980 | 27515.09 |  | 13903.5 | 13611.59
PRC 3352325PH7900 | 2023-07-18 | Inv. 33896 |  | 27515.09 | 10764.5 | 24668 | 2847.09 | FY23
PO 33524257900 | 2023-07-25 | Roll to FY24 | 0 | 27515.09 |  | 24668 | 2847.09
PRC 3352425PI7900 | 2023-09-18 | Inv. 34007 |  | 27515.09 | 172.5 | 24840.5 | 2674.59
PRC 3352425PJ7900 | 2024-07-17 | Inv. 34446 |  | 27515.09 | 2100.5 | 26941 | 574.09 | FY24
PO 33525257800 | 2024-07-19 | Roll to FY25 |  | 27515.09 |  | 26941 | 574.09
PO 33525257800 | 2024-08-09 | CO #2 | 3812 | 31327.09 |  | 26941 | 4386.09
PRC 3352525PK7800 | 2024-09-16 | Inv. 34522 |  | 31327.09 | 3299.25 | 30240.25 | 1086.84
PRC 3352525PL7800 | 2024-12-16 | Inv. 34656 |  | 31327.09 | 318 | 30558.25 | 768.84
PRC 3352525PM7800 | 2025-01-15 | Inv. 34706 |  | 31327.09 | 159 | 30717.25 | 609.84
PO 33525257800 | 2025-02-28 | Closing PO Per PM | -609.84 | 30717.25 |  | 30717.25 | 0
|  |  |  | 30717.25 |  | 30717.25 | 0
|  |  |  | 30717.25 |  | 30717.25 | 0
|  | Totals: | 30717.25 |  | 30717.25 |  | 0
|  | CM Services | 20328 |  | 20328 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | CO #1 | 6980 |  | 6980 |  | 0
|  | CO #2 | 3409.25 |  | 3409.25 |  | 0
|  | Total: | 30717.25 |  | 30717.25 |  | 0

## #9274.00 Waldinger Corp
DHS WRC Myers Hall Chiller Replacement
Project # 9274.00
Program code 927400 |  |  | Major Program 4B02
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | 927400-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523277900 | 2022-10-03 | PO Procore | 175915 | 175915 |  |  | 175915
PRC 3352327PA7900 | 2023-04-27 | Inv. 9274-001 |  | 175915 | 105683.43 | 105683.43 | 70231.57 | 5562.3
PO 33523277900 | 2023-06-15 | CO #1 | 6777 | 182692 |  | 105683.43 | 77008.57
PRC 3352327PB7900 | 2023-06-19 | Inv. 68024S-002 |  | 182692 | 26846.61 | 132530.04 | 50161.96 | 6975.28
PO 33523277900 | 2023-06-23 | Co #2 (No Cost) | 0 | 182692 |  | 132530.04 | 50161.96
PRC 3352327PC7900 | 2023-08-04 | Inv. 68024S-003 |  | 182692 | 26078.15 | 158608.19 | 24083.81 | 8347.81 | FY23
PO 33524277900 | 2023-08-14 | Roll to FY24 | 0 | 182692 |  | 158608.19 | 24083.81
PO 33524277900 | 2023-10-26 | CO #3 (No Cost CO) | 0 | 182692 |  | 158608.19 | 24083.81
PO 33524277900 | 2024-04-26 | CO #4 (No Cost CO) | 0 | 182692 |  | 158608.19 | 24083.81
PO 33524277900 | 2024-06-28 | CO #5 (No Cost CO) | 0 | 182692 |  | 158608.19 | 24083.81
PRC 3352427PD7900 | 2024-07-26 | Inv. 68024S-004 |  | 182692 | 12755.65 | 171363.84 | 11328.16 | 9019.16 | FY24
PO 33525277900 | 2024-07-30 | Roll to FY25 |  | 182692 |  | 171363.84 | 11328.16
PRC 3352527PE7900 | 2024-10-30 | Inv. 68024s-005 |  | 182692 | 522.5 | 171886.34 | 10805.66 | 9046.66
PRC 3352527PF7900 | 2025-02-18 | Inv. 68024S-006 |  | 182692 | 1671.05 | 173557.39 | 9134.61 | 9134.61
PRC 3352527PG7900 | 2025-02-20 | Inv. 68024S-007 Retention |  | 182692 | 9134.61 | 182692 | 0
|  | Totals: | 182692 |  | 182692 |  | 0

## RECAP #9275.00
DPS P12 Window Replacement
Project # 9275.00
| Program code 927500 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 188608.81
C | Boyd Jones |  | 10555.89 | 10555.89 | 0
C | PM TIME |  | 14390.79 | 14390.79 | 0
C | Misc. |  | 1072.47 | 1072.47 | 0
C | Horizon Architecture |  | 11500 | 11500 | 0
C | Boyd Jones (2) |  | 29350.66 | 29350.66 | 0
C | Up Top Roofing Inc. |  | 121739 | 121739 | 0
| Total Project Cost | 188608.81 | 188608.81 | 188608.81 | 0 | 0
Closed 08/14/2024

## #9275.00 Boyd Jones
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  | Major Program 4E12
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522143901 | 2022-05-20 | PO Procore | 11788.35 | 11788.35 |  |  | 11788.35
PRC 3352214PA3901 | 2022-06-16 | Inv. 9275.00-01 |  | 11788.35 | 1565 | 1565 | 10223.35
PRC 3352214PB3901 | 2022-07-15 | Inv. 9275.00-02 |  | 11788.35 | 1333.1 | 2898.1 | 8890.25 | FY22
PO 33523143901 | 2022-08-10 | Rolled to FY23 | 0 | 11788.35 |  | 2898.1 | 8890.25
PRC 3352314PC3901 | 2022-08-17 | Inv. 9275.00-03 |  | 11788.35 | 1450 | 4348.1 | 7440.25
PRC 3352314PD3901 | 2022-09-14 | Inv. 9275.00-04 |  | 11788.35 | 1635 | 5983.1 | 5805.25
PRC 3352314PE3901 | 2022-10-13 | Inv. 9275.00-05 |  | 11788.35 | 2280 | 8263.1 | 3525.25
PRC 3352314PF3901 | 2022-11-08 | Inv. 9275.00-06 |  | 11788.35 | 1244.35 | 9507.45 | 2280.9
PRC 3352314PG3901 | 2022-12-12 | Inv. 9275.00-07 |  | 11788.35 | 1048.44 | 10555.89 | 1232.46 | FY23
PO 33524143901 | 2023-08-03 | Rolled to FY24 | 0 | 11788.35 |  | 10555.89 | 1232.46
PO 33524143901 | 2024-07-22 | Close Per PM & Vendor | -1232.46 | 10555.89 |  | 10555.89 | 0
|  |  |  | 10555.89 |  | 10555.89 | 0
|  |  |  | 10555.89 |  | 10555.89 | 0
|  | Totals: | 10555.89 |  | 10555.89 |  | 0
|  | CM Services | 10442.79 |  | 10442.79 |  | 0
|  | Reimbursables | 113.1 |  | 113.1 |  | 0
|  | Total: | 10555.89 |  | 10555.89 |  | 0

## #9275.00 PM TIME
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E211
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12914.31 | 12914.31 |  |  | 12914.31
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 12914.31 | 200 | 200 | 12714.31
CDE 33522074900 | 2022-03-14 |  | Moving PM time from 9278 | 50 | 12964.31 | 50 | 250 | 12714.31
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 12964.31 | 100 | 350 | 12614.31
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 12964.31 | 600 | 950 | 12014.31
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 12964.31 | 250 | 1200 | 11764.31
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 12964.31 | 525 | 1725 | 11239.31
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 12964.31 | 350 | 2075 | 10889.31
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 12964.31 | -350 | 1725 | 11239.31
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 12964.31 | 385 | 2110 | 10854.31
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 12964.31 | 110 | 2220 | 10744.31
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12964.31 | 495 | 2715 | 10249.31
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12964.31 | 192.5 | 2907.5 | 10056.81
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 12964.31 | 275 | 3182.5 | 9781.81
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 318.1 | 13282.41 | 318.1 | 3500.6 | 9781.81
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 93.53 | 13375.94 | 93.53 | 3594.13 | 9781.81
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 266.41 | 13642.35 | 266.41 | 3860.54 | 9781.81
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 140.55 | 13782.9 | 140.55 | 4001.09 | 9781.81
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 210.81 | 13993.71 | 210.81 | 4211.9 | 9781.81
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 13993.71 | 352.26 | 4564.16 | 9429.55
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 13993.71 | 59.69 | 4623.85 | 9369.86
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 13993.71 | 523.3 | 5147.15 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 45.93 | 14039.64 | 45.93 | 5193.08 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 86.44 | 14126.08 | 86.44 | 5279.52 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 141.85 | 14267.93 | 141.85 | 5421.37 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 18.44 | 14286.37 | 18.44 | 5439.81 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 51.72 | 14338.09 | 51.72 | 5491.53 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 52.7 | 14390.79 | 52.7 | 5544.23 | 8846.56
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 14390.79 | 200.43 | 5744.66 | 8646.13
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 14390.79 | 1215.43 | 6960.09 | 7430.7
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 14390.79 | 300.39 | 7260.48 | 7130.31
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 14390.79 | 1321.26 | 8581.74 | 5809.05
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 14390.79 | 77.45 | 8659.19 | 5731.6
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 14390.79 | 458 | 9117.19 | 5273.6
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 14390.79 | 7.83 | 9125.02 | 5265.77
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 14390.79 | 57.2 | 9182.22 | 5208.57
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 14390.79 | 20.96 | 9203.18 | 5187.61
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 14390.79 | 184.2 | 9387.38 | 5003.41
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 14390.79 | 30.33 | 9417.71 | 4973.08
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 14390.79 | 193.7 | 9611.41 | 4779.38
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 14390.79 | 31.6 | 9643.01 | 4747.78
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 14390.79 | 174.9 | 9817.91 | 4572.88
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 14390.79 | 13.22 | 9831.13 | 4559.66
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 14390.79 | 90.8 | 9921.93 | 4468.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 14390.79 | 89.22 | 10011.15 | 4379.64
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 14390.79 | 717.9 | 10729.05 | 3661.74
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 14390.79 | 111.39 | 10840.44 | 3550.35
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 14390.79 | 841.7 | 11682.14 | 2708.65
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 14390.79 | 61.61 | 11743.75 | 2647.04
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 14390.79 | 451 | 12194.75 | 2196.04
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 14390.79 | 35.69 | 12230.44 | 2160.35
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 14390.79 | 310.6 | 12541.04 | 1849.75
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 14390.79 | 129.73 | 12670.77 | 1720.02
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 14390.79 | 654.1 | 13324.87 | 1065.92
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 14390.79 | 56.6 | 13381.47 | 1009.32
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 14390.79 | 426.8 | 13808.27 | 582.52
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 14390.79 | 37.51 | 13845.78 | 545.01
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 14390.79 | 336.1 | 14181.88 | 208.91
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 14390.79 | 22.61 | 14204.49 | 186.3
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 14390.79 | 186.3 | 14390.79 | -1.4211e-12
[5 empty] | 14390.79 |  | 14390.79 | -1.4211e-12
[5 empty] | 14390.79 |  | 14390.79 | -1.4211e-12
|  |  | Totals: | 14390.79 |  | 14390.79 |  | 0
Note on E9: Huggins, Joni [DAS]: ames Trower - PM Time $Joni Trower, James Feb 15, 2022, 11:06 AM (23 hours ago) to me Finance - Please see the below items: 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement: Add $2,500 to PM Time 9275.00 - DPS P12 Window Replacement: Setup $6,000 in PM Time 9276.00 - DPS P12 Driveway Repairs: Setup $6,000 in PM Time Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Office: 515-725-4150 Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov ADD PM Time $Joni Trower, James Mar 31, 2023, 4:50 PM (4 days ago) to me Finance - Please see the below additional pm time that is needed: 9203.00 - DOC NCCF Treatment Center EIFS Replacement Add PM Time: $3,000 (MM21) 9300.00 - DOC MPFC Storage Bunker Repair Add PM Time: $1,500 (MM21) 9250.00 - DOC MPCF Building 18 Roof Replacement Add PM Time: $8,000 (MM22) 9252.00 - DPS P09 Window Replacement Add PM Time: $2,000 (MM22) 9264.00 - DPS P10 Front Entrance Repair Add PM Time: $1,500 (MM22) 9275.00 - DPS P12 Window Replacement Add PM Time: $3,000 (MM22) 9276.00 - DPS P12 Driveway Repairs Add PM Time: $3,000 (MM22) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Re: PM Time $John Trower, James 10:29 AM (6 minutes ago) to me Finance - See below modifications in red: On Tue, Nov 7, 2023 at 4:10 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James Can you please review the following projects and let me know if we can increase the project budget and by how much in order to post October PM Time? DA23 9352.00 amount to post 1302.40 will be over budget - Increase PM Time by $1,500 MM21 9186.00 amount to post 907.50 will be over budget - This is not my project. MM21 9203.00 amount to post 1381.60 will be over budget - Increase PM Time by $5,000 MM22 9275.00 amount to post 669.90 will be over budget - Increase PM Time by $2,000 Trower, James 9:44 AM (11 minutes ago) to me Finance - Please see the modifications below in red. Thanks, James On Thu, Feb 8, 2024 at 9:15 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James Please review the following projects that need budget increases in order to post January PM Time. 9344.00 in DA23 Amount to post 1684.10 Increase PM Time by $9,000 9346.00 in DA23 Amount to post 492.80 Increase PM Time by $9,000 9275.00 in MM22 Amount to post 287.10 Increase PM Time by $3,000 9304.00 in MM23 Amount to post 1971.20 Increase PM Time by $5,000 9275.00 - DPS P12 Window Replacement - Close Project $Joni Trower, James Tue, Aug 13, 8:13 PM (10 hours ago) to me Finance - MM22 Funding for project 9275.00: 1. Reduce PM Time $1,085.69 and close PM Time 2. Return all remaining MM22 funds from project 9275.00 to the MM22 pool 3. Close Project Thanks, James Trower, Licensed Architect, LEED AP

## #9275.00 Misc
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523258901 | 2022-09-14 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2450911-Final | 912.5 | 912.5
PRC 33523061904 | 2023-03-01 | 9500 | CNST | Rapid Reproductions V#(00002111375) | Inv. INV027834 | 159.97 | 1072.47
PRC 33523061904 | 2023-03-17 | 9500 | CNST | Rapid Reproductions V#(00002111375) | Inv. INV027834 | -159.97 | 912.5
PRC 33523065804 | 2023-03-06 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV027834 | 159.97 | 1072.47
1072.47
1072.47
1072.47
1072.47
1072.47
1072.47
1072.47
1072.47
1072.47
|  |  |  | Totals: |  | 1072.47

## #9275.00 Horizon Architecture
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  | Major Program 4E12
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522157801 | 2022-06-03 | PO Procore | 11500 | 11500 |  |  | 11500
PRC 3352215PA7801 | 2022-07-01 | Inv. 9275.00-01 |  | 11500 | 2875 | 2875 | 8625 | FY22
PO 33523157801 | 2022-08-10 | Rolled to FY23 | 0 | 11500 |  | 2875 | 8625
PRC 3352315PB7801 | 2022-09-09 | Inv. 9275.00-02 |  | 11500 | 2875 | 5750 | 5750
PRC 3352315PC7801 | 2023-04-10 | Inv. 9275.00-03 |  | 11500 | 2125 | 7875 | 3625 | FY23
PO 33524157801 | 2023-08-03 | Rolled to FY24 | 0 | 11500 |  | 7875 | 3625
PRC 3352415PD7801 | 2024-04-03 | Inv. 9275.00-04 - Final |  | 11500 | 3625 | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  |  |  | 11500 |  | 11500 | 0
|  | Totals: | 11500 |  | 11500 |  | 0 | Final
|  | Survey, Design & Documentation | 4500 |  | 4500 |  | 0
|  | Project Management | 2500 |  | 2500 |  | 0
|  | Bidding Assistance | 1500 |  | 1500 |  | 0
|  | Construction Administration | 2000 |  | 2000 |  | 0
|  | Closeout | 1000 |  | 1000 |  | 0
|  | Total: | 11500 |  | 11500 |  | 0

## #9275.00 Boyd Jones (2)
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  | Major Program 4E12
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523074801 | 2023-03-15 | PO Procore | 28380.7 | 28380.7 |  |  | 28380.7
PRC 3352307PA4801 | 2023-03-16 | Inv. 9275.00-01A |  | 28380.7 | 3551.13 | 3551.13 | 24829.57
PRC 3352307PB4801 | 2023-04-11 | Inv. 9275.00-02A |  | 28380.7 | 3755.7 | 7306.83 | 21073.87
PRC 3352307PC4801 | 2023-05-19 | Inv. 9275.00-03A |  | 28380.7 | 1851.98 | 9158.81 | 19221.89
PRC 3352307PD4801 | 2023-06-12 | Inv. 9275.00-04A |  | 28380.7 | 1170.23 | 10329.04 | 18051.66 | FY23
PO 33524074801 | 2023-08-03 | Roll to FY24 | 0 | 28380.7 |  | 10329.04 | 18051.66
PRC 3352407PE4801 | 2023-08-22 | Inv. 9275.00-05A |  | 28380.7 | 1170.23 | 11499.27 | 16881.43
PRC 3352407PF4801 | 2023-09-25 | Inv. 9275.00-06A |  | 28380.7 | 1329.08 | 12828.35 | 15552.35
PRC 3352407PG4801 | 2023-10-18 | Inv. 9275.00-07A |  | 28380.7 | 3936.04 | 16764.39 | 11616.31
PRC 3352407PH4801 | 2023-11-14 | Inv. 9275.00-08A |  | 28380.7 | 5315.41 | 22079.8 | 6300.9
PRC 3352407PI4801 | 2023-12-13 | Inv. 9275.00-09A |  | 28380.7 | 4000.21 | 26080.01 | 2300.69
PRC 3352407PJ4801 | 2024-01-15 | Inv. 9275.00-10A |  | 28380.7 | 1561.22 | 27641.23 | 739.47
PO 33524074801 | 2024-02-23 | CO #1 | 1801.52 | 30182.22 |  | 27641.23 | 2540.99
PRC 3352407PK4801 | 2024-03-18 | Inv. 9275.00-11A - Final | -831.56 | 29350.66 | 1709.43 | 29350.66 | 0
|  |  |  | 29350.66 |  | 29350.66 | 0
|  |  |  | 29350.66 |  | 29350.66 | 0
|  | Totals: | 29350.66 |  | 29350.66 |  | 0 | FINAL
|  | CM Services | 26870.23 |  | 26870.23 |  | 0
|  | Reimbursables | 771 |  | 771 |  | 0
|  | CO #1 | 1709.43 |  | 1709.43 |  | 0
|  | Total: | 29350.66 |  | 29350.66 |  | 0
Vendor used 9275.00-0# format in another tab

## #9275.00 Up Top Roofing Inc.
DPS P12 Window Replacement
Project # 9275.00
Program code 927500 |  |  | Major Program 4E12
Up Top Roofing Inc. |  |  | Vendor: VS000009593
Acct. Codes-0017-335-MM22-9255 |  |  | RFB 927500 01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523100802 | 2023-04-10 | PO Procore | 116609 | 116609 |  |  | 116609 |  | FY23
PO 33524100802 | 2023-08-03 | Roll to FY24 | 0 | 116609 |  | 0 | 116609
PRC 3352410PA0802 | 2023-10-24 | Inv. 9275.00-01 |  | 116609 | 71578.7 | 71578.7 | 45030.3 | 3767.3
PO 33524100802 | 2023-11-29 | CO #1 (No Cost) | 0 | 116609 |  | 71578.7 | 45030.3
PO 33524100802 | 2024-01-11 | CO #2 | 5130 | 121739 |  | 71578.7 | 50160.3
PRC 3352410PB0802 | 2024-03-04 | Inv. 9275.00-02 |  | 121739 | 42770.81 | 114349.51 | 7389.49 | 6018.4
PRC 3352410PC0802 | 2024-03-18 | Inv. 9275.00-03 |  | 121739 | 194.75 | 114544.26 | 7194.74 | 6028.65
PRC 3352410PD0802 | 03/20/204 | Inv. 9275.00-04 |  | 121739 | 1107.79 | 115652.05 | 6086.95 | 6086.95
PRC 3352410PE0802 | 2024-03-25 | Inv. 9275.00-05 - Retainage |  | 121739 | 6086.95 | 121739 | 0
|  |  |  | 121739 |  | 121739 | 0
|  |  |  | 121739 |  | 121739 | 0
|  |  |  | 121739 |  | 121739 | 0
|  |  |  | 121739 |  | 121739 | 0
|  | Totals: | 121739 |  | 121739 |  | 0

## RECAP #9276.00
DPS P12 Driveway Repairs
Project # 9276.00
| Program code 927600 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 60799.39
C | Boyd Jones |  | 10848.4 | 10848.4 | 0
C | PM TIME |  | 14726.08 | 14726.08 | 0
C | Misc. |  | 128.91 | 128.91 | 0
C | Bolton & Menk |  | 35096 | 35096 | 0
| Total Project Cost | 60799.39 | 60799.39 | 60799.39 | 0 | 0
Closed 02/06/2024

## #9276.00 Boyd Jones
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  | Major Program 4E12
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: | CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522143900 | 2022-05-20 | PO Procore | 11788.35 | 11788.35 |  |  | 11788.35
PRC 3352214PA3900 | 2022-06-16 | Inv. 9276.00-01 |  | 11788.35 | 2992.5 | 2992.5 | 8795.85
PRC 3352214PB3900 | 2022-07-11 | Inv. 9276.00-02 |  | 11788.35 | 2030.9 | 5023.4 | 6764.95 | FY22
PO 33523143900 | 2022-08-10 | Rolled to FY23 | 0 | 11788.35 |  | 5023.4 | 6764.95
PRC 3352314PC3900 | 2022-08-17 | Inv. 9276.00-03 |  | 11788.35 | 1990 | 7013.4 | 4774.95
PRC 3352314PD3900 | 2022-09-14 | Inv. 9276.00-04 |  | 11788.35 | 1715 | 8728.4 | 3059.95
PRC 3352314PE3900 | 2022-10-14 | Inv. 9276.00-05 |  | 11788.35 | 2120 | 10848.4 | 939.95 | FY23
PO 33524143900 | 2023-08-03 | Roll to FY24 | 0 | 11788.35 |  | 10848.4 | 939.95
PO 33524143900 | 2023-11-30 | Closing Per PM | -939.95 | 10848.4 |  | 10848.4 | 0
|  |  |  | 10848.4 |  | 10848.4 | 0
|  |  |  | 10848.4 |  | 10848.4 | 0
|  |  |  | 10848.4 |  | 10848.4 | 0
|  |  |  | 10848.4 |  | 10848.4 | 0
|  | Totals: | 10848.4 |  | 10848.4 |  | 0
|  | CM Services | 10727.5 |  | 10727.5 |  | 0
|  | Reimbursables | 120.9 |  | 120.9 |  | 0
|  | Total: | 10848.4 |  | 10848.4 |  | 0

## #9276.00 PM TIME
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E212
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13387.28 | 13387.28 |  |  | 13387.28
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 13387.28 | 250 | 250 | 13137.28
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 13387.28 | 150 | 400 | 12987.28
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 13387.28 | 500 | 900 | 12487.28
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 13387.28 | 225 | 1125 | 12262.28
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 13387.28 | 650 | 1775 | 11612.28
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 13387.28 | 375 | 2150 | 11237.28
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 13387.28 | -375 | 1775 | 11612.28
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 13387.28 | 412.5 | 2187.5 | 11199.78
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 13387.28 | 137.5 | 2325 | 11062.28
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 13387.28 | 330 | 2655 | 10732.28
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 13387.28 | 302.5 | 2957.5 | 10429.78
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 13387.28 | 330 | 3287.5 | 10099.78
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 268.25 | 13655.53 | 268.25 | 3555.75 | 10099.78
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 116.91 | 13772.44 | 116.91 | 3672.66 | 10099.78
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 177.61 | 13950.05 | 177.61 | 3850.27 | 10099.78
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 220.88 | 14170.93 | 220.88 | 4071.15 | 10099.78
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 252.98 | 14423.91 | 252.98 | 4324.13 | 10099.78
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 14423.91 | 422.7 | 4746.83 | 9677.08
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 14423.91 | 71.63 | 4818.46 | 9605.45
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 14423.91 | 627.96 | 5446.42 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 91.86 | 14515.77 | 91.86 | 5538.28 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 43.22 | 14558.99 | 43.22 | 5581.5 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 20.26 | 14579.25 | 20.26 | 5601.76 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 21.52 | 14600.77 | 21.52 | 5623.28 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 62.07 | 14662.84 | 62.07 | 5685.35 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 63.24 | 14726.08 | 63.24 | 5748.59 | 8977.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 14726.08 | 200.43 | 5949.02 | 8777.06
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 14726.08 | 1215.43 | 7164.45 | 7561.63
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 14726.08 | 250.32 | 7414.77 | 7311.31
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 14726.08 | 1101.05 | 8515.82 | 6210.26
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 14726.08 | 129.72 | 8645.54 | 6080.54
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 14726.08 | 763.7 | 9409.24 | 5316.84
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 14726.08 | 7.83 | 9417.07 | 5309.01
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 14726.08 | 57.2 | 9474.27 | 5251.81
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 14726.08 | 57.16 | 9531.43 | 5194.65
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 14726.08 | 513 | 10044.43 | 4681.65
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 14726.08 | 134.55 | 10178.98 | 4547.1
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 14726.08 | 855 | 11033.98 | 3692.1
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 14726.08 | 219.25 | 11253.23 | 3472.85
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 14726.08 | 1223.1 | 12476.33 | 2249.75
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 14726.08 | 58.71 | 12535.04 | 2191.04
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 14726.08 | 408 | 12943.04 | 1783.04
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 14726.08 | 79.04 | 13022.08 | 1704
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 14726.08 | 633.8 | 13655.88 | 1070.2
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 14726.08 | 105.13 | 13761.01 | 965.07
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 14726.08 | 795.3 | 14556.31 | 169.77
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 14726.08 | 20.17 | 14576.48 | 149.6
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 14726.08 | 149.6 | 14726.08 | 1.4495e-12
[5 empty] | 14726.08 |  | 14726.08 | 1.4495e-12
[5 empty] | 14726.08 |  | 14726.08 | 1.4495e-12
[5 empty] | 14726.08 |  | 14726.08 | 1.4495e-12
|  |  | Totals: | 14726.08 |  | 14726.08 |  | 0
Note on E9: Huggins, Joni [DAS]: ames Trower - PM Time $Joni Trower, James Feb 15, 2022, 11:06 AM (23 hours ago) to me Finance - Please see the below items: 9236.00 - DOC NCCF Food Warehouse Walk-in Freezer Replacement: Add $2,500 to PM Time 9275.00 - DPS P12 Window Replacement: Setup $6,000 in PM Time 9276.00 - DPS P12 Driveway Repairs: Setup $6,000 in PM Time Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services Division of Business and Property Services Office: 515-725-4150 Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov ADD PM Time $Joni Trower, James Mar 31, 2023, 4:50 PM (4 days ago) to me Finance - Please see the below additional pm time that is needed: 9203.00 - DOC NCCF Treatment Center EIFS Replacement Add PM Time: $3,000 (MM21) 9300.00 - DOC MPFC Storage Bunker Repair Add PM Time: $1,500 (MM21) 9250.00 - DOC MPCF Building 18 Roof Replacement Add PM Time: $8,000 (MM22) 9252.00 - DPS P09 Window Replacement Add PM Time: $2,000 (MM22) 9264.00 - DPS P10 Front Entrance Repair Add PM Time: $1,500 (MM22) 9275.00 - DPS P12 Window Replacement Add PM Time: $3,000 (MM22) 9276.00 - DPS P12 Driveway Repairs Add PM Time: $3,000 (MM22) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James 1:25 PM (1 hour ago) to me Finance - Increase PM Time for project 9276.00 MM22 by $4,000 Re: PM Time $John Trower, James 1:41 PM (8 minutes ago) to me Finance - Please see below in red: On Fri, Dec 8, 2023 at 1:30 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James What budget would you like to set up on 9364.00 in MM22? Please set up $8,000 in PM Time We have PM time to post for $847.09 Can we increase the budget for PM time on 9276.00 in MM22? Please increase PM Time by $2,000. We have another 734.80 to post

## #9276.00 Misc
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523061903 | 2023-03-01 | 9500 | CNST | Rapid Reproductions V#(00002111375) | Inv. INV027828 | 128.91 | 128.91
PRC 33523061903 | 2023-03-17 | 9500 | CNST | Rapid Reproductions V#(00002111375) | Inv. INV027828 | -128.91 | 0
PRC 33523065803 | 2023-03-06 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV027828 | 128.91 | 128.91
128.91
128.91
128.91
128.91
128.91
128.91
128.91
128.91
128.91
128.91
|  |  |  | Totals: |  | 128.91

## #9276.00 Bolton & Menk
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  | Major Program 4E12
Bolton & Menk, Inc. |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM22-9260 |  |  | RFP927600-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523206800 | 2022-07-25 | PO Procore | 33541 | 33541 |  |  | 33541
PRC 3352320PA6800 | 2022-08-26 | Inv. 0295089 |  | 33541 | 6356 | 6356 | 27185
PRC 3352320PB6800 | 2022-09-27 | Inv. 0297905 |  | 33541 | 6356 | 12712 | 20829
PRC 3352320PC6800 | 2022-11-01 | Inv. 0299895 |  | 33541 | 11440.8 | 24152.8 | 9388.2
PRC 3352320PD6800 | 2022-12-06 | Inv. 0301930 |  | 33541 | 1271.2 | 25424 | 8117
PRC 3352320PE6800 | 2023-03-07 | Inv. 0307624 |  | 33541 | 1975.5 | 27399.5 | 6141.5
PO 33523206800 | 2023-03-24 | CO #1 | 1555 | 35096 |  | 27399.5 | 7696.5
PRC 3352320PF6800 | 2023-04-14 | Inv. 0309567 |  | 35096 | 658.5 | 28058 | 7038
PRC 3352320PG6800 | 2023-05-10 | Inv. 0310485 |  | 35096 | 1370.75 | 29428.75 | 5667.25
PRC 3352320PH6800 | 2023-06-09 | Inv. 0312900 |  | 35096 | 1370.75 | 30799.5 | 4296.5
PRC 3352320PI6800 | 2023-07-12 | Inv. 0315027 |  | 35096 | 1370.75 | 32170.25 | 2925.75 | FY23
PO 33524206800 | 2023-08-14 | Roll to FY24 | 0 | 35096 |  | 32170.25 | 2925.75
PRC 3352420PJ6800 | 2023-10-13 | Inv. 0316080 |  | 35096 | 2651.6 | 34821.85 | 274.15
PRC 3352420PK6800 | 2023-12-01 | Inv. 0325096 |  | 35096 | 274.15 | 35096 | 1.0232e-12
|  |  |  | 35096 |  | 35096 | 1.0232e-12
|  |  |  | 35096 |  | 35096 | 1.0232e-12
|  | Totals: | 35096 |  | 35096 |  | 0
|  | Construction Documents | 25424 |  | 25424 |  | 0
|  | Bidding/Negotiation Assistance | 2634 |  | 2634 |  | 0
|  | Construction Administration Phase (Driveway Only) | 5483 |  | 5483 |  | 0
|  | CO #1 | 1555 |  | 1555 |  | 0
|  | Total: | 35096 |  | 35096 |  | 0

## RECAP #9277.00
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
| Program code 927700 |  |  | Major Program 4F08
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 336796.33
C | DCI Group |  | 10496.48 | 10496.48 | 0
C | PM TIME |  | 13740.44 | 13740.44 | 0
C | Misc. |  | 5660.63 | 5660.63 | 0
C | Bluestone Engineering |  | 13735 | 13735 | 0
C | Cummins Inc. |  | 265442.35 | 265442.35 | 0
C | DCI Group CA |  | 21126.23 | 21126.23 | 0
C | Siemens-BAS Integration |  | 6595.2 | 6595.2 | 0
| Total Project Cost | 336796.33 | 336796.33 | 336796.33 | 0 | 0
Closed 12/17/24

## #9277.00 DCI Group
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522047901 | 2022-02-15 | PO Procore | 10524.54 | 10524.54 |  |  | 10524.54
PRC 3352204PA7901 | 2022-03-28 | Inv. 22-004 PC-01 |  | 10524.54 | 1922.94 | 1922.94 | 8601.6
PRC 3352204PB7901 | 2022-04-25 | Inv. 22-004 PC-02 |  | 10524.54 | 2083.58 | 4006.52 | 6518.02
PRC 3352204PC7901 | 2022-07-18 | Inv. 22-004 PC-03 |  | 10524.54 | 5307.05 | 9313.57 | 1210.97 | FY22
PO 33523047901 | 2022-08-10 | Rolled to FY23 | 0 | 10524.54 |  | 9313.57 | 1210.97
PRC 3352304PD7901 | 2022-09-20 | Inv. 22-004 PC-04 Final | -28.06 | 10496.48 | 1182.91 | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  |  |  | 10496.48 |  | 10496.48 | 1.7408e-13
|  | Totals: | 10496.48 |  | 10496.48 |  | 0

## #9277.00 PM TIME
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E213
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12915.48 | 12915.48 |  |  | 12915.48
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 12915.48 | 250 | 250 | 12665.48
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 12915.48 | 350 | 600 | 12315.48
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 12915.48 | 675 | 1275 | 11640.48
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 12915.48 | 125 | 1400 | 11515.48
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 12915.48 | 275 | 1675 | 11240.48
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 12915.48 | 100 | 1775 | 11140.48
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 12915.48 | 275 | 2050 | 10865.48
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 12915.48 | -275 | 1775 | 11140.48
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 12915.48 | 302.5 | 2077.5 | 10837.98
CDE 33523223900 | 2022-08-11 | 9500 | Move PM Time from DA23 9277.00 to MM22 9277.00 |  | 12915.48 | 25 | 2102.5 | 10812.98
CDE 33523236900 | 2022-08-24 | 9500 | Move PM Time from DA23 9277.00 to MM22 9277.00 |  | 12915.48 | 2.5 | 2105 | 10810.48
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 12915.48 | 137.5 | 2242.5 | 10672.98
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12915.48 | 220 | 2462.5 | 10452.98
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12915.48 | 192.5 | 2655 | 10260.48
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 12915.48 | 137.5 | 2792.5 | 10122.98
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 79.73 | 12995.21 | 79.73 | 2872.23 | 10122.98
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 126.95 | 13122.16 | 126.95 | 2999.18 | 10122.98
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 137.32 | 13259.48 | 137.32 | 3136.5 | 10122.98
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 151.33 | 13410.81 | 151.33 | 3287.83 | 10122.98
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 137.59 | 13548.4 | 137.59 | 3425.42 | 10122.98
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 13548.4 | 110.21 | 3535.63 | 10012.77
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 13548.4 | 36.42 | 3572.05 | 9976.35
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 13548.4 | 319.21 | 3891.26 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 69.97 | 13618.37 | 69.97 | 3961.23 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 37.44 | 13655.81 | 37.44 | 3998.67 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 7.13 | 13662.94 | 7.13 | 4005.8 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 31.74 | 13694.68 | 31.74 | 4037.54 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 29.28 | 13723.96 | 29.28 | 4066.82 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 16.48 | 13740.44 | 16.48 | 4083.3 | 9657.14
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 13740.44 | 14.99 | 4098.29 | 9642.15
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 13740.44 | 90.9 | 4189.19 | 9551.25
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 13740.44 | 10.13 | 4199.32 | 9541.12
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 13740.44 | 44.58 | 4243.9 | 9496.54
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 13740.44 | 7.41 | 4251.31 | 9489.13
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 13740.44 | 46.4 | 4297.71 | 9442.73
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 13740.44 | 7.83 | 4305.54 | 9434.9
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 13740.44 | 57.2 | 4362.74 | 9377.7
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 13740.44 | 36.63 | 4399.37 | 9341.07
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 13740.44 | 327.3 | 4726.67 | 9013.77
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 13740.44 | 376.1 | 5102.77 | 8637.67
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 13740.44 | 2396.4 | 7499.17 | 6241.27
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 13740.44 | 101.07 | 7600.24 | 6140.2
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 13740.44 | 566.2 | 8166.44 | 5574
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 13740.44 | 104.63 | 8271.07 | 5469.37
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 13740.44 | 724.7 | 8995.77 | 4744.67
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 13740.44 | 102.85 | 9098.62 | 4641.82
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 13740.44 | 827.2 | 9925.82 | 3814.62
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 13740.44 | 70.74 | 9996.56 | 3743.88
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 13740.44 | 535.5 | 10532.06 | 3208.38
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 13740.44 | 44.91 | 10576.97 | 3163.47
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 13740.44 | 326.6 | 10903.57 | 2836.87
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 13740.44 | 60.69 | 10964.26 | 2776.18
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 13740.44 | 533.9 | 11498.16 | 2242.28
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 13740.44 | 61.65 | 11559.81 | 2180.63
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 13740.44 | 308.5 | 11868.31 | 1872.13
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 13740.44 | 42.28 | 11910.59 | 1829.85
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 13740.44 | 323.1 | 12233.69 | 1506.75
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 13740.44 | 32.94 | 12266.63 | 1473.81
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 13740.44 | 271.5 | 12538.13 | 1202.31
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 13740.44 | 10.16 | 12548.29 | 1192.15
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 13740.44 | 97.2 | 12645.49 | 1094.95
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 13740.44 | 20.13 | 12665.62 | 1074.82
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 13740.44 | 215 | 12880.62 | 859.82
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 13740.44 | 47.46 | 12928.08 | 812.36
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 13740.44 | 241.9 | 13169.98 | 570.46
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 13740.44 | 24.51 | 13194.49 | 545.95
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 13740.44 | 221.3 | 13415.79 | 324.65
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13740.44 | 32.75 | 13448.54 | 291.9
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13740.44 | 219.9 | 13668.44 | 72
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13740.44 | 9.7 | 13678.14 | 62.3
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13740.44 | 62.3 | 13740.44 | 2.4158e-12
[5 empty] | 13740.44 |  | 13740.44 | 2.4158e-12
[5 empty] | 13740.44 |  | 13740.44 | 2.4158e-12
[5 empty] | 13740.44 |  | 13740.44 | 2.4158e-12
[5 empty] | 13740.44 |  | 13740.44 | 2.4158e-12
[5 empty] | 13740.44 |  | 13740.44 | 2.4158e-12
|  |  | Totals: | 13740.44 |  | 13740.44 |  | 0
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Mon, Jan 31, 4:12 PM (22 hours ago) to me Would you please create the following PM Time Budgets? MM22 9273.00 for $4.000.00 MM22 9274.00 for $4,500.00 MM22 9277.00 for $4,000.00 MM22 9279.00 for $16,875.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Increases $John Kleene, Jennifer Fri, Apr 7, 3:41 PM (3 days ago) to me, Scott Please increase the PM Time for the following projects: DA21 9207.00, please increase the PM time by $4,675.00 MM22 9244.00, please increase the PM time by $9,350.00 MM22 9277.00, please increase the PM time by $4,675.00 Regards, Jennifer PM Time Budget Changes Inbox Kleene, Jennifer 4:08 PM (0 minutes ago) to me For MM21 Project 8982.01, please increase the PM Time budget by $1,100.00. For MM22 9277.00, please increase the PM Time budget by $3,740.00. Regards, Jennifer DAS Cost Budget Increases $Joni Kleene, Jennifer 2:34 PM (4 minutes ago) to me Please make the following DAS Cost/PM Time budget increases: Increase MM22 9277.00 by $1,870.00. Increase DA24 9378.00 by $1,000.00. Regards, Jennifer Re: Split Project 9277.00 $Joni Kleene, Jennifer Mon, Dec 16, 4:59 PM (14 hours ago) to me MM22 MISC tab can be closed, as well as PM time and I will just charge my December time to the MM24 project. Regards, Jennifer

## #9277.00 Misc
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  |  | Major Program 4F08
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523279900 | 2022-10-05 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2447688-Final | 567.5 | 567.5
IET DAS202304115300001 | 2022-11-08 | 2507 |  | #207136356 Electrical | DAS2023041153 | 533.82 | 1101.32
GAX 33523034901 | 2023-02-03 | 9500 | CNST | Trinity Construction V#(VS000004014) | Inv. 1495 | 1317.8 | 2419.12
GAX 33523186801 | 2023-07-05 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010515-IN-FINAL | 1061.51 | 3480.63
GAX 33524268800 | 2023-09-25 | 9500 | CNST | Shermco Industries V#(00003121817) | Inv. 23-12621 | 2180 | 5660.63
5660.63
5660.63
5660.63
5660.63
5660.63
5660.63
5660.63
|  |  |  | Totals: |  | 5660.63

## #9277.00 Bluestone Engineering
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Bluestone Engineering |  |  | Vendor: 00003043700
Acct. Codes-0017-335-MM22-9260 |  |  | RFP927700-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522098801 | 2022-04-07 | PO Procore | 15335 | 15335 |  |  | 15335
PRC 3352209PA8801 | 2022-07-20 | Inv. 11726 |  | 15335 | 10483.25 | 10483.25 | 4851.75 | FY22
PO 33523098801 | 2022-08-10 | Rolled to FY23 | 0 | 15335 |  | 10483.25 | 4851.75
PRC 3352309PB8801 | 2022-09-20 | Inv. 11996 |  | 15335 | 1001.75 | 11485 | 3850
PRC 3352309PC8801 | 2022-12-07 | Inv. 12204 |  | 15335 | 1125 | 12610 | 2725
PRC 3352309PD8801 | 2023-07-12 | Inv. 12683 |  | 15335 | 1125 | 13735 | 1600 | FY23
PO 33524098801 | 2023-07-25 | Roll to FY24 | 0 | 15335 |  | 13735 | 1600
PO 33524098801 | 2024-03-25 | CO #1 | -1600 | 13735 |  | 13735 | 0
|  |  |  | 13735 |  | 13735 | 0
|  |  |  | 13735 |  | 13735 | 0
|  |  |  | 13735 |  | 13735 | 0
|  |  |  | 13735 |  | 13735 | 0
|  |  |  | 13735 |  | 13735 | 0
|  | Total: | 13735 |  | 13735 |  | 0
|  | Design Development Documents | 3835 |  | 3835 |  | 0
|  | 100% Construction Documents | 7200 |  | 7200 |  | 0
|  | Pricing/Negotiation Assistance | 450 |  | 450 |  | 0
|  | Construction Phase | 2250 |  | 2250 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Total: | 13735 |  | 13735 |  | 0

## #9277.00 Cummins
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Cummins Inc. |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM22-9255 |  |  | MA21233A
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split with R22M & DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523234800 | 2022-08-19 | PO Procore | 350495 | 350495 |  |  | 350495 |  | FY23
PO 33524234800 | 2023-08-22 | Roll to FY24 | 0 | 350495 |  | 0 | 350495
PRC 3352423PA4800 | 2023-08-23 | Inv. E3-38102 (Split between MM22, DA23 and R21M) |  | 350495 | 265442.35 | 265442.35 | 85052.65 | 13970.65
PO 33524234800 | 2024-03-22 | CO #1(100% to MM22) | 33495 | 383990 |  | 265442.35 | 118547.65
PO 33524234800 | 2024-07-24 | CO update to Transfer R21M to R22M | 0 | 383990 |  | 265442.35 | 118547.65 |  | FY24
PO 33525234800 | 2024-08-26 | Roll to FY25 |  | 383990 |  | 265442.35 | 118547.65
PO 33525234800 | 2024-08-30 | CO #2(No Cost CO-100% to MM22) | 0 | 383990 |  | 265442.35 | 118547.65
PO 33525234800 | 2024-12-17 | CO #3 (Moving MM22 to MM24) | -118547.65 | 265442.35 |  | 265442.35 | 0
|  |  |  | 265442.35 |  | 265442.35 | 0
|  |  |  | 265442.35 |  | 265442.35 | 0
|  |  |  | 265442.35 |  | 265442.35 | 0
|  |  |  | 265442.35 |  | 265442.35 | 0
|  |  |  | 265442.35 |  | 265442.35 | 0
|  | Total: | 265442.35 |  | 265442.35 |  | 0
|  | R21M (Closed 07/24/24) | 25826.7 |  | 25826.7 |  | 0
|  | DA23 | 108744 |  | 103306.8 |  | 5437.2
|  | R22M | 1359.3 |  | 0 |  | 1359.3
|  | MM24 | 118547.65 |  |  |  | 118547.65
|  | Total Contract: | 519920 |  | 394575.85 |  | 125344.15

## #9277.00 DCI Group (CA)
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
DCI Group CA |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523256901 | 2022-09-12 | PO Procore | 21274.05 | 21274.05 |  |  | 21274.05
PRC 3352325PA6901 | 2022-11-07 | Inv. 22-004 CA-01 |  | 21274.05 | 2933.93 | 2933.93 | 18340.12
PRC 3352325PB6901 | 2022-11-14 | Inv. 22-004 CA-02 |  | 21274.05 | 1596.06 | 4529.99 | 16744.06
PRC 3352325PC6901 | 2023-01-18 | Inv. 22-004 CA-03 |  | 21274.05 | 3330.01 | 7860 | 13414.05
PRC 3352325PD6901 | 2023-03-20 | Inv. 22-004 CA-04 |  | 21274.05 | 610.4 | 8470.4 | 12803.65
PRC 3352325PE6901 | 2023-04-25 | Inv. 22-004 CA-05 |  | 21274.05 | 343.1 | 8813.5 | 12460.55
PRC 3352325PF6901 | 2023-06-25 | Inv. 22-004 CA-06 |  | 21274.05 | 2169.93 | 10983.43 | 10290.62
PRC 3352325PG6901 | 2023-07-17 | Inv. 22-004 CA-07 |  | 21274.05 | 2099.18 | 13082.61 | 8191.44 | FY23
PO 33524256901 | 2023-07-28 | Rolled to FY24 | 0 | 21274.05 |  | 13082.61 | 8191.44
PRC 3352425PH6901 | 2023-10-10 | Inv. 22-004 CA-08 |  | 21274.05 | 8043.62 | 21126.23 | 147.82 | FY24
PO 33525256901 | 2024-07-19 | Roll to FY25 |  | 21274.05 |  | 21126.23 | 147.82
PO 33525256901 | 2024-12-16 | Move to MM24 | -147.82 | 21126.23 |  | 21126.23 | -3.0127e-12
|  |  |  | 21126.23 |  | 21126.23 | -3.0127e-12
|  | Totals: | 21126.23 |  | 21126.23 |  | 0

## #9277.00 Siemens
DAS CC Main Switchgear Master Control Replacement
Project # 9277.00
Program code 927700 |  |  | Major Program 4F08
Siemens-BAS Integration |  |  | Vendor: 00002089900
Acct. Codes-0017-335-MM22-9255 |  |  | MA20358
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523320801 | 2022-11-15 | DO Procore | 7328 | 7328 |  |  | 7328 | FY23
DO 33524320801 | 2023-07-28 | Rolled to FY24 | 0 | 7328 |  | 0 | 7328
PRC 3352432PA0801 | 2024-08-12 | Inv. 5331023575 |  | 7328 | 6595.2 | 6595.2 | 732.8 | FY24
DO 33525320801 | 2024-08-13 | Roll to FY25 |  | 7328 |  | 6595.2 | 732.8
DO 33525320801 | 2024-12-16 | Move to MM24 | -732.8 | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  |  |  | 6595.2 |  | 6595.2 | 0
|  | Total: | 6595.2 |  | 6595.2 |  | 0

## RECAP #9278.00
DOC MPCF Elevator D
Project # 9278.00
Program code 927800 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
CLOSED 09/27/2022

## #9278.00 Vendor A
DOC MPCF Elevator D
Project # 9278.00
Program code 927800 |  |  | Major Program 4D03
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9278.00 PM TIME
DOC MPCF Elevator D
Project # 9278.00
Program code 927800 |  |  | Major Program 4D03
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 150 | 150 |  |  | 150
IET DAS202208115300001 | 2022-03-07 | PM-Feb 1-Feb 28, 2022 |  | 150 | 50 | 50 | 100
CDE 33522074900 | 2022-03-14 | Moving PM time to 9275 | -50 | 100 | -50 | 0 | 100
IET DAS202209115300001 | 2022-04-08 | PM-March 1-March 31, 2022 |  | 100 | 100 | 100 | 0
CDE 33522101903 | 2022-04-11 | Moving PM Time to 9224.00 MM21 | -100 | 0 | -100 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9278.00 Misc
DOC MPCF Elevator D
Project # 9278.00
Program code 927800 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9279.00
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
| Program code 927900 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 386023.27
C | Story Construction |  | 35998.59 | 35998.59 | 0
| PM TIME |  | 32262.48 | 31472.72 | 789.76
| Misc. |  | 13387.2 | 13387.2 | 0
C | Shive Hattery |  | 274800 | 274800 | 0
| SystemWorks LLC |  | 29575 | 25220 | 4355
| Total Project Cost | 386023.27 | 386023.27 | 380878.51 | 5144.76 | 0

## #9279.00 Story Construction
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
Program code 927900 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522111801 | 2022-04-14 | PO Procore | 24349.17 | 24349.17 |  |  | 24349.17
PO 33522111801 | 2022-04-19 | CO #1 (No cost) | 0 | 24349.17 |  | 0 | 24349.17
PRC 3352211PA1801 | 2022-06-20 | Inv. 33175 |  | 24349.17 | 4762.5 | 4762.5 | 19586.67
PRC 3352211PB1801 | 2022-07-20 | Inv. 33228 |  | 24349.17 | 2031.5 | 6794 | 17555.17 | FY22
PO 33523111801 | 2022-08-10 | Rolled to FY23 | 0 | 24349.17 |  | 6794 | 17555.17
PRC 3352311PC1801 | 2022-08-31 | Inv. 33284 |  | 24349.17 | 3690.14 | 10484.14 | 13865.03
PRC 3352311PD1801 | 2022-09-20 | Inv. 33349 |  | 24349.17 | 3012.81 | 13496.95 | 10852.22
PRC 3352311PE1801 | 2022-10-18 | Inv. 33407 |  | 24349.17 | 2358 | 15854.95 | 8494.22
PRC 3352311PF1801 | 2022-11-21 | Inv. 33465 |  | 24349.17 | 4182.14 | 20037.09 | 4312.08
PO 33523111801 | 2022-12-06 | CO #2 | 6318 | 30667.17 |  | 20037.09 | 10630.08
PRC 3352311PG1801 | 2022-12-20 | Inv. 33520 |  | 30667.17 | 2725.5 | 22762.59 | 7904.58
PRC 3352311PH1801 | 2023-01-23 | Inv. 33587 |  | 30667.17 | 7528.5 | 30291.09 | 376.08
PO 33523111801 | 2023-02-23 | CO #3 | 5700 | 36367.17 |  | 30291.09 | 6076.08
PRC 3352311PI1801 | 2023-03-20 | Inv. 33688-Final | -368.58 | 35998.59 | 5707.5 | 35998.59 | -1.8758e-12
|  |  |  | 35998.59 |  | 35998.59 | -1.8758e-12
|  |  |  | 35998.59 |  | 35998.59 | -1.8758e-12
|  |  |  | 35998.59 |  | 35998.59 | -1.8758e-12
|  |  |  | 35998.59 |  | 35998.59 | -1.8758e-12
|  |  |  | 35998.59 |  | 35998.59 | -1.8758e-12
|  | Totals: | 35998.59 |  | 35998.59 |  | 0 | FINAL
|  | CM Services | 23958 |  | 23958
|  | Reimbursables | 31.59 |  | 31.59
|  | CO #2 | 6318 |  | 6318
|  | CO #3 | 5691 |  | 5691
|  | Total: | 35998.59 |  | 35998.59 |  | 0

## #9279.00 PM TIME
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
Program code 927900 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E215
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 25345 | 25345 |  |  | 25345
IET DAS202207115300001 | 2022-02-08 |  | PM-Jan 1-Jan 31, 2022 |  | 25345 | 125 | 125 | 25220
IET DAS202208115300001 | 2022-03-07 |  | PM-Feb 1-Feb 28, 2022 |  | 25345 | 825 | 950 | 24395
IET DAS202209115300001 | 2022-04-08 |  | PM-March 1-March 31, 2022 |  | 25345 | 925 | 1875 | 23470
IET DAS202210115300001 | 2022-05-06 |  | PM-April 1-April 29, 2022 |  | 25345 | 1175 | 3050 | 22295
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 25345 | 600 | 3650 | 21695
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 25345 | 625 | 4275 | 21070
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 25345 | 1200 | 5475 | 19870
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 25345 | -1200 | 4275 | 21070
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 25345 | 1320 | 5595 | 19750
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 25345 | 880 | 6475 | 18870
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 25345 | 825 | 7300 | 18045
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 25345 | 1870 | 9170 | 16175
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 25345 | 1870 | 11040 | 14305
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 478.4 | 25823.4 | 478.4 | 11518.4 | 14305
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 812.44 | 26635.84 | 812.44 | 12330.84 | 14305
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 514.96 | 27150.8 | 514.96 | 12845.8 | 14305
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 1469.99 | 28620.79 | 1469.99 | 14315.79 | 14305
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 1871.21 | 30492 | 1871.21 | 16187 | 14305
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 30492 | 3251.04 | 19438.04 | 11053.96
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 30492 | 400.54 | 19838.58 | 10653.42
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 30492 | 3511.42 | 23350 | 7142
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 305.31 | 30797.31 | 305.31 | 23655.31 | 7142
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 239.59 | 31036.9 | 239.59 | 23894.9 | 7142
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 213.98 | 31250.88 | 213.98 | 24108.88 | 7142
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 126.93 | 31377.81 | 126.93 | 24235.81 | 7142
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 398.3 | 31776.11 | 398.3 | 24634.11 | 7142
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 486.37 | 32262.48 | 486.37 | 25120.48 | 7142
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 32262.48 | 464.72 | 25585.2 | 6677.28
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 32262.48 | 2818.08 | 28403.28 | 3859.2
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 32262.48 | 81.08 | 28484.36 | 3778.12
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 32262.48 | 356.62 | 28840.98 | 3421.5
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 32262.48 | 23.28 | 28864.26 | 3398.22
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 32262.48 | 137 | 29001.26 | 3261.22
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 32262.48 | 47.21 | 29048.47 | 3214.01
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 32262.48 | 427.1 | 29475.57 | 2786.91
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 32262.48 | 155.56 | 29631.13 | 2631.35
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 32262.48 | 991.4 | 30622.53 | 1639.95
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 32262.48 | 59.3 | 30681.83 | 1580.65
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 32262.48 | 331.2 | 31013.03 | 1249.45
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 32262.48 | 16.01 | 31029.04 | 1233.44
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 32262.48 | 130.6 | 31159.64 | 1102.84
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2024 |  | 32262.48 | 6.52 | 31166.16 | 1096.32
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2024 |  | 32262.48 | 46.6 | 31212.76 | 1049.72
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 32262.48 | 17.45 | 31230.21 | 1032.27
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 32262.48 | 87.9 | 31318.11 | 944.37
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 32262.48 | 12.38 | 31330.49 | 931.99
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 32262.48 | 91.7 | 31422.19 | 840.29
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 32262.48 | 6.33 | 31428.52 | 833.96
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 32262.48 | 44.2 | 31472.72 | 789.76
[5 empty] | 32262.48 |  | 31472.72 | 789.76
[5 empty] | 32262.48 |  | 31472.72 | 789.76
[5 empty] | 32262.48 |  | 31472.72 | 789.76
|  |  | Totals: | 32262.48 |  | 31472.72 |  | 789.76
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Mon, Jan 31, 4:12 PM (22 hours ago) to me Would you please create the following PM Time Budgets? MM22 9273.00 for $4.000.00 MM22 9274.00 for $4,500.00 MM22 9277.00 for $4,000.00 MM22 9279.00 for $16,875.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Changes $Joni Kleene, Jennifer Fri, Feb 3, 4:46 PM (3 days ago) to me, Scott Please increase the PM Time budget for DA22 9216.00 by $10,000.00. Please increase the PM Time budget for MM22 9217.00 by $1,100.00. Please increase the PM Time budget for MM22 9279.00 by $4,400.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Re: 9279.00 MM22 PM Time Budget Inbox Kleene, Jennifer 8:02 AM (38 minutes ago) to me Please increase the PM Time budget by $1,870.00. Regards, Jennifer PM Time Changes $John Kleene, Jennifer 1:58 PM (1 hour ago) to me, Scott Please increase PM time for the following projects: MM22 9279.00 increase by $2,200.00 DA20 9159.00 increase by $3,740.00 MM23 9339.00 Increase by $4,488.00 Regards, Jennifer

## #9279.00 Shive Hattery
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
Program code 927900 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 9279.00-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split w/ MM23 and DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522166901 | 2022-06-15 | PO Procore | 532800 | 532800 |  |  | 532800
PRC 3352216PA6901 | 2022-07-05 | Inv. 2142203390-1 |  | 532800 | 7302.75 | 7302.75 | 525497.25 | FY22
PO 33523166901 | 2022-08-10 | Rolled to FY23 | 0 | 532800 |  | 7302.75 | 525497.25
PRC 3352316PB6901 | 2022-08-12 | Inv. 2142203390-2 |  | 532800 | 58422 | 65724.75 | 467075.25
PRC 3352316PC6901 | 2022-09-06 | Inv. 2142203390-3 |  | 532800 | 65856.7 | 131581.45 | 401218.55
PRC 3352316PD6901 | 2022-09-28 | Inv. 2142203390-4 |  | 532800 | 70340.55 | 201922 | 330878
PRC 3352316PE6901 | 2022-10-28 | Inv. 2142203390-5 |  | 532800 | 49160 | 251082 | 281718
PRC 3352316PF6901 | 2023-01-25 | Inv. 2142203390-6 |  | 532800 | 23718 | 274800 | 258000
PO 33523166901 | 2023-02-09 | CO #1 (Split with DA23 and MM23) | -258000 | 274800 |  | 274800 | 0
|  |  |  | 274800 |  | 274800 | 0
|  |  |  | 274800 |  | 274800 | 0
|  |  |  | 274800 |  | 274800 | 0
|  |  |  | 274800 |  | 274800 | 0
|  | Totals: | 274800 |  | 274800 |  | 0
|  | DD Pre-Design | 135276 |  | 135276 |  | 0
|  | DD Design Documents | 70472.5 |  | 70472.5 |  | 0
|  | Construction Documents | 69051.5 |  | 69051.5 |  | 0
|  | Total: | 274800 |  | 274800 |  | 0
|  | 9279.20 MM23 | 79640 |  | 48485 |  | 31155
|  | 9279.21 DA23 | 18203 |  | 8525.45 |  | 9677.55
|  | Total Contract: | 372643 |  | 331810.45 |  | 40832.55

## #9279.00 Misc
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
Program code 927900 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523336806 | 2022-12-02 | 9500 | CNST | Systems Management and Balancing Inc. V#(00002136547) | Inv. 1102 FINAL | 9720 | 9720
GAX 33523055806 | 2023-02-24 | 9500 | CNST | Shive Hattery Inc. V#(00002108803) | Inv. 2142203390 - HAZ-1 | 2719 | 12439
PRC 33523067809 | 2023-03-08 | 9500 | CNST | Rapids Reproductions Inc. V#(00002111375) | Inv. 420536-0 | 472.54 | 12911.54
PRC 33523097801 | 2023-04-07 | 9500 | CNST | Rapids Reproductions Inc. V#(00002111375) | Inv. 420664-0 | 328.8 | 13240.34
PRC 33523159804 | 2023-06-08 | 9500 | CNST | Rapids Reproductions Inc. V#(00002111375) | Inv. 420701-0 | 146.86 | 13387.2
13387.2
13387.2
13387.2
13387.2
13387.2
13387.2
13387.2
|  |  |  | Totals: |  | 13387.2

## #9279.00 SystemWorks LLC
DHS WRC Campus Utility Decentralization Phase 1
Project # 9279.00
Program code 927900 |  |  | Major Program 4B02
SystemWorks LLC |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFQ927900-02
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523350803 | 2022-12-16 | PO Procore | 29575 | 29575 |  |  | 29575
PRC 3352335PA0803 | 2023-02-23 | Inv. 11130 |  | 29575 | 3120 | 3120 | 26455
PRC 3352335PB0803 | 2023-07-12 | Inv. 11290 |  | 29575 | 1560 | 4680 | 24895 | FY23
PO 33524350803 | 2023-08-03 | Roll to FY24 | 0 | 29575 |  | 4680 | 24895
PRC 3352435PC0803 | 2023-09-18 | Inv. 11415 |  | 29575 | 2600 | 7280 | 22295
PRC 3352435PD0803 | 2024-03-20 | Inv. 11687 |  | 29575 | 6140 | 13420 | 16155
PRC 3352435PE0803 | 2024-07-02 | Inv. 11872 |  | 29575 | 675 | 14095 | 15480 | FY24
PO 33525350803 | 2024-07-19 | Roll to FY25 |  | 29575 |  | 14095 | 15480
PRC 3352535PF0803 | 2025-03-21 | Inv. 12278 |  | 29575 | 11125 | 25220 | 4355
|  |  |  | 29575 |  | 25220 | 4355
|  |  |  | 29575 |  | 25220 | 4355
|  |  |  | 29575 |  | 25220 | 4355
|  |  |  | 29575 |  | 25220 | 4355
|  | Totals: | 29575 |  | 25220 |  | 4355

## RECAP #9279.30
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
| Program code 927930 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 266000
C | Story Construction #W02PC |  | 15505.28 | 15505.28 | 0
| PM TIME |  | 14378.65 | 14378.65 | 0
| Misc. |  | 1034.99 | 1034.99 | 0
C | Shive Hattery |  | 217100 | 217100 | 0
| SystemWorks |  | 9515 | 7612 | 1903
C | ATC Group |  | 5202.5 | 5202.5 | 0
| ATC Group (2) |  | 3136.25 | 1883.75 | 1252.5
| Total Project Cost | 266000 | 265872.67 | 262717.17 | 3155.5 | 127.33

## #9279.30 Story Construction
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Story Construction #W02PC |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Split with DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523111901 | 2023-04-21 | PO Procore | 29005.93 | 29005.93 |  |  | 29005.93
PRC 3352311PA1901 | 2023-06-21 | Inv. 33847 |  | 29005.93 | 1530.76 | 1530.76 | 27475.17
PRC 3352311PB1901 | 2023-07-19 | Inv. 33905 |  | 29005.93 | 1868.54 | 3399.3 | 25606.63 | FY23
PO 33524111901 | 2023-07-26 | Rolled to FY24 | 0 | 29005.93 |  | 3399.3 | 25606.63
PRC 3352411PC1901 | 2023-08-22 | Inv. 33962 |  | 29005.93 | 3188.3 | 6587.6 | 22418.33
PRC 3352411PD1901 | 2023-09-18 | Inv. 34016 |  | 29005.93 | 456.26 | 7043.86 | 21962.07
PRC 3352411PE1901 | 2023-10-16 | Inv. 34075 |  | 29005.93 | 6010.84 | 13054.7 | 15951.23
PRC 3352411PF1901 | 2023-11-21 | Inv. 34128 |  | 29005.93 | 11019.65 | 24074.35 | 4931.58
PO 33524111901 | 2024-01-11 | CO #1 | 5075.16 | 34081.09 |  | 24074.35 | 10006.74
PO 33524111901 | 2024-02-08 | CO #2 | -18561.66 | 15519.43 |  | 24074.35 | -8554.92
CDE 33524039803 | 2024-02-08 | Move expense to DA24 |  | 15519.43 | -13783.37 | 10290.98 | 5228.45
PRC 3352411PG1901 | 2024-02-15 | Inv. 34253-FINAL(Split with DA24) | -14.15 | 15505.28 | 5214.3 | 15505.28 | 4.1833e-12
|  |  |  | 15505.28 |  | 15505.28 | 4.1833e-12
|  | Totals: | 15505.28 |  | 15505.28 |  | 0 | FINAL
|  | CM Services | 28887.93 |  | 28887.93 |  | 0
|  | Reimbursables | 118 |  | 118 |  | 0
|  | CO #1 | 5061.01 |  | 5061.01 |  | 0
|  | CO #2 | -18561.66 |  | -18561.66 |  | 0
|  | Total: | 15505.28 |  | 15505.28 |  | 0
|  | DA24 | 24072.7 |  | 24072.7 |  | 0
|  | Total: | 39577.98 |  | 39577.98 |  | 0

## #9279.30 PM TIME
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E260
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14378.65 | 14378.65 |  |  | 14378.65
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 14378.65 | 152.03 | 152.03 | 14226.62
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 14378.65 | 668.67 | 820.7 | 13557.95
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 14378.65 | 124.21 | 944.91 | 13433.74
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 14378.65 | 731 | 1675.91 | 12702.74
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 14378.65 | 364.37 | 2040.28 | 12338.37
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 14378.65 | 2553.1 | 4593.38 | 9785.27
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 14378.65 | 41.92 | 4635.3 | 9743.35
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 14378.65 | 186.9 | 4822.2 | 9556.45
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 14378.65 | 116.33 | 4938.53 | 9440.12
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 14378.65 | 743.7 | 5682.23 | 8696.42
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 14378.65 | 135.04 | 5817.27 | 8561.38
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 14378.65 | 755.3 | 6572.57 | 7806.08
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 14378.65 | 260.62 | 6833.19 | 7545.46
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 14378.65 | 1810.9 | 8644.09 | 5734.56
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 14378.65 | 97.43 | 8741.52 | 5637.13
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 14378.65 | 783.5 | 9525.02 | 4853.63
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 14378.65 | 120.04 | 9645.06 | 4733.59
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 14378.65 | 909.4 | 10554.46 | 3824.19
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 14378.65 | 146 | 10700.46 | 3678.19
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 14378.65 | 1071.9 | 11772.36 | 2606.29
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 14378.65 | 109.85 | 11882.21 | 2496.44
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 14378.65 | 970.1 | 12852.31 | 1526.34
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 14378.65 | 227.38 | 13079.69 | 1298.96
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 14378.65 | 1147.1 | 14226.79 | 151.86
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 14378.65 | 15.76 | 14242.55 | 136.1
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 14378.65 | 136.1 | 14378.65 | -2.5864e-12
[5 empty] | 14378.65 |  | 14378.65 | -2.5864e-12
[5 empty] | 14378.65 |  | 14378.65 | -2.5864e-12
[5 empty] | 14378.65 |  | 14378.65 | -2.5864e-12
[5 empty] | 14378.65 |  | 14378.65 | -2.5864e-12
|  |  | Totals: | 14378.65 |  | 14378.65 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Budgets $Joni Kleene, Jennifer Fri, Mar 31, 5:03 PM (4 days ago) to me For MM22 9279.30, please create a PM time budget of $10,000.00. For MM21 9294.01, please create a PM time budget of $10,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Changes Inbox Kleene, Jennifer 12:20 PM (1 hour ago) to me, Scott MM23 9268.01 Please increase the PM Time budget by $7,480.00. MM22 9248.00 Please increase the PM Time budget by $2,992.00. MM22 9279.30 Please increase the PM Time budget by $7,480.00. Regards, Jennifer

## #9279.30 Misc
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K. | [7 empty] | `
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 165 | 165
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 660 | 825
PRC 33524029909 | 2024-01-29 | 9500 | CNST | Rapids Reproductions Inc. V#(00002111375) | Inv. INVCL240 | 1034.99 | 1859.99
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -825 | 1034.99
1034.99
1034.99
1034.99
1034.99
1034.99
1034.99
1034.99
1034.99
|  |  |  | Totals: |  | 1034.99

## #9279.30 Shive Hattery
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split with DA24 & MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523116902 | 2023-04-26 | PO Procore | 153200 | 153200 |  |  | 153200
PRC 3352311PA6902 | 2023-05-30 | Inv. 2142203394-1 |  | 153200 | 30400 | 30400 | 122800
PO 33523116902 | 2023-06-15 | CO #1 | 63900 | 217100 |  | 30400 | 186700
PRC 3352311PB6902 | 2023-07-10 | Inv. 2142203394-2 |  | 217100 | 80350 | 110750 | 106350 | FY23
PO 33524116902 | 2023-07-26 | Rolled to FY24 | 0 | 217100 |  | 110750 | 106350
PRC 3352411PC6902 | 2023-08-04 | Inv. 2142203394-3 |  | 217100 | 49950 | 160700 | 56400
PO 33524116902 | 2023-08-04 | CO #2 | 0 | 217100 |  | 160700 | 56400
PRC 3352411PD6902 | 2023-08-31 | Inv. 2142203394-4 (Split between MM22 and DA24) |  | 217100 | 12475 | 173175 | 43925
PRC 3352411PE6902 | 2023-10-04 | Inv. 2142203394-5 (Split between MM22 and DA24) |  | 217100 | 34930 | 208105 | 8995
PO 33524116902 | 2023-11-29 | CO #3 (100% DA24) | 0 | 217100 |  | 208105 | 8995
PRC 3352411PF6902 | 2023-12-06 | Inv. 2142203394-6 (Split between MM22 and DA24) |  | 217100 | 2495 | 210600 | 6500
PO 33524116902 | 2024-01-19 | CO #4 (Split between MM24 and DA24) | 0 | 217100 |  | 210600 | 6500
PRC 3352411PG6902 | 2024-01-20 | Inv. 2142203394-7(Split between MM22 and DA24) |  | 217100 | 6500 | 217100 | 0
|  | Totals: | 217100 |  | 217100 |  | 0
|  | Schematic Design | 60800 |  | 60800 |  | 0
|  | Design Development | 36000 |  | 36000 |  | 0
|  | Construction Documents | 49900 |  | 49900 |  | 0
|  | Bidding | 6500 |  | 6500 |  | 0
|  | CO #1 | 63900 |  | 63900 |  | 0
|  | Total: | 217100 |  | 217100 |  | 0
|  | DA24 | 0 |  | 0 |  | 8712
|  | MM24 | 25969 |  | 18402.5 |  | 7566.5
|  | Total: | 243069 |  | 235502.5 |  | 16278.5

## #9279.30 SystemWorks
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM22-9255 |  |  | RFP927900-02
Project Manager - Jennifer K. |  |  | Activity code: CNST
Split with DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524233802 | 2023-08-21 | PO Procore | 9515 | 9515 |  |  | 9515
PRC 3352423PA3802 | 2024-03-18 | Inv. 11688(100% to DA24) |  | 9515 | 0 | 0 | 9515
PRC 3352423PB3802 | 2024-07-03 | Inv. 11873(Split between MM22 and DA24) |  | 9515 | 2000 | 2000 | 7515 | FY24
PO 33525233802 | 2024-08-28 | Roll to FY25 |  | 9515 |  | 2000 | 7515
PRC 3352523PC3802 | 2025-03-21 | Inv. 12279 |  | 9515 | 5612 | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  |  |  | 9515 |  | 7612 | 1903
|  | Totals: | 9515 |  | 7612 |  | 1903
|  | DA24 | 40980 |  | 21833 |  | 19147
|  | Total: | 50495 |  | 29445 |  | 21050

## #9279.30 ATC Group
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA00520262C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Split with DA23 and DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524264800 | 2023-09-21 | DO Procore | 6695 | 6695 |  |  | 6695
DO 33524264800 | 2024-04-16 | CO #1 | -1492.5 | 5202.5 |  | 0 | 5202.5
PRC 3352426PA4800 | 2024-04-26 | Inv. 9279.31-001(Split w/DA23 & DA24) |  | 5202.5 | 5202.5 | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  |  |  | 5202.5 |  | 5202.5 | 0
|  | Totals: | 5202.5 |  | 5202.5 |  | 0
|  | Contract Line 7 - Field Technician Hourly Rate (32 hours at $75.00/hr) | 2400 |  | 2400 |  | 0
|  | Contract Line 8 - Hygienist Hourly Rate (32 hours at $95.00/hr) | 3040 |  | 3040 |  | 0
|  | Contract Line 5 - Adminstrative Hourly Rate (4 hours at $45.00/hr) | 180 |  | 180 |  | 0
|  | Contract Line 2 - Asbestos Per Sample Fee (70 samples at $10.00/ea) | 700 |  | 700 |  | 0
|  | Contract Line 3 - Lead Per Sample Fee (25 samples at $15.00/ea) | 375 |  | 375 |  | 0
|  | CO #1 | -1492.5 |  | -1492.5 |  | 0
|  | Total: | 5202.5 |  | 5202.5 |  | 0
|  | DA23 | 2737.5 |  | 2737.5 |  | 0
|  | DA24 | 14677.5 |  | 14677.5 |  | 0
|  | Total: | 22617.5 |  | 22617.5 |  | 0

## #9279.30 ATC Group (2)
DHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
ATC Group (2) |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA00520262C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Split with DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524349800 | 2023-12-15 | DO Procore | 3136.25 | 3136.25 |  |  | 3136.25
DO 33524349800 | 2024-02-08 | CO #1(100% to DA24) | 0 | 3136.25 |  | 0 | 3136.25
DO 3352434PA9800 | 2024-04-15 | Inv. 2559085(Split with DA24) |  | 3136.25 | 912.5 | 912.5 | 2223.75
DO 33524349800 | 2024-06-28 | Closing DO to Apply CO#2 | 0 | 3136.25 |  | 912.5 | 2223.75
DO 33524349800A | 2024-06-28 | Opeing DO W/4th Commodity Line | 0 | 3136.25 |  | 912.5 | 2223.75
DO 3352434PB9800A | 2024-07-25 | Inv. 9279.30-002(Split with DA24) |  | 3136.25 | 971.25 | 1883.75 | 1252.5 | FY24
DO 33525349800A | 2024-08-28 | Roll to FY25 |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  |  |  | 3136.25 |  | 1883.75 | 1252.5
|  | Totals: | 3136.25 |  | 1883.75 |  | 1252.5
|  | Contract Line 7 - Field Technician Hourly Rate (25.5 hours at $75.00/hr) | 1912.5 |  | 1031.25 |  | 881.25
|  | Contract Line 8 - Hygienist Hourly Rate (10.75 hours at $95.00/hr) | 1021.25 |  | 807.5 |  | 213.75
|  | Contract Line 5 - Adminstrative Hourly Rate (4.5 hours at $45.00/hr) | 202.5 |  | 45 |  | 157.5
|  | CO #1 | 0 |  |  |  | 0
|  | CO #2 | 0 |  |  |  | 0
|  | Total: | 3136.25 |  | 1883.75 |  | 1252.5
|  | DA24 | 11681.25 |  | 3311.25 |  | 8370
|  | Total: | 14817.5 |  | 5195 |  | 9622.5

## RECAP #9290.00
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
| Program code 929000 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
| Funds Recv'd | 152210.17
C | McGough Construction |  | 10496.42 | 10496.42 | 0
C | PM TIME |  | 10348.4 | 10348.4 | 0
C | Misc. |  | 886.93 | 886.93 | 0
C | Shive Hattery |  | 14365 | 14365 | 0
C | Midstate Plumbing & Heating |  | 93095.42 | 93095.42 | 0
C | McGough Construction 2 |  | 23018 | 23018 | 0
| Total Project Cost | 152210.17 | 152210.17 | 152210.17 | 0 | 0
CLOSED 05/21/2024
29C20 Paperwork submitted 03/21/2024
29C20 Funds Recv'd 05/20/24

## #9290.00 Funds Rec'd
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  | Major Program 4B01
Funds Rec'd
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | 29C20 Reimursement | IET 6542378202405172403 | 2024-05-20 | 152210.17 | 152210.17
| Total Requested | 0 | Total Transferred |  |  | 152210.17 | 152210.17

## #9290.00 McGough Construction
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFP 1821335228
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522145800 | 2022-05-25 | PO Procore | 9422.98 | 9422.98 |  |  | 9422.98
PRC 3352214PA5800 | 2022-07-11 | Inv. 9290.001-1 |  | 9422.98 | 2647.15 | 2647.15 | 6775.83 | FY22
PO 33523145800 | 2022-08-10 | Rolled to FY23 | 0 | 9422.98 |  | 2647.15 | 6775.83
PRC 3352314PB5800 | 2022-08-12 | Inv. 9290.00.001-2 |  | 9422.98 | 2585 | 5232.15 | 4190.83
PRC 3352314PC5800 | 2022-09-09 | Inv. 9290.00.001-3 |  | 9422.98 | 1885.27 | 7117.42 | 2305.56
PO 33523145800 | 2022-10-24 | CO 1 | 1073.44 | 10496.42 |  | 7117.42 | 3379
PRC 3352314PD5800 | 2023-01-18 | Inv. 100877.005-4PC |  | 10496.42 | 3379 | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  |  |  | 10496.42 |  | 10496.42 | 0
|  | Totals: | 10496.42 |  | 10496.42 |  | 0
|  | CM Services | 9196 |  | 9196 |  | 0
|  | Reimbursables | 226.98 |  | 226.98 |  | 0
|  | CO 1 | 1073.44 |  | 1073.44 |  | 0
|  | Total: | 10496.42 |  | 10496.42 |  | 0

## #9290.00 PM TIME
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907Q
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8211.89 | 8211.89 |  |  | 8211.89
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 8211.89 | 975 | 975 | 7236.89
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 8211.89 | 300 | 1275 | 6936.89
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 8211.89 | 975 | 2250 | 5961.89
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 8211.89 | -975 | 1275 | 6936.89
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 8211.89 | 1072.5 | 2347.5 | 5864.39
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 8211.89 | 522.5 | 2870 | 5341.89
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 8211.89 | 275 | 3145 | 5066.89
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 8211.89 | 275 | 3420 | 4791.89
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 8211.89 | 55 | 3475 | 4736.89
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 595.71 | 8807.6 | 595.71 | 4070.71 | 4736.89
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 482.4 | 9290 | 482.4 | 4553.11 | 4736.89
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 171.65 | 9461.65 | 171.65 | 4724.76 | 4736.89
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 216.18 | 9677.83 | 216.18 | 4940.94 | 4736.89
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 55.03 | 9732.86 | 55.03 | 4995.97 | 4736.89
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 9732.86 | 165.3 | 5161.27 | 4571.59
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 9732.86 | 20.8 | 5182.07 | 4550.79
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 9732.86 | 182.41 | 5364.48 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 248.07 | 9980.93 | 248.07 | 5612.55 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 142.26 | 10123.19 | 142.26 | 5754.81 | 4368.38
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 71.33 | 10194.52 | 71.33 | 5826.14 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 117.42 | 10311.94 | 117.42 | 5943.56 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 11.72 | 10323.66 | 11.72 | 5955.28 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 24.74 | 10348.4 | 24.74 | 5980.02 | 4368.38
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 10348.4 | 14.99 | 5995.01 | 4353.39
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 10348.4 | 90.9 | 6085.91 | 4262.49
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 10348.4 | 10.13 | 6096.04 | 4252.36
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 10348.4 | 44.58 | 6140.62 | 4207.78
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 10348.4 | 62 | 6202.62 | 4145.78
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 10348.4 | 365.2 | 6567.82 | 3780.58
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 10348.4 | 20.96 | 6588.78 | 3759.62
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 10348.4 | 189.5 | 6778.28 | 3570.12
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 10348.4 | 19.49 | 6797.77 | 3550.63
IET DAS202401115300001 | 08/07/23 | 9500 | DAS Services for July 1-31, 2023 |  | 10348.4 | 123.3 | 6921.07 | 3427.33
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 10348.4 | 51.09 | 6972.16 | 3376.24
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 10348.4 | 284.2 | 7256.36 | 3092.04
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 10348.4 | 51.77 | 7308.13 | 3040.27
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 10348.4 | 361.5 | 7669.63 | 2678.77
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 10348.4 | 151.57 | 7821.2 | 2527.2
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 10348.4 | 1218.4 | 9039.6 | 1308.8
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10348.4 | 28.55 | 9068.15 | 1280.25
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10348.4 | 213.4 | 9281.55 | 1066.85
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 10348.4 | 12.8 | 9294.35 | 1054.05
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 10348.4 | 93.7 | 9388.05 | 960.35
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10348.4 | 38.74 | 9426.79 | 921.61
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10348.4 | 340.1 | 9766.89 | 581.51
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10348.4 | 96.11 | 9863 | 485.4
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10348.4 | 485.4 | 10348.4 | 0
[5 empty] | 10348.4 |  | 10348.4 | 0
[5 empty] | 10348.4 |  | 10348.4 | 0
[5 empty] | 10348.4 |  | 10348.4 | 0
|  |  | Totals: | 10348.4 |  | 10348.4 |  | 0
Note on E9: Durakovic, Selma [DAS]: New PM Time Budget for 9290.00 $Selma Kleene, Jennifer May 12, 2022, 5:12 PM (14 hours ago) to me Please create a PM Time budget for MM22 9290.00 for $5,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 3:24 PM (10 minutes ago) to me Please make the following changes: 9326.00 MM21 - increase by $2,100.00 9054.03 MM22 - increase by $5,000.00 9262.00 MM22 - increase by $8,000.00 9290.00 MM22 - increase by $3,200.00 9268.01 R22M - increase by $1,000.00 Regards, Jennifer Kleene, Jennifer 2:12 PM (2 minutes ago) to me Thanks for the information. My Admin time was lower than usual last month, so I was surprised the overall costs were higher than the available balance. That being said, please increase the PM Time budgets as follows: Increase 9207.00 by $88.94 Increase 9326.00 by $104.93 Increase 9290.00 by $11.89 Regards, Jennifer

## #9290.00 Misc
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523227800 | 2022-08-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV022714 | 111.93 | 111.93
GAX 33523229902 | 2022-08-10 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2444579-Final | 775 | 886.93
886.93
886.93
886.93
886.93
886.93
886.93
886.93
886.93
886.93
886.93
|  |  |  | Totals: |  | 886.93

## #9290.00 Shive Hattery
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522146900 | 2022-05-26 | PO Procore | 14365 | 14365 |  |  | 14365
PRC 3352214PA6900 | 2022-07-13 | Inv. 2142203550-1 |  | 14365 | 8250 | 8250 | 6115 | FY22
PO 33523146900 | 2022-08-10 | Rolled to FY23 | 0 | 14365 |  | 8250 | 6115
PRC 3352314PB6900 | 2022-08-12 | Inv. 2142203550-2 |  | 14365 | 2650 | 10900 | 3465
PRC 3352314PC6900 | 2022-09-28 | Inv. 2142203550-3 |  | 14365 | 693 | 11593 | 2772
PRC 3352314PD6900 | 2023-01-06 | Inv. 2142203550-4 |  | 14365 | 173.25 | 11766.25 | 2598.75
PRC 3352314PE6900 | 2023-04-24 | Inv. 2142203550-5 |  | 14365 | 1732.5 | 13498.75 | 866.25 | FY23
PO 33524146900 | 2023-08-07 | Rolled to FY24 | 0 | 14365 |  | 13498.75 | 866.25
PRC 3352414PF6900 | 2023-08-24 | Inv. 2142203550-6 |  | 14365 | 173.25 | 13672 | 693
PRC 3352414PG6900 | 2023-11-07 | Inv. 2142203550-7 |  | 14365 | 519.75 | 14191.75 | 173.25
PRC 3352414PH6900 | 2024-02-12 | Inv. 2142203550-8FINAL |  | 14365 | 173.25 | 14365 | 0
|  |  |  | 14365 |  | 14365 | 0
|  |  |  | 14365 |  | 14365 | 0
|  | Totals: | 14365 |  | 14365 |  | 0
|  | Water Heater Design | 8250 |  | 8250 |  | 0
|  | Quote/Bidding Services | 2650 |  | 2650 |  | 0
|  | Construction Admin | 3465 |  | 3465 |  | 0
|  | Total: | 14365 |  | 14365 |  | 0

## #9290.00 Midstate Plumbing
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  | Major Program 4B01
Midstate Plumbing & Heating |  |  | Vendor: 00002108635
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: 929000-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split w/DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523231803 | 2022-08-19 | PO Procore | 106241 | 106241 |  |  | 106241
PO 33523231803 | 2022-10-24 | CO #1 (Split w/DA23) | -15975 | 90266 |  | 0 | 90266
PO 33523231803 | 2022-10-25 | Correction of CO 1 (100% to MM22) | 90 | 90356 |  | 0 | 90356
PRC 3352323PA1803 | 2022-11-30 | Inv. P33389 (100% to MM22) |  | 90356 | 24899.5 | 24899.5 | 65456.5 | 1310.5
PO 33523231803 | 2022-12-20 | CO #2 (100% to MM22) No Cost CO | 0 | 90356 |  | 24899.5 | 65456.5
PRC 3352323PB1803 | 2023-01-31 | Inv. P33843 (100% to MM22) |  | 90356 | 15552.45 | 40451.95 | 49904.05 | 2129.05
PRC 3352323PC1803 | 2023-02-23 | Inv. P34477 (Split between MM22 and DA23) |  | 90356 | 3182.5 | 43634.45 | 46721.55 | 2296.55
PRC 3352323PD1803 | 2023-04-04 | Inv. P34578 (100% to MM22) |  | 90356 | 5761.75 | 49396.2 | 40959.8 | 2599.8
PO 33523231803 | 2023-04-25 | CO #3 (100% to MM22) No Cost CO | 0 | 90356 |  | 49396.2 | 40959.8
PO 33523231803 | 2023-06-23 | CO #4 (100% to MM22) No Cost CO | 0 | 90356 |  | 49396.2 | 40959.8 |  | FY23
PO 33524231803 | 2023-08-29 | Roll to FY24 | 0 | 90356 |  | 49396.2 | 40959.8
PRC 3352423PE1803 | 2023-08-11 | Inv. P34224 |  | 90356 | 19772.35 | 69168.55 | 21187.45 | 3640.45
PO 33524231803 | 2023-09-06 | CO #5 (100% to MM22) | 1657.95 | 92013.95 |  | 69168.55 | 22845.4
PO 33524231803 | 2023-09-22 | CO #6 (100% to MM22) | 1081.47 | 93095.42 |  | 69168.55 | 23926.87
PRC 3352423PF1803 | 2023-10-31 | Inv. 9290.00 Midstate Invoice 6 (Split between MM22 and DA23) |  | 93095.42 | 13479.95 | 82648.5 | 10446.92 | 4349.92
PRC 3352423PG1803 | 2024-01-09 | Inv. P35329 (100% to MM22) |  | 93095.42 | 4783.25 | 87431.75 | 5663.67 | 4601.67
PRC 3352423PH1803 | 2024-01-25 | Inv. P35330 (100% to MM22) |  | 93095.42 | 1008.9 | 88440.65 | 4654.77 | 4654.77
PRC 3352423PI1803 | 2024-01-29 | Inv. P33390 - Retainage |  | 93095.42 | 4654.77 | 93095.42 | 0
|  | Totals: | 93095.42 |  | 93095.42 |  | 0
|  | DA23 | 24835 |  | 24835 |  | 0
|  | Total Contract | 117930.42 |  | 117930.42 |  | 0

## #9290.00 McGough Constructi (2)
DOC FDCF Bldg C Water Heater Replacement (29C20)
Project # 9290.00
Program code 929000 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: RFP1821335228-McGough110112021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523256900 | 2022-09-12 | PO Procore | 26110 | 26110 |  |  | 26110
PRC 3352325PA6900 | 2023-02-10 | Inv. 100877.005CA1 |  | 26110 | 4200.5 | 4200.5 | 21909.5
PRC 3352325PB6900 | 2023-03-13 | Inv. 100877.005CA2 |  | 26110 | 75 | 4275.5 | 21834.5
PRC 3352325PC6900 | 2023-04-07 | Inv. 100877.005-03 |  | 26110 | 807.5 | 5083 | 21027
PRC 3352325PD6900 | 2023-05-09 | Inv. 100877.005-04 |  | 26110 | 582.5 | 5665.5 | 20444.5
PRC 3352325PE6900 | 2023-06-09 | Inv. 100877.005-05 |  | 26110 | 571 | 6236.5 | 19873.5
PRC 3352325PF6900 | 2023-07-07 | Inv. 100877.005-06 |  | 26110 | 894 | 7130.5 | 18979.5 | FY23
PO 33524256900 | 2023-08-07 | Roll to FY24 | 0 | 26110 |  | 7130.5 | 18979.5
PRC 3352425PG6900 | 2023-08-24 | Inv. 100877.005-07 |  | 26110 | 1747.5 | 8878 | 17232
PRC 3352425PH6900 | 2023-09-14 | Inv. 100877.005-08 |  | 26110 | 1721 | 10599 | 15511
PRC 3352425PI6900 | 2023-10-11 | Inv. 100877.005-09 |  | 26110 | 1864 | 12463 | 13647
PRC 3352425PJ6900 | 2023-11-13 | Inv. 100877.005-10 |  | 26110 | 5783.5 | 18246.5 | 7863.5
PRC 3352425PK6900 | 2023-12-12 | Inv. 100877.005-11 |  | 26110 | 1882.5 | 20129 | 5981
PRC 3352425PL6900 | 2024-01-12 | Inv. 100877.005-12 |  | 26110 | 2090.5 | 22219.5 | 3890.5
PRC 3352425PM6900 | 2024-02-06 | Inv. 100877.005-13 |  | 26110 | 504.5 | 22724 | 3386
PRC 3352425PN6900 | 2024-02-16 | Inv. 100877.005-14 - Final | -3092 | 23018 | 294 | 23018 | 0
|  |  |  | 23018 |  | 23018 | 0
|  | Totals: | 23018 |  | 23018 |  | 0 | FINAL
|  | CM Services | 22749 |  | 22749 |  | 0
|  | Reimbursables | 269 |  | 269 |  | 0
|  | Total: | 23018 |  | 23018 |  | 0

## RECAP #9291.00
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
| Program code 929100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
| Funds Recv'd | 259551.33
C | Samuels Group |  | 11670.4 | 11670.4 | 0
C | PM TIME |  | 25749 | 25749 | 0
C | Misc. |  | 167.62 | 167.62 | 0
C | ATC Group Services |  | 1201.25 | 1201.25 | 0
C | IMEG Corporation |  | 20133 | 20133 | 0
C | Capital City Boiler |  | 168792.5 | 168792.5 | 0
C | Samuels Group #117CA |  | 31837.56 | 31837.56 | 0
| Total Project Cost | 259551.33 | 259551.33 | 259551.33 | 0 | 0
Project closed 06/12/2024
29C20 Funds Rec'v'd 10/09/2024
Note on C8: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #9291.00 Funds Rec'd
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
Funds Rec'd
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Executive Council Approval 10.7.24 - DOC Clarinda | IET 6542376202510082401 | 2024-10-07 | 259551.33 | 259551.33
| Total Requested | 0 | Total Transferred |  |  | 259551.33 | 259551.33

## #9291.00 Samuels Group
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522158901 | 2022-06-07 | PO Procore | 11982.2 | 11982.2 |  |  | 11982.2
PRC 3352215PA8901 | 2022-07-06 | Inv. 7415.01929100 |  | 11982.2 | 719.83 | 719.83 | 11262.37 | FY22
PO 33523158901 | 2022-08-10 | Rolled to FY23 | 0 | 11982.2 |  | 719.83 | 11262.37
PRC 3352315PB8901 | 2022-08-12 | Inv. 7415.02929100 |  | 11982.2 | 1807.67 | 2527.5 | 9454.7
PRC 3352315PC8901 | 2022-09-11 | Inv. 7415.03929100 |  | 11982.2 | 1721.09 | 4248.59 | 7733.61
PRC 3352315PD8901 | 2022-10-04 | Inv. 7415.04929100 |  | 11982.2 | 997.44 | 5246.03 | 6736.17
PRC 3352315PE8901 | 2022-11-09 | Inv. 7415.05929100 |  | 11982.2 | 1098.69 | 6344.72 | 5637.48
PRC 3352315PF8901 | 2022-12-12 | Inv. 7415.06929100 |  | 11982.2 | 1033.74 | 7378.46 | 4603.74
PRC 3352315PG8901 | 2023-01-11 | Inv. 7415.07929100 FINAL | -311.8 | 11670.4 | 4291.94 | 11670.4 | 0 | FINAL
|  |  |  | 11670.4 |  | 11670.4 | 0
|  |  |  | 11670.4 |  | 11670.4 | 0
|  |  |  | 11670.4 |  | 11670.4 | 0
|  |  |  | 11670.4 |  | 11670.4 | 0
|  | Totals: | 11670.4 |  | 11670.4 |  | 0
|  | CM Services | 11576.8 |  | 11576.8 |  | 0
|  | Reimbursables | 93.6 |  | 93.6 |  | 0
|  | Total: | 11670.4 |  | 11670.4 |  | 0

## #9291.00 PM TIME
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907R
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22851.12 | 22851.12 |  |  | 22851.12
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 22851.12 | 200 | 200 | 22651.12
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 22851.12 | 125 | 325 | 22526.12
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 22851.12 | 500 | 825 | 22026.12
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 22851.12 | -500 | 325 | 22526.12
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 22851.12 | 550 | 875 | 21976.12
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 22851.12 | 907.5 | 1782.5 | 21068.62
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 22851.12 | 935 | 2717.5 | 20133.62
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 22851.12 | 385 | 3102.5 | 19748.62
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 22851.12 | 275 | 3377.5 | 19473.62
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 536.66 | 23387.78 | 536.66 | 3914.16 | 19473.62
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 690.98 | 24078.76 | 690.98 | 4605.14 | 19473.62
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 597.68 | 24676.44 | 597.68 | 5202.82 | 19473.62
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 242.43 | 24918.87 | 242.43 | 5445.25 | 19473.62
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 188.78 | 25107.65 | 188.78 | 5634.03 | 19473.62
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 25107.65 | 704.14 | 6338.17 | 18769.48
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 25107.65 | 70.19 | 6408.36 | 18699.29
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 25107.65 | 615.27 | 7023.63 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 153.42 | 25261.07 | 153.42 | 7177.05 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 226.16 | 25487.23 | 226.16 | 7403.21 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 14.39 | 25501.62 | 14.39 | 7417.6 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 92.66 | 25594.28 | 92.66 | 7510.26 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 49.38 | 25643.66 | 49.38 | 7559.64 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 105.34 | 25749 | 105.34 | 7664.98 | 18084.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 25749 | 158.24 | 7823.22 | 17925.78
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 25749 | 959.58 | 8782.8 | 16966.2
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 25749 | 176.29 | 8959.09 | 16789.91
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 25749 | 775.41 | 9734.5 | 16014.5
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 25749 | 125.06 | 9859.56 | 15889.44
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 25749 | 737 | 10596.56 | 15152.44
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 25749 | 111.08 | 10707.64 | 15041.36
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 25749 | 778.8 | 11486.44 | 14262.56
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 25749 | 69.02 | 11555.46 | 14193.54
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 25749 | 564.9 | 12120.36 | 13628.64
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 25749 | 129.54 | 12249.9 | 13499.1
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 25749 | 825 | 13074.9 | 12674.1
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 25749 | 110.38 | 13185.28 | 12563.72
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 25749 | 616.5 | 13801.78 | 11947.22
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 25749 | 121.75 | 13923.53 | 11825.47
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 25749 | 843.9 | 14767.43 | 10981.57
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 25749 | 58.03 | 14825.46 | 10923.54
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 25749 | 466.6 | 15292.06 | 10456.94
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 25749 | 216.96 | 15509.02 | 10239.98
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 25749 | 1640.8 | 17149.82 | 8599.18
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 25749 | 264.21 | 17414.03 | 8334.97
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 25749 | 1940.5 | 19354.53 | 6394.47
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 25749 | 174.01 | 19528.54 | 6220.46
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 25749 | 1535.1 | 21063.64 | 4685.36
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 25749 | 259.05 | 21322.69 | 4426.31
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 25749 | 1307.1 | 22629.79 | 3119.21
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 25749 | 111.68 | 22741.47 | 3007.53
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 25749 | 844.3 | 23585.77 | 2163.23
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 25749 | 97.05 | 23682.82 | 2066.18
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 25749 | 859.1 | 24541.92 | 1207.08
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 25749 | 129.38 | 24671.3 | 1077.7
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 25749 | 1077.7 | 25749 | 0
[5 empty] | 25749 |  | 25749 | 0
[5 empty] | 25749 |  | 25749 | 0
[5 empty] | 25749 |  | 25749 | 0
|  |  | Totals: | 25749 |  | 25749 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time Budgets $Selma Herman, Josh Tue, Jun 7, 4:07 PM (17 hours ago) to me Please set the PM Time budget for 9291.00 AND 9292.00 to $5,000 each. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Herman, Josh Sun, Feb 19, 3:22 PM (18 hours ago) to me, Bradley Please make DAS PM Time budget a total of $15,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Tonyan, Brad 2:05 PM (38 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Tonyan, Brad 9:16 AM (20 minutes ago) to me Finance, Yes, please increase the following projects by the exact amount needed to cover the PM time. 9172.00 in DA21 Amount to post 602.80 9242.00 in DA22 Amount to post 1032.90 9291.00 in MM22 Amount to post 1420.10 Re: PM Time Inbox Tonyan, Brad 2:58 PM (6 minutes ago) to DAS, me, Brad John and Finance, 9172.00 DA21 Amount to post 625.90 Brad update - Please raise total PM time budget to $60K 9242.00 DA22 Amount to post 751.30 Brad update - Please raise total PM time budget to $38K 9282.00 DA22 Amount to post 284.68 Brad update - Please increase only to cover this amount and stop charging edas time to DA22 and instead charge time to MM24 9282.00 org. 9291.00 MM22 Amount to post 1211.10 Brad update - Please raise total PM time budget to $25K 9324.00 MM23 Amount to post 459.80 Brad update - Please raise total PM time budget to $18K

## #9291.00 Misc
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523349801 | 2022-12-15 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV026183 | 167.62 | 167.62
167.62
167.62
167.62
167.62
167.62
167.62
167.62
167.62
167.62
167.62
167.62
|  |  |  | Totals: |  | 167.62

## #9291.00 ATC Group Services
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
ATC Group Services |  |  | Vendor: 00002134218
Acct. Codes-0017-335-MM22-9255 |  |  | MA005 2026B
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523231801 | 2022-08-19 | DO Procore | 1930 | 1930 |  |  | 1930
PRC 3352323PA1801 | 2022-10-13 | Inv. 2458353-Final | -728.75 | 1201.25 | 1201.25 | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  |  |  | 1201.25 |  | 1201.25 | 0
|  | Totals: | 1201.25 |  | 1201.25 |  | 0
|  | Contract Line 7: Field Technician Time (14 hrs x $75/hr) | 731.25 |  | 731.25 |  | 0
|  | Contract Line 8: Hygienist (3 hours x $95/hr) | 285 |  | 285 |  | 0
|  | Contract Line 5: Administration time (1 hr x $45/hr) | 45 |  | 45 |  | 0
|  | Contract Line 2: Asbestos Per Sample Fee (40 samples x $10/sample) | 140 |  | 140 |  | 0
|  | Contract Line 3: Lead Per Sample Fee (10 Samples x $15/sample) | 0 |  |  |  | 0
|  | Total: | 1201.25 |  | 1201.25 |  | 0

## #9291.00 IMEG Corporation
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
IMEG Corporation |  |  | Vendor: 00003106665
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: 929100-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523231804 | 2022-08-19 | PO Procore | 21420 | 21420 |  |  | 21420
PRC 3352323PA1804 | 2022-12-05 | Inv. 22006073.00-1 |  | 21420 | 9827.5 | 9827.5 | 11592.5
PRC 3352323PB1804 | 2023-01-06 | Inv. 22006073.00-2 |  | 21420 | 2059.5 | 11887 | 9533
PRC 3352323PC1804 | 2023-03-02 | Inv. 22006073.00-3 |  | 21420 | 1165.2 | 13052.2 | 8367.8
PRC 3352323PD1804 | 2023-04-24 | Inv. 22006073.00-4 |  | 21420 | 388.4 | 13440.6 | 7979.4
PRC 3352323PE1804 | 2023-06-30 | Inv. 22006073.00-5 |  | 21420 | 1553.6 | 14994.2 | 6425.8 | FY23
PO 33524231804 | 2023-08-03 | Roll to FY24 | 0 | 21420 |  | 14994.2 | 6425.8
PRC 3352423PF1804 | 2024-03-08 | Inv. 22006073.00-6 Revised |  | 21420 | 1673.1 | 16667.3 | 4752.7
PRC 3352423PG1804 | 2024-04-25 | Inv. 22006073.00-7 |  | 21420 | 1792.6 | 18459.9 | 2960.1
PRC 3352423PH1804 | 2024-05-14 | Inv. 22006073.00-8 |  | 21420 | 776.8 | 19236.7 | 2183.3
PRC 3352423PI1804 | 2024-05-15 | Inv. 22006073.00-9 FINAL | -1287 | 20133 | 896.3 | 20133 | 0
|  |  |  | 20133 |  | 20133 | 0
|  |  |  | 20133 |  | 20133 | 0
|  | Totals: | 20133 |  | 20133 |  | 0 | FINAL
|  | Design Development Documents | 4855 |  | 4855 |  | 0
|  | Construction Documents | 4855 |  | 4855 |  | 0
|  | Bidding Assistance | 1942 |  | 1942 |  | 0
|  | Construction Administration | 7768 |  | 7768 |  | 0
|  | Reimbursable Costs | 713 |  | 713 |  | 0
|  | Total: | 20133 |  | 20133 |  | 0

## #9291.00 Capital City Boiler
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
Capital City Boiler |  |  | Vendor: 00002112380
Acct. Codes-0017-335-MM22-9255 |  |  | RFB929100-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523355900 | 2022-12-20 | PO Procore | 163220 | 163220 |  |  | 163220
PRC 3352335PA5900 | 2023-06-27 | Inv. 9291.00-01 |  | 163220 | 4750 | 4750 | 158470 | 250 | FY23
PO 33524355900 | 2023-08-03 | Roll to FY24 | 0 | 163220 |  | 4750 | 158470
PO 33524355900 | 2023-10-04 | CO #1(No cost CO) | 0 | 163220 |  | 4750 | 158470
PRC 3352435PB5900 | 2023-11-17 | Inv. 9291.00-02 |  | 163220 | 25650 | 30400 | 132820 | 1600
PO 33524355900 | 2023-12-15 | CO #2 | 3887.4 | 167107.4 |  | 30400 | 136707.4
PRC 3352435PC5900 | 2024-01-05 | Inv. 9291.00-03 |  | 167107.4 | 70062.5 | 100462.5 | 66644.9 | 5287.5
PO 33524355900 | 2024-02-01 | CO #3(No Cost CO) | 0 | 167107.4 |  | 100462.5 | 66644.9
PO 33524355900 | 2024-02-16 | CO #4 | 1685.1 | 168792.5 |  | 100462.5 | 68330
PRC 3352435PD5900 | 2024-02-29 | Inv. 9291.00-04 |  | 168792.5 | 58339.78 | 158802.28 | 9990.22 | 8358.02
PRC 3352435PE5900 | 2024-05-02 | Inv. 9291.00-05 |  | 168792.5 | 1550.59 | 160352.87 | 8439.63 | 8439.63
PRC 3352435PF5900 | 2024-05-07 | Inv. 9291.00-06-Retainage |  | 168792.5 | 8439.63 | 168792.5 | 0
|  |  |  | 168792.5 |  | 168792.5 | 0
|  | Totals: | 168792.5 |  | 168792.5 |  | 0

## #9291.00 Samuels Group #117CA
DOC CCF Condensate Tank Replacement(29C20)
Project # 9291.00
Program code 929100 |  |  | Major Program 4B01
Samuels Group #117CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523018805 | 2023-01-18 | PO Procore | 28772.44 | 28772.44 |  |  | 28772.44
PRC 3352301PA8805 | 2023-02-08 | Inv. 7415.51929100 |  | 28772.44 | 974.21 | 974.21 | 27798.23
PRC 3352301PB8805 | 2023-03-06 | Inv. 7415.52929100 |  | 28772.44 | 405.92 | 1380.13 | 27392.31
PRC 3352301PC8805 | 2023-04-04 | Inv. 7415.53929100 |  | 28772.44 | 1217.75 | 2597.88 | 26174.56
PRC 3352301PD8805 | 2023-05-08 | Inv. 7415.54929100 |  | 28772.44 | 595.35 | 3193.23 | 25579.21
PRC 3352301PE8805 | 2023-07-10 | Inv. 7415.55929100 |  | 28772.44 | 1093.27 | 4286.5 | 24485.94 | FY23
PO 33524018805 | 2023-08-03 | Roll to FY24 | 0 | 28772.44 |  | 4286.5 | 24485.94
PRC 3352401PF8805 | 2023-08-04 | Inv. 7415.56929100 |  | 28772.44 | 687.35 | 4973.85 | 23798.59
PRC 3352401PG8805 | 2023-09-14 | Inv. 7415.57929100 |  | 28772.44 | 1413.5 | 6387.35 | 22385.09
PRC 3352401PH8805 | 2023-10-05 | Inv. 7415.58929100 |  | 28772.44 | 503.34 | 6890.69 | 21881.75
PRC 3352401PI8805 | 2023-11-07 | Inv. 7415.59929100 |  | 28772.44 | 725.25 | 7615.94 | 21156.5
PRC 3352401PJ8805 | 2023-12-11 | Inv. 7415.60929100 |  | 28772.44 | 4061.45 | 11677.39 | 17095.05
PRC 3352401PK8805 | 2024-01-08 | Inv. 7415.61929200 |  | 28772.44 | 4531.84 | 16209.23 | 12563.21
PRC 3352401PL8805 | 2024-02-05 | Inv. 7415.62929100 |  | 28772.44 | 7464.27 | 23673.5 | 5098.94
PO 33524018805 | 2024-02-14 | CO #001 | 3065.12 | 31837.56 |  | 23673.5 | 8164.06
PRC 3352401PM8805 | 2024-03-05 | Inv. 7415.63929100 |  | 31837.56 | 4484.06 | 28157.56 | 3680
PRC 3352401PN8805 | 2024-04-08 | Inv. 7415.64929100 |  | 31837.56 | 1174.46 | 29332.02 | 2505.54
PRC 3352401PO8805 | 2024-05-06 | Inv. 7415.65929100-FINAL |  | 31837.56 | 2505.54 | 31837.56 | 0
|  |  |  | 31837.56 |  | 31837.56 | 0
|  | Totals: | 31837.56 |  | 31837.56 |  | 0 | FINAL
|  | CM Services | 27212.44 |  | 27212.44 |  | 0
|  | Reimbursables | 1560 |  | 1560 |  | 0
|  | CO #001 | 3065.12 |  | 3065.12 |  | 0
|  | Total: | 31837.56 |  | 31837.56 |  | 0

## RECAP #9292.00
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
| Program code 929200 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
| Funds Recv'd | 359463.21
C | Samuels Group |  | 11343.74 | 11343.74 | 0
C | PM TIME |  | 10676.51 | 10676.51 | 0
C | Misc. |  | 156.58 | 156.58 | 0
C | Shive Hattery |  | 43160 | 43160 | 0
C | For Sure Roofing |  | 232688 | 232688 | 0
C | MTS Contracting |  | 28762 | 28762 | 0
C | Samuels Group #118CA |  | 32676.38 | 32676.38 | 0
| Total Project Cost | 359463.21 | 359463.21 | 359463.21 | 0 | 0
Closed 08/21/2023
Note on C8: Durakovic, Selma [DAS]: MM22 Project Increases $Selma Herman, Josh Thu, Aug 11, 4:41 PM (4 days ago) to me, Jennifer, Scott Finance Please make the following changes to over all project budgets. 9245.00 in MM22 ADD $155,000 (Should total $255,000) 9291.00 in MM22 ADD $75,000 (Should total $200,000) 9292.00 in MM22 ADD $300,000 (Should total $350,000) Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #9292.00 Funds Rec'd
DHS WRC Birches Storm Repairs 29C20
Project # 9292.00
Program code 929200 |  |  | Major Program 3D02
Funds Received
Acct. Codes-0017-335-MM22
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | 29C20 Funds Recv'd | IET 654202308172302 | 2023-08-18 | 359463.21 | 359463.21
| Total Requested | 0 | Total Transferred |  |  | 359463.21 | 359463.21

## #9292.00 Samuels Group
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522158900 | 2022-06-07 | PO Procore | 12097.06 | 12097.06 |  |  | 12097.06
PRC 3352215PA8900 | 2022-06-30 | Inv. 7414.01929200 |  | 12097.06 | 1033.74 | 1033.74 | 11063.32 | FY22
PO 33523158900 | 2022-08-10 | Rolled to FY23 | 0 | 12097.06 |  | 1033.74 | 11063.32
PRC 3352315PB8900 | 2022-08-12 | Inv. 7414.02929200 |  | 12097.06 | 1066.21 | 2099.95 | 9997.11
PRC 3352315PC8900 | 2022-09-11 | Inv. 7414.03929200 |  | 12097.06 | 3598.87 | 5698.82 | 6398.24
PRC 3352315PD8900 | 2022-09-27 | Inv. 7414.04929200 FINAL | -753.32 | 11343.74 | 5644.92 | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  |  |  | 11343.74 |  | 11343.74 | 0
|  | Totals: | 11343.74 |  | 11343.74 |  | 0
|  | CM Services | 11333.16 |  | 11333.16 |  | 0
|  | Reimbursables | 10.58 |  | 10.58 |  | 0
|  | Total: | 11343.74 |  | 11343.74 |  | 0

## #9292.00 PM TIME
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 907S
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7672.4 | 7672.4 |  |  | 7672.4
IET DAS202211115300001 | 2022-06-07 |  | PM-May 2-May 31, 2022 |  | 7672.4 | 275 | 275 | 7397.4
IET DAS202212115300001 | 2022-07-08 |  | PM June1-June30, 2022 |  | 7672.4 | 425 | 700 | 6972.4
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 7672.4 | 400 | 1100 | 6572.4
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 7672.4 | -400 | 700 | 6972.4
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 7672.4 | 440 | 1140 | 6532.4
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 7672.4 | 1402.5 | 2542.5 | 5129.9
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 7672.4 | 522.5 | 3065 | 4607.4
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 7672.4 | 192.5 | 3257.5 | 4414.9
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 7672.4 | 275 | 3532.5 | 4139.9
IET DAS202305115300001 | 2022-12-07 | 9500 | PM-July 1-July 29, 2022 9997.23 Disbursement | 385.08 | 8057.48 | 385.08 | 3917.58 | 4139.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 1067.88 | 9125.36 | 1067.88 | 4985.46 | 4139.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 334 | 9459.36 | 334 | 5319.46 | 4139.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 121.22 | 9580.58 | 121.22 | 5440.68 | 4139.9
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 188.78 | 9769.36 | 188.78 | 5629.46 | 4139.9
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 9769.36 | 1314.39 | 6943.85 | 2825.51
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 9769.36 | 86.38 | 7030.23 | 2739.13
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 9769.36 | 757.26 | 7787.49 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 122.73 | 9892.09 | 122.73 | 7910.22 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 349.51 | 10241.6 | 349.51 | 8259.73 | 1981.87
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 136.77 | 10378.37 | 136.77 | 8396.5 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 52.12 | 10430.49 | 52.12 | 8448.62 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 49.38 | 10479.87 | 49.38 | 8498 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 196.64 | 10676.51 | 196.64 | 8694.64 | 1981.87
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 10676.51 | 166.04 | 8860.68 | 1815.83
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 10676.51 | 1006.89 | 9867.57 | 808.94
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 10676.51 | 149.84 | 10017.41 | 659.1
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 10676.51 | 659.1 | 10676.51 | 0
|  |  | Totals: | 10676.51 |  | 10676.51 |  | 0
Note on E9: Durakovic, Selma [DAS]: PM Time Budgets $Selma Herman, Josh Tue, Jun 7, 4:07 PM (17 hours ago) to me Please set the PM Time budget for 9291.00 AND 9292.00 to $5,000 each. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9292.00 MM22 PM Time $Joni Herman, Josh 12:44 PM (1 hour ago) to me Please increase from $5,000 to $7,700 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov

## #9292.00 Misc
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523259902 | 2022-09-16 | 9500 | CNST | Beeline & Blue V# (00002108204) | Inv. INV023723 | 156.58 | 156.58
156.58
156.58
156.58
156.58
156.58
156.58
156.58
156.58
156.58
156.58
156.58
|  |  |  | Totals: |  | 156.58

## #9292.00 Shive Hattery
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  | Major Program 4E02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP/B#: Emergency
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522179800 | 2022-06-28 | PO Procore | 32300 | 32300 |  |  | 32300
PRC 3352217PA9800 | 2022-07-08 | Inv. 21422038001 |  | 32300 | 12430 | 12430 | 19870 | FY22
PO 33523179800 | 2022-08-10 | Rolled to FY23 | 0 | 32300 |  | 12430 | 19870
PRC 3352317PB9800 | 2022-08-18 | Inv. 2142203800-2 |  | 32300 | 15695 | 28125 | 4175
PO 33523179800 | 2022-09-21 | CO #1 | 10860 | 43160 |  | 28125 | 15035
PRC 3352317PC9800 | 2022-09-22 | Inv. 2142203800-3 |  | 43160 | 4175 | 32300 | 10860
PRC 3352317PD9800 | 2022-10-25 | Inv. 2142203800-4 |  | 43160 | 1629 | 33929 | 9231
PRC 3352317PE9800 | 2022-12-20 | Inv. 2142203800-5 |  | 43160 | 5973 | 39902 | 3258
PRC 3352317PF9800 | 2023-02-10 | Inv. 2142203800-6 |  | 43160 | 3040.8 | 42942.8 | 217.2
PRC 3352317PG9800 | 2023-03-29 | Inv. 2142203800-7FINAL |  | 43160 | 217.2 | 43160 | 0
|  |  |  | 43160 |  | 43160 | 0
|  |  |  | 43160 |  | 43160 | 0
|  |  |  | 43160 |  | 43160 | 0
|  | Totals: | 43160 |  | 43160 |  | 0
|  | Initial Site Observation & Recommendations | 4400 |  | 4400 |  | 0
|  | Aerial Drone Imagery | 3300 |  | 3300 |  | 0
|  | Design Phase Services | 21500 |  | 21500 |  | 0
|  | Quoting/Bidding Phase Services | 3100 |  | 3100 |  | 0
|  | CO #1 | 10860 |  | 10860 |  | 0
|  | Total: | 43160 |  | 43160 |  | 0

## #9292.00 For Sure Roofing
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  | Major Program 4E02
For Sure Roofing |  |  | Vendor: 00003081739
Acct. Codes-0017-335-MM22-9255 |  |  | RFB#929200-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523263900 | 2022-09-20 | PO Procore | 245288 | 245288 |  |  | 245288
PRC 3352326PA3900 | 2022-12-15 | Inv. 9292.00-01 |  | 245288 | 188364.25 | 188364.25 | 56923.75 | 9913.908
PO 33523263900 | 2023-01-25 | CO #1 | -12600 | 232688 |  | 188364.25 | 44323.75
PRC 3352326PB3900 | 2023-01-25 | Inv. 9292.00-02 |  | 232688 | 30359.11 | 218723.36 | 13964.64 | 11511.758
PRC 3352326PC3900 | 2023-03-22 | Inv. 9292.00-03 |  | 232688 | 2330.24 | 221053.6 | 11634.4 | 11634.398
PRC 3352326PD3900 | 2023-03-28 | Inv. 9292.00-04-Retainage |  | 232688 | 11634.4 | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  |  |  | 232688 |  | 232688 | 0
|  | Totals: | 232688 |  | 232688 |  | 0

## #9292.00 MTS Contracting
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  | Major Program 4E02
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM22-9255 |  |  | MA005 20243A
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523263901 | 2022-09-20 | PO Procore | 28762 | 28762 |  |  | 28762
PRC 3352326PA3901 | 2023-02-07 | Inv. 22-4507FINAL |  | 28762 | 28762 | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  |  |  | 28762 |  | 28762 | 0
|  | Totals: | 28762 |  | 28762 |  | 0 | FINAL
|  | Mason(248mh x 81.50) | 20212 |  | 20212 |  | 0
|  | Materials | 5175 |  | 5175 |  | 0
|  | Equipment | 3375 |  | 3375 |  | 0
|  | Total: | 28762 |  | 28762 |  | 0

## #9292.00 Samuels Group #118CA
DOC CCF CTC Roof Storm Damage 2022(29C20)
Project # 9292.00
Program code 929200 |  |  | Major Program 4E02
Samuels Group #118CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523264800 | 2022-09-21 | PO Procore | 33347.03 | 33347.03 |  |  | 33347.03
PRC 3352326PA4800 | 2022-11-09 | Inv. 7414.51929200 |  | 33347.03 | 4410.06 | 4410.06 | 28936.97
PRC 3352326PB4800 | 2022-12-12 | Inv. 7414.52929200 |  | 33347.03 | 7797.04 | 12207.1 | 21139.93
PRC 3352326PC4800 | 2023-01-11 | Inv. 7414.53929200 |  | 33347.03 | 3994.02 | 16201.12 | 17145.91
PRC 3352326PD4800 | 2023-02-10 | Inv. 7414.54929200 |  | 33347.03 | 6285.82 | 22486.94 | 10860.09
PRC 3352326PE4800 | 2023-03-09 | Inv. 7414.55929200 |  | 33347.03 | 5234.53 | 27721.47 | 5625.56
PRC 3352326PF4800 | 2023-04-04 | Inv. 7414.56929200 Final | -670.65 | 32676.38 | 4954.91 | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  |  |  | 32676.38 |  | 32676.38 | -3.0695e-12
|  | Totals: | 32676.38 |  | 32676.38 |  | 0 | FINAL
|  | CM Services | 31079.31 |  | 31079.31 |  | 0
|  | Reimbursables | 1597.07 |  | 1597.07 |  | 0
|  | Total: | 32676.38 |  | 32676.38 |  | 0

## RECAP #9299.00
DAS ANK SHL Ductwork Replacement
Project # 9299.00
Program code 929900 |  |  | Major Program 4F03
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1280.52
VendorA |  | 0 | 0 | 0
PM TIME |  | 1280.52 | 1280.52 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 1280.52 | 1280.52 | 1280.52 | 0 | -1.0459e-11
Closed 05/08/2023

## #9299.00 Vendor A
DAS ANK SHL Ductwork Replacement
Project # 9299.00
Program code 929900 |  |  | Major Program 4F03
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9299.00 PM TIME
DAS ANK SHL Ductwork Replacement
Project # 9299.00
Program code 929900 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS 908N
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 1280.52 | 1280.52 |  |  | 1280.52
CDE 33523320902 | 2022-11-16 | 9500 | Moving PM Expense from MM21 9299.00 |  | 1280.52 | 687.5 | 687.5 | 593.02
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 1280.52 | 37.48 | 724.98 | 555.54
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 1280.52 | 227.26 | 952.24 | 328.28
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 1280.52 | 60.81 | 1013.05 | 267.47
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 1280.52 | 267.47 | 1280.52 | 0
|  |  | Totals: | 1280.52 |  | 1280.52 |  | 0
Note on E9: Huggins, Joni [DAS]: Please close MM22 Project 9299.00 $Joni Kleene, Jennifer May 5, 2023, 1:40 PM (3 days ago) to me, Scott All DAS costs have been posted and there were no other invoices, so please close MM22 Project 9299.00 and remove it from the billables sheet. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9299.00 Misc
DAS ANK SHL Ductwork Replacement
Project # 9299.00
Program code 929900 |  |  |  | Major Program 4F03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9302.00
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
| Program code 930200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 258205.98
C | Samuels Group #124PC |  | 10336.52 | 10336.52 | 0
C | PM TIME |  | 29354.42 | 29354.42 | 0
C | Misc. |  | 673.75 | 673.75 | 0
C | IMEG Corporation |  | 18850 | 18850 | 0
C | Daikin Applied |  | 91000 | 91000 | 0
C | Waldinger Corporation |  | 96351.89 | 96351.89 | 0
C | Samuels Group #142CA |  | 11639.4 | 11639.4 | 0
| Total Project Cost | 258205.98 | 258205.98 | 258205.98 | 0 | 0
Closed 07/10/24

## #9302.00 Samuels Group #124PC
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  | Major Program 4E01
Samuels Group #124PC |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523257805 | 2022-09-14 | PO Procore | 14668.1 | 14668.1 |  |  | 14668.1
PRC 3352325PA7805 | 2023-03-09 | Inv. 7437.01930200 |  | 14668.1 | 5696.97 | 5696.97 | 8971.13
PRC 3352325PB7805 | 2023-05-08 | Inv. 7437.02930200 |  | 14668.1 | 2370.54 | 8067.51 | 6600.59
PRC 3352325PC7805 | 2023-06-09 | Inv. 7437.03930200 |  | 14668.1 | 2269.01 | 10336.52 | 4331.58
PO 33523257805 | 2023-08-02 | Close PO per PM | -4331.58 | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  |  |  | 10336.52 |  | 10336.52 | 0
|  | Totals: | 10336.52 |  | 10336.52 |  | 0 | FINAL
|  | CM Services | 10261.52 |  | 10261.52 |  | 0
|  | Reimbursables | 75 |  | 75 |  | 0
|  | Total: | 10336.52 |  | 10336.52 |  | 0

## #9302.00 PM TIME
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E231
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 27697.38 | 27697.38 |  |  | 27697.38
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 27697.38 | 302.5 | 302.5 | 27394.88
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 27697.38 | 440 | 742.5 | 26954.88
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 27697.38 | 880 | 1622.5 | 26074.88
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 27697.38 | 467.5 | 2090 | 25607.38
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 230.33 | 27927.71 | 230.33 | 2320.33 | 25607.38
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 281.26 | 28208.97 | 281.26 | 2601.59 | 25607.38
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 554.11 | 28763.08 | 554.11 | 3155.7 | 25607.38
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 320.91 | 29083.99 | 320.91 | 3476.61 | 25607.38
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 29083.99 | 375.54 | 3852.15 | 25231.84
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 29083.99 | 91.77 | 3943.92 | 25140.07
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 29083.99 | 804.59 | 4748.51 | 24335.48
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 75.39 | 29159.38 | 75.39 | 4823.9 | 24335.48
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 14.39 | 29173.77 | 14.39 | 4838.29 | 24335.48
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 40.54 | 29214.31 | 40.54 | 4878.83 | 24335.48
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 83.93 | 29298.24 | 83.93 | 4962.76 | 24335.48
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 56.18 | 29354.42 | 56.18 | 5018.94 | 24335.48
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 29354.42 | 251.06 | 5270 | 24084.42
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 29354.42 | 1522.48 | 6792.48 | 22561.94
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 29354.42 | 212.83 | 7005.31 | 22349.11
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 29354.42 | 936.14 | 7941.45 | 21412.97
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 29354.42 | 46.76 | 7988.21 | 21366.21
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 29354.42 | 274.6 | 8262.81 | 21091.61
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 29354.42 | 161.66 | 8424.47 | 20929.95
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 29354.42 | 1135.2 | 9559.67 | 19794.75
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 29354.42 | 410.28 | 9969.95 | 19384.47
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 29354.42 | 3634.5 | 13604.45 | 15749.97
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 29354.42 | 70.41 | 13674.86 | 15679.56
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 29354.42 | 449.6 | 14124.46 | 15229.96
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 29354.42 | 103.86 | 14228.32 | 15126.1
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 29354.42 | 581.5 | 14809.82 | 14544.6
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 29354.42 | 44.4 | 14854.22 | 14500.2
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 29354.42 | 356.2 | 15210.42 | 14144
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 29354.42 | 255.66 | 15466.08 | 13888.34
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 29354.42 | 1933.4 | 17399.48 | 11954.94
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 29354.42 | 438 | 17837.48 | 11516.94
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 29354.42 | 3213 | 21050.48 | 8303.94
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 29354.42 | 190.11 | 21240.59 | 8113.83
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 29354.42 | 1674.3 | 22914.89 | 6439.53
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 29354.42 | 295.87 | 23210.76 | 6143.66
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 29354.42 | 1493.3 | 24704.06 | 4650.36
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 29354.42 | 176.91 | 24880.97 | 4473.45
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 29354.42 | 1343.7 | 26224.67 | 3129.75
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 29354.42 | 176.83 | 26401.5 | 2952.92
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 29354.42 | 1571.2 | 27972.7 | 1381.72
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 29354.42 | 81.8 | 28054.5 | 1299.92
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 29354.42 | 684.9 | 28739.4 | 615.02
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 29354.42 | 60.82 | 28800.22 | 554.2
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 29354.42 | 554.2 | 29354.42 | 0
[5 empty] | 29354.42 |  | 29354.42 | 0
29354.42
|  |  | Totals: | 29354.42 |  | 29354.42 |  | 0
Note on E9: Huggins, Joni [DAS]: 9203.00 PM Time in MM22 $Joni Herman, Josh Mon, Aug 29, 5:19 PM (16 hours ago) to me Please set to $8,000. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time $John Adams, Brandon 10:16 AM (11 minutes ago) to me Finance, Please increase: 9224.00 MM23 by $15,000 9287.00 MM21 by $5,000 9302.00 MM22 by $8,000 Thanks you, Re: PM TIme $John Adams, Brandon 1:37 PM (16 minutes ago) to me Please increase, MM22 9302.00 - $6,000 DA24 9360.00 - $4,000 Regards, Brandon Adams Adams, Brandon 2:25 PM (16 minutes ago) to me John, Please increase 9302.00 - MM22 PM Time by $5000.00. Regards Re: PM Time Postings $Joni Adams, Brandon 7:27 AM (24 minutes ago) to me Finance, DA24 9414.00 Needs a PM Time Budget set - currently (2939.13) Please set PM Time budget at $10,000.00 MM22 9302.00 (82.36) Increase PM time by $1500 MM23 9317.00 (865.96) Increase PM time by $5,000 MM23 9370.00 (1,722.26) Increase PM time by $5000 Regards, Brandon Adams

## #9302.00 Misc
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523103800 | 2023-04-13 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2494844 | 673.75 | 673.75
673.75
673.75
673.75
673.75
673.75
673.75
673.75
673.75
673.75
673.75
673.75
|  |  |  | Totals: |  | 673.75

## #9302.00 IMEG Corporation
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  | Major Program 4E01
IMEG Corporation |  |  | Vendor: 00003106665
Acct. Codes-0017-335-MM22-9260 |  |  | RFP930200-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523307901 | 2022-10-31 | PO Procore | 18850 | 18850 |  |  | 18850
PRC 3352330PA7901 | 2023-01-04 | Inv. 22007802.00-1 |  | 18850 | 2828 | 2828 | 16022
PRC 3352330PB7901 | 2023-01-27 | Inv. 22007802.00-2 |  | 18850 | 942.5 | 3770.5 | 15079.5
PRC 3352330PC7901 | 2023-03-03 | Inv. 22007802.00-3 |  | 18850 | 6597.5 | 10368 | 8482
PRC 3352330PD7901 | 2023-03-29 | Inv. 22007802.00-4 |  | 18850 | 3016 | 13384 | 5466
PRC 3352330PE7901 | 2023-05-04 | Inv. 22007802.00-5 |  | 18850 | 754 | 14138 | 4712
PRC 3352330PF7901 | 2023-06-27 | Inv. 22007802.00-6 |  | 18850 | 942 | 15080 | 3770 | FY23
PO 33524307901 | 2023-08-04 | Roll to FY24 | 0 | 18850 |  | 15080 | 3770
PRC 3352430PG7901 | 2024-01-26 | Inv. 22007802.00-7 |  | 18850 | 1508 | 16588 | 2262
PRC 3352430PH7901 | 2024-03-04 | Inv. 22007802.00-8 |  | 18850 | 754 | 17342 | 1508
PRC 3352430PI7901 | 2024-05-30 | Inv. 22007802.00-9 |  | 18850 | 1131 | 18473 | 377
PRC 3352430PJ7901 | 2024-07-08 | Inv. 22007802.00-10 FINAL |  | 18850 | 377 | 18850 | 0
|  |  |  | 18850 |  | 18850 | 0
|  | Totals: | 18850 |  | 18850 |  | 0 | FINAL
|  | Schematic Design | 2828 |  | 2828 |  | 0
|  | Design Development | 3770 |  | 3770 |  | 0
|  | Construction Documents | 7540 |  | 7540 |  | 0
|  | Bidding Assistance | 942 |  | 942 |  | 0
|  | Construction Documents | 3770 |  | 3770 |  | 0
|  | Total: | 18850 |  | 18850 |  | 0

## #9302.00 Daikin Applied
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  | Major Program 4E01
Daikin Applied |  |  | Vendor: 00002103894
Acct. Codes-0017-335-MM22-9255 |  |  | MA 21194
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523010801 | 2023-01-10 | DO Procore | 91000 | 91000 |  |  | 91000 | FY23
DO 33524010801 | 2023-08-04 | Roll to FY24 | 0 | 91000 |  | 0 | 91000
PRC 3352401PA0801 | 2024-01-19 | Inv. 3425711 |  | 91000 | 91000 | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  |  |  | 91000 |  | 91000 | 0
|  | Totals: | 91000 |  | 91000 |  | 0

## #9302.00 Waldinger
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  | Major Program 4E01
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM22-9255 |  |  | RFQ930200-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523174800 | 2023-06-23 | PO Procore | 87811 | 87811 |  |  | 87811 |  | FY23
PO 33524174800 | 2023-08-04 | Roll to FY24 | 0 | 87811 |  | 0 | 87811
PRC 3352417PA4800 | 2024-02-02 | Inv. 73372S-001 |  | 87811 | 53217.5 | 53217.5 | 34593.5 | 2800.92
PRC 3352417PB4800 | 2024-02-13 | Inv. 73372S-002 |  | 87811 | 7113.79 | 60331.29 | 27479.71 | 3175.33
PO 33524174800 | 2024-05-22 | CO #1 | 8540.89 | 96351.89 |  | 60331.29 | 36020.6
PRC 3352417PC4800 | 2024-06-06 | Inv. 73372S-004 |  | 96351.89 | 17342.43 | 77673.72 | 18678.17 | 4088.08
PRC 3352417PD4800 | 2024-07-08 | Inv. 73372S-005 |  | 96351.89 | 13860.59 | 91534.31 | 4817.58 | 4817.58
PRC 3352417PE4800 | 2024-07-08 | Inv. 74393S-Retainage |  | 96351.89 | 4817.58 | 96351.89 | 0
|  |  |  | 96351.89 |  | 96351.89 | 0
|  |  |  | 96351.89 |  | 96351.89 | 0
|  |  |  | 96351.89 |  | 96351.89 | 0
|  |  |  | 96351.89 |  | 96351.89 | 0
|  |  |  | 96351.89 |  | 96351.89 | 0
|  | Totals: | 96351.89 |  | 96351.89 |  | 0

## #9302.00 Samuels Group #142CA
DOC ICIW Unit 9 Chiller Replacement
Project # 9302.00
Program code 930200 |  |  | Major Program 4E01
Samuels Group #142CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP/B#: Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523177800 | 2023-06-26 | PO Procore | 11839.84 | 11839.84 |  |  | 11839.84 | FY23
PO 33524177800 | 2023-08-04 | Roll to FY24 | 0 | 11839.84 |  | 0 | 11839.84
PRC 3352417PA7800 | 2023-12-14 | Inv. 7519.51930200 |  | 11839.84 | 2687.4 | 2687.4 | 9152.44
PRC 3352417PB7800 | 2024-02-09 | Inv. 7519.52930200 |  | 11839.84 | 4983.23 | 7670.63 | 4169.21
PRC 3352417PC7800 | 2024-03-07 | Inv. 7519.53930200 |  | 11839.84 | 2542.72 | 10213.35 | 1626.49
PRC 3352417PD7800 | 2024-04-09 | Inv. 7519.54930200 |  | 11839.84 | 736 | 10949.35 | 890.49
PRC 3352417PE7800 | 2024-07-08 | Inv. 7519.55930200 FINAL | -200.44 | 11639.4 | 690.05 | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  |  |  | 11639.4 |  | 11639.4 | 1.1937e-12
|  | Totals: | 11639.4 |  | 11639.4 |  | 0 | FINAL
|  | CM Services | 11589.4 |  | 11589.4 |  | 0
|  | Reimbursables | 50 |  | 50 |  | 0
|  | Total: | 11639.4 |  | 11639.4 |  | 0

## RECAP #9303.00
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
| Program code 930300 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 295591.3
C | Story Construction |  | 17512.5 | 17512.5 | 0
C | PM TIME |  | 13229.99 | 13229.99 | 0
C | Misc. |  | 1809.34 | 1809.34 | 0
C | Shive Hattery |  | 47794 | 47794 | 0
C | McGough Construction |  | 5074.46 | 5074.46 | 0
C | On Track Construction |  | 183950 | 183950 | 0
C | McGough Construction #101031.003CA |  | 22638.01 | 22638.01 | 0
C | Terracon Consultants |  | 3583 | 3583 | 0
| Total Project Cost | 295591.3 | 295591.3 | 295591.3 | 0 | 0
Closed 10/03/2024

## #9303.00 Story Construction
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523279901 | 2022-10-24 | PO Procore | 17732.72 | 17732.72 |  |  | 17732.72
PRC 3352327PA9901 | 2022-12-21 | Inv. 33525 |  | 17732.72 | 1545 | 1545 | 16187.72
PRC 3352327PB9901 | 2023-01-19 | Inv. 33592 |  | 17732.72 | 1074 | 2619 | 15113.72
PRC 3352327PC9901 | 2023-02-22 | Inv. 33639 |  | 17732.72 | 2685 | 5304 | 12428.72
PRC 3352327PD9901 | 2023-03-15 | Inv. 33693 |  | 17732.72 | 2619 | 7923 | 9809.72
PRC 3352327PE9901 | 2023-04-21 | Inv. 33737 |  | 17732.72 | 3138 | 11061 | 6671.72
PRC 3352327PF9901 | 2023-05-19 | Inv. 33794 |  | 17732.72 | 6388.5 | 17449.5 | 283.22
PRC 3352327PG9901 | 2023-06-21 | Inv. 33841-FINAL | -220.22 | 17512.5 | 63 | 17512.5 | 1.1653e-12
|  |  |  | 17512.5 |  | 17512.5 | 1.1653e-12
|  |  |  | 17512.5 |  | 17512.5 | 1.1653e-12
|  |  |  | 17512.5 |  | 17512.5 | 1.1653e-12
|  |  |  | 17512.5 |  | 17512.5 | 1.1653e-12
|  |  |  | 17512.5 |  | 17512.5 | 1.1653e-12
|  | Totals: | 17512.5 |  | 17512.5 |  | 0 | FINAL
|  | CM Services | 17431.5 |  | 17431.5 |  | 0
|  | Reimbursables | 81 |  | 81 |  | 0
|  | Total: | 17512.5 |  | 17512.5 |  | 0

## #9303.00 PM TIME
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E232
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12435.52 | 12435.52 |  |  | 12435.52
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12435.52 | 165 | 165 | 12270.52
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12435.52 | 247.5 | 412.5 | 12023.02
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30,2022 |  | 12435.52 | 220 | 632.5 | 11803.02
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 88.8 | 12524.32 | 88.8 | 721.3 | 11803.02
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 180.72 | 12705.04 | 180.72 | 902.02 | 11803.02
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 168.65 | 12873.69 | 168.65 | 1070.67 | 11803.02
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 12873.69 | 1197.67 | 2268.34 | 10605.35
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 12873.69 | 77.6 | 2345.94 | 10527.75
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 12873.69 | 680.28 | 3026.22 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 72.03 | 12945.72 | 72.03 | 3098.25 | 9847.47
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | -72.03 | 12873.69 | -72.03 | 3026.22 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 108.08 | 12981.77 | 108.08 | 3134.3 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 27.67 | 13009.44 | 27.67 | 3161.97 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 41.38 | 13050.82 | 41.38 | 3203.35 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 179.17 | 13229.99 | 179.17 | 3382.52 | 9847.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 13229.99 | 176.38 | 3558.9 | 9671.09
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 13229.99 | 1069.58 | 4628.48 | 8601.51
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 13229.99 | 287.87 | 4916.35 | 8313.64
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 13229.99 | 1266.2 | 6182.55 | 7047.44
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 13229.99 | 69.62 | 6252.17 | 6977.82
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 13229.99 | 406.7 | 6658.87 | 6571.12
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 13229.99 | 82.31 | 6741.18 | 6488.81
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 13229.99 | 573.1 | 7314.28 | 5915.71
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 13229.99 | 25.61 | 7339.89 | 5890.1
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 13229.99 | 191.1 | 7530.99 | 5699
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 13229.99 | 79.3 | 7610.29 | 5619.7
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 13229.99 | 505.8 | 8116.09 | 5113.9
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 13229.99 | 54.98 | 8171.07 | 5058.92
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 13229.99 | 305.5 | 8476.57 | 4753.42
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 13229.99 | 39.23 | 8515.8 | 4714.19
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 13229.99 | 272.4 | 8788.2 | 4441.79
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 13229.99 | 68.2 | 8856.4 | 4373.59
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 13229.99 | 550.2 | 9406.6 | 3823.39
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 13229.99 | 12.11 | 9418.71 | 3811.28
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 13229.99 | 92.8 | 9511.51 | 3718.48
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 13229.99 | 13.9 | 9525.41 | 3704.58
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 13229.99 | 100.3 | 9625.71 | 3604.28
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 13229.99 | 5 | 9630.71 | 3599.28
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 13229.99 | 44.2 | 9674.91 | 3555.08
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 13229.99 | 77.57 | 9752.48 | 3477.51
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 13229.99 | 393.1 | 10145.58 | 3084.41
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 13229.99 | 56.6 | 10202.18 | 3027.81
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 13229.99 | 426.8 | 10628.98 | 2601.01
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 13229.99 | 81.3 | 10710.28 | 2519.71
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 13229.99 | 720.3 | 11430.58 | 1799.41
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 13229.99 | 38.95 | 11469.53 | 1760.46
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 13229.99 | 326.7 | 11796.23 | 1433.76
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 13229.99 | 53.03 | 11849.26 | 1380.73
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 13229.99 | 486.5 | 12335.76 | 894.23
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 13229.99 | 57.73 | 12393.49 | 836.5
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 13229.99 | 635.2 | 13028.69 | 201.3
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 13229.99 | 33.1 | 13061.79 | 168.2
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 13229.99 | 168.2 | 13229.99 | 0
[5 empty] | 13229.99 |  | 13229.99 | 0
|  |  | Totals: | 13229.99 |  | 13229.99 |  | 0
Note on E9: Durakovic, Selma [DAS]: James Trower Projects & PM Time $Selma Trower, James Sep 2, 2022, 3:53 PM (5 days ago) to me Finance - Please see the below items: 9243.00 - DOC NCCF Grease Interceptor Evaluation: Please close this project (It was an evaluation only). 9286.00 - DPS Fleet & Supply Level 2 Floor Framing: It appears the DA22 funding was returned to DAS Finance. This project can be closed and it appears $212.65 will be returned to DPS. 9303.00 - DOC NCCF Kitchen Grease Pit Replacement: Please set up $6,000 in PM Time (MM22). Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9303.00 - DOC NCCF Kitchen Grease Pit Replacement Inbox Trower, James 12:24 PM (1 minute ago) to me Finance - Please add $6,000in PM Time to project 9303.00 (MM22). Thanks, Trower, James 9:42 AM (29 minutes ago) to me We are over budget on PM time for 9303.00 in MM22: Increase PM Time by $4,000

## #9303.00 Misc
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523143802 | 2023-05-23 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 420783-0 | 82.03 | 82.03
PRC 33524292805 | 2023-10-19 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV034130 | 102.31 | 184.34
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 275 | 459.34
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -275 | 184.34
GAX 33524220907 | 2024-08-07 | 9500 | CNST | Ground Penetrating Radar Systems V#(00003035582) | Inv. 772263 | 1625 | 1809.34
1809.34
1809.34
1809.34
1809.34
1809.34
1809.34
1809.34
|  |  |  | Totals: |  | 1809.34

## #9303.00 Shive Hattery
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 930300-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523355901 | 2022-12-20 | PO Procore | 43744 | 43744 |  |  | 43744
PRC 3352335PA5901 | 2023-01-23 | Inv. 4216561-1 |  | 43744 | 5353.92 | 5353.92 | 38390.08
PRC 3352335PB5901 | 2023-02-28 | Inv. 4216561-2 |  | 43744 | 11600.16 | 16954.08 | 26789.92
PRC 3352335PC5901 | 2023-04-05 | Inv. 4216561-3 |  | 43744 | 11302.72 | 28256.8 | 15487.2
PRC 3352335PD5901 | 2023-05-12 | Inv. 4216561-4 |  | 43744 | 4087.2 | 32344 | 11400 | FY23
PO 33524355901 | 2023-08-11 | Rolled to FY24 | 0 | 43744 |  | 32344 | 11400
PO 33524355901 | 2023-10-02 | CO #1 | 4050 | 47794 |  | 32344 | 15450
PRC 3352435PE5901 | 2023-12-05 | Inv. 4216561-5 |  | 47794 | 3740 | 36084 | 11710
PRC 3352435PF5901 | 2024-03-07 | Inv. 4216561-6 |  | 47794 | 912 | 36996 | 10798
PRC 3352435PG5901 | 2024-03-20 | Inv. 4216561-7 |  | 47794 | 903.5 | 37899.5 | 9894.5
PRC 3352435PH5901 | 2024-06-05 | Inv. 4216561-8R |  | 47794 | 9210.5 | 47110 | 684
PRC 3352435PI5901 | 2024-07-12 | Inv. 4216561-9 |  | 47794 | 684 | 47794 | 3.638e-12
|  |  |  | 47794 |  | 47794 | 3.638e-12
|  | Totals: | 47794 |  | 47794 |  | 0 | FINAL
|  | Construction Documents | 29744 |  | 29744 |  | 0
|  | Bidding Assistance | 2600 |  | 2600 |  | 0
|  | Construction Phase | 11400 |  | 11400 |  | 0
|  | CO #1 | 4050 |  | 4050 |  | 0
|  | Total: | 47794 |  | 47794 |  | 0

## #9303.00 McGough Construction
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524208806 | 2023-07-27 | PO Procore | 5164.31 | 5164.31 |  |  | 5164.31
PRC 3352420PA8806 | 2023-09-14 | Inv. 101031.003PC-001 |  | 5164.31 | 1028.8 | 1028.8 | 4135.51
PRC 3352420PB8806 | 2023-10-11 | Inv. 101031.003PC-002 |  | 5164.31 | 1849.84 | 2878.64 | 2285.67
PRC 3352420PC8806 | 2023-11-13 | Inv. 101031.003PC-003 Final | -89.85 | 5074.46 | 2195.82 | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  |  |  | 5074.46 |  | 5074.46 | 0
|  | Totals: | 5074.46 |  | 5074.46 |  | 0 | FINAL
|  | CM Services | 4900.46 |  | 4900.46 |  | 0
|  | Reimbursables | 174 |  | 174 |  | 0
|  | Total: | 5074.46 |  | 5074.46 |  | 0

## #9303.00 On Track Construction
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
On Track Construction |  |  | Vendor: 00003167130
Acct. Codes-0017-335-MM22-9255 |  |  | RFB 930300-02
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524303800 | 2023-10-30 | PO Procore | 183950 | 183950 |  |  | 183950
PRC 3352430PA3800 | 2024-01-22 | Inv. 9303.00-01 |  | 183950 | 20348.05 | 20348.05 | 163601.95 | 1070.95
PRC 3352430PB3800 | 2024-04-02 | Inv. 2335RC-2 |  | 183950 | 91811.8 | 112159.85 | 71790.15 | 5903.15
PRC 3352430PC3800 | 2024-05-02 | Inv. Pay Application #03 |  | 183950 | 54128.15 | 166288 | 17662 | 8752
PRC 3352430PD3800 | 2024-06-24 | Inv. Pay Application #04 |  | 183950 | 6716.5 | 173004.5 | 10945.5 | 9105.5
PRC 3352430PE3800 | 2024-07-11 | Inv. Pay Application #05 |  | 183950 | 1748 | 174752.5 | 9197.5 | 9197.5
PRC 3352430PF3800 | 2024-07-12 | Inv. 9303.00-06 - Retainage |  | 183950 | 9197.5 | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  |  |  | 183950 |  | 183950 | 0
|  | Totals: | 183950 |  | 183950 |  | 0

## #9303.00 McGough Constructi (2)
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
McGough Construction #101031.003CA |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524307800 | 2023-11-03 | PO Procore | 40659.24 | 40659.24 |  |  | 40659.24
PRC 3352430PA7800 | 2023-12-15 | Inv. 101031.003CA-01 |  | 40659.24 | 2353.59 | 2353.59 | 38305.65
PRC 3352430PB7800 | 2024-01-12 | Inv. 101031.003CA-02 |  | 40659.24 | 1419.57 | 3773.16 | 36886.08
PRC 3352430PC7800 | 2024-02-06 | Inv. 101031.003CA-03 |  | 40659.24 | 509.9 | 4283.06 | 36376.18
PRC 3352430PD7800 | 2024-03-18 | Inv. 101031.003CA-04 |  | 40659.24 | 1742.02 | 6025.08 | 34634.16
PRC 3352430PE7800 | 2024-04-09 | Inv. 101031.003CA-05 |  | 40659.24 | 5371.17 | 11396.25 | 29262.99
PRC 3352430PF7800 | 2024-05-10 | Inv. 101031.003CA#06 |  | 40659.24 | 6805.44 | 18201.69 | 22457.55
PRC 3352430PG7800 | 2024-06-12 | Inv. 101031.003CA-07 |  | 40659.24 | 2553.95 | 20755.64 | 19903.6
PRC 3352430PH7800 | 2024-07-08 | Inv. 101031.003CA-08 |  | 40659.24 | 1628.21 | 22383.85 | 18275.39 | FY24
PO 33525307800 | 2024-07-22 | Roll to FY25 |  | 40659.24 |  | 22383.85 | 18275.39
PRC 3352530PI7800 | 2024-08-15 | Inv. 101031.003CA-09-Final | -18021.23 | 22638.01 | 254.16 | 22638.01 | 0
|  |  |  | 22638.01 |  | 22638.01 | 0
|  |  |  | 22638.01 |  | 22638.01 | 0
|  | Totals: | 22638.01 |  | 22638.01 |  | 0 | FINAL
|  | CM Services | 22026.01 |  | 22026.01 |  | 0
|  | Reimbursables | 612 |  | 612 |  | 0
|  | Total: | 22638.01 |  | 22638.01 |  | 0

## #9303.00 Terracon Consultants
DOC NCCF Kitchen Grease Pit Replacement
Project # 9303.00
Program code 930300 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0017-335-MM22-9255 |  |  | SRVV5
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524094802 | 2024-04-03 | PO Procore | 4603 | 4603 |  |  | 4603
PRC 3352409PA4802 | 2024-05-03 | Inv. TL05007 |  | 4603 | 3331.75 | 3331.75 | 1271.25
PRC 3352409PB4802 | 2024-07-19 | Inv. TM07920 - FINAL | -1020 | 3583 | 251.25 | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  |  |  | 3583 |  | 3583 | 0
|  | Totals: | 3583 |  | 3583 |  | 0 | FINAL

## RECAP #9306.00
DOC CCF Metal Roof Replacement
Project # 9306.00
Program code 930600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1175000
Modern Builders |  | 1175000 | 1116250 | 58750
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 1175000 | 1175000 | 1116250 | 58750 | 0

## #9306.00 Modern Builders
DOC CCF Metal Roof Replacement
Project # 9306.00
Program code 930600 |  |  | Major Program 4E01
Modern Builders |  |  | Vendor: 00002109592
Acct. Codes-0017-335-MM22-9255 |  |  | RFB930600-01
Project Manager - Brad T |  |  | Activity code: BRIN
Split w/MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525292802 | 2025-01-28 | Opening PO in MM22 | 1175000 | 1175000 |  |  | 1175000
CDE 33525028901 | 2025-01-28 | Moving Expenses From MM24 |  | 1175000 | 1116250 | 1116250 | 58750 | 58750
PO 33525292802 | 2025-01-30 | Closing PO to adjust after CDE |  | 1175000 |  | 1116250 | 58750
PO 33525292802A | 2025-01-30 | Reopening PO with correct amount |  | 1175000 |  | 1116250 | 58750
PRC 3352529PJ2802A | 2025-02-12 | Inv. 19486(100% to MM24) |  | 1175000 | 0 | 1116250 | 58750
PRC 3352529PK2802A | 2025-03-11 | Inv. 19523(100% to MM24) |  | 1175000 | 0 | 1116250 | 58750
PO 33525292802A | 2025-03-21 | CO #5(No Cost CO) | 0 | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  |  |  | 1175000 |  | 1116250 | 58750
|  | Totals: | 1175000 |  | 1116250 |  | 58750
|  | MM24 | 3164727.18 |  | 2818658.59 |  | 346068.59
|  | Totals: | 4339727.18 |  | 3934908.59 |  | 404818.59

## #9306.00 PM TIME
DOC CCF Metal Roof Replacement
Project # 9306.00
Program code 930600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brad T
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9306.00 Misc
DOC CCF Metal Roof Replacement
Project # 9306.00
Program code 930600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx |  |  |  | Shipping Code:
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9354.00
DOC ASP Luc Plumbing Repairs Design
Project # 9354.00
| Program code 935400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 200000
C | McGough Construction |  | 40152.32 | 40152.32 | 0
| PM TIME |  | 20000 | 19951.76 | 48.24
| Misc. |  | 3026.25 | 3026.25 | 0
| Shive Hattery |  | 91622 | 76222 | 15400
| Total Project Cost | 200000 | 154800.57 | 139352.33 | 15448.24 | 45199.43

## #9354.00 McGough Construction
DOC ASP Luc Plumbing Repairs Design
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524255801 | 2023-09-12 | PO Procore | 23598.01 | 23598.01 |  |  | 23598.01
PRC 3352425PA5801 | 2023-10-11 | Inv. 101031.005-PC1 |  | 23598.01 | 622.68 | 622.68 | 22975.33
PRC 3352425PB5801 | 2023-11-09 | Inv. 101031.005-PC2 |  | 23598.01 | 3780.9 | 4403.58 | 19194.43
PRC 3352425PC5801 | 2023-12-27 | Inv. 101031.005-PC3 |  | 23598.01 | 1771.25 | 6174.83 | 17423.18
PO 33524255801 | 2024-01-10 | CO #1 | 638.75 | 24236.76 |  | 6174.83 | 18061.93
PRC 3352425PD5801 | 2024-01-12 | Inv. 101031.005-PC4 |  | 24236.76 | 5704.22 | 11879.05 | 12357.71
PRC 3352425PE5801 | 2024-02-12 | Inv. 101031.005-PC5 |  | 24236.76 | 4408.56 | 16287.61 | 7949.15
PRC 3352425PF5801 | 2024-03-18 | Inv. 101031.005-PC6 |  | 24236.76 | 3118.7 | 19406.31 | 4830.45
PRC 3352425PG5801 | 2024-04-05 | Inv. 101031.005-PC7 |  | 24236.76 | 2415.02 | 21821.33 | 2415.43
PO 33524255801 | 2024-04-11 | CO #2 | 7183.32 | 31420.08 |  | 21821.33 | 9598.75
PO 33524255801 | 2024-04-26 | CO #3 | 2572.94 | 33993.02 |  | 21821.33 | 12171.69
PRC 3352425PH5801 | 2024-05-13 | Inv. 101031.005PC#08 |  | 33993.02 | 4676.73 | 26498.06 | 7494.96
PRC 3352425PI5801 | 2024-06-11 | Inv. 101031.005-PC09 |  | 33993.02 | 1135.78 | 27633.84 | 6359.18
PRC 3352425PJ5801 | 2024-07-11 | Inv. 101031.005-PC10 |  | 33993.02 | 1358.17 | 28992.01 | 5001.01 | FY24
PO 33525255801 | 2024-07-19 | Roll to FY25 |  | 33993.02 |  | 28992.01 | 5001.01
PRC 3352525PK5801 | 2024-08-22 | Inv. 101031.005PC#11 |  | 33993.02 | 500.38 | 29492.39 | 4500.63
PRC 3352525PL5801 | 2024-09-17 | Inv. 101031.005PC#12 |  | 33993.02 | 1080.18 | 30572.57 | 3420.45
PRC 3352525PM5801 | 2024-10-14 | Inv. 101031.005PC#13 |  | 33993.02 | 2350.98 | 32923.55 | 1069.47
PO 33525255801 | 2024-12-16 | CO #5 | 6574.42 | 40567.44 |  | 32923.55 | 7643.89
PRC 3352525PN5801 | 2024-12-23 | Inv. 101031.005PC#14 |  | 40567.44 | 5862.66 | 38786.21 | 1781.23
PRC 3352525PO5801 | 2025-01-27 | Inv. 101031.005PC#15 |  | 40567.44 | 1111.95 | 39898.16 | 669.28
PRC 3352525PP5801 | 2025-02-12 | Inv. 101031.005PC#16 - FINAL | -415.12 | 40152.32 | 254.16 | 40152.32 | -4.0927e-12
|  | Totals: | 40152.32 |  | 40152.32 |  | 0 | FINAL
|  | CM Services | 23016.76 |  | 23016.76 |  | 0
|  | Reimbursables | 581.25 |  | 581.25 |  | 0
|  | CO #1 | 247.5 |  | 247.5 |  | 0
|  | CO #2 | 7183.32 |  | 7183.32 |  | 0
|  | CO #3 | 2572.94 |  | 2572.94 |  | 0
|  | CO #4 | 6550.55 |  | 6550.55 |  | 0
|  | Total: | 40152.32 |  | 40152.32 |  | 0

## #9354.00 PM TIME
DOC ASP Luc Plumbing Repairs Design
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E271
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 20000 | 72.36 | 72.36 | 19927.64
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 20000 | 463.8 | 536.16 | 19463.84
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 20000 | 165.38 | 701.54 | 19298.46
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 20000 | 923.1 | 1624.64 | 18375.36
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 20000 | 91.42 | 1716.06 | 18283.94
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 20000 | 633.9 | 2349.96 | 17650.04
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 20000 | 245.78 | 2595.74 | 17404.26
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 20000 | 1970.7 | 4566.44 | 15433.56
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 20000 | 85.22 | 4651.66 | 15348.34
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 20000 | 644.1 | 5295.76 | 14704.24
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 20000 | 146 | 5441.76 | 14558.24
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 20000 | 1067 | 6508.76 | 13491.24
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 20000 | 149.43 | 6658.19 | 13341.81
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 20000 | 1318.9 | 7977.09 | 12022.91
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 20000 | 173.26 | 8150.35 | 11849.65
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 20000 | 875.2 | 9025.55 | 10974.45
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 20000 | 170.23 | 9195.78 | 10804.22
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 20000 | 1286.9 | 10482.68 | 9517.32
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 20000 | 373.05 | 10855.73 | 9144.27
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 20000 | 3320 | 14175.73 | 5824.27
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 20000 | 71.04 | 14246.77 | 5753.23
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 20000 | 586.2 | 14832.97 | 5167.03
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 20000 | 9.74 | 14842.71 | 5157.29
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 20000 | 87.9 | 14930.61 | 5069.39
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 20000 | 13.8 | 14944.41 | 5055.59
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 20000 | 151.7 | 15096.11 | 4903.89
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 20000 | 63.38 | 15159.49 | 4840.51
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 20000 | 323.8 | 15483.29 | 4516.71
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 57.34 | 15540.63 | 4459.37
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 510.4 | 16051.03 | 3948.97
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 103.71 | 16154.74 | 3845.26
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 692.6 | 16847.34 | 3152.66
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 56.36 | 16903.7 | 3096.3
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 373.7 | 17277.4 | 2722.6
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 132.89 | 17410.29 | 2589.71
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 1418 | 18828.29 | 1171.71
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 210.77 | 19039.06 | 960.94
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 912.7 | 19951.76 | 48.24
[5 empty] | 20000 |  | 19951.76 | 48.24
[5 empty] | 20000 |  | 19951.76 | 48.24
[5 empty] | 20000 |  | 19951.76 | 48.24
|  |  | Totals: | 20000 |  | 19951.76 |  | 48.24
Note on E9: Huggins, Joni [DAS]: PM Time - 9354.00 - MM22 $Joni Elliott, Jennie 7:42 AM (46 minutes ago) to me Can you please set up PM Time in 9354.00 - DOC ASP LUC Plumbing Repairs Design for $12,500.00 in "Contracted". Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov Elliott, Jennie 9:46 AM (10 minutes ago) to me Please increase PM Time in the "contracted" line to a total of $20,000 from 9354.00 (MM22). Thank you, Jennie Elliott

## #9354.00 Misc
DOC ASP Luc Plumbing Repairs Design
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 55 | 55
GAX 33524114911 | 2024-04-23 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2562466 | 3026.25 | 3081.25
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -55 | 3026.25
3026.25
3026.25
3026.25
3026.25
3026.25
3026.25
3026.25
3026.25
3026.25
|  |  |  | Totals: |  | 3026.25

## #9354.00 Shive Hattery
DOC ASP Luc Plumbing Repairs Design
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | 935400-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524317902 | 2023-11-13 | PO Procore | 83600 | 83600 |  |  | 83600
PRC 3352431PA7902 | 2023-12-19 | Inv. 9354.00-01 |  | 83600 | 31000 | 31000 | 52600
PRC 3352431PB7902 | 2024-01-22 | Inv. 2112309650-2 |  | 83600 | 15600 | 46600 | 37000
PRC 3352431PC7902 | 2024-02-21 | Inv. 9354.00-03 |  | 83600 | 7750 | 54350 | 29250
PO 33524317902 | 2024-03-19 | CO 1 | 2522 | 86122 |  | 54350 | 31772
PRC 3352431PD7902 | 2024-04-04 | Inv. 9354.00-04 |  | 86122 | 8722 | 63072 | 23050
PO 33524317902 | 2024-04-25 | CO #2 | 5500 | 91622 |  | 63072 | 28550 | FY24
PO 33525317902 | 2024-07-22 | Roll to FY25 |  | 91622 |  | 63072 | 28550
PRC 3352531PE7902 | 2024-08-22 | Inv. 9354.00-05 |  | 91622 | 620 | 63692 | 27930
PRC 3352531PF7902 | 2024-09-27 | Inv. 9354.00-06 |  | 91622 | 5810 | 69502 | 22120
PRC 3352531PG7902 | 2024-11-20 | Inv. 9354.00-07 |  | 91622 | 620 | 70122 | 21500
PRC 3352531PH7902 | 2024-12-20 | Inv. 9354.00-08 |  | 91622 | 1600 | 71722 | 19900
PRC 3352531PI7902 | 2025-02-17 | Inv. 2112309650-9 |  | 91622 | 2700 | 74422 | 17200
PRC 3352531PJ7902 | 2025-03-24 | Inv. 2112309650-10 |  | 91622 | 1800 | 76222 | 15400
|  |  |  | 91622 |  | 76222 | 15400
|  | Totals: | 91622 |  | 76222 |  | 15400
|  | Design Documents | 31000 |  | 31000 |  | 0
|  | Construction Documents | 31000 |  | 31000 |  | 0
|  | Bidding Assistance | 1600 |  | 1600 |  | 0
|  | Construction Phase | 18000 |  | 4500 |  | 13500
|  | Reimbursables | 2000 |  | 100 |  | 1900
|  | CO 1 | 2522 |  | 2522 |  | 0
|  | CO 2 | 5500 |  | 5500 |  | 0
|  | Total: | 91622 |  | 76222 |  | 15400

## RECAP #9364.00
DAS MEBS House Structural Repairs
Project # 9364.00
| Program code 936400 |  |  | Major Program 4E16
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 186000
C | Samuels Group |  | 11826.88 | 11826.88 | 0
C | PM TIME |  | 10251.26 | 10251.26 | 0
| Misc. |  | 0 | 0 | 0
| Genesis Architectural |  | 13620 | 11620 | 2000
| Total Project Cost | 186000 | 35698.14 | 33698.14 | 2000 | 150301.86

## #9364.00 Samuels Group
DAS MEBS House Structural Repairs
Project # 9364.00
Program code 936400 |  |  | Major Program 4E16
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524102800 | 2024-04-11 | PO Procore | 18488.28 | 18488.28 |  |  | 18488.28
PRC 3352410PA2800 | 2024-05-09 | Inv. 9364.01 PC |  | 18488.28 | 1447.86 | 1447.86 | 17040.42
PRC 3352410PB2800 | 2024-06-01 | Inv. 9364.02 PC |  | 18488.28 | 798.7 | 2246.56 | 16241.72
PRC 3352410PC2800 | 2024-07-16 | Inv. 9364.03 PC |  | 18488.28 | 1373.09 | 3619.65 | 14868.63 | FY24
PO 33525102800 | 2024-07-19 | Roll to FY25 |  | 18488.28 |  | 3619.65 | 14868.63
PRC 3352510PD2800 | 2024-08-08 | Inv. 9364.04PC |  | 18488.28 | 1298.32 | 4917.97 | 13570.31
PRC 3352510PE2800 | 2024-09-13 | Inv. 9364.05 PC |  | 18488.28 | 1298.32 | 6216.29 | 12271.99
PRC 3352510PF2800 | 2024-11-05 | Inv. 9364.06 PC |  | 18488.28 | 2346.83 | 8563.12 | 9925.16
PRC 3352510PG2800 | 2025-02-10 | Inv. 7368.07PC |  | 18488.28 | 3263.76 | 11826.88 | 6661.4
PO 33525102800 | 2025-02-18 | CO #1 Moving PO from MM22 to MM24 | -6661.4 | 11826.88 |  | 11826.88 | 0
|  |  |  | 11826.88 |  | 11826.88 | 0
|  |  |  | 11826.88 |  | 11826.88 | 0
|  |  |  | 11826.88 |  | 11826.88 | 0
|  | Totals: | 11826.88 |  | 11826.88 |  | 0
|  | CM Services | 18488.28 |  | 11826.88 |  | 6661.4
|  | Reimbursables | 0 |  |  |  | 0
|  | CO #1 | -6661.4 |  |  |  | -6661.4
|  | Total: | 11826.88 |  | 11826.88 |  | 0
|  | MM24 | 6661.4 |  | 0 |  | 6661.4
|  | Total: | 18488.28 |  | 11826.88 |  | 6661.4

## #9364.00 PM TIME
DAS MEBS House Structural Repairs
Project # 9364.00
Program code 936400 |  |  |  | Major Program 4E16
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AB
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10251.26 | 10251.26 |  |  | 10251.26
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10251.26 | 99.29 | 99.29 | 10151.97
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10251.26 | 747.8 | 847.09 | 9404.17
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 10251.26 | 34.07 | 881.16 | 9370.1
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 10251.26 | 249.9 | 1131.06 | 9120.2
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10251.26 | 40.69 | 1171.75 | 9079.51
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10251.26 | 354.3 | 1526.05 | 8725.21
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10251.26 | 138.8 | 1664.85 | 8586.41
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10251.26 | 698.3 | 2363.15 | 7888.11
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10251.26 | 62.03 | 2425.18 | 7826.08
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10251.26 | 469.9 | 2895.08 | 7356.18
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 10251.26 | 216.29 | 3111.37 | 7139.89
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 10251.26 | 1922.6 | 5033.97 | 5217.29
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 10251.26 | 117.95 | 5151.92 | 5099.34
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10251.26 | 977.9 | 6129.82 | 4121.44
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10251.26 | 58.88 | 6188.7 | 4062.56
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10251.26 | 535.1 | 6723.8 | 3527.46
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10251.26 | 61.68 | 6785.48 | 3465.78
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10251.26 | 675 | 7460.48 | 2790.78
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10251.26 | 57.47 | 7517.95 | 2733.31
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10251.26 | 292.7 | 7810.65 | 2440.61
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10251.26 | 18.46 | 7829.11 | 2422.15
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10251.26 | 164.5 | 7993.61 | 2257.65
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10251.26 | 85.86 | 8079.47 | 2171.79
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10251.26 | 571 | 8650.47 | 1600.79
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10251.26 | 11.94 | 8662.41 | 1588.85
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10251.26 | 79.2 | 8741.61 | 1509.65
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10251.26 | 16.74 | 8758.35 | 1492.91
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10251.26 | 164.9 | 8923.25 | 1328.01
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10251.26 | 113.91 | 9037.16 | 1214.1
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10251.26 | 1214.1 | 10251.26 | 0
[5 empty] | 10251.26 |  | 10251.26 | 0
[5 empty] | 10251.26 |  | 10251.26 | 0
[5 empty] | 10251.26 |  | 10251.26 | 0
|  |  | Totals: | 10251.26 |  | 10251.26 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: PM Time $John Trower, James 1:41 PM (3 minutes ago) to me Finance - Please see below in red: On Fri, Dec 8, 2023 at 1:30 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James What budget would you like to set up on 9364.00 in MM22? Please set up $8,000 in PM Time We have PM time to post for $847.09 Please see below: On Tue, Nov 12, 2024 at 7:19 AM Huggins, Joni <joni.huggins@iowa.gov> wrote: DA23 9344.00 (1407.82) Increase PM Time by $4,000 DA24 9412.00 (795.82) Increase PM Time by $2,000 MM22 9364.00 (650.47) Increase PM Time by $650.47 MM22 9407.00 (633.47) Increase PM Time by $3,000 Re: November PM Time - $Joni Trower, James Dec 12, 2024, 3:31 PM (4 days ago) to me Please see below in red: On Tue, Dec 10, 2024 at 10:08 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good morning DA24 9412.00 -856.71 Increase PM Time by $2,000 MM22 9364.00 -91.14 Increase PM Time by $2,000 MM23 9373.00 -340.15 Increase PM Time by $3,000 PARK 9411.0 -1,407.60 Increase PM Time by $10,000 e: PM Time 9364.00 MM24 $Joni Trower, James 3:00 PM (4 minutes ago) to me, Oliver Finance - Can you please close the MM22 PM Time for project 9364.00 and remove it from my spreadsheet? As of January 2025, I will not bill this project. Thanks, James

## #9364.00 Misc
DAS MEBS House Structural Repairs
Project # 9364.00
Program code 936400 |  |  |  | Major Program 4E16
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9364.00 Genesis Architectural
DAS MEBS House Structural Repairs
Project # 9364.00
Program code 936400 |  |  | Major Program 4E16
Genesis Architectural |  |  | Vendor:00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP936500-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524156906 | 2024-06-01 | PO Procore | 25000 | 25000 |  |  | 25000
PRC 3352415PA6906 | 2024-07-05 | Inv. 2407-01 |  | 25000 | 4176 | 4176 | 20824 | FY24
PO 33525156906 | 2024-07-19 | Roll to FY25 |  | 25000 |  | 4176 | 20824
PRC 3352515PB6906 | 2025-01-08 | Inv. 2407-02 |  | 25000 | 7444 | 11620 | 13380
PO 33525156906 | 2025-02-18 | CO #1 (100% to MM22) | 2000 | 27000 |  | 11620 | 15380
PO 33525156906 | 2025-02-18 | CO #2 Opening PO in MM24 | -13380 | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  |  |  | 13620 |  | 11620 | 2000
|  | Totals: | 13620 |  | 11620 |  | 2000
|  | Design Development | 8700 |  | 8700 |  | 0
|  | Construction Documents | 7300 |  | 2920 |  | 4380
|  | Bid Phase | 1700 |  |  |  | 1700
|  | Construction Phase | 7300 |  |  |  | 7300
|  | CO #1 | 2000 |  |  |  | 2000
|  | CO #2 | -13380 |  |  |  | -13380
|  | Total: | 13620 |  | 11620 |  | 2000
|  | MM24 | 13380 |  | 0 |  | 13380
|  | Total: | 27000 |  | 11620 |  | 15380

## RECAP #9365.00
DAS MON Front Porch Column Repair/Replacement
Project # 9365.00
| Program code 936500 |  |  | Major Program 4E16
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 4044.57
C | Boyd Jones |  | 1841.81 | 1841.81 | 0
| PM TIME |  | 1927.76 | 1927.76 | 0
| Misc. |  | 275 | 275 | 0
| Total Project Cost | 4044.57 | 4044.57 | 4044.57 | 0 | 0
Closed 03/18/2024

## #9365.00 Boyd Jones
DAS MON Front Porch Column Repair/Replacement
Project # 9365.00
Program code 936500 |  |  | Major Program 4E16
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524009900 | 2024-01-09 | PO Procore | 13364.6 | 13364.6 |  |  | 13364.6
PRC 3352400PA9900 | 2024-03-31 | Inv. 9365.00-01 - Final | -11522.79 | 1841.81 | 1841.81 | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  |  |  | 1841.81 |  | 1841.81 | 0
|  | Totals: | 1841.81 |  | 1841.81 |  | 0
|  | CM Services | 1841.81 |  | 1841.81 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 1841.81 |  | 1841.81 |  | 0

## #9365.00 PM TIME
DAS MON Front Porch Column Repair/Replacement
Project # 9365.00
Program code 936500 |  |  |  | Major Program 4E16
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AC
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 1927.76 | 1927.76 |  |  | 1927.76
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 1927.76 | 68.37 | 68.37 | 1859.39
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 1927.76 | 513.1 | 581.47 | 1346.29
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 1927.76 | 13.9 | 595.37 | 1332.39
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 1927.76 | 100.3 | 695.67 | 1232.09
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 1927.76 | 40.69 | 736.36 | 1191.4
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 1927.76 | 354.3 | 1090.66 | 837.1
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 1927.76 | 138.8 | 1229.46 | 698.3
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 1927.76 | 698.3 | 1927.76 | 0
[5 empty] | 1927.76 |  | 1927.76 | 0
[5 empty] | 1927.76 |  | 1927.76 | 0
[5 empty] | 1927.76 |  | 1927.76 | 0
[5 empty] | 1927.76 |  | 1927.76 | 0
|  |  | Totals: | 1927.76 |  | 1927.76 |  | 0
Note on E9: Jurgenson, John [DAS]: 9365.00 - DAS MON Front Porch Column Repair/Replacement Inbox Trower, James 3:31 PM (0 minutes ago) to me Finance - Can you please set up $6,000 in PM Time (MM22) for project 9365.00. Thanks,

## #9365.00 Misc
DAS MON Front Porch Column Repair/Replacement
Project # 9365.00
Program code 936500 |  |  |  | Major Program 4E16
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2024 | DAS2024071153 | 165 | 165
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 110 | 275
275
275
275
275
275
275
275
275
275
275
|  |  |  | Totals: |  | 275

## RECAP #9366.00
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
| Program code 936600 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 403000
C | McGough Construction |  | 16569.56 | 16569.56 | 0
| PM TIME |  | 12000 | 9836.87 | 2163.13
| Misc. |  | 0 | 0 | 0
C | Shive Hattery |  | 11401.78 | 11401.78 | 0
| Shive Hattery |  | 39600 | 29200 | 10400
| Jensen Builders |  | 255172 | 0 | 255172
| McGough Construction (2) |  | 30499.68 | 1371.86 | 29127.82
| Total Project Cost | 403000 | 365243.02 | 68380.07 | 296862.95 | 37756.98

## #9366.00 McGough Construction
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524331802 | 2023-11-27 | PO Procore | 17543.15 | 17543.15 |  |  | 17543.15
PRC 3352433PA1802 | 2024-01-12 | Inv. 101174.001-PC1 |  | 17543.15 | 934.02 | 934.02 | 16609.13
PRC 3352433PB1802 | 2024-02-06 | Inv. 101174.001-PC2 |  | 17543.15 | 1148.8 | 2082.82 | 15460.33
PRC 3352433PC1802 | 2024-03-18 | Inv. 101174.001-PC3 |  | 17543.15 | 689.93 | 2772.75 | 14770.4
PRC 3352433PD1802 | 2024-04-09 | Inv. 101174.001-PC4 |  | 17543.15 | 964.75 | 3737.5 | 13805.65
PRC 3352433PE1802 | 2024-05-13 | Inv. 101174.001-PC#05 |  | 17543.15 | 1630.13 | 5367.63 | 12175.52
PRC 3352433PF1802 | 2024-06-13 | Inv. 101174.001-PC6 |  | 17543.15 | 770.42 | 6138.05 | 11405.1
PRC 3352433PG1802 | 2024-07-08 | Inv. 101174.001-PC7 |  | 17543.15 | 2263.61 | 8401.66 | 9141.49 | FY24
PO 33525331802 | 2024-07-22 | Roll to FY25 |  | 17543.15 |  | 8401.66 | 9141.49
PRC 3352533PH1802 | 2024-08-15 | Inv. 101174.001-PC8 |  | 17543.15 | 328.29 | 8729.95 | 8813.2
PRC 3352533PI1802 | 2024-09-17 | Inv. 101174.001-PC9 |  | 17543.15 | 889.56 | 9619.51 | 7923.64
PRC 3352533PJ1802 | 2024-10-22 | Inv. 101174.001-PC10 |  | 17543.15 | 1397.88 | 11017.39 | 6525.76
PRC 3352533PK1802 | 2024-11-20 | Inv. 101174.001-PC11 |  | 17543.15 | 3232.96 | 14250.35 | 3292.8
PRC 3352533PL1802 | 2024-12-20 | Inv. 101174.001-PC12 |  | 17543.15 | 1016.64 | 15266.99 | 2276.16
PRC 3352533PM1802 | 2025-01-27 | Inv. 101174.001-PC13 |  | 17543.15 | 730.71 | 15997.7 | 1545.45
PRC 3352533PN1802 | 2025-02-12 | Inv. 101174.001-PC14 |  | 17543.15 | 444.78 | 16442.48 | 1100.67
PRC 3352533PO1802 | 2025-03-21 | Inv. 101174.001-PC15 - FINAL | -973.59 | 16569.56 | 127.08 | 16569.56 | 0
|  |  |  | 16569.56 |  | 16569.56 | 0
|  |  |  | 16569.56 |  | 16569.56 | 0
|  | Totals: | 16569.56 |  | 16569.56 |  | 0 | FINAL
|  | CM Services | 16210.06 |  | 16210.06 |  | 0
|  | Reimbursables | 359.5 |  | 359.5 |  | 0
|  | Total: | 16569.56 |  | 16569.56 |  | 0

## #9366.00 PM TIME
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AD
Project Manager - Jennie E
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12000 | 12000 |  |  | 12000
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 12000 | 123.94 | 123.94 | 11876.06
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 12000 | 934.5 | 1058.44 | 10941.56
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 12000 | 20.17 | 1078.61 | 10921.39
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 12000 | 149.6 | 1228.21 | 10771.79
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 12000 | 100.95 | 1329.16 | 10670.84
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 12000 | 887.1 | 2216.26 | 9783.74
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 12000 | 86.63 | 2302.89 | 9697.11
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12000 | 435.7 | 2738.59 | 9261.41
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12000 | 67.87 | 2806.46 | 9193.54
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12000 | 511.4 | 3317.86 | 8682.14
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 12000 | 43.37 | 3361.23 | 8638.77
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 12000 | 384.2 | 3745.43 | 8254.57
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 12000 | 73.41 | 3818.84 | 8181.16
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12000 | 605.3 | 4424.14 | 7575.86
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 12000 | 63.63 | 4487.77 | 7512.23
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12000 | 583.7 | 5071.47 | 6928.53
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 12000 | 28.87 | 5100.34 | 6899.66
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12000 | 317.6 | 5417.94 | 6582.06
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12000 | 65.77 | 5483.71 | 6516.29
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12000 | 335.3 | 5819.01 | 6180.99
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12000 | 46.91 | 5865.92 | 6134.08
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12000 | 416.4 | 6282.32 | 5717.68
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12000 | 173.55 | 6455.87 | 5544.13
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12000 | 1151.8 | 7607.67 | 4392.33
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12000 | 40.33 | 7648 | 4352
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12000 | 266.6 | 7914.6 | 4085.4
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12000 | 43.31 | 7957.91 | 4042.09
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12000 | 429.2 | 8387.11 | 3612.89
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12000 | 11.39 | 8398.5 | 3601.5
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12000 | 118.6 | 8517.1 | 3482.9
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12000 | 247.57 | 8764.67 | 3235.33
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12000 | 1072.2 | 9836.87 | 2163.13
[5 empty] | 12000 |  | 9836.87 | 2163.13
[5 empty] | 12000 |  | 9836.87 | 2163.13
[5 empty] | 12000 |  | 9836.87 | 2163.13
|  |  | Totals: | 12000 |  | 9836.87 |  | 2163.13
Note on E9: Jurgenson, John [DAS]: Set Up PM Time Inbox Trower, James 3:38 PM (1 minute ago) to me Finance - Please set up PM time for the following projects: 9366.00 - DOC NCCF IPI Sally Port Vehicle Gate Funding source: MM22 Set up Pm Time: $6,000 9372.00 - DOC MPCF Bldg 20 Plumbing Replacement Funding source: MM24 Set up Pm Time: $15,000

## #9366.00 Misc
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx |  |  |  | Shipping Code: 177
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 110 | 110
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -110 | 0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9366.00 Shive Hattery
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524088904 | 2024-03-28 | PO Procore | 11440 | 11440 |  |  | 11440
PRC 3352408PA8904 | 2024-06-11 | Inv. 22400004590-1 - Final | -38.22 | 11401.78 | 11401.78 | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  |  |  | 11401.78 |  | 11401.78 | -6.537e-13
|  | Totals: | 11401.78 |  | 11401.78 |  | 0 | FINAL
|  | Recommendations | 11300 |  | 11300 |  | 0
|  | Reimbursables | 101.78 |  | 101.78 |  | 0
|  | Total: | 11401.78 |  | 11401.78 |  | 0

## #9366.00 Shive Hattery (2)
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM22-9260 |  |  | RFP936600-00
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525248900 | 2024-09-04 | PO Procore | 39600 | 39600 |  |  | 39600
PRC 3352524PA8900 | 2024-09-27 | Inv. 2240004590-2 |  | 39600 | 23480 | 23480 | 16120
PRC 3352524PB8900 | 2024-11-20 | Inv. 2240004590-3 |  | 39600 | 5107.5 | 28587.5 | 11012.5
PRC 3352524PC8900 | 2024-12-20 | Inv. 2240004590-4 |  | 39600 | 612.5 | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  |  |  | 39600 |  | 29200 | 10400
|  | Totals: | 39600 |  | 29200 |  | 10400
|  | Design Development Docs | 10400 |  | 10400 |  | 0
|  | Construction Docs | 16350 |  | 16350 |  | 0
|  | Bidding Assistance | 2450 |  | 2450 |  | 0
|  | Construction Phase | 10400 |  |  |  | 10400
|  | Total: | 39600 |  | 29200 |  | 10400

## #9366.00 Jensen Builders
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
Jensen Builders |  |  | Vendor: 00002115639
Acct. Codes-0017-335-MM22-9255 |  |  | RFB936600-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525351900 | 2024-12-16 | PO Procore | 255172 | 255172 |  |  | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  |  |  | 255172 |  | 0 | 255172
|  | Totals: | 255172 |  | 0 |  | 255172

## #9366.00 McGough Constructi (2)
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525043902 | 2025-02-11 | PO Procore | 30499.68 | 30499.68 |  |  | 30499.68
PRC 3352504PA3902 | 2025-03-24 | Inv. 101174.001-CA#01 |  | 30499.68 | 1371.86 | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  |  |  | 30499.68 |  | 1371.86 | 29127.82
|  | Totals: | 30499.68 |  | 1371.86 |  | 29127.82
|  | CM Services | 28939.68 |  | 1300.86 |  | 27638.82
|  | Reimbursables | 1560 |  | 71 |  | 1489
|  | Total: | 30499.68 |  | 1371.86 |  | 29127.82

## RECAP #9367.00
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
| Program code 936700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 305000
C | McGough Construction |  | 8700 | 8700 | 0
| PM TIME |  | 19000 | 18202.68 | 797.32
| Misc. |  | 962.32 | 962.32 | 0
C | Genesis Architectural Design |  | 14000 | 14000 | 0
C | Black Hawk Roofing |  | 203400 | 203400 | 0
| McGough Construction (2) |  | 23876.92 | 19790.91 | 4086.01
| Total Project Cost | 305000 | 269939.24 | 265055.91 | 4883.33 | 35060.76

## #9367.00 McGough Construction
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
McGough |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524303801 | 2023-10-30 | PO Procore | 9655.52 | 9655.52 |  |  | 9655.52
PRC 3352430PA3801 | 2023-12-18 | Inv. 101031.007-PC01 |  | 9655.52 | 586.15 | 586.15 | 9069.37
PRC 3352430PB3801 | 2024-01-12 | Inv. 101031.007-PC02 |  | 9655.52 | 769.35 | 1355.5 | 8300.02
PRC 3352430PC3801 | 2024-02-08 | Inv. 101031.007-PC03 |  | 9655.52 | 1120.41 | 2475.91 | 7179.61
PRC 3352430PD3801 | 2024-03-18 | Inv. 101031.007-PC04 |  | 9655.52 | 1774.81 | 4250.72 | 5404.8
PRC 3352430PE3801 | 2024-04-08 | Inv. 101031.007-PC05 |  | 9655.52 | 2430.84 | 6681.56 | 2973.96
PRC 3352430PF3801 | 2024-05-08 | Inv. 101031.007-PC06 |  | 9655.52 | 1465.64 | 8147.2 | 1508.32
PRC 3352430PG3801 | 2024-06-12 | Inv. 101031.007-PC07- Final | -955.52 | 8700 | 552.8 | 8700 | 0
|  |  |  | 8700 |  | 8700 | 0
|  |  |  | 8700 |  | 8700 | 0
|  |  |  | 8700 |  | 8700 | 0
|  |  |  | 8700 |  | 8700 | 0
|  |  |  | 8700 |  | 8700 | 0
|  | Totals: | 8700 |  | 8700 |  | 0 | FINAL
|  | CM Services | 8644 |  | 8644 |  | 0
|  | Reimbursables | 56 |  | 56 |  | 0
|  | Total: | 8700 |  | 8700 |  | 0

## #9367.00 PM TIME
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AE
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 19000 | 19000 |  |  | 19000
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 19000 | 109.37 | 109.37 | 18890.63
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 19000 | 874.7 | 984.07 | 18015.93
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 19000 | 49.3 | 1033.37 | 17966.63
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 19000 | 376.1 | 1409.47 | 17590.53
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 19000 | 72.02 | 1481.49 | 17518.51
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 19000 | 526.1 | 2007.59 | 16992.41
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 19000 | 162.49 | 2170.08 | 16829.92
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 19000 | 1434.1 | 3604.18 | 15395.82
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 19000 | 587.71 | 4191.89 | 14808.11
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 19000 | 2961.23 | 7153.12 | 11846.88
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 19000 | 148.96 | 7302.08 | 11697.92
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 19000 | 1135.2 | 8437.28 | 10562.72
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 19000 | 101.38 | 8538.66 | 10461.34
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 19000 | 893 | 9431.66 | 9568.34
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 19000 | 68.25 | 9499.91 | 9500.09
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 19000 | 571.3 | 10071.21 | 8928.79
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 19000 | 47.19 | 10118.4 | 8881.6
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 19000 | 430.8 | 10549.2 | 8450.8
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 19000 | 69.56 | 10618.76 | 8381.24
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 19000 | 755.8 | 11374.56 | 7625.44
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 19000 | 336.89 | 11711.45 | 7288.55
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 19000 | 1715.2 | 13426.65 | 5573.35
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 19000 | 118.75 | 13545.4 | 5454.6
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 19000 | 1057.4 | 14602.8 | 4397.2
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 19000 | 133.77 | 14736.57 | 4263.43
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 19000 | 897.7 | 15634.27 | 3365.73
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 19000 | 84.04 | 15718.31 | 3281.69
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 19000 | 560 | 16278.31 | 2721.69
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 19000 | 52.45 | 16330.76 | 2669.24
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 19000 | 520.3 | 16851.06 | 2148.94
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 19000 | 65.67 | 16916.73 | 2083.27
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 19000 | 700.8 | 17617.53 | 1382.47
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 19000 | 109.95 | 17727.48 | 1272.52
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 19000 | 475.2 | 18202.68 | 797.32
[5 empty] | 19000 |  | 18202.68 | 797.32
[5 empty] | 19000 |  | 18202.68 | 797.32
[5 empty] | 19000 |  | 18202.68 | 797.32
|  |  | Totals: | 19000 |  | 18202.68 |  | 797.32
Note on E9: Jurgenson, John [DAS]: 9367.00 DOE IPBS JOH 6535 Corporate Dr Roof Replacement Inbox Adams, Brandon 2:46 PM (0 minutes ago) to me Finance, Please set my PM budget to $11,000 for project 9367.00 - MM22 Regards, Re: PM Time Inbox Adams, Brandon 7:49 AM (54 minutes ago) to me Please increase PM Time budget $6,000 for 9367.00 in MM22. Regards, Re: PM time Inbox Adams, Brandon 11:41 AM (35 minutes ago) to me Please increase my PM Time for the following projects: MM22 9367.00 - $2,000 MM22 9387.00 - $1,000 Regards,

## #9367.00 Misc
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524050801 | 2024-02-19 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2555636 | 625 | 625
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 137.5 | 762.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -137.5 | 625
PRC 33524141904 | 2024-05-20 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL626 | 337.32 | 962.32
962.32
962.32
962.32
962.32
962.32
962.32
962.32
962.32
|  |  |  | Totals: |  | 962.32

## #9367.00 Genesis
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
Genesis Architectural Design |  |  | Vendor:00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524012801 | 2024-01-12 | PO Procore | 14000 | 14000 |  |  | 14000
PRC 3352401PA2801 | 2024-02-13 | Inv. 2401-01 |  | 14000 | 3300 | 3300 | 10700
PRC 3352401PB2801 | 2024-04-08 | Inv. 2401-02 |  | 14000 | 5560 | 8860 | 5140
PRC 3352401PC2801 | 2024-05-06 | Inv. 2401-03 |  | 14000 | 840 | 9700 | 4300
PRC 3352401PD2801 | 2024-07-08 | Inv. 2401-04 |  | 14000 | 215 | 9915 | 4085 | FY24
PO 33525012801 | 2024-07-19 | Roll to FY25 |  | 14000 |  | 9915 | 4085
PRC 3352501PE2801 | 2024-08-23 | Inv. 2401-05 |  | 14000 | 2580 | 12495 | 1505
PRC 3352501PF2801 | 2025-03-26 | Inv. 2401-06 FINAL |  | 14000 | 1505 | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  | Totals: | 14000 |  | 14000 |  | 0 | FINAL
|  | Design Development | 3300 |  | 3300 |  | 0
|  | Construction Documents | 5200 |  | 5200 |  | 0
|  | Bid/Negotiation Phase | 1200 |  | 1200 |  | 0
|  | Construction Phase | 4300 |  | 4300 |  | 0
|  | Total: | 14000 |  | 14000 |  | 0

## #9367.00 Black Hawk Roofing
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
Black Hawk Roofing |  |  | Vendor:00002120676
Acct. Codes-0017-335-MM22-9255 |  |  | RFB 936700-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Split w/DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524123900 | 2024-05-02 | PO Procore | 203400 | 203400 |  |  | 203400 |  | FY24
PO 33525123900 | 2024-08-19 | Roll to FY25 |  | 203400 |  | 0 | 203400
PRC 3352512PA3900 | 2024-12-19 | Inv. 9367.00-01(Split w/DA24) |  | 203400 | 187530 | 187530 | 15870 | 9870
PRC 3352512PB3900 | 2025-03-25 | Inv. 9367.00-02(Split w/DA24) |  | 203400 | 5700 | 193230 | 10170 | 10170
PRC 3352512PC3900 | 2025-03-26 | Inv. 9367.00-03-Retainage(Split w/DA24) |  | 203400 | 10170 | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  |  |  | 203400 |  | 203400 | 0
|  | Totals: | 203400 |  | 203400 |  | 0
|  | DA24 | 6600 |  | 6600 |  | 0
|  | Total | 210000 |  | 210000 |  | 0

## #9367.00 McGough Construction(2
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
McGough Construction (2) |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524127900 | 2024-05-06 | PO Procore | 21639.79 | 21639.79 |  |  | 21639.79
PRC 3352412PA7900 | 2024-06-12 | Inv. 101031.007-CA01 |  | 21639.79 | 698.74 | 698.74 | 20941.05
PRC 3352412PB7900 | 2024-07-08 | Inv. 101031.007-CA02 |  | 21639.79 | 1267.97 | 1966.71 | 19673.08 | FY24
PO 33525127900 | 2024-07-19 | Roll to FY25 |  | 21639.79 |  | 1966.71 | 19673.08
PRC 3352512PC7900 | 2024-08-09 | Inv. 101031.007-CA03 |  | 21639.79 | 1025.66 | 2992.37 | 18647.42
PRC 3352512PD7900 | 2024-09-12 | Inv. 101031.007-CA04 |  | 21639.79 | 5799.59 | 8791.96 | 12847.83
PRC 3352512PE7900 | 2024-10-09 | Inv. 101031.007-CA05 |  | 21639.79 | 3911.43 | 12703.39 | 8936.4
PRC 3352512PF7900 | 2024-11-12 | Inv. 101031.007-CA06 |  | 21639.79 | 760.68 | 13464.07 | 8175.72
PO 33525127900 | 2024-12-17 | CO #1 | 2237.13 | 23876.92 |  | 13464.07 | 10412.85
PRC 3352512PG7900 | 2024-12-19 | Inv. 101031.007-CA07 |  | 23876.92 | 4273.46 | 17737.53 | 6139.39
PRC 3352512PH7900 | 2025-01-14 | Inv. 101031.007-CA08 |  | 23876.92 | 1641.85 | 19379.38 | 4497.54
PRC 3352512PI7900 | 2025-02-12 | Inv. 101031.007-CA09 |  | 23876.92 | 411.53 | 19790.91 | 4086.01
|  |  |  | 23876.92 |  | 19790.91 | 4086.01
|  | Totals: | 23876.92 |  | 19790.91 |  | 4086.01
|  | CM Services | 21279.79 |  | 17301.78 |  | 3978.01
|  | Reimbursables | 360 |  | 252 |  | 108
|  | CO #1 | 2237.13 |  | 2237.13 |  | 0
|  | Total: | 23876.92 |  | 19790.91 |  | 4086.01

## RECAP #9368.00
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
| Program code 936800 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 210000
C | Samuels Group |  | 24420.55 | 24420.55 | 0
| PM TIME |  | 10000 | 9993.43 | 6.57
| Misc. |  | 1460.04 | 1460.04 | 0
| Genesis Architectural |  | 22500 | 15460 | 7040
| Service Roofing Company |  | 100358 | 0 | 100358
| Samuels Group (2) |  | 22019.54 | 7501 | 14518.54
| Total Project Cost | 210000 | 180758.13 | 58835.02 | 121923.11 | 29241.87

## #9368.00 Samuels Group
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010803 | 2024-01-10 | PO Procore | 24422.52 | 24422.52 |  |  | 24422.52
PRC 3352401PA0803 | 2024-02-12 | Inv. 7669.10 PC |  | 24422.52 | 1653.91 | 1653.91 | 22768.61
PRC 3352401PB0803 | 2024-03-08 | Inv. 7669.11 PC |  | 24422.52 | 4361.79 | 6015.7 | 18406.82
PRC 3352401PC0803 | 2024-04-04 | Inv. 7669.12 PC |  | 24422.52 | 2015.88 | 8031.58 | 16390.94
PRC 3352401PD0803 | 2024-05-13 | Inv. 7669.13 PC |  | 24422.52 | 4488.06 | 12519.64 | 11902.88
PRC 3352401PE0803 | 2024-06-01 | Inv. 7669.14 PC |  | 24422.52 | 2339.54 | 14859.18 | 9563.34
PRC 3352401PF0803 | 2024-07-11 | Inv. 7669.15 PC |  | 24422.52 | 4177.02 | 19036.2 | 5386.32 | FY24
PO 33525010803 | 2024-07-19 | Roll to FY25 |  | 24422.52 |  | 19036.2 | 5386.32
PRC 3352501PG0803 | 2024-09-06 | Inv. 7669.16 PC |  | 24422.52 | 3255.39 | 22291.59 | 2130.93
PRC 3352501PH0803 | 2024-09-11 | Inv. 7669.17 PC FINAL | -1.97 | 24420.55 | 2128.96 | 24420.55 | -3.838e-12
|  |  |  | 24420.55 |  | 24420.55 | -3.838e-12
|  |  |  | 24420.55 |  | 24420.55 | -3.838e-12
|  |  |  | 24420.55 |  | 24420.55 | -3.838e-12
|  | Totals: | 24420.55 |  | 24420.55 |  | 0 | FINAL
|  | CM Services | 23820.55 |  | 23820.55 |  | 0
|  | Reimbursables | 600 |  | 600 |  | 0
|  | Total: | 24420.55 |  | 24420.55 |  | 0

## #9368.00 PM Time
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AF
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 10000 | 9.32 | 9.32 | 9990.68
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 10000 | 75.4 | 84.72 | 9915.28
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10000 | 30.49 | 115.21 | 9884.79
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10000 | 230.9 | 346.11 | 9653.89
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10000 | 43.74 | 389.85 | 9610.15
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10000 | 382.7 | 772.55 | 9227.45
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10000 | 331.03 | 1103.58 | 8896.42
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10000 | 1669.1 | 2772.68 | 7227.32
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10000 | 143.11 | 2915.79 | 7084.21
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10000 | 1086.6 | 4002.39 | 5997.61
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 10000 | 211.97 | 4214.36 | 5785.64
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 10000 | 1883.8 | 6098.16 | 3901.84
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 10000 | 167.48 | 6265.64 | 3734.36
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10000 | 1383.8 | 7649.44 | 2350.56
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10000 | 29.23 | 7678.67 | 2321.33
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10000 | 263.2 | 7941.87 | 2058.13
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10000 | 10.28 | 7952.15 | 2047.85
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10000 | 113.5 | 8065.65 | 1934.35
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10000 | 94.93 | 8160.58 | 1839.42
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10000 | 486 | 8646.58 | 1353.42
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10000 | 62.55 | 8709.13 | 1290.87
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10000 | 555.2 | 9264.33 | 735.67
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10000 | 34.57 | 9298.9 | 701.1
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10000 | 232.4 | 9531.3 | 468.7
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10000 | 48.21 | 9579.51 | 420.49
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10000 | 320.7 | 9900.21 | 99.79
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 3.79 | 9904 | 96
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 39.9 | 9943.9 | 56.1
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 9.13 | 9953.03 | 46.97
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 40.4 | 9993.43 | 6.57
[5 empty] | 10000 |  | 9993.43 | 6.57
[5 empty] | 10000 |  | 9993.43 | 6.57
[5 empty] | 10000 |  | 9993.43 | 6.57
|  |  | Totals: | 10000 |  | 9993.43 |  | 6.57
Note on E9: Huggins, Joni [DAS]: On Mon, Apr 29, 2024 at 9:35 AM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Please increase PM Time in the "contracted" line to a total of $10,000.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau

## #9368.00 Misc
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 137.5 | 137.5
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 165 | 302.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -302.5 | 0
GAX 33524138905 | 2024-05-17 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2573138 | 1035 | 1035
PRC 33524200906 | 2024-07-18 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV041446 | 425.04 | 1460.04
1460.04
1460.04
1460.04
1460.04
1460.04
1460.04
1460.04
|  |  |  | Totals: |  | 1460.04

## #9368.00 Genesis Architectural
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor:00002092152
Acct. Codes-0017-335-MM22-9260 |  |  | RFP936800-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524080905 | 2024-03-20 | PO Procore | 22500 | 22500 |  |  | 22500
PRC 3352408PA0905 | 2024-05-13 | Inv. 2401-01A** |  | 22500 | 5650 | 5650 | 16850
PRC 3352408PB0905 | 2024-06-01 | Inv. 2404-02 |  | 22500 | 4920 | 10570 | 11930
PRC 3352408PC0905 | 2024-07-11 | Inv. 2404-03 |  | 22500 | 1230 | 11800 | 10700 | FY24
PO 33525080905 | 2024-07-19 | Roll to FY25 |  | 22500 |  | 11800 | 10700
PRC 3352508PD0905 | 2024-09-27 | Inv. 2404-04 |  | 22500 | 3220 | 15020 | 7480
PRC 3352508PE0905 | 2024-11-20 | Inv. 2404-05 |  | 22500 | 440 | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  |  |  | 22500 |  | 15460 | 7040
|  | Totals: | 22500 |  | 15460 |  | 7040
|  | Design Development | 5650 |  | 5650 |  | 0
|  | Construction Documents | 6150 |  | 6150 |  | 0
|  | Bid Phase | 1900 |  | 1900 |  | 0
|  | Construction Phase | 8800 |  | 1760 |  | 7040
|  | Total: | 22500 |  | 15460 |  | 7040
** "A" added since vendor has used this invoice number before

## #9368.00 Service Roofing Co
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  | Major Program 4E02
Service Roofing Co |  |  | Vendor:00002109133
Acct. Codes-0017-335-MM22-9255 |  |  | RFP936800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525222904 | 2024-08-09 | PO Procore | 100358 | 100358 |  |  | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  |  |  | 100358 |  | 0 | 100358
|  | Totals: | 100358 |  | 0 |  | 100358

## #9368.00 Samuels Group (2)
HHS IMHI Reynolds Bldg North Annex Roof Replacement
Project # 9368.00
Program code 936800 |  |  | Major Program 4E02
Samuels Group (2) |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525249912 | 2024-09-05 | PO Procore | 22019.54 | 22019.54 |  |  | 22019.54
PRC 3352524PA9912 | 2024-10-07 | Inv. 7716.519368 CA |  | 22019.54 | 2596.64 | 2596.64 | 19422.9
PRC 3352524PB9912 | 2024-11-07 | Inv. 7716.529368 CA |  | 22019.54 | 2746.18 | 5342.82 | 16676.72
PRC 3352524PC9912 | 2024-12-06 | Inv. 7716.539368 CA |  | 22019.54 | 985.63 | 6328.45 | 15691.09
PRC 3352524PD9912 | 2025-01-14 | Inv. 7716.549368 CA |  | 22019.54 | 1172.55 | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  |  |  | 22019.54 |  | 7501 | 14518.54
|  | Totals: | 22019.54 |  | 7501 |  | 14518.54
|  | CM Services | 20519.54 |  | 7501 |  | 13018.54
|  | Reimbursables | 1500 |  |  |  | 1500
|  | Total: | 22019.54 |  | 7501 |  | 14518.54

## RECAP #9369.00
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
| Program code 936900 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM22
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 147783.65
C | Samuels Group |  | 21537.04 | 21537.04 | 0
C | PM TIME |  | 7884.62 | 7884.62 | 0
C | Misc. |  | 11198.23 | 11198.23 | 0
C | Horizon Architecture |  | 17985 | 17985 | 0
C | Timekey Enterprise |  | 60343.4 | 60343.4 | 0
C | Samuels Group (2) |  | 28835.36 | 28835.36 | 0
| Total Project Cost | 147783.65 | 147783.65 | 147783.65 | 0 | 0
Closed 03/11/25

## #9369.00 Samuels Group
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  | Major Program 4B02
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010802 | 2024-01-10 | PO Procore | 21825.88 | 21825.88 |  |  | 21825.88
PRC 3352401PA0802 | 2024-02-12 | Inv. 7670.01 PC |  | 21825.88 | 1167.04 | 1167.04 | 20658.84
PRC 3352401PB0802 | 2024-03-18 | Inv. 7670.02 PC |  | 21825.88 | 2458.99 | 3626.03 | 18199.85
PRC 3352401PC0802 | 2024-04-04 | Inv. 7670.03 PC |  | 21825.88 | 3144.62 | 6770.65 | 15055.23
PRC 3352401PD0802 | 2024-05-13 | Inv. 7670.04 PC |  | 21825.88 | 1854.95 | 8625.6 | 13200.28
PRC 3352401PE0802 | 2024-06-01 | Inv. 7670.05 PC |  | 21825.88 | 1852.67 | 10478.27 | 11347.61
PRC 3352401PF0802 | 2024-07-11 | Inv. 7670.06 PC |  | 21825.88 | 4376.53 | 14854.8 | 6971.08 | FY24
PO 33525010802 | 2024-07-19 | Roll to FY25 |  | 21825.88 |  | 14854.8 | 6971.08
PRC 3352501PG0802 | 2024-08-09 | Inv. 7670.07 PC |  | 21825.88 | 4996.82 | 19851.62 | 1974.26
PRC 3352501PH0802 | 2024-09-11 | Inv. 7670.08 PC FINAL | -288.84 | 21537.04 | 1685.42 | 21537.04 | 0
|  |  |  | 21537.04 |  | 21537.04 | 0
|  |  |  | 21537.04 |  | 21537.04 | 0
|  |  |  | 21537.04 |  | 21537.04 | 0
|  | Totals: | 21537.04 |  | 21537.04 |  | 0 | FINAL
|  | CM Services | 21217.11 |  | 21217.11 |  | 0
|  | Reimbursables | 319.93 |  | 319.93 |  | 0
|  | Total: | 21537.04 |  | 21537.04 |  | 0

## #9369.00 PM TIME
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2AG
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7884.62 | 7884.62 |  |  | 7884.62
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 7884.62 | 9.32 | 9.32 | 7875.3
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 7884.62 | 75.4 | 84.72 | 7799.9
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 7884.62 | 6.27 | 90.99 | 7793.63
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 7884.62 | 46.4 | 137.39 | 7747.23
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 7884.62 | 43.74 | 181.13 | 7703.49
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 7884.62 | 382.7 | 563.83 | 7320.79
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 7884.62 | 66.39 | 630.22 | 7254.4
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 7884.62 | 334.7 | 964.92 | 6919.7
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 7884.62 | 58.56 | 1023.48 | 6861.14
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 7884.62 | 442.6 | 1466.08 | 6418.54
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 7884.62 | 86.04 | 1552.12 | 6332.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 7884.62 | 762.9 | 2315.02 | 5569.6
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 7884.62 | 136.92 | 2451.94 | 5432.68
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 7884.62 | 1132.5 | 3584.44 | 4300.18
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 7884.62 | 33.55 | 3617.99 | 4266.63
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 7884.62 | 307.4 | 3925.39 | 3959.23
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 7884.62 | 20.56 | 3945.95 | 3938.67
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 7884.62 | 227 | 4172.95 | 3711.67
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 7884.62 | 167.04 | 4339.99 | 3544.63
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 7884.62 | 848.6 | 5188.59 | 2696.03
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 7884.62 | 46.91 | 5235.5 | 2649.12
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 7884.62 | 416.4 | 5651.9 | 2232.72
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 7884.62 | 80.66 | 5732.56 | 2152.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 7884.62 | 538.7 | 6271.26 | 1613.36
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 7884.62 | 104.57 | 6375.83 | 1508.79
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 7884.62 | 694.4 | 7070.23 | 814.39
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 7884.62 | 12.94 | 7083.17 | 801.45
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 7884.62 | 128.9 | 7212.07 | 672.55
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 7884.62 | 7.6 | 7219.67 | 664.95
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 7884.62 | 78.7 | 7298.37 | 586.25
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 7884.62 | 109.95 | 7408.32 | 476.3
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 7884.62 | 476.3 | 7884.62 | 0
[5 empty] | 7884.62 |  | 7884.62 | 0
|  |  | Totals: | 7884.62 |  | 7884.62 |  | 0
Note on E9: Jurgenson, John [DAS]: 9369.00 - HHS IMHI Plant Operations Bldg Window Replacement - MM22 $Joni Elliott, Jennie Mar 8, 2025, 12:10 PM (3 days ago) to me, Jennifer, Scott DAS Finance, Please reduce PM Time in 9369.00 - HHS IMHI Plant Operations Bldg Window Replacement to $7,298.37 in the Contracted Line. Then please close the project and return $7,802.60 in funds to the Total Unassigned/Unallocated line for MM22. Thank you, Jennie Elliott Owner's Representative, State Design & Construction

## #9369.00 Misc
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Jennie E. |  |  |  | Shipping Code: 556
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524138906 | 2024-05-17 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2573120 | 1596.25 | 1596.25
PRC 33524200905 | 2024-07-18 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV041444 | 478.88 | 2075.13
PRC 33525023910 | 2025-01-23 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010845-IN | 7677.1 | 9752.23
PRC 33525048907 | 2025-02-17 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010867-IN | 1446 | 11198.23
11198.23
11198.23
11198.23
11198.23
11198.23
11198.23
11198.23
11198.23
|  |  |  | Totals: |  | 11198.23

## #9369.00 Horizon Architecture
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  | Major Program 4B02
Horizon Architecture |  |  | Vendor:00003108847
Acct. Codes-0017-335-MM22-9260 |  |  | RFP936900-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524059900 | 2024-02-26 | PO Procore | 17985 | 17985 |  |  | 17985
PRC 3352405PA9900 | 2024-05-13 | Inv. 9369.00-01 |  | 17985 | 6920 | 6920 | 11065
PRC 3352405PB9900 | 2024-06-21 | Inv. 9369.00-02 |  | 17985 | 4620 | 11540 | 6445
PRC 3352405PC9900 | 2024-07-11 | Inv. 9369.00-03 |  | 17985 | 1035 | 12575 | 5410 | FY24
PO 33525059900 | 2024-07-19 | Roll to FY25 |  | 17985 |  | 12575 | 5410
PRC 3352505PD9900 | 2024-08-09 | Inv. 9369.00-04 |  | 17985 | 1035 | 13610 | 4375
PRC 3352505PE9900 | 2024-11-21 | Inv. 9369.00-05 |  | 17985 | 1531.25 | 15141.25 | 2843.75
PRC 3352505PF9900 | 2025-02-05 | Inv. 9369.00-06 - Final |  | 17985 | 2843.75 | 17985 | 0
|  |  |  | 17985 |  | 17985 | 0
|  |  |  | 17985 |  | 17985 | 0
|  |  |  | 17985 |  | 17985 | 0
|  |  |  | 17985 |  | 17985 | 0
|  |  |  | 17985 |  | 17985 | 0
|  | Totals: | 17985 |  | 17985 |  | 0 | Final
|  | Design Development | 6920 |  | 6920 |  | 0
|  | Construction Documents | 4620 |  | 4620 |  | 0
|  | Bidding Phase | 2070 |  | 2070 |  | 0
|  | Construction Phase | 4375 |  | 4375 |  | 0
|  | Total: | 17985 |  | 17985 |  | 0

## #9369.00 Timekey Enterprise
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  | Major Program 4B02
Timekey Enterprise |  |  | Vendor: 00003220172
Acct. Codes-0017-335-MM22-9255 |  |  | RFP936900-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525225901 | 2024-08-12 | PO Procore | 59932 | 59932 |  |  | 59932
PRC 3352522PA5901 | 2024-10-24 | Inv. 9369.00-01 |  | 59932 | 3480.64 | 3480.64 | 56451.36 | 183.19
PRC 3352522PB5901 | 2024-10-30 | Inv. 9369.00-02 |  | 59932 | 2531.15 | 6011.79 | 53920.21 | 316.41
PRC 3352522PC5901 | 2024-12-03 | Inv. 9369.00-03 |  | 59932 | 50354.26 | 56366.05 | 3565.95 | 2966.63
PO 33525225901 | 2024-12-06 | CO #1 | 411.4 | 60343.4 |  | 56366.05 | 3977.35
PRC 3352522PD5901 | 2024-12-20 | Inv. 9369.00-04 |  | 60343.4 | 960.18 | 57326.23 | 3017.17 | 3017.17
PRC 3352522PE5901 | 2025-01-13 | Inv. 9369.00-05 -Retainage |  | 60343.4 | 3017.17 | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  |  |  | 60343.4 |  | 60343.4 | 0
|  | Totals: | 60343.4 |  | 60343.4 |  | 0

## #9369.00 Samuels Group (2)
HHS IMHI Plant Operations Bldg Window Replacement
Project # 9369.00
Program code 936900 |  |  | Major Program 4B02
Samuels Group (2) |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525249913 | 2024-09-05 | PO Procore | 29842.1 | 29842.1 |  |  | 29842.1
PRC 3352524PA9913 | 2024-10-07 | Inv. 7717.519369 CA |  | 29842.1 | 2596.64 | 2596.64 | 27245.46
PRC 3352524PB9913 | 2024-11-06 | Inv. 7717.529369 CA |  | 29842.1 | 4811.26 | 7407.9 | 22434.2
PRC 3352524PC9913 | 2025-01-27 | Inv. 7717.539369 CA FINAL | -1006.74 | 28835.36 | 21427.46 | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  |  |  | 28835.36 |  | 28835.36 | 0
|  | Totals: | 28835.36 |  | 28835.36 |  | 0 | FINAL
|  | CM Services | 28340.41 |  | 28340.41 |  | 0
|  | Reimbursables | 494.95 |  | 494.95 |  | 0
|  | Total: | 28835.36 |  | 28835.36 |  | 0

## RECAP #9387.00
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
| Program code 938700 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM22
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 254000
C | Samuels Group |  | 18328.01 | 18328.01 | 0
| PM TIME |  | 19200 | 18030.24 | 1169.76
| Misc. |  | 661.35 | 661.35 | 0
| Watersmith Engineering LLC |  | 26612 | 25759.77 | 852.23
| Blue Top Excavating |  | 157016 | 136626.26 | 20389.74
| Samuels Group |  | 22430.67 | 16756.39 | 5674.28
| Total Project Cost | 254000 | 244248.03 | 216162.02 | 28086.01 | 9751.97

## #9387.00 Samuels Group
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524067901 | 2024-03-07 | PO Procore | 18660.12 | 18660.12 |  |  | 18660.12
PRC 3352406PA7901 | 2024-04-02 | Inv. 7677.01938700 |  | 18660.12 | 1029.22 | 1029.22 | 17630.9
PRC 3352406PB7901 | 2024-05-02 | Inv. 7677.02938700 |  | 18660.12 | 3432.73 | 4461.95 | 14198.17
PRC 3352406PC7901 | 2024-07-08 | Inv. 7677.03938700 |  | 18660.12 | 3395.34 | 7857.29 | 10802.83 | FY24
PO 33525067901 | 2024-07-19 | Roll to FY25 |  | 18660.12 |  | 7857.29 | 10802.83
PRC 3352506PD7901 | 2024-08-08 | Inv. 7677.04938700 |  | 18660.12 | 1447.86 | 9305.15 | 9354.97
PRC 3352506PE7901 | 2024-09-16 | Inv. 7677.05938700 |  | 18660.12 | 4461.08 | 13766.23 | 4893.89
PRC 3352506PF7901 | 2024-10-02 | Inv. 7677.06938700 |  | 18660.12 | 3064.22 | 16830.45 | 1829.67
PRC 3352506PG7901 | 2024-11-06 | Inv. 7677.07938700 PC FINAL | -332.11 | 18328.01 | 1497.56 | 18328.01 | -2.16e-12
|  |  |  | 18328.01 |  | 18328.01 | -2.16e-12
|  |  |  | 18328.01 |  | 18328.01 | -2.16e-12
|  |  |  | 18328.01 |  | 18328.01 | -2.16e-12
|  |  |  | 18328.01 |  | 18328.01 | -2.16e-12
|  | Totals: | 18328.01 |  | 18328.01 |  | 0 | FINAL
|  | CM Services | 17899.01 |  | 17899.01 |  | 0
|  | Reimbursables | 429 |  | 429 |  | 0
|  | Total: | 18328.01 |  | 18328.01 |  | 0

## #9387.00 PM TIME
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx |  |  |  | eDAS E2BK
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 19200 | 19200 |  |  | 19200
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 19200 | 84.26 | 84.26 | 19115.74
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 19200 | 424.8 | 509.06 | 18690.94
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 19200 | 311.4 | 820.46 | 18379.54
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 19200 | 2357.7 | 3178.16 | 16021.84
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 19200 | 183.52 | 3361.68 | 15838.32
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 19200 | 1629.1 | 4990.78 | 14209.22
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 19200 | 129.8 | 5120.58 | 14079.42
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 19200 | 1083.6 | 6204.18 | 12995.82
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 19200 | 148.26 | 6352.44 | 12847.56
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 19200 | 1356.3 | 7708.74 | 11491.26
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 19200 | 113.49 | 7822.23 | 11377.77
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 19200 | 1242 | 9064.23 | 10135.77
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 19200 | 348.45 | 9412.68 | 9787.32
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 19200 | 1772 | 11184.68 | 8015.32
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 19200 | 113.12 | 11297.8 | 7902.2
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 19200 | 1005.5 | 12303.3 | 6896.7
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 19200 | 283.16 | 12586.46 | 6613.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 19200 | 1888.1 | 14474.56 | 4725.44
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 19200 | 112.43 | 14586.99 | 4613.01
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 19200 | 746.3 | 15333.29 | 3866.71
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 19200 | 88.59 | 15421.88 | 3778.12
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 19200 | 885 | 16306.88 | 2893.12
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 19200 | 87.32 | 16394.2 | 2805.8
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 19200 | 934.2 | 17328.4 | 1871.6
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 19200 | 132.14 | 17460.54 | 1739.46
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 19200 | 569.7 | 18030.24 | 1169.76
[5 empty] | 19200 |  | 18030.24 | 1169.76
[5 empty] | 19200 |  | 18030.24 | 1169.76
[5 empty] | 19200 |  | 18030.24 | 1169.76
|  |  | Totals: | 19200 |  | 18030.24 |  | 1169.76
Note on E9: Jurgenson, John [DAS]: Adams, Brandon 9:07 AM (1 minute ago) to me Finance, Please set the follow PM budgets, 9387.00 - MM22 - DOC MPCF IPI Building Stormwater Management $9,000 9392.00 - MM24 - DOC ASP Admin Bldg Entry Porch Repairs $12,000 9396.00 - MM24 - DOC FDCF Generator, Switchgear-Master Controller Modification/Upgrade $8,000 Regards, Brandon Adams Re: PM Time Inbox Adams, Brandon 7:52 AM (52 minutes ago) to me Please increase PM Time budget $4,000 for 9387.00 in MM22. Regards, From: Adams, Brandon <brandon.adams@iowa.gov> Date: Tue, Nov 12, 2024 at 11:19 AM Subject: Re: October PM Time Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Please increase my PM Time on the following projects: DA24 9414.00 $5,000 DA24 9423.00 $5,000 MM22 9429.00 $2,000 MM22 9387.00 $4,000 MM23 9317.00 $4,000 Re: PM time Inbox Adams, Brandon 11:41 AM (35 minutes ago) to me Please increase my PM Time for the following projects: MM22 9367.00 - $2,000 MM22 9387.00 - $1,000 Regards, Re: PM Time for February has posted $Joni Adams, Brandon 10:50 AM (19 minutes ago) to me Finance, Please increase my PM as follows: DA24 9423.00 $9,500 MM22 9387.00 $1,200 MM23 9370.00 $3,000 MM25 9451.00 $5,000 Regards, Brandon Adams

## #9387.00 Misc
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - Brandon A. |  |  |  | Shipping Code 171
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 165 | 165
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -165 | 0
PRC 33525255906 | 2024-09-11 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV042591 | 326.46 | 326.46
PRC 33525292901 | 2024-10-18 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV043644 | 334.89 | 661.35
661.35
661.35
|  |  |  | Totals: |  | 661.35

## #9387.00 Watersmith Engineering
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  | Major Program 4E01
Watersmith Engineering LLC |  |  | Vendor: VS000000493
Acct. Codes-0017-335-MM22-9260 |  |  | RFP938700-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524108802 | 2024-04-17 | PO Procore | 21592 | 21592 |  |  | 21592
PRC 3352410PA8802 | 2024-05-15 | Inv. 1270201 |  | 21592 | 4634 | 4634 | 16958
PRC 3352410PB8802 | 2024-06-17 | Inv. 1270202 |  | 21592 | 4476 | 9110 | 12482
PO 33524108802 | 2024-06-19 | CO #1 | 5020 | 26612 |  | 9110 | 17502
PRC 3352410PC8802 | 2024-07-03 | Inv. 1270203 |  | 26612 | 5020 | 14130 | 12482 | FY24
PO 33525108802 | 2024-07-19 | Roll to FY25 |  | 26612 |  | 14130 | 12482
PRC 3352510PD8802 | 2024-08-07 | Inv. 1270204 |  | 26612 | 4814 | 18944 | 7668
PRC 3352510PE8802 | 2024-09-12 | Inv. 1270205 |  | 26612 | 1420 | 20364 | 6248
PRC 3352510PF8802 | 2024-10-14 | Inv. 1270206 |  | 26612 | 567.94 | 20931.94 | 5680.06
PRC 3352510PG8802 | 2024-11-07 | Inv. 1270207 |  | 26612 | 639.17 | 21571.11 | 5040.89
PRC 3352510PH8802 | 2024-12-03 | Inv. 1270208 |  | 26612 | 319.9 | 21891.01 | 4720.99
PRC 3352510PI8802 | 2025-01-09 | Inv. 9387.00-09 |  | 26612 | 3016.54 | 24907.55 | 1704.45
PRC 3352510PJ8802 | 2025-03-14 | Inv. 9387.00-10 |  | 26612 | 852.22 | 25759.77 | 852.23
|  |  |  | 26612 |  | 25759.77 | 852.23
|  |  |  | 26612 |  | 25759.77 | 852.23
|  | Totals: | 26612 |  | 25759.77 |  | 852.23

## #9387.00 Blue Top Excavating
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  | Major Program 4E01
Blue Top Excavating |  |  | Vendor: 000003196535
Acct. Codes-0017-335-MM22-9255 |  |  | RFP938700-02
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525297901 | 2024-10-22 | PO Procore | 151540 | 151540 |  |  | 151540
PRC 3352529PA7901 | 2025-01-15 | Inv. 9387.00-01 |  | 151540 | 136626.26 | 136626.26 | 14913.74 | 7190.88
PO 33525297901 | 2025-01-24 | CO #1 | 5476 | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  |  |  | 157016 |  | 136626.26 | 20389.74
|  | Totals: | 157016 |  | 136626.26 |  | 20389.74

## #9387.00 Samuels Group(2)
DOC ASP LUC Plumbing Repairs Phase 1
Project # 9387.00
Program code 938700 |  |  | Major Program 4E01
Samuels Group (2) |  |  | Vendor: 000003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298903 | 2024-10-22 | PO Procore | 22430.67 | 22430.67 |  |  | 22430.67
PRC 3352529PA8903 | 2024-12-06 | Inv. 9387.01 CA |  | 22430.67 | 3399.68 | 3399.68 | 19030.99
PRC 3352529PB8903 | 2025-01-06 | Inv. 9387.02 CA |  | 22430.67 | 7355.01 | 10754.69 | 11675.98
PRC 3352529PC8903 | 2025-02-06 | Inv. 9387.03 CA |  | 22430.67 | 3940.21 | 14694.9 | 7735.77
PRC 3352529PD8903 | 2025-03-05 | Inv. 9387.04 CA |  | 22430.67 | 2061.49 | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  |  |  | 22430.67 |  | 16756.39 | 5674.28
|  | Totals: | 22430.67 |  | 16756.39 |  | 5674.28
|  | CM Services | 19330.67 |  | 15953.52 |  | 3377.15
|  | Reimbursables | 3100 |  | 802.87 |  | 2297.13
|  | Total: | 22430.67 |  | 16756.39 |  | 5674.28

## RECAP #9407.00
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
| Program code 940700 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 65442.13
| DCI Group |  | 19474.63 | 16651.74 | 2822.89
| PM TIME |  | 11000 | 8633.47 | 2366.53
| Misc. |  | 37.5 | 37.5 | 0
| MA Architecture |  | 24980 | 24302.5 | 677.5
C | Allender Butzke Engineers |  | 2950 | 2950 | 0
| Total Project Cost | 65442.13 | 58442.13 | 52575.21 | 5866.92 | 7000

## #9407.00 DCI Group
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
Program code 940700 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524110900 | 2024-04-19 | PO Procore | 12474.63 | 12474.63 |  |  | 12474.63
PRC 3352411PA0900 | 2024-06-11 | Inv. 9407.00-01 |  | 12474.63 | 1732.97 | 1732.97 | 10741.66
PRC 3352411PB0900 | 2024-06-20 | Inv. 24-010 PC 02 |  | 12474.63 | 2273.14 | 4006.11 | 8468.52
PO 33524110900 | 2024-07-10 | CO #1 | 5000 | 17474.63 |  | 4006.11 | 13468.52
PRC 3352411PC0900 | 2024-07-19 | Inv. 24-010 PC 03 |  | 17474.63 | 1217.75 | 5223.86 | 12250.77 | FY24
PO 33525110900 | 2024-07-22 | Roll to FY25 |  | 17474.63 |  | 5223.86 | 12250.77
PO 33525110900 | 2024-08-06 | CO #2 | 2000 | 19474.63 |  | 5223.86 | 14250.77
PRC 3352511PD0900 | 2024-08-15 | Inv. 24-010 PC 04 |  | 19474.63 | 7392.92 | 12616.78 | 6857.85
PRC 3352511PE0900 | 2024-09-30 | Inv. 24-010 PC 05 |  | 19474.63 | 2704.96 | 15321.74 | 4152.89
PRC 3352511PF0900 | 2024-12-03 | Inv. 24-010 PC 06 |  | 19474.63 | 1330 | 16651.74 | 2822.89
|  |  |  | 19474.63 |  | 16651.74 | 2822.89
|  |  |  | 19474.63 |  | 16651.74 | 2822.89
|  |  |  | 19474.63 |  | 16651.74 | 2822.89
|  | Totals: | 19474.63 |  | 16651.74 |  | 2822.89

## #9407.00 PM TIME
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
Program code 940700 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11000 | 11000 |  |  | 11000
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 11000 | 102.65 | 102.65 | 10897.35
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 11000 | 912.1 | 1014.75 | 9985.25
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 11000 | 163.17 | 1177.92 | 9822.08
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 11000 | 1350.5 | 2528.42 | 8471.58
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 11000 | 101.07 | 2629.49 | 8370.51
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 11000 | 924.4 | 3553.89 | 7446.11
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 11000 | 134.75 | 3688.64 | 7311.36
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 11000 | 1469 | 5157.64 | 5842.36
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 11000 | 271.55 | 5429.19 | 5570.81
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 11000 | 1384.3 | 6813.49 | 4186.51
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 11000 | 69.03 | 6882.52 | 4117.48
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 11000 | 614.2 | 7496.72 | 3503.28
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 11000 | 148.25 | 7644.97 | 3355.03
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 11000 | 988.5 | 8633.47 | 2366.53
[5 empty] | 11000 |  | 8633.47 | 2366.53
[5 empty] | 11000 |  | 8633.47 | 2366.53
[5 empty] | 11000 |  | 8633.47 | 2366.53
[5 empty] | 11000 |  | 8633.47 | 2366.53
[5 empty] | 11000 |  | 8633.47 | 2366.53
|  |  | Totals: | 11000 |  | 8633.47 |  | 2366.53
Note on E9: Jurgenson, John [DAS]: Re: PM TIme $John Trower, James May 8, 2024, 4:35 PM (15 hours ago) to me Finance - See below modifications in RED. On Wed, May 8, 2024 at 11:20 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James Can you please review the following projects to see if the budget can be increases to allow us to post the April PM time? 9338.00 in DA23 Amount is $155.51 Increase the PM Time by $3,000. 9375.00 in DA24 Amount is $2337.65 Increase the PM Time by $14,000 9342.00 in MM21 Amount is $1042.99 Increase the PM Time by $1,042.99 9407.00 in MM22 Amount is $1014.75 Set up $8,000 in PM Time 9305.00 in MM23 Amount is $631.96 A previous email was sent on 5/8/24 stating to increase the PM Time by $20,000. Please see below: On Tue, Nov 12, 2024 at 7:19 AM Huggins, Joni <joni.huggins@iowa.gov> wrote: DA23 9344.00 (1407.82) Increase PM Time by $4,000 DA24 9412.00 (795.82) Increase PM Time by $2,000 MM22 9364.00 (650.47) Increase PM Time by $650.47 MM22 9407.00 (633.47) Increase PM Time by $3,000

## #9407.00 Misc
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
Program code 940700 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524166910 | 2024-06-13 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV038673 | 37.5 | 37.5
37.5
37.5
37.5
37.5
37.5
37.5
37.5
37.5
37.5
37.5
37.5
|  |  |  | Totals: |  | 37.5

## #9407.00 MA Architecture
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
Program code 940700 |  |  | Major Program 4D04
MA Architecture |  |  | Vendor: 00003166868
Acct. Codes-0017-335-MM22-9260 |  |  | TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524134903 | 2024-05-13 | PO Procore | 24180 | 24180 |  |  | 24180
PRC 3352413PA4903 | 2024-06-24 | Inv. 2435 |  | 24180 | 5615 | 5615 | 18565 | FY24
PO 33525134903 | 2024-07-23 | Roll to FY25 |  | 24180 |  | 5615 | 18565
PO 33525134903 | 2024-08-19 | CO #1 | 800 | 24980 |  | 5615 | 19365
PRC 3352513PB4903 | 2024-08-20 | Inv. 2436 |  | 24980 | 8992.5 | 14607.5 | 10372.5
PRC 3352513PC4903 | 2024-09-19 | Inv. 2437 |  | 24980 | 2577.5 | 17185 | 7795
PRC 3352513PD4903 | 2024-11-08 | Inv. 2438 |  | 24980 | 1697.5 | 18882.5 | 6097.5
PRC 3352513PE4903 | 2025-01-14 | Inv. 2439 |  | 24980 | 5420 | 24302.5 | 677.5
|  |  |  | 24980 |  | 24302.5 | 677.5
|  |  |  | 24980 |  | 24302.5 | 677.5
|  |  |  | 24980 |  | 24302.5 | 677.5
|  |  |  | 24980 |  | 24302.5 | 677.5
|  |  |  | 24980 |  | 24302.5 | 677.5
|  | Totals: | 24980 |  | 24302.5 |  | 677.5
|  | Survey | 2000 |  | 2000 |  | 0
|  | 100% DD | 4615 |  | 4615 |  | 0
|  | 50% CD | 4615 |  | 4615 |  | 0
|  | 100% CD | 5155 |  | 5155 |  | 0
|  | Bidding | 1020 |  | 1020 |  | 0
|  | Construction Admin | 6775 |  | 6097.5 |  | 677.5
|  | CO#1 | 800 |  | 800 |  | 0
|  | Total | 24980 |  | 24302.5 |  | 677.5

## #9407.00 Allender Butzke
DAS TH Carriage House Exterior Stair Replacement
Project # 9407.00
Program code 940700 |  |  | Major Program 4D04
Allender Butzke Engineers |  |  | Vendor: 00002119950
Acct. Codes-0017-335-MM22-9260 |  |  | SRVV5
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524156903 | 2024-06-01 | PO Procore | 2950 | 2950 |  |  | 2950
PRC 3352415PA6903 | 2024-07-08 | Inv. 241221A |  | 2950 | 2950 | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  |  |  | 2950 |  | 2950 | 0
|  | Totals: | 2950 |  | 2950 |  | 0

## RECAP #9420.00
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
| Program code 942000 |  |  | Major Program 4D01
Recap
Acct. Codes-0017-335-MM22
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 130614.31
C | Samuels Group |  | 20609.69 | 20609.69 | 0
C | PM TIME |  | 6774.12 | 6774.12 | 0
C | Misc. |  | 3434.5 | 3434.5 | 0
C | OPN Architects |  | 99796 | 99796 | 0
| Total Project Cost | 130614.31 | 130614.31 | 130614.31 | 0 | 0
Closed 02/18/25

## #9420.00 Samuels Group
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM22-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524156905 | 2024-06-04 | PO Procore | 21692 | 21692 |  |  | 21692 | FY24
PO 33525156905 | 2024-07-23 | Roll to FY25 |  | 21692 |  | 0 | 21692
PRC 3352515PA6905 | 2024-08-08 | Inv. 7698.01940200 |  | 21692 | 5072.72 | 5072.72 | 16619.28
PRC 3352515PB6905 | 2024-09-11 | Inv. 7698.02940200 |  | 21692 | 934.28 | 6007 | 15685
PRC 3352515PC6905 | 2024-10-04 | Inv. 7698.03940200 |  | 21692 | 3374.99 | 9381.99 | 12310.01
PRC 3352515PD6905 | 2024-11-12 | Inv. 7698.04940200 |  | 21692 | 1907.14 | 11289.13 | 10402.87
PRC 3352515PE6905 | 2024-12-05 | Inv. 7698.05942000-FINAL | -1082.31 | 20609.69 | 9320.56 | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  |  |  | 20609.69 |  | 20609.69 | 0
|  | Totals: | 20609.69 |  | 20609.69 |  | 0 | FINAL
|  | CM Services | 20609.69 |  | 20609.69 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 20609.69 |  | 20609.69 |  | 0

## #9420.00 PM TIME
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  |  | Major Program 4D01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T. |  |  |  | eDAS E2DF
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 6774.12 | 6774.12 |  |  | 6774.12
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 6774.12 | 247.34 | 247.34 | 6526.78
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 6774.12 | 2047.6 | 2294.94 | 4479.18
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 6774.12 | 441.98 | 2736.92 | 4037.2
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 6774.12 | 4037.2 | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
[5 empty] | 6774.12 |  | 6774.12 | 0
|  |  | Totals: | 6774.12 |  | 6774.12 |  | 0
Note on E9: Jurgenson, John [DAS]: On Thu, May 16, 2024 at 9:10 AM Trower, James <james.trower@iowa.gov> wrote: Finance - Please set up the below project in MM22 funding and send a job number to me: XXXX.XX - DAS CC Capitol West Stairs & Surrounding Landings Repairs Total project budget for preconstruction: $60,000 PM Time: $6,000 (please add this project to my billables) The Samuels Group will be the CM. Thanks, James Trower 9420.00 - DAS CC Capitol West Stairs & Surrounding Landings Repairs $Joni Trower, James Jun 13, 2024, 4:53 PM (14 hours ago) to me Finance - Please increase the MM22 budget by $75,000. Increase PM Time by $6,000. Thanks, James Trower, Licensed Architect, LEED AP

## #9420.00 Misc
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  |  | Major Program 4D01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524166909 | 2024-06-14 | 9500 | CNST | Neumann Brothers V#(00002106354) | Inv. 56253 | 3434.5 | 3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
3434.5
|  |  |  | Totals: |  | 3434.5

## #9420.00 OPN Architects
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM22-9260 |  |  | 930500-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524166913 | 2024-06-14 | PO Procore | 92280 | 92280 |  |  | 92280
PRC 3352416PA6913 | 2024-07-05 | Inv. 19802016-1 |  | 92280 | 37111.1 | 37111.1 | 55168.9 | FY24
PO 33525166913 | 2024-07-23 | Roll to FY25 |  | 92280 |  | 37111.1 | 55168.9
PRC 3352516PB6913 | 2024-08-13 | Inv. 19802016-2 |  | 92280 | 18918.9 | 56030 | 36250
PO 33525166913 | 2024-08-29 | CO #1 | 18720 | 111000 |  | 56030 | 54970
PRC 3352516PC6913 | 2024-09-11 | Inv. 19802016-3 |  | 111000 | 3192 | 59222 | 51778
PRC 3352516PD6913 | 2024-10-10 | Inv. 19802016-4 |  | 111000 | 9215.4 | 68437.4 | 42562.6
PRC 3352516PE6913 | 2024-11-12 | Inv. 19802016-5 |  | 111000 | 9647.65 | 78085.05 | 32914.95
PRC 3352516PF6913 | 2024-12-16 | Inv. 19802016-6 - FINAL | -11204 | 99796 | 21710.95 | 99796 | 0
|  |  |  | 99796 |  | 99796 | 0
|  |  |  | 99796 |  | 99796 | 0
|  |  |  | 99796 |  | 99796 | 0
|  |  |  | 99796 |  | 99796 | 0
|  | Totals: | 99796 |  | 99796 |  | 0
|  | DD | 29960 |  | 29960 |  | 0
|  | CD | 21670 |  | 21670 |  | 0
|  | BD | 4400 |  | 4400 |  | 0
|  | CA | 21546 |  | 21546 |  | 0
|  | Structural Consultant | 0 |  |  |  | 0
|  | Civil Consultant | 3500 |  | 3500 |  | 0
|  | Soil Bearings | 0 |  |  |  | 0
|  | CO #1 | 18720 |  | 18720 |  | 0
|  | Total: | 99796 |  | 99796 |  | 0

## #9997.24 PM TIME Error
Project Management Time
PM time 9997.24
Program Code 999724 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - NA
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
CDE 33524220800 | 45145 | 2507 | Finance Support for July 1-31, 2023 |  | 0 | 563.52 | 563.52 | -563.52
CDE 33524220800 | 45145 | 9500 | Finance Support for July 1-31, 2023 |  | 0 | 1086 | 1649.52 | -1649.52
CDE 33524220808 | 45145 | 2507 | Finance Support for July 1-31, 2023 |  | 0 | -563.52 | 1086 | -1086
CDE 33524220808 | 45145 | 9500 | Finance Support for July 1-31, 2023 |  | 0 | -1086 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: 9997.22 Closing Inbox Gustafson, Scott 2:40 PM (13 minutes ago) to me Joni, Yes, please move Emily's August time to 9997.23, close 9997.22 and return any unused funds to MM22. Respectfully, Scott Scott Gustafson, AIA, CPM, NCARB, CxA+BE Bureau Chief, State Design & Construction Resources Bureau Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1213 ¦ Mobile: 515-490-9555 scott.gustafson@iowa.gov https://das.iowa.gov On Tue, Aug 9, 2022 at 2:14 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good afternoon Scott, We need to close down 9997.22. Emily has time recorded in 8/1, 8/2 & 8/3. I believe this should be in 9997.23. 1) May I move Emily's time to 9997.23? 2) May I close 9997.22 and move the funds to MM22 pool? Thank you ~Joni

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM22
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #xxxx.xx Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #xxxx.xx PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM22-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #xxxx.xx Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM22-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0