## Language
Approp R52, final reversion FY2024 - 2018 Ia Acts, ch 1162, sec 1.1; 2020 Ia Acts, ch 1120, sec 7

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 20000000
|  | Additional Funds | 794591.12
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 20794591.12
| . | Less: Total Assigned |  | 20642456.1
|  | Total Unassigned / Unallocated |  | 152135.02
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
|  | Funds Received |  |  | 559509.58
C | 9997.23 | Project Management Time | Scott G | 129424.94 | 0 | 129424.94 | 129424.94 | 129424.94 | 0 | 0
C | 9224.00 | DOC MPCF Elevator B C & D Replacements | Brandon A | 877991.08 | 0 | 877991.08 | 877991.08 | 877991.08 | 0 | 0
C | 9249.00 | DOC MPCF Front Steps Repair | James T | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9250.00 | DOC MPCF Building 18 Roof Replacement | Brandon A | 1145000 | 0 | 1145000 | 1100115.19 | 968151.75 | 131963.44 | 44884.81 | 0.17
C | 9253.00 | DOC FDCF Floyd and Bldg K Units Roof Replacements | Jennifer K | 777382.24 | 0 | 777382.24 | 777382.24 | 777382.24 | 0 | 0
C | 9255.00 | DOC NCF Building K (Admin) and CRC Boiler and Dorms 1 &2 Roof Replacement | Brad T | 608883.56 | 0 | 608883.56 | 608883.56 | 608883.56 | 0 | 0
| 9268.01 | DAS CC Tunnel System Infiltration Mitigation | Jennifer K | 815000 | 0 | 815000 | 810217.85 | 675577.75 | 134640.1 | 4782.15 | 1003.34
C | 9270.00 | DOC ASP Tuckpointing Priority 4 | Jennie E | 776497.58 | 0 | 776497.58 | 776497.58 | 776497.58 | 0 | 0
C | 9276.00 | DPS P12 Driveway Repairs | James T | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9279.20 | DHS WRC Campus Utility Decentralization Phase 2 | Jennifer K | 2705000 | 0 | 2705000 | 2694933.51 | 2544120.12 | 150813.39 | 10066.49 | 1083.07
| 9294.00 | DHS WRC Fire Alarm System Replacement Phase 1 | Jennifer K | 1107615.79 | 0 | 1107615.79 | 1107423.87 | 984180.31 | 123243.56 | 191.92 | 1863.94
| 9294.01 | DHS WRC Fire Alarm System Replacement Phase 2 | Jennifer K | 700000 | 0 | 700000 | 680901.88 | 486541.59 | 194360.29 | 19098.12 | 3939.25
| 9304.00 | DAS CC Parking Ramp Concrete and Piping Repair | James T | 1012876.59 | 0 | 1012876.59 | 1006043.76 | 976846.92 | 29196.84 | 6832.83 | 2240.78
| 9305.00 | DAS CC Capitol North and South Stair Repair | James T | 1793919.79 | 0 | 1793919.79 | 1758196.46 | 1531903.79 | 226292.67 | 35723.33 | 2869.53
| 9306.00 | DOC CCF Metal Roof Replacement Design | Brad T | 99231.92 | 0 | 99231.92 | 98815.68 | 89071.68 | 9744 | 416.24
| 9307.00 | DHS IMHI Generator System Control Replacement | Jennie E | 300925.82 | 0 | 300925.82 | 248933.77 | 231430.33 | 17503.44 | 51992.05 | 5418.01
C | 9308.00 | DOC NCCF Generator System Control Replacement | James T | 200115.49 | 0 | 200115.49 | 200115.49 | 200115.49 | 0 | 0 | 0
C | 9309.00 | DOC ASP Gym Roof Replacement | Jennie E | 284190.05 | 0 | 284190.05 | 284190.05 | 284190.05 | 0 | 0
C | 9310.00 | DVA IVH Sheeler Clinical Roof Replacement | Brad T | 502324.07 | 0 | 502324.07 | 502324.07 | 502324.07 | 0 | 0
C | 9317.00 | DOC MPCF Interlock and Corridor Door Replacement | Brandon A | 990196.82 | 0 | 990196.82 | 990196.82 | 990196.82 | 0 | 0 | 0
C | 9319.00 | DOC NCF Building H (Main Server) and Master Control HVAC Replacement | Brad T | 496102.69 | 0 | 496102.69 | 496102.69 | 496102.69 | 0 | 0
C | 9320.00 | DOC NCCF Powerhouse Window Replacement | James T | 124991.55 | 0 | 124991.55 | 124991.55 | 124991.55 | 0 | 0
C | 9321.00 | DVA IVH North Parking Lot Replacement | Brad T | 629026.44 | 0 | 629026.44 | 629026.44 | 629026.44 | 0 | 0
C | 9322.00 | DHS IMHI Reynolds Building Partial Roof Replacement | Jennie E | 1023889.75 | 0 | 1023889.75 | 1023889.75 | 1023889.75 | 0 | 0
C | 9324.00 | DOC NCF Generator Switchgear Controls Replacement | Brad T | 254346.33 | 0 | 254346.33 | 254346.33 | 254346.33 | 0 | 0
C | 9327.00 | DOC IMCC East/West Living Unit Roof Replacement and Soffit Repair | Jennifer K | 5997.36 | 0 | 5997.36 | 5997.36 | 5997.36 | 0 | 0
C | 9330.00 | DAS CC Jessie Parker Elevator Code Update | Brad T | 58503.51 | 0 | 58503.51 | 58503.51 | 58503.51 | 0 | 0
C | 9331.00 | DOC FDCF Unit H Laundry Unit Tank Replacement (29C20) | Jennifer K | 0 | 112135.86 | 112135.86 | 112135.86 | 112135.86 | 0 | 0
C | 9332.00 | DOC FDCF Unit A Domestic Water Heater Replacement (29C20) | Jennifer K | 0 | 122417.55 | 122417.55 | 122417.55 | 122417.55 | 0 | 0
C | 9339.00 | DOC IMCC Grease Trap Replacement | Jennifer K | 134585.17 | 0 | 134585.17 | 134585.17 | 134585.17 | 0 | 0
| 9370.00 | DOC ISP Perimeter Fence Deterrent System Replacement | Brandon A | 400000 | 528.13 | 400528.13 | 391957.17 | 61040.11 | 330917.06 | 8570.96 | 1836
| 9371.00 | DPS Post 3 Parking Lot Replacement | Jennie E. | 145000 | 0 | 145000 | 81088.07 | 62761.01 | 18327.06 | 63911.93 | 8141.06
| 9373.00 | DAS TH Terrace Rd Retaining Wall Repairs | James T | 375000 | 0 | 375000 | 350187.6 | 256309.42 | 93878.18 | 24812.4 | 2067.95
| 9388.00 | DPS P08 Water Infiltration Mitigation | Jennie E. | 134500 | 0 | 134500 | 70913.21 | 42032.52 | 28880.69 | 63586.79 | 1418.36
| 9389.00 | DOC 2JD BCRC ERV Replacement | Brad T. | 281385.78 | 0 | 281385.78 | 255984.68 | 92953.85 | 163030.83 | 25401.1 | 4433.57
| 9404.00 | DOC NCF CRC Boiler Replacements | Brad T. | 771024.24 | 0 | 771024.24 | 619618.87 | 30578.5 | 589040.37 | 151405.37 | 14528.96
| 9437.00 | DAS CC Lot 21 Repairs Phase 3 | Brad T | 146446 | 0 | 146446 | 71596.02 | 3871.16 | 67724.86 | 74849.98 | 9128.84
| 9438.00 | DOC FDCF Warehouse Loading Dock Ramp Repairs | Jennifer K | 120000 | 0 | 120000 | 30480.54 | 5922.96 | 24557.58 | 89519.46 | 2100.82
| 9439.00 | DOC FDCF Unit K Pre-Cast Sealant Replacement | Jennifer K | 100000 | 0 | 100000 | 28895.54 | 5924.83 | 22970.71 | 71104.46 | 1979.41
| 9450.00 | DOC MPFC North Parkig Lot Replacement | Brandon A. | 370000 | 0 | 370000 | 57329.84 | 5143.84 | 52186 | 312670.16 | 6114.92
| 9465.00 | DAS TMVC Floor Slab Repair Evaluation | Brandon A. | 10000 | 0 | 10000 | 3500 | 114.57 | 3385.43 | 6500 | 1385.43
|  | Major Maintenance Totals |  | 20407374.56 | 794591.12 | 20642456.1 | 19576135.55 | 17163479.05 | 2412656.5 | 1066320.55
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 152135.02
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 1218455.57
[6 empty] | Total funds Available |  |  | 20794591.12
[6 empty] | Total obligated by contract or PO |  |  | -19576135.55 | 1218455.57
[6 empty] | Variance |  |  |  | 0
Note on E16: Huggins, Joni [DAS]: Re: 9224.00 PM Time $Joni Adams, Brandon 1:19 PM (1 minute ago) to me Yes, Please close. Regards, Brandon Adams On Mon, Jul 1, 2024 at 3:44 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Finance, Once project 9099.00 has been closed out in MM21 per the previous email, please create project 9224.00 in MM21 for $938,917.32. Please then move the following expenses from 9224.00 in MM23 to 9244.00 in MM21. $783,288.22 (Schumacher Elevator) $140,009.79 (Esco Electric) $15,619.31 (Total Construction) Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau
Note on E17: Jurgenson, John [DAS]: 9249.00 - DOC MPCF Front Steps Repair Inbox Trower, James 12:50 PM (0 minutes ago) to me Finance - Please make the following changes to project 9249.00: 1. Return $300,000 in MM23 funding to the MM23 pool fund. 2. Increase the MM22 funding by $310,000.
Note on E18: Huggins, Joni [DAS]: Trower, James 11:36 AM (1 hour ago) to me Finance - Please see the below modifications for project 9250.00: MM22: Reduce PM Time by 5,755.92 Return $50,000 to the MM22 pool fund MM23: Increase project budget by $145,000 Thanks,
Note on E19: Huggins, Joni [DAS]: Changes to MM23 Project 9253.00 $Joni Kleene, Jennifer 11:48 AM (3 minutes ago) to me, Scott We have changed the scope of this project. In the title, would you please replace "Grove" with "Bldg K" and reduce the overall budget by $266,000.00? Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov MM23 9253.00 Budget Change Inbox Kleene, Jennifer 3:10 PM (0 minutes ago) to me, Scott Please decrease the overall budget for MM23 9253.00 by $90,000.00. Regards, Jennife MM23 9253.00 Budget Decrease $Joni Kleene, Jennifer 7:27 AM (29 minutes ago) to me, Scott Please reduce the budget for project 9253.00 (DOC FDCF Floyd and Bldg K Units Roof Replacements) by $80,000.00. Regards, Jennifer Jennifer Kleene
Note on E20: Huggins, Joni [DAS]: Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K Re: DOC NCF BLDG K (Admin) and CRC Boiler and Dorms 1&2 Roof Replacement: Action Required for Subcontractor Invoice #1: State of Iowa - Department of Administrative Services $John Tonyan, Brad 2:50 PM (6 minutes ago) to me, John John, I have adjusted the PM time as my sheet where I track I had 0 hours for 9255.00 in January but I put it in the wrong line on the DAS billables sheet as I was one line low so have adjusted it correctly. Project PM time and overall can be closed. Thank you and good catch on my line error.
Note on E21: Jurgenson, John [DAS]: MM23 9268.01 Additional Funding Inbox Kleene, Jennifer 12:34 PM (34 minutes ago) to me, Scott Please increase the budget for MM23 9268.01 by $200,000.00. Regards, Jennifer Re: MM23 9268.01 Iowa Contracting CO #1 $Joni Kleene, Jennifer 8:36 AM (5 minutes ago) to me Sorry about that! Please increase the budget for MM23 9268.01 by $15,000.00. Regards, Jennifer
Note on E22: Huggins, Joni [DAS]: 9270.00 - DOC ASP Tuckpointing - Closeout $Joni Elliott, Jennie Dec 8, 2024, 11:29 AM (21 hours ago) to me, Scott Please reduce PM time in 9270.00 to $4,457.96 and Close Out the project. This should return $23.809.35 to the Total Unassigned/Unallocated line in MM23. Thank you, Jennie Elliott
Note on E23: Huggins, Joni [DAS]: Funding Transfers $Joni Trower, James Dec 22, 2022, 1:45 PM (6 days ago) to me Finance - 9276.00 - DPS P12 Driveway Repairs Transfer $200,000 in MM22 funds from project 9276.00 - DPS P12 Driveway Repairs to the MM22 pool fund. Set up MM23 funds in the amount of $700,000 from the MM23 pool fund. 9275.00 - DPS P12 Window Replacement Increase MM22 funds by $125,000 from the MM22 pool fund. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James Mar 10, 2023, 4:39 PM (3 days ago) to me Finance - See below changes for project 9276.00 - DPS P12 Driveway Repairs: 1. Return $700,000 in MM23 funding to the MM23 pool fund (this funding source can be closed for project 9276.00). 2. Set up $470,000 in MM21 funding 3. Return $53,000 in MM22 funding to the MM22 pool fund. Thanks,
Note on E24: Jurgenson, John [DAS]: MM23 9279.20 Changes $John Kleene, Jennifer 12:41 PM (10 minutes ago) to me, Scott Please increase the PM Time budget by $9,000.00 and decrease the overall budget by $320,000.00. This decrease offsets the amount allocated in MM22 for Phase 3 preconstruction activities, which has already been set-up. The original intent for the Phase 2 $3,400,000 was to be split between 9279.20 construction phase and 9279.30 preconstruction phase. Regards, Jennifer
Note on E25: Jurgenson, John [DAS]: MM23 9294.00 Budget Change $John Kleene, Jennifer 3:21 PM (0 minutes ago) to me, Scott Please decrease the overall budget by $100,000.00. This decrease in MM23 9294.00 offsets the amount allocated in MM21 for Phase 2 preconstruction activities, which has already been set-up. The original intent for the Phase 1 $1,251,616 was to be split between 9294.00 and 9294.01 preconstruction phase. Regards, Jennifer Budget Decrease for MM23 9294.00 WRC Fire Alarm Phase 1 $Joni Kleene, Jennifer 9:59 AM (31 minutes ago) to me, Scott Please decrease the budget by $65,000.00. Regards, Jennifer MM23 9294.00 Budget Increase $Joni Kleene, Jennifer 8:21 AM (1 hour ago) to me, Scott Please increase the budget for MM23 9294.00 by $15,000.00. Regards, Jennifer Jennifer Kleene MM23 9294.00 Budget Changes $Joni Kleene, Jennifer 11:58 AM (2 minutes ago) to me, Scott Please reduce the PM Time budget by $2,000 and then increase the total budget for MM23 9294.00 by $5,000.00. Regards, Jennifer
Note on E27: Huggins, Joni [DAS]: 9304.00 - DAS CC Parking Ramp Concrete and Piping Repair - Budget Increase Inbox Trower, James Wed, Jun 14, 4:37 PM (14 hours ago) to me, Scott, Jennifer Finance - Please increase MM23 funding for project 9304.00 by $302,000.00. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov
Note on E28: Huggins, Joni [DAS]: Project Funding Modifications $Joni Trower, James 6:42 AM (1 hour ago) to me, Jennifer, Scott Finance - Please transfer $205,000 in MM23 funds from project 9320.00 - DOC NCCF Powerhouse Window Replacement to the MM23 pool fund. Please keep this project open. Please transfer $168,646.76 in MM23 funds from project 9305.00 - DAS CC Capitol South Stair Repair to the MM23 pool fund. If you have any questions, please call me at 515-380-8049. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov 9305.00 - DAS CC Capitol North and South Stairs Repair Inbox Trower, James 4:17 PM (3 minutes ago) to me, Scott, Jennifer Finance - Please increase MM23 funding for project 9305.00 by $1,181,000.00. Thanks, 9305.00 - DAS CC Capitol North and South Stair Repair $Joni Trower, James Tue, Jul 9, 4:22 PM (14 hours ago) to me Finance - Please increase the MM23 budget for project 9305.00 by $100,000. Thanks, James Trower, Licensed Architect, LEED AP Re: 9305.00 - Neumann Brothers, Inc. - Change Order #002 $Joni Trower, James Wed, Sep 11, 5:39 PM (14 hours ago) to me Finance - Please increase the MM23 budget for project 9305.00 by $50,000. Thanks, James Re: 9373.00 - DAS TH Terrace Road Retaining Wall Repairs - Funding $Joni Trower, James 11:39 AM (5 minutes ago) to me Finance - Disregard the previous email. See below items: Please increase MM23 funding by $25,000 to Project 9373.00. Please increase MM23 funding by $25,000 to Project 9305.00. Thanks, James Trower, Licensed Architect, LEED AP 9305.00 - DAS CC Capitol North and South Stairs Repair - Increase Funding $Joni Trower, James Fri, Oct 11, 5:07 PM (3 days ago) to me Finance - Please increase MM23 funding for project 9305.00 by $85,000. Thanks, James Trower, Licensed Architect, LEED AP
Note on E29: Huggins, Joni [DAS]: MM23: 9306.00 - Decrease overall budget by $145,000 and give back to general org. fund MM23 9310.00 - Increase PM Time by $5K 9319.00 - Increase PM Time by $5K 9330.00 - Increase PM time as needed to pay January PM time. Once this PM time hits all financials can be closed and remaining roughly $12K can be returned to general org. fund MM23 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative MM23 (Project 9404.00 - Likely $350K short on funds, bids today 10.15.24) - Shift $6K from 9306.00 to 9404.00 - Shift $60K from project 9310.00 (MM23) to project 9389.00 (MM23). - Shift $9K from project 9310.00 (MM23) to project 9404.00 (MM23).
Note on E31: Jurgenson, John [DAS]: 9308.00 - DOC NCCF Generator System Control Replacement $John Trower, James 1:58 PM (1 minute ago) to me Finance - Please increase the MM23 budget to project 9308.00 by $20,000. Thanks
Note on E32: Huggins, Joni [DAS]: Project Closeout - 9309.00 - DOC ASP Gym Roof Replacement - MM23 $Joni Elliott, Jennie Feb 11, 2024, 2:14 PM (17 hours ago) to me, Scott Per previous email please close Story Construction (2) contract per confirmation that they have final billed. Please reduce PM time in project 9309.00 to a total Contracted amount of $11,883.49. Following this please close out the project and return remaining funds to the Total Unassigned/Unallocated line for MM23. Total of returned funds should be $41,269.02. Thank you, Jennie Elliott
Note on E33: Jurgenson, John [DAS]: Project Budget Adjustments $John Tonyan, Brad 12:28 PM (9 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. MM23 (Project 9404.00 - Likely $350K short on funds, bids today 10.15.24) - Shift $6K from 9306.00 to 9404.00 - Shift $60K from project 9310.00 (MM23) to project 9389.00 (MM23). - Shift $9K from project 9310.00 (MM23) to project 9404.00 (MM23).
Note on E34: Huggins, Joni [DAS]: MM Project Additional Funding $Joni Herman, Josh Dec 20, 2022, 8:55 AM (22 hours ago) to me, Jennifer, Scott, James, Josh Finance Please add $125,000 to 9317.00 in MM23. Can we rename this to DOC MPCF Interlock and Corridor Door Replacement? Also please add $300,000 to 9245.00 in MM22. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov 9317.00 - DOC MPCF Interlock and Corridor Door Replacement $Joni Trower, James Dec 1, 2023, 4:19 PM (3 days ago) to me Finance - Please increase the MM23 budget for project 9317.00 by $60,000. Please increase PM Time (MM23) by 8,425.28. Thanks, James Trower, Licensed Architect, LEED AP 9317.00 - DOC MPCF Tk and 10 Cell Interlock Door Replacement $John Trower, James Dec 7, 2023, 4:26 PM (15 hours ago) to me Finance - Please increase the project budget (MM23) for project 9317.00 by $150,000 Thanks,
Note on E35: Huggins, Joni [DAS]: Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov On Mon, Jan 29, 2024 at 2:00 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: Finance, I made a "dummy" invoice to charge the final PM Time in the DAS Financials to Procore and approved on "finances" behalf. I will be doing another one for a couple other projects as well. Please shift the remaining PM Time of $59.86 into the overall budget or contingency for 9255.00 (MM23) which should now total $16,834.41. Please close out the financials for project 9255.00 and also remove this project from the billabiles sheet. Please shift the remaining $16,834.41 balance from project 9255.00 to 9319.00. Thank you and please let me know when this is completed. Tonyan, Brad Oct 11, 2024, 8:56 AM (3 days ago) to me, Brad, Scott Finance, I just submitted the final PM time for project 9319.00 under funding org MM23 to balance the billables in DAS Financials with Procore. With that said this project is 100% invoiced and can be closed. Can you please transfer the remaining balance in project 9319.00 to project 9389.00 also under MM23. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative
Note on E36: Huggins, Joni [DAS]: Project Funding Modifications $Joni Trower, James 6:42 AM (1 hour ago) to me, Jennifer, Scott Finance - Please transfer $205,000 in MM23 funds from project 9320.00 - DOC NCCF Powerhouse Window Replacement to the MM23 pool fund. Please keep this project open. Please transfer $168,646.76 in MM23 funds from project 9305.00 - DAS CC Capitol South Stair Repair to the MM23 pool fund. If you have any questions, please call me at 515-380-8049. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov New Major Mainenance Projects $Joni Kleene, Jennifer Fri, Jun 23, 5:02 PM (3 days ago) to me, Scott, Jennie, James Please increase the budget for MM23 Project 9320.00 DOC NCCF Powerhouse Window Replacement by $205,000.00 (this was originally created earlier this fiscal year and then de-funded when other projects popped up that needed funding). Please also create the following new major maintenance project, or let me know if you have any questions. 9320.00 - DOC NCCF Powerhouse Window Replacement $Joni Trower, James May 2, 2024, 5:45 PM (14 hours ago) to me Finance - Project 9320.00: Please increase MM23 PM Time by $3,000. Return $60,000 in MM23 funds to the MM23 Pool fund Thanks, James Trower, Licensed Architect, LEED AP
Note on E37: Huggins, Joni [DAS]: Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed.
Note on E38: Huggins, Joni [DAS]: 9322.00 - HHS IMHI Reynolds Building Partial Roof Replacement - CloseOut $Joni Elliott, Jennie Dec 8, 2024, 10:09 AM (22 hours ago) to me, Scott Please reduce PM time to $16,244.13 and Close Out this project. This should return $76,355.15 to the Total Unassigned/Unallocated line in MM23. Thank you, Jennie Elliott
Note on E39: Huggins, Joni [DAS]: Project Fund Adjustments Request $Joni Tonyan, Brad Jun 2, 2023, 10:13 AM (3 days ago) to me, Scott, Brad, Jennifer Finance, Please see the following project budget adjustments I would like made: MM22 9234.00 - Reduce budget by ($40,000) 9235.00 - Reduce budget by ($10,000) 9246.00 - Reduce budget by ($10,000) 9271.00 - Reduce budget by ($15,000) 9272.00 - Reduce budget by ($375,000) 9291.00 - Reduce budget by ($40,000) MM23 9255.00 - Reduce budget by ($275,000) 9319.00 - Increase budget by ($100,000) 9321.00 - Reduce budget by ($100,000) 9324.00 - Increase budget by ($125,000) Thank you and please let me know when these are complete. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K 9324.00-DOC NCF Generator Switchgear Controls Replacement $John Tonyan, Brad 1:21 PM (12 minutes ago) to me, Scott, Brad Finance, All of the commitments on project 9324.00 have been closed and I had no PM time to post in March as all time was covered in February of 2024.With that said the project financials can be completely closed and return the remaining balance of $26,317.39 back to the general MM23 funding source. Note that I will be processing and approving a "dummy" invoice to have DAS financial PM time hit the Procore project to balance. Please also remove this project from the DAS billable sheet for this month. Thank you and please let me know when this is done
Note on E41: Jurgenson, John [DAS]: Project Budget Adjustments $John Tonyan, Brad 12:28 PM (0 minutes ago) to me, Scott, Brad, Jennifer Finance, Please make the following adjustments and closure of (1) project below: - 9245.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org - 9272.00 - MM22 - Please reduce budget by $75,000 and put funds back into general MM22 org 9321.00 - MM23 (CLOSE PROJECT) - Please closeout financials and shift remaining funds to project 9310.00 also in MM23 9255.00 - MM23 - Please reduce budget by $100,000 and put funds back into general MM23 org 9324.00 - MM23 - Please reduce budget by $25,000 put funds back into general MM23 org 9330.00 - MM23 - Please reduce budget by $75,000 put funds back into general MM23 org Thank you and please let me know when these adjustments are completed. PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K PM Time / Budget Adjustments Inbox Tonyan, Brad Thu, Feb 1, 1:33 PM (7 days ago) to me, Scott, Brad Finance, Please make the following adjustments/set ups: DA22: 9295.00 - Increase PM Time by $5K 9239.01 - Increase PM Time by $5K DA23: 9318.00 - Increase PM Time by $15K DA24: 9223.00 - Setup PM Time budget of $40K MM23: 9306.00 - Decrease overall budget by $145,000 and give back to general org. fund MM23 9310.00 - Increase PM Time by $5K 9319.00 - Increase PM Time by $5K 9330.00 - Increase PM time as needed to pay January PM time. Once this PM time hits all financials can be closed and remaining roughly $12K can be returned to general org. fund MM23 Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E44: Huggins, Joni [DAS]: Budget change for MM23 9339.00 Grease Trap $Joni Kleene, Jennifer 10:44 AM (1 minute ago) to me, Scott Please decrease the budget for MM23 Project # 9339.00 by $185,000.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Please Close MM23 Project 9339.00 $John Kleene, Jennifer 12:04 PM (2 hours ago) to me, Scott All invoices have been paid and all PM time has posted, so please close project 9339.00. Regards, Jennifer
Note on E45: Huggins, Joni [DAS]: 9370.00 MM23 DOC ISP Perimeter Fence Deterrent System Replacement $Joni Adams, Brandon 1:56 PM (11 minutes ago) to me, Jennifer, Scott Finance, Please increase project 9370.00 MM23 by $30,000.00. Regards, Brandon Adams Owner's Representative, State Design & Construction Resou
Note on E47: Huggins, Joni [DAS]: 9373.00 - DAS TH Terrace Road Retaining Wall Repairs - Increase Budget $Joni Trower, James Thu, Aug 15, 4:18 PM (15 hours ago) to me Finance - Please increase the MM23 budget for project 9373.00 by $100,000. Thanks, James Trower, Licensed Architect, LEED AP Re: 9373.00 - DAS TH Terrace Road Retaining Wall Repairs - Funding $Joni Trower, James 11:39 AM (5 minutes ago) to me Finance - Disregard the previous email. See below items: Please increase MM23 funding by $25,000 to Project 9373.00. Please increase MM23 funding by $25,000 to Project 9305.00. Thanks, James Trower, Licensed Architect, LEED AP
Note on E49: Huggins, Joni [DAS]: Tonyan, Brad Oct 11, 2024, 8:56 AM (3 days ago) to me, Brad, Scott Finance, I just submitted the final PM time for project 9319.00 under funding org MM23 to balance the billables in DAS Financials with Procore. With that said this project is 100% invoiced and can be closed. Can you please transfer the remaining balance in project 9319.00 to project 9389.00 also under MM23. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative MM23 (Project 9404.00 - Likely $350K short on funds, bids today 10.15.24) - Shift $6K from 9306.00 to 9404.00 - Shift $60K from project 9310.00 (MM23) to project 9389.00 (MM23). - Shift $9K from project 9310.00 (MM23) to project 9404.00 (MM23).
Note on E50: Huggins, Joni [DAS]: MM23 (Project 9404.00 - Likely $350K short on funds, bids today 10.15.24) - Shift $6K from 9306.00 to 9404.00 - Shift $60K from project 9310.00 (MM23) to project 9389.00 (MM23). - Shift $9K from project 9310.00 (MM23) to project 9404.00 (MM23). Tonyan, Brad 8:32 AM (12 minutes ago) to me Finance, I created and processed the following final "dummy" invoice for the PM time on project 9310.00. All of the invoices have been paid and if you could please close the PM time / Misc. on this project in MM23 and shift the remaining balance of $6,024.24 to project 9404.00 in MM23. Thank you, Brad Tonyan, CPM, LEED Green Associate Fwd: 9404.00 DOC NCF CRC Boiler Replacement $Joni Tonyan, Brad Tue, Oct 22, 4:43 PM (15 hours ago) to me, Scott, Jennifer, Brad Finance, Please increase the overall project budget on project 9404.00 in MM23 by $220,000. Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E52: Jenkins, Jennifer [DAS]: Budget Increase for MM23 9438.00 Inbox Kleene, Jennifer 2:04 PM (22 minutes ago) to me, Scott Please increase the budget for MM23 9438.00 by $90,000.00. Regards, Jennifer Jennifer Kleene

## MM23 Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct. Codes-0017-335-MM23
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | 29C20 payment for IVH Campus Storm Damage Repairs - Permanent 8965.01 | IET 6540306623007 | 2023-03-08 | 206718.74 | 206718.74
|  |  | 29C20 payment for IVH Campus 2018 Storm Damage Repairs (DVA Reimbursement) 9074.00 | IET 6540306623008 | 2023-03-08 | 352790.84 | 352790.84
| Total Requested | 0 | Total Transferred |  |  | 559509.58 | 559509.58

## RECAP #9997.23
Project Management Time
Project # 9997.23
| Program code 999723 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - NA
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 129424.94
C | PM TIME |  | 129424.94 | 129424.94 | 0
| Total Project Cost | 129424.94 | 129424.94 | 129424.94 | 0 | 0
Closed 08/21/2023

## #9997.23 PM TIME
Project Management Time
Project # 9997.23
Program code 999723 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 907V
Project Manager - NA
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 129424.94 | 129424.94 |  |  | 129424.94
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 129424.94 | 43150 | 43150 | 86274.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 129424.94 | -43150 | 0 | 129424.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 129424.94 | 47465 | 47465 | 81959.94
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 129424.94 | 60665 | 108130 | 21294.94
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 129424.94 | 45677.5 | 153807.5 | -24382.56
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 129424.94 | 52882.5 | 206690 | -77265.06
CDE 33523312902 | 2022-11-08 | 9500 | Moving PM Time Expense From DA23 9318.00 |  | 129424.94 | 220 | 206910 | -77485.06
CDE 33523318900 | 2022-11-10 | 9500 | Moving PM Time Expense From DA20 9170.00 |  | 129424.94 | 55 | 206965 | -77540.06
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 129424.94 | 45622.5 | 252587.5 | -123162.56
CDE 33523353200 | 2022-12-21 | 9500 | Move PM Expense from MM21 9299.00 |  | 129424.94 | 126.95 | 252714.45 | -123289.51
CDE 33523353201 | 2022-12-21 | 9500 | Move PM Expense from MM21 9299.00 |  | 129424.94 | 137.32 | 252851.77 | -123426.83
CDE 33523353202 | 2022-12-21 | 9500 | Move PM Expense from MM21 9299.00 |  | 129424.94 | 259.41 | 253111.18 | -123686.24
CDE 33523353203 | 2022-12-21 | 9500 | Move PM Expense from MM22 9255.00 |  | 129424.94 | 234.9 | 253346.08 | -123921.14
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-July 9997.23 disbursement |  | 129424.94 | -42354.15 | 210991.93 | -81566.99
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement |  | 129424.94 | -60081.06 | 150910.87 | -21485.93
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement |  | 129424.94 | -45334.19 | 105576.68 | 23848.26
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement |  | 129424.94 | -52601.48 | 52975.2 | 76449.74
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement |  | 129424.94 | -45622.5 | 7352.7 | 122072.24
CDE 33523353204 | 2022-12-21 | 9500 | Move PM Expense from R527 8908.01 |  | 129424.94 | 143.09 | 7495.79 | 121929.15
CDE 33523353205 | 2022-12-21 | 9500 | Move PM Expense from R528 9074.00 |  | 129424.94 | 117.07 | 7612.86 | 121812.08
CDE 33523353206 | 2022-12-21 | 9500 | Move PM Expense from RMST 9084.00 |  | 129424.94 | 495.89 | 8108.75 | 121316.19
CDE 33523353209 | 2022-12-21 | 9500 | Move PM Expense from July MOU projects disbursement back to 9997.23 |  | 129424.94 | 16528.66 | 24637.41 | 104787.53
CDE 33523353210 | 2022-12-22 | 9500 | Move PM Expense from Aug MOU projects disbursement back to 9997.23 |  | 129424.94 | 20150.1 | 44787.51 | 84637.43
CDE 33523353211 | 2022-12-21 | 9500 | Move PM Expense from Sept MOU projects disbursement back to 9997.23 |  | 129424.94 | 17337.16 | 62124.67 | 67300.27
CDE 33523353207 | 2022-12-22 | 9500 | Move PM Expense from Oct MOU projects disbursement back to 9997.23 |  | 129424.94 | 17695.76 | 79820.43 | 49604.51
CDE 33523353208 | 2022-12-22 | 9500 | Move PM Expense from Nov MOU projects disbursement back to 9997.23 |  | 129424.94 | 14384.78 | 94205.21 | 35219.73
CDE 33523363900 | 2022-12-29 | 9500 | Move PM time from 9997.23 MM23 to DA22 9259.00 |  | 129424.94 | -47.43 | 94157.78 | 35267.16
CDE 33523363900 | 2022-12-29 | 9500 | Move PM time from 9259.00 R20M to MM23 9997.23 |  | 129424.94 | 47.43 | 94205.21 | 35219.73
CDE 33523363901 | 2022-12-29 | 9500 | Move PM time from 9997.23 MM23 to DA22 9293.00 |  | 129424.94 | -191.04 | 94014.17 | 35410.77
CDE 33523363901 | 2022-12-29 | 9500 | Move PM time from DA23 9293.00 to MM23 9997.23 |  | 129424.94 | 191.04 | 94205.21 | 35219.73
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 129424.94 | 48312.55 | 142517.76 | -13092.82
IET DAS202306115300001 | 2023-01-09 | 9500 | Reallocation from 4095 to 4570 |  | 129424.94 | -80300 | 62217.76 | 67207.18
CDE 33523034900 | 2023-02-02 | 9500 | Reversing CDE 33523353206 |  | 129424.94 | -495.89 | 61721.87 | 67703.07
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 129424.94 | 768.97 | 62490.84 | 66934.1
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 129424.94 | 2810.51 | 65301.35 | 64123.59
CDE 33523067808 | 2023-03-08 | 9500 | Move PM Time Expense from DA 23 9328.00 |  | 129424.94 | 144.83 | 65446.18 | 63978.76
CDE 33523075200 | 2023-03-07 | 2507 | Move Finance time from 0506 funds for July through December 2022 |  | 129424.94 | 5681.59 | 71127.77 | 58297.17
CDE 33523075203 | 2023-03-07 | 9500 | Move PM Time Expense to correct MM20 units |  | 129424.94 | -6378.86 | 64748.91 | 64676.03
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 |  | 129424.94 | 7209.23 | 71958.14 | 57466.8
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 |  | 129424.94 | 8615.19 | 80573.33 | 48851.61
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 |  | 129424.94 | 10029.19 | 90602.52 | 38822.42
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 |  | 129424.94 | 3920.14 | 94522.66 | 34902.28
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 |  | 129424.94 | 4410.79 | 98933.45 | 30491.49
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 |  | 129424.94 | 5088.02 | 104021.47 | 25403.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 129424.94 | 1040.59 | 105062.06 | 24362.88
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 129424.94 | 2322.43 | 107384.49 | 22040.45
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 129424.94 | 902.5 | 108286.99 | 21137.95
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 129424.94 | 1302.13 | 109589.12 | 19835.82
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 129424.94 | 679.92 | 110269.04 | 19155.9
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 129424.94 | 1511.9 | 111780.94 | 17644
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 129424.94 | 995.54 | 112776.48 | 16648.46
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 129424.94 | 3649.8 | 116426.28 | 12998.66
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 129424.94 | 349.31 | 116775.59 | 12649.35
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 129424.94 | 4978.1 | 121753.69 | 7671.25
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 129424.94 | 563.52 | 122317.21 | 7107.73
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 129424.94 | 1086 | 123403.21 | 6021.73
CDE 33524220800 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 (Move to FY24) |  | 129424.94 | -563.52 | 122839.69 | 6585.25
CDE 33524220800 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 (Move to FY24) |  | 129424.94 | -1086 | 121753.69 | 7671.25
CDE 33523221803 | 2023-08-09 | 2507 | Move PM time from 9316.00 DA23 June |  | 129424.94 | 502.6 | 122256.29 | 7168.65
CDE 33523221803 | 2023-08-09 | 9500 | Move PM time from 9316.00 DA23 June |  | 129424.94 | 4065.1 | 126321.39 | 3103.55
CDE 33523221803 | 2023-08-09 | 2507 | Move PM time from 9341.00 DA23 June |  | 129424.94 | 344.65 | 126666.04 | 2758.9
CDE 33523221803 | 2023-08-09 | 9500 | Move PM time from 9341.00 DA23 June |  | 129424.94 | 2758.9 | 129424.94 | 1.0459e-11
[5 empty] | 129424.94 |  | 129424.94 | 1.0459e-11
[5 empty] | 129424.94 |  | 129424.94 | 1.0459e-11
[5 empty] | 129424.94 |  | 129424.94 | 1.0459e-11
[5 empty] | 129424.94 |  | 129424.94 | 1.0459e-11
[5 empty] | 129424.94 |  | 129424.94 | 1.0459e-11
|  |  | Totals: | 129424.94 |  | 129424.94 |  | 0

## RECAP #9224.00
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
| Program code 922400 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 877991.08
C | OPN Architects |  | 75970 | 75970 | 0
C | PM TIME |  | 40652.14 | 40652.14 | 0
C | Misc. |  | 1181.19 | 1181.19 | 0
C | Esco Electric Co |  | 181038.69 | 181038.69 | 0
C | Schumacher Elevator |  | 321274.98 | 321274.98 | 0
C | Total Construction Solutions |  | 82694.74 | 82694.74 | 0
C | Samuels Group |  | 171811.04 | 171811.04 | 0
C | Controlled Asbestos |  | 3368.3 | 3368.3 | 0
| Total Project Cost | 877991.08 | 877991.08 | 877991.08 | 0 | 0
Closed 06/10/2024

## #9224.00 OPN Architects
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM23-9260 |  |  | RFP922400-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523117801 | 2022-09-30 | CO 1 | 75970 | 75970 |  |  | 75970
PRC 3352311PE7801 | 2022-10-03 | Inv. 21840001-5 (100% to MM21) | 0 | 75970 |  | 0 | 75970
PO 33523117801 | 2022-12-02 | CO 2 (Internal only) JT | 0 | 75970 |  | 0 | 75970
PRC 3352311PF7801 | 2022-12-02 | Inv. 21840001-6(100% to MM21) |  | 75970 | 0 | 0 | 75970
PO 33523117801 | 2022-12-12 | CO 3 (Internal only) JT | 0 | 75970 |  | 0 | 75970
PRC 3352311PG7801 | 2022-12-16 | Inv. 21840001-6A (100% to MM23) |  | 75970 | 2059.37 | 2059.37 | 73910.63
PRC 3352311PH7801 | 2023-01-17 | Inv. 21840001-7 |  | 75970 | 4776.17 | 6835.54 | 69134.46
PRC 3352311PI7801 | 2023-02-06 | Inv. 21840001-9 |  | 75970 | 2553.76 | 9389.3 | 66580.7
PRC 3352311PJ7801 | 2023-04-11 | Inv. 21840001-10 |  | 75970 | 4285.3 | 13674.6 | 62295.4
PRC 3352311PK7801 | 2023-05-08 | Inv. 21840001-11 |  | 75970 | 12914.9 | 26589.5 | 49380.5
PRC 3352311PL7801 | 2023-05-30 | Inv. 21840001-12 |  | 75970 | 4288.51 | 30878.01 | 45091.99
PRC 3352311PM7801 | 2023-06-30 | Inv. 21840001-13 |  | 75970 | 2548.79 | 33426.8 | 42543.2 | FY23
PO 33524117801 | 2023-08-04 | Roll to FY24 | 0 | 75970 |  | 33426.8 | 42543.2
PRC 3352411PN7801 | 2023-08-21 | Inv. 21840001-14 |  | 75970 | 5317.9 | 38744.7 | 37225.3
PRC 3352411PO7801 | 2023-09-13 | Inv. 21840001-15 |  | 75970 | 10540.84 | 49285.54 | 26684.46
PRC 3352411PP7801 | 2023-11-09 | Inv. 21840001-16 |  | 75970 | 4034 | 53319.54 | 22650.46
PRC 3352411PQ7801 | 2023-12-01 | Inv. 21840001-17 |  | 75970 | 2909.66 | 56229.2 | 19740.8
PRC 3352411PR7801 | 2024-01-11 | Inv. 21840001-18 |  | 75970 | 2005.6 | 58234.8 | 17735.2
PRC 3352411PS7801 | 2024-02-12 | Inv. 21840001-19 |  | 75970 | 2161.35 | 60396.15 | 15573.85
PRC 3352411PT7801 | 2024-05-21 | Inv. 21840001-20FINAL |  | 75970 | 15573.85 | 75970 | 0
|  |  |  | 75970 |  | 75970 | 0
|  |  |  | 75970 |  | 75970 | 0
|  | Totals: | 75970 |  | 75970 |  | 0 | FINAL
|  | MM21(Closed 12/2/2022) | 94570 |  | 94570 |  | 0
|  | Contract Total | 170540 |  | 170540 |  | 0

## #9224.00 PM TIME
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 908I
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 40652.14 | 40652.14 |  |  | 40652.14
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 40652.14 | 1101.29 | 1101.29 | 39550.85
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 40652.14 | 9981.2 | 11082.49 | 29569.65
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 40652.14 | 724.93 | 11807.42 | 28844.72
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 40652.14 | 4615.5 | 16422.92 | 24229.22
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 40652.14 | 797.54 | 17220.46 | 23431.68
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 40652.14 | 4455.8 | 21676.26 | 18975.88
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 40652.14 | 539.88 | 22216.14 | 18436
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 40652.14 | 3746.5 | 25962.64 | 14689.5
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 40652.14 | 284.76 | 26247.4 | 14404.74
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 40652.14 | 2287.6 | 28535 | 12117.14
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 40652.14 | 298.7 | 28833.7 | 11818.44
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 40652.14 | 2257.6 | 31091.3 | 9560.84
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 40652.14 | 157.7 | 31249 | 9403.14
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 40652.14 | 1158.5 | 32407.5 | 8244.64
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 40652.14 | 209.69 | 32617.19 | 8034.95
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 40652.14 | 1850.1 | 34467.29 | 6184.85
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 40652.14 | 372.6 | 34839.89 | 5812.25
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 40652.14 | 1879.3 | 36719.19 | 3932.95
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 40652.14 | 217.94 | 36937.13 | 3715.01
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 40652.14 | 1651.5 | 38588.63 | 2063.51
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 40652.14 | 144.06 | 38732.69 | 1919.45
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 40652.14 | 1279.9 | 40012.59 | 639.55
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 40652.14 | 68.25 | 40080.84 | 571.3
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 40652.14 | 571.3 | 40652.14 | -5.6843e-12
[5 empty] | 40652.14 |  | 40652.14 | -5.6843e-12
|  |  | Totals: | 40652.14 |  | 40652.14 |  | 0
Note on E9: Huggins, Joni [DAS]: 9224.00 - DOC MPCF Elevator B C & D Replacements - Funding Transfer $Joni Trower, James Dec 12, 2022, 10:21 PM (10 hours ago) to me, Joni Finance/Joni - 9224.00 - DOC MPCF Elevator B C & D Replacements MM21 Funding: Decrease PM Time by $350.87. 9224.00 - DOC MPCF Elevator B C & D Replacements MM23 Funding: Increase PM Time (currently $0.00) by $8,000. Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Re: PM Time $John Adams, Brandon 10:16 AM (11 minutes ago) to me Finance, Please increase: 9224.00 MM23 by $15,000 9287.00 MM21 by $5,000 9302.00 MM22 by $8,000 Thanks you, Re: PM Time $John Adams, Brandon 8:07 AM (1 hour ago) to me Finance, Please increase the following projects: 9224.00 - MM23 - increase by $10,000 9287.00 - MM21 - increase by $5,000 Thanks, Re: PM Time $John Adams, Brandon 11:21 AM (1 minute ago) to me Finance, Please increase MM23 9224.00 PM time $3000.00. Regards, Adams, Brandon 1:42 PM (0 minutes ago) to me Finance, Please increase the follow PM Time, 9249.00 in MM22 increase by $4,000 9224.00 in MM23 increase by $1,000 9370.00 in MM23 increase by $3,000 Regards9224.00 PM Time $Joni Adams, Brandon Jun 3, 2024, 12:54 PM (7 days ago) to me Finance, Please close PM Time for project 9224.00 when you post May hours. Regards, Brandon Adams

## #9224.00 Misc
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523278901 | 2022-10-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV024208 | 366.19 | 366.19
GAX 33523186800 | 2023-07-05 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2511113 | 815 | 1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
1181.19
|  |  |  | Totals: |  | 1181.19

## #9224.00 Esco Electric Co
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
Esco Electric Co |  |  | Vendor: 00002119529
Acct. Codes-0017-335-MM23-9255 |  |  | RFP922400-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523297900 | 2022-10-24 | PO Procore | 247979.18 | 247979.18 |  |  | 247979.18
PO 33523297900 | 2023-02-24 | CO #1 | 14273.2 | 262252.38 |  | 0 | 262252.38
PO 33523297900 | 2023-03-09 | CO #2 | 5340.78 | 267593.16 |  | 0 | 267593.16
PRC 3352329PA7900 | 2023-03-21 | Inv. 131220 |  | 267593.16 | 16395.79 | 16395.79 | 251197.37 | 862.93
PO 33523297900 | 2023-03-22 | CO #3 | 35332.23 | 302925.39 |  | 16395.79 | 286529.6
PO 33523297900 | 2023-05-03 | CO #4 | 473.13 | 303398.52 |  | 16395.79 | 287002.73
PRC 3352329PB7900 | 2023-05-08 | Inv. 132315 |  | 303398.52 | 63843.1 | 80238.89 | 223159.63 | 4223.09
PO 33523297900 | 2023-05-17 | CO #5 | 12148.05 | 315546.57 |  | 80238.89 | 235307.68
PO 33523297900 | 2023-07-06 | CO #6 | 4620.38 | 320166.95 |  | 80238.89 | 239928.06
PRC 3352329PC7900 | 2023-07-14 | Inv. 134313 |  | 320166.95 | 100799.8 | 181038.69 | 139128.26 | 9528.35 | FY23
PO 33524297900A | 2023-08-04 | Roll to FY24 (With new Vendor#) | 0 | 320166.95 |  | 181038.69 | 139128.26
PRC 3352429PD7900A | 2023-10-04 | Inv. 135911 |  | 320166.95 | 64264.08 | 245302.77 | 74864.18 | 12910.67
PO 33524297900A | 2023-10-19 | CO #7 | 2518.18 | 322685.13 |  | 245302.77 | 77382.36
PRCN 3352429PE7900A | 2023-10-19 | Inv. 135911A |  | 322685.13 | 8835 | 254137.77 | 68547.36 | 13375.67
PRCN 3352429PF7900A | 2023-11-29 | Inv. 137184 |  | 322685.13 | 12180.4 | 266318.17 | 56366.96 | 14016.74
PRC 3352429PG7900A | 2024-03-18 | Inv. 140679 |  | 322685.13 | 36321.89 | 302640.06 | 20045.07 | 15928.42
PO 33524297900A | 2024-04-05 | CO #8 | -1636.65 | 321048.48 |  | 302640.06 | 18408.42
PRC 3352429PH7900A | 2024-05-09 | Inv. 140850 |  | 321048.48 | 2356 | 304996.06 | 16052.42 | 16052.42
PRC 3352429PI7900A | 2024-05-13 | Inv. 140851-Retainage |  | 321048.48 | 16052.42 | 321048.48 | 0
CDE 33524187913 | 2024-07-05 | Moving Expense from MM23 to MM21 | -140009.79 | 181038.69 | -140009.79 | 181038.69 | 0
CDE 33524208905 | 2024-07-26 | Reversing CDE33524187913 to Correct Program Code | 140009.79 | 321048.48 | 140009.79 | 321048.48 | 0
CDE 33524208910 | 2024-07-26 | Moving Expense from MM23 to MM21 | -140009.79 | 181038.69 | -140009.79 | 181038.69 | 0
|  | Totals: | 181038.69 |  | 181038.69 |  | 0

## #9224.00 Schumacher Elevator
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
Schumacher Elevator |  |  | Vendor: 00002108471
Acct. Codes-0017-335-MM23-9255 |  |  | RFP922400-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523299900 | 2022-10-25 | PO Procore | 1098001 | 1098001 |  |  | 1098001
PRC 3352329PA9900 | 2023-05-08 | Inv. 90581225 |  | 1098001 | 90491.11 | 90491.11 | 1007509.89 | 4762.69
PO 33523299900 | 2023-06-05 | CO #1 | 3623.65 | 1101624.65 |  | 90491.11 | 1011133.54
PRC 3352329PB9900 | 2023-06-06 | Inv. 90583936 |  | 1101624.65 | 121018.88 | 211509.99 | 890114.66 | 11132.11
PRC 3352329PC9900 | 2023-06-30 | Inv. 90586380 |  | 1101624.65 | 109764.99 | 321274.98 | 780349.67 | 16909.22
PO 33523299900 | 2023-07-12 | CO #2 | 560 | 1102184.65 |  | 321274.98 | 780909.67 |  | FY23
PO 33524299900 | 2023-08-04 | Roll to FY24 | 0 | 1102184.65 |  | 321274.98 | 780909.67
PRC 3352429PD9900 | 2023-07-31 | Inv. 90588725 |  | 1102184.65 | 72722.5 | 393997.48 | 708187.17 | 20736.72
PRC 3352429PE9900 | 2023-08-28 | Inv. 90591162 |  | 1102184.65 | 130117.79 | 524115.27 | 578069.38 | 27585.03
PO 33524299900 | 2023-09-08 | CO #3 | 15243.25 | 1117427.9 |  | 524115.27 | 593312.63
PRC 3352429PF9900 | 2023-09-25 | Inv. 90593818 |  | 1117427.9 | 191828.37 | 715943.64 | 401484.26 | 37681.26
PRC 3352429PG9900 | 2023-12-13 | Inv. 90599677-8 |  | 1117427.9 | 42338.57 | 758282.21 | 359145.69 | 39909.61
PRC 3352429PG9900A | 2023-12-15 | Inv. 90599677-8A |  | 1117427.9 | 50 | 758332.21 | 359095.69 | 39912.24
PRC 3352429PH9900 | 2024-01-03 | Inv. MINV#51638-40 |  | 1117427.9 | 99977.61 | 858309.82 | 259118.08 | 45174.23
PRC 3352429PI9900 | 2024-02-05 | Inv. 90604710-11 |  | 1117427.9 | 120090.4 | 978400.22 | 139027.68 | 51494.78
PRC 3352429PJ9900 | 2024-03-05 | Inv. 90607375 |  | 1117427.9 | 17863.99 | 996264.21 | 121163.69 | 52434.99
PRC 3352429PK9900 | 2024-03-06 | Inv. 90607983 |  | 1117427.9 | 42639.8 | 1038904.01 | 78523.89 | 54679.19
PO 33524299900 | 2024-03-08 | CO #4 | -12864.7 | 1104563.2 |  | 1038904.01 | 65659.19
PRC 3352429PL9900 | 2024-05-06 | Inv. 90612821 |  | 1104563.2 | 10431 | 1049335.01 | 55228.19 | 55228.19
PRC 3352429PM9900 | 2024-05-09 | Inv. 9224.00-Retainage |  | 1104563.2 | 55228.19 | 1104563.2 | 0
CDE 33524187912 | 2024-07-05 | Moving Expense from MM23 to MM21 | -783288.22 | 321274.98 | -783288.22 | 321274.98 | 0
CDE 33524208904 | 2024-07-26 | Reversing CDE33524187913 to Correct Program Code | 783288.22 | 1104563.2 | 783288.22 | 1104563.2 | 0
CDE 33524208908 | 2024-07-26 | Moving Expense from MM23 to MM21 | -783288.22 | 321274.98 | -783288.22 | 321274.98 | 0
|  |  |  | 321274.98 |  | 321274.98 | 0
|  | Totals: | 321274.98 |  | 321274.98 |  | 0
**Inv #8 Paid $50 short #8A is the fix

## #9224.00 Total Construction
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
Total Construction Solutions |  |  | Vendor: 00003166405
Acct. Codes-0017-335-MM23-9255 |  |  | RFB922400-02
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523308900 | 2022-11-02 | PO Procore | 95166.4 | 95166.4 |  |  | 95166.4
PRC 3352330PA8900 | 2023-05-22 | Inv. 1458 |  | 95166.4 | 30837.47 | 30837.47 | 64328.93 | 1623.03
PRC 3352330PB8900 | 2023-06-30 | Inv. 4347 |  | 95166.4 | 23406.65 | 54244.12 | 40922.28 | 2854.96
PO 33523308900 | 2023-07-06 | CO #1 | 2100 | 97266.4 |  | 54244.12 | 43022.28 |  | FY23
PO 33524308900 | 2023-08-04 | Roll to FY24 | 0 | 97266.4 |  | 54244.12 | 43022.28
PO 33524308900 | 2023-09-07 | CO #2 | 1920.5 | 99186.9 |  | 54244.12 | 44942.78
PO 33524308900 | 2023-10-27 | CO #3 | 656.65 | 99843.55 |  | 54244.12 | 45599.43
PRC 3352430PC8900 | 2024-01-11 | Inv. 4560 |  | 99843.55 | 14695.69 | 68939.81 | 30903.74 | 3628.42
PO 33524308900 | 2024-01-12 | CO #4 | 391 | 100234.55 |  | 68939.81 | 31294.74
PRC 3352430PD8900 | 2024-02-13 | Inv. 4680 |  | 100234.55 | 23508.52 | 92448.33 | 7786.22 | 4865.72
PO 33524308900 | 2024-02-23 | CO #5 | -1920.5 | 98314.05 |  | 92448.33 | 5865.72
PRC 3352430PE8900 | 2024-05-14 | Inv. 4995 |  | 98314.05 | 950 | 93398.33 | 4915.72 | 4915.72
PRC 3352430PF8900 | 2024-05-20 | Inv. 4996-Retainage |  | 98314.05 | 4915.72 | 98314.05 | 0
CDE 33524187914 | 2024-07-05 | Moving Expense from MM23 to MM21 | -15619.31 | 82694.74 | -15619.31 | 82694.74 | 0
CDE 33524208906 | 2024-07-26 | Reversing CDE33524187914 to Correct Program Code | 15619.31 | 98314.05 | 15619.31 | 98314.05 | 0
CDE 33524208907 | 2024-07-26 | Moving Expense from MM23 to MM21 | -15619.31 | 82694.74 | -15619.31 | 82694.74 | 0
|  |  |  | 82694.74 |  | 82694.74 | 0
|  | Totals: | 82694.74 |  | 82694.74 |  | 0 | FINAL

## #9224.00 Samuels Group
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523313900 | 2022-10-26 | PO Procore | 174100.53 | 174100.53 |  |  | 174100.53
PRC 3352331PA3900 | 2022-12-01 | Inv. 7450.10 CA |  | 174100.53 | 5443.83 | 5443.83 | 168656.7
PRC 3352331PB3900 | 2023-01-04 | Inv. 7450.11 CA |  | 174100.53 | 2714.04 | 8157.87 | 165942.66
PRC 3352331PC3900 | 2023-02-03 | Inv. 7450.12 CA |  | 174100.53 | 7891.84 | 16049.71 | 158050.82
PRC 3352331PD3900 | 2023-03-08 | Inv. 7450.13 CA |  | 174100.53 | 7730.07 | 23779.78 | 150320.75
PRC 3352331PE3900 | 2023-04-06 | Inv. 7450.14 CA |  | 174100.53 | 11094.16 | 34873.94 | 139226.59
PRC 3352331PF3900 | 2023-05-05 | Inv. 7450.15 CA |  | 174100.53 | 15773.54 | 50647.48 | 123453.05
PRC 3352331PG3900 | 2023-06-01 | Inv. 7450.16 CA |  | 174100.53 | 14636 | 65283.48 | 108817.05
PRC 3352331PH3900 | 2023-07-10 | Inv. 7450.17 CA |  | 174100.53 | 14752.49 | 80035.97 | 94064.56 | FY23
PO 33524313900 | 2023-08-04 | Roll to FY24 | 0 | 174100.53 |  | 80035.97 | 94064.56
PRC 3352431PI3900 | 2023-08-08 | Inv. 7450.18 CA |  | 174100.53 | 15610.99 | 95646.96 | 78453.57
PRC 3352431PJ3900 | 2023-09-12 | Inv. 7450.19 CA |  | 174100.53 | 11951.34 | 107598.3 | 66502.23
PRC 3352431PK3900 | 2023-10-02 | Inv. 7450.20 CA |  | 174100.53 | 11658.25 | 119256.55 | 54843.98
PRC 3352431PL3900 | 2023-11-09 | Inv. 7450.21 CA |  | 174100.53 | 7212.83 | 126469.38 | 47631.15
PRC 3352431PM3900 | 2023-12-11 | Inv. 7450.22CA |  | 174100.53 | 6363.63 | 132833.01 | 41267.52
PRC 3352431PN3900 | 2024-01-04 | Inv. 7450.23 CA |  | 174100.53 | 8780.68 | 141613.69 | 32486.84
PRC 3352431PO3900 | 2024-02-09 | Inv. 7450.24CA |  | 174100.53 | 9480.73 | 151094.42 | 23006.11
PRC 3352431PP3900 | 2024-03-04 | Inv. 7450.25 CA |  | 174100.53 | 7632.51 | 158726.93 | 15373.6
PRC 3352431PQ3900 | 2024-04-03 | Inv. 7450.26CA |  | 174100.53 | 2939.86 | 161666.79 | 12433.74
PRC 3352431PR3900 | 2024-05-06 | Inv. 7450.27 CA |  | 174100.53 | 6897.12 | 168563.91 | 5536.62
PRC 3352431PS3900 | 2024-05-21 | Inv. 7450.28 CA FINAL | -2289.49 | 171811.04 | 3247.13 | 171811.04 | -1.819e-11
|  |  |  | 171811.04 |  | 171811.04 | -1.819e-11
|  |  |  | 171811.04 |  | 171811.04 | -1.819e-11
|  |  |  | 171811.04 |  | 171811.04 | -1.819e-11
|  | Totals: | 171811.04 |  | 171811.04 |  | 0 | FINAL
|  | CM Services | 92751.78 |  | 92751.78 |  | 0
|  | Reimbursables | 7001.93 |  | 7001.93 |  | 0
|  | Fees | 72057.33 |  | 72057.33 |  | 0
|  | Totals: | 171811.04 |  | 171811.04 |  | 0

## #9224.00 Controlled Asbestos
DOC MPCF Elevator B C & D Replacements
Project # 9224.00
Program code 922400 |  |  | Major Program 4D03
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA21060
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523010800 | 2023-01-10 | DO Procore | 3613.04 | 3613.04 |  |  | 3613.04
DO 33523010800 | 2023-08-14 | CO #1 | 2946.04 | 6559.08 |  | 0 | 6559.08 | FY23
DO 33524010800 | 2023-08-18 | Roll to FY24 | 0 | 6559.08 |  | 0 | 6559.08
PRC 3352401PA0800 | 2024-01-17 | Inv. 0010632 -final | -3190.78 | 3368.3 | 3368.3 | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  |  |  | 3368.3 |  | 3368.3 | 0
|  | Totals: | 3368.3 |  | 3368.3 |  | 0 | FINAL
|  | Line 1 32hrs x 58 = $1,856.00 | 1856 |  | 1856 |  | 0
|  | Line 1 Drive time 4.5hrs x 4 trips = 1044 | 1044 |  | 1044 |  | 0
|  | Line 7 Air Samples = 120 | 0 |  |  |  | 0
|  | Line 11 Disposal Fee = 150 | 31.5 |  | 31.5 |  | 0
|  | Line 12 Mileage 2m x 2 trips= 1136x 0.39 | 436.8 |  | 436.8 |  | 0
|  | Totals: | 3368.3 |  | 3368.3 |  | 0

## RECAP #9249.00
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 08/10/23

## #9249.00 Vendor A
DOC MPCF Building 18 Roof Replacement
Project # 9249.00
Program code 924900 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9249.00 PM TIME
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E257
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 0 | 118.98 | 118.98 | -118.98
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 0 | 1079.7 | 1198.68 | -1198.68
CDE 33523195800 | 2023-07-14 | 2507 | Finance Support for June 1-30, 2023 (Move Expense to MM22) |  | 0 | -118.98 | 1079.7 | -1079.7
CDE 33523195800 | 2023-07-14 | 9500 | DAS Services for June 1-30, 2023 (Move Expense to MM22) |  | 0 | -1079.7 | 0 | 0
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 0 | 42.45 | 42.45 | -42.45
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 0 | 271.7 | 314.15 | -314.15
CDE 33524222806 | 2023-08-10 | 2507 | Finance Support for July 1-31, 2023 (Move Expense to MM22) |  | 0 | -42.45 | 271.7 | -271.7
CDE 33524222806 | 2023-08-10 | 9500 | DAS Services for July 1-31, 2023 (Move Expense to MM22) |  | 0 | -271.7 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9249.00 Misc
DOC MPCF Front Steps Repair
Project # 9249.00
Program code 924900 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9250.00
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
| Program code 925000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1145000
| Tricon General |  | 844950.47 | 752260.48 | 92689.99
| PM TIME |  | 22000 | 21999.83 | 0.17
| Misc. |  | 0 | 0 | 0
C | REW Services |  | 87244 | 87244 | 0
| McGough Construction |  | 145920.72 | 106647.44 | 39273.28
| Total Project Cost | 1145000 | 1100115.19 | 968151.75 | 131963.44 | 44884.81

## #9250.00 Tricon General
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
Tricon General |  |  | Vendor: 00002124028
Acct. Codes-0017-335-MM23-9255 |  |  | RFB 925000-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524276901 | 2023-09-29 | PO Procore | 789000 | 789000 |  |  | 789000
PRC 3352427PA6901 | 2024-05-13 | Inv. 9250.00 AIA #1 |  | 789000 | 217116.5 | 217116.5 | 571883.5 | 11427.19
PO 33524276901 | 2024-06-21 | CO #1 | 51015.89 | 840015.89 |  | 217116.5 | 622899.39
PO 33524276901 | 2024-07-08 | CO #2 | 617.81 | 840633.7 |  | 217116.5 | 623517.2
PO 33524276901 | 2024-07-16 | CO #3 | 4399.4 | 845033.1 |  | 217116.5 | 627916.6
PRC 3352427PB6901 | 2024-07-17 | Inv. 9250.00 AIA #2 |  | 845033.1 | 127453.85 | 344570.35 | 500462.75 | 18135.31
PO 33525276901 | 2024-07-19 | Roll to FY25 |  | 845033.1 |  | 344570.35 | 500462.75
PO 33524276901 | 2024-08-19 | Roll Back to FY24 for Invoice |  | 845033.1 |  | 344570.35 | 500462.75
PO 33524276901 | 2024-08-22 | CO #4 | 3880 | 848913.1 |  | 344570.35 | 504342.75
PRC 3352427PC6901 | 2024-08-26 | Inv. AIA #3R |  | 848913.1 | 3686 | 348256.35 | 500656.75 | 18329.31 | FY24
PO 33525276901A | 2024-08-26 | Roll to FY25 |  | 848913.1 |  | 348256.35 | 500656.75
PRC 3352527PD6901A | 2024-10-03 | Inv. Ala #4 |  | 848913.1 | 404004.13 | 752260.48 | 96652.62 | 39592.7
PO 33525276901A | 2024-11-04 | CO #5 | 5229.4 | 854142.5 |  | 752260.48 | 101882.02
PO 33525276901A | 2024-11-08 | CO #6 | -6607.48 | 847535.02 |  | 752260.48 | 95274.54
PO 33525276901A | 2025-01-13 | CO #7 | -2584.55 | 844950.47 |  | 752260.48 | 92689.99
|  |  |  | 844950.47 |  | 752260.48 | 92689.99
|  |  |  | 844950.47 |  | 752260.48 | 92689.99
|  |  |  | 844950.47 |  | 752260.48 | 92689.99
|  | Totals: | 844950.47 |  | 752260.48 |  | 92689.99

## #9250.00 PM TIME
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E258
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22000 | 22000 |  |  | 22000
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 22000 | 8.89 | 8.89 | 21991.11
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 22000 | 51.3 | 60.19 | 21939.81
CDE 33523128800 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 22000 | -8.89 | 51.3 | 21948.7
CDE 33523128800 | 2023-05-07 | 2507 | DAS Services for: April 1-30, 2023 |  | 22000 | -51.3 | 0 | 22000
CDE 33523135800 | 2023-05-15 | 2507 | Finance Support for: April 1-30, 2023 |  | 22000 | 8.89 | 8.89 | 21991.11
CDE 33523135800 | 2023-05-15 | 2507 | DAS Services for: April 1-30, 2023 |  | 22000 | 51.3 | 60.19 | 21939.81
CDE 33523135800 | 2023-05-15 | 2507 | Finance Support for: April 1-30, 2023 |  | 22000 | -8.89 | 51.3 | 21948.7
CDE 33523135800 | 2023-05-15 | 9500 | DAS Services for: April 1-30, 2023 |  | 22000 | -51.3 | 0 | 22000
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 22000 | 88.07 | 88.07 | 21911.93
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 22000 | 797.9 | 885.97 | 21114.03
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 22000 | 152.08 | 1038.05 | 20961.95
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 22000 | 969.6 | 2007.65 | 19992.35
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 22000 | 305.15 | 2312.8 | 19687.2
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 22000 | 1704.6 | 4017.4 | 17982.6
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 22000 | 169.62 | 4187.02 | 17812.98
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 22000 | 1178.1 | 5365.12 | 16634.88
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 22000 | 84.48 | 5449.6 | 16550.4
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 22000 | 676.4 | 6126 | 15874
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 22000 | 30.92 | 6156.92 | 15843.08
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 22000 | 233.6 | 6390.52 | 15609.48
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 22000 | 88.72 | 6479.24 | 15520.76
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 22000 | 650.5 | 7129.74 | 14870.26
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 22000 | 20 | 7149.74 | 14850.26
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 22000 | 178.5 | 7328.24 | 14671.76
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 22000 | 69.18 | 7397.42 | 14602.58
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 22000 | 348.9 | 7746.32 | 14253.68
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 22000 | 39.23 | 7785.55 | 14214.45
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 22000 | 298 | 8083.55 | 13916.45
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 22000 | 172.93 | 8256.48 | 13743.52
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 22000 | 1537.3 | 9793.78 | 12206.22
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 22000 | 252.92 | 10046.7 | 11953.3
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 22000 | 2094.6 | 12141.3 | 9858.7
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 22000 | 143.94 | 12285.24 | 9714.76
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 22000 | 1313.7 | 13598.94 | 8401.06
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 22000 | 183.05 | 13781.99 | 8218.01
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 22000 | 1998.3 | 15780.29 | 6219.71
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 22000 | 358.87 | 16139.16 | 5860.84
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 22000 | 1828.8 | 17967.96 | 4032.04
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 30,2024 |  | 22000 | 147.21 | 18115.17 | 3884.83
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 30,2024 |  | 22000 | 1307.7 | 19422.87 | 2577.13
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 22000 | 164.27 | 19587.14 | 2412.86
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 22000 | 1095.3 | 20682.44 | 1317.56
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 22000 | 75.05 | 20757.49 | 1242.51
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 22000 | 497.7 | 21255.19 | 744.81
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 22000 | 67.64 | 21322.83 | 677.17
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 22000 | 677 | 21999.83 | 0.17
[5 empty] | 22000 |  | 21999.83 | 0.17
[5 empty] | 22000 |  | 21999.83 | 0.17
[5 empty] | 22000 |  | 21999.83 | 0.17
|  |  | Totals: | 22000 |  | 21999.83 |  | 0.17

## #9250.00 Misc
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brandon A.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9250.00 REW Services
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
REW Services |  |  | Vendor: 00003105700
Acct. Codes-0017-335-MM23-9255 |  |  | RFB 925000-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524276902 | 2023-09-29 | PO Procore | 87244 | 87244 |  |  | 87244
PRC 3352427PA6902 | 2024-05-23 | Inv. 9250.00-01 |  | 87244 | 82053.17 | 82053.17 | 5190.83 | 4318.59
PRC 3352427PB6902 | 2024-07-18 | Inv. 9250.00-02 |  | 87244 | 828.63 | 82881.8 | 4362.2 | 4362.2 | FY24
PO 33525276902 | 2024-07-22 | Roll to FY25 |  | 87244 |  | 82881.8 | 4362.2
JVA CW0716247315161625 | 2024-07-22 | Cancelled Warrant |  | 87244 | -828.63 | 82053.17 | 5190.83 | 4362.2
PRC 3352527PB6902A | 2024-07-22 | Inv. 9250.00-02A |  | 87244 | 828.63 | 82881.8 | 4362.2 | 4362.2
PRC 3352527PC6902 | 2024-07-26 | Inv 9250.00-03 Retainage |  | 87244 | 4362.2 | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  |  |  | 87244 |  | 87244 | 0
|  | Totals: | 87244 |  | 87244 |  | 0 | FINAL

## #9250.00 McGough Construction
DOC MPCF Building 18 Roof Replacement
Project # 9250.00
Program code 925000 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524284805 | 2023-10-11 | PO Procore | 145920.72 | 145920.72 |  |  | 145920.72
PRC 3352428PA4805 | 2023-11-13 | Inv. 100877.003-01 |  | 145920.72 | 2909.83 | 2909.83 | 143010.89
PRC 3352428PB4805 | 2023-12-12 | Inv. 100877.003-CA02 |  | 145920.72 | 754.55 | 3664.38 | 142256.34
PRC 3352428PC4805 | 2024-01-12 | Inv. 100877.003-CA03 |  | 145920.72 | 1178.15 | 4842.53 | 141078.19
PRC 3352428PD4805 | 2024-02-08 | Inv. 100877.003-CA04 |  | 145920.72 | 749.25 | 5591.78 | 140328.94
PRC 3352428PE4805 | 2024-03-18 | Inv. 100877.003-CA05 |  | 145920.72 | 905.46 | 6497.24 | 139423.48
PRC 3352428PF4805 | 2024-04-05 | Inv. 100877.003-CA06 |  | 145920.72 | 1858.27 | 8355.51 | 137565.21
PRC 3352428PG4805 | 2024-05-10 | Inv. 100877.003-CA07 |  | 145920.72 | 16264.4 | 24619.91 | 121300.81
PRC 3352428PH4805 | 2024-06-17 | Inv. 100877.003-CA08 |  | 145920.72 | 12352.21 | 36972.12 | 108948.6
PRC 3352428PI4805 | 2024-07-16 | Inv. 100877.003-CA09 |  | 145920.72 | 16190.57 | 53162.69 | 92758.03 | FY24
PO 33525284805 | 2024-07-23 | Roll to FY25 |  | 145920.72 |  | 53162.69 | 92758.03
PRC 3352528PJ4805 | 2024-08-12 | Inv. 100877.003-CA10 |  | 145920.72 | 6485.68 | 59648.37 | 86272.35
PRC 3352528PK4805 | 2024-09-12 | Inv. 100877.003-CA11 |  | 145920.72 | 9229.99 | 68878.36 | 77042.36
PRC 3352528PL4805 | 2024-10-14 | Inv. 100877.003-CA12 |  | 145920.72 | 26498.97 | 95377.33 | 50543.39
PRC 3352528PM4805 | 2024-11-13 | Inv. 100877.003-CA13 |  | 145920.72 | 2627.7 | 98005.03 | 47915.69
PRC 3352528PN4805 | 2024-12-19 | Inv. 100877.003-CA14 |  | 145920.72 | 2763.73 | 100768.76 | 45151.96
PRC 3352528PO4805 | 2025-01-14 | Inv. 100877.003-15 |  | 145920.72 | 5878.68 | 106647.44 | 39273.28
|  |  |  | 145920.72 |  | 106647.44 | 39273.28
|  |  |  | 145920.72 |  | 106647.44 | 39273.28
|  | Totals: | 145920.72 |  | 106647.44 |  | 39273.28
|  | CM Services | 91413.52 |  | 59607.02 |  | 31806.5
|  | Reimbursables | 10920 |  | 5319.5 |  | 5600.5
|  | Construction Fee | 43587.2 |  | 41720.92 |  | 1866.28
|  | Totals: | 145920.72 |  | 106647.44 |  | 39273.28

## RECAP #9253.00
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
| Program code 925300 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 777382.24
C | McGough Construction |  | 11219.41 | 11219.41 | 0
C | PM TIME |  | 15554.65 | 15554.65 | 0
C | Misc. |  | 1179.74 | 1179.74 | 0
C | Genesis Architectural |  | 13040 | 13040 | 0
C | Black Hawk Roof Co |  | 673440.35 | 673440.35 | 0
C | McGough Construction(2) |  | 62948.09 | 62948.09 | 0
| Total Project Cost | 777382.24 | 777382.24 | 777382.24 | 0 | 0
Closed 05/14/2024

## #9253.00 McGough Construction
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523318901 | 2022-11-10 | PO Procore | 13403.04 | 13403.04 |  |  | 13403.04
PRC 3352331PA8901 | 2022-12-09 | Inv. 100877.010-1 |  | 13403.04 | 669.83 | 669.83 | 12733.21
PRC 3352331PB8901 | 2023-01-13 | Inv. 100877.010PC2 |  | 13403.04 | 873.7 | 1543.53 | 11859.51
PRC 3352331PC8901 | 2023-02-10 | Inv. 100877.010PC3 |  | 13403.04 | 698.77 | 2242.3 | 11160.74
PRC 3352331PD8901 | 2023-03-13 | Inv. 100877.010PC4 |  | 13403.04 | 2971.66 | 5213.96 | 8189.08
PRC 3352331PE8901 | 2023-04-07 | Inv. 100877.010-05 |  | 13403.04 | 3510.62 | 8724.58 | 4678.46
PRC 3352331PF8901 | 2023-05-09 | Inv. 100877.010-06 |  | 13403.04 | 1687.33 | 10411.91 | 2991.13
PRC 3352331PG8901 | 2023-06-12 | Inv. 100877.010-07 Final | -2183.63 | 11219.41 | 807.5 | 11219.41 | 0
|  |  |  | 11219.41 |  | 11219.41 | 0
|  |  |  | 11219.41 |  | 11219.41 | 0
|  |  |  | 11219.41 |  | 11219.41 | 0
|  |  |  | 11219.41 |  | 11219.41 | 0
|  |  |  | 11219.41 |  | 11219.41 | 0
|  | Totals: | 11219.41 |  | 11219.41 |  | 0 | Final
|  | CM Services | 11083.91 |  | 11083.91 |  | 0
|  | Reimbursables | 135.5 |  | 135.5 |  | 0
|  | Totals: | 11219.41 |  | 11219.41 |  | 0

## #9253.00 PM TIME
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E243
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14404.2 | 14404.2 |  |  | 14404.2
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 14404.2 | 880 | 880 | 13524.2
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 880.57 | 15284.77 | 880.57 | 1760.57 | 13524.2
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 15284.77 | 551.02 | 2311.59 | 12973.18
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 15284.77 | 140.45 | 2452.04 | 12832.73
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 15284.77 | 1231.27 | 3683.31 | 11601.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 22.21 | 15306.98 | 22.21 | 3705.52 | 11601.46
CDE 33523075203 | 2023-03-07 | 2507 | Move to correct unit | -22.21 | 15284.77 | -22.21 | 3683.31 | 11601.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 187.44 | 15472.21 | 187.44 | 3870.75 | 11601.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 82.44 | 15554.65 | 82.44 | 3953.19 | 11601.46
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 15554.65 | 217.37 | 4170.56 | 11384.09
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 15554.65 | 1318.14 | 5488.7 | 10065.95
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 15554.65 | 304.05 | 5792.75 | 9761.9
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 15554.65 | 1337.35 | 7130.1 | 8424.55
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 15554.65 | 170.99 | 7301.09 | 8253.56
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 15554.65 | 1003.9 | 8304.99 | 7249.66
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 15554.65 | 129.7 | 8434.69 | 7119.96
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 15554.65 | 908.6 | 9343.29 | 6211.36
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 15554.65 | 52.29 | 9395.58 | 6159.07
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 15554.65 | 405.6 | 9801.18 | 5753.47
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 15554.65 | 19.49 | 9820.67 | 5733.98
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 15554.65 | 123.3 | 9943.97 | 5610.68
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 15554.65 | 67.52 | 10011.49 | 5543.16
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 15554.65 | 377.1 | 10388.59 | 5166.06
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 15554.65 | 163.78 | 10552.37 | 5002.28
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 15554.65 | 1138.7 | 11691.07 | 3863.58
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 15554.65 | 70.15 | 11761.22 | 3793.43
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 15554.65 | 565.5 | 12326.72 | 3227.93
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 15554.65 | 162.65 | 12489.37 | 3065.28
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 15554.65 | 1229.8 | 13719.17 | 1835.48
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 15554.65 | 25.17 | 13744.34 | 1810.31
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 15554.65 | 186.3 | 13930.64 | 1624.01
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 15554.65 | 49.16 | 13979.8 | 1574.85
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 15554.65 | 436.2 | 14416 | 1138.65
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 15554.65 | 61.65 | 14477.65 | 1077
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 15554.65 | 308.5 | 14786.15 | 768.5
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 15554.65 | 48.13 | 14834.28 | 720.37
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 15554.65 | 368.4 | 15202.68 | 351.97
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 15554.65 | 35.57 | 15238.25 | 316.4
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 15554.65 | 316.4 | 15554.65 | -1.3074e-12
[5 empty] | 15554.65 |  | 15554.65 | -1.3074e-12
[5 empty] | 15554.65 |  | 15554.65 | -1.3074e-12
[5 empty] | 15554.65 |  | 15554.65 | -1.3074e-12
[5 empty] | 15554.65 |  | 15554.65 | -1.3074e-12
|  |  | Totals: | 15554.65 |  | 15554.65 |  | 0
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Tue, Nov 1, 11:31 AM (2 days ago) to me Please create the following PM Time Budgets: 9253.00 $11,000.00 9325.00 $5,280.00 9326.00 $4,400.00 9327.00 $11,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Changes $Joni Kleene, Jennifer Jun 6, 2023, 3:46 PM (15 hours ago) to me, Scott DA23 9244.00 Please increase the PM Time budget by $1,100.00. MM23 9253.00 Please increase the PM Time budget by $7,400.00. MM21 9329.00 Please increase the PM Time budget by $6,300.00. MM21 9325.00 Please increase the PM Time budget by $3,100.00. Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9253.00 Misc
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523009900 | 2023-01-09 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2473120-Final | 1085 | 1085
PRC 33523159805 | 2023-06-08 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV030062 | 94.74 | 1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
1179.74
|  |  |  | Totals: |  | 1179.74

## #9253.00 Genesis Architectural
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 9253000-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523013800 | 2023-01-13 | PO Procore | 13040 | 13040 |  |  | 13040
PRC 3352301PA3800 | 2023-02-17 | Inv. 2301.01-01 |  | 13040 | 3150 | 3150 | 9890
PRC 3352301PB3800 | 2023-03-09 | Inv. 2301.01-02 |  | 13040 | 2115 | 5265 | 7775
PRC 3352301PC3800 | 2023-04-17 | Inv. 2301.01-03 |  | 13040 | 2665 | 7930 | 5110
PRC 3352301PD3800 | 2023-06-06 | Inv. 2301.01-04 |  | 13040 | 550 | 8480 | 4560
PRC 3352301PE3800 | 2023-07-06 | Inv. 2301.01-05 |  | 13040 | 228 | 8708 | 4332 | FY23
PO 33524013800 | 2023-07-24 | Roll to FY24 | 0 | 13040 |  | 8708 | 4332
PRC 3352401PF3800 | 2023-10-06 | Inv. 2301.01-06 |  | 13040 | 1140 | 9848 | 3192
PRC 3352401PG3800 | 2023-11-29 | Inv. 2301.01-07 |  | 13040 | 2508 | 12356 | 684
PRC 3352401PH3800 | 2024-01-04 | Inv. 2301.01-08 |  | 13040 | 456 | 12812 | 228
PRC 3352401PI3800 | 2024-03-20 | Inv. 2301.01-09 FINAL |  | 13040 | 228 | 13040 | 0
|  |  |  | 13040 |  | 13040 | 0
|  |  |  | 13040 |  | 13040 | 0
|  | Totals: | 13040 |  | 13040 |  | 0 | FINAL
|  | Design Development Phase | 3150 |  | 3150 |  | 0
|  | Construction Documents | 4230 |  | 4230 |  | 0
|  | Bid Phase | 1100 |  | 1100 |  | 0
|  | Construction Phase | 4560 |  | 4560 |  | 0
|  | Totals: | 13040 |  | 13040 |  | 0

## #9253.00 Black Hawk Roof Co
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
Black Hawk Roof Co |  |  | Vendor: 00002120676
Acct. Codes-0017-335-MM23-9255 |  |  | RFP 9253000-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523156900 | 2023-05-31 | PO Procore | 685400 | 685400 |  |  | 685400 | FY23
PO 33524156900 | 2023-07-24 | Roll to FY24 | 0 | 685400 |  | 0 | 685400
PRC 3352415PA6900 | 2023-10-12 | Inv. 9253.00-01 |  | 685400 | 506698.84 | 506698.84 | 178701.16 | 26668.36
PO 33524156900 | 2023-12-04 | CO #1 | -11959.65 | 673440.35 |  | 506698.84 | 166741.51
PRC 3352415PB6900 | 2023-12-12 | Inv. 9253.00-02 |  | 673440.35 | 99075.04 | 605773.88 | 67666.47 | 31882.84
PRC 3352415PC6900 | 2024-03-04 | Inv. 9253.00-04 |  | 673440.35 | 33994.45 | 639768.33 | 33672.02 | 33672.02
PRC 3352415PD6900 | 2024-03-18 | Inv. 9253.00-05-Retainage |  | 673440.35 | 33672.02 | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  |  |  | 673440.35 |  | 673440.35 | 0
|  | Totals: | 673440.35 |  | 673440.35 |  | 0 | FINAL

## #9253.00 McGough Constructi (2)
DOC FDCF Floyd and Bldg K Units Roof Replacements
Project # 9253.00
Program code 925300 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523156904 | 2023-06-02 | PO Procore | 107941.4 | 107941.4 |  |  | 107941.4
PRC 3352315PA6904 | 2023-07-07 | Inv. 100877.010-01 |  | 107941.4 | 840.41 | 840.41 | 107100.99 | FY23
PO 33524156904 | 2023-07-24 | Roll to FY24 | 0 | 107941.4 |  | 840.41 | 107100.99
PRC 3352415PB6904 | 2023-08-04 | Inv. 100877.010-02 |  | 107941.4 | 971.65 | 1812.06 | 106129.34
PRC 3352415PC6904 | 2023-09-15 | Inv. 100877.010-03 |  | 107941.4 | 2660.96 | 4473.02 | 103468.38
PRC 3352415PD6904 | 2023-10-11 | Inv. 100877.010-04 |  | 107941.4 | 32119.84 | 36592.86 | 71348.54
PRC 3352415PE6904 | 2023-11-13 | Inv. 100877.010-05 CA |  | 107941.4 | 7609.2 | 44202.06 | 63739.34
PRC 3352415PF6904 | 2023-12-13 | Inv. 100877.010-06 CA |  | 107941.4 | 11331.15 | 55533.21 | 52408.19
PRC 3352415PG6904 | 2024-01-17 | Inv. 100877.010-07 CA |  | 107941.4 | 2945.44 | 58478.65 | 49462.75
PRC 3352415PH6904 | 2024-02-06 | Inv. 100877.010-08 CA |  | 107941.4 | 659.23 | 59137.88 | 48803.52
PRC 3352415PI6904 | 2024-03-18 | Inv. 100877.010-09 CA |  | 107941.4 | 2505.34 | 61643.22 | 46298.18
PRC 3352415PJ6904 | 2024-04-04 | Inv. 100877.010-10 CA FINAL | -44993.31 | 62948.09 | 1304.87 | 62948.09 | 0
|  |  |  | 62948.09 |  | 62948.09 | 0
|  | Totals: | 62948.09 |  | 62948.09 |  | 0 | FINAL
|  | CM Services | 26907.09 |  | 26907.09 |  | 0
|  | Reimbursables | 1771 |  | 1771 |  | 0
|  | Construction Fees | 34270 |  | 34270 |  | 0
|  | Totals: | 62948.09 |  | 62948.09 |  | 0

## RECAP #9255.00
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
| Program code 925500 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 608883.56
C | Boyd Jones |  | 13440.51 | 13440.51 | 0
C | PM TIME |  | 28171.81 | 28171.81 | 0
C | Misc. |  | 104.13 | 104.13 | 0
C | Genesis Architectural |  | 18400 | 18400 | 0
C | Boyd Jones (2) |  | 52667.11 | 52667.11 | 0
C | Academy Roofing |  | 496100 | 496100 | 0
| Total Project Cost | 608883.56 | 608883.56 | 608883.56 | 0 | 0
Closed 01/29/2024

## #9255.00 Boyd Jones
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Boyd Jones |  |  | Vendor:00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP/B#: RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523341813 | 2022-12-07 | PO Procore | 18644.03 | 18644.03 |  |  | 18644.03
PRC 3352334PA1813 | 2023-01-10 | Inv. 9255.00-01 |  | 18644.03 | 1928.49 | 1928.49 | 16715.54
PRC 3352334PB1813 | 2023-02-14 | Inv. 9255.00-02 |  | 18644.03 | 2110.4 | 4038.89 | 14605.14
PRC 3352334PC1813 | 2023-03-22 | Inv. 9255.00-03 |  | 18644.03 | 1285.66 | 5324.55 | 13319.48
PRC 3352334PD1813 | 2023-04-11 | Inv. 9255.00-04 |  | 18644.03 | 4011.68 | 9336.23 | 9307.8
PRC 3352334PE1813 | 2023-05-22 | Inv. 9255.00-05-Final | -5203.52 | 13440.51 | 4104.28 | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  |  |  | 13440.51 |  | 13440.51 | 0
|  | Totals: | 13440.51 |  | 13440.51 |  | 0 | FINAL
|  | CM Services | 13286.51 |  | 13286.51 |  | 0
|  | Reimbursables | 154 |  | 154 |  | 0
|  | Totals: | 13440.51 |  | 13440.51 |  | 0

## #9255.00 PM TIME
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E242
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 27453.84 | 27453.84 |  |  | 27453.84
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 27453.84 | 55 | 55 | 27398.84
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 27453.84 | 385 | 440 | 27013.84
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 62.27 | 27516.11 | 62.27 | 502.27 | 27013.84
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 341.34 | 27857.45 | 341.34 | 843.61 | 27013.84
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 27857.45 | 1533.83 | 2377.44 | 25480.01
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 27857.45 | 223.37 | 2600.81 | 25256.64
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 27857.45 | 1958.17 | 4558.98 | 23298.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 7.57 | 27865.02 | 7.57 | 4566.55 | 23298.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 77.33 | 27942.35 | 77.33 | 4643.88 | 23298.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 229.46 | 28171.81 | 229.46 | 4873.34 | 23298.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 28171.81 | 220.62 | 5093.96 | 23077.85
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 28171.81 | 1337.85 | 6431.81 | 21740
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 28171.81 | 423.1 | 6854.91 | 21316.9
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 28171.81 | 1860.98 | 8715.89 | 19455.92
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 28171.81 | 292.24 | 9008.13 | 19163.68
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 28171.81 | 1720.7 | 10728.83 | 17442.98
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 28171.81 | 333.68 | 11062.51 | 17109.3
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 28171.81 | 2339.7 | 13402.21 | 14769.6
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 28171.81 | 178.89 | 13581.1 | 14590.71
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 28171.81 | 1444.5 | 15025.6 | 13146.21
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 28171.81 | 184.79 | 15210.39 | 12961.42
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 28171.81 | 1179.1 | 16389.49 | 11782.32
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 28171.81 | 433.51 | 16823 | 11348.81
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 28171.81 | 2422.2 | 19245.2 | 8926.61
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 28171.81 | 519.71 | 19764.91 | 8406.9
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 28171.81 | 3610.3 | 23375.21 | 4796.6
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 28171.81 | 368.12 | 23743.33 | 4428.48
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 28171.81 | 2955.8 | 26699.13 | 1472.68
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 28171.81 | 101.23 | 26800.36 | 1371.45
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 28171.81 | 765.8 | 27566.16 | 605.65
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 28171.81 | 72.45 | 27638.61 | 533.2
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 28171.81 | 533.2 | 28171.81 | 0
[5 empty] | 28171.81 |  | 28171.81 | 0
[5 empty] | 28171.81 |  | 28171.81 | 0
[5 empty] | 28171.81 |  | 28171.81 | 0
[5 empty] | 28171.81 |  | 28171.81 | 0
[5 empty] | 28171.81 |  | 28171.81 | 0
|  |  | Totals: | 28171.81 |  | 28171.81 |  | 0
Note on E9: Huggins, Joni [DAS]: Setup - PM Time Budgets on New Projects $Joni Tonyan, Brad 2:17 PM (11 minutes ago) to me, Scott, Brad Finance, Please set up the following PM time budgets below as these are new projects: 9255.00 - DOC NCF Building K (Admin) and CRC Boiler and Dorms 1 &2 Roof Replacement - $25,000 9319.00 - DOC NCF Building H (Main Server) and Master Control HVAC Replacement - $8,500 9321.00 - DVA IVH North Parking Lot Replacement - $17,000 9324.00 - DOC NCF Generator Switchgear Controls Replacement - $8,500 Thank you and please let me know once completed. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K Re: PM Time $John Tonyan, Brad 2:13 PM (15 minutes ago) to me, John John, Please increase the exact amount needed to post for each project. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Jan 9, 2024 at 2:12 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Brad I need specific amounts that you need each to be increased by for our audit...unless you are wanting each project increased by the exact amount i need to post? John On Tue, Jan 9, 2024 at 12:35 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: John and Finance, Please increase the PM time as needed from the project's contingency funds to cover for the following. DA21 9172.00 Amt. $654.50 MM22 9272.00 Amt. $748.00 MM23 9255.00 Amt. $513.70 MM23 9310.00 Amt. $981.20 MM23 9324.00 Amt. $1449.80 Thank you,

## #9255.00 Misc
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523166802 | 2023-06-15 | 9500 | CNST | Beeline & Blue (00002108204) | Inv. INV030080 | 104.13 | 104.13
104.13
104.13
104.13
104.13
104.13
104.13
104.13
104.13
104.13
104.13
104.13
|  |  |  | Totals: |  | 104.13

## #9255.00 Genesis Architectural
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor:00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP925500-01
Project Manager - Brad T. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523033900 | 2023-02-01 | PO Procore | 18400 | 18400 |  |  | 18400
PRC 3352303PA3900 | 2023-03-13 | Inv. 2302-01 |  | 18400 | 4700 | 4700 | 13700
PRC 3352303PB3900 | 2023-04-14 | Inv. 2302-02 |  | 18400 | 5500 | 10200 | 8200
PRC 3352303PC3900 | 2023-06-28 | Inv. 2302-03 |  | 18400 | 1700 | 11900 | 6500
PRC 3352303PD3900 | 2023-06-30 | Inv. 2302-04 |  | 18400 | 325 | 12225 | 6175 | FY23
PO 33524033900 | 2023-08-04 | Roll to FY24 | 0 | 18400 |  | 12225 | 6175
PRC 3352403PE3900 | 2023-11-28 | Inv. 2302-05 |  | 18400 | 5525 | 17750 | 650
PRC 3352403PF3900 | 2023-01-12 | Inv. 2302-06 FINAL |  | 18400 | 650 | 18400 | 0
|  |  |  | 18400 |  | 18400 | 0
|  |  |  | 18400 |  | 18400 | 0
|  |  |  | 18400 |  | 18400 | 0
|  |  |  | 18400 |  | 18400 | 0
|  |  |  | 18400 |  | 18400 | 0
|  | Totals: | 18400 |  | 18400 |  | 0
|  | Schematic Design | 2000 |  | 2000 |  | 0
|  | Design Development Phase | 3000 |  | 3000 |  | 0
|  | Construction Documents | 5200 |  | 5200 |  | 0
|  | Bid Phase | 1700 |  | 1700 |  | 0
|  | Construction Phase | 6500 |  | 6500 |  | 0
|  | Totals: | 18400 |  | 18400 |  | 0

## #9255.00 Boyd Jones (2)
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Boyd Jones |  |  | Vendor:00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP/B#: RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523138901 | 2023-05-18 | PO Procore | 55752.72 | 55752.72 |  |  | 55752.72
PRC 3352313PA8901 | 2023-06-12 | Inv. 9255.00-001 |  | 55752.72 | 2133.94 | 2133.94 | 53618.78
PRC 3352313PB8901 | 2023-07-11 | Inv. 9255.00-002 |  | 55752.72 | 1373.56 | 3507.5 | 52245.22 | FY23
PO 33524138901 | 2023-08-04 | Roll to FY24 | 0 | 55752.72 |  | 3507.5 | 52245.22
PRC 3352413PC8901 | 2023-08-23 | Inv. 9255.00-003 |  | 55752.72 | 2158.29 | 5665.79 | 50086.93
PRC 3352413PD8901 | 2023-09-25 | Inv. 9255.00-004 |  | 55752.72 | 14279.97 | 19945.76 | 35806.96
PRC 3352413PE8901 | 2023-10-12 | Inv. 9255.00-005 |  | 55752.72 | 21729.64 | 41675.4 | 14077.32
PRC 3352413PF8901 | 2023-11-14 | Inv. 9255.00-006 |  | 55752.72 | 4970.28 | 46645.68 | 9107.04
PRC 3352413PG8901 | 2024-01-22 | Inv. 9255.00-007 - Final | -3085.61 | 52667.11 | 6021.43 | 52667.11 | 0
|  |  |  | 52667.11 |  | 52667.11 | 0
|  |  |  | 52667.11 |  | 52667.11 | 0
|  |  |  | 52667.11 |  | 52667.11 | 0
|  |  |  | 52667.11 |  | 52667.11 | 0
|  | Totals: | 52667.11 |  | 52667.11 |  | 0 | FINAL
|  | CM Services | 27032.11 |  | 27032.11 |  | 0
|  | Reimbursables | 660 |  | 660 |  | 0
|  | CM Fee | 24975 |  | 24975 |  | 0
|  | Totals: | 52667.11 |  | 52667.11 |  | 0

## #9255.00 Academy Roofing
DOC NCF Bldg K and CRC Roof Replacement
Project # 9255.00
Program code 925500 |  |  | Major Program 4E02
Academy Roofing |  |  | Vendor:00003010234
Acct. Codes-0017-335-MM23-9255 |  |  | RFB925500-01
Project Manager - Brad T. |  |  | Activity code:BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523143800 | 2023-05-23 | PO Procore | 499500 | 499500 |  |  | 499500 |  | FY23
PO 33524143800 | 2023-08-04 | Roll to FY24 | 0 | 499500 |  | 0 | 499500
PRC 3352414PA3800 | 2023-09-12 | Inv. 9255.00-01 |  | 499500 | 266585.2 | 266585.2 | 232914.8 | 14030.8
PRC 3352414PB3800 | 2023-10-17 | Inv. 9255.00-02 |  | 499500 | 174163.5 | 440748.7 | 58751.3 | 23197.3
PO 33524143800 | 2023-10-27 | CO #1 | -3400 | 496100 |  | 440748.7 | 55351.3
PRC 3352414PC3800 | 2023-11-17 | Inv. 9255.00-03 |  | 496100 | 25796.3 | 466545 | 29555 | 24555
PRC 3352414PD3800 | 2023-12-13 | Inv. 9255.00-04 |  | 496100 | 4750 | 471295 | 24805 | 24805
PRC 3352414PE3800 | 2024-01-03 | Inv. 9255.00-05 - Retainage |  | 496100 | 24805 | 496100 | 0
|  |  |  | 496100 |  | 496100 | 0
|  |  |  | 496100 |  | 496100 | 0
|  |  |  | 496100 |  | 496100 | 0
|  |  |  | 496100 |  | 496100 | 0
|  |  |  | 496100 |  | 496100 | 0
|  | Totals: | 496100 |  | 496100 |  | 0

## RECAP #9268.01
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
| Program code 926801 |  |  | Major Program 4E17
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 815000
C | DCI Group |  | 38550.17 | 38550.17 | 0
| PM TIME |  | 29280 | 28276.66 | 1003.34
| Misc. |  | 6016.64 | 6016.64 | 0
| Shive Hattery |  | 85478 | 83430.52 | 2047.48
C | Terracon Consultants |  | 40696.99 | 40696.99 | 0
| DCI Group #22-009 CA |  | 61752.45 | 34509.01 | 27243.44
| Pullman SST |  | 372150.59 | 327471.26 | 44679.33
| Iowa Contracting |  | 114642 | 70157.5 | 44484.5
| DCI Group #22-009.1 CA |  | 18694.57 | 12622.44 | 6072.13
C | DCI Group #22-009.2 PC |  | 3832.68 | 3832.68 | 0
C | Neumann Brothers |  | 26500 | 26500 | 0
| DCI Group #22-009.2 CA |  | 12623.76 | 3513.88 | 9109.88
| Total Project Cost | 815000 | 810217.85 | 675577.75 | 134640.1 | 4782.15

## #9268.01 DCI Group
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group #22-009.1 PC |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Split with R22M and DA23(9268.02)
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523013801 | 2023-01-13 | PO Procore | 13812.35 | 13812.35 |  |  | 13812.35
PRC 3352301PA3801 | 2023-03-20 | Inv. 22-009.1 PC-01 (Split with R22M) |  | 13812.35 | 3820.44 | 3820.44 | 9991.91
PRC 3352301PB3801 | 2023-04-25 | Inv. 22-009.1 PC-02 (100% to MM23) |  | 13812.35 | 3054.28 | 6874.72 | 6937.63
PO 33523013801 | 2023-05-19 | CO 1 | 25180.06 | 38992.41 |  | 6874.72 | 32117.69
PRC 3352301PC3801 | 2023-07-06 | Inv. 22-009.1 PC-03 (100% to MM23) |  | 38992.41 | 10094.63 | 16969.35 | 22023.06
PO 33523013801 | 2023-07-12 | CO #2 (100% to DA23) | 0 | 38992.41 |  | 16969.35 | 22023.06
PRC 3352301PD3801 | 2023-07-28 | Inv. 22-009.1 PC 04 (Split between MM23 and DA23) |  | 38992.41 | 11773 | 28742.35 | 10250.06 | FY23
PO 33524013801 | 2023-08-25 | Roll to FY24 | 0 | 38992.41 |  | 28742.35 | 10250.06
PRC 3352401PE3801 | 2023-11-13 | Inv. 22-009.1 PC-05 (Split between MM23 and R22M) |  | 38992.41 | 1387.04 | 30129.39 | 8863.02
PRC 3352401PF3801 | 2023-11-16 | Inv. 22-009.1 PC-06 (100% to MM23) |  | 38992.41 | 6810.88 | 36940.27 | 2052.14
PRC 3352401PG3801 | 2023-12-21 | Inv. 22-009.1 PC 07 FINAL | -442.24 | 38550.17 | 1609.9 | 38550.17 | 3.8654e-12
|  |  |  | 38550.17 |  | 38550.17 | 3.8654e-12
|  |  |  | 38550.17 |  | 38550.17 | 3.8654e-12
|  | Totals: | 38550.17 |  | 38550.17 |  | 0 | FINAL
|  | DA23(Closed 07/28/23) | 2250.46 |  | 2250.46 |  | 0
|  | R22M(Closed 12/21/23) | 3440.17 |  | 3440.17 |  | 0
|  | Total Contract: | 44240.8 |  | 44240.8 |  | 0

## #9268.01 PM TIME
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  |  | Major Program 4E17
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E248
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 29280 | 29280 |  |  | 29280
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 29280 | 97.18 | 97.18 | 29182.82
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 29280 | 851.92 | 949.1 | 28330.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 40.54 | 29320.54 | 40.54 | 989.64 | 28330.9
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | -40.54 | 29280 | -40.54 | 949.1 | 28330.9
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 29280 | 237.33 | 1186.43 | 28093.57
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 29280 | 1439.21 | 2625.64 | 26654.36
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 29280 | 263.51 | 2889.15 | 26390.85
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 29280 | 1159.04 | 4048.19 | 25231.81
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 29280 | 209.71 | 4257.9 | 25022.1
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 29280 | 1232.1 | 5490 | 23790
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 29280 | 250.94 | 5740.94 | 23539.06
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 29280 | 1758.9 | 7499.84 | 21780.16
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 29280 | 104.79 | 7604.63 | 21675.37
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 29280 | 814.9 | 8419.53 | 20860.47
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 29280 | 187.84 | 8607.37 | 20672.63
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 29280 | 1197.1 | 9804.47 | 19475.53
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 29280 | 118.61 | 9923.08 | 19356.92
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 29280 | 661.3 | 10584.38 | 18695.62
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 29280 | 22.54 | 10606.92 | 18673.08
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 29280 | 154.8 | 10761.72 | 18518.28
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 29280 | 130.13 | 10891.85 | 18388.15
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 29280 | 1044.1 | 11935.95 | 17344.05
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 29280 | 148.59 | 12084.54 | 17195.46
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 29280 | 1122.8 | 13207.34 | 16072.66
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 29280 | 88.72 | 13296.06 | 15983.94
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 29280 | 651.6 | 13947.66 | 15332.34
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 29280 | 11.11 | 13958.77 | 15321.23
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 29280 | 96.6 | 14055.37 | 15224.63
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 29280 | 113.56 | 14168.93 | 15111.07
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 29280 | 572.2 | 14741.13 | 14538.87
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 29280 | 152.02 | 14893.15 | 14386.85
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 29280 | 1152.1 | 16045.25 | 13234.75
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 29280 | 86.47 | 16131.72 | 13148.28
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 29280 | 768.4 | 16900.12 | 12379.88
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 29280 | 119.9 | 17020.02 | 12259.98
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 29280 | 994.3 | 18014.32 | 11265.68
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 29280 | 185.29 | 18199.61 | 11080.39
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 29280 | 1694.8 | 19894.41 | 9385.59
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 29280 | 157.7 | 20052.11 | 9227.89
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 29280 | 1720 | 21772.11 | 7507.89
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 29280 | 408.31 | 22180.42 | 7099.58
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 29280 | 2080 | 24260.42 | 5019.58
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 30,2024 |  | 29280 | 118.33 | 24378.75 | 4901.25
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 29280 | 1051.4 | 25430.15 | 3849.85
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 29280 | 85.86 | 25516.01 | 3763.99
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 29280 | 573.4 | 26089.41 | 3190.59
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 29280 | 188.19 | 26277.6 | 3002.4
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 29280 | 1248.4 | 27526 | 1754
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 29280 | 68.06 | 27594.06 | 1685.94
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 29280 | 682.6 | 28276.66 | 1003.34
[5 empty] | 29280 |  | 28276.66 | 1003.34
[5 empty] | 29280 |  | 28276.66 | 1003.34
[5 empty] | 29280 |  | 28276.66 | 1003.34
|  |  | Totals: | 29280 |  | 28276.66 |  | 1003.34
Note on E9: Huggins, Joni [DAS]: 9268.01 PM Time $Joni Herman, Josh Jan 18, 2023, 10:05 AM (23 hours ago) to me Please set PM Time for the following in 9268.01 MM23 $11,000 R22M $2,750 Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov PM Time Changes Inbox Kleene, Jennifer 12:20 PM (1 hour ago) to me, Scott MM23 9268.01 Please increase the PM Time budget by $7,480.00. MM22 9248.00 Please increase the PM Time budget by $2,992.00. MM22 9279.30 Please increase the PM Time budget by $7,480.00. Regards, Jennifer PM Time Changes $Joni Kleene, Jennifer 11:59 AM (29 minutes ago) to me, Scott For MM22 9244.00, please increase the PM Time budget by $4,000.00 For MM23 9268.01, please increase the PM Time budget by $8,800.00 For DA22 9216.00, please increase the PM Time budget by $4,000.00 For DA23 9293.00, please increase the PM Time budget by $3,500.00 For DA24 9377.00, please increase the PM Time budget by $4,400.00 Re: November PM Time $Joni Kleene, Jennifer Dec 10, 2024, 5:20 PM (13 hours ago) to Scott, me OK. In that case, please increase the PM Time budgets as follows: MM22 9244.00 Increase by $1,000 MM23 9268.01 Increase by $2,000 Regards, Jennifer

## #9268.01 Misc
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  |  | Major Program 4E17
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523193904 | 2023-07-12 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2507886 | 1068.75 | 1068.75
PRC 33524338802 | 2023-12-04 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV035463 | 108.13 | 1176.88
CDE 33524012800 | 2024-01-12 | 2507 |  | Move Expense from 9186.01 to 9268.01 Nov Procurement time |  | 330 | 1506.88
PRC 33524043800 | 2024-02-12 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010660-IN-Final | 1816.72 | 3323.6
GAX 33524187911 | 2024-07-05 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2576392 | 751.25 | 4074.85
IET DAS202412115300001 | 2024-07-10 | 2507 |  | HVAC | DAS2024121153 | 330 | 4404.85
IET DAS202501115300001 | 2024-08-07 | 2507 |  | Fire Watch Service July 1-31, 2024 | DAS2025011153 | 365.36 | 4770.21
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Fire Watch Service August 1-31, 2024 | DAS2025021153 | 182.68 | 4952.89
PRC 33525276901 | 2024-10-02 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2599214 | 1063.75 | 6016.64
6016.64
6016.64
6016.64
|  |  |  | Totals: |  | 6016.64

## #9268.01 Shive Hattery
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP9268.00-02
Project Manager - Jennifer K. |  |  | Activity code:DSGN
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523045903 | 2023-02-14 | PO Procore | 57800 | 57800 |  |  | 57800
PO 33523045903 | 2023-07-06 | CO #1 (100% to DA23 9268.02) |  | 57800 |  | 0 | 57800
PRC 3352304PA5903 | 2023-07-17 | Inv. 2142201940-101 (Split Between MM23, DA23, and R22M) |  | 57800 | 23580 | 23580 | 34220 | FY23
PO 33524045903 | 2023-08-25 | Roll to FY24 | 0 | 57800 |  | 23580 | 34220
PO 33524045903 | 2023-08-29 | CO #2 (No Cost) | 0 | 57800 |  | 23580 | 34220
PRC 3352404PB5903 | 2023-08-30 | Inv. 2142201940-102 (Split Between MM23 and R22M) |  | 57800 | 11880 | 35460 | 22340
PRC 3352404PC5903 | 2023-10-12 | Inv. 2142201940-103 (Split Between MM23, DA23, and R22M) |  | 57800 | 4950 | 40410 | 17390
PRC 3352404PD5903 | 2023-12-13 | Inv. 2142201940-104 (Split Between MM23 and DA23) |  | 57800 | 3090 | 43500 | 14300
PO 33524045903 | 2024-02-09 | CO #3 (100% to MM23) | 19904 | 77704 |  | 43500 | 34204
PRC 3352404PE5903 | 2024-03-18 | Inv. 2142201940-105 (Split Between MM23 and R22M) |  | 77704 | 1063 | 44563 | 33141
PRC 3352404PF5903 | 2024-03-20 | Inv. 2142201940-106 |  | 77704 | 4680 | 49243 | 28461
PRC 3352404PG5903 | 2024-04-30 | Inv. 2142201940-107 |  | 77704 | 8903 | 58146 | 19558
PRC 3352404PH5903 | 2024-06-04 | Inv. 2142201940-108 |  | 77704 | 1986 | 60132 | 17572
PO 33524045903 | 2024-06-17 | CO #4 | 8670 | 86374 |  | 60132 | 26242
PRC 3352404PI5903 | 2024-07-08 | Inv. 2142201940-109 |  | 86374 | 10179.88 | 70311.88 | 16062.12 | FY24
PO 33525045903 | 2024-07-23 | Roll to FY25 |  | 86374 |  | 70311.88 | 16062.12
PRC 3352504PJ5903 | 2024-08-15 | Inv. 2142201940-110 |  | 86374 | 5906.42 | 76218.3 | 10155.7
PO 33525045903 | 2024-08-22 | CO #5(100% To X674) | 0 | 86374 |  | 76218.3 | 10155.7
PRC 3352504PK5903 | 2024-09-13 | Inv. 2142201940-111(Split Between X674 & MM23) |  | 86374 | 0 | 76218.3 | 10155.7
PRC 3352504PK5903B* | 2024-09-13 | Inv. 2142201940-111B(Split Between X674 & MM23) |  | 86374 | 5690 | 81908.3 | 4465.7
PRC 3352504PL5903 | 2024-10-30 | Inv. 2142201940-112(100% to MM23) |  | 86374 | 1522.22 | 83430.52 | 2943.48
PO 33525045903 | 2024-12-10 | CO #6(100% To MM23) | -896 | 85478 |  | 83430.52 | 2047.48
|  |  |  | 85478 |  | 83430.52 | 2047.48
|  |  |  | 85478 |  | 83430.52 | 2047.48
|  |  |  | 85478 |  | 83430.52 | 2047.48
|  | Totals: | 85478 |  | 83430.52 |  | 2047.48
|  | Curtain Grouting Repair Design | 21600 |  | 21600 |  | 0
|  | Curtain Grouting Repair Docs | 19800 |  | 19800 |  | 0
|  | Bidding/Quoting Phase Services | 2100 |  | 2100 |  | 0
|  | Construction Phase Services | 14300 |  | 13442 |  | 858
|  | CO #3 | 19904 |  | 19798.52 |  | 105.48
|  | CO #4 | 8670 |  | 6690 |  | 1980
|  | CO #6 | -896 |  |  |  | -896
|  | Totals: | 85478 |  | 83430.52 |  | 2047.48
|  | 9268.02 DA23(Closed on 12/13/2023) | 6860 |  | 6860 |  | 0
|  | 9268.01 R22M(Closed on 03/18/2024) | 42400 |  | 42400 |  | 0
|  | 9268.01 X674(Closed 09/23/2024) | 1075 |  | 1075 |  | 0
|  | Total Contract: | 135813 |  | 133765.52 |  | 2047.48
*Because this is split between departments, it must be two separate documents per SAE

## #9268.01 Terracon Consultants
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
Terracon Consultants |  |  | Vendor:00002116512
Acct. Codes-0017-335-MM23-9260 |  |  | IRFP926800-02
Project Manager - Jennifer K. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523123803 | 2023-05-03 | PO Procore | 32300 | 32300 |  |  | 32300
PRC 3352312PA3803 | 2023-05-30 | Inv. TJ44768 |  | 32300 | 4845 | 4845 | 27455
PO 33523123803 | 2023-06-15 | CO #1 | 17790 | 50090 |  | 4845 | 45245
PRC 3352312PB3803 | 2023-06-21 | Inv. 9268.01-02 |  | 50090 | 4000 | 8845 | 41245
PRC 3352312PC3803 | 2023-07-28 | Inv. TJ74605 |  | 50090 | 25201.99 | 34046.99 | 16043.01 | FY23
PO 33524123803 | 2023-08-04 | Roll to FY24 | 0 | 50090 |  | 34046.99 | 16043.01
PRC 3352412PD3803 | 2023-08-25 | Inv. 9268.01-04-Final | -9393.01 | 40696.99 | 6650 | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  |  |  | 40696.99 |  | 40696.99 | 0
|  | Totals: | 40696.99 |  | 40696.99 |  | 0 | FINAL
|  | Field Services | 15250 |  | 15250 |  | 0
|  | Laboratory Services | 5300 |  | 5300 |  | 0
|  | Engineering Services | 8350 |  | 8350 |  | 0
|  | Piezometers | 1700 |  | 1700 |  | 0
|  | CO #1 | 10096.99 |  | 10096.99 |  | 0
|  | Totals: | 40696.99 |  | 40696.99 |  | 0

## #9268.01 DCI Group #22-009 CA
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group #22-009 CA |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524293803 | 2023-10-20 | PO Procore | 61752.45 | 61752.45 |  |  | 61752.45
PRC 3352429PA3803 | 2023-12-21 | Inv. 22-009 CA-01 |  | 61752.45 | 2246.66 | 2246.66 | 59505.79
PRC 3352429PB3803 | 2024-01-29 | Inv. 9268.01-02 |  | 61752.45 | 1244.21 | 3490.87 | 58261.58
PRC 3352429PC3803 | 2024-03-01 | Inv. 9268.01-03 |  | 61752.45 | 2473.79 | 5964.66 | 55787.79
PRC 3352429PD3803 | 2024-05-02 | Inv. 22-009 CA 04 |  | 61752.45 | 6283.32 | 12247.98 | 49504.47
PRC 3352429PE3803 | 2024-06-18 | Inv. 22-009 CA 05 |  | 61752.45 | 2433.72 | 14681.7 | 47070.75
PRC 3352429PF3803 | 2024-07-18 | Inv. 22-009 CA 06 |  | 61752.45 | 8988.99 | 23670.69 | 38081.76 | FY24
PO 33525293803 | 2024-07-23 | Rolled to FY25 |  | 61752.45 |  | 23670.69 | 38081.76
PRC 3352529PG3803 | 2024-09-06 | Inv. 22-009 CA 07 |  | 61752.45 | 10371.76 | 34042.45 | 27710
PRC 3352529PH3803 | 2024-10-15 | Inv. 22-009 CA 08 |  | 61752.45 | 466.56 | 34509.01 | 27243.44
|  |  |  | 61752.45 |  | 34509.01 | 27243.44
|  |  |  | 61752.45 |  | 34509.01 | 27243.44
|  |  |  | 61752.45 |  | 34509.01 | 27243.44
|  | Totals: | 61752.45 |  | 34509.01 |  | 27243.44

## #9268.01 Pullman SST
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
Pullman SST |  |  | Vendor:VS000009495
Acct. Codes-0017-335-MM23-9255 |  |  | RFB926801-01
Project Manager - Jennifer K. |  |  | Activity code:BRUM
Split W/X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524347800 | 2023-12-13 | PO Procore | 376833 | 376833 |  |  | 376833
PRC 3352434PA7800 | 2024-03-26 | Inv. 657634-001 |  | 376833 | 9500 | 9500 | 367333 | 500
PRC 3352434PB7800 | 2024-06-20 | Inv. 657634-002 |  | 376833 | 114876.85 | 124376.85 | 252456.15 | 6546.15
PRC 3352434PC7800 | 2024-07-16 | Inv. 657634-03 |  | 376833 | 70300 | 194676.85 | 182156.15 | 10246.15 | FY24
PO 33525347800 | 2024-07-23 | Roll to FY25 |  | 376833 |  | 194676.85 | 182156.15
PO 33525347800 | 2024-08-19 | CO #1 | -4682.41 | 372150.59 |  | 194676.85 | 177473.74
PRC 3352534PD7800 | 2024-09-06 | Inv. 657634-004(100% to MM23) |  | 372150.59 | 132794.41 | 327471.26 | 44679.33 | 17235.33
PO 33525347800 | 2024-12-04 | CO #2 (No Cost CO) | 0 | 372150.59 |  | 327471.26 | 44679.33
|  |  |  | 372150.59 |  | 327471.26 | 44679.33
|  |  |  | 372150.59 |  | 327471.26 | 44679.33
|  |  |  | 372150.59 |  | 327471.26 | 44679.33
|  |  |  | 372150.59 |  | 327471.26 | 44679.33
|  |  |  | 372150.59 |  | 327471.26 | 44679.33
|  | Totals: | 372150.59 |  | 327471.26 |  | 44679.33
|  | X674 9268.01 | 15096.47 |  | 0 |  | 15096.47
|  | Total Contract | 387247.06 |  | 327471.26 |  | 59775.8

## #9268.01 Iowa Contracting
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
Iowa Contracting |  |  | Vendor: 00003106386
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ #926801-02
Project Manager - Jennifer K. |  |  | Activity code:BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524169902 | 2023-12-13 | PO Procore | 74850 | 74850 |  |  | 74850 |  | FY24
PO 33525169902 | 2024-07-23 | Roll to FY25 |  | 74850 |  | 0 | 74850
PRC 3352516PA9902 | 2024-09-06 | Inv. 9268.01-01 |  | 74850 | 70157.5 | 70157.5 | 4692.5 | 3692.5
PO 33525169902 | 2024-12-05 | CO #1 | 39792 | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  |  |  | 114642 |  | 70157.5 | 44484.5
|  | Totals: | 114642 |  | 70157.5 |  | 44484.5

## #9268.01 DCI Group #22-009.1 CA
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group #22-009.1 CA |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525184902 | 2024-07-02 | PO Procore | 16664.57 | 16664.57 |  |  | 16664.57
PO 33525184902 | 2024-08-22 | CO #1 | 2030 | 18694.57 |  | 0 | 18694.57
PRC 3352518PA4902 | 2024-09-25 | Inv. 9268.01-01 |  | 18694.57 | 9578.08 | 9578.08 | 9116.49
PRC 3352518PB4902 | 2024-10-30 | Inv. 22-009.1 CA 02 |  | 18694.57 | 507.18 | 10085.26 | 8609.31
PRC 3352518PC4902 | 2025-01-24 | Inv. 22-009.1 CA 03 |  | 18694.57 | 2537.18 | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  |  |  | 18694.57 |  | 12622.44 | 6072.13
|  | Totals: | 18694.57 |  | 12622.44 |  | 6072.13

## #9268.01 DCI Group #22-009.2 PC
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group #22-009.2 PC |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525184901 | 2024-07-02 | PO Procore | 6740.17 | 6740.17 |  |  | 6740.17
PRC 3352518PA4901 | 2024-10-18 | Inv. 22-009.2 PC 01 |  | 6740.17 | 2343.06 | 2343.06 | 4397.11
PRC 3352518PB4901 | 2024-12-03 | Inv. 22-009.2 PC 02 |  | 6740.17 | 1489.62 | 3832.68 | 2907.49
PO 33525184901 | 2024-12-19 | Closing PO Per PM | -2907.49 | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  |  |  | 3832.68 |  | 3832.68 | 0
|  | Totals: | 3832.68 |  | 3832.68 |  | 0

## #9268.01 Neumann Brothers
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
Neumann Brothers |  |  | Vendor: 00002106354
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ926801-03
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525284902 | 2024-10-10 | PO Procore | 26500 | 26500 |  |  | 26500
PRC 3352528PA4902 | 2024-12-19 | Inv. 56652 |  | 26500 | 24225 | 24225 | 2275 | 1275
PRC 3352528PB4902 | 2025-01-17 | Inv. 56696 |  | 26500 | 950 | 25175 | 1325 | 1325
PRC 3352528PC4902 | 2025-01-31 | Inv. 56728-Retainage |  | 26500 | 1325 | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  |  |  | 26500 |  | 26500 | 0
|  | Totals: | 26500 |  | 26500 |  | 0 | FINAL

## #9268.01 DCI Group #22-009.2 CA
DAS CC Tunnel System Infiltration Mitigation
Project # 9268.01
Program code 926801 |  |  | Major Program 4E17
DCI Group #22-009.2 CA |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525289900 | 2024-10-15 | PO Procore | 12623.76 | 12623.76 |  |  | 12623.76
PRC 3352528PA9900 | 2024-12-19 | Inv. 22-009.2 CA 01 |  | 12623.76 | 2624.48 | 2624.48 | 9999.28
PRC 3352528PB9900 | 2025-01-03 | Inv. 22-009.2 CA 02 |  | 12623.76 | 889.4 | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  |  |  | 12623.76 |  | 3513.88 | 9109.88
|  | Totals: | 12623.76 |  | 3513.88 |  | 9109.88

## RECAP #9270.00
DOC ASP Tuckpointing Priority 4
Project # 9270.00
| Program code 927000 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 776497.58
C | Story Construction |  | 63097.55 | 63097.55 | 0
C | PM TIME |  | 4764.89 | 4764.89 | 0
C | Misc. |  | 183.14 | 183.14 | 0
C | BiState Masonry |  | 695521 | 695521 | 0
C | RDG Planning & Design |  | 12931 | 12931 | 0
| Total Project Cost | 776497.58 | 776497.58 | 776497.58 | 0 | 0
Closed 12/09/24

## #9270.00 Story Construction
DOC ASP Tuckpointing Priority 4
Project # 9270.00
Program code 927000 |  |  | Major Program 4E10
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523259904 | 2022-09-16 | PO Procore | 61759.84 | 61759.84 |  |  | 61759.84
PRC 3352325PA9904 | 2022-11-29 | Inv. 33463 |  | 61759.84 | 2935 | 2935 | 58824.84
PRC 3352325PB9904 | 2022-12-20 | Inv. 33515 |  | 61759.84 | 440 | 3375 | 58384.84
PRC 3352325PC9904 | 2023-04-18 | Inv. 33732 |  | 61759.84 | 2205 | 5580 | 56179.84
PRC 3352325PD9904 | 2023-05-22 | Inv. 33787 |  | 61759.84 | 12137 | 17717 | 44042.84
PRC 3352325PE9904 | 2023-06-21 | Inv. 33835 |  | 61759.84 | 18493 | 36210 | 25549.84
PRC 3352325PF9904 | 2023-07-18 | Inv. 33893 |  | 61759.84 | 3427 | 39637 | 22122.84
PO 33523259904 | 2023-07-21 | CO #1 | 1393.2 | 63153.04 |  | 39637 | 23516.04 | FY23
PO 33524259904 | 2023-07-26 | Rolled to FY24 | 0 | 63153.04 |  | 39637 | 23516.04
PRC 3352425PG9904 | 2023-08-21 | Inv. 33950 |  | 63153.04 | 4162 | 43799 | 19354.04
PRC 3352425PH9904 | 2023-09-18 | Inv. 34004 |  | 63153.04 | 5291 | 49090 | 14063.04
PRC 3352425PI9904 | 2023-10-17 | Inv. 34065 |  | 63153.04 | 1001 | 50091 | 13062.04
PRC 3352425PJ9904 | 2023-11-21 | Inv. 34118 |  | 63153.04 | 1355 | 51446 | 11707.04
PRC 3352425PK9904 | 2023-12-20 | Inv. 34159 |  | 63153.04 | 923 | 52369 | 10784.04
PO 33524259904 | 2024-02-01 | CO #2 | 1782.05 | 64935.09 |  | 52369 | 12566.09
PRC 3352425PL9904 | 2024-02-24 | Inv. 34247 |  | 64935.09 | 996 | 53365 | 11570.09
PRC 3352425PM9904 | 2024-04-22 | Inv. 34320 |  | 64935.09 | 1462.5 | 54827.5 | 10107.59
PRC 3352425PN9904 | 2024-05-17 | Inv. 34354 |  | 64935.09 | 629 | 55456.5 | 9478.59
PRC 3352425PO9904 | 2024-06-17 | Inv. 34391 |  | 64935.09 | 3517 | 58973.5 | 5961.59
PRC 3352425PP9904 | 2024-07-17 | Inv. 34437 |  | 64935.09 | 2797.05 | 61770.55 | 3164.54 | FY24
PO 33525259904 | 2024-07-24 | Rolled to FY25 |  | 64935.09 |  | 61770.55 | 3164.54
PRC 3352525PQ9904 | 2024-09-13 | Inv. 34514 |  | 64935.09 | 1152 | 62922.55 | 2012.54
PRC 3352525PR9904 | 2024-11-21 | Inv. 34604 Final | -1837.54 | 63097.55 | 175 | 63097.55 | 0
|  | Totals: | 63097.55 |  | 63097.55 |  | 0 | FINAL
|  | CM Services | 27661.5 |  | 27661.5 |  | 0
|  | Reimbursables | 660 |  | 660 |  | 0
|  | Fees (5%) | 31600.8 |  | 31600.8 |  | 0
|  | CO #1 | 1393.2 |  | 1393.2 |  | 0
|  | CO#2 | 1782.05 |  | 1782.05 |  | 0
|  | Totals: | 63097.55 |  | 63097.55 |  | 0

## #9270.00 PM TIME
DOC ASP Tuckpointing Priority 4
Project # 9270.00
Program code 927000 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 908G
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 5248.58 | 5248.58 |  |  | 5248.58
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 5248.58 | 68.47 | 68.47 | 5180.11
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 5248.58 | 415.22 | 483.69 | 4764.89
CDE 33523080900 | 2023-03-21 | 2507 | Move Finance support Time to MM21 9270.00 | -68.47 | 5180.11 | -68.47 | 415.22 | 4764.89
CDE 33523080900 | 2023-03-21 | 9500 | Move DAS Service Time to MM21 9270.00 | -415.22 | 4764.89 | -415.22 | 0 | 4764.89
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 4764.89 | 115.48 | 115.48 | 4649.41
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 4764.89 | 733.9 | 849.38 | 3915.51
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 4764.89 | 94.8 | 944.18 | 3820.71
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 4764.89 | 527.4 | 1471.58 | 3293.31
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 4764.89 | 60.67 | 1532.25 | 3232.64
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 4764.89 | 422.8 | 1955.05 | 2809.84
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 4764.89 | 29.15 | 1984.2 | 2780.69
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 4764.89 | 255.5 | 2239.7 | 2525.19
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 4764.89 | 37.87 | 2277.57 | 2487.32
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 4764.89 | 350 | 2627.57 | 2137.32
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 4764.89 | 27.32 | 2654.89 | 2110
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 4764.89 | 302.3 | 2957.19 | 1807.7
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 4764.89 | 87.32 | 3044.51 | 1720.38
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 4764.89 | 445.6 | 3490.11 | 1274.78
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4764.89 | 88.33 | 3578.44 | 1186.45
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4764.89 | 788 | 4366.44 | 398.45
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4764.89 | 11.52 | 4377.96 | 386.93
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4764.89 | 80 | 4457.96 | 306.93
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 4764.89 | 40.33 | 4498.29 | 266.6
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 4764.89 | 266.6 | 4764.89 | 0
[5 empty] | 4764.89 |  | 4764.89 | 0
|  |  | Totals: | 4764.89 |  | 4764.89 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time - 9270.00 - MM 23 FY23 Elliott, Jennie 7:39 AM (52 minutes ago) to me Can you please increase PM to $7,000 in "Contracted" in project 9270.00 DOC ASP Tuckpointing Priority 4 in MM23. Thank you, Jennie Elliott, Owner's Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 jennie.elliott@iowa.gov https://das.iowa.gov

## #9270.00 Misc
DOC ASP Tuckpointing Priority 4
Project # 9270.00
Program code 927000 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523336805 | 2022-12-02 | 9500 | CNST | Rapid Reporductions (V#00002111375) | Inv. 42037-0 | 183.14 | 183.14
183.14
183.14
183.14
183.14
183.14
183.14
183.14
183.14
183.14
183.14
183.14
|  |  |  | Totals: |  | 183.14

## #9270.00 BiState Masonry
DOC ASP Tuckpointing Priority 4
Project # 9270.00
Program code 927000 |  |  | Major Program 4E10
BiState Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM23-9255 |  |  | RFP/B#: 927000-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523265802 | 2022-09-22 | PO Procore | 632016 | 632016 |  |  | 632016
PO 33523265802 | 2022-09-28 | Updated PO to MM23 | 0 | 632016 |  | 0 | 632016
PRC 3352326PA5802 | 2023-04-18 | Inv. 5528 |  | 632016 | 130689.3 | 130689.3 | 501326.7 | 6878.4
PRC 3352326PB5802 | 2023-05-05 | Inv. 5558 |  | 632016 | 200507 | 331196.3 | 300819.7 | 17431.4
PO 33523265802 | 2023-05-25 | CO #1 | 27864 | 659880 |  | 331196.3 | 328683.7
PRC 3352326PC5802 | 2023-06-05 | Inv. 5584 |  | 659880 | 186176.9 | 517373.2 | 142506.8 | 27230.2
PRC 3352326PD5802 | 2023-07-11 | Inv. 5616 |  | 659880 | 97332.1 | 614705.3 | 45174.7 | 32352.95 | FY23
PO 33524265802 | 2023-07-26 | Rolled to FY24 | 0 | 659880 |  | 614705.3 | 45174.7
PRC 3352426PE5802 | 2023-08-21 | Inv. 5654 |  | 659880 | 6005.66 | 620710.96 | 39169.04 | 32669.04
PO 33524265802 | 2023-11-21 | CO #2 | 35641 | 695521 |  | 620710.96 | 74810.04
PO 33524265802 | 2024-02-06 | CO #3(No cost CO) | 0 | 695521 |  | 620710.96 | 74810.04
PO 33524265802 | 2024-05-02 | CO #4(No cost CO) | 0 | 695521 |  | 620710.96 | 74810.04
PRC 3352426PF5802 | 2024-07-11 | Inv. 6006 |  | 695521 | 33250 | 653960.96 | 41560.04 | 34419.04 | FY24
PO 33525265802 | 2024-07-24 | Rolled to FY25 |  | 695521 |  | 653960.96 | 41560.04
PRC 3352526PG5802 | 2024-10-18 | Inv. 6034 |  | 695521 | 608.95 | 654569.91 | 40951.09 | 34451.09
PRC 3352526PH5802 | 2024-10-23 | Inv. 6118 |  | 695521 | 6175 | 660744.91 | 34776.09 | 34776.09
PRC 3352526PI5802 | 2024-11-06 | Inv. 6119 |  | 695521 | 34776.09 | 695521 | 0
|  |  |  | 695521 |  | 695521 | 0
|  |  |  | 695521 |  | 695521 | 0
|  | Totals: | 695521 |  | 695521 |  | 0 | FINAL

## #9270.00 RDG Planning
DOC ASP Tuckpointing Priority 4
Project # 9270.00
Program code 927000 |  |  | Major Program 4E10
RDG Planning & Design |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM23-9260 |  |  | RFP/B#: 927000-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524129800 | 2023-09-19 | CO #4 | 10400 | 10400 |  |  | 10400
PRC 3352412PI9800 | 2023-09-29 | Inv. 55127 (100% to MM21) |  | 10400 | 0 | 0 | 10400
PRC 3352412PJ9800 | 2023-10-17 | Inv. 55380 (100% to MM21) |  | 10400 | 0 | 0 | 10400
PRC 3352412PK9800 | 2023-11-21 | Inv. 55639 (100% to MM23) |  | 10400 | 2080 | 2080 | 8320
PRC 3352412PL9800 | 2023-12-20 | Inv. 55858 (100% to MM21) |  | 10400 | 0 | 2080 | 8320
PRC 3352412PM9800 | 2024-03-18 | Inv. 56542 (100% to MM23) |  | 10400 | 2080 | 4160 | 6240
PO 33524129800 | 2024-06-18 | Moving PO from MM21 | 2531 | 12931 |  | 4160 | 8771 | FY24
PO 33525129800 | 2024-07-24 | Roll to FY25 |  | 12931 |  | 4160 | 8771
PRC 3352512PN9800 | 2024-11-20 | Inv. 57918 |  | 12931 | 8771 | 12931 | 0
|  |  |  | 12931 |  | 12931 | 0
|  |  |  | 12931 |  | 12931 | 0
|  |  |  | 12931 |  | 12931 | 0
|  |  |  | 12931 |  | 12931 | 0
|  | Totals: | 12931 |  | 12931 |  | 0
|  | MM21(Closed 06/18/2024) | 66047 |  | 66047 |  | 0
|  | Total: | 78978 |  | 78978 |  | 0 | FINAL

## RECAP #9276.00
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 03/13/23

## #9276.00 Vendor A
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  | Major Program 4E12
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9276.00 PM TIME
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E256
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9276.00 Misc
DPS P12 Driveway Repairs
Project # 9276.00
Program code 927600 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9279.20
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
| Program code 927920 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 2705000
| Shive Hattery |  | 79640 | 76495 | 3145
| PM TIME |  | 44640 | 43556.93 | 1083.07
| Misc. |  | 19246.25 | 19246.25 | 0
C | Grainger |  | 3285.02 | 3285.02 | 0
| Story Construction |  | 612286.35 | 563368.59 | 48917.76
| Van Maanen |  | 90325.48 | 84859.16 | 5466.32
| Pleva |  | 1231043.56 | 1157529.93 | 73513.63
| Hilsabeck Schacht |  | 251876.18 | 233188.57 | 18687.61
C | Controlled Asbestos |  | 52699.23 | 52699.23 | 0
C | Controlled Asbestos (2) |  | 32229.69 | 32229.69 | 0
C | Black Hills Energy |  | 259232 | 259232 | 0
C | Tri-City Fire Portection |  | 18234.75 | 18234.75 | 0
C | Controlled Asbestos (3) |  | 195 | 195 | 0
| Total Project Cost | 2705000 | 2694933.51 | 2544120.12 | 150813.39 | 10066.49

## #9279.20 Shive Hattery
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | 9279.00-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Split w/ DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523166901 | 2023-02-09 | CO #1 (Split with MM22 and DA23) | 70500 | 70500 |  |  | 70500
PRC 3352316PG6901 | 2023-03-03 | Inv. 2142203390-7 (Split with DA23) |  | 70500 | 7600 | 7600 | 62900
PRC 3352316PH6901 | 2023-04-24 | Inv. 2142203390-8 (Split with DA23) |  | 70500 | 3145 | 10745 | 59755
PRC 3352316PI6901 | 2023-06-07 | Inv. 2142203390-9 (Split with DA23) |  | 70500 | 6290 | 17035 | 53465
PRC 3352316PJ6901 | 2023-07-06 | Inv. 2142203390-10 (100% to MM23) |  | 70500 | 3145 | 20180 | 50320 | FY23
PO 33524166901 | 2023-08-29 | Roll to FY24 | 0 | 70500 |  | 20180 | 50320
PO 33524166901 | 2023-09-13 | CO #2 (100% to DA23) | 0 | 70500 |  | 20180 | 50320
PO 33524166901 | 2023-09-14 | CO #3 (100% to MM23) | 9140 | 79640 |  | 20180 | 59460
PRC 3352416PK6901 | 2023-09-18 | Inv. 2142203390-11 (100% to MM23) |  | 79640 | 3145 | 23325 | 56315
PRC 3352416PL6901 | 2023-09-25 | Inv. 2142203390-12 (100% to MM23) |  | 79640 | 3145 | 26470 | 53170
PRC 3352416PM6901 | 2023-10-04 | Inv. 2142203390-13 (100% to MM23) |  | 79640 | 6290 | 32760 | 46880
PRC 3352416PN6901 | 2023-11-07 | Inv. 2142203390-14 (Split with DA23) |  | 79640 | 6290 | 39050 | 40590
PRC 3352416PO6901 | 2023-12-06 | Inv. 2142203390-15 (Split with DA23) |  | 79640 | 3145 | 42195 | 37445
PRC 3352416PP6901 | 2024-01-04 | Inv. 2142203390-16 (100% to MM23) |  | 79640 | 1258 | 43453 | 36187
PRC 3352416PQ6901 | 2024-01-30 | Inv. 2142203390-17 (Split with DA23) |  | 79640 | 5032 | 48485 | 31155
PRC 3352416PR6901 | 2024-03-05 | Inv. 2142203390-18 (Split with DA23) |  | 79640 | 6290 | 54775 | 24865
PRC 3352416PS6901 | 2024-04-10 | Inv. 2142203390-19 (Split with DA23) |  | 79640 | 3145 | 57920 | 21720
PRC 3352416PT6901 | 2024-05-06 | Inv. 2142203390-20 (Split with DA23) |  | 79640 | 3145 | 61065 | 18575
PRC 3352416PU6901 | 2024-07-16 | Inv. 2142203390-21 (Split with DA23) |  | 79640 | 15430 | 76495 | 3145 | FY24
PO 33525166901 | 2024-08-26 | Roll to FY25 |  | 79640 |  | 76495 | 3145
|  |  |  | 79640 |  | 76495 | 3145
|  |  |  | 79640 |  | 76495 | 3145
|  |  |  | 79640 |  | 76495 | 3145
|  |  |  | 79640 |  | 76495 | 3145
|  | Totals: | 79640 |  | 76495 |  | 3145
|  | 9279.00 MM22 (Closed) | 274800 |  | 274800 |  | 0
|  | 9279.21 DA23 | 18203 |  | 0 |  | 2592.8
|  | Total Contract: | 372643 |  | 351295 |  | 5737.8

## #9279.20 PM TIME
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E251
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 44640 | 44640 |  |  | 44640
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 44640 | 59.97 | 59.97 | 44580.03
CDE 33523075203 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 44640 | 363.63 | 423.6 | 44216.4
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 44640 | 476.35 | 899.95 | 43740.05
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 44640 | 2095.18 | 2995.13 | 41644.87
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 44640 | 209.71 | 3204.84 | 41435.16
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 44640 | 1232.1 | 4436.94 | 40203.06
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 44640 | 445.18 | 4882.12 | 39757.88
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 44640 | 3121.8 | 8003.92 | 36636.08
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 44640 | 345.5 | 8349.42 | 36290.58
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 44640 | 2893.5 | 11242.92 | 33397.08
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 44640 | 531.66 | 11774.58 | 32865.42
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 44640 | 3387.3 | 15161.88 | 29478.12
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 44640 | 718.33 | 15880.21 | 28759.79
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 44640 | 4014.2 | 19894.41 | 24745.59
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 44640 | 305.7 | 20200.11 | 24439.89
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 44640 | 2121 | 22321.11 | 22318.89
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 44640 | 373.96 | 22695.07 | 21944.93
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 44640 | 3003.9 | 25698.97 | 18941.03
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 44640 | 233.38 | 25932.35 | 18707.65
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 44640 | 1764.7 | 27697.05 | 16942.95
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 44640 | 228.2 | 27925.25 | 16714.75
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 44640 | 1678 | 29603.25 | 15036.75
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 44640 | 225.8 | 29829.05 | 14810.95
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 44640 | 1988.2 | 31817.25 | 12822.75
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 44640 | 463.55 | 32280.8 | 12359.2
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 44640 | 2336.8 | 34617.6 | 10022.4
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 44640 | 163.7 | 34781.3 | 9858.7
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 44640 | 1243.8 | 36025.1 | 8614.9
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 44640 | 183.52 | 36208.62 | 8431.38
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 44640 | 1627.5 | 37836.12 | 6803.88
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 44640 | 87.39 | 37923.51 | 6716.49
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 44640 | 723.3 | 38646.81 | 5993.19
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 44640 | 110.81 | 38757.62 | 5882.38
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 44640 | 1017.2 | 39774.82 | 4865.18
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 44640 | 47.45 | 39822.27 | 4817.73
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 44640 | 516.2 | 40338.47 | 4301.53
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 44640 | 85.35 | 40423.82 | 4216.18
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 44640 | 435.2 | 40859.02 | 3780.98
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 44640 | 99.88 | 40958.9 | 3681.1
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 44640 | 885.8 | 41844.7 | 2795.3
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 44640 | 111.86 | 41956.56 | 2683.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 44640 | 747.1 | 42703.66 | 1936.34
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 44640 | 65.35 | 42769.01 | 1870.99
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 44640 | 437.1 | 43206.11 | 1433.89
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 44640 | 31.92 | 43238.03 | 1401.97
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 44640 | 318.9 | 43556.93 | 1083.07
[5 empty] | 44640 |  | 43556.93 | 1083.07
[5 empty] | 44640 |  | 43556.93 | 1083.07
[5 empty] | 44640 |  | 43556.93 | 1083.07
|  |  | Totals: | 44640 |  | 43556.93 |  | 1083.07
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Tue, Dec 20, 2:34 PM (16 hours ago) to me Please create the following new PM Time budgets: MM23 9279.20 for $11,000.00 MM21 9329.00 for $4,400.00 MM23 9331.00 for $4,400.00 MM23 9332.00 for $8,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov Kleene, Jennifer 10:28 AM (2 hours ago) to me Sorry about that. Please increase the PM Time for DA22 9216.00 by $14,960.00 and increase the PM Time for MM23 9279.20 by $22,440.00. Regards, Jennifer MM23 9279.20 Changes $John Kleene, Jennifer 12:41 PM (10 minutes ago) to me, Scott Please increase the PM Time budget by $9,000.00 and decrease the overall budget by $320,000.00. This decrease offsets the amount allocated in MM22 for Phase 3 preconstruction activities, which has already been set-up. The original intent for the Phase 2 $3,400,000 was to be split between 9279.20 construction phase and 9279.30 preconstruction phase. Regards, Jennifer ---------- Forwarded message --------- From: Kleene, Jennifer <jennifer.kleene@iowa.gov> Date: Tue, Nov 12, 2024 at 7:48 AM Subject: Re: October PM Time Posting Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Sorry about that! Please increase the DAS Cost budgets as follows: DA24 9377.00 Increase budget by $4,400.00 DA24 9378.00 Increase budget by $298.43 DA25 9245.01 Create a budget for $14,370.00 MM23 9279.20 Increase budget by $2200.00

## #9279.20 Misc
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523193902 | 2023-07-11 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 9279.20-2507893 | 500 | 500
PRC 33524348900 | 2023-12-14 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2544331 | 2081.25 | 2581.25
PRC 33524349900 | 2023-12-14 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2523069 | 1606.25 | 4187.5
PRC 33524356800 | 2023-12-22 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2543130 | 7386.25 | 11573.75
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 55 | 11628.75
PRC 33524095806 | 2024-04-04 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2564614 | 6190 | 17818.75
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -55 | 17763.75
PRC 33524179900 | 2024-06-27 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2580278 | 1482.5 | 19246.25
19246.25
19246.25
19246.25
19246.25
|  |  |  | Totals: |  | 19246.25

## #9279.20 Grainger
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Grainger |  |  | Vendor:00002099406
Acct. Codes-0017-335-MM23-9255 |  |  | MA00518298A
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523054801 | 2023-02-23 | DO Procore | 3538.5 | 3538.5 |  |  | 3538.5
PRC 3352305PA4801 | 2023-04-05 | Inv. 9657754579 |  | 3538.5 | 1511.54 | 1511.54 | 2026.96
DO 33523054801 | 2023-04-14 | CO #1 | -253.48 | 3285.02 |  | 1511.54 | 1773.48
PRC 3352305PB4801 | 2023-04-20 | Inv. 9673897956 |  | 3285.02 | 1773.48 | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  |  |  | 3285.02 |  | 3285.02 | 0
|  | Totals: | 3285.02 |  | 3285.02 |  | 0
|  | Contract Line 19 - Electrical Equipment and Supplies - 2 Item 6MUZ9 4HP VFDs (2 at $898.31 each) | 1511.54 |  | 1511.54 |  | 0
|  | Contract Line 19 - Electrical Equipment and Supplies - 2 Item 6MVA0 5HP VFDs (2 at $870.94 each) | 1773.48 |  | 1773.48 |  | 0
|  | Total Contract: | 3285.02 |  | 3285.02 |  | 0

## #9279.20 Story Construction
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Story Construction |  |  | Vendor:00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523069802 | 2023-03-10 | PO Procore | 600759.32 | 600759.32 |  |  | 600759.32
PRC 3352306PA9802 | 2023-05-25 | Inv. 33789 |  | 600759.32 | 39696.64 | 39696.64 | 561062.68
PRC 3352306PB9802 | 2023-06-23 | Inv. 33837 |  | 600759.32 | 86357.75 | 126054.39 | 474704.93
PO 33523069802 | 2023-06-23 | CO #1 | 11527.03 | 612286.35 |  | 126054.39 | 486231.96
PRC 3352306PC9802 | 2023-07-25 | Inv. 33895 |  | 612286.35 | 49615.71 | 175670.1 | 436616.25 | FY23
PO 33524069802 | 2023-08-04 | Roll to FY24 | 0 | 612286.35 |  | 175670.1 | 436616.25
PRC 3352406PD9802 | 2023-08-25 | Inv. 33952 |  | 612286.35 | 37838.72 | 213508.82 | 398777.53
PRC 3352406PE9802 | 2023-09-22 | Inv. 34006 |  | 612286.35 | 33294.02 | 246802.84 | 365483.51
PRC 3352406PF9802 | 2023-10-19 | Inv. 34067 |  | 612286.35 | 33606.31 | 280409.15 | 331877.2
PRC 3352406PG9802 | 2023-11-26 | Inv. 34120 |  | 612286.35 | 58411.57 | 338820.72 | 273465.63
PRC 3352406PH9802 | 2023-12-21 | Inv. 34160 |  | 612286.35 | 22054.06 | 360874.78 | 251411.57
PRC 3352406PI9802 | 2024-01-24 | Inv. 34206 |  | 612286.35 | 32800.33 | 393675.11 | 218611.24
PRC 3352406PJ9802 | 2024-02-15 | Inv. 34248 |  | 612286.35 | 24070.66 | 417745.77 | 194540.58
PRC 3352406PK9802 | 2024-03-26 | Inv. 34282 |  | 612286.35 | 35430.1 | 453175.87 | 159110.48
PRC 3352406PL9802 | 2024-04-24 | Inv. 34321 |  | 612286.35 | 37663.37 | 490839.24 | 121447.11
PRC 3352406PM9802 | 2024-05-21 | Inv. 34355 |  | 612286.35 | 11884.77 | 502724.01 | 109562.34
PRC 3352406PN9802 | 2024-06-13 | Inv. 34392 |  | 612286.35 | 27683.07 | 530407.08 | 81879.27
PRC 3352406PO9802 | 2024-07-25 | Inv. 34438 |  | 612286.35 | 7499.09 | 537906.17 | 74380.18 | FY24
PO 33525069802 | 2024-07-29 | Roll to FY25 |  | 612286.35 |  | 537906.17 | 74380.18
PRC 3352506PP9802 | 2024-09-06 | Inv. 34484 |  | 612286.35 | 5349.36 | 543255.53 | 69030.82
PRC 3352506PQ9802 | 2024-09-17 | Inv. 34515 |  | 612286.35 | 5362.25 | 548617.78 | 63668.57
PRC 3352506PR9802 | 2024-10-16 | Inv. 34561 |  | 612286.35 | 4719.76 | 553337.54 | 58948.81
PRC 3352506PS9802 | 2024-11-18 | Inv. 34605 |  | 612286.35 | 2739.11 | 556076.65 | 56209.7
PRC 3352506PT9802 | 2024-12-20 | Inv. 34655 |  | 612286.35 | 3597.44 | 559674.09 | 52612.26
PRC 3352506PU9802 | 2025-01-16 | Inv. 34697 |  | 612286.35 | 3694.5 | 563368.59 | 48917.76
|  |  |  | 612286.35 |  | 563368.59 | 48917.76
|  | Totals: | 612286.35 |  | 563368.59 |  | 48917.76
|  | CM Services | 333300 |  | 326358.5 |  | 6941.5
|  | Reimbursables | 6000 |  | 4661 |  | 1339
|  | Fee | 47979.32 |  | 46371.12 |  | 1608.2
|  | General Conditions | 213480 |  | 177504.35 |  | 35975.65
|  | CO #1 | 11527.03 |  | 8473.62 |  | 3053.41
|  | Total Contract: | 612286.35 |  | 563368.59 |  | 48917.76

## #9279.20 Van Maanen
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Van Maanen |  |  | Vendor:00002091370
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523074800 | 2023-03-15 | PO Procore | 89736 | 89736 |  |  | 89736
PRC 3352307PA4800 | 2023-07-12 | Inv. 2271-01B |  | 89736 | 31766.59 | 31766.59 | 57969.41 | 1671.94 | FY23
PO 33524074800 | 2023-07-24 | Roll to FY24 | 0 | 89736 |  | 31766.59 | 57969.41
PRC 3352407PB4800 | 2023-09-22 | Inv. 2271-02B |  | 89736 | 1080.24 | 32846.83 | 56889.17 | 1728.8
PRC 3352407PC4800 | 2023-11-17 | Inv. 2271-03 |  | 89736 | 4501.21 | 37348.04 | 52387.96 | 1965.72
PO 33524074800 | 2023-12-06 | CO #1 | 589.48 | 90325.48 |  | 37348.04 | 52977.44
PRC 3352407PD4800 | 2024-04-11 | Inv. 2271-04B |  | 90325.48 | 36390.39 | 73738.43 | 16587.05 | 3881
PO 33524074800 | 2024-04-19 | CO #2(No Cost CO) | 0 | 90325.48 |  | 73738.43 | 16587.05
PRC 3352407PE4800 | 2024-06-21 | Inv. 2271-05B |  | 90325.48 | 8324.41 | 82062.84 | 8262.64 | 4319.14 | FY24
PO 33525074800 | 2024-07-24 | Roll to FY25 |  | 90325.48 |  | 82062.84 | 8262.64
PRC 3352507PF4800 | 2025-01-17 | Inv. 2271-06B |  | 90325.48 | 2796.32 | 84859.16 | 5466.32 | 4466.32
|  |  |  | 90325.48 |  | 84859.16 | 5466.32
|  |  |  | 90325.48 |  | 84859.16 | 5466.32
|  |  |  | 90325.48 |  | 84859.16 | 5466.32
|  | Totals: | 90325.48 |  | 84859.16 |  | 5466.32

## #9279.20 Pleva
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Pleva |  |  | Vendor:00003054699
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523080802 | 2023-03-21 | PO Procore | 1209048 | 1209048 |  |  | 1209048
PO 33523080802 | 2023-06-29 | CO #1 | 8572 | 1217620 |  | 0 | 1217620
PRC 3352308PA0802 | 2023-08-11 | Inv. 9279.20-001 |  | 1217620 | 340160.61 | 340160.61 | 877459.39 | 17903.19 | FY23
PO 33524080802 | 2023-08-18 | Roll to FY24 | 0 | 1217620 |  | 340160.61 | 877459.39
PRC 3352408PB0802 | 2023-09-14 | Inv. 9279.20-002 |  | 1217620 | 133182.4 | 473343.01 | 744276.99 | 24912.79
PRC 3352408PC0802 | 2023-10-12 | Inv. 9279.20-003 |  | 1217620 | 224836.5 | 698179.51 | 519440.49 | 36746.29
PRC 3352408PD0802 | 2023-10-24 | Inv. 9279.20-004 |  | 1217620 | 76623.2 | 774802.71 | 442817.29 | 40779.09
PO 33524080802 | 2023-12-19 | CO #2 | 5980 | 1223600 |  | 774802.71 | 448797.29
PRC 3352408PE0802 | 2024-01-05 | Inv. 9279.20-005 |  | 1223600 | 47944.6 | 822747.31 | 400852.69 | 43302.49
PO 33524080802 | 2024-02-22 | CO #3 | 6037.76 | 1229637.76 |  | 822747.31 | 406890.45
PRC 3352408PF0802 | 2024-03-18 | Inv. 9279.20-006 |  | 1229637.76 | 273056.6 | 1095803.91 | 133833.85 | 57673.89
PRC 3352408PG0802 | 2024-04-10 | Inv. 9279.20-007 |  | 1229637.76 | 40410.87 | 1136214.78 | 93422.98 | 59800.78
PO 33524080802 | 2024-04-16 | CO #4 (No Cost) | 0 | 1229637.76 |  | 1136214.78 | 93422.98
PO 33524080802 | 2024-05-02 | CO #5 | 3317 | 1232954.76 |  | 1136214.78 | 96739.98
PRC 3352408PH0802 | 2024-05-03 | Inv. 9279.20-008 |  | 1232954.76 | 3325 | 1139539.78 | 93414.98 | 59975.78
PO 33524080802 | 2024-06-18 | CO #6(No Cost CO) | 0 | 1232954.76 |  | 1139539.78 | 93414.98
PRC 3352408PI0802 | 2024-07-03 | Inv. 9279.20-009 |  | 1232954.76 | 3151.15 | 1142690.93 | 90263.83 | 60141.63 | FY24
PO 33525080802 | 2024-07-24 | Roll to FY25 |  | 1232954.76 |  | 1142690.93 | 90263.83
PO 33525080802 | 2024-10-14 | CO #7(No Cost CO) | 0 | 1232954.76 |  | 1142690.93 | 90263.83
PRC 3352508PJ0802 | 2024-12-06 | Inv. 9279.00-10 |  | 1232954.76 | 14839 | 1157529.93 | 75424.83 | 60922.63
PO 33525080802 | 2024-12-23 | CO #8 | -1911.2 | 1231043.56 |  | 1157529.93 | 73513.63
|  |  |  | 1231043.56 |  | 1157529.93 | 73513.63
|  | Totals: | 1231043.56 |  | 1157529.93 |  | 73513.63
Follow invoice number pattern with 9279.20-00#

## #9279.20 Hilsabeck Schacht
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523081901 | 2023-03-22 | PO Procore | 228900 | 228900 |  |  | 228900
PRC 3352308PA1901 | 2023-06-06 | Inv. 9279.20-01 |  | 228900 | 27648.8 | 27648.8 | 201251.2 | 1455.2
PRC 3352308PB1901 | 2023-07-17 | Inv. 9279.20-02 |  | 228900 | 12005.62 | 39654.42 | 189245.58 | 2087.08 | FY23
PO 33524081901 | 2023-07-24 | Roll to FY24 | 0 | 228900 |  | 39654.42 | 189245.58
PRC 3352408PC1901 | 2023-09-01 | Inv. 9279.20-03 |  | 228900 | 31012.75 | 70667.17 | 158232.83 | 3719.33
PRC 3352408PD1901 | 2023-10-12 | Inv. 9279.20-04 |  | 228900 | 55585.92 | 126253.09 | 102646.91 | 6644.91
PO 33524081901 | 2024-01-17 | CO #1 | 6500.67 | 235400.67 |  | 126253.09 | 109147.58
PRC 3352408PE1901 | 2024-01-29 | Inv. 9279.20-05 |  | 235400.67 | 73969.54 | 200222.63 | 35178.04 | 10538.04
PO 33524081901 | 2024-04-22 | CO #2(No Cost CO) | 0 | 235400.67 |  | 200222.63 | 35178.04
PO 33524081901 | 2024-06-18 | CO #3 | 19043.51 | 254444.18 |  | 200222.63 | 54221.55
PRC 3352408PF1901 | 2024-08-07 | Inv. 9279.20-06 |  | 254444.18 | 14874.61 | 215097.24 | 39346.94 | 11320.91 | FY24
PO 33525081901 | 2024-08-12 | Roll to FY25 |  | 254444.18 |  | 215097.24 | 39346.94
PO 33525081901 | 2024-09-26 | CO #4 | -2568 | 251876.18 |  | 215097.24 | 36778.94 | 12273.09
PRC 3352508PG1901 | 2025-01-16 | Inv. 9279.20-07 |  | 251876.18 | 18091.33 | 233188.57 | 18687.61
|  |  |  | 251876.18 |  | 233188.57 | 18687.61
|  |  |  | 251876.18 |  | 233188.57 | 18687.61
|  | Totals: | 251876.18 |  | 233188.57 |  | 18687.61

## #9279.20 Controlled Asbestos
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA 00521060
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523143801 | 2023-05-22 | DO Procore | 13752.5 | 13752.5 |  |  | 13752.5
DO 33523143801 | 2023-06-26 | CO #1 | 2917.3 | 16669.8 |  | 0 | 16669.8
DO 33523143801 | 2023-06-29 | CO #2 | 4912.64 | 21582.44 |  | 0 | 21582.44
PRC 3352314PA3801 | 2023-08-10 | Inv. 10579 |  | 21582.44 | 19707.17 | 19707.17 | 1875.27 | FY23
DO 33524143801 | 2023-08-18 | Roll to FY24 | 0 | 21582.44 |  | 19707.17 | 1875.27
DO 33524143801 | 2023-12-29 | CO #3 | 45497.84 | 67080.28 |  | 19707.17 | 47373.11
PRC 3352414PB3801 | 2024-01-05 | Inv. 0010621 - Final | -14381.05 | 52699.23 | 32992.06 | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  |  |  | 52699.23 |  | 52699.23 | 0
|  | Totals: | 52699.23 |  | 52699.23 |  | 0 | FINAL
|  | Contract Line 1 - Asbestos Abatement Services Hourly Rate (209.50 hours at $58.00/hr) | 47995 |  | 47995 |  | 0
|  | Contract Line 7 - Materials Cost for Non-Disposable Items (lump sum) | 1168.4 |  | 1168.4 |  | 0
|  | Constract Line 10 - Friable Disposal Fee )5 tons at $75.00/ton) | 294.75 |  | 294.75 |  | 0
|  | Contract Line 12 - Travel Expenses (1,550 miles at $0.39/mile) | 2321.28 |  | 2321.28 |  | 0
|  | Contract Line 11 - Non Friable (Lump Sum) | 919.8 |  | 919.8 |  | 0
|  | Total Contract: | 52699.23 |  | 52699.23 |  | 0

## #9279.20 Controlled Asbestos(2)
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Controlled Asbestos (2) |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA 00521060
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523160800 | 2023-06-09 | PO Procore | 45762.82 | 45762.82 |  |  | 45762.82
PO 33523160800 | 2023-06-28 | CO #1 (No Cost CO) | 0 | 45762.82 |  | 0 | 45762.82
PRC 3352316PA0800 | 2023-08-14 | Inv. 10595 |  | 45762.82 | 10779.05 | 10779.05 | 34983.77 | 567.32 | FY23
PO 33524160800 | 2023-08-18 | Roll to FY24 | 0 | 45762.82 |  | 10779.05 | 34983.77
PRC 3352416PB0800 | 2023-10-12 | Inv. 0010628 |  | 45762.82 | 19839.15 | 30618.2 | 15144.62 | 1611.49
PO 33524160800 | 2024-02-15 | CO #2 | -13533.13 | 32229.69 |  | 30618.2 | 1611.49
PRC 3352416PC0800 | 2024-02-16 | Inv. 5370-Retainage |  | 32229.69 | 1611.49 | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  |  |  | 32229.69 |  | 32229.69 | 0
|  | Totals: | 32229.69 |  | 32229.69 |  | 0

## #9279.20 Black Hills Energy
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Black Hills Energy |  |  | Vendor: 00003015755
Acct. Codes-0017-335-MM23-9255 |  |  | Sole Source
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523173800 | 2023-06-22 | PO Procore | 356732 | 356732 |  |  | 356732
PO 33523173800 | 2023-06-23 | Update T&C per PM | 0 | 356732 |  | 0 | 356732 | FY23
PO 33524173800 | 2023-08-04 | Roll to FY24 | 0 | 356732 |  | 0 | 356732
PRC 3352417PA3800 | 2024-03-08 | Inv. 269322468-FINAL | -97500 | 259232 | 259232 | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  |  |  | 259232 |  | 259232 | 0
|  | Totals: | 259232 |  | 259232 |  | 0 | FINAL
|  | Phase 1 - 4" HDPE Natural Gas Main and Service Line/Meter for Myers Hall | 166902 |  | 166902 |  | 0
|  | Phase 2 - 4" HDPE Natural Gas Main and Service Line/Meter for Dispatch Garage | 92330 |  | 92330 |  | 0
|  | Total Contract: | 259232 |  | 0 |  | 0

## #9279.20 Tri-City Fire
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Tri-City Fire Protection |  |  | Vendor: 00003206377
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Split w/ DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524083800 | 2023-12-06 | CO #1 | 18234.75 | 18234.75 |  |  | 18234.75
PRC 3352408PB3800 | 2024-04-03 | Inv. 16709(100% to DA23) |  | 18234.75 | 0 | 0 | 18234.75
PO 33524083800 | 2024-04-16 | CO #2 | 0 | 18234.75 |  | 0 | 18234.75
PRC 3352408PC3800 | 2024-04-18 | Inv. 16798(Split between MM23 & DA23) |  | 18234.75 | 17323.01 | 17323.01 | 911.74 | 911.74
PO 33524083800 | 2024-06-24 | CO#3(No Cost CO) | 0 | 18234.75 |  | 17323.01 | 911.74
PRC 3352408PD3800 | 2024-08-09 | Inv. 16896(100% to DA23) |  | 18234.75 | 0 | 17323.01 | 911.74 |  | FY24
PO 33525083800 | 2024-08-26 | Roll to FY25 |  | 18234.75 |  | 17323.01 | 911.74
PRC 3352508PE3800 | 2024-10-07 | Inv. 16942(100% to DA23) |  | 18234.75 | 0 | 17323.01 | 911.74
PRC 3352508PF3800 | 2025-01-06 | Inv. 17108 (100% to DA23) |  | 18234.75 | 0 | 17323.01 | 911.74
PRC 3352508PG3800 | 2025-01-16 | Inv. Retainage Release(Split w/DA23) |  | 18234.75 | 911.74 | 18234.75 | 0
|  |  |  | 18234.75 |  | 18234.75 | 0
|  |  |  | 18234.75 |  | 18234.75 | 0
|  |  |  | 18234.75 |  | 18234.75 | 0
|  | Totals: | 18234.75 |  | 18234.75 |  | 0 | FINAL
|  | DA23 | 328965 |  | 328965 |  | 0
|  | Total Contract: | 347199.75 |  | 347199.75 |  | 0

## #9279.20 Controlled Asbesto (3)
DHS WRC Campus Utility Decentralization Phase 2
Project # 9279.20
Program code 927920 |  |  | Major Program 4B02
Controlled Asbestos (3) |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA00521060A
Project Manager - Jennifer K |  |  | Activity code: CNST
Split w/ DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524030804 | 2024-05-17 | CO #1 | 195 | 195 |  |  | 195
PRC 3352403PA0804 | 2024-07-09 | Inv. 10760, 10780(Split with DA23) |  | 195 | 195 | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  |  |  | 195 |  | 195 | 0
|  | Totals: | 195 |  | 195 |  | 0
|  | DA23 | 3909 |  | 453.5 |  | 3455.5
|  | Total Contract: | 4104 |  | 648.5 |  | 3455.5

## RECAP #9294.00
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
| Program code 929400 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer Kleene
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1107615.79
C | Story Construction |  | 24227.5 | 24227.5 | 0
| PM TIME |  | 24615.79 | 22751.85 | 1863.94
| Misc. |  | 4698 | 4698 | 0
| Shive Hattery |  | 103090 | 100908 | 2182
| Story Construction (2) |  | 139493.49 | 132034.81 | 7458.68
| Van Maanen |  | 768384.93 | 675148.49 | 93236.44
| Hilsabeck Schacht Inc |  | 10000 | 0 | 10000
C | Controlled Asbestos |  | 17278.16 | 17278.16 | 0
| Controlled Asbestos (2) |  | 15636 | 7133.5 | 8502.5
| Total Project Cost | 1107615.79 | 1107423.87 | 984180.31 | 123243.56 | 191.92

## #9294.00 Story Construction PC
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255
Project Manager - Jennifer Kleene |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33522196900 | 2022-07-15 | PO Procore | 24445 | 24445 |  |  | 24445
PO 33523196900 | 2022-09-20 | Correcting PO to FY23 | 0 | 24445 |  | 0 | 24445
PRC 3352319PA6900 | 2022-09-20 | Inv. 33352 |  | 24445 | 785 | 785 | 23660
PRC 3352319PB6900 | 2022-10-18 | Inv. 33409 |  | 24445 | 1320 | 2105 | 22340
PRC 3352319PC6900 | 2022-11-21 | Inv. 33468 |  | 24445 | 1625 | 3730 | 20715
PRC 3352319PD6900 | 2022-12-20 | Inv. 33523 |  | 24445 | 557.5 | 4287.5 | 20157.5
PRC 3352319PE6900 | 2023-01-23 | Inv. 33590 |  | 24445 | 5225 | 9512.5 | 14932.5
PRC 3352319PF6900 | 2023-02-17 | Inv. 33637 |  | 24445 | 9405 | 18917.5 | 5527.5
PRC 3352319PG6900 | 2023-03-20 | Inv. 33691 - FINAL | -217.5 | 24227.5 | 5310 | 24227.5 | 0
|  |  |  | 24227.5 |  | 24227.5 | 0
|  |  |  | 24227.5 |  | 24227.5 | 0
|  |  |  | 24227.5 |  | 24227.5 | 0
|  |  |  | 24227.5 |  | 24227.5 | 0
|  | Totals: | 24227.5 |  | 24227.5 |  | 0 | FINAL
|  | CM Services | 24227.5 |  | 24227.5 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Totals: | 24227.5 |  | 24227.5 |  | 0

## #9294.00 PM TIME
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 907T
Project Manager - Jennifer Kleene
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 23000 | 23000 |  |  | 23000
IET DAS202301115300001 | 2022-08-10 | 9500 | PM-July 1-July 29, 2022 |  | 23000 | 200 | 200 | 22800
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Credit |  | 23000 | -200 | 0 | 23000
IET DAS202302115300001 | 2022-09-08 | 9500 | PM-July 1-July 29, 2022 Reposted with correct amount |  | 23000 | 220 | 220 | 22780
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 23000 | 302.5 | 522.5 | 22477.5
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 23000 | 302.5 | 825 | 22175
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 23000 | 880 | 1705 | 21295
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 23000 | 27.5 | 1732.5 | 21267.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-July 9997.23 disbursement | 57.98 | 23057.98 | 57.98 | 1790.48 | 21267.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 279.29 | 23337.27 | 279.29 | 2069.77 | 21267.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 188.82 | 23526.09 | 188.82 | 2258.59 | 21267.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 691.77 | 24217.86 | 691.77 | 2950.36 | 21267.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 27.52 | 24245.38 | 27.52 | 2977.88 | 21267.5
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 24245.38 | 936.74 | 3914.62 | 20330.76
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 24245.38 | 182.06 | 4096.68 | 20148.7
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 24245.38 | 1596.1 | 5692.78 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: July 1-31, 2022 | 50.89 | 24296.27 | 50.89 | 5743.67 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 82.36 | 24378.63 | 82.36 | 5826.03 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 78.46 | 24457.09 | 78.46 | 5904.49 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 12.7 | 24469.79 | 12.7 | 5917.19 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 5.86 | 24475.65 | 5.86 | 5923.05 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 140.14 | 24615.79 | 140.14 | 6063.19 | 18552.6
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 24615.79 | 172.39 | 6235.58 | 18380.21
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 24615.79 | 1045.41 | 7280.99 | 17334.8
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 24615.79 | 182.43 | 7463.42 | 17152.37
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 24615.79 | 802.4 | 8265.82 | 16349.97
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 24615.79 | 70.04 | 8335.86 | 16279.93
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 24615.79 | 410.5 | 8746.36 | 15869.43
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 24615.79 | 121.24 | 8867.6 | 15748.19
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 24615.79 | 850.3 | 9717.9 | 14897.89
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 24615.79 | 88.91 | 9806.81 | 14808.98
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 24615.79 | 741.9 | 10548.71 | 14067.08
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 24615.79 | 97.26 | 10645.97 | 13969.82
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 24615.79 | 619.3 | 11265.27 | 13350.52
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 24615.79 | 177.91 | 11443.18 | 13172.61
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 24615.79 | 992.5 | 12435.68 | 12180.11
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 24615.79 | 45.08 | 12480.76 | 12135.03
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 24615.79 | 310.1 | 12790.86 | 11824.93
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 24615.79 | 65.41 | 12856.27 | 11759.52
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 24615.79 | 522.3 | 13378.57 | 11237.22
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 24615.79 | 56.67 | 13435.24 | 11180.55
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 24615.79 | 427.4 | 13862.64 | 10753.15
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 24615.79 | 32.11 | 13894.75 | 10721.04
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 24615.79 | 234 | 14128.75 | 10487.04
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 24615.79 | 120.95 | 14249.7 | 10366.09
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 24615.79 | 1066.7 | 15316.4 | 9299.39
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 24615.79 | 288.35 | 15604.75 | 9011.04
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 24615.79 | 1455.6 | 17060.35 | 7555.44
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 24615.79 | 121.42 | 17181.77 | 7434.02
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 24615.79 | 921.8 | 18103.57 | 6512.22
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 24615.79 | 71.39 | 18174.96 | 6440.83
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 24615.79 | 633.4 | 18808.36 | 5807.43
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 24615.79 | 43.69 | 18852.05 | 5763.74
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 24615.79 | 362.2 | 19214.25 | 5401.54
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 24615.79 | 79.21 | 19293.46 | 5322.33
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 24615.79 | 726.2 | 20019.66 | 4596.13
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 24615.79 | 24.07 | 20043.73 | 4572.06
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 24615.79 | 258.1 | 20301.83 | 4313.96
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 24615.79 | 85.35 | 20387.18 | 4228.61
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 24615.79 | 435.2 | 20822.38 | 3793.41
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 24615.79 | 55.79 | 20878.17 | 3737.62
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 24615.79 | 497.8 | 21375.97 | 3239.82
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 24615.79 | 137.85 | 21513.82 | 3101.97
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 24615.79 | 921.9 | 22435.72 | 2180.07
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 24615.79 | 28.39 | 22464.11 | 2151.68
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 24615.79 | 187.4 | 22651.51 | 1964.28
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 24615.79 | 9.14 | 22660.65 | 1955.14
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 24615.79 | 91.2 | 22751.85 | 1863.94
[5 empty] | 24615.79 |  | 22751.85 | 1863.94
[5 empty] | 24615.79 |  | 22751.85 | 1863.94
[5 empty] | 24615.79 |  | 22751.85 | 1863.94
|  |  | Totals: | 24615.79 |  | 22751.85 |  | 1863.94
Note on E9: Huggins, Joni [DAS]: MM23 9294.00 PM Time Budget $Joni Kleene, Jennifer Fri, Jul 15, 3:49 PM (3 days ago) to me Please create a PM Time budget for $25,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9294.00 Misc
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer Kleene
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523055807 | 2023-02-24 | 9500 | CNST | Shive Hattery V#(00002108803) | Inv. 2142203390 - HAZ-2 | 4698 | 4698
4698
4698
4698
4698
4698
4698
4698
4698
4698
4698
4698
|  |  |  | Totals: |  | 4698

## #9294.00 Shive Hattery
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP/B#: 927900-01
Project Manager - Jennifer Kleene |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523235800 | 2022-08-23 | PO Procore | 95000 | 95000 |  |  | 95000
PRC 3352323PA5800 | 2022-09-28 | Inv. 2142203392-1 |  | 95000 | 5115 | 5115 | 89885
PRC 3352323PB5800 | 2022-10-28 | Inv. 2142203392-2 |  | 95000 | 28985 | 34100 | 60900
PRC 3352323PC5800 | 2022-12-05 | Inv. 2142203392-3 |  | 95000 | 27550 | 61650 | 33350
PRC 3352323PD5800 | 2023-01-25 | Inv. 2142203392-4 |  | 95000 | 1450 | 63100 | 31900
PRC 3352323PE5800 | 2023-03-03 | Inv. 2142203392-5 |  | 95000 | 3300 | 66400 | 28600
PRC 3352323PF5800 | 2023-05-30 | Inv. 2142203392-6 |  | 95000 | 2860 | 69260 | 25740
PO 33523235800 | 2023-06-23 | CO #1 | 5440 | 100440 |  | 69260 | 31180
PRC 3352323PG5800 | 2023-07-06 | Inv. 2142203392-7 |  | 100440 | 3968 | 73228 | 27212 | FY23
PO 33524235800 | 2023-08-04 | Roll to FY24 | 0 | 100440 |  | 73228 | 27212
PRC 3352423PH5800 | 2023-08-04 | Inv. 2142203392-8 |  | 100440 | 1430 | 74658 | 25782
PRC 3352423PI5800 | 2023-08-31 | Inv. 2142203392-9 |  | 100440 | 2860 | 77518 | 22922
PRC 3352423PJ5800 | 2023-10-04 | Inv. 2142203392-10 |  | 100440 | 2860 | 80378 | 20062
PO 33524235800 | 2023-11-17 | CO #2 | 6400 | 106840 |  | 80378 | 26462
PRC 3352423PK5800 | 2023-12-06 | Inv. 2142203392-11 |  | 106840 | 1430 | 81808 | 25032
PRC 3352423PL5800 | 2024-01-04 | Inv. 2142203392-12 |  | 106840 | 4460 | 86268 | 20572
PRC 3352423PM5800 | 2024-01-30 | Inv. 2142203392-13 |  | 106840 | 6060 | 92328 | 14512
PO 33524235800 | 2024-03-04 | CO #3 | -3750 | 103090 |  | 92328 | 10762
PRC 3352423PN5800 | 2024-03-05 | Inv. 2142203392-14 |  | 103090 | 2860 | 95188 | 7902
PRC 3352423PO5800 | 2024-04-10 | Inv. 2142203392-15 |  | 103090 | 1430 | 96618 | 6472
PRC 3352423PP5800 | 2024-05-06 | Inv. 2142203392-16 |  | 103090 | 2860 | 99478 | 3612
PRC 3352423PQ5800 | 2024-07-23 | Inv. 2142203392-17 |  | 103090 | 1430 | 100908 | 2182 | FY24
PO 33525235800 | 2024-07-25 | Roll to FY25 |  | 103090 |  | 100908 | 2182
|  |  |  | 103090 |  | 100908 | 2182
|  | Totals: | 103090 |  | 100908 |  | 2182
|  | Design Development Documents | 34100 |  | 34100 |  | 0
|  | Construction Documents | 29000 |  | 29000 |  | 0
|  | Bidding/Negotiation Assistance | 3300 |  | 3300 |  | 0
|  | Construction Phase | 28600 |  | 25740 |  | 2860
|  | CO #1 | 5440 |  | 3968 |  | 1472
|  | CO #2 | 6400 |  | 4800 |  | 1600
|  | CO #3 | -3750 |  |  |  | -3750
|  | Totals: | 103090 |  | 100908 |  | 2182

## #9294.00 Story Construction (2)
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer Kleene |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523069800 | 2023-03-10 | PO Procore | 120933.15 | 120933.15 |  |  | 120933.15
PRC 3352306PA9800 | 2023-05-23 | Inv. 33792 |  | 120933.15 | 4183.05 | 4183.05 | 116750.1
PRC 3352306PB9800 | 2023-06-21 | Inv. 33839 |  | 120933.15 | 7640.69 | 11823.74 | 109109.41
PRC 3352306PC9800 | 2023-07-20 | Inv. 33898 |  | 120933.15 | 11344.17 | 23167.91 | 97765.24 | FY23
PO 33524069800 | 2023-08-04 | Roll to FY24 | 0 | 120933.15 |  | 23167.91 | 97765.24
PRC 3352406PD9800 | 2023-08-22 | Inv. 33955 |  | 120933.15 | 14945.53 | 38113.44 | 82819.71
PRC 3352406PE9800 | 2023-09-18 | Inv. 34009 |  | 120933.15 | 6909.99 | 45023.43 | 75909.72
PRC 3352406PF9800 | 2023-10-17 | Inv. 34069 |  | 120933.15 | 3664.14 | 48687.57 | 72245.58
PRC 3352406PG9800 | 2023-11-26 | Inv. 34122 |  | 120933.15 | 6607.41 | 55294.98 | 65638.17
PRC 3352406PH9800 | 2023-12-20 | Inv. 34162 |  | 120933.15 | 4024.2 | 59319.18 | 61613.97
PRC 3352406PI9800 | 2024-01-17 | Inv. 34208 |  | 120933.15 | 11245.57 | 70564.75 | 50368.4
PRC 3352406PJ9800 | 2024-02-15 | Inv. 34250 |  | 120933.15 | 12477.29 | 83042.04 | 37891.11
PO 33524069800 | 2024-03-20 | CO #1 | 16914.63 | 137847.78 |  | 83042.04 | 54805.74
PRC 3352406PK9800 | 2024-03-20 | Inv. 34284 |  | 137847.78 | 16977.83 | 100019.87 | 37827.91
PRC 3352406PL9800 | 2024-04-24 | Inv. 34323 |  | 137847.78 | 1829.07 | 101848.94 | 35998.84
PRC 3352406PM9800 | 2024-05-21 | Inv. 34357 |  | 137847.78 | 12435.35 | 114284.29 | 23563.49
PRC 3352406PN9800 | 2024-06-13 | Inv. 34394 |  | 137847.78 | 4198.31 | 118482.6 | 19365.18
PO 33524069800 | 2024-06-28 | CO #2 | 1645.71 | 139493.49 |  | 118482.6 | 21010.89
PRC 3352406PO9800 | 2024-07-18 | Inv. 34447 |  | 139493.49 | 2948.94 | 121431.54 | 18061.95 | FY24
PO 33525069800 | 2024-07-24 | Roll to FY25 |  | 139493.49 |  | 121431.54 | 18061.95
PRC 3352506PP9800 | 2024-08-20 | Inv. 34485 |  | 139493.49 | 3039.35 | 124470.89 | 15022.6
PRC 3352506PQ9800 | 2024-09-16 | Inv. 34516 |  | 139493.49 | 4169.82 | 128640.71 | 10852.78
PRC 3352506PR9800 | 2024-10-16 | Inv. 34562 |  | 139493.49 | 2467.47 | 131108.18 | 8385.31
PRC 3352506PS9800 | 2024-11-18 | Inv. 34606 |  | 139493.49 | 926.63 | 132034.81 | 7458.68
|  |  |  | 139493.49 |  | 132034.81 | 7458.68
|  | Totals: | 139493.49 |  | 132034.81 |  | 7458.68
|  | CM Services | 82347.6 |  | 82347.6 |  | 0
|  | Reimbursables | 3250 |  |  |  | 3250
|  | Fee | 35335.55 |  | 31779.42 |  | 3556.13
|  | CO #1 | 16914.63 |  | 16687.21 |  | 227.42
|  | CO #2 | 1645.71 |  | 1220.58 |  | 425.13
|  | Totals: | 139493.49 |  | 132034.81 |  | 7458.68

## #9294.00 Van Maanen
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Van Maanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer Kleene |  |  | Activity code: BRUM
Split w/DA25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523073801 | 2023-03-14 | PO Procore | 696711 | 696711 |  |  | 696711
PRC 3352307PA3801 | 2023-07-12 | Inv. 2271-01FA |  | 696711 | 159964.61 | 159964.61 | 536746.39 | 8419.19 | FY23
PO 33524073801 | 2023-08-04 | Roll to FY24 | 0 | 696711 |  | 159964.61 | 536746.39
PRC 3352407PB3801 | 2023-09-14 | Inv. 2271-02FA |  | 696711 | 5683.75 | 165648.36 | 531062.64 | 8718.34
PO 33524073801 | 2023-11-15 | CO #1 | 24978.5 | 721689.5 |  | 165648.36 | 556041.14
PO 33524073801 | 2024-01-19 | CO #2 | 3647.06 | 725336.56 |  | 165648.36 | 559688.2
PRC 3352407PC3801 | 2024-02-16 | Inv. 2271-03FA |  | 725336.56 | 162714.19 | 328362.55 | 396974.01 | 17282.26
PO 33524073801 | 2024-04-19 | CO #3(No cost CO) | 0 | 725336.56 |  | 328362.55 | 396974.01
PRC 3352407PD3801 | 2024-05-03 | Inv. 2271-04FA |  | 725336.56 | 334821.39 | 663183.94 | 62152.62 | 34904.45
PO 33524073801 | 2024-06-24 | CO #4 | 36024.03 | 761360.59 |  | 663183.94 | 98176.65
PRC 3352407PE3801 | 2024-07-25 | Inv. 2271-05FA |  | 761360.59 | 11964.55 | 675148.49 | 86212.1 | 35534.17 | FY24
PO 33525073801 | 2024-07-29 | Roll to FY25 |  | 761360.59 |  | 675148.49 | 86212.1
PO 33525073801 | 2024-10-14 | CO# 5 | 7024.34 | 768384.93 |  | 675148.49 | 93236.44
PO 33525073801 | 2024-12-19 | CO #6(No cost CO) | 0 | 768384.93 |  | 675148.49 | 93236.44
|  |  |  | 768384.93 |  | 675148.49 | 93236.44
|  | Totals: | 768384.93 |  | 675148.49 |  | 93236.44
|  | DA25 | 12362.4 |  | 0 |  | 12362.4
|  | Total Contract | 780747.33 |  | 675148.49 |  | 105598.84

## #9294.00 Hilsabeck Schacht Inc
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Hilsabeck Schacht Inc |  |  | Vendor: 00003178029
Acct. Codes-0017-335-MM23-9255 |  |  | 927920-01
Project Manager - Jennifer Kleene |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523082801 | 2023-03-23 | PO Procore | 10000 | 10000 |  |  | 10000 | FY23
PO 33524082801 | 2023-08-04 | Roll to FY24 |  | 10000 |  | 0 | 10000
PO 33524082801 | 2024-04-23 | CO #1(No Cost CO) | 0 | 10000 |  | 0 | 10000
PO 33524082801 | 2024-06-19 | CO #2(No Cost CO) | 0 | 10000 |  | 0 | 10000 | FY24
PO 33525082801 | 2024-07-29 | Roll to FY25 |  | 10000 |  | 0 | 10000
PO 33525082801 | 2024-11-18 | CO #3(No Cost CO) | 0 | 10000 |  | 0 | 10000
PO 33525082801 | 2024-12-17 | CO #4(No Cost CO) | 0 | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  |  |  | 10000 |  | 0 | 10000
|  | Totals: | 10000 |  | 0 |  | 10000

## #9294.00 Controlled Asbestos
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA00521060A
Project Manager - Jennifer Kleene |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524005903 | 2024-01-05 | DO Procore | 17278.16 | 17278.16 |  |  | 17278.16
PRC 3352400PA5903 | 2024-01-08 | Inv. 0010679-final |  | 17278.16 | 17278.16 | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  |  |  | 17278.16 |  | 17278.16 | 0
|  | Totals: | 17278.16 |  | 17278.16 |  | 0
|  | Lead Abatement Line 5 | 16492 |  | 16492 |  | 0
|  | Mileage Line 12 Before 11/01/23 | 290.16 |  | 290.16 |  | 0
|  | Mileage Line 12 After 11/01/23 | 496 |  | 496 |  | 0
|  | Totals: | 17278.16 |  | 17278.16 |  | 0

## #9294.00 Controlled Asbestos 2
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Controlled Asbestos 2 |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA 00521060A
Project Manager - Jennifer Kleene |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524030803 | 2024-01-30 | DO Procore | 15636 | 15636 |  |  | 15636
PRC 3352403PA0803 | 2024-06-14 | Inv. 0010755, 0010712 |  | 15636 | 6485 | 6485 | 9151
PRC 3352403PB0803 | 2024-07-03 | Inv. 0010760-B |  | 15636 | 648.5 | 7133.5 | 8502.5 | FY24
DO 33525030803 | 2024-07-24 | Roll to FY25 |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  |  |  | 15636 |  | 7133.5 | 8502.5
|  | Totals: | 15636 |  | 7133.5 |  | 8502.5
|  | Contract Line 5 - Lead Abatement Services Hourly Rate (228 hours at $65/hr) | 14820 |  | 6792.5 |  | 8027.5
|  | Contract Line 11 - Non-Friable Disposal (0.8 tons at $90/ton) | 72 |  |  |  | 72
|  | Contract Line 12 - Mileage (1488 miles at $0.50/mile) | 744 |  | 341 |  | 403
|  | Totals: | 15636 |  | 7133.5 |  | 8502.5

## RECAP #9294.01
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
| Program code 929401 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 700000
| Van Maanen Electric |  | 467388.57 | 378574.18 | 88814.39
| PM TIME |  | 12540 | 8600.75 | 3939.25
| Misc. |  | 0 | 0 | 0
| Shive Hattery |  | 18869 | 15987 | 2882
| Story Construction |  | 135104.31 | 83379.66 | 51724.65
C | Earth Services & Abatement |  | 0 | 0 | 0
| Hilsbeck Schacht |  | 40000 | 0 | 40000
| Schumacher Elevator |  | 7000 | 0 | 7000
| Total Project Cost | 700000 | 680901.88 | 486541.59 | 194360.29 | 19098.12

## #9294.01 Van Maanen Electric
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Van Maanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0017-335-MM23-9255 |  |  | 927930-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524018904 | 2024-01-18 | PO Procore | 415500 | 415500 |  |  | 415500
PRC 3352401PA8904 | 2024-07-05 | Inv. 2394-01FA |  | 415500 | 233289.39 | 233289.39 | 182210.61 | 12278.41 | FY24
PO 33525018904 | 2024-07-24 | Roll to FY25 |  | 415500 |  | 233289.39 | 182210.61
PO 33525018904 | 2024-10-30 | CO #1 | 33555.39 | 449055.39 |  | 233289.39 | 215766
PRC 3352501PB8904 | 2024-11-18 | Inv. 2394-03 |  | 449055.39 | 145284.79 | 378574.18 | 70481.21 | 19925
PO 33525018904 | 2024-12-17 | CO #2 | 18333.18 | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  |  |  | 467388.57 |  | 378574.18 | 88814.39
|  | Totals: | 467388.57 |  | 378574.18 |  | 88814.39

## #9294.01 PM TIME
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 728Z
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 12540 | 12540 |  |  | 12540
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 12540 | 55.27 | 55.27 | 12484.73
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 12540 | 485.3 | 540.57 | 11999.43
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 12540 | 87.05 | 627.62 | 11912.38
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12540 | 440.6 | 1068.22 | 11471.78
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12540 | 84.99 | 1153.21 | 11386.79
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12540 | 645.1 | 1798.31 | 10741.69
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 12540 | 50.9 | 1849.21 | 10690.79
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 12540 | 452.5 | 2301.71 | 10238.29
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 12540 | 71.04 | 2372.75 | 10167.25
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12540 | 587.3 | 2960.05 | 9579.95
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 12540 | 69.05 | 3029.1 | 9510.9
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12540 | 630.1 | 3659.2 | 8880.8
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 12540 | 31.26 | 3690.46 | 8849.54
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12540 | 343.8 | 4034.26 | 8505.74
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12540 | 161.82 | 4196.08 | 8343.92
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12540 | 821.3 | 5017.38 | 7522.62
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12540 | 155.66 | 5173.04 | 7366.96
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12540 | 1383.1 | 6556.14 | 5983.86
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12540 | 131.53 | 6687.67 | 5852.33
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12540 | 880.7 | 7568.37 | 4971.63
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12540 | 56.36 | 7624.73 | 4915.27
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12540 | 374.8 | 7999.53 | 4540.47
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12540 | 55.12 | 8054.65 | 4485.35
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12540 | 546.1 | 8600.75 | 3939.25
[5 empty] | 12540 |  | 8600.75 | 3939.25
[5 empty] | 12540 |  | 8600.75 | 3939.25
[5 empty] | 12540 |  | 8600.75 | 3939.25
|  |  | Totals: | 12540 |  | 8600.75 |  | 3939.25
Note on E9: Huggins, Joni [DAS]: MM23 9294.01 PM Time Budget $Joni Kleene, Jennifer 11:35 AM (4 minutes ago) to me Please create a PM Time Budget of $8,800.00 for MM23 9294.01. Regards, Jennifer PM Time Budget Changes $Joni Kleene, Jennifer 10:13 AM (1 hour ago) to me, Scott Please increase the PM Time Budgets as follows: MM23 9294.01 increase by $3,740.00 DA25 9424.00 increase by $2,000.00 MM22 9244.00 increase by $2,000.00 MM22 9274.00 increase by $600.00 X674 9379.00 increase by $8,800.00 MM24 9391.00 increase by $8,800.00 Regards, Jennifer

## #9294.01 Misc
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 55 | 55
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -55 | 0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9294.01 Shive Hattery
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524116800 | 2024-01-19 | CO #4 | 16794 | 16794 |  |  | 16794
PRC 3352411PH6800 | 2024-01-30 | Inv. 2142203393-8(100% to MM21) |  | 16794 | 0 | 0 | 16794
PO 33524116800 | 2024-03-04 | CO #5 | 2075 | 18869 |  | 0 | 18869
PRC 3352411PI6800 | 2024-05-06 | Inv. 2142203393-9(100% to MM23) |  | 18869 | 784.15 | 784.15 | 18084.85
PRC 3352411PJ6800 | 2024-07-23 | Inv. 2142203393-10R |  | 18869 | 6170.1 | 6954.25 | 11914.75 | FY24
PO 33525116800 | 2024-07-25 | Roll to FY25 |  | 18869 |  | 6954.25 | 11914.75
PRC 3352511PK6800 | 2024-10-30 | Inv. 2142203393-11 |  | 18869 | 2499.1 | 9453.35 | 9415.65
PRC 3352511PL6800 | 2024-11-21 | Inv. 2142203393-12 |  | 18869 | 1124.15 | 10577.5 | 8291.5
PRC 3352511PM6800 | 2025-01-16 | Inv. 2142203393-13 |  | 18869 | 5409.5 | 15987 | 2882
|  |  |  | 18869 |  | 15987 | 2882
|  |  |  | 18869 |  | 15987 | 2882
|  |  |  | 18869 |  | 15987 | 2882
|  |  |  | 18869 |  | 15987 | 2882
|  | Totals: | 18869 |  | 15987 |  | 2882
|  | MM21 Closed 03/04/2024 | 56113 |  | 56113 |  | 0
|  | Total Contract: | 74982 |  | 72100 |  | 2882

## #9294.01 Story Construction
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524033912 | 2024-02-02 | PO Procore | 135104.31 | 135104.31 |  |  | 135104.31
PRC 3352403PA3912 | 2024-03-18 | Inv. 34288 |  | 135104.31 | 6202.16 | 6202.16 | 128902.15
PRC 3352403PB3912 | 2024-04-24 | Inv. 34327 |  | 135104.31 | 5974.07 | 12176.23 | 122928.08
PRC 3352403PC3912 | 2024-05-22 | Inv. 34361 |  | 135104.31 | 2864.47 | 15040.7 | 120063.61
PRC 3352403PD3912 | 2024-06-20 | Inv. 34399 |  | 135104.31 | 4640.88 | 19681.58 | 115422.73
PRC 3352403PE3912 | 2024-07-18 | Inv. 34443 |  | 135104.31 | 9704.04 | 29385.62 | 105718.69 | FY24
PO 33525033912 | 2024-07-24 | Roll to FY25 |  | 135104.31 |  | 29385.62 | 105718.69
PRC 3352503PF3912 | 2024-08-22 | Inv. 34489 |  | 135104.31 | 8306.16 | 37691.78 | 97412.53
PRC 3352503PG3912 | 2024-09-16 | Inv. 34519 |  | 135104.31 | 3034.74 | 40726.52 | 94377.79
PRC 3352503PH3912 | 2024-10-16 | Inv. 34566 |  | 135104.31 | 9800.02 | 50526.54 | 84577.77
PRC 3352503PI3912 | 2024-11-18 | Inv. 34609 |  | 135104.31 | 7914.86 | 58441.4 | 76662.91
PRC 3352503PJ3912 | 2024-12-17 | Inv. 34660 |  | 135104.31 | 12226.03 | 70667.43 | 64436.88
PRC 3352503PK3912 | 2025-01-16 | Inv. 34699 |  | 135104.31 | 12712.23 | 83379.66 | 51724.65
|  | Totals: | 135104.31 |  | 83379.66 |  | 51724.65
|  | CM Services | 134986.31 |  | 83320.66 |  | 51665.65
|  | Reimbursables | 118 |  | 59 |  | 59
|  | Total: | 135104.31 |  | 83379.66 |  | 51724.65

## #9294.01 Earth Services
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Earth Services & Abatement |  |  | Vendor: VS000007582
Acct. Codes-0017-335-MM23-9255 |  |  | RFB927930-02
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524060900 | 2024-02-29 | PO Procore | 9750 | 9750 |  |  | 9750 | FY24
PO 33525090900 | 2024-07-24 | Roll to FY25 |  | 9750 |  | 0 | 9750
PO 33525090900 | 2024-12-23 | CO #1 | -9750 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9294.01 Hilsabeck Schacht
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0017-335-MM23-9255 |  |  | RFB927930-02
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524064902 | 2024-03-04 | PO Procore | 40000 | 40000 |  |  | 40000 | FY24
PO 33525064902 | 2024-07-29 | Roll to FY25 |  | 40000 |  | 0 | 40000
PO 33525064902 | 2024-12-27 | CO #1 (No Cost CO) | 0 | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  |  |  | 40000 |  | 0 | 40000
|  | Totals: | 40000 |  | 0 |  | 40000

## #9294.01 Schumacher Elevator
DHS WRC Fire Alarm System Replacement Phase 2
Project # 9294.01
Program code 929401 |  |  | Major Program 4B02
Schumacher Elevator |  |  | Vendor: 00002108471
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ929401-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524158902 | 2024-06-06 | PO Procore | 7000 | 7000 |  |  | 7000 | FY24
PO 33525158902 | 2024-07-24 | Roll to FY25 |  | 7000 |  | 0 | 7000
PO 33525158902 | 2024-09-27 | CO #1(No Cost CO) | 0 | 7000 |  | 0 | 7000
PO 33525158902 | 2024-12-19 | CO #2(No Cost CO) | 0 | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  |  |  | 7000 |  | 0 | 7000
|  | Totals: | 7000 |  | 0 |  | 7000

## RECAP #9304.00
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
| Program code 930400 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1012876.59
C | DCI Group #22-028 PC |  | 13733.79 | 13733.79 | 0
| PM TIME |  | 31876.59 | 29635.81 | 2240.78
| Misc. |  | 9004.56 | 9004.56 | 0
| Shive Hattery Inc. |  | 68543.03 | 67575.03 | 968
C | Western Waterproofing |  | 365288.38 | 365288.38 | 0
C | DCI Group #22-028 CA |  | 73893.86 | 73893.86 | 0
| Proctor Mechanical |  | 443703.55 | 417715.49 | 25988.06
| Total Project Cost | 1012876.59 | 1006043.76 | 976846.92 | 29196.84 | 6832.83

## #9304.00 DCI Group #22-028 PC
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  | Major Program 4G01
DCI Group #22-028 PC |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523262800 | 2022-09-16 | PO Procore | 13757.71 | 13757.71 |  |  | 13757.71
PRC 3352326PA2800 | 2022-11-10 | Inv. 22-028 PC-01 |  | 13757.71 | 2794.03 | 2794.03 | 10963.68
PRC 3352326PB2800 | 2022-11-14 | Inv. 22-028 PC-02 |  | 13757.71 | 2383.25 | 5177.28 | 8580.43
PRC 3352326PC2800 | 2023-01-18 | Inv. 22-028 PC-03 |  | 13757.71 | 3793.38 | 8970.66 | 4787.05
PRC 3352326PD2800 | 2023-03-15 | Inv. 22-028 PC-04 |  | 13757.71 | 2483.07 | 11453.73 | 2303.98
PRC 3352326PE2800 | 2023-04-25 | Inv. 22-028 PC-05 |  | 13757.71 | 1518.06 | 12971.79 | 785.92
PRC 3352326PF2800 | 2023-06-23 | Inv. 22-028 PC-06 Final | -23.92 | 13733.79 | 762 | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  |  |  | 13733.79 |  | 13733.79 | -1.7479e-12
|  | Totals: | 13733.79 |  | 13733.79 |  | 0 | Final

## #9304.00 PM TIME
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E233
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 31000 | 31000 |  |  | 31000
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 31000 | 247.5 | 247.5 | 30752.5
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 31000 | 495 | 742.5 | 30257.5
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 31000 | 220 | 962.5 | 30037.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 158.2 | 31158.2 | 158.2 | 1120.7 | 30037.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 311.7 | 31469.9 | 311.7 | 1432.4 | 30037.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 151.02 | 31620.92 | 151.02 | 1583.42 | 30037.5
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 31620.92 | 844.97 | 2428.39 | 29192.53
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 31620.92 | 70.19 | 2498.58 | 29122.34
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 31620.92 | 615.27 | 3113.85 | 28507.07
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 89.76 | 31710.68 | 89.76 | 3203.61 | 28507.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 39.5 | 31750.18 | 39.5 | 3243.11 | 28507.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 126.41 | 31876.59 | 126.41 | 3369.52 | 28507.07
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 31876.59 | 211.33 | 3580.85 | 28295.74
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 31876.59 | 1281.52 | 4862.37 | 27014.22
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 31876.59 | 500.65 | 5363.02 | 26513.57
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 31876.59 | 2202.09 | 7565.11 | 24311.48
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 31876.59 | 260.07 | 7825.18 | 24051.41
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 31876.59 | 1529.1 | 9354.28 | 22522.31
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 31876.59 | 155.73 | 9510.01 | 22366.58
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 31876.59 | 1091.2 | 10601.21 | 21275.38
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 31876.59 | 336.4 | 10937.61 | 20938.98
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 31876.59 | 2969 | 13906.61 | 17969.98
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 31876.59 | 182.84 | 14089.45 | 17787.14
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 31876.59 | 1164.9 | 15254.35 | 16622.24
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 31876.59 | 344.13 | 15598.48 | 16278.11
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 31876.59 | 1923.2 | 17521.68 | 14354.91
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 31876.59 | 163.35 | 17685.03 | 14191.56
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 31876.59 | 1132.7 | 18817.73 | 13058.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 31876.59 | 152.67 | 18970.4 | 12906.19
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 31876.59 | 1225.5 | 20195.9 | 11680.69
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 31876.59 | 62.09 | 20257.99 | 11618.6
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 31876.59 | 466.7 | 20724.69 | 11151.9
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 31876.59 | 75.5 | 20800.19 | 11076.4
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 31876.59 | 551.3 | 21351.49 | 10525.1
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 31876.59 | 241.91 | 21593.4 | 10283.19
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 31876.59 | 2130.7 | 23724.1 | 8152.49
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 31876.59 | 276.49 | 24000.59 | 7876
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 31876.59 | 1396.1 | 25396.69 | 6479.9
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 31876.59 | 129.9 | 25526.59 | 6350
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 31876.59 | 981.3 | 26507.89 | 5368.7
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 31876.59 | 37.51 | 26545.4 | 5331.19
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 31876.59 | 336.1 | 26881.5 | 4995.09
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 31876.59 | 38.95 | 26920.45 | 4956.14
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 31876.59 | 326.7 | 27247.15 | 4629.44
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 31876.59 | 37.45 | 27284.6 | 4591.99
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 31876.59 | 339.6 | 27624.2 | 4252.39
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 31876.59 | 28.87 | 27653.07 | 4223.52
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 31876.59 | 317.6 | 27970.67 | 3905.92
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 31876.59 | 8.03 | 27978.7 | 3897.89
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 31876.59 | 41.5 | 28020.2 | 3856.39
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 31876.59 | 18.46 | 28038.66 | 3837.93
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 31876.59 | 164.5 | 28203.16 | 3673.43
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 31876.59 | 85.86 | 28289.02 | 3587.57
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 31876.59 | 571 | 28860.02 | 3016.57
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 31876.59 | 30.21 | 28890.23 | 2986.36
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 31876.59 | 199.4 | 29089.63 | 2786.96
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 31876.59 | 49.78 | 29139.41 | 2737.18
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 31876.59 | 496.4 | 29635.81 | 2240.78
[5 empty] | 31876.59 |  | 29635.81 | 2240.78
[5 empty] | 31876.59 |  | 29635.81 | 2240.78
[5 empty] | 31876.59 |  | 29635.81 | 2240.78
|  |  | Totals: | 31876.59 |  | 29635.81 |  | 2240.78

## #9304.00 Misc
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523059801 | 2023-02-28 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2485098-Final | 970 | 970
IET DAS202309115300001 | 2023-04-07 | 9500 |  | DAS Services for: March 1-31, 2023 | DAS202309115300001 | 60.38 | 1030.38
PRC 33523153801 | 2023-06-02 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV030545 | 146.21 | 1176.59
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Grounds | DAS2024081153 | 7827.97 | 9004.56
9004.56
9004.56
9004.56
9004.56
9004.56
9004.56
9004.56
9004.56
|  |  |  | Totals: |  | 9004.56

## #9304.00 Shive Hattery
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  | Major Program 4G01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP820400-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523320802 | 2022-11-16 | PO Procore | 47062 | 47062 |  |  | 47062
PRC 3352332PA0802 | 2023-01-20 | Inv. 2142205910-1 |  | 47062 | 9840 | 9840 | 37222
PRC 3352332PB0802 | 2023-01-25 | Inv. 2142205910-2 |  | 47062 | 13020 | 22860 | 24202
PO 33523320802 | 2023-02-14 | CO #1 | 20188 | 67250 |  | 22860 | 44390
PRC 3352332PC0802 | 2023-03-17 | Inv. 2142205910-3 |  | 67250 | 24239.2 | 47099.2 | 20150.8
PRC 3352332PD0802 | 2023-04-05 | Inv. 2142205910-4 |  | 67250 | 1879.4 | 48978.6 | 18271.4
PRC 3352332PE0802 | 2023-05-09 | Inv. 2142205910-5 |  | 67250 | 3971.4 | 52950 | 14300
PRC 3352332PF0802 | 2023-06-12 | Inv. 2142205910-6 |  | 67250 | 2200 | 55150 | 12100
PRC 3352332PG0802 | 2023-07-10 | Inv. 2142205910-7 |  | 67250 | 605 | 55755 | 11495
PO 33523320802 | 2023-07-14 | CO #2 | 4331 | 71581 |  | 55755 | 15826 | FY23
PO 33524320802 | 2023-08-11 | Rolled to FY24 | 0 | 71581 |  | 55755 | 15826
PRC 3352432PH0802 | 2023-08-28 | Inv. 2142205910-8 |  | 71581 | 3630 | 59385 | 12196
PRC 3352432PI0802 | 2023-11-03 | Inv. 2142205910-9 |  | 71581 | 6413 | 65798 | 5783
PO 33524320802 | 2024-02-23 | CO #3 | -4410 | 67171 |  | 65798 | 1373
PO 33524320802 | 2024-03-18 | CO #4 | 1372.03 | 68543.03 |  | 65798 | 2745.03
PRC 3352432PJ0802 | 2024-03-28 | Inv. 2142205910-10 |  | 68543.03 | 1535.03 | 67333.03 | 1210
PRC 3352432PK0802 | 2024-07-15 | Inv. 2142205910-11 |  | 68543.03 | 242 | 67575.03 | 968 | FY24
PO 33525320802 | 2024-07-24 | Roll to FY25 |  | 68543.03 |  | 67575.03 | 968
|  |  |  | 68543.03 |  | 67575.03 | 968
|  |  |  | 68543.03 |  | 67575.03 | 968
|  | Totals: | 68543.03 |  | 67575.03 |  | 968
|  | Design Development Documents | 16400 |  | 16400 |  | 0
|  | 50% Construction Documents | 7600 |  | 7600 |  | 0
|  | 95% Construction Documents | 5800 |  | 5800 |  | 0
|  | 100% Construction Documents | 2962 |  | 2962 |  | 0
|  | Bidding Assistance | 2200 |  | 2200 |  | 0
|  | Construction Phase | 12100 |  | 11132 |  | 968
|  | CO #1 | 20188 |  | 20188 |  | 0
|  | CO #2 | 4331 |  | 4331 |  | 0
|  | CO #3 | -4410 |  | -4410 |  | 0
|  | CO #4 | 1372.03 |  | 1372.03 |  | 0
|  | Totals: | 68543.03 |  | 67575.03 |  | 968

## #9304.00 Western Waterproofing
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  | Major Program 4G01
Western Waterproofing |  |  | Vendor: 00002132736
Acct. Codes-0017-335-MM23-9255 |  |  | RFB930400-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523172801 | 2023-06-21 | PO Procore | 344000 | 344000 |  |  | 344000 |  | FY23
PO 33524172801 | 2023-08-07 | Roll to FY24 | 0 | 344000 |  | 0 | 344000
PRC 3352417PA2801 | 2023-08-07 | Inv. 114296 |  | 344000 | 30134 | 30134 | 313866 | 1586
PRC 3352417PB2801 | 2023-08-29 | Inv. 115460 |  | 344000 | 138106.87 | 168240.87 | 175759.13 | 8854.78
PO 33524172801 | 2023-09-11 | CO #1 | 9808.5 | 353808.5 |  | 168240.87 | 185567.63
PRC 3352417PC2801 | 2023-10-13 | Inv. 116215 |  | 353808.5 | 133619.25 | 301860.12 | 51948.38 | 15887.38
PO 33524172801 | 2023-10-20 | CO #2 | 8712.98 | 362521.48 |  | 301860.12 | 60661.36
PRC 3352417PD2801 | 2023-10-25 | Inv. 117142 |  | 362521.48 | 37603.83 | 339463.95 | 23057.53 | 17866.53
PO 33524172801 | 2023-10-26 | CO #3 | 2766.9 | 365288.38 |  | 339463.95 | 25824.43
PRC 3352417PE2801 | 2023-11-29 | Inv. 118091 |  | 365288.38 | 3949.05 | 343413 | 21875.38 | 18074.38
PO 33524172801 | 2023-12-06 | CO #4 (No Cost CO) | 0 | 365288.38 |  | 343413 | 21875.38
PRC 3352417PF2801 | 2024-03-18 | Inv. 120274 |  | 365288.38 | 275.5 | 343688.5 | 21599.88 | 18088.88
PRC 3352417PG2801 | 2024-05-13 | Inv. 120801 |  | 365288.38 | 3335.45 | 347023.95 | 18264.43 | 18264.43
PRC 3352417PH2801 | 2024-05-28 | Inv. 121917 Retainage |  | 365288.38 | 18264.43 | 365288.38 | 0
|  |  |  | 365288.38 |  | 365288.38 | 0
|  | Totals: | 365288.38 |  | 365288.38 |  | 0 | FINAL

## #9304.00 DCI Group #22-028 CA
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  | Major Program 4G01
DCI Group #22-028 CA |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523174801 | 2023-06-23 | PO Procore | 77209.51 | 77209.51 |  |  | 77209.51
PRC 3352317PA4801 | 2023-07-13 | Inv. 22-028 CA-01 |  | 77209.51 | 3370.71 | 3370.71 | 73838.8 | FY23
PO 33524174801 | 2023-08-07 | Roll to FY24 | 0 | 77209.51 |  | 3370.71 | 73838.8
PRC 3352417PB4801 | 2023-10-05 | Inv. 22-028 CA-02 |  | 77209.51 | 38204.89 | 41575.6 | 35633.91
PRC 3352417PC4801 | 2023-11-17 | Inv. 22-028 CA-03 |  | 77209.51 | 24859.33 | 66434.93 | 10774.58
PRC 3352417PD4801 | 2023-12-21 | Inv. 22-028 CA 04 |  | 77209.51 | 3012.12 | 69447.05 | 7762.46
PRC 3352417PE4801 | 2024-01-23 | Inv. 9304.00-05 |  | 77209.51 | 1560.65 | 71007.7 | 6201.81
PRC 3352417PF4801 | 2024-03-05 | Inv. 22-028 CA 6 |  | 77209.51 | 621.56 | 71629.26 | 5580.25
PO 33524174801 | 2024-06-28 | CO #1 | 2224.16 | 79433.67 |  | 71629.26 | 7804.41
PRC 3352417PG4801 | 2024-07-15 | Inv. 22-028 CA 07 |  | 79433.67 | 621.56 | 72250.82 | 7182.85
PRC 3352417PH4801 | 2024-07-22 | Inv. 22-028 CA 08 |  | 79433.67 | 1014.36 | 73265.18 | 6168.49 | FY24
PO 33525174801 | 2024-07-24 | Roll to FY25 |  | 79433.67 |  | 73265.18 | 6168.49
PRC 3352517PI4801 | 2025-01-14 | Inv. 22-028 CA #9 Final | -5539.81 | 73893.86 | 628.68 | 73893.86 | 0
|  |  |  | 73893.86 |  | 73893.86 | 0
|  |  |  | 73893.86 |  | 73893.86 | 0
|  | Totals: | 73893.86 |  | 73893.86 |  | 0 | FINAL
|  | Construction Management Staff Hours | 29759.09 |  | 29759.09 |  | 0
|  | Construction Management Fee | 37490 |  | 37490 |  | 0
|  | Reimbursable Expenses | 4432.49 |  | 4432.49 |  | 0
|  | CO #1 | 2212.28 |  | 2212.28 |  | 0
|  | Totals: | 73893.86 |  | 73893.86 |  | 0

## #9304.00 Proctor Mechanical
DAS CC Parking Ramp Concrete and Piping Repair
Project # 9304.00
Program code 930400 |  |  | Major Program 4G01
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM23-9255 |  |  | RFB930400-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523202800 | 2023-07-21 | PO Procore | 400300 | 400300 |  |  | 400300 |  | FY23
PO 33524202800 | 2023-08-07 | Roll to FY24 | 0 | 400300 |  | 0 | 400300
PRC 3352420PA2800 | 2023-08-31 | Inv. 7574.0/1 |  | 400300 | 135961.9 | 135961.9 | 264338.1 | 7155.9
PRC 3352420PB2800 | 2023-10-13 | Inv. 9304.00-02 |  | 400300 | 174804.12 | 310766.02 | 89533.98 | 16356.13
PO 33524202800 | 2023-12-08 | CO #1 | 1762.66 | 402062.66 |  | 310766.02 | 91296.64
PRC 3352420PC2800 | 2024-01-03 | Inv. 7574.0/3 |  | 402062.66 | 46909.48 | 357675.5 | 44387.16 | 18825.05
PO 33524202800 | 2024-02-12 | CO #2 | 4410 | 406472.66 |  | 357675.5 | 48797.16
PRC 3352420PD2800 | 2024-03-06 | Inv. 7574.0/4 |  | 406472.66 | 16301.15 | 373976.65 | 32496.01 | 19683.01
PO 33524202800 | 2024-03-08 | CO #3 | -1372.03 | 405100.63 |  | 373976.65 | 31123.98
PO 33524202800 | 2024-04-02 | CO #4 | 38602.92 | 443703.55 |  | 373976.65 | 69726.9
PRC 3352420PE2800 | 2024-04-15 | Inv. 7574.0/5 |  | 443703.55 | 7066.07 | 381042.72 | 62660.83 | 20054.91
PO 33524202800 | 2024-07-23 | CO #5(No Cost CO) | 0 | 443703.55 |  | 381042.72 | 62660.83 |  | FY24
PO 33525202800 | 2024-07-24 | Roll to FY25 |  | 443703.55 |  | 381042.72 | 62660.83
PO 33525202800 | 2024-10-31 | CO #6(No Cost CO) | 0 | 443703.55 |  | 381042.72 | 62660.83
PRC 3352520PF2800 | 2025-01-03 | Inv. 7574.0/6 |  | 443703.55 | 36672.77 | 417715.49 | 25988.06 | 21985.06
|  |  |  | 443703.55 |  | 417715.49 | 25988.06
|  |  |  | 443703.55 |  | 417715.49 | 25988.06
|  | Totals: | 443703.55 |  | 417715.49 |  | 25988.06

## RECAP #9305.00
DAS CC Capitol North and South Stair Repair
Project # 9305.00
| Program code 930500 |  |  | Major Program 4D01
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1793919.79
C | Samuels Group |  | 17724.37 | 17724.37 | 0
| PM TIME |  | 46776.41 | 43906.88 | 2869.53
| Misc. |  | 22075.99 | 22075.99 | 0
| OPN Architects |  | 57455 | 54978.61 | 2476.39
| Samuels Group |  | 144611.06 | 128608.44 | 16002.62
| Neumann Brothers Inc |  | 1449553.63 | 1261192.03 | 188361.6
| Waldinger Electric |  | 20000 | 3417.47 | 16582.53
| Total Project Cost | 1793919.79 | 1758196.46 | 1531903.79 | 226292.67 | 35723.33

## #9305.00 Samuels Group
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  | Major Program 4D01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523294901 | 2022-10-21 | PO Procore | 12353.24 | 12353.24 |  |  | 12353.24
PRC 3352329PA4901 | 2022-11-07 | Inv. 7448.01930500 |  | 12353.24 | 497.92 | 497.92 | 11855.32
PRC 3352329PB4901 | 2022-12-12 | Inv. 7448.02930500 |  | 12353.24 | 530.4 | 1028.32 | 11324.92
PRC 3352329PC4901 | 2023-01-09 | Inv. 7448.03930500 |  | 12353.24 | 779.36 | 1807.68 | 10545.56
PRC 3352329PD4901 | 2023-07-13 | Inv. 7448.04930500 |  | 12353.24 | 497.92 | 2305.6 | 10047.64 | FY23
PO 33524294901 | 2023-08-11 | Rolled to FY24 | 0 | 12353.24 |  | 2305.6 | 10047.64
PRC 3352429PE4901 | 2023-08-21 | Inv. 7448.05930500 |  | 12353.24 | 2430.07 | 4735.67 | 7617.57
PRC 3352429PF4901 | 2023-09-12 | Inv. 7448.06930500 |  | 12353.24 | 757.72 | 5493.39 | 6859.85
PRC 3352429PG4901 | 2023-10-04 | Inv. 7448.07930500 |  | 12353.24 | 941.73 | 6435.12 | 5918.12
PRC 3352429PH4901 | 2023-11-08 | Inv. 7448.08930500 |  | 12353.24 | 849.73 | 7284.85 | 5068.39
PRC 3352429PI4901 | 2023-12-12 | Inv. 7448.09930500 |  | 12353.24 | 1953.2 | 9238.05 | 3115.19
PRC 3352429PJ4901 | 2024-01-05 | Inv. 7448.10930500 |  | 12353.24 | 1374.7 | 10612.75 | 1740.49
PRC 3352429PK4901 | 2024-02-05 | Inv. 7448.11930500 |  | 12353.24 | 627.82 | 11240.57 | 1112.67
PRC 3352429PL4901 | 2024-03-05 | Inv. 7448.12930500 |  | 12353.24 | 995.84 | 12236.41 | 116.83
PRC 33524294901 | 2024-03-18 | CO #1 | 5408.61 | 17761.85 |  | 12236.41 | 5525.44
PRC 3352429PM4901 | 2024-04-08 | Inv. 7448.13930500 |  | 17761.85 | 4113.26 | 16349.67 | 1412.18
PRC 3352429PN4901 | 2024-05-06 | Inv. 7448.14930500 Final | -37.48 | 17724.37 | 1374.7 | 17724.37 | -6.608e-13
|  | Totals: | 17724.37 |  | 17724.37 |  | 0 | FINAL
|  | CM Services | 12253.24 |  | 12253.24 |  | 0
|  | Reimbursables | 77.87 |  | 77.87 |  | 0
|  | CO#1 | 5393.26 |  | 5393.26 |  | 0
|  | Total: | 17724.37 |  | 17724.37 |  | 0

## #9305.00 PM TIME
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  |  | Major Program 4D01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E234
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 45000 | 45000 |  |  | 45000
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 45000 | 275 | 275 | 44725
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 45000 | 275 | 550 | 44450
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 45000 | 1265 | 1815 | 43185
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 45000 | 247.5 | 2062.5 | 42937.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 233.84 | 45233.84 | 233.84 | 2296.34 | 42937.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 148 | 45381.84 | 148 | 2444.34 | 42937.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 923.66 | 46305.5 | 923.66 | 3368 | 42937.5
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 189.73 | 46495.23 | 189.73 | 3557.73 | 42937.5
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 46495.23 | 352.26 | 3909.99 | 42585.24
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 46495.23 | 23.87 | 3933.86 | 42561.37
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 46495.23 | 209.32 | 4143.18 | 42352.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 40.53 | 46535.76 | 40.53 | 4183.71 | 42352.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 141.4 | 46677.16 | 141.4 | 4325.11 | 42352.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 46.55 | 46723.71 | 46.55 | 4371.66 | 42352.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 52.7 | 46776.41 | 52.7 | 4424.36 | 42352.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 46776.41 | 32.07 | 4456.43 | 42319.98
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 46776.41 | 194.47 | 4650.9 | 42125.51
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 46776.41 | 25.03 | 4675.93 | 42100.48
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 46776.41 | 110.11 | 4786.04 | 41990.37
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 46776.41 | 43.38 | 4829.42 | 41946.99
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 46776.41 | 254.4 | 5083.82 | 41692.59
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 46776.41 | 7.83 | 5091.65 | 41684.76
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 46776.41 | 57.2 | 5148.85 | 41627.56
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 46776.41 | 93.36 | 5242.21 | 41534.2
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 46776.41 | 841.2 | 6083.41 | 40693
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 46776.41 | 170.72 | 6254.13 | 40522.28
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 46776.41 | 1086.9 | 7341.03 | 39435.38
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 46776.41 | 242.64 | 7583.67 | 39192.74
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 46776.41 | 1355.4 | 8939.07 | 37837.34
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 46776.41 | 123.7 | 9062.77 | 37713.64
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 46776.41 | 861.4 | 9924.17 | 36852.24
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 46776.41 | 89.22 | 10013.39 | 36763.02
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 46776.41 | 717.9 | 10731.29 | 36045.12
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 46776.41 | 179.08 | 10910.37 | 35866.04
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 46776.41 | 1354.8 | 12265.17 | 34511.24
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 46776.41 | 266.16 | 12531.33 | 34245.08
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 46776.41 | 1953.1 | 14484.43 | 32291.98
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 46776.41 | 302.17 | 14786.6 | 31989.81
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 46776.41 | 2663.5 | 17450.1 | 29326.31
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 46776.41 | 276.49 | 17726.59 | 29049.82
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 46776.41 | 1396.1 | 19122.69 | 27653.72
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 46776.41 | 416.55 | 19539.24 | 27237.17
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 46776.41 | 3158.9 | 22698.14 | 24078.27
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 46776.41 | 172.93 | 22871.07 | 23905.34
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 46776.41 | 1537.3 | 24408.37 | 22368.04
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 46776.41 | 163.17 | 24571.54 | 22204.87
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 46776.41 | 1350.5 | 25922.04 | 20854.37
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 46776.41 | 324.9 | 26246.94 | 20529.47
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 46776.41 | 2967.6 | 29214.54 | 17561.87
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 46776.41 | 283.45 | 29497.99 | 17278.42
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 46776.41 | 3096.8 | 32594.79 | 14181.62
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 46776.41 | 387.18 | 32981.97 | 13794.44
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 46776.41 | 1972.4 | 34954.37 | 11822.04
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 46776.41 | 220.32 | 35174.69 | 11601.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 46776.41 | 1964 | 37138.69 | 9637.72
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 46776.41 | 382.36 | 37521.05 | 9255.36
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 46776.41 | 2551.1 | 40072.15 | 6704.26
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 46776.41 | 263.66 | 40335.81 | 6440.6
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 46776.41 | 1751.6 | 42087.41 | 4689
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 46776.41 | 165.37 | 42252.78 | 4523.63
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 46776.41 | 1654.1 | 43906.88 | 2869.53
[5 empty] | 46776.41 |  | 43906.88 | 2869.53
[5 empty] | 46776.41 |  | 43906.88 | 2869.53
[5 empty] | 46776.41 |  | 43906.88 | 2869.53
|  |  | Totals: | 46776.41 |  | 43906.88 |  | 2869.53
Note on E9: Huggins, Joni [DAS]: James Trower - PM Time $Joni Trower, James 1:08 PM (50 minutes ago) to me Finance - See below items: 9203.00 - DOC NCCF Treatment Center EIFS Replacement: Increase PM Time by $5,000 (MM21) 9231.00 - DAS CC Jessie Parker Water: Increase PM Time by $4,000 (MM22) 9250.00 - DOC MPCF Building 18 Roof Replacement: Increase PM Time by $5,000 (MM22) 9297.00 - DOC MPCF Gym Floor Repair: Set up $6,000 in PM Time (MM21) 9300.00 - DOC MPFC Storage Bunker Repair: Set up $6,000 in PM Time (MM21) 9301.00 - DPS DSM Fleet & Supply 2nd Floor Structural: Set up $4,000 in PM Time (MM21) 9305.00 - DAS CC Capitol South Stair Repair:Set up $6,000 in PM Time (MM23) 9308.00 - DOC NCCF Generator System Control Replacement: Set up $6,000 in PM Time (MM23) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov Trower, James Aug 31, 2023, 2:05 PM (6 days ago) to me Finance - Please make the below increases to PM Time: 9203.00 - Treatment Center EIFS Replacement (MM21) - Increase PM Time by $5,000 9231.00 - Jessie Parker Water Infiltration Repair (MM22) - Increase PM Time by $1,000 9251.00 - DPS P09 Parking Lot Replacement (MM22) - Increase PM Time by $1,000 9252.00 - Window Replacement (MM22) - Increase PM Time by $1,000 9305.00 - DAS CC Capitol North and South Stair Repair (MM23) - Increase PM Time by $6,000 Re: PM Time $John Trower, James 12:39 PM (1 hour ago) to me Finance - See below in red: DA23 9336.00 Amt. $578.60 INCREASE PM TIME BY $3,000 MM21 9176.00 Amt. $4342.80 INCREASE PM TIME BY $7,000 MM21 9342.00 Amt. $1254.00 INCREASE PM TIME BY $5,000 MM22 9258.00 Amt. $627.00 INCREASE PM TIME BY $3,000 MM23 9305.00 Amt. $1882.10 INCREASE PM TIME BY $10,000 Thanks, James 9305.00 - DAS CC Capitol North and South Stairs Repair - Budget $Joni Trower, James May 8, 2024, 4:24 PM (14 hours ago) to me Finance - Increase the project's funds by $300,000 (MM23) Increase PM Time by $20,000 (MM23) After adding $300,000 (per the above request), the new total funding for project 9305.00 should be $1,501,129.65. Trower, James Thu, Jan 9, 12:42 PM (18 hours ago) to me Joni - Please increase PM Time by $3,000.

## #9305.00 Misc
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  |  | Major Program 4D01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202404115300001 | 2023-11-08 | 2507 |  | Electrical Services | DAS2024041153 | 91.94 | 91.94
GAX 33524347907 | 2023-12-13 | 9500 | BRUM | Earth Services V#(VS000007582) | Inv. DES-I001754 | 1686 | 1777.94
PRC 33524362800 | 2023-12-28 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 254521 | 905 | 2682.94
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 27.5 | 2710.44
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 357.5 | 3067.94
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -385 | 2682.94
PRC 33524166905 | 2024-06-13 | 9500 |  | Rapids Reproductions V#(00002111375) | Inv. INVCL616 | 388.5 | 3071.44
IET DAS202412115300001 | 2024-07-17 | 2507 |  | Electrical Services June 1-30, 2024 | DAS2024121153 | 6836.71 | 9908.15
PRC 33524213900 | 2024-07-30 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL493 | 322.18 | 10230.33
IET DAS202501115300001 | 2024-08-07 | 2507 |  | Electrical Services July 1-31, 2024 | DAS2025011153 | 110.83 | 10341.16
IET DAS202502115300001 | 2024-09-09 | 2507 |  | Grounds Services August 1-31, 2024 | DAS2025021153 | 1557.68 | 11898.84
PRC 33525276907 | 2024-10-02 | 9500 | CNST | Earth Services V#(VS000007582) | Inv. DES-i002131 | 9514.39 | 21413.23
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Fire Watch | DAS202531153 | 80.42 | 21493.65
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Fire Watch | DAS202541153 | 582.34 | 22075.99
22075.99
22075.99
|  |  |  | Totals: |  | 22075.99

## #9305.00 OPN Architects
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  | Major Program 4D01
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM23-9260 |  |  | RFP930500-02
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 335241216800 | 2023-08-04 | PO Procore | 45680 | 45680 |  |  | 45680
PRC 33524121PA6800 | 2023-11-21 | Inv. 19802015-1 |  | 45680 | 18154 | 18154 | 27526
PRC 33524121PB6800 | 2023-12-01 | Inv. 19802015-2 |  | 45680 | 6630 | 24784 | 20896
PRC 33524121PC6800 | 2024-01-17 | Inv. 19802015-3 |  | 45680 | 5592 | 30376 | 15304
PO 335241216800 | 2024-02-06 | CO #1 | 11775 | 57455 |  | 30376 | 27079
PRC 33524121PD6800 | 2024-02-23 | Inv. 19802015-4 |  | 57455 | 15794 | 46170 | 11285
PRC 33524121PE6800 | 2024-06-10 | Inv. 19802015-5 |  | 57455 | 2247.06 | 48417.06 | 9037.94
PRC 33524121PF6800 | 2024-07-03 | Inv. 19802015-6 |  | 57455 | 681.6 | 49098.66 | 8356.34 | FY24
PO 335251216800 | 2024-07-24 | Roll to FY25 |  | 57455 |  | 49098.66 | 8356.34
PRC 33525121PG6800 | 2024-08-15 | Inv. 19802015-7 |  | 57455 | 446.6 | 49545.26 | 7909.74
PRC 33525121PH6800 | 2024-09-06 | Inv. 19802015-8 |  | 57455 | 917.6 | 50462.86 | 6992.14
PRC 33525121PI6800 | 2024-10-10 | Inv. 19802015-9 |  | 57455 | 441.82 | 50904.68 | 6550.32
PRC 33525121PJ6800 | 2024-11-12 | Inv. 19802015-10 |  | 57455 | 906.43 | 51811.11 | 5643.89
PRC 33525121PK6800 | 2024-12-10 | Inv. 19802015-11 |  | 57455 | 438.63 | 52249.74 | 5205.26
PRC 33525121PL6800 | 2025-01-14 | Inv. 19802015-12 |  | 57455 | 2728.87 | 54978.61 | 2476.39
|  |  |  | 57455 |  | 54978.61 | 2476.39
|  | Totals: | 57455 |  | 54978.61 |  | 2476.39

## #9305.00 Samuels Group (2)
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  | Major Program 4D01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524137902 | 2024-05-16 | PO Procore | 138276.76 | 138276.76 |  |  | 138276.76
PRC 3352413PA7902 | 2024-06-03 | Inv. 7693.51930500 CA |  | 138276.76 | 2333.76 | 2333.76 | 135943
PRC 3352413PB7902 | 2024-07-05 | Inv. 7693.52930500 |  | 138276.76 | 9739.61 | 12073.37 | 126203.39
PO 33524137902 | 2024-07-22 | CO #1 | 6334.3 | 144611.06 |  | 12073.37 | 132537.69 | FY24
PO 33525137902 | 2024-07-24 | Roll to FY25 |  | 144611.06 |  | 12073.37 | 132537.69
PRC 3352513PC7902 | 2024-08-09 | Inv. 7693.53930500 |  | 144611.06 | 12815.41 | 24888.78 | 119722.28
PRC 3352513PD7902 | 2024-09-12 | Inv. 7693.54930500 |  | 144611.06 | 22073.1 | 46961.88 | 97649.18
PRC 3352513PE7902 | 2024-10-03 | Inv. 7693.55930500 |  | 144611.06 | 18199.93 | 65161.81 | 79449.25
PRC 3352513PF7902 | 2024-11-12 | Inv. 7693.56930500 |  | 144611.06 | 28969.35 | 94131.16 | 50479.9
PRC 3352513PG7902 | 2024-12-05 | Inv. 7693.57930500 |  | 144611.06 | 19422.66 | 113553.82 | 31057.24
PRC 3352513PH7902 | 2025-01-06 | Inv. 7693.58930500 |  | 144611.06 | 15054.62 | 128608.44 | 16002.62
|  |  |  | 144611.06 |  | 128608.44 | 16002.62
|  |  |  | 144611.06 |  | 128608.44 | 16002.62
|  | Totals: | 144611.06 |  | 128608.44 |  | 16002.62
|  | CM Services | 77121.76 |  | 68454.53 |  | 8667.23
|  | Reimbursables | 2000 |  | 572.82 |  | 1427.18
|  | Fee | 59155 |  | 55507.1 |  | 3647.9
|  | CO #1 | 6334.3 |  | 4073.99 |  | 2260.31
|  | Total: | 144611.06 |  | 128608.44 |  | 16002.62

## #9305.00 Neumann Brothers Inc
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  | Major Program 4D01
Neumann Brothers Inc |  |  | Vendor: 00002106354
Acct. Codes-0017-335-MM23-9255 |  |  | RFB930500-02
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524142801 | 2024-05-21 | PO Procore | 1183100 | 1183100 |  |  | 1183100
PRC 3352414PA2801 | 2024-07-03 | Inv. 56296 |  | 1183100 | 83381.23 | 83381.23 | 1099718.77 | 4388.5 | FY24
PO 33525142801 | 2024-07-24 | Roll to FY25 |  | 1183100 |  | 83381.23 | 1099718.77
PO 33525142801 | 2024-08-06 | CO #1 | 63569.83 | 1246669.83 |  | 83381.23 | 1163288.6
PRC 3352514PB2801 | 2024-08-07 | Inv. 56393 |  | 1246669.83 | 206785.24 | 290166.47 | 956503.36 | 15271.95
PO 33525142801 | 2024-09-06 | CO #2 | 77012.7 | 1323682.53 |  | 290166.47 | 1033516.06
PRC 3352514PC2801 | 2024-09-19 | Inv. 56452 |  | 1323682.53 | 185398.32 | 475564.79 | 848117.74 | 25029.75
PO 33525142801 | 2024-10-07 | CO #3 | 46442.98 | 1370125.51 |  | 475564.79 | 894560.72
PRC 3352514PD2801 | 2024-10-14 | Inv. 56507 |  | 1370125.51 | 319853.89 | 795418.68 | 574706.83 | 41864.2
PRC 3352514PE2801 | 2024-11-12 | Inv. 56561 |  | 1370125.51 | 152672.48 | 948091.16 | 422034.35 | 49899.6
PO 33525142801 | 2024-11-15 | CO #4 | 79428.12 | 1449553.63 |  | 948091.16 | 501462.47
PRC 3352514PF2801 | 2024-12-03 | Inv. 56616 |  | 1449553.63 | 216396.56 | 1164487.72 | 285065.91 | 61288.9
PRC 3352514PG2801 | 2025-01-07 | Inv. 56689 |  | 1449553.63 | 96704.31 | 1261192.03 | 188361.6 | 66378.63
|  |  |  | 1449553.63 |  | 1261192.03 | 188361.6
|  |  |  | 1449553.63 |  | 1261192.03 | 188361.6
|  | Totals: | 1449553.63 |  | 1261192.03 |  | 188361.6

## #9305.00 Waldinger Electric
DAS CC Capitol North and South Stair Repair
Project # 9305.00
Program code 930500 |  |  | Major Program 4D01
Waldinger Electric |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM23-9255 |  |  | MA20452A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525211905 | 2024-07-29 | PO Procore | 20000 | 20000 |  |  | 20000
PRC 3352521PA1905 | 2024-10-21 | Inv. 8088E-001 |  | 20000 | 3417.47 | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  |  |  | 20000 |  | 3417.47 | 16582.53
|  | Totals: | 20000 |  | 3417.47 |  | 16582.53
|  | Labor | 6500 |  | 2917.48 |  | 3582.52
|  | Materials | 13500 |  | 499.99 |  | 13000.01
|  | Total: | 20000 |  | 3417.47 |  | 16582.53

## RECAP #9306.00
DOC CCF Metal Roof Replacement Design
Project # 9306.00
| Program code 930600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 99231.92
C | Samuels Group |  | 31751.13 | 31751.13 | 0
C | PM TIME |  | 12013.55 | 12013.55 | 0
| Misc. |  | 251 | 251 | 0
| Genesis Architectural Design |  | 48900 | 39156 | 9744
C | Septagon Construction |  | 5900 | 5900 | 0
| Total Project Cost | 99231.92 | 98815.68 | 89071.68 | 9744 | 416.24

## #9306.00 Samuels Group
DOC CCF Metal Roof Replacement Design
Project # 9306.00
Program code 930600 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels1012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523061800 | 2023-03-02 | PO Procore | 34169.36 | 34169.36 |  |  | 34169.36
PRC 3352306PA1800 | 2023-04-04 | Inv. 7478.01930600 |  | 34169.36 | 993.6 | 993.6 | 33175.76
PRC 3352306PB1800 | 2023-05-11 | Inv. 7478.02930600 |  | 34169.36 | 2674.25 | 3667.85 | 30501.51
PRC 3352306PC1800 | 2023-06-05 | Inv. 7478.03930600 |  | 34169.36 | 3334.43 | 7002.28 | 27167.08
PRC 3352306PD1800 | 2023-07-06 | Inv. 7478.04930600 |  | 34169.36 | 1691.25 | 8693.53 | 25475.83 | FY23
PO 33524061800 | 2023-08-04 | Roll to FY24 | 0 | 34169.36 |  | 8693.53 | 25475.83
PRC 3352406PE1800 | 2023-08-07 | Inv. 7478.05930600 |  | 34169.36 | 3779.25 | 12472.78 | 21696.58
PRC 3352406PF1800 | 2023-09-14 | Inv. 7478.06930600 |  | 34169.36 | 8531.59 | 21004.37 | 13164.99
PRC 3352406PG1800 | 2023-10-06 | Inv. 7478.07930600 |  | 34169.36 | 4619.44 | 25623.81 | 8545.55
PRC 3352406PH1800 | 2023-11-07 | Inv. 7478.08930600 Final PC | -2418.23 | 31751.13 | 6127.32 | 31751.13 | 0
|  | Totals: | 31751.13 |  | 31751.13 |  | 0
|  | CM Services | 31271.13 |  | 31271.13 |  | 0
|  | Reimbursables | 480 |  | 480 |  | 0
|  | Total: | 31751.13 |  | 31751.13 |  | 0

## #9306.00 PM Time
DOC CCF Metal Roof Replacement Design
Project # 9306.00
Program code 930600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E235
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11781.63 | 11781.63 |  |  | 11781.63
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 11781.63 | 55 | 55 | 11726.63
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 11781.63 | 82.5 | 137.5 | 11644.13
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 35.17 | 11816.8 | 35.17 | 172.67 | 11644.13
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 56.63 | 11873.43 | 56.63 | 229.3 | 11644.13
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 11873.43 | 140.83 | 370.13 | 11503.3
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 11873.43 | 32.39 | 402.52 | 11470.91
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 11873.43 | 283.98 | 686.5 | 11186.93
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 104.24 | 11977.67 | 104.24 | 790.74 | 11186.93
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 14.81 | 11992.48 | 14.81 | 805.55 | 11186.93
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 21.07 | 12013.55 | 21.07 | 826.62 | 11186.93
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 12013.55 | 33.98 | 860.6 | 11152.95
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 12013.55 | 206.09 | 1066.69 | 10946.86
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 12013.55 | 149.84 | 1216.53 | 10797.02
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 12013.55 | 659.1 | 1875.63 | 10137.92
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 12013.55 | 167.17 | 2042.8 | 9970.75
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 12013.55 | 983.2 | 3026 | 8987.55
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 12013.55 | 205.46 | 3231.46 | 8782.09
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 12013.55 | 1439.9 | 4671.36 | 7342.19
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 12013.55 | 132.74 | 4804.1 | 7209.45
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 12013.55 | 1097.2 | 5901.3 | 6112.25
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 12013.55 | 117.43 | 6018.73 | 5994.82
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 12013.55 | 747.5 | 6766.23 | 5247.32
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 12013.55 | 284.41 | 7050.64 | 4962.91
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 12013.55 | 1586 | 8636.64 | 3376.91
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 12013.55 | 168.78 | 8805.42 | 3208.13
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 12013.55 | 1172.6 | 9978.02 | 2035.53
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 12013.55 | 187.33 | 10165.35 | 1848.2
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 12013.55 | 1503.6 | 11668.95 | 344.6
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 12013.55 | 26.51 | 11695.46 | 318.09
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12013.55 | 135.4 | 11830.86 | 182.69
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12013.55 | 21.69 | 11852.55 | 161
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12013.55 | 161 | 12013.55 | 8.2423e-13
|  |  | Totals: | 12013.55 |  | 12013.55 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: PM Time for September $Joni Herman, Josh 8:53 AM (5 hours ago) to me 8983.02 in MM22 Please add $5,500. 9306.00 in MM23 Please set at $8,800 9313.00 in DA23 Please set at $4,200. 9246.00 in MM22 Please change to $10,000 total. 9245.00 in MM22 Please change to $10,000 total. 9287.00 in MM21 Please change to $10,000 total. 9268.00 in MM20 Please add $1,100. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time $John Tonyan, Brad 3:13 PM (9 minutes ago) to me John, Please see the following below: DA22 - 9242.00 - Increase budget by $5,000 please MM23 - 9306.00 - Increase budget by $3,000 please Thank you Tonyan, Brad 12:12 PM (53 minutes ago) to DAS, me Joni, Thank you and I am going to process a PM Time "dummy" invoice for 9306.00 on MM23 if you could close out the PM Time on this as well. Brad Tonyan, CPM, LEED Green Associate

## #9306.00 Misc
DOC CCF Metal Roof Replacement Design
Project # 9306.00
Program code 930600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524242801 | 2023-08-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV032830 | 15 | 15
PRC 33524271801 | 2023-09-28 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV033578 | 236 | 251
251
251
251
251
251
251
251
251
251
251
|  |  |  | Totals: |  | 251

## #9306.00 Genesis Architectural
DOC CCF Metal Roof Replacement Design
Project # 9306.00
Program code 930600 |  |  | Major Program 4E01
Genesis Architectural Design |  |  | Vendor:00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP930600-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523129801 | 2023-05-09 | PO Procore | 48900 | 48900 |  |  | 48900
PRC 3352312PA9801 | 2023-06-09 | Inv. 2306-01 |  | 48900 | 7350 | 7350 | 41550
PRC 3352312PB9801 | 2023-06-30 | Inv. 2306-02 |  | 48900 | 6470 | 13820 | 35080 | FY23
PO 33524129801 | 2023-08-04 | Roll to FY24 | 0 | 48900 |  | 13820 | 35080
PRC 3352412PC9801 | 2023-08-21 | Inv. 2306-03 |  | 48900 | 8710 | 22530 | 26370
PRC 3352412PD9801 | 2023-10-02 | Inv. 2306-04 |  | 48900 | 3170 | 25700 | 23200
PRC 3352412PE9801 | 2024-02-29 | Inv. 2306-05 |  | 48900 | 1160 | 26860 | 22040
PRC 3352412PF9801 | 2024-04-03 | Inv. 2306-06 |  | 48900 | 1856 | 28716 | 20184
PRC 3352412PG9801 | 2024-05-30 | Inv. 2306-07 |  | 48900 | 2262 | 30978 | 17922
PRC 3352412PH9801 | 2024-07-08 | Inv. 2303-08 |  | 48900 | 1798 | 32776 | 16124 | FY24
PO 33525129801 | 2024-07-29 | Roll to FY25 |  | 48900 |  | 32776 | 16124
PRC 3352512PI9801 | 2024-10-03 | Inv. 2306-09 |  | 48900 | 2088 | 34864 | 14036
PRC 3352512PJ9801 | 2024-12-16 | Inv. 2306-10 |  | 48900 | 4292 | 39156 | 9744
|  |  |  | 48900 |  | 39156 | 9744
|  |  |  | 48900 |  | 39156 | 9744
|  |  |  | 48900 |  | 39156 | 9744
|  | Totals: | 48900 |  | 39156 |  | 9744
|  | Design Development Documents | 9800 |  | 9800 |  | 0
|  | Construction Documents | 13400 |  | 13400 |  | 0
|  | Bidding Assistance | 2500 |  | 2500 |  | 0
|  | Construction Adminstration | 23200 |  | 13456 |  | 9744
|  | Total: | 48900 |  | 39156 |  | 9744

## #9306.00 Septagon Construction
DOC CCF Metal Roof Replacement Design
Project # 9306.00
Program code 930600 |  |  | Major Program 4E01
Septagon Construction |  |  | Vendor:00003208920
Acct. Codes-0017-335-MM23-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523171802 | 2023-06-20 | PO Procore | 10900 | 10900 |  |  | 10900
PRC 3352317PA1802 | 2023-06-30 | Inv. 423109 |  | 10900 | 5900 | 5900 | 5000
PO 33523171802 | 2023-08-02 | Close PO per PM | -5000 | 5900 |  | 5900 | 0
|  |  |  | 5900 |  | 5900 | 0
|  | Totals: | 5900 |  | 5900 |  | 0 | FINAL

## RECAP #9307.00
DHS IMHI Generator System Control Replacement
Project # 9307.00
| Program code 930700 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 300925.82
C | Samuels Group #123PC |  | 11215.02 | 11215.02 | 0
| PM TIME |  | 20000 | 14581.99 | 5418.01
| Misc. |  | 0 | 0 | 0
| West Plains Engineering |  | 17780 | 16010 | 1770
| Cummins |  | 174586.87 | 164271.44 | 10315.43
C | Samuels Group #143CA |  | 25351.88 | 25351.88 | 0
| Total Project Cost | 300925.82 | 248933.77 | 231430.33 | 17503.44 | 51992.05

## #9307.00 Samuels Group #123PC
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  | Major Program 4B02
Samuels Group #123PC |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP/B#: Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523259800 | 2022-09-22 | PO Procore | 15168.1 | 15168.1 |  |  | 15168.1
PRC 3352325PA9800 | 2023-01-20 | Inv. 7440.01930700 |  | 15168.1 | 4197.31 | 4197.31 | 10970.79
PRC 3352325PB9800 | 2023-05-08 | Inv. 7440.029307 |  | 15168.1 | 2446.33 | 6643.64 | 8524.46
PRC 3352325PC9800 | 2023-06-12 | Inv. 7440.03930700 |  | 15168.1 | 3377.22 | 10020.86 | 5147.24
PRC 3352325PD9800 | 2023-07-11 | Inv. 7440.04930700 |  | 15168.1 | 1194.16 | 11215.02 | 3953.08 | FY23
PO 33524259800 | 2023-07-26 | Roll to FY24 | 0 | 15168.1 |  | 11215.02 | 3953.08
PO 33524259800 | 2023-08-02 | Closing Per Vendor & PM | -3953.08 | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  |  |  | 11215.02 |  | 11215.02 | 0
|  | Totals: | 11215.02 |  | 11215.02 |  | 0
|  | CM Services | 10911.02 |  | 10911.02 |  | 0
|  | Reimbursables | 304 |  | 304 |  | 0
|  | Total: | 11215.02 |  | 11215.02 |  | 0

## #9307.00 PM TIME
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E236
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 19074.18 | 19074.18 |  |  | 19074.18
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 19074.18 | 165 | 165 | 18909.18
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 19074.18 | 110 | 275 | 18799.18
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 19074.18 | 660 | 935 | 18139.18
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 109.52 | 19183.7 | 109.52 | 1044.52 | 18139.18
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 77.36 | 19261.06 | 77.36 | 1121.88 | 18139.18
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 529.41 | 19790.47 | 529.41 | 1651.29 | 18139.18
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 19790.47 | 180.2 | 1831.49 | 17958.98
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 19790.47 | 114.07 | 1945.56 | 17844.91
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 19790.47 | 1000.05 | 2945.61 | 16844.86
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 43.83 | 19834.3 | 43.83 | 2989.44 | 16844.86
CDE 33523075203 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 12.11 | 19846.41 | 12.11 | 3001.55 | 16844.86
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 126.63 | 19973.04 | 126.63 | 3128.18 | 16844.86
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 26.96 | 20000 | 26.96 | 3155.14 | 16844.86
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 20000 | 159.76 | 3314.9 | 16685.1
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 20000 | 968.85 | 4283.75 | 15716.25
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 20000 | 274.51 | 4558.26 | 15441.74
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 20000 | 1207.43 | 5765.69 | 14234.31
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 20000 | 35.55 | 5801.24 | 14198.76
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 20000 | 206.9 | 6008.14 | 13991.86
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 20000 | 151.5 | 6159.64 | 13840.36
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 20000 | 1060.4 | 7220.04 | 12779.96
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 20000 | 157.09 | 7377.13 | 12622.87
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 20000 | 1339 | 8716.13 | 11283.87
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 20000 | 36.18 | 8752.31 | 11247.69
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 20000 | 230.8 | 8983.11 | 11016.89
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 20000 | 15.59 | 8998.7 | 11001.3
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 20000 | 88 | 9086.7 | 10913.3
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 20000 | 15.17 | 9101.87 | 10898.13
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 20000 | 105 | 9206.87 | 10793.13
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 20000 | 33.12 | 9239.99 | 10760.01
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 20000 | 265 | 9504.99 | 10495.01
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 20000 | 18.39 | 9523.38 | 10476.62
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 20000 | 138.1 | 9661.48 | 10338.52
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 20000 | 34.07 | 9695.55 | 10304.45
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 20000 | 246.6 | 9942.15 | 10057.85
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 20000 | 57.64 | 9999.79 | 10000.21
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 20000 | 511 | 10510.79 | 9489.21
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 20000 | 16.6 | 10527.39 | 9472.61
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 20000 | 83 | 10610.39 | 9389.61
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 20000 | 63.98 | 10674.37 | 9325.63
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 20000 | 483 | 11157.37 | 8842.63
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 20000 | 35.14 | 11192.51 | 8807.49
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 20000 | 314.8 | 11507.31 | 8492.69
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 20000 | 76.2 | 11583.51 | 8416.49
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 20000 | 628.8 | 12212.31 | 7787.69
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 20000 | 43.29 | 12255.6 | 7744.4
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 20000 | 394.2 | 12649.8 | 7350.2
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 20000 | 30.84 | 12680.64 | 7319.36
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 20000 | 339.4 | 13020.04 | 6979.96
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 20000 | 87.32 | 13107.36 | 6892.64
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 20000 | 445.6 | 13552.96 | 6447.04
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 62.55 | 13615.51 | 6384.49
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 555.2 | 14170.71 | 5829.29
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 28.94 | 14199.65 | 5800.35
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 193.6 | 14393.25 | 5606.75
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 16.74 | 14409.99 | 5590.01
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 172 | 14581.99 | 5418.01
[5 empty] | 20000 |  | 14581.99 | 5418.01
[5 empty] | 20000 |  | 14581.99 | 5418.01
[5 empty] | 20000 |  | 14581.99 | 5418.01
|  |  | Totals: | 20000 |  | 14581.99 |  | 5418.01
Note on E9: Huggins, Joni [DAS]: PM Time budgets $Joni Carper, Douglas 9:27 AM (17 minutes ago) to me Please set up the PM Time budgets for these projects: 9307.00 MM23 $9,000.00. 9309.00 MM23 $7,000.00. 9311.00 DA23 $3,000.00. 9312.00 DA23 $1,500.00. 9315.00 DA23 $15,000.00. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov Elliott, Jennie 8:30 AM (5 hours ago) to me Can you please increase the PM Time budget in 9307.00 DHS IMHI Generator Control System Replacement - MM23 to a total contracted amount of $20,000. Jennie Elliott

## #9307.00 Misc
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9307.00 West Plains Engineerin
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  | Major Program 4B02
West Plains Engineering Inc. |  |  | Vendor: 00003073483
Acct. Codes-0017-335-MM23-9260 |  |  | RFP930700-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523052806 | 2023-02-21 | PO Procore | 17780 | 17780 |  |  | 17780
PRC 3352305PA2806 | 2023-04-03 | Inv. BI23023-001001 |  | 17780 | 2170 | 2170 | 15610
PRC 3352305PB2806 | 2023-05-22 | Inv. BI23023-001002 |  | 17780 | 6510 | 8680 | 9100
PRC 3352305PC2806 | 2023-06-28 | Inv. BI23023-001003 |  | 17780 | 2020 | 10700 | 7080 | FY23
PO 33524052806 | 2023-07-26 | Roll to FY24 | 0 | 17780 |  | 10700 | 7080
PRC 3352405PD2806 | 2023-11-06 | Inv. BI23023-001004 |  | 17780 | 1416 | 12116 | 5664
PRC 3352405PE2806 | 2023-12-08 | Inv. BI23023-001005 |  | 17780 | 2124 | 14240 | 3540
PRC 3352405PF2806 | 2024-07-11 | Inv. BI23023-001006 |  | 17780 | 1770 | 16010 | 1770 | FY24
PO 33525052806 | 2024-07-24 | Roll to FY25 |  | 17780 |  | 16010 | 1770
|  |  |  | 17780 |  | 16010 | 1770
|  |  |  | 17780 |  | 16010 | 1770
|  |  |  | 17780 |  | 16010 | 1770
|  |  |  | 17780 |  | 16010 | 1770
|  | Totals: | 17780 |  | 16010 |  | 1770
|  | Construction Documents | 8680 |  | 8680 |  | 0
|  | Bidding | 2020 |  | 2020 |  | 0
|  | Construction Adminstration | 7080 |  | 5310 |  | 1770
|  | Total: | 17780 |  | 16010 |  | 1770

## #9307.00 Cummins
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  | Major Program 4B02
Cummins |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ930700-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523181805 | 2023-06-30 | PO Procore | 166955 | 166955 |  |  | 166955 |  | FY23
PO 33524181805 | 2023-07-26 | Roll to FY24 | 0 | 166955 |  | 0 | 166955
PRC 3352418PA1805 | 2024-06-01 | Inv. E3-55462 |  | 166955 | 16555.35 | 16555.35 | 150399.65 | 871.34
PO 33524181805 | 2024-06-18 | CO #1 | 7631.87 | 174586.87 |  | 16555.35 | 158031.52
PRC 3352418PB1805 | 2024-07-12 | Inv. E3-47852 |  | 174586.87 | 12980.05 | 29535.4 | 145051.47 | 1554.5 | FY24
PO 33525181805 | 2024-07-24 | Roll to FY25 |  | 174586.87 |  | 29535.4 | 145051.47
PRC 3352518PC1805 | 2024-11-20 | Inv. E3-62399 |  | 174586.87 | 134736.04 | 164271.44 | 10315.43 | 8645.88
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  |  |  | 174586.87 |  | 164271.44 | 10315.43
|  | Totals: | 174586.87 |  | 164271.44 |  | 10315.43

## #9307.00 Samuels Group #143CA
DHS IMHI Generator System Control Replacement
Project # 9307.00
Program code 930700 |  |  | Major Program 4B02
Samuels Group #143CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523187908 | 2023-06-30 | PO Procore | 25637.37 | 25637.37 |  |  | 25637.37 | FY23
PO 33524187908 | 2023-07-26 | Roll to FY24 | 0 | 25637.37 |  | 0 | 25637.37
PRC 3352418PA7908 | 2023-09-18 | Inv. 7518.50930200 CA |  | 25637.37 | 2293.76 | 2293.76 | 23343.61
PRC 3352418PB7908 | 2023-10-11 | Inv. 7518.51930200 CA |  | 25637.37 | 2867.2 | 5160.96 | 20476.41
PRC 3352418PC7908 | 2023-12-20 | Inv. 7518.5293 |  | 25637.37 | 6059.15 | 11220.11 | 14417.26
PRC 3352418PD7908 | 2024-02-12 | Inv. 7518.5294 |  | 25637.37 | 3197.37 | 14417.48 | 11219.89
PRC 3352418PE7908 | 2024-04-15 | Inv. 7518.5394 |  | 25637.37 | 2591.19 | 17008.67 | 8628.7
PRC 3352418PF7908 | 2024-05-13 | Inv. 7518.5494 |  | 25637.37 | 2537.04 | 19545.71 | 6091.66
PRC 3352418PG7908 | 2024-06-01 | Inv. 7518.5495 |  | 25637.37 | 378.86 | 19924.57 | 5712.8
PRC 3352418PH7908 | 2024-07-11 | Inv. 7518.5575 |  | 25637.37 | 1560.79 | 21485.36 | 4152.01 | FY24
PO 33525187908 | 2024-07-24 | Roll to FY25 |  | 25637.37 |  | 21485.36 | 4152.01
PRC 3352518PI7908 | 2024-08-09 | Inv. 7518.5675 |  | 25637.37 | 1443.44 | 22928.8 | 2708.57
PRC 3352518PJ7908 | 2024-09-12 | Inv. 7518.5775 |  | 25637.37 | 1888.6 | 24817.4 | 819.97
PRC 3352518PK7908 | 2024-10-02 | Inv. 7518.5875 FINAL | -285.49 | 25351.88 | 534.48 | 25351.88 | 0
|  | Totals: | 25351.88 |  | 25351.88 |  | 0 | FINAL
|  | CM Services | 16539.13 |  | 16539.13 |  | 0
|  | Reimbursables | 465 |  | 465 |  | 0
|  | Fee | 8347.75 |  | 8347.75 |  | 0
|  | Total: | 25351.88 |  | 25351.88 |  | 0

## RECAP #9308.00
DOC NCCF Generator System Control Replacement
Project # 9308.00
| Program code 930800 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 200115.49
C | Story Construction |  | 13843.5 | 13843.5 | 0
C | PM TIME |  | 13560.22 | 13560.22 | 0
C | Misc. |  | 0 | 0 | 0
C | Innovative Engineers, Inc |  | 16920 | 16920 | 0
C | Cummins Inc. |  | 131448 | 131448 | 0
C | Story Construction2 |  | 24343.77 | 24343.77 | 0
| Total Project Cost | 200115.49 | 200115.49 | 200115.49 | 0 | 0
Closed 12/31/24

## #9308.00 Story Construction
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  | Major Program 4E01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523299903 | 2022-10-25 | PO Procore | 15455.54 | 15455.54 |  |  | 15455.54
PRC 3352329PA9903 | 2022-12-26 | Inv. 33524 |  | 15455.54 | 1734 | 1734 | 13721.54
PRC 3352329PB9903 | 2023-01-19 | Inv. 33591 |  | 15455.54 | 504 | 2238 | 13217.54
PRC 3352329PC9903 | 2023-02-16 | Inv. 33638 |  | 15455.54 | 2148 | 4386 | 11069.54
PRC 3352329PD9903 | 2023-03-15 | Inv. 33692 |  | 15455.54 | 3723 | 8109 | 7346.54
PRC 3352329PE9903 | 2023-04-17 | Inv. 33736 |  | 15455.54 | 819 | 8928 | 6527.54
PRC 3352329PF9903 | 2023-05-19 | Inv. 33793 |  | 15455.54 | 2301 | 11229 | 4226.54
PRC 3352329PG9903 | 2023-06-20 | Inv. 33840 |  | 15455.54 | 1543.5 | 12772.5 | 2683.04
PRC 3352329PH9903 | 2023-07-14 | Inv. 33899- FINAL | -1612.04 | 13843.5 | 1071 | 13843.5 | 0
|  |  |  | 13843.5 |  | 13843.5 | 0
|  |  |  | 13843.5 |  | 13843.5 | 0
|  |  |  | 13843.5 |  | 13843.5 | 0
|  |  |  | 13843.5 |  | 13843.5 | 0
|  | Totals: | 13843.5 |  | 13843.5 |  | 0 | FINAL
|  | CM Services | 13843.5 |  | 13843.5 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 13843.5 |  | 13843.5 |  | 0

## #9308.00 PM TIME
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E237
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12388.12 | 12388.12 |  |  | 12388.12
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 12388.12 | 275 | 275 | 12113.12
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 12388.12 | 165 | 440 | 11948.12
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 12388.12 | 412.5 | 852.5 | 11535.62
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 12388.12 | 302.5 | 1155 | 11233.12
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 233.84 | 12621.96 | 233.84 | 1388.84 | 11233.12
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 88.8 | 12710.76 | 88.8 | 1477.64 | 11233.12
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 301.2 | 13011.96 | 301.2 | 1778.84 | 11233.12
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 231.9 | 13243.86 | 231.9 | 2010.74 | 11233.12
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 13243.86 | 493.15 | 2503.89 | 10739.97
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 13243.86 | 77.6 | 2581.49 | 10662.37
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 13243.86 | 680.28 | 3261.77 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 72.03 | 13315.89 | 72.03 | 3333.8 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 67.55 | 13383.44 | 67.55 | 3401.35 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 46.11 | 13429.55 | 46.11 | 3447.46 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 56.89 | 13486.44 | 56.89 | 3504.35 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 73.78 | 13560.22 | 73.78 | 3578.13 | 9982.09
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 13560.22 | 168.36 | 3746.49 | 9813.73
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 13560.22 | 1020.96 | 4767.45 | 8792.77
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 13560.22 | 175.22 | 4942.67 | 8617.55
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 13560.22 | 770.74 | 5713.41 | 7846.81
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 13560.22 | 164.85 | 5878.26 | 7681.96
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 13560.22 | 967.9 | 6846.16 | 6714.06
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 13560.22 | 73.42 | 6919.58 | 6640.64
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 13560.22 | 515.9 | 7435.48 | 6124.74
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 13560.22 | 82.78 | 7518.26 | 6041.96
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 13560.22 | 711.4 | 8229.66 | 5330.56
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 13560.22 | 54.82 | 8284.48 | 5275.74
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 13560.22 | 349.2 | 8633.68 | 4926.54
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 13560.22 | 47.19 | 8680.87 | 4879.35
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 13560.22 | 261.8 | 8942.67 | 4617.55
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 13560.22 | 13.22 | 8955.89 | 4604.33
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 13560.22 | 90.8 | 9046.69 | 4513.53
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 13560.22 | 84.48 | 9131.17 | 4429.05
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 13560.22 | 676.4 | 9807.57 | 3752.65
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 13560.22 | 6.27 | 9813.84 | 3746.38
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 13560.22 | 46.4 | 9860.24 | 3699.98
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 13560.22 | 6.95 | 9867.19 | 3693.03
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 13560.22 | 50.4 | 9917.59 | 3642.63
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 13560.22 | 10 | 9927.59 | 3632.63
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 13560.22 | 89 | 10016.59 | 3543.63
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 13560.22 | 43.1 | 10059.69 | 3500.53
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 13560.22 | 218.4 | 10278.09 | 3282.13
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 13560.22 | 22.54 | 10300.63 | 3259.59
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 13560.22 | 170.3 | 10470.93 | 3089.29
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 13560.22 | 32.35 | 10503.28 | 3056.94
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 13560.22 | 289.1 | 10792.38 | 2767.84
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 13560.22 | 79 | 10871.38 | 2688.84
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 13560.22 | 651.2 | 11522.58 | 2037.64
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 13560.22 | 53.03 | 11575.61 | 1984.61
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 13560.22 | 486.5 | 12062.11 | 1498.11
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 13560.22 | 83.78 | 12145.89 | 1414.33
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 13560.22 | 912.4 | 13058.29 | 501.93
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 13560.22 | 82.53 | 13140.82 | 419.4
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 13560.22 | 419.4 | 13560.22 | 0
|  |  | Totals: | 13560.22 |  | 13560.22 |  | 0
Note on E9: Huggins, Joni [DAS]: James Trower - PM Time $Joni Trower, James 1:08 PM (50 minutes ago) to me Finance - See below items: 9203.00 - DOC NCCF Treatment Center EIFS Replacement: Increase PM Time by $5,000 (MM21) 9231.00 - DAS CC Jessie Parker Water: Increase PM Time by $4,000 (MM22) 9250.00 - DOC MPCF Building 18 Roof Replacement: Increase PM Time by $5,000 (MM22) 9297.00 - DOC MPCF Gym Floor Repair: Set up $6,000 in PM Time (MM21) 9300.00 - DOC MPFC Storage Bunker Repair: Set up $6,000 in PM Time (MM21) 9301.00 - DPS DSM Fleet & Supply 2nd Floor Structural: Set up $4,000 in PM Time (MM21) 9305.00 - DAS CC Capitol South Stair Repair:Set up $6,000 in PM Time (MM23) 9308.00 - DOC NCCF Generator System Control Replacement: Set up $6,000 in PM Time (MM23) Thanks, James Trower, Licensed Architect/LEED AP Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-380-8049 james.trower@iowa.gov https://das.iowa.gov e: PM Time adjustments Inbox Trower, James 10:33 AM (17 minutes ago) to me Finance - Please increase the PM Time by $5,000 fpr MM23 funding for project 9308.00. Thanks, James On Fri, Jun 16, 2023 at 10:13 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good Morning James MM23 9308.00 is short 263.38 for posting 515.90 pm time Please let me know how you would like this adjusted. Thank you ~Joni Trower, James 9:40 AM (0 minutes ago) to me Project 9308.00 in MM23 is over budget for PM Time: Increase PM Time by $5,000.

## #9308.00 Misc
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9308.00 Innovative Engineers
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  | Major Program 4E01
Innovative Engineers |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM23-9260 |  |  | 930800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523046900 | 2023-02-15 | PO Procore | 16920 | 16920 |  |  | 16920
PRC 3352304PA6900 | 2023-06-05 | Inv. 9308.00-01 |  | 16920 | 11045 | 11045 | 5875 | FY23
PO 33524046900 | 2023-08-11 | Roll to FY24 | 0 | 16920 |  | 11045 | 5875
PRC 3352404PB6900 | 2024-06-24 | Inv. 9308.00-02 |  | 16920 | 2945.5 | 13990.5 | 2929.5 | FY24
PO 33525046900 | 2024-07-24 | Roll to FY25 |  | 16920 |  | 13990.5 | 2929.5
PRC 3352504PC6900 | 2024-10-10 | Inv. 9308.00-03 |  | 16920 | 2929.5 | 16920 | 0
|  |  |  | 16920 |  | 16920 | 0
|  | Totals: | 16920 |  | 16920 |  | 0 | FINAL
|  | Construction Documents | 11045 |  | 11045 |  | 0
|  | Bidding Assistance | 1690 |  | 1690 |  | 0
|  | Construction Phase | 4185 |  | 4185 |  | 0
|  | Total: | 16920 |  | 16920 |  | 0

## #9308.00 Cummins Inc.
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  | Major Program 4E01
Cummins Inc. |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM23-9255 |  |  | MA23133
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523172803 | 2023-06-21 | PO Procore | 131448 | 131448 |  |  | 131448 |  | FY23
PO 33524172803 | 2023-08-04 | Roll to FY24 | 0 | 131448 |  | 0 | 131448
PO 33524172803 | 2024-06-13 | CO #1 (No Cost CO) | 0 | 131448 |  | 0 | 131448
PRC 3352417PA2803 | 2024-08-09 | Inv. E3-58675-1 and E3-58675-2 |  | 131448 | 114114.32 | 114114.32 | 17333.68 | 6006.02 | FY24
PO 33525172803 | 2024-08-13 | Roll to FY25 |  | 131448 |  | 114114.32 | 17333.68
PRC 3352517PB2803 | 2024-10-14 | Inv. E3-58676 |  | 131448 | 10761.28 | 124875.6 | 6572.4 | 6572.4
PRC 3352517PC2803 | 2024-10-22 | Inv. 9308.00-01 - Retainage |  | 131448 | 6572.4 | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  |  |  | 131448 |  | 131448 | 0
|  | Totals: | 131448 |  | 131448 |  | 0 | FINAL

## #9308.00 Story Construction 2
DOC NCCF Generator System Control Replacement
Project # 9308.00
Program code 930800 |  |  | Major Program 4E01
Story Construction 2 |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523187906 | 2023-06-30 | PO Procore | 28673.54 | 28673.54 |  |  | 28673.54 | FY23
PO 33524187906 | 2023-08-04 | Roll to FY24 | 0 | 28673.54 |  | 0 | 28673.54
PRC 3352418PA7906 | 2023-08-22 | Inv. 33956 |  | 28673.54 | 2271.5 | 2271.5 | 26402.04
PRC 3352418PB7906 | 2023-09-15 | Inv. 34010 |  | 28673.54 | 900.65 | 3172.15 | 25501.39
PRC 3352418PC7906 | 2023-11-16 | Inv. 34123 |  | 28673.54 | 3738.06 | 6910.21 | 21763.33
PRC 3352418PD7906 | 2024-02-15 | Inv. 34251 |  | 28673.54 | 4233.46 | 11143.67 | 17529.87
PRC 3352418PE7906 | 2024-05-16 | Inv. 34359 |  | 28673.54 | 2328.29 | 13471.96 | 15201.58
PRC 3352418PF7906 | 2024-06-18 | Inv. 34395 |  | 28673.54 | 1479 | 14950.96 | 13722.58
PRC 3352418PG7906 | 2024-07-18 | Inv. 34440 |  | 28673.54 | 3157.1 | 18108.06 | 10565.48 | FY24
PO 33525187906 | 2024-07-24 | Roll to FY25 |  | 28673.54 |  | 18108.06 | 10565.48
PRC 3352518PH7906 | 2024-08-19 | Inv. 34486 |  | 28673.54 | 2711.13 | 20819.19 | 7854.35
PRC 3352518PI7906 | 2024-10-16 | Inv. 34563 - Final | -4329.77 | 24343.77 | 3524.58 | 24343.77 | 0
|  |  |  | 24343.77 |  | 24343.77 | 0
|  | Totals: | 24343.77 |  | 24343.77 |  | 0 | FINAL
|  | CM Services | 24343.77 |  | 24343.77 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 24343.77 |  | 24343.77 |  | 0

## RECAP #9309.00
DOC ASP Gym Roof Replacement
Project # 9309.00
| Program code 930900 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 284190.05
C | Story Construction |  | 17376.31 | 17376.31 | 0
C | PM TIME |  | 11883.49 | 11883.49 | 0
C | Misc. |  | 1196.96 | 1196.96 | 0
C | Genesis Architectural Design |  | 15000 | 15000 | 0
C | Story Construction (2) |  | 26972.29 | 26972.29 | 0
C | For Sure Roofing |  | 211761 | 211761 | 0
| Total Project Cost | 284190.05 | 284190.05 | 284190.05 | 0 | 0
Closed 02/12/2024

## #9309.00 Story Construction
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  | Major Program 4E01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523336900 | 2022-12-02 | PO Procore | 18584.7 | 18584.7 |  |  | 18584.7
PRC 3352333PA6900 | 2023-01-24 | Inv. 33593 |  | 18584.7 | 1267.59 | 1267.59 | 17317.11
PRC 3352333PB6900 | 2023-02-17 | Inv. 33640 |  | 18584.7 | 3739.23 | 5006.82 | 13577.88
PRC 3352333PC6900 | 2023-03-20 | Inv. 33694 |  | 18584.7 | 2401.74 | 7408.56 | 11176.14
PRC 3352333PD6900 | 2023-04-18 | Inv. 33738 |  | 18584.7 | 2109.49 | 9518.05 | 9066.65
PRC 3352333PE6900 | 2023-05-22 | Inv. 33795 |  | 18584.7 | 4729.37 | 14247.42 | 4337.28
PRC 3352333PF6900 | 2023-06-21 | Inv. 33842 |  | 18584.7 | 3128.89 | 17376.31 | 1208.39
PO 33523336900 | 2023-07-26 | Close PO per PM | -1208.39 | 17376.31 |  | 17376.31 | 0
|  |  |  | 17376.31 |  | 17376.31 | 0
|  |  |  | 17376.31 |  | 17376.31 | 0
|  |  |  | 17376.31 |  | 17376.31 | 0
|  |  |  | 17376.31 |  | 17376.31 | 0
|  |  |  | 17376.31 |  | 17376.31 | 0
|  | Totals: | 17376.31 |  | 17376.31 |  | 0 | Final
|  | CM Services | 17244.31 |  | 17244.31 |  | 0
|  | Reimbursables | 132 |  | 132 |  | 0
|  | Total: | 17376.31 |  | 17376.31 |  | 0

## #9309.00 PM TIME
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E238
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11424.42 | 11424.42 |  |  | 11424.42
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 11424.42 | 220 | 220 | 11204.42
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 11424.42 | 220 | 440 | 10984.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 146.03 | 11570.45 | 146.03 | 586.03 | 10984.42
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 176.47 | 11746.92 | 176.47 | 762.5 | 10984.42
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 11746.92 | 630.72 | 1393.22 | 10353.7
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 11746.92 | 199.63 | 1592.85 | 10154.07
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 11746.92 | 1750.08 | 3342.93 | 8403.99
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 42.21 | 11789.13 | 42.21 | 3385.14 | 8403.99
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 94.36 | 11883.49 | 94.36 | 3479.5 | 8403.99
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 11883.49 | 220.64 | 3700.14 | 8183.35
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 11883.49 | 1337.94 | 5038.08 | 6845.41
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 11883.49 | 166.67 | 5204.75 | 6678.74
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 11883.49 | 733.08 | 5937.83 | 5945.66
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 11883.49 | 140.52 | 6078.35 | 5805.14
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 11883.49 | 826.5 | 6904.85 | 4978.64
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 11883.49 | 236.98 | 7141.83 | 4741.66
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 11883.49 | 1658.8 | 8800.63 | 3082.86
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 11883.49 | 9.52 | 8810.15 | 3073.34
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 11883.49 | -41.3 | 8768.85 | 3114.64
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 11883.49 | 66.51 | 8835.36 | 3048.13
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 11883.49 | 424.5 | 9259.86 | 2623.63
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 11883.49 | 15.59 | 9275.45 | 2608.04
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 11883.49 | 88 | 9363.45 | 2520.04
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 11883.49 | 30.33 | 9393.78 | 2489.71
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 11883.49 | 211.1 | 9604.88 | 2278.61
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 11883.49 | 103.95 | 9708.83 | 2174.66
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 11883.49 | 834.3 | 10543.13 | 1340.36
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 11883.49 | 36.76 | 10579.89 | 1303.6
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 11883.49 | 276.2 | 10856.09 | 1027.4
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 11883.49 | 123.2 | 10979.29 | 904.2
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 11883.49 | 904.2 | 11883.49 | 0
[5 empty] | 11883.49 |  | 11883.49 | 0
[5 empty] | 11883.49 |  | 11883.49 | 0
[5 empty] | 11883.49 |  | 11883.49 | 0
[5 empty] | 11883.49 |  | 11883.49 | 0
[5 empty] | 11883.49 |  | 11883.49 | 0
|  |  | Totals: | 11883.49 |  | 11883.49 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time budgets $Joni Carper, Douglas 9:27 AM (18 minutes ago) to me Please set up the PM Time budgets for these projects: 9307.00 MM23 $9,000.00. 9309.00 MM23 $7,000.00. 9311.00 DA23 $3,000.00. 9312.00 DA23 $1,500.00. 9315.00 DA23 $15,000.00. Let me know if you have any questions. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9309.00 DOC ASP Gym Roof Replacement Inbox Elliott, Jennie 2:46 PM (1 minute ago) to me Please increase the PM Time Budget in 9309.00 - DOC ASP Gym Roof Replacement to a total of $25,000 in the Contracted line. Thank you,

## #9309.00 Misc
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523082802 | 2023-03-23 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2485604-FINAL | 1035 | 1035
PRC 33523156903 | 2023-06-01 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 420811-0 | 129.47 | 1164.47
PRC 33524300906 | 2023-10-27 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. 421212-0 | 32.49 | 1196.96
1196.96
1196.96
1196.96
1196.96
1196.96
1196.96
1196.96
1196.96
1196.96
|  |  |  | Totals: |  | 1196.96

## #9309.00 Genesis Architectural
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  | Major Program 4E01
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | 930900-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523040800 | 2023-02-09 | PO Procore | 15000 | 15000 |  |  | 15000
PRC 3352304PA0800 | 2023-02-20 | Inv. 2303-01 |  | 15000 | 1104 | 1104 | 13896
PRC 3352304PB0800 | 2023-03-09 | Inv. 2303-02 |  | 15000 | 1840 | 2944 | 12056
PRC 3352304PC0800 | 2023-04-18 | Inv. 2303-03 |  | 15000 | 3680 | 6624 | 8376
PRC 3352304PD0800 | 2023-06-06 | Inv. 2303-04 |  | 15000 | 2736 | 9360 | 5640 | FY23
PO 33524040800 | 2023-07-28 | Rolled to FY24 | 0 | 15000 |  | 9360 | 5640
PRC 3352404PE0800 | 2023-08-21 | Inv. 2303-05 |  | 15000 | 564 | 9924 | 5076
PRC 3352404PF0800 | 2023-12-20 | Inv. 2303-06 |  | 15000 | 4512 | 14436 | 564
PRC 3352404PG0800 | 2024-02-01 | Inv. 2303-07 Final |  | 15000 | 564 | 15000 | 0
|  |  |  | 15000 |  | 15000 | 0
|  |  |  | 15000 |  | 15000 | 0
|  |  |  | 15000 |  | 15000 | 0
|  |  |  | 15000 |  | 15000 | 0
|  | Totals: | 15000 |  | 15000 |  | 0
|  | Construction Documents | 7360 |  | 7360 |  | 0
|  | Bid Phase | 2000 |  | 2000 |  | 0
|  | Construction Phase | 5640 |  | 5640 |  | 0
|  | Total: | 15000 |  | 15000 |  | 0

## #9309.00 Story Construction (2)
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  | Major Program 4E01
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523157805 | 2023-06-06 | PO Procore | 27238.77 | 27238.77 |  |  | 27238.77
PRC 3352315PA7805 | 2023-07-17 | Inv. 33900 |  | 27238.77 | 946.71 | 946.71 | 26292.06 | FY23
PO 33524157805 | 2023-07-26 | Rolled to FY24 | 0 | 27238.77 |  | 946.71 | 26292.06
PRC 3352415PB7805 | 2023-08-21 | Inv. 33957 |  | 27238.77 | 1546.11 | 2492.82 | 24745.95
PRC 3352415PC7805 | 2023-09-18 | Inv. 34011 |  | 27238.77 | 1253.31 | 3746.13 | 23492.64
PRC 3352415PD7805 | 2023-10-17 | Inv. 34070 |  | 27238.77 | 6112.21 | 9858.34 | 17380.43
PRC 3352415PE7805 | 2023-11-21 | Inv. 34124 |  | 27238.77 | 14180.15 | 24038.49 | 3200.28
PRC 3352415PF7805 | 2024-01-19 | Inv. 34209 |  | 27238.77 | 2933.8 | 26972.29 | 266.48
PO 33524157805 | 2024-02-12 | Closing per PM | -266.48 | 26972.29 |  | 26972.29 | 0
|  |  |  | 26972.29 |  | 26972.29 | 0
|  |  |  | 26972.29 |  | 26972.29 | 0
|  |  |  | 26972.29 |  | 26972.29 | 0
|  |  |  | 26972.29 |  | 26972.29 | 0
|  | Totals: | 26972.29 |  | 26972.29 |  | 0
|  | CM Services | 26312.29 |  | 26312.29 |  | 0
|  | Reimbursables | 660 |  | 660 |  | 0
|  | Total: | 26972.29 |  | 26972.29 |  | 0

## #9309.00 For Sure Roofing
DOC ASP Gym Roof Replacement
Project # 9309.00
Program code 930900 |  |  | Major Program 4E01
For Sure Roofing |  |  | Vendor: 00003081739
Acct. Codes-0017-335-MM23-9255 |  |  | 930900-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523157806 | 2023-06-06 | PO Procore | 211761 | 211761 |  |  | 211761 |  | FY23
PO 33524157806 | 2023-07-28 | Rolled to FY24 | 0 | 211761 |  | 0 | 211761
PRC 3352415PA7806 | 2023-10-11 | Inv. 9309.00-01 |  | 211761 | 125289.69 | 125289.69 | 86471.31 | 6594.19
PRC 3352415PB7806 | 2023-12-20 | Inv. 9309.00-02 |  | 211761 | 73872.11 | 199161.8 | 12599.2 | 10482.2
PRC 3352415PC7806 | 2024-01-03 | Inv. 9309.00-03-Closeout |  | 211761 | 2011.15 | 201172.95 | 10588.05 | 10588.05
PRC 3352415PD7806 | 2024-01-09 | Inv. 9309.00-04 - Retainage |  | 211761 | 10588.05 | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  |  |  | 211761 |  | 211761 | 0
|  | Totals: | 211761 |  | 211761 |  | 0
`

## RECAP #9310.00
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
| Program code 931000 |  |  | Major Program 4B03
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 502324.07
C | DCI Group |  | 12936.54 | 12936.54 | 0
C | PM TIME |  | 30222.96 | 30222.96 | 0
C | Misc. |  | 5239.81 | 5239.81 | 0
C | Farnsworth Group |  | 44583 | 44583 | 0
C | BlackHawk Roofing |  | 287039.75 | 287039.75 | 0
C | DCI Group #22-031 CA |  | 33901.13 | 33901.13 | 0
C | Proctor Mechanical |  | 88400.88 | 88400.88 | 0
| Total Project Cost | 502324.07 | 502324.07 | 502324.07 | 0 | 0
Closed 10/17/2024

## #9310.00 DCI Group
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523262900 | 2022-09-19 | PO Procore | 12975.86 | 12975.86 |  |  | 12975.86
PRC 3352326PA2900 | 2022-11-07 | Inv. 22-031 PC-01 |  | 12975.86 | 2476.13 | 2476.13 | 10499.73
PRC 3352326PB2900 | 2022-11-14 | Inv. 22-031 PC-02 |  | 12975.86 | 2560.49 | 5036.62 | 7939.24
PRC 3352326PC2900 | 2023-01-17 | Inv. 22-031 PC-03 |  | 12975.86 | 4904.56 | 9941.18 | 3034.68
PRC 3352326PD2900 | 2023-03-15 | Inv. 22-031 PC-04 |  | 12975.86 | 1730.3 | 11671.48 | 1304.38
PRC 3352326PE2900 | 2023-05-04 | Inv. 22-031 PC-05 FINAL | -39.32 | 12936.54 | 1265.06 | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  |  |  | 12936.54 |  | 12936.54 | -5.187e-13
|  | Totals: | 12936.54 |  | 12936.54 |  | 0 | FINAL
|  | Pre-Construction Staff | 12473.04 |  | 12473.04 |  | 0
|  | Reimbursables | 463.5 |  | 463.5 |  | 0
|  | Totals: | 12936.54 |  | 12936.54 |  | 0

## #9310.00 PM TIME
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E239
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 26981.55 | 26981.55 |  |  | 26981.55
IET DAS202302115300001 | 2022-09-08 | 9500 | PM Time-August 1-August 31, 2022 |  | 26981.55 | 247.5 | 247.5 | 26734.05
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 26981.55 | 852.5 | 1100 | 25881.55
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 26981.55 | 742.5 | 1842.5 | 25139.05
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 26981.55 | 715 | 2557.5 | 24424.05
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Aug 9997.23 disbursement | 255.23 | 27236.78 | 255.23 | 2812.73 | 24424.05
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 769.42 | 28006.2 | 769.42 | 3582.15 | 24424.05
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 840.61 | 28846.81 | 840.61 | 4422.76 | 24424.05
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 633.91 | 29480.72 | 633.91 | 5056.67 | 24424.05
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 29480.72 | 1110.7 | 6167.37 | 23313.35
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 29480.72 | 143.95 | 6311.32 | 23169.4
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 29480.72 | 1261.93 | 7573.25 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support For: August 1-31, 2022 | 71.17 | 29551.89 | 71.17 | 7644.42 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: September 1-30, 2022 | 259.01 | 29810.9 | 259.01 | 7903.43 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 102.28 | 29913.18 | 102.28 | 8005.71 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 143.61 | 30056.79 | 143.61 | 8149.32 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 166.17 | 30222.96 | 166.17 | 8315.49 | 21907.47
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 30222.96 | 220.62 | 8536.11 | 21686.85
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 30222.96 | 1337.85 | 9873.96 | 20349
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 30222.96 | 202.73 | 10076.69 | 20146.27
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 30222.96 | 891.72 | 10968.41 | 19254.55
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 30222.96 | 236.79 | 11205.2 | 19017.76
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 30222.96 | 1392.6 | 12597.8 | 17625.16
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 30222.96 | 146 | 12743.8 | 17479.16
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 30222.96 | 1020.8 | 13764.6 | 16458.36
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 30222.96 | 105.64 | 13870.24 | 16352.72
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 30222.96 | 877.8 | 14748.04 | 15474.92
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 30222.96 | 92.52 | 14840.56 | 15382.4
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 30222.96 | 589.3 | 15429.86 | 14793.1
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 30222.96 | 236.79 | 15666.65 | 14556.31
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 30222.96 | 1320.4 | 16987.05 | 13235.91
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 30222.96 | 277.31 | 17264.36 | 12958.6
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 30222.96 | 1923 | 19187.36 | 11035.6
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 30222.96 | 199.86 | 19387.22 | 10835.74
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 30222.96 | 1607.4 | 20994.62 | 9228.34
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 30222.96 | 115.72 | 21110.34 | 9112.62
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 30222.96 | 875 | 21985.34 | 8237.62
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 30222.96 | 139.05 | 22124.39 | 8098.57
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 30222.96 | 1018.2 | 23142.59 | 7080.37
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 30222.96 | 63.74 | 23206.33 | 7016.63
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 30222.96 | 559 | 23765.33 | 6457.63
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 30222.96 | 160.98 | 23926.31 | 6296.65
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 30222.96 | 810.8 | 24737.11 | 5485.85
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 30222.96 | 69.4 | 24806.51 | 5416.45
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 30222.96 | 523.4 | 25329.91 | 4893.05
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 30222.96 | 58.01 | 25387.92 | 4835.04
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 30222.96 | 514.8 | 25902.72 | 4320.24
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 30222.96 | 184.93 | 26087.65 | 4135.31
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 30222.96 | 1539.8 | 27627.45 | 2595.51
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 30222.96 | 97.17 | 27724.62 | 2498.34
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 30222.96 | 888.9 | 28613.52 | 1609.44
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 30222.96 | 78.29 | 28691.81 | 1531.15
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 30222.96 | 856.2 | 29548.01 | 674.95
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 30222.96 | 110.85 | 29658.86 | 564.1
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 30222.96 | 564.1 | 30222.96 | 2.7285e-12
[5 empty] | 30222.96 |  | 30222.96 | 2.7285e-12
|  |  | Totals: | 30222.96 |  | 30222.96 |  | 0
Note on E9: Huggins, Joni [DAS]: MM23 - 9310.00 - DVA IVH Sheeler Clinical Roof Replacement - PM Time Budget $Joni Tonyan, Brad 1:22 PM (2 hours ago) to me, Jennifer, Scott, Brad Finance, I have set up project 9310.00 - DVA IVH Sheeler Clinical Roof Replacement in Procore and would like the PM time set up please as $13,000. Please let me know once this is completed. Thank you, Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. Re: PM Time $John Tonyan, Brad 2:13 PM (15 minutes ago) to me, John John, Please increase the exact amount needed to post for each project. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Jan 9, 2024 at 2:12 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Brad I need specific amounts that you need each to be increased by for our audit...unless you are wanting each project increased by the exact amount i need to post? John On Tue, Jan 9, 2024 at 12:35 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: John and Finance, Please increase the PM time as needed from the project's contingency funds to cover for the following. DA21 9172.00 Amt. $654.50 MM22 9272.00 Amt. $748.00 MM23 9255.00 Amt. $513.70 MM23 9310.00 Amt. $981.20 MM23 9324.00 Amt. $1449.80 Thank you, MM23: 9306.00 - Decrease overall budget by $145,000 and give back to general org. fund MM23 9310.00 - Increase PM Time by $5K 9319.00 - Increase PM Time by $5K 9330.00 - Increase PM time as needed to pay January PM time. Once this PM time hits all financials can be closed and remaining roughly $12K can be returned to general org. fund MM23 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative Re: PM Time posted Inbox Tonyan, Brad 10:33 AM (1 minute ago) to me Joni, Please update the following: MM24 9376.00 -1927.65 Brad comment - Please raise PM time $7,000 as we have added scope so overall PM Time budget to $32K MM23 9310.00 -500.35 Brad Comment - Please raise PM time $2,000 to cover the overage and project is almost done. Tonyan, Brad 8:32 AM (12 minutes ago) to me Finance, I created and processed the following final "dummy" invoice for the PM time on project 9310.00. All of the invoices have been paid and if you could please close the PM time / Misc. on this project in MM23 and shift the remaining balance of $6,024.24 to project 9404.00 in MM23. Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9310.00 Misc
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  |  | Major Program 4B03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523026803 | 2023-01-26 | 9500 | CNST | Black Hawk Roof Company V#(00002120676) | Inv. 5551 | 323.19 | 323.19
GAX 33523051800 | 2023-02-20 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2483656-Final | 1385 | 1708.19
PRC 33523102900 | 2023-04-12 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV029075 | 155.69 | 1863.88
PRC 33523178802 | 2023-06-27 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV031124 | 100.81 | 1964.69
GAX 33524313903 | 2023-11-08 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010646-IN-FINAL | 2131.12 | 4095.81
GAX 33525257902 | 2024-09-13 | 9500 | CNST | Black Hawk Roof Company V#(00002120676) | Inv. 6959 | 1144 | 5239.81
5239.81
5239.81
5239.81
5239.81
5239.81
5239.81
|  |  |  | Totals: |  | 5239.81

## #9310.00 Farnsworth Group
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  | Major Program 4B03
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0017-335-MM23-9260 |  |  | RFP931000-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523308901 | 2022-11-02 | PO Procore | 48171.5 | 48171.5 |  |  | 48171.5
PRC 3352330PA8901 | 2023-01-25 | Inv. 9310.00-01 |  | 48171.5 | 12772.5 | 12772.5 | 35399
PRC 3352330PB8901 | 2023-02-28 | Inv. 9310.00-02 |  | 48171.5 | 12833 | 25605.5 | 22566
PRC 3352330PC8901 | 2023-03-15 | Inv. 9310.00-03 |  | 48171.5 | 2656 | 28261.5 | 19910
PRC 3352330PD8901 | 2023-06-22 | Inv. 9310.00-04 |  | 48171.5 | 3441.5 | 31703 | 16468.5
PO 33523308901 | 2023-06-28 | CO #1 | -3588.5 | 44583 |  | 31703 | 12880 | FY23
PO 33524308901 | 2023-07-25 | Rolled to FY24 | 0 | 44583 |  | 31703 | 12880
PRC 3352430PE8901 | 2023-09-20 | Inv. 9310.00-05 |  | 44583 | 6440 | 38143 | 6440
PRC 3352430PF8901 | 2024-06-01 | Inv. 9310.00-06 |  | 44583 | 6440 | 44583 | 0
|  |  |  | 44583 |  | 44583 | 0
|  |  |  | 44583 |  | 44583 | 0
|  |  |  | 44583 |  | 44583 | 0
|  |  |  | 44583 |  | 44583 | 0
|  | Totals: | 44583 |  | 44583 |  | 0 | FINAL
|  | Roof 50% CDs | 9021 |  | 9021 |  | 0
|  | Roof 95% CDs | 11251 |  | 11251 |  | 0
|  | Roof 100% CDs | 1851 |  | 1851 |  | 0
|  | Roof Bidding/Negotiating | 2253.5 |  | 2253.5 |  | 0
|  | Roof Construction Phase | 12880 |  | 12880 |  | 0
|  | AHU 50%CDs | 3751.5 |  | 3751.5 |  | 0
|  | AHU 95%CDs | 1582 |  | 1582 |  | 0
|  | AHU 100%CDs | 805 |  | 805 |  | 0
|  | AHU Bidding/Negotiating | 1188 |  | 1188 |  | 0
|  | AHU Construction Phase | 3588.5 |  |  |  | 3588.5
|  | CO #1 | -3588.5 |  |  |  | -3588.5
|  | Totals: | 44583 |  | 44583 |  | 0

## #9310.00 BlackHawk Roofing
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  | Major Program 4B03
BlackHawk Roofing |  |  | Vendor: 00002120676
Acct. Codes-0017-335-MM23-9255 |  |  | RFP931000-02
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523187905 | 2023-06-30 | PO Procore | 287120 | 287120 |  |  | 287120 |  | FY23
PO 33524187905 | 2023-08-04 | Roll to FY24 | 0 | 287120 |  | 0 | 287120
PRC 3352418PA7905 | 2023-10-11 | Inv. 9310.00-01 |  | 287120 | 248299.6 | 248299.6 | 38820.4 | 13068.4
PRC 3352418PB7905 | 2023-12-07 | Inv. 9310.00-02 |  | 287120 | 17250.1 | 265549.7 | 21570.3 | 13976.3
PO 33524187905 | 2023-12-28 | CO #1 | -80.25 | 287039.75 |  | 265549.7 | 21490.05
PRC 3352418PC7905 | 2024-03-26 | Inv. 9310.00-03 |  | 287039.75 | 4673.76 | 270223.46 | 16816.29 | 14222.29
PRC 3352418PD7905 | 2024-05-09 | Inv. 9310.00-04 |  | 287039.75 | 2464.3 | 272687.76 | 14351.99 | 14351.99
PRC 3352418PE7905 | 2024-06-01 | Inv. 9310.00-05-Retainage |  | 287039.75 | 14351.99 | 287039.75 | 0
|  |  |  | 287039.75 |  | 287039.75 | 0
|  |  |  | 287039.75 |  | 287039.75 | 0
|  |  |  | 287039.75 |  | 287039.75 | 0
|  |  |  | 287039.75 |  | 287039.75 | 0
|  |  |  | 287039.75 |  | 287039.75 | 0
|  | Totals: | 287039.75 |  | 287039.75 |  | 0

## #9310.00 DCI Group #22-031 CA
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  | Major Program 4B03
DCI Group #22-031 CA |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFB931000-02
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523181804 | 2023-06-30 | PO Procore | 31253.99 | 31253.99 |  |  | 31253.99 | FY23
PO 33524181804 | 2023-08-04 | Roll to FY24 | 0 | 31253.99 |  | 0 | 31253.99
PRC 3352418PA1804 | 2023-10-17 | Inv. 22-031 CA-01 |  | 31253.99 | 10695.98 | 10695.98 | 20558.01
PO 33524181804 | 2023-10-19 | CO #1 | 6483.58 | 37737.57 |  | 10695.98 | 27041.59
PRC 3352418PB1804 | 2023-11-16 | Inv. 22-031 CA-02 |  | 37737.57 | 11788.22 | 22484.2 | 15253.37
PRC 3352418PC1804 | 2023-12-19 | Inv. 22-031 CA-03 |  | 37737.57 | 1197.99 | 23682.19 | 14055.38
PRC 3352418PD1804 | 2024-01-24 | Inv. 22-031 CA-04 |  | 37737.57 | 2189.51 | 25871.7 | 11865.87
PRC 3352418PE1804 | 2024-03-05 | Inv. 22-031 CA 05 |  | 37737.57 | 2524.74 | 28396.44 | 9341.13
PRC 3352418PF1804 | 2024-05-02 | Inv. 22-031 CA 06 |  | 37737.57 | 1111.75 | 29508.19 | 8229.38
PRC 3352418PG1804 | 2024-06-20 | Inv. 22-031 CA 07 |  | 37737.57 | 2089.84 | 31598.03 | 6139.54
PRC 3352418PH1804 | 2024-07-22 | Inv. 22-031 CA 08 |  | 37737.57 | 1482.27 | 33080.3 | 4657.27 | FY24
PO 33525181804 | 2024-07-25 | Roll to FY25 |  | 37737.57 |  | 33080.3 | 4657.27
PRC 3352518PI1804 | 2024-10-16 | Inv. 22-031 CA-09 - Final | -3836.44 | 33901.13 | 820.83 | 33901.13 | 0
|  |  |  | 33901.13 |  | 33901.13 | 0
|  |  |  | 33901.13 |  | 33901.13 | 0
|  | Totals: | 33901.13 |  | 33901.13 |  | 0
|  | Construction Management Staff Hours | 23746.77 |  | 23746.77 |  | 0
|  | Reimbursables | 3694.14 |  | 3694.14 |  | 0
|  | CO #1 | 6460.22 |  | 6460.22 |  | 0
|  | Totals: | 33901.13 |  | 33901.13 |  | 0

## #9310.00 Proctor Mechanical
DVA IVH Sheeler Clinical Roof Replacement
Project # 9310.00
Program code 931000 |  |  | Major Program 4B03
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM23-9255 |  |  | MA 21010A
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524292804 | 2023-10-19 | PO Procore | 110634 | 110634 |  |  | 110634
PO 33524292804 | 2023-11-14 | CO #1 | 15928.28 | 126562.28 |  | 0 | 126562.28
PRC 3352429PA2804 | 2024-02-16 | Inv. 7593.1 |  | 126562.28 | 13865.25 | 13865.25 | 112697.03 | 729.75
PRC 3352429PB2804 | 2024-07-23 | Inv. 7593.2 - Final | -38161.4 | 88400.88 | 70115.59 | 83980.84 | 4420.04 | 4420.04
PRC 3352429PC2804 | 2024-07-26 | Inv. 7593.3Retainage |  | 88400.88 | 4420.04 | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  |  |  | 88400.88 |  | 88400.88 | 0
|  | Totals: | 88400.88 |  | 88400.88 |  | 0

## RECAP #9317.00
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
| Program code 931700 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 990196.82
C | McGough Construction |  | 20313.5 | 20313.5 | 0
C | PM TIME |  | 32456.78 | 32456.78 | 0
C | Misc. |  | 2852.43 | 2852.43 | 0
C | Horizon Architecture |  | 45000 | 45000 | 0
C | Earth Services & Abatement |  | 18750 | 18750 | 0
C | SG Construction |  | 776984.17 | 776984.17 | 0
C | McGough Construction(2) |  | 93839.94 | 93839.94 | 0
| Total Project Cost | 990196.82 | 990196.82 | 990196.82 | 0 | 0
Closed 01/09/25

## #9317.00 McGough Construction
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523278900 | 2022-10-05 | PO Procore | 12467.5 | 12467.5 |  |  | 12467.5
PRC 3352327PA8900 | 2022-11-14 | Inv. 100877.009-1PC |  | 12467.5 | 1390 | 1390 | 11077.5
PRC 3352327PB8900 | 2022-12-12 | Inv. 100877.009-2 |  | 12467.5 | 950 | 2340 | 10127.5
PRC 3352327PC8900 | 2023-01-14 | Inv. 100877.009PC3 |  | 12467.5 | 155 | 2495 | 9972.5
PRC 3352327PD8900 | 2023-02-11 | Inv. 100877.009PC4 |  | 12467.5 | 294 | 2789 | 9678.5
PRC 3352327PE8900 | 2023-03-13 | Inv. 100877.009PC5 |  | 12467.5 | 637 | 3426 | 9041.5
PRC 3352327PF8900 | 2023-04-11 | Inv. 100877.009-06 |  | 12467.5 | 2041.5 | 5467.5 | 7000
PRC 3352327PG8900 | 2023-05-08 | Inv. 100877.009-07 |  | 12467.5 | 1413 | 6880.5 | 5587
PRC 3352327PH8900 | 2023-06-14 | Inv. 100877.009-08 |  | 12467.5 | 862 | 7742.5 | 4725
PRC 3352327PI8900 | 2023-06-30 | Inv. 100877.009-09 |  | 12467.5 | 2140 | 9882.5 | 2585 | FY23
PO 33524278900 | 2023-08-07 | Roll to FY24 | 0 | 12467.5 |  | 9882.5 | 2585
PRC 3352427PJ8900 | 2023-08-07 | Inv. 100877.009-10 |  | 12467.5 | 2160.5 | 12043 | 424.5
PO 33524278900 | 2023-08-21 | CO #1 | 7896 | 20363.5 |  | 12043 | 8320.5
PRC 3352427PK8900 | 2023-09-14 | Inv. 100877.009-11 |  | 20363.5 | 3048 | 15091 | 5272.5
PRC 3352427PL8900 | 2023-10-05 | Inv. 100877.009-12 |  | 20363.5 | 1626 | 16717 | 3646.5
PRC 3352427PM8900 | 2023-11-13 | Inv. 100877.009-13 |  | 20363.5 | 2159.5 | 18876.5 | 1487
PRC 3352427PN8900 | 2023-12-13 | Inv. 100877.009-14 Final | -50 | 20313.5 | 1437 | 20313.5 | 0
|  |  |  | 20313.5 |  | 20313.5 | 0
|  |  |  | 20313.5 |  | 20313.5 | 0
|  | Totals: | 20313.5 |  | 20313.5 |  | 0 | Final
|  | CM Services | 12058 |  | 12058 |  | 0
|  | Reimbursables | 409.5 |  | 409.5 |  | 0
|  | CO #1 | 7846 |  | 7846 |  | 0
|  | Totals: | 20313.5 |  | 20313.5 |  | 0

## #9317.00 Misc
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524311800 | 2023-11-07 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2528938 | 1140 | 1140
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 247.5 | 1387.5
PRC 33524363801 | 2023-12-29 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV035459 | 112.79 | 1500.29
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 82.5 | 1582.79
PRC 33524018902 | 2024-01-18 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2523078 | 912.5 | 2495.29
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -330 | 2165.29
PRC 33525009905 | 2025-01-09 | 9500 | CNST | Controlled Installations of Iowa V#(00002115535) | Inv. 158173 | 687.14 | 2852.43
2852.43
2852.43
2852.43
|  |  |  | ` |  |  | 2852.43
2852.43
2852.43
|  |  |  | Totals: |  | 2852.43

## #9317.00 PM TIME
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 908H
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 31382.06 | 31382.06 |  |  | 31382.06
IET DAS202303115300001 | 2022-10-07 | 9500 | PM Time-September 1-September 30, 2022 |  | 31382.06 | 55 | 55 | 31327.06
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 31382.06 | 990 | 1045 | 30337.06
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 31382.06 | 440 | 1485 | 29897.06
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Sep 9997.23 disbursement | 35.17 | 31417.23 | 35.17 | 1520.17 | 29897.06
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 623.38 | 32040.61 | 623.38 | 2143.55 | 29897.06
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 302.05 | 32342.66 | 302.05 | 2445.6 | 29897.06
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 32342.66 | 234.71 | 2680.31 | 29662.35
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 79.01 | 32421.67 | 79.01 | 2759.32 | 29662.35
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 35.11 | 32456.78 | 35.11 | 2794.43 | 29662.35
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 32456.78 | 117.93 | 2912.36 | 29544.42
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 32456.78 | 715.17 | 3627.53 | 28829.25
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 32456.78 | 275.36 | 3902.89 | 28553.89
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 32456.78 | 1211.15 | 5114.04 | 27342.74
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 32456.78 | 277.43 | 5391.47 | 27065.31
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 32456.78 | 1630.1 | 7021.57 | 25435.21
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 32456.78 | 90.13 | 7111.7 | 25345.08
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 32456.78 | 631.4 | 7743.1 | 24713.68
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 32456.78 | 124.27 | 7867.37 | 24589.41
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 32456.78 | 1078.7 | 8946.07 | 23510.71
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 32456.78 | 121.75 | 9067.82 | 23388.96
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 32456.78 | 777 | 9844.82 | 22611.96
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 32456.78 | 148.68 | 9993.5 | 22463.28
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 32456.78 | 830.7 | 10824.2 | 21632.58
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 32456.78 | 143.19 | 10967.39 | 21489.39
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 32456.78 | 996.5 | 11963.89 | 20492.89
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 32456.78 | 121.49 | 12085.38 | 20371.4
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 32456.78 | 972.5 | 13057.88 | 19398.9
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 32456.78 | 111.39 | 13169.27 | 19287.51
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 32456.78 | 841.7 | 14010.97 | 18445.81
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 32456.78 | 300.22 | 14311.19 | 18145.59
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 32456.78 | 2204.1 | 16515.29 | 15941.49
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 32456.78 | 221.23 | 16736.52 | 15720.26
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 32456.78 | 1953.8 | 18690.32 | 13766.46
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 32456.78 | 132.1 | 18822.42 | 13634.36
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 32456.78 | 667.2 | 19489.62 | 12967.16
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 32456.78 | 124.47 | 19614.09 | 12842.69
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 32456.78 | 943.1 | 20557.19 | 11899.59
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 32456.78 | 65.55 | 20622.74 | 11834.04
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 32456.78 | 582 | 21204.74 | 11252.04
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 32456.78 | 177.82 | 21382.56 | 11074.22
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 32456.78 | 1483.4 | 22865.96 | 9590.82
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 32456.78 | 175.54 | 23041.5 | 9415.28
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 32456.78 | 1602 | 24643.5 | 7813.28
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 32456.78 | 143.48 | 24786.98 | 7669.8
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 32456.78 | 1565.6 | 26352.58 | 6104.2
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 32456.78 | 358.87 | 26711.45 | 5745.33
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 32456.78 | 1828.8 | 28540.25 | 3916.53
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 32456.78 | 135.24 | 28675.49 | 3781.29
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 32456.78 | 1206.6 | 29882.09 | 2574.69
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 32456.78 | 193.64 | 30075.73 | 2381.05
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 32456.78 | 1294 | 31369.73 | 1087.05
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 32456.78 | 75.05 | 31444.78 | 1012
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 32456.78 | 497.7 | 31942.48 | 514.3
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 32456.78 | 46.4 | 31988.88 | 467.9
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 32456.78 | 467.9 | 32456.78 | -6.1391e-12
[5 empty] | 32456.78 |  | 32456.78 | -6.1391e-12
[5 empty] | 32456.78 |  | 32456.78 | -6.1391e-12
[5 empty] | 32456.78 |  | 32456.78 | -6.1391e-12
|  |  | Totals: | 32456.78 |  | 32456.78 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: New MM Project $Joni Herman, Josh Tue, Sep 27, 3:01 PM (2 days ago) to me Please set up the PM budget to be $5,500. Thank you, Josh Josh Herman CPM, Owner Representative Iowa Department of Administrative Services General Services Enterprise Office: 515-725-1293 ¦ Mobile: 515-201-2197 josh.herman@iowa.gov https://das.iowa.gov Re: PM Time Inbox Trower, James 3:53 PM (13 minutes ago) to me John - For project 9317.00: Please increase PM Time by $7,000. Thanks, James 9317.00 - DOC MPCF Interlock and Corridor Door Replacement $Joni Trower, James Dec 1, 2023, 4:19 PM (3 days ago) to me Finance - Please increase the MM23 budget for project 9317.00 by $60,000. Please increase PM Time (MM23) by 8,425.28. Thanks, James Trower, Licensed Architect, LEED AP Re: PM Time Postings $Joni Adams, Brandon 7:27 AM (26 minutes ago) to me Finance, DA24 9414.00 Needs a PM Time Budget set - currently (2939.13) Please set PM Time budget at $10,000.00 MM22 9302.00 (82.36) Increase PM time by $1500 MM23 9317.00 (865.96) Increase PM time by $5,000 MM23 9370.00 (1,722.26) Increase PM time by $5000 Regards, Brandon Adams Adams, Brandon 9:28 AM (17 minutes ago) to me Finance, Please increase my PM Time for the following projects: DA24 9414.00 $3,000 DA24 9423.00 $3,000 MM23 9317.00 $3,000 From: Adams, Brandon <brandon.adams@iowa.gov> Date: Tue, Nov 12, 2024 at 11:19 AM Subject: Re: October PM Time Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Please increase my PM Time on the following projects: DA24 9414.00 $5,000 DA24 9423.00 $5,000 MM22 9429.00 $2,000 MM22 9387.00 $4,000 MM23 9317.00 $4,000

## #9317.00 Horizon Architecture
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  | Major Program 4B01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM23-9260 |  |  | RFP931700-02
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523116801 | 2023-04-26 | PO Procore | 38450 | 38450 |  |  | 38450
PRC 3352311PA6801 | 2023-06-26 | Inv. 9317.00-01A |  | 38450 | 9375 | 9375 | 29075
PO 33523116801 | 2023-08-04 | CO #1 | 7500 | 45950 |  | 9375 | 36575 | FY23
PO 33524116801 | 2023-08-18 | Roll to FY24 | 0 | 45950 |  | 9375 | 36575
PRC 3352411PB6801 | 2023-08-31 | Inv. 9317.00-02 |  | 45950 | 24375 | 33750 | 12200
PRC 3352411PC6801 | 2023-10-03 | Inv. 9317.00-03 |  | 45950 | 1875 | 35625 | 10325
PRC 3352411PD6801 | 2024-01-04 | Inv. 9317.00-04 |  | 45950 | 1875 | 37500 | 8450
PRC 3352411PE6801 | 2024-03-18 | Inv. 9317.00-05 |  | 45950 | 1500 | 39000 | 6950
PRC 3352411PF6801 | 2024-06-12 | Inv. 9317.00-06 |  | 45950 | 1500 | 40500 | 5450
PRC 3352411PG6801 | 2024-07-08 | Inv. 9317.00-07 |  | 45950 | 750 | 41250 | 4700 | FY24
PO 33525116801 | 2024-07-24 | Roll to FY25 |  | 45950 |  | 41250 | 4700
PRC 3352511PH6801 | 2024-08-08 | Inv. 9317.00-08 |  | 45950 | 1875 | 43125 | 2825
PRC 3352511PI6801 | 2024-09-06 | Inv. 9317.00-09 |  | 45950 | 750 | 43875 | 2075
PRC 3352511PJ6801 | 2024-12-16 | Inv. 9317.00-10 - Final | -950 | 45000 | 1125 | 45000 | 0
|  |  |  | 45000 |  | 45000 | 0
|  | Totals: | 45000 |  | 45000 |  | 0 | Final
|  | Design Development | 9375 |  | 9375 |  | 0
|  | Construction Documents | 18750 |  | 18750 |  | 0
|  | Bid/Negotiation Phase | 1875 |  | 1875 |  | 0
|  | Construction Phase | 7500 |  | 7500 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | CO1 | 7500 |  | 7500 |  | 0
|  | Totals: | 45000 |  | 45000 |  | 0

## #9317.00 Earth Services
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  | Major Program 4B01
Earth Services |  |  | Vendor: VS000007582
Acct. Codes-0017-335-MM23-9255 |  |  | MA21062A
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524349906 | 2023-12-15 | PO Procore | 16750 | 16750 |  |  | 16750
PO 33524349906 | 2024-05-06 | CO #1 | 2000 | 18750 |  | 0 | 18750
PRC 3352434PA9906 | 2024-06-18 | Inv. 1 (DES-i001999) |  | 18750 | 17812.5 | 17812.5 | 937.5 | 937.5
PRC 3352434PB9906 | 2024-08-09 | Inv. 2 (DES-i002121) - Retainage |  | 18750 | 937.5 | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  |  |  | 18750 |  | 18750 | 0
|  | Totals: | 18750 |  | 18750 |  | 0 | FINAL

## #9317.00 SG Construction
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  | Major Program 4B01
SG Construction |  |  | Vendor: 00003039074
Acct. Codes-0017-335-MM23-9255 |  |  | RFB 931700-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524355801 | 2023-12-21 | PO Procore | 762651 | 762651 |  |  | 762651
PRC 3352435PA5801 | 2024-05-07 | Inv. 6510 |  | 762651 | 45528.75 | 45528.75 | 717122.25 | 2396.25
PO 33524355801 | 2024-06-13 | CO #1 | 6842.32 | 769493.32 |  | 45528.75 | 723964.57
PO 33524355801 | 2024-06-17 | CO #2 | 12771.45 | 782264.77 |  | 45528.75 | 736736.02
PRC 3352435PB5801 | 2024-06-17 | Inv. 6541 |  | 782264.77 | 88540 | 134068.75 | 648196.02 | 7056.25
PRC 3352435PC5801 | 2024-07-02 | Inv. 6575 |  | 782264.77 | 255818.42 | 389887.17 | 392377.6 | 20520.38 | FY24
PO 33525355801 | 2024-07-24 | Roll to FY25 |  | 782264.77 |  | 389887.17 | 392377.6
PRC 3352535PD5801 | 2024-08-06 | Inv. 6605 |  | 782264.77 | 183095.02 | 572982.19 | 209282.58 | 30156.96 |  | `
PO 33525355801 | 2024-08-20 | CO #3 | 1323.25 | 783588.02 |  | 572982.19 | 210605.83
PO 33525355801 | 2024-08-26 | CO #4 | -603.85 | 782984.17 |  | 572982.19 | 210001.98
PRC 3352535PE5801 | 2024-09-12 | Inv. 6640 |  | 782984.17 | 79724.02 | 652706.21 | 130277.96 | 34352.96
PRC 3352535PF5801 | 2024-10-09 | Inv. 6673 |  | 782984.17 | 62035 | 714741.21 | 68242.96 | 37617.96
PO 33525355801 | 2024-10-10 | CO #5 | -6000 | 776984.17 |  | 714741.21 | 62242.96
PRC 3352535PG5801 | 2024-11-06 | Inv. 6709 |  | 776984.17 | 16150 | 730891.21 | 46092.96 | 38467.96
PRC 3352535PH5801 | 2024-12-09 | Inv. 6771 |  | 776984.17 | 7243.75 | 738134.96 | 38849.21 | 38849.21
PRC 3352535PI5801 | 2024-12-16 | Inv. 6772-Retainage |  | 776984.17 | 38849.21 | 776984.17 | -1.3824e-10
|  |  |  | 776984.17 |  | 776984.17 | -1.3824e-10
|  |  |  | 776984.17 |  | 776984.17 | -1.3824e-10
|  | Totals: | 776984.17 |  | 776984.17 |  | 0 | FINAL

## #9317.00 McGough Construction 2
DOC MPCF Interlock and Corridor Door Replacement
Project # 9317.00
Program code 931700 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524356903 | 2023-12-21 | PO Procore | 95582.51 | 95582.51 |  |  | 95582.51
PRC 3352435PA6903 | 2024-01-12 | Inv. 100877.009-01CA |  | 95582.51 | 2049 | 2049 | 93533.51
PRC 3352435PB6903 | 2024-02-08 | Inv. 100877.009-02CA |  | 95582.51 | 2454.77 | 4503.77 | 91078.74
PRC 3352435PC6903 | 2024-03-08 | Inv. 100877.009-03CA |  | 95582.51 | 1200.05 | 5703.82 | 89878.69
PRC 3352435PD6903 | 2024-04-08 | Inv. 100877.009-04CA |  | 95582.51 | 1174.15 | 6877.97 | 88704.54
PRC 3352435PE6903 | 2024-05-08 | Inv. 100877.009-05CA |  | 95582.51 | 3524.35 | 10402.32 | 85180.19
PRC 3352435PF6903 | 2024-06-11 | Inv. 100877.009-06CA |  | 95582.51 | 3092.6 | 13494.92 | 82087.59
PRC 3352435PG6903 | 2024-07-08 | Inv. 100877.009-07CA |  | 95582.51 | 22586.1 | 36081.02 | 59501.49 | FY24
PO 33525356903 | 2024-07-24 | Roll to FY25 |  | 95582.51 |  | 36081.02 | 59501.49
PRC 3352535PH6903 | 2024-08-09 | Inv. 100877.009-0CA |  | 95582.51 | 12772.25 | 48853.27 | 46729.24
PRC 3352535PI6903 | 2024-09-12 | Inv. 100877.009-09CA |  | 95582.51 | 12557.69 | 61410.96 | 34171.55
PRC 3352535PJ6903 | 2024-10-14 | Inv. 100877.009-10CA |  | 95582.51 | 15174.31 | 76585.27 | 18997.24
PRC 3352535PK6903 | 2024-11-12 | Inv. 100877.009-11CA |  | 95582.51 | 12206.63 | 88791.9 | 6790.61
PO 33525356903 | 2024-11-21 | CO #1 | 33.06 | 95615.57 |  | 88791.9 | 6823.67
PRC 3352535PL6903 | 2024-12-23 | Inv. 100877.009-12CA-Final | -1775.63 | 93839.94 | 5048.04 | 93839.94 | -1.5461e-11
|  |  |  | 93839.94 |  | 93839.94 | -1.5461e-11
|  | Totals: | 93839.94 |  | 93839.94 |  | 0 | FINAL
|  | CM Services | 52244.83 |  | 52244.83 |  | 0
|  | Reimbursables | 3429.5 |  | 3429.5 |  | 0
|  | 5% fee | 38132.55 |  | 38132.55 |  | 0
|  | CO #1 | 33.06 |  | 33.06 |  | 0
|  | Totals: | 93839.94 |  | 93839.94 |  | 0

## RECAP #9319.00
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
| Program code 931900 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 496102.69
C | Samuels Group |  | 13327.08 | 13327.08 | 0
C | PM TIME |  | 23326.89 | 23326.89 | 0
C | Misc. |  | 3784 | 3784 | 0
C | Shive Hattery |  | 28800 | 28800 | 0
C | Proctor Mechanical |  | 398375 | 398375 | 0
C | Samuels Group 131CA |  | 28489.72 | 28489.72 | 0
| Total Project Cost | 496102.69 | 496102.69 | 496102.69 | 0 | 0
Closed 10/14/2024

## #9319.00 Samuels Group
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523321803 | 2022-11-17 | PO Procore | 17132.2 | 17132.2 |  |  | 17132.2
PRC 3352332PA1803 | 2023-02-16 | Inv. 7458.01931900 |  | 17132.2 | 1527.39 | 1527.39 | 15604.81
PRC 3352332PB1803 | 2023-03-14 | Inv. 7458.02931900 |  | 17132.2 | 1077.36 | 2604.75 | 14527.45
PRC 3352332PC1803 | 2023-06-09 | Inv. 7458.03931900 |  | 17132.2 | 5362.23 | 7966.98 | 9165.22
PRC 3352332PD1803 | 2023-07-10 | Inv. 7458.04931900 |  | 17132.2 | 916.32 | 8883.3 | 8248.9 | FY23
PO 33524321803 | 2023-08-04 | Roll to FY24 | 0 | 17132.2 |  | 8883.3 | 8248.9
PRC 3352432PE1803 | 2023-09-14 | Inv. 7458.05931900 FINAL PC | -3805.12 | 13327.08 | 4443.78 | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  |  |  | 13327.08 |  | 13327.08 | 0
|  | Totals: | 13327.08 |  | 13327.08 |  | 0 | FINAL
|  | CM Services | 13239.08 |  | 13239.08 |  | 0
|  | Reimbursables | 88 |  | 88 |  | 0
|  | Totals: | 13327.08 |  | 13327.08 |  | 0

## #9319.00 PM TIME
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E244
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22672.83 | 22672.83 |  |  | 22672.83
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 22672.83 | 27.5 | 27.5 | 22645.33
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 22672.83 | 467.5 | 495 | 22177.83
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 31.13 | 22703.96 | 31.13 | 526.13 | 22177.83
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 414.47 | 23118.43 | 414.47 | 940.6 | 22177.83
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 23118.43 | 740.47 | 1681.07 | 21437.36
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 23118.43 | 39.71 | 1720.78 | 21397.65
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 23118.43 | 348.11 | 2068.89 | 21049.54
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 3.79 | 23122.22 | 3.79 | 2072.68 | 21049.54
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 93.9 | 23216.12 | 93.9 | 2166.58 | 21049.54
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 110.77 | 23326.89 | 110.77 | 2277.35 | 21049.54
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 23326.89 | 153.76 | 2431.11 | 20895.78
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 23326.89 | 932.45 | 3363.56 | 19963.33
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 23326.89 | 149.84 | 3513.4 | 19813.49
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 23326.89 | 659.1 | 4172.5 | 19154.39
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 23326.89 | 132.69 | 4305.19 | 19021.7
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 23326.89 | 779 | 5084.19 | 18242.7
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 23326.89 | 170.96 | 5255.15 | 18071.74
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 23326.89 | 1200.1 | 6455.25 | 16871.64
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 23326.89 | 128.51 | 6583.76 | 16743.13
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 23326.89 | 1074.3 | 7658.06 | 15668.83
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 23326.89 | 129.54 | 7787.6 | 15539.29
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 23326.89 | 825 | 8612.6 | 14714.29
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 23326.89 | 150.21 | 8762.81 | 14564.08
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 23326.89 | 837.8 | 9600.61 | 13726.28
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 23326.89 | 128.02 | 9728.63 | 13598.26
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 23326.89 | 890.4 | 10619.03 | 12707.86
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 23326.89 | 103.27 | 10722.3 | 12604.59
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 23326.89 | 829.9 | 11552.2 | 11774.69
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 23326.89 | 64.9 | 11617.1 | 11709.79
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 23326.89 | 491.8 | 12108.9 | 11217.99
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 23326.89 | 184.81 | 12293.71 | 11033.18
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 23326.89 | 1358.5 | 13652.21 | 9674.68
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 23326.89 | 126.37 | 13778.58 | 9548.31
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 23326.89 | 1116.4 | 14894.98 | 8431.91
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 23326.89 | 98.48 | 14993.46 | 8333.43
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 23326.89 | 496.3 | 15489.76 | 7837.13
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 23326.89 | 95.41 | 15585.17 | 7741.72
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 23326.89 | 723.7 | 16308.87 | 7018.02
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 23326.89 | 135.42 | 16444.29 | 6882.6
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 23326.89 | 1202.3 | 17646.59 | 5680.3
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 23326.89 | 172.65 | 17819.24 | 5507.65
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 23326.89 | 1436 | 19255.24 | 4071.65
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 23326.89 | 102.59 | 19357.83 | 3969.06
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 23326.89 | 936.4 | 20294.23 | 3032.66
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 23326.89 | 281.12 | 20575.35 | 2751.54
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 23326.89 | 1432.9 | 22008.25 | 1318.64
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 30,2024 |  | 23326.89 | 132.84 | 22141.09 | 1185.8
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 30,2024 |  | 23326.89 | 1185.8 | 23326.89 | 1.1369e-11
[5 empty] | 23326.89 |  | 23326.89 | 1.1369e-11
[5 empty] | 23326.89 |  | 23326.89 | 1.1369e-11
[5 empty] | 23326.89 |  | 23326.89 | 1.1369e-11
|  |  | Totals: | 23326.89 |  | 23326.89 |  | 0
Note on E9: Huggins, Joni [DAS]: Setup - PM Time Budgets on New Projects $Joni Tonyan, Brad 2:17 PM (11 minutes ago) to me, Scott, Brad Finance, Please set up the following PM time budgets below as these are new projects: 9255.00 - DOC NCF Building K (Admin) and CRC Boiler and Dorms 1 &2 Roof Replacement - $25,000 9319.00 - DOC NCF Building H (Main Server) and Master Control HVAC Replacement - $8,500 9321.00 - DVA IVH North Parking Lot Replacement - $17,000 9324.00 - DOC NCF Generator Switchgear Controls Replacement - $8,500 Thank you and please let me know once completed. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. MM23: 9306.00 - Decrease overall budget by $145,000 and give back to general org. fund MM23 9310.00 - Increase PM Time by $5K 9319.00 - Increase PM Time by $5K 9330.00 - Increase PM time as needed to pay January PM time. Once this PM time hits all financials can be closed and remaining roughly $12K can be returned to general org. fund MM23 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative

## #9319.00 Misc
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525270901 | 2024-09-26 | 9500 | CNST | Proctor Mechanical V#(00003166259) | Inv. DMM24-132 | 3784 | 3784
3784
3784
3784
3784
3784
3784
3784
3784
3784
3784
3784
|  |  |  | Totals: |  | 3784

## #9319.00 Shive Hattery
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP931900-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523055801 | 2023-02-24 | PO Procore | 26800 | 26800 |  |  | 26800
PRC 3352305PA5801 | 2023-03-22 | Inv. 2142301280-1 |  | 26800 | 1605 | 1605 | 25195
PRC 3352305PB5801 | 2023-04-24 | Inv. 2142301280-2 |  | 26800 | 9095 | 10700 | 16100
PRC 3352305PC5801 | 2023-05-31 | Inv. 2142301280-3 |  | 26800 | 7505 | 18205 | 8595
PRC 3352305PD5801 | 2023-06-30 | Inv. 2142301280-4 |  | 26800 | 395 | 18600 | 8200 | FY23
PO 33524055801 | 2023-08-04 | Roll to FY24 | 0 | 26800 |  | 18600 | 8200
PRC 3352405PE5801 | 2023-08-07 | Inv. 2142301280-5 |  | 26800 | 1700 | 20300 | 6500
PRC 3352405PF5801 | 2023-09-06 | Inv. 2142301280-6 |  | 26800 | 975 | 21275 | 5525
PRC 3352405PG5801 | 2023-10-05 | Inv. 2142301280-7 |  | 26800 | 650 | 21925 | 4875
PRC 3352405PH5801 | 2023-12-06 | Inv. 2142301280-8 |  | 26800 | 325 | 22250 | 4550
PRC 3352405PI5801 | 2024-01-03 | Inv. 2142301280-9 |  | 26800 | 650 | 22900 | 3900
PO 33524055801 | 2024-01-05 | CO #1 | 2000 | 28800 |  | 22900 | 5900
PRC 3352405PJ5801 | 2024-02-05 | Inv. 2142301280-10 |  | 28800 | 1500 | 24400 | 4400
PRC 3352405PK5801 | 2024-03-04 | Inv. 2142301280-11 |  | 28800 | 1475 | 25875 | 2925
PRC 3352405PL5801 | 2024-04-03 | Inv. 2142301280-12 |  | 28800 | 325 | 26200 | 2600
PRC 3352405PM5801 | 2024-05-06 | Inv. 2142301280-13 |  | 28800 | 975 | 27175 | 1625
PRC 3352405PN5801 | 2024-07-09 | Inv. 2142301280-14RFINAL |  | 28800 | 1625 | 28800 | 0
|  |  |  | 28800 |  | 28800 | 0
|  |  |  | 28800 |  | 28800 | 0
|  | Totals: | 28800 |  | 28800 |  | 0 | FINAL
|  | Design Development | 10700 |  | 10700 |  | 0
|  | Construction Documents | 7900 |  | 7900 |  | 0
|  | Bidding | 1700 |  | 1700 |  | 0
|  | Construction Phase | 6500 |  | 6500 |  | 0
|  | CO #1 | 2000 |  | 2000 |  | 0
|  | Totals: | 28800 |  | 28800 |  | 0

## #9319.00 Proctor Mechanical
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  | Major Program 4B01
Proctor Mechanical |  |  | Vendor:00003166259
Acct. Codes-0017-335-MM23-9255 |  |  | RFP931900-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524220901 | 2023-08-08 | PO Procore | 384950 | 384950 |  |  | 384950
PRC 3352422PA0901 | 2023-10-30 | Inv. 7578.0/1 |  | 384950 | 89015 | 89015 | 295935 | 4685
PO 33524220901 | 2024-02-01 | CO #1 | 13425 | 398375 |  | 89015 | 309360
PRC 3352422PB0901 | 2024-03-25 | Inv. 7578.0/2 |  | 398375 | 13149.42 | 102164.42 | 296210.58 | 5377.08
PRC 3352422PC0901 | 2024-04-22 | Inv. 7578.0/3 |  | 398375 | 36689.47 | 138853.89 | 259521.11 | 7308.11
PRC 3352422PD0901 | 2024-04-30 | Inv. 7578.0/4 |  | 398375 | 126033.53 | 264887.42 | 133487.58 | 13941.48
PRC 3352422PE0901 | 2024-06-01 | Inv. 7578.0/5 |  | 398375 | 110718.77 | 375606.19 | 22768.81 | 19768.81
PRC 3352422PF0901 | 2024-07-15 | Inv. 7578.0/6 FINAL |  | 398375 | 2850 | 378456.19 | 19918.81 | 19918.81
PRC 3352422PG0901 | 2024-07-16 | Inv. 7578.0/07-Retainage |  | 398375 | 19918.81 | 398375 | 0
|  |  |  | 398375 |  | 398375 | 0
|  |  |  | 398375 |  | 398375 | 0
|  |  |  | 398375 |  | 398375 | 0
|  |  |  | 398375 |  | 398375 | 0
|  | Totals: | 398375 |  | 398375 |  | 0

## #9319.00 Samuels Group 131CA
DOC NCF Building H (Main Server) and Master Control HVAC Replacement
Project # 9319.00
Program code 931900 |  |  | Major Program 4B01
Samuels Group 131CA |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524249800 | 2023-09-06 | PO Procore | 28498.28 | 28498.28 |  |  | 28498.28
PRC 3352424PA9800 | 2023-09-14 | Inv. 7458.509319 CA |  | 28498.28 | 2962.52 | 2962.52 | 25535.76
PRC 3352424PB9800 | 2023-10-11 | Inv. 7458.519319 CA |  | 28498.28 | 1435.13 | 4397.65 | 24100.63
PRC 3352424PC9800 | 2023-12-12 | Inv. 7458.529319 CA |  | 28498.28 | 3306.42 | 7704.07 | 20794.21
PRC 3352424PD9800 | 2024-02-08 | Inv. 7458.539319 CA |  | 28498.28 | 4363.26 | 12067.33 | 16430.95
PRC 3352424PE9800 | 2024-03-05 | Inv. 7458.549319 CA |  | 28498.28 | 665.98 | 12733.31 | 15764.97
PRC 3352424PF9800 | 2024-04-10 | Inv. 7458.559319 CA |  | 28498.28 | 4906.59 | 17639.9 | 10858.38
PRC 3352424PG9800 | 2024-05-06 | Inv. 7458.569319 CA |  | 28498.28 | 8729.5 | 26369.4 | 2128.88
PRC 3352424PH9800 | 2024-05-29 | Inv. 7458.579319 CA |  | 28498.28 | 1469.52 | 27838.92 | 659.36
PRC 3352424PI9800 | 2024-07-09 | Inv. 7458.589319 CA FINAL | -8.56 | 28489.72 | 650.8 | 28489.72 | -2.5562e-12
|  |  |  | 28489.72 |  | 28489.72 | -2.5562e-12
|  |  |  | 28489.72 |  | 28489.72 | -2.5562e-12
|  |  |  | 28489.72 |  | 28489.72 | -2.5562e-12
|  | Totals: | 28489.72 |  | 28489.72 |  | 0 | FINAL
|  | CM Services | 28247.72 |  | 28247.72 |  | 0
|  | Reimbursables | 242 |  | 242 |  | 0
|  | Totals: | 28489.72 |  | 28489.72 |  | 0

## RECAP #9320.00
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
| Program code 932000 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 124991.55
C | McGough Construction |  | 12137.71 | 12137.71 | 0
C | PM TIME |  | 8666.73 | 8666.73 | 0
C | Misc. |  | 1351 | 1351 | 0
C | MA Architecture |  | 24335 | 24335 | 0
C | McGough Construction (2) |  | 17231.11 | 17231.11 | 0
C | Boone Glass Company |  | 61270 | 61270 | 0
| Total Project Cost | 124991.55 | 124991.55 | 124991.55 | 0 | 0
Closed 10/04/2024

## #9320.00 McGough Construction
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  | Major Program 4B01
McGough Construction #101031.004PC |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524208803 | 2023-07-27 | PO Procore | 12290.55 | 12290.55 |  |  | 12290.55
PRC 3352420PA8803 | 2023-09-14 | Inv. 101031.004PC-001 |  | 12290.55 | 1725.09 | 1725.09 | 10565.46
PRC 3352420PB8803 | 2023-10-10 | Inv. 101031.004PC-002 |  | 12290.55 | 1202.8 | 2927.89 | 9362.66
PRC 3352420PC8803 | 2023-11-13 | Inv. 101031.004PC-003 |  | 12290.55 | 3453.9 | 6381.79 | 5908.76
PRC 3352420PD8803 | 2023-12-11 | Inv. 101031.004PC-04 |  | 12290.55 | 2494.44 | 8876.23 | 3414.32
PRC 3352420PE8803 | 2024-01-12 | Inv. 101031.004PC-05 |  | 12290.55 | 2192.96 | 11069.19 | 1221.36
PRC 3352420PF8803 | 2024-02-06 | Inv. 101031.004PC-06 - Final | -152.84 | 12137.71 | 1068.52 | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  |  |  | 12137.71 |  | 12137.71 | 0
|  | Totals: | 12137.71 |  | 12137.71 |  | 0 | FINAL
|  | CM Services | 11843.71 |  | 11843.71 |  | 0
|  | Reimbursables | 294 |  | 294 |  | 0
|  | Totals: | 12137.71 |  | 12137.71 |  | 0

## #9320.00 PM TIME
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E245
Project Manager - James T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8666.73 | 8666.73 |  |  | 8666.73
IET DAS202308115300001 | 2023-03-07 |  | Finance Support for: October 1-31, 2022 | 113.73 | 8780.46 | 113.73 | 113.73 | 8666.73
CDE 33523075203 | 2023-03-07 |  | Move to correct project 9176.00 MM21 | -113.73 | 8666.73 | -113.73 | 0 | 8666.73
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 8666.73 | 146.24 | 146.24 | 8520.49
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 8666.73 | 932.5 | 1078.74 | 7587.99
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 8666.73 | 132.67 | 1211.41 | 7455.32
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 8666.73 | 742.7 | 1954.11 | 6712.62
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 8666.73 | 97.69 | 2051.8 | 6614.93
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 8666.73 | 679.3 | 2731.1 | 5935.63
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 8666.73 | 79.04 | 2810.14 | 5856.59
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8666.73 | 633.8 | 3443.94 | 5222.79
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 8666.73 | 80.48 | 3524.42 | 5142.31
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 8666.73 | 608.6 | 4133.02 | 4533.71
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 8666.73 | 20.17 | 4153.19 | 4513.54
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 8666.73 | 149.6 | 4302.79 | 4363.94
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 8666.73 | 45.68 | 4348.47 | 4318.26
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 8666.73 | 399.6 | 4748.07 | 3918.66
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 8666.73 | 69.18 | 4817.25 | 3849.48
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 8666.73 | 348.9 | 5166.15 | 3500.58
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 8666.73 | 56.6 | 5222.75 | 3443.98
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 8666.73 | 426.8 | 5649.55 | 3017.18
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 8666.73 | 16.18 | 5665.73 | 3001
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 8666.73 | 144.3 | 5810.03 | 2856.7
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8666.73 | 157.58 | 5967.61 | 2699.12
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8666.73 | 1303.5 | 7271.11 | 1395.62
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8666.73 | 47.61 | 7318.72 | 1348.01
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8666.73 | 437.9 | 7756.62 | 910.11
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 8666.73 | 76.31 | 7832.93 | 833.8
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 8666.73 | 833.8 | 8666.73 | 0
[5 empty] | 8666.73 |  | 8666.73 | 0
[5 empty] | 8666.73 |  | 8666.73 | 0
[5 empty] | 8666.73 |  | 8666.73 | 0
|  |  | Totals: | 8666.73 |  | 8666.73 |  | 0
Note on E9: Jurgenson, John [DAS]: PM Time Inbox Trower, James 4:09 PM (0 minutes ago) to me Finance - See below PM Time modifications and please make the modifications to my billing file for month of July 2023 9320.00 - DOC NCCF Powerhouse Window Replacement Please setup $6,000 in PM Time (MM23) 9352.00 - HSS ANK IMEO Expansion Please setup $8,000 in PM Time (DA23) 9320.00 - DOC NCCF Powerhouse Window Replacement $Joni Trower, James Thu, May 2, 5:45 PM (14 hours ago) to me Finance - Project 9320.00: Please increase MM23 PM Time by $3,000. Return $60,000 in MM23 funds to the MM23 Pool fund

## #9320.00 Misc
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524216802 | 2023-07-31 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV031663 | 86 | 86
IET DAS202403115300001 | 2023-10-08 | 2325 |  | Purchasing Adminstration Fee |  | 0.86 | 86.86
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 110 | 196.86
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 82.5 | 279.36
GAX 33524023800 | 2024-01-23 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2528839 | 1265 | 1544.36
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 302.5 | 1846.86
IET DAS202410115300001 | 2024-05-07 | 2325 |  | Purchasing Adminstration Fee | DAS2024101153 | -0.86 | 1846
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -495 | 1351
1351
1351
1351
1351
|  |  |  | Totals: |  | 1351

## #9320.00 MA Architecture
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  | Major Program 4B01
MA Architecture |  |  | Vendor:00003166868
Acct. Codes-0017-335-MM23-9260 |  |  | TSB
Project Manager - James T. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524251801 | 2023-09-08 | PO Procore | 24335 | 24335 |  |  | 24335
PRC 3352425PA1801 | 2023-11-28 | Inv. 1102 |  | 24335 | 15260 | 15260 | 9075
PRC 3352425PB1801 | 2024-05-09 | Inv. 1103 |  | 24335 | 7701 | 22961 | 1374
PRC 3352425PC1801 | 2024-07-11 | Inv. 2021 |  | 24335 | 1374 | 24335 | 0
CW0712247314731125 | 2025-01-14 | Canceled missing warrant 79147911 |  | 24335 | -1374 | 22961 | 1374
GAXN33525029901 | 2025-01-29 | Reissue of warrant 73147911 |  | 24335 | 1374 | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  |  |  | 24335 |  | 24335 | 0
|  | Totals: | 24335 |  | 24335 |  | 0 | FINAL
|  | Pre-Design | 1770 |  | 1770 |  | 0
|  | Design Development | 4705 |  | 4705 |  | 0
|  | Construction Documents | 8785 |  | 8785 |  | 0
|  | Bidding Assistance | 2205 |  | 2205 |  | 0
|  | Construction Adminstration | 6870 |  | 6870 |  | 0
|  | Totals: | 24335 |  | 24335 |  | 0

## #9320.00 McGough Constructi (2)
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  | Major Program 4B01
McGough Construction #101031.004CA |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524030801 | 2024-01-30 | PO Procore | 18232.13 | 18232.13 |  |  | 18232.13
PRC 3352403PA0801 | 2024-03-18 | Inv. 101031.004-PC1 |  | 18232.13 | 2153.76 | 2153.76 | 16078.37
PRC 3352403PB0801 | 2024-04-08 | Inv. 101031.004CA-02 |  | 18232.13 | 3408.91 | 5562.67 | 12669.46
PRC 3352403PC0801 | 2024-05-10 | Inv. 101031.004CA#03 |  | 18232.13 | 3434.14 | 8996.81 | 9235.32
PRC 3352403PD0801 | 2024-06-12 | Inv. 101031.004CA-04 |  | 18232.13 | 6775.2 | 15772.01 | 2460.12
PRC 3352403PE0801 | 2024-07-12 | Inv. 101031.004CA-05 |  | 18232.13 | 1182.82 | 16954.83 | 1277.3 | FY24
PO 33525030801 | 2024-07-24 | Roll to FY25 |  | 18232.13 |  | 16954.83 | 1277.3
PRC 3352503PF0801 | 2024-08-15 | Inv. 101031.004CA-06-Final | -1001.02 | 17231.11 | 276.28 | 17231.11 | 0
|  |  |  | 17231.11 |  | 17231.11 | 0
|  |  |  | 17231.11 |  | 17231.11 | 0
|  |  |  | 17231.11 |  | 17231.11 | 0
|  |  |  | 17231.11 |  | 17231.11 | 0
|  |  |  | 17231.11 |  | 17231.11 | 0
|  | Totals: | 17231.11 |  | 17231.11 |  | 0 | Final
|  | CM Services | 16631.11 |  | 16631.11 |  | 0
|  | Reimbursables | 600 |  | 600 |  | 0
|  | Totals: | 17231.11 |  | 17231.11 |  | 0

## #9320.00 Boone Glass Co
DOC NCCF Powerhouse Window Replacement
Project # 9320.00
Program code 932000 |  |  | Major Program 4B01
Boone Glass Company |  |  | Vendor:00002114218
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ932000-01
Project Manager - James T. |  |  | Activity code: Brum
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524038910 | 2024-02-07 | PO Procore | 61270 | 61270 |  |  | 61270
PRC 3352403PA8910 | 2024-06-13 | Inv. Pay App #1 |  | 61270 | 57256.5 | 57256.5 | 4013.5 | 3013.5
PRC 3352403PB8910 | 2024-07-19 | Inv. Pay App #2 |  | 61270 | 950 | 58206.5 | 3063.5 | 3063.5
PRC 3352403PC8910 | 2024-07-25 | Inv. Pay App #3-Retainage |  | 61270 | 3063.5 | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  |  |  | 61270 |  | 61270 | 0
|  | Totals: | 61270 |  | 61270 |  | 0

## RECAP #9321.00
DVA IVH North Parking Lot Replacement
Project # 9321.00
| Program code 932100 |  |  | Major Program 4B03
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 629026.44
C | DCI Group |  | 17469 | 17469 | 0
C | PM TIME |  | 16801.94 | 16801.94 | 0
C | Misc. |  | 125.79 | 125.79 | 0
C | Bolton & Menk, Inc. |  | 26013 | 26013 | 0
C | Des Moines Asphalt |  | 534995.35 | 534995.35 | 0
C | DCI Group (2) |  | 33621.36 | 33621.36 | 0
| Total Project Cost | 629026.44 | 629026.44 | 629026.44 | 0 | 0
Closed 10/05/23

## #9321.00 DCI Group
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523320900 | 2022-11-15 | PO Procore | 17352.27 | 17352.27 |  |  | 17352.27
PRC 3352332PA0900 | 2023-01-17 | Inv. 22-040-01 |  | 17352.27 | 7777.69 | 7777.69 | 9574.58
PRC 3352332PB0900 | 2023-03-15 | Inv. 22-040-02 |  | 17352.27 | 4210.41 | 11988.1 | 5364.17
PO 33523320900 | 2023-04-17 | CO #1 | 3585.21 | 20937.48 |  | 11988.1 | 8949.38
PRC 3352332PC0900 | 2023-04-26 | Inv. 22-040 PC-03 FINAL | -3468.48 | 17469 | 5480.9 | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  |  |  | 17469 |  | 17469 | 0
|  | Totals: | 17469 |  | 17469 |  | 0 | FINAL
|  | CM Services | 9852.27 |  | 9852.27 |  | 0
|  | Reimbursables | 4088 |  | 4088 |  | 0
|  | CO #1 | 3528.73 |  | 3528.73 |  | 0
|  | Totals: | 17469 |  | 17469 |  | 0

## #9321.00 PM TIME
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E246
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15668.6 | 15668.6 |  |  | 15668.6
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 15668.6 | 27.5 | 27.5 | 15641.1
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 15668.6 | 770 | 797.5 | 14871.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 31.13 | 15699.73 | 31.13 | 828.63 | 14871.1
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 682.65 | 16382.38 | 682.65 | 1511.28 | 14871.1
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16382.38 | 1745.38 | 3256.66 | 13125.72
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16382.38 | 109.2 | 3365.86 | 13016.52
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16382.38 | 957.32 | 4323.18 | 12059.2
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 3.79 | 16386.17 | 3.79 | 4326.97 | 12059.2
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 154.65 | 16540.82 | 154.65 | 4481.62 | 12059.2
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 261.12 | 16801.94 | 261.12 | 4742.74 | 12059.2
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 16801.94 | 260.73 | 5003.47 | 11798.47
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 16801.94 | 1581.08 | 6584.55 | 10217.39
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 16801.94 | 273.25 | 6857.8 | 9944.14
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 16801.94 | 1201.88 | 8059.68 | 8742.26
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 16801.94 | 243.78 | 8303.46 | 8498.48
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 16801.94 | 1433 | 9736.46 | 7065.48
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 16801.94 | 393.56 | 10130.02 | 6671.92
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 16801.94 | 2759.9 | 12889.92 | 3912.02
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 16801.94 | 192.23 | 13082.15 | 3719.79
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 16801.94 | 1537.2 | 14619.35 | 2182.59
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 16801.94 | 98.79 | 14718.14 | 2083.8
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 16801.94 | 629.1 | 15347.24 | 1454.7
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 16801.94 | 221.2 | 15568.44 | 1233.5
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 16801.94 | 1233.5 | 16801.94 | 0
|  |  | Totals: | 16801.94 |  | 16801.94 |  | 0
Note on E9: Huggins, Joni [DAS]: Setup - PM Time Budgets on New Projects $Joni Tonyan, Brad 2:17 PM (13 minutes ago) to me, Scott, Brad Finance, Please set up the following PM time budgets below as these are new projects: 9255.00 - DOC NCF Building K (Admin) and CRC Boiler and Dorms 1 &2 Roof Replacement - $25,000 9319.00 - DOC NCF Building H (Main Server) and Master Control HVAC Replacement - $8,500 9321.00 - DVA IVH North Parking Lot Replacement - $17,000 9324.00 - DOC NCF Generator Switchgear Controls Replacement - $8,500 Thank you and please let me know once completed. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Fwd: DVA IVH North Parking Lot Replacement: Action Required for Contract #MISC-9321.00-006: Miscellaneous - DAS Costs - PM Time $John Tonyan, Brad 10:23 AM (6 minutes ago) to me, Scott, Brad Finance, I am doing a final balancing PM time change order and invoice that is a "dummy" invoice to put DAS financials into Procore to match. If you could please close the PM time final financials in Project 9321.00 under MM23 and return the remaining unspent funds to the project unspent funds under MM23. The retainage invoice for the contractor and final for DCI Group shall be forthcoming this week and then we can close out the project of which I will email as well. Thank you

## #9321.00 Misc
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  |  | Major Program 4B03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33523087900 | 2023-03-27 | 9500 | CNST | Beeline&Blue (V#00002108204) | Inv. INVO28472 | 125.79 | 125.79
125.79
125.79
125.79
125.79
125.79
125.79
125.79
125.79
125.79
125.79
125.79
|  |  |  | Totals: |  | 125.79

## #9321.00 Bolton & Menk, Inc
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  | Major Program 4B03
Bolton & Menk, Inc. |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM23-9260 |  |  | RFP/B#: RFP932100-00
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523347802 | 2022-12-13 | PO Procore | 26013 | 26013 |  |  | 26013
PRC 3352334PA7802 | 2023-02-07 | Inv. 0305105 |  | 26013 | 1849.5 | 1849.5 | 24163.5
PRC 3352334PB7802 | 2023-03-15 | Inv. 0307625 |  | 26013 | 13989.5 | 15839 | 10174
PRC 3352334PC7802 | 2023-04-10 | Inv. 0309568 |  | 26013 | 2061 | 17900 | 8113
PRC 3352334PD7802 | 2023-05-05 | Inv. 0310486 |  | 26013 | 687 | 18587 | 7426
PRC 3352334PE7802 | 2023-06-05 | Inv. 0312901 |  | 26013 | 1856.5 | 20443.5 | 5569.5 | FY23
PO 33524347802 | 2023-07-25 | Rolled to FY24 | 0 | 26013 |  | 20443.5 | 5569.5
PRC 3352434PF7802 | 2023-08-28 | Inv. 0314299 - FINAL |  | 26013 | 5569.5 | 26013 | 0
|  |  |  | 26013 |  | 26013 | 0
|  |  |  | 26013 |  | 26013 | 0
|  |  |  | 26013 |  | 26013 | 0
|  |  |  | 26013 |  | 26013 | 0
|  |  |  | 26013 |  | 26013 | 0
|  | Totals: | 26013 |  | 26013 |  | 0 | FINAL
|  | Design Development Documents | 7398 |  | 7398 |  | 0
|  | Construction Documents | 8441 |  | 8441 |  | 0
|  | Bidding | 2748 |  | 2748 |  | 0
|  | Construction Phase | 7426 |  | 7426 |  | 0
|  | Totals: | 26013 |  | 26013 |  | 0

## #9321.00 Des Moines Asphalt
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  | Major Program 4B03
Des Moines Asphalt/ OMG Midwest |  |  | Vendor: 00002116001 00003100449
Acct. Codes-0017-335-MM23-9255 |  |  | RFB932100-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523089804 | 2023-03-30 | PO Procore | 445429.9 | 445429.9 |  |  | 445429.9
PO 33523089804 | 2023-05-18 | CO #1 | 89565.45 | 534995.35 |  | 0 | 534995.35
PRC 3352308PA9804 | 2023-06-30 | Inv. 9321.00-01 |  | 534995.35 | 504013.99 | 504013.99 | 30981.36 | 26527.07 | FY23
PO 33524089804 | 2023-08-18 | Roll to FY24 | 0 | 534995.35 |  | 504013.99 | 30981.36
PRC 3352408PB9804 | 2023-08-24 | Inv. 9321.00-02 |  | 534995.35 | 4231.58 | 508245.57 | 26749.78 | 26749.78
PRC 3352408PC9804 | 2023-09-19 | Inv. 9321.00-03-Retainage |  | 534995.35 | 26749.78 | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  |  |  | 534995.35 |  | 534995.35 | 0
|  | Totals: | 534995.35 |  | 534995.35 |  | 0 | FINAL

## #9321.00 DCI Group (2)
DVA IVH North Parking Lot Replacement
Project # 9321.00
Program code 932100 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523095900 | 2023-04-05 | PO Procore | 37803.4 | 37803.4 |  |  | 37803.4
PRC 3352309PA5900 | 2023-06-22 | Inv. 22-040 CA-01 |  | 37803.4 | 27146.72 | 27146.72 | 10656.68
PRC 3352309PB5900 | 2023-07-13 | Inv. 22-040 CA-02 |  | 37803.4 | 3636.06 | 30782.78 | 7020.62 | FY23
PO 33524095900 | 2023-08-18 | Roll to FY24 | 0 | 37803.4 |  | 30782.78 | 7020.62
PRC 3352409PC5900 | 2023-10-04 | Inv. 22-040 CA-03 FINAL | -4182.04 | 33621.36 | 2838.58 | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  |  |  | 33621.36 |  | 33621.36 | 0
|  | Totals: | 33621.36 |  | 33621.36 |  | 0 | FINAL
|  | CM Services | 31010.87 |  | 31010.87 |  | 0
|  | Reimbursables | 2610.49 |  | 2610.49 |  | 0
|  | Totals: | 33621.36 |  | 33621.36 |  | 0

## RECAP #9322.00
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
| Program code 932200 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1023889.75
C | Samuels Group |  | 18255.76 | 18255.76 | 0
C | PM TIME |  | 16244.13 | 16244.13 | 0
C | Misc. |  | 2844.63 | 2844.63 | 0
C | Genesis Architectural |  | 31500 | 31500 | 0
C | Samuels Group 140 CA |  | 121268.68 | 121268.68 | 0
C | Black Hawk Roof Company |  | 819672.97 | 819672.97 | 0
C | Controlled Asbestos |  | 14103.58 | 14103.58 | 0
| Total Project Cost | 1023889.75 | 1023889.75 | 1023889.75 | 0 | 0
Closed 12/09/24

## #9322.00 Samuels Group
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  | Major Program 4B02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523334901 | 2022-11-30 | PO Procore | 18391.8 | 18391.8 |  |  | 18391.8
PRC 3352333PA4901 | 2023-02-06 | Inv. 9322.10 |  | 18391.8 | 3860.32 | 3860.32 | 14531.48
PRC 3352333PB4901 | 2023-03-04 | Inv. 9322.11 |  | 18391.8 | 2567.67 | 6427.99 | 11963.81
PRC 3352333PB4901A | 2023-03-08 | Inv. 9322.11A |  | 18391.8 | 9 | 6436.99 | 11954.81
PO 33523334901 | 2023-03-10 | CO #1 (No Cost) | 0 | 18391.8 |  | 6436.99 | 11954.81
PRC 3352333PC4901 | 2023-04-06 | Inv. 9322.12 |  | 18391.8 | 4418.23 | 10855.22 | 7536.58
PRC 3352333PD4901 | 2023-05-05 | Inv. 9322.13 |  | 18391.8 | 4418.23 | 15273.45 | 3118.35
PRC 3352333PE4901 | 2023-06-21 | Inv. 9322.14 FINAL | -136.04 | 18255.76 | 2982.31 | 18255.76 | 0
|  |  |  | 18255.76 |  | 18255.76 | 0
|  |  |  | 18255.76 |  | 18255.76 | 0
|  |  |  | 18255.76 |  | 18255.76 | 0
|  |  |  | 18255.76 |  | 18255.76 | 0
|  |  |  | 18255.76 |  | 18255.76 | 0
|  | Totals: | 18255.76 |  | 18255.76 |  | 0 | FINAL
|  | CM Services | 17790.76 |  | 17790.76 |  | 0
|  | Reimbursables | 465 |  | 465 |  | 0
|  | Total: | 18255.76 |  | 18255.76 |  | 0

## #9322.00 PM TIME
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E247
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15999.23 | 15999.23 |  |  | 15999.23
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 15999.23 | 165 | 165 | 15834.23
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 132.36 | 16131.59 | 132.36 | 297.36 | 15834.23
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16131.59 | 540.61 | 837.97 | 15293.62
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16131.59 | 323.2 | 1161.17 | 14970.42
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16131.59 | 2833.47 | 3994.64 | 12136.95
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 31.66 | 16163.25 | 31.66 | 4026.3 | 12136.95
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 80.88 | 16244.13 | 80.88 | 4107.18 | 12136.95
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 16244.13 | 159.76 | 4266.94 | 11977.19
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 16244.13 | 968.85 | 5235.79 | 11008.34
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 16244.13 | 156.87 | 5392.66 | 10851.47
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 16244.13 | 689.96 | 6082.62 | 10161.51
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 16244.13 | 253.1 | 6335.72 | 9908.41
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 16244.13 | 1487.6 | 7823.32 | 8420.81
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 16244.13 | 39.57 | 7862.89 | 8381.24
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 16244.13 | 277.2 | 8140.09 | 8104.04
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 16244.13 | 92.3 | 8232.39 | 8011.74
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 16244.13 | 813.5 | 9045.89 | 7198.24
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 16244.13 | 30.33 | 9076.22 | 7167.91
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 16244.13 | 193.7 | 9269.92 | 6974.21
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 16244.13 | 31.6 | 9301.52 | 6942.61
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 16244.13 | 176 | 9477.52 | 6766.61
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 16244.13 | 30.33 | 9507.85 | 6736.28
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 16244.13 | 211.1 | 9718.95 | 6525.18
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 16244.13 | 75.57 | 9794.52 | 6449.61
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 16244.13 | 605.9 | 10400.42 | 5843.71
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 16244.13 | 66.84 | 10467.26 | 5776.87
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 16244.13 | 506 | 10973.26 | 5270.87
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 16244.13 | 67.03 | 11040.29 | 5203.84
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 16244.13 | 493.2 | 11533.49 | 4710.64
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 16244.13 | 67.21 | 11600.7 | 4643.43
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 16244.13 | 595.6 | 12196.3 | 4047.83
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 16244.13 | 74.35 | 12270.65 | 3973.48
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 16244.13 | 376.2 | 12646.85 | 3597.28
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 16244.13 | 106.26 | 12753.11 | 3491.02
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 16244.13 | 805 | 13558.11 | 2686.02
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 16244.13 | 40.31 | 13598.42 | 2645.71
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 16244.13 | 358.5 | 13956.92 | 2287.21
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 16244.13 | 65.88 | 14022.8 | 2221.33
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 16244.13 | 545.2 | 14568 | 1676.13
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 16244.13 | 23.94 | 14591.94 | 1652.19
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 16244.13 | 120.7 | 14712.64 | 1531.49
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 16244.13 | 82.7 | 14795.34 | 1448.79
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 16244.13 | 741 | 15536.34 | 707.79
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 16244.13 | 92.19 | 15628.53 | 615.6
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 16244.13 | 615.6 | 16244.13 | 0
[5 empty] | 16244.13 |  | 16244.13 | 0
|  |  | Totals: | 16244.13 |  | 16244.13 |  | 0
Note on E9: Huggins, Joni [DAS]: 9322.00 MM23 Inbox Carper, Douglas 10:06 AM (43 minutes ago) to DAS, me Please set the PM Time budget to $16,500.00. Thanks. Sincerely, Doug Douglas L. Carper, PE, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-745-3244 douglas.carper@iowa.gov https://das.iowa.gov 9322.00 - HHS IMHI Reynolds Building Partial Roof Replacement - CloseOut $Joni Elliott, Jennie Dec 8, 2024, 10:09 AM (22 hours ago) to me, Scott Please reduce PM time to $16,244.13 and Close Out this project. This should return $76,355.15 to the Total Unassigned/Unallocated line in MM23. Thank you, Jennie Elliott

## #9322.00 Misc
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523123804 | 2023-05-03 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2495182 | 2660 | 2660
PRC 33523156901 | 2023-06-01 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV030079 | 184.63 | 2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
2844.63
|  |  |  | Totals: |  | 2844.63

## #9322.00 Genesis Architectural
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  | Major Program 4B02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP932200-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523038901 | 2023-02-07 | PO Procore | 31500 | 31500 |  |  | 31500
PRC 3352303PA8901 | 2023-03-01 | Inv. 2304-01 |  | 31500 | 3000 | 3000 | 28500
PRC 3352303PB8901 | 2023-03-08 | Inv. 2304-02 |  | 31500 | 4580 | 7580 | 23920
PO 33523038901 | 2023-03-10 | CO #1 (No Cost) | 0 | 31500 |  | 7580 | 23920
PRC 3352303PC8901 | 2023-04-19 | Inv. 2304-03 |  | 31500 | 5530 | 13110 | 18390
PRC 3352303PD8901 | 2023-06-12 | Inv. 2304-04 |  | 31500 | 3040 | 16150 | 15350
PRC 3352303PE8901 | 2023-06-30 | Inv. 2304-05 |  | 31500 | 307 | 16457 | 15043 | FY23
PO 33524038901 | 2023-07-25 | Rolled to FY24 | 0 | 31500 |  | 16457 | 15043
PRC 3352403PF8901 | 2023-08-10 | Inv. 2304-06 |  | 31500 | 460.5 | 16917.5 | 14582.5
PRC 3352403PG8901 | 2023-12-04 | Inv. 2304-07 |  | 31500 | 1535 | 18452.5 | 13047.5
PRC 3352403PH8901 | 2024-02-21 | Inv. 2304-08 |  | 31500 | 1688.5 | 20141 | 11359
PRC 3352403PI8901 | 2024-04-05 | Inv. 2304-09 |  | 31500 | 1381.5 | 21522.5 | 9977.5
PRC 3352403PJ8901 | 2024-06-11 | Inv. 2304-10 |  | 31500 | 8442.5 | 29965 | 1535
PRC 3352403PK8901 | 2024-07-11 | Inv. 2304-11 FINAL |  | 31500 | 1535 | 31500 | 0
|  |  |  | 31500 |  | 31500 | 0
|  | Totals: | 31500 |  | 31500 |  | 0 | FINAL
|  | Design Development Phase | 6000 |  | 6000 |  | 0
|  | Construction Documents | 7900 |  | 7900 |  | 0
|  | Bid Phase | 2250 |  | 2250 |  | 0
|  | Construction Phase | 15350 |  | 15350 |  | 0
|  | Total: | 31500 |  | 31500 |  | 0

## #9322.00 Samuels Group 140 CA
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  | Major Program 4B02
Samuels Group 140 CA |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523145802 | 2023-05-25 | PO Procore | 129199.64 | 129199.64 |  |  | 129199.64
PRC 3352314PA5802 | 2023-07-07 | Inv. 9322.50 CA |  | 129199.64 | 2031.07 | 2031.07 | 127168.57 | FY23
PO 33524145802 | 2023-07-25 | Rolled to FY24 | 0 | 129199.64 |  | 2031.07 | 127168.57
PRC 3352414PB5802 | 2023-08-11 | Inv. 9322.51CA |  | 129199.64 | 2648.03 | 4679.1 | 124520.54
PRC 3352414PC5802 | 2023-09-18 | Inv. 9322.52 CA |  | 129199.64 | 2175.23 | 6854.33 | 122345.31
PRC 3352414PD5802 | 2023-10-06 | Inv. 9322.53 CA |  | 129199.64 | 3254.58 | 10108.91 | 119090.73
PRC 3352414PE5802 | 2023-11-21 | Inv. 9322.54 CA |  | 129199.64 | 6061.36 | 16170.27 | 113029.37
PRC 3352414PF5802 | 2023-12-12 | Inv. 9322.55 CA |  | 129199.64 | 10413.61 | 26583.88 | 102615.76
PRC 3352414PG5802 | 2024-01-04 | Inv. 9322.56 CA |  | 129199.64 | 9204.54 | 35788.42 | 93411.22
PRC 3352414PH5802 | 2024-02-12 | Inv. 9322.57 CA |  | 129199.64 | 7946.21 | 43734.63 | 85465.01
PRC 3352414PI5802 | 2024-03-18 | Inv. 9322.58 CA |  | 129199.64 | 18478.54 | 62213.17 | 66986.47
PRC 3352414PJ5802 | 2024-04-04 | Inv. 9322.59 CA |  | 129199.64 | 23170.08 | 85383.25 | 43816.39
PRC 3352414PK5802 | 2024-05-13 | Inv. 9322.60 |  | 129199.64 | 22453.1 | 107836.35 | 21363.29
PRC 3352414PL5802 | 2024-06-01 | Inv. 9322.61 |  | 129199.64 | 5622.81 | 113459.16 | 15740.48
PRC 3352414PM5802 | 2024-07-11 | Inv. 9322.62 FINAL | -7930.96 | 121268.68 | 7809.52 | 121268.68 | 0
|  | Totals: | 121268.68 |  | 121268.68 |  | 0 | FINAL
|  | CM Services | 78236.26 |  | 78236.26 |  | 0
|  | Reimbursables | 5792.42 |  | 5792.42 |  | 0
|  | Fee | 37240 |  | 37240 |  | 0
|  | Total: | 121268.68 |  | 121268.68 |  | 0

## #9322.00 Black Hawk Roof Co
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  | Major Program 4B02
Black Hawk Roof Company |  |  | Vendor: 00002120676
Acct. Codes-0017-335-MM23-9255 |  |  | RFB932200-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523157804 | 2023-06-06 | PO Procore | 744800 | 744800 |  |  | 744800 |  | FY23
PO 33524157804 | 2023-07-28 | Rolled to FY24 | 0 | 744800 |  | 0 | 744800
PRC 3352415PA7804 | 2023-12-04 | Inv. 9322.00-01 |  | 744800 | 306361.89 | 306361.89 | 438438.11 | 16124.31
PO 33524157804 | 2023-12-13 | CO #1 | 4690.5 | 749490.5 |  | 306361.89 | 443128.61
PRC 3352415PB7804 | 2024-01-03 | Inv. 9322.00-02 |  | 749490.5 | 56073.27 | 362435.16 | 387055.34 | 19075.54
PRC 3352415PC7804 | 2024-02-02 | Inv. 9322.00-03 |  | 749490.5 | 33630 | 396065.16 | 353425.34 | 20845.54
PRC 3352415PD7804 | 2024-02-29 | Inv. 9322.00-04 |  | 749490.5 | 72550.16 | 468615.32 | 280875.18 | 24663.98
PO 33524157804 | 2024-03-18 | CO #2 | 83815.27 | 833305.77 |  | 468615.32 | 364690.45
PRC 3352415PE7804 | 2024-03-27 | Inv. 9322.00-05 |  | 833305.77 | 236937.17 | 705552.49 | 127753.28 | 37134.36
PRC 3352415PF7804 | 2024-04-29 | Inv. 9322.00-06 |  | 833305.77 | 64292.3 | 769844.79 | 63460.98 | 40518.18
PO 33524157804 | 2024-06-21 | CO #3 | -13632.8 | 819672.97 |  | 769844.79 | 49828.18
PRC 3352415PG7804 | 2024-07-11 | Inv. 9322.00-07 |  | 819672.97 | 8844.5 | 778689.29 | 40983.68 | 40983.68
PRC 3352415PH7804 | 2024-07-17 | Inv. 9322.00-08-Retainage |  | 819672.97 | 40983.68 | 819672.97 | 0
|  | Totals: | 819672.97 |  | 819672.97 |  | 0

## #9322.00 Controlled Asbestos
DHS IMHI Reynolds Building Partial Roof Replacement
Project # 9322.00
Program code 932200 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA21060
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524284802 | 2023-10-11 | DO Procore | 24265.8 | 24265.8 |  |  | 24265.8
PRC 3352428PA4802 | 2023-11-07 | Inv. 0010671-IN |  | 24265.8 | 3496.48 | 3496.48 | 20769.32
DO 33524284802 | 2023-12-19 | CO #1 | 584.2 | 24850 |  | 3496.48 | 21353.52
PRC 3352428PB4802 | 2023-12-20 | Inv. 0010682-final | -10746.42 | 14103.58 | 10607.1 | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  |  |  | 14103.58 |  | 14103.58 | 0
|  | Totals: | 14103.58 |  | 14103.58 |  | 0 | FINAL
|  | Line 1 - 160 hours x $58 | 5560.2 |  | 5560.2 |  | 0
|  | Line 1 - Drive time 100 hours x $58 | 3110 |  | 3110 |  | 0
|  | Line 7 - DNR, Air Samples, Lift Rental | 3749 |  | 3749 |  | 0
|  | Line 11 - Disposal Fee | 2.7 |  | 2.7 |  | 0
|  | Line 12 - Mileage, lodging, meals | 1681.68 |  | 1681.68 |  | 0
|  | Total: | 14103.58 |  | 14103.58 |  | 0

## RECAP #9324.00
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
| Program code 932400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 254346.33
C | Boyd Jones |  | 12906.49 | 12906.49 | 0
C | PM TIME |  | 17118.73 | 17118.73 | 0
C | Misc. |  | 0 | 0 | 0
C | Innovative Engineers Inc. |  | 21735 | 21735 | 0
C | Cummins Inc. |  | 183487.85 | 183487.85 | 0
C | Boyd Jones 004CA |  | 19098.26 | 19098.26 | 0
| Total Project Cost | 254346.33 | 254346.33 | 254346.33 | 0 | 0
Closed 04/04/24

## #9324.00 Boyd Jones
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  | Major Program 4B01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523342900 | 2022-12-07 | PO Procore | 16412.5 | 16412.5 |  |  | 16412.5
PRC 3352334PA2900 | 2023-01-10 | Inv. 9324.00-01 |  | 16412.5 | 1450.87 | 1450.87 | 14961.63
PRC 3352334PB2900 | 2023-02-14 | Inv. 9324.00-02 |  | 16412.5 | 2568.98 | 4019.85 | 12392.65
PRC 3352334PC2900 | 2023-03-15 | Inv. 9324.00-03 |  | 16412.5 | 1838.24 | 5858.09 | 10554.41
PRC 3352334PD2900 | 2023-04-17 | Inv. 9324.00-04 |  | 16412.5 | 2019.09 | 7877.18 | 8535.32
PRC 3352334PE2900 | 2023-05-19 | Inv. 9324.00-05 |  | 16412.5 | 2577.67 | 10454.85 | 5957.65
PRC 3352334PF2900 | 2023-06-12 | Inv. 9324.00-06-Final | -3506.01 | 12906.49 | 2451.64 | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  |  |  | 12906.49 |  | 12906.49 | 0
|  | Totals: | 12906.49 |  | 12906.49 |  | 0 | FINAL
|  | CM Services | 12840.49 |  | 12840.49 |  | 0
|  | Reimbursables | 66 |  | 66 |  | 0
|  | Total: | 12906.49 |  | 12906.49 |  | 0

## #9324.00 PM TIME
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E249
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 16455.01 | 16455.01 |  |  | 16455.01
IET DAS202304115300001 | 2022-11-08 | 9500 | PM Time-October 1-October 31, 2022 |  | 16455.01 | 27.5 | 27.5 | 16427.51
IET DAS202305115300001 | 2022-12-07 | 9500 | PM Time-November 1-November 30, 2022 |  | 16455.01 | 440 | 467.5 | 15987.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Oct 9997.23 disbursement | 31.13 | 16486.14 | 31.13 | 498.63 | 15987.51
IET DAS202205115300001 | 2022-12-07 | 9500 | PM Time-Nov 9997.23 disbursement | 390.08 | 16876.22 | 390.08 | 888.71 | 15987.51
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 16876.22 | 1004.92 | 1893.63 | 14982.59
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 16876.22 | 119.12 | 2012.75 | 14863.47
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 16876.22 | 1044.36 | 3057.11 | 13819.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: October 1-31, 2022 | 3.79 | 16880.01 | 3.79 | 3060.9 | 13819.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: November 1-30, 2022 | 88.38 | 16968.39 | 88.38 | 3149.28 | 13819.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 | 150.34 | 17118.73 | 150.34 | 3299.62 | 13819.11
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 17118.73 | 147.08 | 3446.7 | 13672.03
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 17118.73 | 891.91 | 4338.61 | 12780.12
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 17118.73 | 123.4 | 4462.01 | 12656.72
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 17118.73 | 542.79 | 5004.8 | 12113.93
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 17118.73 | 146.65 | 5151.45 | 11967.28
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 17118.73 | 860.9 | 6012.35 | 11106.38
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 17118.73 | 162.72 | 6175.07 | 10943.66
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 17118.73 | 1139.6 | 7314.67 | 9804.06
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 17118.73 | 118.98 | 7433.65 | 9685.08
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 17118.73 | 994.4 | 8428.05 | 8690.68
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 17118.73 | 98.79 | 8526.84 | 8591.89
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 17118.73 | 629.1 | 9155.94 | 7962.79
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 17118.73 | 158 | 9313.94 | 7804.79
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 17118.73 | 881 | 10194.94 | 6923.79
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 17118.73 | 128.02 | 10322.96 | 6795.77
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 17118.73 | 890.4 | 11213.36 | 5905.37
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 17118.73 | 135.56 | 11348.92 | 5769.81
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 17118.73 | 1088.9 | 12437.82 | 4680.91
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 17118.73 | 181.03 | 12618.85 | 4499.88
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 17118.73 | 1366.8 | 13985.65 | 3133.08
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 17118.73 | 204.56 | 14190.21 | 2928.52
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 17118.73 | 1504.3 | 15694.51 | 1424.22
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 17118.73 | 84.84 | 15779.35 | 1339.38
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 17118.73 | 744.6 | 16523.95 | 594.78
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 17118.73 | 98.48 | 16622.43 | 496.3
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 17118.73 | 496.3 | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
[5 empty] | 17118.73 |  | 17118.73 | -3.5811e-12
|  |  | Totals: | 17118.73 |  | 17118.73 |  | 0
Note on E9: Huggins, Joni [DAS]: Setup - PM Time Budgets on New Projects $Joni Tonyan, Brad 2:17 PM (13 minutes ago) to me, Scott, Brad Finance, Please set up the following PM time budgets below as these are new projects: 9255.00 - DOC NCF Building K (Admin) and CRC Boiler and Dorms 1 &2 Roof Replacement - $25,000 9319.00 - DOC NCF Building H (Main Server) and Master Control HVAC Replacement - $8,500 9321.00 - DVA IVH North Parking Lot Replacement - $17,000 9324.00 - DOC NCF Generator Switchgear Controls Replacement - $8,500 Thank you and please let me know once completed. Brad Tonyan, CPM, LEED Green Associate, Owner Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-360-7718 brad.tonyan@iowa.gov https://das.iowa.gov Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K Re: PM Time $John Tonyan, Brad 2:13 PM (15 minutes ago) to me, John John, Please increase the exact amount needed to post for each project. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov On Tue, Jan 9, 2024 at 2:12 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Brad I need specific amounts that you need each to be increased by for our audit...unless you are wanting each project increased by the exact amount i need to post? John On Tue, Jan 9, 2024 at 12:35 PM Tonyan, Brad <brad.tonyan@iowa.gov> wrote: John and Finance, Please increase the PM time as needed from the project's contingency funds to cover for the following. DA21 9172.00 Amt. $654.50 MM22 9272.00 Amt. $748.00 MM23 9255.00 Amt. $513.70 MM23 9310.00 Amt. $981.20 MM23 9324.00 Amt. $1449.80 Thank you, Re: PM Time Inbox Tonyan, Brad 2:58 PM (6 minutes ago) to DAS, me, Brad John and Finance, 9172.00 DA21 Amount to post 625.90 Brad update - Please raise total PM time budget to $60K 9242.00 DA22 Amount to post 751.30 Brad update - Please raise total PM time budget to $38K 9282.00 DA22 Amount to post 284.68 Brad update - Please increase only to cover this amount and stop charging edas time to DA22 and instead charge time to MM24 9282.00 org. 9291.00 MM22 Amount to post 1211.10 Brad update - Please raise total PM time budget to $25K 9324.00 MM23 Amount to post 459.80 Brad update - Please raise total PM time budget to $18K

## #9324.00 Misc
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9324.00 Innovative Engineers
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  | Major Program 4B01
Innovative Engineers Inc. |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM23-9260 |  |  | RFP932400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523030800 | 2023-01-30 | PO Procore | 21735 | 21735 |  |  | 21735
PRC 3352303PA0800 | 2023-05-19 | Inv. 9324.00-01 |  | 21735 | 11190 | 11190 | 10545 | FY23
PO 33524030800 | 2023-07-25 | Rolled to FY24 | 0 | 21735 |  | 11190 | 10545
PRC 3352403PB0800 | 2024-03-29 | Inv. 9324.00-02 - Final |  | 21735 | 10545 | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  |  |  | 21735 |  | 21735 | 0
|  | Totals: | 21735 |  | 21735 |  | 0
|  | Design Development Documents | 7165 |  | 7165 |  | 0
|  | Construction Documents | 8050 |  | 8050 |  | 0
|  | Bidding or Negotiation Assistance | 1545 |  | 1545 |  | 0
|  | Construction Phase | 3785 |  | 3785 |  | 0
|  | Closeout Phase | 1190 |  | 1190 |  | 0
|  | Total: | 21735 |  | 21735 |  | 0

## #9324.00 Cummins Inc.
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  | Major Program 4B01
Cummins Inc. |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM23-9255 |  |  | MA-23133
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523066800 | 2023-03-07 | PO Procore | 102340 | 102340 |  |  | 102340
PO 33523066800 | 2023-06-21 | CO #1 | 81150 | 183490 |  | 0 | 183490 |  | FY23
PO 33524066800 | 2023-07-25 | Rolled to FY24 | 0 | 183490 |  | 0 | 183490
PRC 3352406PA6800 | 2023-10-19 | Inv. E3-42331 |  | 183490 | 72166.75 | 72166.75 | 111323.25 | 3798.25
PRC 3352406PB6800 | 2023-12-27 | Inv. E3-44409 |  | 183490 | 99358 | 171524.75 | 11965.25 | 9027.62
PRC 3352406PC6800 | 2024-03-25 | Inv. E3-49507 |  | 183490 | 2788.71 | 174313.46 | 9176.54 | 9174.39
PRC 3352406PD6800 | 2024-04-02 | Inv. 9324.00-04 - Retainage | -2.15 | 183487.85 | 9174.39 | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  |  |  | 183487.85 |  | 183487.85 | 1.4553e-12
|  | Totals: | 183487.85 |  | 183487.85 |  | 0 | FINAL

## #9324.00 Boyd Jones 004CA
DOC NCF Generator Switchgear Controls Replacement
Project # 9324.00
Program code 932400 |  |  | Major Program 4B01
Boyd Jones 004CA |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523174802 | 2023-06-23 | PO Procore | 22109.95 | 22109.95 |  |  | 22109.95
PRC 3352317PA4802 | 2023-07-20 | Inv. 9324.00-001 |  | 22109.95 | 1048.44 | 1048.44 | 21061.51 | FY23
PO 33524174802 | 2023-07-25 | Rolled to FY24 | 0 | 22109.95 |  | 1048.44 | 21061.51
PRC 3352417PB4802 | 2023-10-12 | Inv. 9324.00-002 |  | 22109.95 | 2556.22 | 3604.66 | 18505.29
PRC 3352417PC4802 | 2023-11-15 | Inv. 9324.00-003 |  | 22109.95 | 3878.7 | 7483.36 | 14626.59
PRC 3352417PD4802 | 2023-12-13 | Inv. 9324.00-004 |  | 22109.95 | 5322.53 | 12805.89 | 9304.06
PRC 3352417PE4802 | 2024-01-22 | Inv. 9324.00-005 |  | 22109.95 | 2528.17 | 15334.06 | 6775.89
PRC 3352417PF4802 | 2024-02-29 | Inv. 9324.00-006 |  | 22109.95 | 1139.62 | 16473.68 | 5636.27
PRC 3352417PG4802 | 2024-03-29 | Inv. 9324.00-007 - Final | -3011.69 | 19098.26 | 2624.58 | 19098.26 | 0
|  |  |  | 19098.26 |  | 19098.26 | 0
|  |  |  | 19098.26 |  | 19098.26 | 0
|  |  |  | 19098.26 |  | 19098.26 | 0
|  |  |  | 19098.26 |  | 19098.26 | 0
|  | Totals: | 19098.26 |  | 19098.26 |  | 0 | FINAL
|  | CM Services | 19054.26 |  | 19054.26 |  | 0
|  | Reimbursables | 44 |  | 44 |  | 0
|  | Total: | 19098.26 |  | 19098.26 |  | 0
Inv # 9324.00-07 Was used in a previous tab by this vendor

## RECAP #9327.00
DOC IMCC East/West Living Unit Roof Replacement and Soffit Repair
Project # 9327.00
| Program code 932700 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 5997.36
C | Samuels Group |  | 2172.23 | 2172.23 | 0
C | PM TIME |  | 2765.13 | 2765.13 | 0
C | Misc. |  | 1060 | 1060 | 0
| Total Project Cost | 5997.36 | 5997.36 | 5997.36 | 0 | 0
Closed 01/23/2023

## #9327.00 Samuels Group
DOC IMCC East/West Living Unit Roof Replacement and Soffit Repair
Project # 9327.00
Program code 932700 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523307905 | 2022-11-02 | PO Procore | 17472.76 | 17472.76 |  |  | 17472.76
PRC 3352330PA7905 | 2022-12-20 | Inv. 7453.10 PC FINAL | -15300.53 | 2172.23 | 2172.23 | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  |  |  | 2172.23 |  | 2172.23 | 0
|  | Totals: | 2172.23 |  | 2172.23 |  | 0 | FINAL
|  | CM Srvices | 2055.23 |  | 2055.23 |  | 0
|  | Reimbursables | 117 |  | 117 |  | 0
|  | Totals: | 2172.23 |  | 2172.23 |  | 0

## #9327.00 PM TIME
DOC IMCC East/West Living Unit Roof Replacement and Soffit Repair
Project # 9327.00
Program code 932700 |  |  | Major Program 4B01
PM TIME |  |  | Internal documents
PM TIME = 9500
Acct. Codes-0017-335-MM23-xxxx |  |  | eDAS E24C
Project Manager - Jennifer K.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 1568.12 | 1568.12 |  |  | 1568.12
IET DAS202304115300001 | 2022-11-08 | PM Time-October 1-October 31, 2022 |  | 1568.12 | 192.5 | 192.5 | 1375.62
IET DAS202305115300001 | 2022-12-07 | PM Time-November 1-November 30, 2022 |  | 1568.12 | 1045 | 1237.5 | 330.62
IET DAS202205115300001 | 2022-12-07 | PM Time-Oct 9997.23 disbursement | 151.33 | 1719.45 | 151.33 | 1388.83 | 330.62
IET DAS202205115300001 | 2022-12-07 | PM Time-Nov 9997.23 disbursement | 1045.68 | 2765.13 | 1045.68 | 2434.51 | 330.62
IET DAS202306115300001 | 2023-01-09 | PM Time-December 1-December 31, 2022 |  | 2765.13 | 330.62 | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  |  |  | 2765.13 |  | 2765.13 | 0
|  | Totals: | 2765.13 |  | 2765.13 |  | 0
Note on D9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Tue, Nov 1, 11:31 AM (2 days ago) to me Please create the following PM Time Budgets: 9253.00 $11,000.00 9325.00 $5,280.00 9326.00 $4,400.00 9327.00 $11,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9327.00 Misc
DOC IMCC East/West Living Unit Roof Replacement and Soffit Repair
Project # 9327.00
Program code 932700 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523343805 | 2022-12-09 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2470873 - Final | 1060 | 1060
1060
1060
1060
1060
1060
1060
1060
1060
1060
1060
1060
|  |  |  | Totals: |  | 1060

## RECAP #9330.00
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
| Program code 933000 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 58503.51
C | DCI Group |  | 10942.02 | 10942.02 | 0
C | PM TIME |  | 12762.38 | 12762.38 | 0
C | Misc. |  | 642.25 | 642.25 | 0
C | OPN Architects |  | 14999 | 14999 | 0
C | Bergstrom |  | 8290 | 8290 | 0
C | Waldinger Corp |  | 2440.86 | 2440.86 | 0
C | DCI Group #23-001 CA |  | 8427 | 8427 | 0
| Total Project Cost | 58503.51 | 58503.51 | 58503.51 | 0 | 0
Closed 02/08/2024

## #9330.00 DCI Group
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  | Major Program 4D03
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523018801 | 2023-01-18 | PO Procore | 10984.78 | 10984.78 |  |  | 10984.78
PRC 3352301PA8801 | 2023-03-28 | Inv. 23-001 PC-01 |  | 10984.78 | 2235.85 | 2235.85 | 8748.93
PRC 3352301PB8801 | 2023-04-25 | Inv. 23-001 PC-02 |  | 10984.78 | 2892.02 | 5127.87 | 5856.91
PRC 3352301PC8801 | 2023-06-22 | Inv. 23-001 PC-03 |  | 10984.78 | 4802.02 | 9929.89 | 1054.89
PRC 3352301PD8801 | 2023-07-13 | Inv. 23-001 PC-04 FINAL | -42.76 | 10942.02 | 1012.13 | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  |  |  | 10942.02 |  | 10942.02 | -5.7554e-13
|  | Totals: | 10942.02 |  | 10942.02 |  | 0 | FINAL
|  | CM Srvices | 10942.02 |  | 10942.02 |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Fee |  |  |  |  | 0
|  | Totals: | 10942.02 |  | 10942.02 |  | 0

## #9330.00 PM TIME
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E252
Project Manager - Brad T.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12762.38 | 12762.38 |  |  | 12762.38
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 12762.38 | 370.24 | 370.24 | 12392.14
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 12762.38 | 49.64 | 419.88 | 12342.5
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 12762.38 | 435.15 | 855.03 | 11907.35
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 |  | 12762.38 | 55.39 | 910.42 | 11851.96
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 12762.38 | 80.22 | 990.64 | 11771.74
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 12762.38 | 486.49 | 1477.13 | 11285.25
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 12762.38 | 105.77 | 1582.9 | 11179.48
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 12762.38 | 465.24 | 2048.14 | 10714.24
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 12762.38 | 125.06 | 2173.2 | 10589.18
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 12762.38 | 737 | 2910.2 | 9852.18
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 12762.38 | 128.23 | 3038.43 | 9723.95
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 12762.38 | 899.8 | 3938.23 | 8824.15
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 12762.38 | 114.75 | 4052.98 | 8709.4
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 12762.38 | 970.9 | 5023.88 | 7738.5
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 12762.38 | 110.91 | 5134.79 | 7627.59
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 12762.38 | 706.6 | 5841.39 | 6920.99
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 12762.38 | 173.59 | 6014.98 | 6747.4
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 12762.38 | 969 | 6983.98 | 5778.4
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 12762.38 | 155.56 | 7139.54 | 5622.84
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 12762.38 | 1079.1 | 8218.64 | 4543.74
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 12762.38 | 148.77 | 8367.41 | 4394.97
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 12762.38 | 1192.7 | 9560.11 | 3202.27
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 12762.38 | 123.09 | 9683.2 | 3079.18
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 12762.38 | 930.1 | 10613.3 | 2149.08
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 12762.38 | 132.11 | 10745.41 | 2016.97
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 12762.38 | 971.1 | 11716.51 | 1045.87
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2023 |  | 12762.38 | 106.37 | 11822.88 | 939.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2023 |  | 12762.38 | 939.5 | 12762.38 | 4.8885e-12
[5 empty] | 12762.38 |  | 12762.38 | 4.8885e-12
[5 empty] | 12762.38 |  | 12762.38 | 4.8885e-12
[7 empty] | 12762.38 | 4.8885e-12
|  |  | Totals: | 12762.38 |  | 12762.38 |  | 0
Note on E9: Jurgenson, John [DAS]: Tonyan, Brad 10:31 AM (2 hours ago) to me, John John and finance, 9172.00 DA21 amounts to post 85.71+42.80+154.50+924.00=1207.01 Brad Response - Increase PM time budget $7,000 9234.00 MM22 amounts to post 110.19+54.94+219.50+1140.70=1525.33 Brad Response - Increase PM time budget $3,000 9246.00 MM22 amount to post 39.61+194.00+745.80=979.41 Brad Response - Increase PM time budget $979.41 and then close PM Time budget in Financials and remove from Billing log 9235.00 MM22 amount to post 48.55+241.50+910.80=1200.85 Brad Response - Increase PM time budget $1,200.85 and then close PM Time budget in Financials and remove from Billing log 9211.00 DA21 - Increase PM time budget by $1,000 9272.00 MM22 - Increase PM time budget by $5,000 9295.00 DA22 - Increase PM time budget by $6,500 9310.00 MM23 - Increase PM time budget by $6,000 9319.00 MM23 - Increase PM time budget by $5,000 9324.00 MM23 - Increase PM time budget by $4,000 9330.00 MM23 - Increase PM time budget by $4,000 Thank you and please let me know when this is completed. PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (42 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K MM23: 9306.00 - Decrease overall budget by $145,000 and give back to general org. fund MM23 9310.00 - Increase PM Time by $5K 9319.00 - Increase PM Time by $5K 9330.00 - Increase PM time as needed to pay January PM time. Once this PM time hits all financials can be closed and remaining roughly $12K can be returned to general org. fund MM23 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Represen

## #9330.00 Misc
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523188802 | 2023-07-07 | 9500 | CNST | ATC Group V# (00002134218) | Inv. 2512112-Final | 347.5 | 347.5
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Locksmith & Key Service | DAS2024051153 | 294.75 | 642.25
642.25
642.25
642.25
642.25
642.25
642.25
642.25
642.25
642.25
642.25
|  |  |  | Totals: |  | 642.25

## #9330.00 OPN Architects
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor:00003035830
Acct. Codes-0017-335-MM23-9260 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523045800 | 2023-02-14 | PO Procore | 14999 | 14999 |  |  | 14999
PRC 3352304PA5800 | 2023-07-13 | Inv. 23805000-1 |  | 14999 | 12749.15 | 12749.15 | 2249.85 | FY23
PO 33524045800 | 2023-07-25 | Rolled to FY24 | 0 | 14999 |  | 12749.15 | 2249.85
PO 33524045800 | 2023-09-26 | CO #1 (No Cost) | 0 | 14999 |  | 12749.15 | 2249.85
PRC 3352404PB5800 | 2023-10-25 | Inv. 23805000-2 |  | 14999 | 449.97 | 13199.12 | 1799.88
PRC 3352404PC5800 | 2024-01-04 | Inv. 23805000-3 - Final |  | 14999 | 1799.88 | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  |  |  | 14999 |  | 14999 | 0
|  | Totals: | 14999 |  | 14999 |  | 0 | FINAL

## #9330.00 Bergstrom
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  | Major Program 4D03
Bergstrom |  |  | Vendor:00002110114
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ #933000-01
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523178804 | 2023-06-27 | PO Procore | 7954 | 7954 |  |  | 7954 | FY23
PO 33524178804 | 2023-07-25 | Rolled to FY24 | 0 | 7954 |  | 0 | 7954
PO 33524178804 | 2023-08-21 | CO #1 | 336 | 8290 |  | 0 | 8290
PO 33524178804 | 2023-10-02 | CO #2(No Cost CO) | 0 | 8290 |  | 0 | 8290
PRC 3352417PA8804 | 2023-10-26 | Inv. 8598-1 |  | 8290 | 7735 | 7735 | 555
PRC 3352417PB8804 | 2023-12-20 | Inv. 8598-2 - Final |  | 8290 | 555 | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  |  |  | 8290 |  | 8290 | 0
|  | Totals: | 8290 |  | 8290 |  | 0

## #9330.00 Waldinger Corp
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  | Major Program 4D03
Waldinger Corporation |  |  | Vendor: 00002116105
Acct. Codes-0017-335-MM23-9255 |  |  | MA 00520452
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523180900 | 2023-06-29 | DO Procore | 5297 | 5297 |  |  | 5297 | FY23
DO 33524180900 | 2023-07-25 | Rolled to FY24 | 0 | 5297 |  | 0 | 5297
DO 33524180900 | 2023-09-28 | CO #1 (No Cost) | 0 | 5297 |  | 0 | 5297
PRC 3352418PA0900 | 2024-01-03 | Inv. 73356E-001 |  | 5297 | 2440.86 | 2440.86 | 2856.14
DO 33524180900 | 2024-01-04 | Closing PO per PM | -2856.14 | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  |  |  | 2440.86 |  | 2440.86 | 0
|  | Totals: | 2440.86 |  | 2440.86 |  | 0

## #9330.00 DCI Group #23-001 CA
DAS CC Jessie Parker Elevator Code Update
Project # 9330.00
Program code 933000 |  |  | Major Program 4D03
DCI Group #23-001 CA |  |  | Vendor:00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ #933000-01
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523181801 | 2023-06-30 | PO Procore | 9071.97 | 9071.97 |  |  | 9071.97 | FY23
PO 33524181801 | 2023-07-25 | Rolled to FY24 | 0 | 9071.97 |  | 0 | 9071.97
PRC 3352418PA1801 | 2023-11-16 | Inv. 23-001 CA-01 |  | 9071.97 | 6851.73 | 6851.73 | 2220.24
PRC 3352418PB1801 | 2023-12-19 | Inv. 23-001 CA-02 |  | 9071.97 | 766.08 | 7617.81 | 1454.16
PRC 3352418PC1801 | 2024-01-24 | Inv. 23-001 CA-03 FINAL | -644.97 | 8427 | 809.19 | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  |  |  | 8427 |  | 8427 | 0
|  | Totals: | 8427 |  | 8427 |  | 0 | FINAL

## RECAP #9331.00
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
| Program code 933100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
| Funds Recv'd | 112135.86
C | McGough Construction |  | 7206.08 | 7206.08 | 0
C | PM TIME |  | 8187.56 | 8187.56 | 0
C | Misc. |  | 895 | 895 | 0
C | Shive Hattery |  | 14800 | 14800 | 0
C | Midstate Plmg & Htg |  | 61033.93 | 61033.93 | 0
C | McGough Construction (2) |  | 15543.29 | 15543.29 | 0
C | Controlled Asbestos |  | 4470 | 4470 | 0
| Total Project Cost | 112135.86 | 112135.86 | 112135.86 | 0 | 0
Project Closed 06/11/2024
29C20 Funds Recevived 10/09/2024

## #9331.00 Funds Rec'd
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
Funds Rec'd
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Executive Council Approval 10.7.24 - DOC Fort Dodge | IET 6542531202510082401 | 2024-10-09 | 112135.86 | 112135.86
| Total Requested | 0 | Total Transferred |  |  | 112135.86 | 112135.86

## #9331.00 McGough Construction
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523011800 | 2023-01-11 | Po Procore | 9802.16 | 9802.16 |  |  | 9802.16
PRC 3352301PA1800 | 2023-02-13 | Inv. 101031.001PC1 |  | 9802.16 | 880.1 | 880.1 | 8922.06
PRC 3352301PB1800 | 2023-03-13 | Inv. 101031.001PC2 |  | 9802.16 | 855.14 | 1735.24 | 8066.92
PRC 3352301PC1800 | 2023-04-10 | Inv. 101031.001-03 |  | 9802.16 | 4551.53 | 6286.77 | 3515.39
PRC 3352301PD1800 | 2023-05-09 | Inv. 101031.001-04_Final | -2596.08 | 7206.08 | 919.31 | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  |  |  | 7206.08 |  | 7206.08 | 0
|  | Totals: | 7206.08 |  | 7206.08 |  | 0 | FINAL
|  | CM Srvices | 7128.58 |  | 7128.58 |  | 0
|  | Reimbursables | 77.5 |  | 77.5 |  | 0
|  | Totals: | 7206.08 |  | 7206.08 |  | 0

## #9331.00 PM TIME
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E253
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8187.56 | 8187.56 |  |  | 8187.56
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 8187.56 | 110.21 | 110.21 | 8077.35
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 8187.56 | 130.04 | 240.25 | 7947.31
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 8187.56 | 1140.06 | 1380.31 | 6807.25
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 |  | 8187.56 | 16.48 | 1396.79 | 6790.77
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 8187.56 | 97.44 | 1494.23 | 6693.33
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 8187.56 | 590.89 | 2085.12 | 6102.44
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 8187.56 | 192.56 | 2277.68 | 5909.88
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 8187.56 | 846.98 | 3124.66 | 5062.9
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 8187.56 | 170.99 | 3295.65 | 4891.91
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 8187.56 | 1003.9 | 4299.55 | 3888.01
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 8187.56 | 48.87 | 4348.42 | 3839.14
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 8187.56 | 341 | 4689.42 | 3498.14
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 8187.56 | 5.3 | 4694.72 | 3492.84
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 8187.56 | 21.7 | 4716.42 | 3471.14
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 8187.56 | 26.01 | 4742.43 | 3445.13
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 8187.56 | 164.8 | 4907.23 | 3280.33
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 8187.56 | 25.33 | 4932.56 | 3255
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 8187.56 | 142.1 | 5074.66 | 3112.9
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 8187.56 | 51.77 | 5126.43 | 3061.13
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 8187.56 | 361.5 | 5487.93 | 2699.63
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 8187.56 | 48.72 | 5536.65 | 2650.91
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8187.56 | 391.2 | 5927.85 | 2259.71
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 8187.56 | 14.07 | 5941.92 | 2245.64
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 8187.56 | 107 | 6048.92 | 2138.64
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 8187.56 | 37.97 | 6086.89 | 2100.67
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 8187.56 | 279.5 | 6366.39 | 1821.17
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 8187.56 | 44.16 | 6410.55 | 1777.01
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 8187.56 | 387.6 | 6798.15 | 1389.41
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 8187.56 | 61.65 | 6859.8 | 1327.76
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 8187.56 | 308.5 | 7168.3 | 1019.26
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 8187.56 | 24.06 | 7192.36 | 995.2
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 8187.56 | 185 | 7377.36 | 810.2
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 8187.56 | 15.76 | 7393.12 | 794.44
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 8187.56 | 136.1 | 7529.22 | 658.34
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8187.56 | 71.04 | 7600.26 | 587.3
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8187.56 | 587.3 | 8187.56 | 0
[5 empty] | 8187.56 |  | 8187.56 | 0
|  |  | Totals: | 8187.56 |  | 8187.56 |  | 0
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Dec 20, 2022, 2:34 PM (16 hours ago) to me Please create the following new PM Time budgets: MM23 9279.20 for $11,000.00 MM21 9329.00 for $4,400.00 MM23 9331.00 for $4,400.00 MM23 9332.00 for $8,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Budget Adjustments $John Kleene, Jennifer 2:09 PM (41 minutes ago) to me, Scott Please increase the PM Time budget for MM23 9331.00 by $4,400.00. Regards, Jennife

## #9331.00 Misc
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523048801 | 2023-02-17 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2483650-Final | 895 | 895
895
895
895
895
895
895
895
895
895
895
895
|  |  |  | Totals: |  | 895

## #9331.00 Shive Hattery
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523019904 | 2023-01-19 | PO Procore | 10800 | 10800 |  |  | 10800
PRC 3352301PA9904 | 2023-03-06 | Inv. 2142301150-1 |  | 10800 | 3825 | 3825 | 6975
PRC 3352301PB9904 | 2023-03-23 | Inv. 2142301150-2 |  | 10800 | 1020 | 4845 | 5955
PO 33523019904 | 2023-04-03 | CO 1 | 4000 | 14800 |  | 4845 | 9955
PRC 3352301PC9904 | 2023-04-24 | Inv. 2142301150-3 |  | 14800 | 5205 | 10050 | 4750
PRC 3352301PD9904 | 2023-05-30 | Inv. 2142301150-4 |  | 14800 | 1140 | 11190 | 3610
PRC 3352301PE9904 | 2023-07-06 | Inv. 2142301150-5 |  | 14800 | 760 | 11950 | 2850 | FY23
PO 33524019904 | 2023-07-25 | Rolled to FY24 |  | 14800 |  | 11950 | 2850
PRC 3352401PF9904 | 2023-08-07 | Inv. 2142301150-6 |  | 14800 | 190 | 12140 | 2660
PRC 3352401PG9904 | 2023-09-11 | Inv. 2142301150-7 |  | 14800 | 760 | 12900 | 1900
PRC 3352401PH9904 | 2023-10-04 | Inv. 2142301150-8 |  | 14800 | 1140 | 14040 | 760
PRC 3352401PI9904 | 2024-02-02 | Inv. 2142301150-9 |  | 14800 | 570 | 14610 | 190
PRC 3352401PJ9904 | 2024-05-22 | Inv. 2142301150-10 FINAL |  | 14800 | 190 | 14800 | 0
|  |  |  | 14800 |  | 14800 | 0
|  | Totals: | 14800 |  | 14800 |  | 0 | FINAL
|  | Storage Tank Replacement Design | 5100 |  | 5100 |  | 0
|  | Quoting/Bidding Services | 1900 |  | 1900 |  | 0
|  | Construction Administration | 3800 |  | 3800 |  | 0
|  | Additional Design | 4000 |  | 4000 |  | 0
|  | Totals: | 14800 |  | 14800 |  | 0

## #9331.00 Midstate Plmg & Htg
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
Midstate Plumbing & Heating |  |  | Vendor:00002108635
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ933100-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523116901 | 2023-04-26 | PO Procore | 56139 | 56139 |  |  | 56139 |  | FY23
PO 33524116901 | 2023-07-25 | Rolled to FY24 | 0 | 56139 |  | 0 | 56139
PO 33524116901 | 2023-08-02 | CO #1 | 0 | 56139 |  | 0 | 56139
PRC 3352411PA6901 | 2023-08-02 | Inv. P34660 |  | 56139 | 12019.4 | 12019.4 | 44119.6 | 632.6
PRC 3352411PB6901 | 2023-10-11 | Inv. P35104 |  | 56139 | 21761.65 | 33781.05 | 22357.95 | 1777.95
PO 33524116901 | 2023-10-17 | Co #2 | 5510.61 | 61649.61 |  | 33781.05 | 27868.56
PO 33524116901 | 2023-12-19 | CO #3 | -615.68 | 61033.93 |  | 33781.05 | 27252.88
PRC 3352411PC6901 | 2024-01-26 | Inv. P35328 |  | 61033.93 | 18790.63 | 52571.68 | 8462.25 | 2766.93
PRC 3352411PD6901 | 2024-05-14 | Inv. P35825 |  | 61033.93 | 5410.55 | 57982.23 | 3051.7 | 3051.7
PRC 3352411PE6901 | 2024-05-20 | Inv. P36157-Retainage |  | 61033.93 | 3051.7 | 61033.93 | 0
|  |  |  | 61033.93 |  | 61033.93 | 0
|  |  |  | 61033.93 |  | 61033.93 | 0
|  |  |  | 61033.93 |  | 61033.93 | 0
|  | Totals: | 61033.93 |  | 61033.93 |  | 0 | FINAL

## #9331.00 McGough Constructi (2)
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523124806 | 2023-05-04 | Po Procore | 18341.54 | 18341.54 |  |  | 18341.54
PRC 3352312PA4806 | 2023-06-09 | Inv. 101031.001-01 |  | 18341.54 | 1340.68 | 1340.68 | 17000.86
PRC 3352312PB4806 | 2023-07-07 | Inv. 101031.001-02 |  | 18341.54 | 461.19 | 1801.87 | 16539.67 | FY23
PO 33524124806 | 2023-07-25 | Rolled to FY24 | 0 | 18341.54 |  | 1801.87 | 16539.67
PRC 3352412PC4806 | 2023-08-08 | Inv. 101031.001-03-9331.00 |  | 18341.54 | 547.9 | 2349.77 | 15991.77
PRC 3352412PD4806 | 2023-09-14 | Inv. 101031.001-04-9331.00 |  | 18341.54 | 546.44 | 2896.21 | 15445.33
PRC 3352412PE4806 | 2023-10-11 | Inv. 101031.001-05-9331.00 |  | 18341.54 | 2158.54 | 5054.75 | 13286.79
PRC 3352412PF4806 | 2023-11-13 | Inv. 101031.001-06-9331.00 |  | 18341.54 | 1889.76 | 6944.51 | 11397.03
PRC 3352412PG4806 | 2023-12-12 | Inv. 101031.001-07-9331.00 |  | 18341.54 | 1825.69 | 8770.2 | 9571.34
PRC 3352412PH4806 | 2024-01-17 | Inv. 101031.001-08-9331.00 |  | 18341.54 | 2154.32 | 10924.52 | 7417.02
PRC 3352412PI4806 | 2024-02-06 | Inv. 101031.001-09-9331.00 |  | 18341.54 | 1172.3 | 12096.82 | 6244.72
PRC 3352412PJ4806 | 2024-03-18 | Inv. 101031.001-10-9331.00 |  | 18341.54 | 1208.83 | 13305.65 | 5035.89
PRC 3352412PK4806 | 2024-04-10 | Inv. 101031.001-11-9331.00 |  | 18341.54 | 1065.34 | 14370.99 | 3970.55
PO 33524124806A | 2024-05-02 | PO Mistakenly Closed with last Invoice |  | 18341.54 | 0 | 14370.99 | 3970.55
PRC 3352412PL4806A | 2024-05-13 | Inv. 101031.001-12-9331.00 |  | 18341.54 | 573.97 | 14944.96 | 3396.58
PO 33524124806B | 2024-05-29 | Closed with invoice 12 |  | 18341.54 | 0 | 14944.96 | 3396.58
PO 3352412PM4806B | 2024-05-30 | Inv. 101031.001-13-9331.00 Final | -2798.25 | 15543.29 | 598.33 | 15543.29 | 0
|  |  |  | 15543.29 |  | 15543.29 | 0
|  | Totals: | 15543.29 |  | 15543.29 |  | 0 | FINAL
|  | CM Srvices | 15292.29 |  | 15292.29 |  | 0
|  | Reimbursables | 251 |  | 251 |  | 0
|  | Totals: | 15543.29 |  | 15543.29 |  | 0

## #9331.00 Controlled Asbestos
DOC FDCF Unit H Laundry Unit Tank Replacement (29C20)
Project # 9331.00
Program code 933100 |  |  | Major Program 4B01
Controlled Asbestos |  |  | Vendor:00002118118
Acct. Codes-0017-335-MM23-9255 |  |  | MA00521060
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33523145808 | 2023-05-25 | DO Procore | 4720 | 4720 |  |  | 4720 | FY23
DO 33524145808 | 2023-07-25 | Rolled to FY24 | 0 | 4720 |  | 0 | 4720
PRC 3352414PA5808 | 2023-11-27 | Inv. 0010670 |  | 4720 | 4470 | 4470 | 250
DO 33524145808 | 2024-04-02 | Closing PO Per PM Request | -250 | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  |  |  | 4470 |  | 4470 | 0
|  | Totals: | 4470 |  | 4470 |  | 0
|  | Contract Line 5 - Lead Abatement Services Hourly Rate (69 hours at $58.00/hr) | 4002 |  | 4002 |  | 0
|  | Contract Line 7 - Materials Cost for Non-Disposable Items (lump sum) | 0 |  |  |  | 0
|  | Contract Line 12 - Mileage (1,200 miles at $0.39/mile) | 468 |  | 468 |  | 0
|  | Totals: | 4470 |  | 4470 |  | 0

## RECAP #9332.00
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
| Program code 933200 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 0
122417.55
C | McGough Construction |  | 6372.66 | 6372.66 | 0
C | PM TIME |  | 7925.16 | 7925.16 | 0
C | Misc. |  | 835 | 835 | 0
C | Shive Hattery |  | 8400 | 8400 | 0
C | Midstate Plumbing & Heating |  | 80993 | 80993 | 0
C | McGough Construction (2) |  | 17891.73 | 17891.73 | 0
| Total Project Cost | 122417.55 | 122417.55 | 122417.55 | 0 | 0
Project Closed 07/11/2024
29C20 Funds Recv'd 10/09/2024

## #9332.00 Funds Rec'd
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  | Major Program 4B01
Funds Rec'd
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Executive Council Approval 10.7.24 - DOC Ft Dodge | IET 6542376202510082401 | 2024-10-07 | 122417.55 | 122417.55
| Total Requested | 0 | Total Transferred |  |  | 122417.55 | 122417.55

## #9332.00 McGough Construction
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  | Major Program 4B01
Mc Gough Construction |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523011802 | 2023-01-11 | PO Procore | 9802.16 | 9802.16 |  |  | 9802.16
PRC 3352301PA1802 | 2023-02-13 | Inv. 101031.002PC1 |  | 9802.16 | 983.88 | 983.88 | 8818.28
PRC 3352301PB1802 | 2023-03-13 | Inv. 101031.002PC2 |  | 9802.16 | 1120.95 | 2104.83 | 7697.33
PRC 3352301PC1802 | 2023-04-10 | Inv. 101031.002-03 |  | 9802.16 | 2982.11 | 5086.94 | 4715.22
PRC 3352301PD1802 | 2023-05-10 | Inv. 101031.002-04_Final | -3429.5 | 6372.66 | 1285.72 | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  |  |  | 6372.66 |  | 6372.66 | 0
|  | Totals: | 6372.66 |  | 6372.66 |  | 0 | Final
|  | CM Services | 6295.16 |  | 6295.16 |  | 0
|  | Reimbursables | 77.5 |  | 77.5 |  | 0
|  | Totals: | 6372.66 |  | 6372.66 |  | 0

## #9332.00 PM TIME
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E254
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7925.16 | 7925.16 |  |  | 7925.16
IET DAS202306115300001 | 2023-01-09 | 9500 | PM Time-December 1-December 31, 2022 |  | 7925.16 | 110.21 | 110.21 | 7814.95
IET DAS202307115300001 | 2023-02-07 | 2507 | Finance Support for: January 1-31, 2023 |  | 7925.16 | 109.24 | 219.45 | 7705.71
IET DAS202307115300001 | 2023-02-07 | 9500 | DAS Services For: January 1-31, 2023 |  | 7925.16 | 957.66 | 1177.11 | 6748.05
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: December 1-31, 2022 |  | 7925.16 | 16.48 | 1193.59 | 6731.57
IET DAS202308115300001 | 2023-03-07 | 2507 | Finance Support for: February 1-28, 2023 |  | 7925.16 | 127.43 | 1321.02 | 6604.14
CDE 33523075203 | 2023-03-07 | 9500 | Move to 9279.20 MM23 per billing file error |  | 7925.16 | -59.97 | 1261.05 | 6664.11
IET DAS202308115300001 | 2023-03-07 | 9500 | DAS Services for: February 1-28, 2023 |  | 7925.16 | 772.71 | 2033.76 | 5891.4
CDE 33523075203 | 2023-03-07 | 9500 | Move to 9279.20 MM23 per billing file error |  | 7925.16 | -363.63 | 1670.13 | 6255.03
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 7925.16 | 182.43 | 1852.56 | 6072.6
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 7925.16 | 802.4 | 2654.96 | 5270.2
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 7925.16 | 155.54 | 2810.5 | 5114.66
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 7925.16 | 913.3 | 3723.8 | 4201.36
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 7925.16 | 56.71 | 3780.51 | 4144.65
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 7925.16 | 397.1 | 4177.61 | 3747.55
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 7925.16 | 10.37 | 4187.98 | 3737.18
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 7925.16 | 64.5 | 4252.48 | 3672.68
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 7925.16 | 32.28 | 4284.76 | 3640.4
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 7925.16 | 206.8 | 4491.56 | 3433.6
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 7925.16 | 25.33 | 4516.89 | 3408.27
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 7925.16 | 142.1 | 4658.99 | 3266.17
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 7925.16 | 15.17 | 4674.16 | 3251
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 7925.16 | 103.9 | 4778.06 | 3147.1
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 7925.16 | 27.28 | 4805.34 | 3119.82
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 7925.16 | 216.9 | 5022.24 | 2902.92
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 7925.16 | 6.69 | 5028.93 | 2896.23
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 7925.16 | 53.5 | 5082.43 | 2842.73
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 7925.16 | 19.32 | 5101.75 | 2823.41
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 7925.16 | 140.3 | 5242.05 | 2683.11
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 7925.16 | 21.53 | 5263.58 | 2661.58
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 7925.16 | 193.8 | 5457.38 | 2467.78
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 7925.16 | 201.3 | 5658.68 | 2266.48
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 7925.16 | 1015 | 6673.68 | 1251.48
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 7925.16 | 42.28 | 6715.96 | 1209.2
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 7925.16 | 323.1 | 7039.06 | 886.1
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 7925.16 | 20.5 | 7059.56 | 865.6
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 7925.16 | 179.8 | 7239.36 | 685.8
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 7925.16 | 22.19 | 7261.55 | 663.61
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 7925.16 | 180.3 | 7441.85 | 483.31
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 7925.16 | 47.61 | 7489.46 | 435.7
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 7925.16 | 435.7 | 7925.16 | 0
[5 empty] | 7925.16 |  | 7925.16 | 0
[5 empty] | 7925.16 |  | 7925.16 | 0
[5 empty] | 7925.16 |  | 7925.16 | 0
|  |  | Totals: | 7925.16 |  | 7925.16 |  | 0
Note on E9: Huggins, Joni [DAS]: New PM Time Budgets $Joni Kleene, Jennifer Dec 20, 2022, 2:34 PM (16 hours ago) to me Please create the following new PM Time budgets: MM23 9279.20 for $11,000.00 MM21 9329.00 for $4,400.00 MM23 9331.00 for $4,400.00 MM23 9332.00 for $8,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov

## #9332.00 Misc
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523048800 | 2023-02-17 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2483645-Final | 835 | 835
835
835
835
835
835
835
835
835
835
835
835
|  |  |  | Totals: |  | 835

## #9332.00 Shive Hattery
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523020906 | 2023-01-20 | PO Procore | 8400 | 8400 |  |  | 8400
PRC 3352302PA0906 | 2023-03-06 | Inv. 2142301160-1 |  | 8400 | 4425 | 4425 | 3975
PRC 3352302PB0906 | 2023-03-23 | Inv. 2142301160-2 |  | 8400 | 1180 | 5605 | 2795
PRC 3352302PC0906 | 2023-04-24 | Inv. 2142301160-3 |  | 8400 | 695 | 6300 | 2100
PRC 3352302PD0906 | 2023-05-30 | Inv. 2142301160-4 |  | 8400 | 485 | 6785 | 1615
PRC 3352302PE0906 | 2023-07-07 | Inv. 2142301160-5 |  | 8400 | 510 | 7295 | 1105 | FY23
PO 33524020906 | 2023-07-24 | Rolled to FY24 | 0 | 8400 |  | 7295 | 1105
PRC 3352402PF0906 | 2023-09-11 | Inv. 2142301160-6 |  | 8400 | 255 | 7550 | 850
PRC 3352402PG0906 | 2024-01-04 | Inv. 2142301160-7 |  | 8400 | 170 | 7720 | 680
PRC 3352402PH0906 | 2024-03-04 | Inv. 2142301160-8 |  | 8400 | 510 | 8230 | 170
PRC 3352402PI0906 | 2024-06-28 | Inv. 2142301160-9FINAL |  | 8400 | 170 | 8400 | 0
|  |  |  | 8400 |  | 8400 | 0
|  |  |  | 8400 |  | 8400 | 0
|  | Totals: | 8400 |  | 8400 |  | 0 | FINAL
|  | Storage Tank Replacement Design | 5900 |  | 5900 |  | 0
|  | Quoting/Bidding Services | 800 |  | 800 |  | 0
|  | Construction Administration | 1700 |  | 1700 |  | 0
|  | Totals: | 8400 |  | 8400 |  | 0

## #9332.00 Midstate Plg & Htg
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  | Major Program 4B01
Midstate Plg & Htg |  |  | Vendor:00002108635
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ933200-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Split W/DA23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523116900 | 2023-04-26 | PO Procore | 80993 | 80993 |  |  | 80993 |  | FY23
PO 33524116900 | 2023-08-29 | Roll to FY24 | 0 | 80993 |  | 0 | 80993
PRC 3352411PA6900 | 2023-08-23 | Inv. P34659 |  | 80993 | 4553.35 | 4553.35 | 76439.65 | 239.65
PO 33524116900 | 2023-09-06 | CO #1 (No Cost CO) | 0 | 80993 |  | 4553.35 | 76439.65
PO 33524116900 | 2023-10-24 | CO #2 (No Cost CO) | 0 | 80993 |  | 4553.35 | 76439.65
PO 33524116900 | 2023-12-21 | CO #3 (No Cost CO for MM23) | 0 | 80993 |  | 4553.35 | 76439.65
PRC 3352411PB6900 | 2024-01-09 | Inv. P35103 |  | 80993 | 21216.35 | 25769.7 | 55223.3 | 1356.3
PRC 3352411PC6900 | 2024-02-08 | Inv. P35824(Split with DA23) |  | 80993 | 20629.25 | 46398.95 | 34594.05 | 2442.05
PRC 3352411PD6900 | 2024-04-15 | Inv. P36031(Split with DA23) |  | 80993 | 13243.95 | 59642.9 | 21350.1 | 3139.1
PRC 3352411PE6900 | 2024-06-24 | Inv. P36504(Split With DA23) |  | 80993 | 17300.45 | 76943.35 | 4049.65 | 4049.65
PRC 3352411PF6900 | 2024-06-27 | Inv. P36321 Retainage(Split With DA23) |  | 80993 | 4049.65 | 80993 | 0
|  |  |  | 80993 |  | 80993 | 0
|  |  |  | 80993 |  | 80993 | 0
|  | Totals: | 80993 |  | 80993 |  | 0 | FINAL
|  | DA23 | 19075 |  | 19075 |  | 0
|  | Total Contract | 100068 |  | 100068 |  | 0

## #9332.00 McGough Constructi (2)
DOC FDCF Unit A Domestic Water Heater Replacement (29C20)
Project # 9332.00
Program code 933200 |  |  | Major Program 4B01
Mc Gough Construction (2) |  |  | Vendor:00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ933200-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523124801 | 2023-05-04 | PO Procore | 25506.1 | 25506.1 |  |  | 25506.1
PRC 3352312PA4801 | 2023-06-09 | Inv. 101031.002-01 |  | 25506.1 | 1197.18 | 1197.18 | 24308.92
PRC 3352312PB4801 | 2023-07-07 | Inv. 101031.002-02 |  | 25506.1 | 461.19 | 1658.37 | 23847.73 | FY23
PO 33524124801 | 2023-07-24 | Rolled to FY24 | 0 | 25506.1 |  | 1658.37 | 23847.73
PRC 3352412PC4801 | 2023-08-31 | Inv. 101031.002-CA03 |  | 25506.1 | 949.38 | 2607.75 | 22898.35
PRC 3352412PD4801 | 2023-09-15 | Inv. 101031.002-CA04 |  | 25506.1 | 909.67 | 3517.42 | 21988.68
PRC 3352412PE4801 | 2023-10-11 | Inv. 101031.002-CA05 |  | 25506.1 | 1187.65 | 4705.07 | 20801.03
PRC 3352412PF4801 | 2023-11-13 | Inv. 101031.002-CA06 |  | 25506.1 | 789.11 | 5494.18 | 20011.92
PRC 3352412PG4801 | 2023-12-13 | Inv. 101031.002-CA07 |  | 25506.1 | 4160.95 | 9655.13 | 15850.97
PRC 3352412PH4801 | 2024-01-17 | Inv. 101031.002-CA08 |  | 25506.1 | 1299.72 | 10954.85 | 14551.25
PRC 3352412PI4801 | 2024-02-06 | Inv. 101031.002-CA09 |  | 25506.1 | 1060.74 | 12015.59 | 13490.51
PRC 3352412PJ4801 | 2024-03-18 | Inv. 101031.002-CA10 |  | 25506.1 | 2053.72 | 14069.31 | 11436.79
PRC 3352412PK4801 | 2024-04-10 | Inv. 101031.002-CA11 |  | 25506.1 | 1694.38 | 15763.69 | 9742.41
PRC 3352412PL4801 | 2024-05-13 | Inv. 101031.002-CA12 |  | 25506.1 | 732.82 | 16496.51 | 9009.59
PRC 3352412PM4801 | 2024-06-12 | Inv. 101031.002-CA13 |  | 25506.1 | 900.67 | 17397.18 | 8108.92
PRC 3352412PN4801 | 2024-06-28 | Inv. 101031.002-CA14 FINAL | -7614.37 | 17891.73 | 494.55 | 17891.73 | 0
|  |  |  | 17891.73 |  | 17891.73 | 0
|  | Totals: | 17891.73 |  | 17891.73 |  | 0 | FINAL
|  | CM Services | 17507.73 |  | 17507.73 |  | 0
|  | Reimbursables | 384 |  | 384 |  | 0
|  | Totals: | 17891.73 |  | 17891.73 |  | 0

## RECAP #9339.00
DOC IMCC Grease Trap Replacement
Project # 9339.00
| Program code 933900 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 134585.17
C | Shive Hattery |  | 19000 | 19000 | 0
C | PM TIME |  | 8049.47 | 8049.47 | 0
C | Misc. |  | 250 | 250 | 0
C | Samuels Group |  | 23977.9 | 23977.9 | 0
C | S&S Plumbing |  | 83307.8 | 83307.8 | 0
| Total Project Cost | 134585.17 | 134585.17 | 134585.17 | 0 | 0
Closed 11/28/23

## #9339.00 Shive Hattery
DOC IMCC Grease Trap Replacement
Project # 9339.00
Program code 933900 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523082800 | 2023-03-23 | PO Procore | 19000 | 19000 |  |  | 19000
PRC 3352308PA2800 | 2023-04-28 | Inv. 2112303150-1 |  | 19000 | 13800 | 13800 | 5200
PRC 3352308PB2800 | 2023-06-05 | Inv. 2112303150-2 |  | 19000 | 1950 | 15750 | 3250
PRC 3352308PC2800 | 2023-07-10 | Inv. 2112303150-3 |  | 19000 | 650 | 16400 | 2600 | FY23
PO 33524082800 | 2023-07-24 | Rolled to FY24 | 0 | 19000 |  | 16400 | 2600
PRC 3352408PD2800 | 2023-08-04 | Inv. 9339.00-04 |  | 19000 | 325 | 16725 | 2275
PRC 3352408PE2800 | 2023-09-19 | Inv. 9339.00-05 |  | 19000 | 1950 | 18675 | 325
PRC 3352408PF2800 | 2023-10-23 | Inv. 9339.00-06 Final |  | 19000 | 325 | 19000 | 0
|  |  |  | 19000 |  | 19000 | 0
|  |  |  | 19000 |  | 19000 | 0
|  |  |  | 19000 |  | 19000 | 0
|  |  |  | 19000 |  | 19000 | 0
|  |  |  | 19000 |  | 19000 | 0
|  | Totals: | 19000 |  | 19000 |  | 0 | FINAL
|  | Topographic Survey | 3000 |  | 3000 |  | 0
|  | Grease Trap Replacement Design Services | 12000 |  | 12000 |  | 0
|  | Limited Bid Phase Services | 750 |  | 750 |  | 0
|  | Limited Construction Phase Services | 3250 |  | 3250 |  | 0
|  | Totals: | 19000 |  | 19000 |  | 0

## #9339.00 PM TIME
DOC IMCC Grease Trap Replacement
Project # 9339.00
Program code 933900 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E25L
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8049.47 | 8049.47 |  |  | 8049.47
IET DAS202309115300001 | 2023-04-07 | 2507 | Finance Support for: March 1-31, 2023 |  | 8049.47 | 547.29 | 547.29 | 7502.18
IET DAS202309115300001 | 2023-04-07 | 9500 | DAS Services for: March 1-31, 2023 |  | 8049.47 | 2407.22 | 2954.51 | 5094.96
IET DAS202310115300001 | 2023-05-07 | 2507 | Finance Support for: April 1-30, 2023 |  | 8049.47 | 271.72 | 3226.23 | 4823.24
IET DAS202310115300001 | 2023-05-07 | 9500 | DAS Services for: April 1-30, 2023 |  | 8049.47 | 1596.8 | 4823.03 | 3226.44
IET DAS202311115300001 | 2023-06-07 | 2507 | Finance Support for: May 1-31, 2023 |  | 8049.47 | 113.41 | 4936.44 | 3113.03
IET DAS202311115300001 | 2023-06-07 | 9500 | DAS Services for: May1-31, 2023 |  | 8049.47 | 794.2 | 5730.64 | 2318.83
IET DAS202312115300001 | 2023-07-07 | 2507 | Finance Support for June 1-30, 2023 |  | 8049.47 | 41.92 | 5772.56 | 2276.91
IET DAS202312115300001 | 2023-07-07 | 9500 | DAS Services for June 1-30, 2023 |  | 8049.47 | 320.1 | 6092.66 | 1956.81
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 8049.47 | 26.01 | 6118.67 | 1930.8
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 8049.47 | 164.8 | 6283.47 | 1766
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 8049.47 | 75.74 | 6359.21 | 1690.26
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 8049.47 | 424.1 | 6783.31 | 1266.16
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 8049.47 | 66.94 | 6850.25 | 1199.22
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 8049.47 | 464.9 | 7315.15 | 734.32
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 8049.47 | 81.42 | 7396.57 | 652.9
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8049.47 | 652.9 | 8049.47 | 0
[5 empty] | 8049.47 |  | 8049.47 | 0
[5 empty] | 8049.47 |  | 8049.47 | 0
|  |  | Totals: | 8049.47 |  | 8049.47 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Budget Changes $Joni Kleene, Jennifer 2:52 PM (0 minutes ago) to me, Scott Please create a PM Time budget for $6,600.00 for MM23 Project 9339.00. Please increase the PM Time budget for DA22 9217.01 by $500.00 Please increase the PM Time budget for MM21 9298.00 by $6,600.00 Please increase the PM Time budget for DA20 9159.00 by $1,000.00 Regards, Jennifer Jennifer Kleene, Owner’s Representative Iowa Department of Administrative Services General Services Enterprise Mobile: 515-822-8197 Fax: 515-281-8748 Jennifer.Kleene@iowa.gov https://das.iowa.gov PM Time Changes $John Kleene, Jennifer 1:58 PM (1 hour ago) to me, Scott Please increase PM time for the following projects: MM22 9279.00 increase by $2,200.00 DA20 9159.00 increase by $3,740.00 MM23 9339.00 Increase by $4,488.00 Regards, Jennifer Please Close MM23 Project 9339.00 $John Kleene, Jennifer 12:04 PM (2 hours ago) to me, Scott All invoices have been paid and all PM time has posted, so please close project 9339.00. Regards, Jennifer

## #9339.00 Misc
DOC IMCC Grease Trap Replacement
Project # 9339.00
Program code 933900 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33523097800 | 2023-04-07 | 9500 | CNST | Quality Excavating V#(00003206957) | Inv. 9442 | 250 | 250
250
250
250
250
250
250
250
250
250
250
250
|  |  |  | Totals: |  | 250

## #9339.00 Samuels Group
DOC IMCC Grease Trap Replacement
Project # 9339.00
Program code 933900 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33523083802 | 2023-03-24 | PO Procore | 24071.52 | 24071.52 |  |  | 24071.52
PRC 3352308PA3802 | 2023-05-08 | Inv. 7480.019339 PC |  | 24071.52 | 4211.01 | 4211.01 | 19860.51
PRC 3352308PB3802 | 2023-06-06 | Inv. 7480.029339 PC |  | 24071.52 | 1705.21 | 5916.22 | 18155.3
PRC 3352308PC3802 | 2023-07-10 | Inv. 7480.039339 PC |  | 24071.52 | 757.41 | 6673.63 | 17397.89 | FY23
PO 33524083802 | 2023-07-24 | Rolled to FY24 | 0 | 24071.52 |  | 6673.63 | 17397.89
PRC 3352408PD3802 | 2023-08-07 | Inv. 7480.049339 PC |  | 24071.52 | 2613.93 | 9287.56 | 14783.96
PRC 3352408PE3802 | 2023-09-15 | Inv. 7483.05 CA |  | 24071.52 | 6876.08 | 16163.64 | 7907.88
PRC 3352408PF3802 | 2023-10-06 | Inv. 7480.06 CA |  | 24071.52 | 4559.42 | 20723.06 | 3348.46
PRC 3352408PG3802 | 2023-10-27 | Inv. 7480.07 Final PC | -93.62 | 23977.9 | 3254.84 | 23977.9 | 2.6148e-12
|  |  |  | 23977.9 |  | 23977.9 | 2.6148e-12
|  |  |  | 23977.9 |  | 23977.9 | 2.6148e-12
|  |  |  | 23977.9 |  | 23977.9 | 2.6148e-12
|  |  |  | 23977.9 |  | 23977.9 | 2.6148e-12
|  | Totals: | 23977.9 |  | 23977.9 |  | 0
|  | CM Services | 23070.23 |  | 23070.23 |  | 0
|  | Reimbursables | 907.67 |  | 907.67 |  | 0
|  | Totals: | 23977.9 |  | 23977.9 |  | 0

## #9339.00 S & S Plumbing
DOC IMCC Grease Trap Replacement
Project # 9339.00
Program code 933900 |  |  | Major Program 4E01
S&S Plumbing, Heating & AC |  |  | Vendor:00003036947
Acct. Codes-0017-335-MM23-9255 |  |  | RFQ933900-01
Project Manager - Jennifer K. |  |  | Activity code:BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33523159803 | 2023-06-08 | PO Procore | 80731 | 80731 |  |  | 80731 |  | FY23
PO 33524159803 | 2023-07-24 | Rolled to FY24 | 0 | 80731 |  | 0 | 80731
PO 33524159803 | 2023-09-14 | CO #1 | 2576.8 | 83307.8 |  | 0 | 83307.8
PRC 3352415PA9803 | 2023-09-25 | Inv. 9339.00-01 |  | 83307.8 | 77242.41 | 77242.41 | 6065.39 | 4065.39
PRC 3352415PB9803 | 2023-10-18 | Inv. 9339.00-02 |  | 83307.8 | 1900 | 79142.41 | 4165.39 | 4165.39
PRC 3352415PC9803 | 2023-10-20 | Inv. 9339.00-03-Retainage |  | 83307.8 | 4165.39 | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  |  |  | 83307.8 |  | 83307.8 | 0
|  | Totals: | 83307.8 |  | 83307.8 |  | 0 | FINAL

## RECAP #9370.00
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
| Program code 937000 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 400000
| Additional Funds Received | 528.13
C | Boyd Jones |  | 10991.81 | 10991.81 | 0
| PM TIME |  | 27500 | 25664 | 1836
| Misc. |  | 495.75 | 495.75 | 0
| Innovative Engineers |  | 19655 | 12170 | 7485
| Florida Detention Systems |  | 320380.72 | 0 | 320380.72
| Boyd Jones |  | 12933.89 | 11718.55 | 1215.34
| Total Project Cost | 400528.13 | 391957.17 | 61040.11 | 330917.06 | 8570.96

## 9370.00 Funds Rec'd
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  | Major Program 4B01
Funds Rec'd
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds received from Agency | JV1 655ISP4413001 | 2024-05-23 | 527.49 | 527.49
|  |  | May Interest ISP DR 6-800-512 | CR 6554424163001 | 2024-06-12 | 0.64 | 0.64
| Total Requested | 0 | Total Transferred |  |  | 528.13 | 528.13

## #9370.00 Boyd Jones
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  | Major Program 4B01
Boyd Jones |  |  | Vendor:00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524342800 | 2023-12-08 | PO Procore | 11520.89 | 11520.89 |  |  | 11520.89
PRC 3352434PA2800 | 2024-01-18 | Inv. 9370.00-01 |  | 11520.89 | 2241.77 | 2241.77 | 9279.12
PRC 3352434PB2800 | 2024-02-26 | Inv. 9370.00-02 |  | 11520.89 | 1007.24 | 3249.01 | 8271.88
PRC 3352434PC2800 | 2024-03-19 | Inv. 9370.00-03 |  | 11520.89 | 1444.67 | 4693.68 | 6827.21
PRC 3352434PD2800 | 2024-04-09 | Inv. 9370.00-04 |  | 11520.89 | 1974.19 | 6667.87 | 4853.02
PRC 3352434PE2800 | 2024-05-10 | Inv. 9370.00-05 |  | 11520.89 | 2860.56 | 9528.43 | 1992.46 | FY24
PO 33525342800 | 2024-07-24 | Roll to FY25 |  | 11520.89 |  | 9528.43 | 1992.46
PRC 3352534PF2800 | 2024-08-12 | Inv. 9370.00-06 |  | 11520.89 | 518.01 | 10046.44 | 1474.45
PRC 3352534PG2800 | 2024-09-23 | Inv. 9370.00-07 - Final | -529.08 | 10991.81 | 945.37 | 10991.81 | 0
|  |  |  | 10991.81 |  | 10991.81 | 0
|  |  |  | 10991.81 |  | 10991.81 | 0
|  |  |  | 10991.81 |  | 10991.81 | 0
|  |  |  | 10991.81 |  | 10991.81 | 0
|  | Totals: | 10991.81 |  | 10991.81 |  | 0 | FINAL
|  | CM Services | 10804.81 |  | 10804.81 |  | 0
|  | Reimbursables | 187 |  | 187 |  | 0
|  | Totals: | 10991.81 |  | 10991.81 |  | 0

## #9370.00 PM TIME
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E2AH
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 27500 | 27500 |  |  | 27500
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 27500 | 646.97 | 646.97 | 26853.03
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 27500 | 4886.4 | 5533.37 | 21966.63
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 27500 | 392 | 5925.37 | 21574.63
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 27500 | 2874.3 | 8799.67 | 18700.33
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 27500 | 202.75 | 9002.42 | 18497.58
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 27500 | 1786.2 | 10788.62 | 16711.38
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 27500 | 274.12 | 11062.74 | 16437.26
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 27500 | 1383.5 | 12446.24 | 15053.76
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 27500 | 162.86 | 12609.1 | 14890.9
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 27500 | 1233.4 | 13842.5 | 13657.5
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 27500 | 136.94 | 13979.44 | 13520.56
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 27500 | 1215.4 | 15194.84 | 12305.16
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 27500 | 489.92 | 15684.76 | 11815.24
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 27500 | 4081.5 | 19766.26 | 7733.74
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 27500 | 51.08 | 19817.34 | 7682.66
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 27500 | 466.3 | 20283.64 | 7216.36
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 27500 | 77.44 | 20361.08 | 7138.92
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 27500 | 842 | 21203.08 | 6296.92
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 27500 | 153.95 | 21357.03 | 6142.97
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 27500 | 782.5 | 22139.53 | 5360.47
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 27500 | 118.75 | 22258.28 | 5241.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 27500 | 1057.4 | 23315.68 | 4184.32
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 27500 | 81.78 | 23397.46 | 4102.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 27500 | 549.4 | 23946.86 | 3553.14
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 27500 | 75.05 | 24021.91 | 3478.09
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 27500 | 497.7 | 24519.61 | 2980.39
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 27500 | 103.79 | 24623.4 | 2876.6
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 27500 | 1040.6 | 25664 | 1836
[5 empty] | 27500 |  | 25664 | 1836
[5 empty] | 27500 |  | 25664 | 1836
[5 empty] | 27500 |  | 25664 | 1836
|  |  | Totals: | 27500 |  | 25664 |  | 1836
Note on E9: Huggins, Joni [DAS]: On Thu, Nov 9, 2023 at 1:19 PM Adams, Brandon <brandon.adams@iowa.gov> wrote: Finance, Please set the PM Budget for 9370.00 MM23 to $10,000. Regards, Re: PM Time $John Adams, Brandon 10:00 AM (2 minutes ago) to me Finance, Please increase the following PM Time, 9297.00 in MM21 - Increase by $3000 9224.00 in MM23 - Increase by $4000 9370.00 in MM23 - Increase by $5000 Regards, Brandon Adams Adams, Brandon 1:42 PM (0 minutes ago) to me Finance, Please increase the follow PM Time, 9249.00 in MM22 increase by $4,000 9224.00 in MM23 increase by $1,000 9370.00 in MM23 increase by $3,000 Regards Re: PM Time Postings $Joni Adams, Brandon 7:27 AM (26 minutes ago) to me Finance, DA24 9414.00 Needs a PM Time Budget set - currently (2939.13) Please set PM Time budget at $10,000.00 MM22 9302.00 (82.36) Increase PM time by $1500 MM23 9317.00 (865.96) Increase PM time by $5,000 MM23 9370.00 (1,722.26) Increase PM time by $5000 Regards, Brandon Adams Adams, Brandon 8:37 AM (50 minutes ago) to me Please increase my PM Time by $2000.00 for MM23 9370.00 Regards, Brandon Adams

## #9370.00 Misc
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 165 | 165
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 165 | 330
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -330 | 0
PRC 33524211904 | 2024-07-29 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL661 | 172.25 | 172.25
PRC 33525261905 | 2024-09-17 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV042841 | 323.5 | 495.75
495.75
495.75
495.75
495.75
495.75
495.75
495.75
|  |  |  | Totals: |  | 495.75

## #9370.00 Innovative Engineers
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  | Major Program 4B01
Innovative Engineers |  |  | Vendor:00003080298
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 937000-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524003901 | 2024-01-03 | PO Procore | 19655 | 19655 |  |  | 19655
PRC 3352400PA3901 | 2024-05-07 | Inv. 9370.00-01 |  | 19655 | 12170 | 12170 | 7485 | FY24
PO 33525003901 | 2024-07-24 | Roll to FY25 |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  |  |  | 19655 |  | 12170 | 7485
|  | Totals: | 19655 |  | 12170 |  | 7485
|  | Design Development | 5570 |  | 5570 |  | 0
|  | Construction Documents | 6600 |  | 6600 |  | 0
|  | Bidding Assistance | 2270 |  |  |  | 2270
|  | Construction Phase | 3285 |  |  |  | 3285
|  | Closeout Phase | 1930 |  |  |  | 1930
|  | Totals: | 19655 |  | 12170 |  | 7485

## #9370.00 Florida Detention
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  | Major Program 4B01
Florida DetentionSystem |  |  | Vendor:00003222752
Acct. Codes-0017-335-MM23-9255 |  |  | RFP 937000-02
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525268902 | 2024-09-24 | PO Procore | 296000 | 296000 |  |  | 296000
PO 33525268902 | 2024-12-27 | CO #1 | 24380.72 | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  |  |  | 320380.72 |  | 0 | 320380.72
|  | Totals: | 320380.72 |  | 0 |  | 320380.72

## #9370.00 Boyd Jones (2)
DOC ISP Perimeter Fence Deterrent System Replacement
Project # 9370.00
Program code 937000 |  |  | Major Program 4B01
Boyd Jones |  |  | Vendor:00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525288904 | 2024-10-14 | PO Procore | 12933.89 | 12933.89 |  |  | 12933.89
PRC 3352528PA8904 | 2024-10-24 | Inv. 9370.00-001* |  | 12933.89 | 2135.36 | 2135.36 | 10798.53
PRC 3352528PB8904 | 2024-11-22 | Inv. 9370.00-002* |  | 12933.89 | 2676.39 | 4811.75 | 8122.14
PRC 3352528PC8904 | 2024-12-16 | Inv. 9370.00-003* |  | 12933.89 | 2762.72 | 7574.47 | 5359.42
PRC 3352528PD8904 | 2025-01-24 | Inv. 9370.00-004* |  | 12933.89 | 4144.08 | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  |  |  | 12933.89 |  | 11718.55 | 1215.34
|  | Totals: | 12933.89 |  | 11718.55 |  | 1215.34
|  | CM Services | 11945.89 |  | 11718.55 |  | 227.34
|  | Reimbursables | 988 |  |  |  | 988
|  | Totals: | 12933.89 |  | 11718.55 |  | 1215.34
**Inv. 9370.00-0X was used in a previous tab by this vendor
Please use Inv. 9370.00-001

## RECAP #9371.00
DPS Post 3 Parking Lot Replacement
Project # 9371.00
| Program code 937100 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM23
Project Manager -Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 145000
C | Boyd Jones |  | 6146.17 | 6146.17 | 0
| PM TIME |  | 19000 | 10858.94 | 8141.06
| Misc. |  | 300 | 300 | 0
C | Samuels Group |  | 8560.9 | 8560.9 | 0
| Snyder & Associates |  | 47081 | 36895 | 10186
| Total Project Cost | 145000 | 81088.07 | 62761.01 | 18327.06 | 63911.93

## #9371.00 Boyd Jones
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager -Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010902 | 2024-01-10 | PO Procore | 11217.74 | 11217.74 |  |  | 11217.74
PRC 3352401PA0902 | 2024-02-26 | Inv. 9371.00-01 |  | 11217.74 | 874.86 | 874.86 | 10342.88
PRC 3352401PB0902 | 2024-03-18 | Inv. 9371.00-02 |  | 11217.74 | 1351.71 | 2226.57 | 8991.17
PRC 3352401PC0902 | 2024-04-09 | Inv. 9371.00-03 |  | 11217.74 | 1628.85 | 3855.42 | 7362.32
PRC 3352401PD0902 | 2024-08-09 | Inv. 9371.00-04 |  | 11217.74 | 1323.8 | 5179.22 | 6038.52
PRC 3352401PE0902 | 2024-06-01 | Inv. 9371.00-05-Final | -5071.57 | 6146.17 | 966.95 | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  |  |  | 6146.17 |  | 6146.17 | 0
|  | Totals: | 6146.17 |  | 6146.17 |  | 0 | FINAL
|  | CM Services | 6026.17 |  | 6026.17 |  | 0
|  | Reimbursables | 120 |  | 120 |  | 0
|  | Totals: | 6146.17 |  | 6146.17 |  | 0

## #9371.00 PM TIME
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E2AI
Project Manager -Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 19000 | 19000 |  |  | 19000
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 19000 | 49.3 | 49.3 | 18950.7
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 19000 | 373.9 | 423.2 | 18576.8
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 19000 | 20.17 | 443.37 | 18556.63
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 19000 | 149.6 | 592.97 | 18407.03
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 19000 | 55.69 | 648.66 | 18351.34
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 19000 | 488.6 | 1137.26 | 17862.74
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 19000 | 121.35 | 1258.61 | 17741.39
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 19000 | 611.5 | 1870.11 | 17129.89
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 19000 | 101.25 | 1971.36 | 17028.64
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 19000 | 767.9 | 2739.26 | 16260.74
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 19000 | 123.98 | 2863.24 | 16136.76
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 19000 | 1105.6 | 3968.84 | 15031.16
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 19000 | 79 | 4047.84 | 14952.16
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 19000 | 651.2 | 4699.04 | 14300.96
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 19000 | 69.13 | 4768.17 | 14231.83
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 19000 | 754.7 | 5522.87 | 13477.13
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 19000 | 47.46 | 5570.33 | 13429.67
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 19000 | 243 | 5813.33 | 13186.67
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 19000 | 218.63 | 6031.96 | 12968.04
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 19000 | 1945.4 | 7977.36 | 11022.64
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 19000 | 247.88 | 8225.24 | 10774.76
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 19000 | 1656.3 | 9881.54 | 9118.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 19000 | 72.1 | 9953.64 | 9046.36
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 19000 | 480.8 | 10434.44 | 8565.56
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 19000 | 38.4 | 10472.84 | 8527.16
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 19000 | 386.1 | 10858.94 | 8141.06
[5 empty] | 19000 |  | 10858.94 | 8141.06
[5 empty] | 19000 |  | 10858.94 | 8141.06
[5 empty] | 19000 |  | 10858.94 | 8141.06
|  |  | Totals: | 19000 |  | 10858.94 |  | 8141.06
Note on E9: Jurgenson, John [DAS]: 9371.00 - DPS Post 3 Parking Lot Replacement Inbox Trower, James 3:54 PM (0 minutes ago) to me Finance - Please set up $6,000 in PM Time for project 9371.00 (MM23). Thanks

## #9371.00 Misc
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 849
Project Manager -Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 55 | 55
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 82.5 | 137.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -137.5 | 0
PRC 33525344902 | 2024-12-09 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV044444 | 300 | 300
300
300
300
300
300
300
300
300
|  |  |  | Totals: |  | 300

## #9371.00 Samuels Group
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager -Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524143907 | 2024-05-22 | PO Procore | 8674.89 | 8674.89 |  |  | 8674.89
PRC 3352414PA3907 | 2024-07-11 | Inv. 7697.01.937100 |  | 8674.89 | 548.89 | 548.89 | 8126 | FY24
PO 33525143907 | 2024-07-24 | Roll to FY25 |  | 8674.89 |  | 548.89 | 8126
PRC 3352514PB3907 | 2024-09-06 | Inv. 7697.02937100 |  | 8674.89 | 2155.75 | 2704.64 | 5970.25
PRC 3352514PC3907 | 2024-10-02 | Inv. 7697.03937100 |  | 8674.89 | 2605.81 | 5310.45 | 3364.44
PRC 3352514PD3907 | 2024-11-06 | Inv. 7697.04937100 |  | 8674.89 | 2441.33 | 7751.78 | 923.11
PRC 3352514PE3907 | 2024-11-20 | Inv. 7697.05937100-FINAL | -113.99 | 8560.9 | 809.12 | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  |  |  | 8560.9 |  | 8560.9 | -7.816e-13
|  | Totals: | 8560.9 |  | 8560.9 |  | 0 | FINAL
|  | CM Services | 8434.89 |  | 8434.89 |  | 0
|  | Reimbursables | 126.01 |  | 126.01 |  | 0
|  | Totals: | 8560.9 |  | 8560.9 |  | 0

## #9371.00 Snyder & Associates
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Synder & Associates |  |  | Vendor: 00002119810
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 937100-02
Project Manager -Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525208916 | 2024-07-26 | PO Procore | 47081 | 47081 |  |  | 47081
PRC 3352520PA8916 | 2024-10-09 | Inv. 124.0835.10-1 |  | 47081 | 25687 | 25687 | 21394
PRC 3352520PB8916 | 2024-12-06 | Inv. 9371.00-02 |  | 47081 | 11208 | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  |  |  | 47081 |  | 36895 | 10186
|  | Totals: | 47081 |  | 36895 |  | 10186
|  | Design 50% | 13034 |  | 13034 |  | 0
|  | Design 95% | 7402 |  | 7402 |  | 0
|  | Design 100% | 7386 |  | 7386 |  | 0
|  | Bidding | 2492 |  | 1246 |  | 1246
|  | Construction Admin | 8940 |  |  |  | 8940
|  | Geotechnical Work Base | 2675 |  | 2675 |  | 0
|  | Survey | 5152 |  | 5152 |  | 0
|  | Totals: | 47081 |  | 36895 |  | 10186

## RECAP #9373.00
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
| Program code 937300 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM23
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 375000
C | DCI Group |  | 35148.55 | 35148.55 | 0
| PM TIME |  | 19000 | 16932.05 | 2067.95
| Misc. |  | 2991.26 | 2991.26 | 0
| Shive Hattery |  | 35826 | 33126 | 2700
| Core Construction |  | 198310 | 136564.4 | 61745.6
| DCI Group (2) |  | 58911.79 | 31547.16 | 27364.63
| Total Project Cost | 375000 | 350187.6 | 256309.42 | 93878.18 | 24812.4

## #9373.00 DCI Group
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524033905 | 2024-02-01 | PO Procore | 35849.31 | 35849.31 |  |  | 35849.31
PRC 3352403PA3905 | 2024-03-05 | Inv. 24-001 PC-01 |  | 35849.31 | 8414.21 | 8414.21 | 27435.1
PRC 3352403PB3905 | 2024-05-02 | Inv. 24-001 PC 02 |  | 35849.31 | 3740.71 | 12154.92 | 23694.39
PRC 3352403PC3905 | 2024-06-17 | Inv. 24-001 PC 03 |  | 35849.31 | 3258.65 | 15413.57 | 20435.74
PRC 3352403PD3905 | 2024-07-22 | Inv. 24-001 PC 04 |  | 35849.31 | 4565.31 | 19978.88 | 15870.43 | FY24
PO 33525033905 | 2024-07-24 | Roll to FY25 |  | 35849.31 |  | 19978.88 | 15870.43
PRC 3352503PE3905 | 2024-08-15 | Inv. 24-001 PC 05 |  | 35849.31 | 2874.02 | 22852.9 | 12996.41
PRC 3352503PF3905 | 2024-09-26 | Inv. 24-001 PC 06 |  | 35849.31 | 2655.64 | 25508.54 | 10340.77
PRC 3352503PG3905 | 2024-10-18 | Inv. 24-001 PC-07 |  | 35849.31 | 6700.01 | 32208.55 | 3640.76
PRC 3352503PH3905 | 2024-11-22 | Inv. 24-001 PC 08 |  | 35849.31 | 1050 | 33258.55 | 2590.76
PRC 3352503PI3905 | 2024-12-20 | Inv. 24-001 PC 09 FINAL | -700.76 | 35148.55 | 1890 | 35148.55 | -3.4106e-12
|  |  |  | 35148.55 |  | 35148.55 | -3.4106e-12
|  |  |  | 35148.55 |  | 35148.55 | -3.4106e-12
|  | Totals: | 35148.55 |  | 35148.55 |  | 0 | FINAL
|  | CM Staff Hours | 15847.9 |  | 15847.9 |  | 0
|  | Reimbursables | 19300.65 |  | 19300.65 |  | 0
|  | Totals: | 35148.55 |  | 35148.55 |  | 0

## #9373.00 PM TIME
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS: E2BC
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 19000 | 19000 |  |  | 19000
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 19000 | 191.22 | 191.22 | 18808.78
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 19000 | 1687.4 | 1878.62 | 17121.38
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 19000 | 389.21 | 2267.83 | 16732.17
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 19000 | 1963.9 | 4231.73 | 14768.27
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 19000 | 191.24 | 4422.97 | 14577.03
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 19000 | 1451.2 | 5874.17 | 13125.83
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 19000 | 76.14 | 5950.31 | 13049.69
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 19000 | 672.2 | 6622.51 | 12377.49
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 19000 | 224.72 | 6847.23 | 12152.77
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 19000 | 1861.3 | 8708.53 | 10291.47
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 19000 | 37.45 | 8745.98 | 10254.02
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 19000 | 339.6 | 9085.58 | 9914.42
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 19000 | 105.18 | 9190.76 | 9809.24
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 19000 | 1151.4 | 10342.16 | 8657.84
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 19000 | 255.21 | 10597.37 | 8402.63
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 19000 | 1300.2 | 11897.57 | 7102.43
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 19000 | 142.42 | 12039.99 | 6960.01
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 19000 | 1267.8 | 13307.79 | 5692.21
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 19000 | 234.11 | 13541.9 | 5458.1
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 19000 | 1561 | 15102.9 | 3897.1
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 19000 | 162.05 | 15264.95 | 3735.05
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 19000 | 1075.2 | 16340.15 | 2659.85
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 19000 | 54 | 16394.15 | 2605.85
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 19000 | 537.9 | 16932.05 | 2067.95
[5 empty] | 19000 |  | 16932.05 | 2067.95
[5 empty] | 19000 |  | 16932.05 | 2067.95
[5 empty] | 19000 |  | 16932.05 | 2067.95
|  |  | Totals: | 19000 |  | 16932.05 |  | 2067.95
Note on E9: Huggins, Joni [DAS]: Re: PM Time Postings Inbox Trower, James 10:52 AM (6 minutes ago) to me Finance - MM23 9373.00 - Increase PM Time by $8,000 MM24 9380.00 - Increase PM Time by $6,000 Thanks, James Re: November PM Time - $Joni Trower, James Dec 12, 2024, 3:31 PM (4 days ago) to me Please see below in red: On Tue, Dec 10, 2024 at 10:08 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good morning DA24 9412.00 -856.71 Increase PM Time by $2,000 MM22 9364.00 -91.14 Increase PM Time by $2,000 MM23 9373.00 -340.15 Increase PM Time by $3,000 PARK 9411.0 -1,407.60 Increase PM Time by $10,000

## #9373.00 Misc
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524058800 | 2024-02-27 | 9500 | BRUM | Tree Doctor V#(00003166892) | Inv. 3326 | 900 | 900
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 55 | 955
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 82.5 | 1037.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -137.5 | 900
GAX 33524166906 | 2024-06-14 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2573132 | 725 | 1625
GAX 33524166907 | 2024-06-14 | 9500 | BRUM | Neumann Brother V#(00002106354) | Inv. 56254 | 370.51 | 1995.51
GAX 33524166908 | 2024-06-14 | 9500 | CNST | Bi-State Masonry V#(00002141136) | Inv. 5977 | 750 | 2745.51
PRC 33525295900 | 2024-10-21 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1030 | 245.75 | 2991.26
2991.26
2991.26
2991.26
2991.26
|  |  |  | Totals: |  | 2991.26

## #9373.00 Shive Hattery
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  | Major Program 4D04
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP937300-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524079900 | 2024-03-19 | PO Procore | 27876 | 27876 |  |  | 27876
PRC 3352407PA9900 | 2024-05-28 | Inv. 2142202241-101 |  | 27876 | 16676 | 16676 | 11200
PO 33524079900 | 2024-06-01 | CO #1 | 7950 | 35826 |  | 16676 | 19150
PRC 3352407PB9900 | 2024-07-08 | Inv. 2142202241-102 |  | 35826 | 10249.5 | 26925.5 | 8900.5 | FY24
PO 33525079900 | 2024-07-24 | Roll to FY25 |  | 35826 |  | 26925.5 | 8900.5
PRC 3352507PC9900 | 2024-08-15 | Inv. 2142202241-103 |  | 35826 | 1930 | 28855.5 | 6970.5
PRC 3352507PD9900 | 2024-09-13 | Inv. 2142202241-104 |  | 35826 | 360 | 29215.5 | 6610.5
PRC 3352507PE9900 | 2024-10-24 | Inv. 2142202241-105 |  | 35826 | 3043.5 | 32259 | 3567
PRC 3352507PF9900 | 2024-12-10 | Inv. 2142202241-106 |  | 35826 | 867 | 33126 | 2700
|  |  |  | 35826 |  | 33126 | 2700
|  |  |  | 35826 |  | 33126 | 2700
|  |  |  | 35826 |  | 33126 | 2700
|  |  |  | 35826 |  | 33126 | 2700
|  | Totals: | 35826 |  | 33126 |  | 2700
|  | Geotechnical Survey | 5500 |  | 5500 |  | 0
|  | Design Development | 6576 |  | 6576 |  | 0
|  | 50% CD's | 4600 |  | 4600 |  | 0
|  | 100% CD's | 4300 |  | 4300 |  | 0
|  | Bidding/Negotiation | 1800 |  | 1800 |  | 0
|  | Construction Phase | 5100 |  | 3672 |  | 1428
|  | CO #1 | 7950 |  | 6678 |  | 1272
|  | Totals: | 35826 |  | 33126 |  | 2700

## #9373.00 Core Contruction
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  | Major Program 4D04
Core Construction |  |  | Vendor: 00003201207
Acct. Codes-0017-335-MM23-9260 |  |  | RFB#937300-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525249907 | 2024-09-05 | PO Procore | 198310 | 198310 |  |  | 198310
PRC 3352524PA9907 | 2024-10-04 | Inv. 9373.00-01 |  | 198310 | 37647.55 | 37647.55 | 160662.45 | 1981.45
PRC 3352524PB9907 | 2024-11-04 | Inv. 9373.00-02 |  | 198310 | 66085.8 | 103733.35 | 94576.65 | 5459.65
PRC 3352524PC9907 | 2024-12-03 | Inv. 9373.00-03 |  | 198310 | 30175.8 | 133909.15 | 64400.85 | 7047.85
PRC 3352524PD9907 | 2024-12-27 | Inv. 9373.00-04 |  | 198310 | 2655.25 | 136564.4 | 61745.6 | 7187.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  |  |  | 198310 |  | 136564.4 | 61745.6
|  | Totals: | 198310 |  | 136564.4 |  | 61745.6

## #9373.00 DCI Group (2)
DAS TH Terrace Rd Retaining Wall Repairs
Project # 9373.00
Program code 937300 |  |  | Major Program 4D04
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP937300-01
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525282905 | 2024-10-08 | PO Procore | 55911.79 | 55911.79 |  |  | 55911.79
PRC 3352528PA2905 | 2024-11-25 | Inv. 24-001 CA 01 |  | 55911.79 | 13894.94 | 13894.94 | 42016.85
PRC 3352528PB2905 | 2024-12-20 | Inv. 24-001 CA 02 |  | 55911.79 | 14367.04 | 28261.98 | 27649.81
PO 33525282905 | 2024-12-27 | CO #1 | 3000 | 58911.79 |  | 28261.98 | 30649.81
PRC 3352528PC2905 | 2025-01-08 | Inv. 24-001 CA 03 |  | 58911.79 | 3285.18 | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  |  |  | 58911.79 |  | 31547.16 | 27364.63
|  | Totals: | 58911.79 |  | 31547.16 |  | 27364.63
|  | CM Staff Hours | 40911.79 |  | 15384.08 |  | 25527.71
|  | Reimbursables | 15000 |  | 15000 |  | 0
|  | CO #1 | 3000 |  | 1163.08 |  | 1836.92
|  | Totals: | 58911.79 |  | 31547.16 |  | 27364.63

## RECAP #9388.00
DPS P08 Water Infiltration Mitigation
Project # 9388.00
| Program code 938800 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 134500
C | Boyd Jones |  | 4102.47 | 4102.47 | 0
| PM TIME |  | 10000 | 8581.64 | 1418.36
| Misc. |  | 1721.25 | 1721.25 | 0
| DCI Group |  | 13384.49 | 9903.57 | 3480.92
| Cannon Moss Brygger |  | 41705 | 17723.59 | 23981.41
| Total Project Cost | 134500 | 70913.21 | 42032.52 | 28880.69 | 63586.79

## #9388.00 Boyd Jones
DPS P08 Water Infiltration Mitigation
Project # 9388.00
Program code 938800 |  |  | Major Program 4E12
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524067902 | 2024-03-07 | PO Procore | 15879.12 | 15879.12 |  |  | 15879.12
PRC 3352406PA7902 | 2024-04-10 | Inv. 9388.00-01 |  | 15879.12 | 702.19 | 702.19 | 15176.93
PRC 3352406PB7902 | 2024-05-06 | Inv. 9388.00-02 |  | 15879.12 | 1863.52 | 2565.71 | 13313.41
PRC 3352406PC7902 | 2024-05-29 | Inv. 9388.00-03-FINAL | -11776.65 | 4102.47 | 1536.76 | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  |  |  | 4102.47 |  | 4102.47 | 0
|  | Totals: | 4102.47 |  | 4102.47 |  | 0 | FINAL
|  | CM Services | 4040.47 |  | 4040.47 |  | 0
|  | Reimbursables | 62 |  | 62 |  | 0
|  | Totals: | 4102.47 |  | 4102.47 |  | 0

## #9388.00 PM TIME
DPS P08 Water Infiltration Mitigation
Project # 9388.00
Program code 938800 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10000 | 98.48 | 98.48 | 9901.52
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10000 | 496.3 | 594.78 | 9405.22
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10000 | 69.4 | 664.18 | 9335.82
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10000 | 523.4 | 1187.58 | 8812.42
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 10000 | 97.05 | 1284.63 | 8715.37
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 10000 | 859.1 | 2143.73 | 7856.27
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 10000 | 92.13 | 2235.86 | 7764.14
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10000 | 770.7 | 3006.56 | 6993.44
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10000 | 33.55 | 3040.11 | 6959.89
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10000 | 307.4 | 3347.51 | 6652.49
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10000 | 145.46 | 3492.97 | 6507.03
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10000 | 1584.7 | 5077.67 | 4922.33
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10000 | 301.82 | 5379.49 | 4620.51
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10000 | 1536.1 | 6915.59 | 3084.41
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10000 | 67.76 | 6983.35 | 3016.65
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10000 | 602.2 | 7585.55 | 2414.45
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10000 | 40.47 | 7626.02 | 2373.98
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10000 | 270.6 | 7896.62 | 2103.38
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10000 | 40.33 | 7936.95 | 2063.05
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10000 | 266.6 | 8203.55 | 1796.45
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 34.59 | 8238.14 | 1761.86
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 343.5 | 8581.64 | 1418.36
[5 empty] | 10000 |  | 8581.64 | 1418.36
[5 empty] | 10000 |  | 8581.64 | 1418.36
[5 empty] | 10000 |  | 8581.64 | 1418.36
|  |  | Totals: | 10000 |  | 8581.64 |  | 1418.36

## #9388.00 Misc
DPS P08 Water Infiltration Mitigation
Project # 9388.00
Program code 938800 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525261900 | 2024-09-17 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2597493 | 1421.25 | 1421.25
PRC 33525318902 | 2024-11-13 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV043593 | 300 | 1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
1721.25
|  |  |  | Totals: |  | 1721.25

## #9388.00 DCI Group
DPS P08 Water Infiltration Mitigation
Project # 9388.00
Program code 938800 |  |  | Major Program 4E12
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524157900 | 2024-06-05 | PO Procore | 13384.49 | 13384.49 |  |  | 13384.49
PRC 3352415PA7900 | 2024-07-22 | Inv. 24-023 PC 01 |  | 13384.49 | 2570.23 | 2570.23 | 10814.26 | FY24
PO 33525157900 | 2024-07-24 | Roll to FY25 |  | 13384.49 |  | 2570.23 | 10814.26
PRC 3352515PB7900 | 2024-08-22 | Inv. 24-023 PC 02 |  | 13384.49 | 2063.05 | 4633.28 | 8751.21
PRC 3352515PC7900 | 2024-09-27 | Inv. 24-023 PC 03 |  | 13384.49 | 3859.96 | 8493.24 | 4891.25
PRC 3352515PD7900 | 2024-10-17 | Inv. 24-023 PC 04 |  | 13384.49 | 1410.33 | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  |  |  | 13384.49 |  | 9903.57 | 3480.92
|  | Totals: | 13384.49 |  | 9903.57 |  | 3480.92
|  | CM Services | 12884.49 |  | 9667.57 |  | 3216.92
|  | Reimbursables | 500 |  | 236 |  | 264
|  | Totals: | 13384.49 |  | 9903.57 |  | 3480.92

## #9388.00 Cannon Moss Brygger
DPS P08 Water Infiltration Mitigation
Project # 9388.00
Program code 938800 |  |  | Major Program 4E12
Cannon Moss Brygger |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 938800-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525211907 | 2024-07-29 | PO Procore | 31205 | 31205 |  |  | 31205
PRC 3352521PA1907 | 2024-10-16 | Inv. 64393 |  | 31205 | 5610.2 | 5610.2 | 25594.8
PRC 3352521PB1907 | 2024-10-17 | Inv. 64634 |  | 31205 | 9530.05 | 15140.25 | 16064.75
PRC 3352521PC1907 | 2024-10-22 | Inv. 64717 |  | 31205 | 2081.3 | 17221.55 | 13983.45
PRC 3352521PD1907 | 2024-11-13 | Inv. 64837 |  | 31205 | 142.04 | 17363.59 | 13841.41
PO 33525211907 | 2024-12-06 | CO #001 | 10500 | 41705 |  | 17363.59 | 24341.41
PRC 3352521PE1907 | 2025-01-27 | Inv. 65008 |  | 41705 | 360 | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  |  |  | 41705 |  | 17723.59 | 23981.41
|  | Totals: | 41705 |  | 17723.59 |  | 23981.41
|  | Project Start up | 1346 |  | 1346 |  | 0
|  | Construction Documents | 11707 |  | 11707 |  | 0
|  | Bidding/Negotiations | 3841 |  | 3841 |  | 0
|  | Construction Phase | 12972 |  |  |  | 12972
|  | Reimbursables | 1339 |  | 469.59 |  | 869.41
|  | CO #001 | 10500 |  | 360 |  | 10140
|  | Totals: | 41705 |  | 17723.59 |  | 23981.41

## RECAP #9389.00
DOC 2JD BCRC ERV Replacement
Project # 9389.00
| Program code 938900 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 281385.78
C | Boyd Jones |  | 4430.54 | 4430.54 | 0
| PM TIME |  | 15000 | 10566.43 | 4433.57
| Misc. |  | 1826.8 | 1826.8 | 0
C | DCI Group |  | 10870.08 | 10870.08 | 0
| Innovative Engineers |  | 21535 | 12475 | 9060
| Baker Group |  | 180783 | 47663.04 | 133119.96
| DCI Group(2) |  | 21539.26 | 5121.96 | 16417.3
| Total Project Cost | 281385.78 | 255984.68 | 92953.85 | 163030.83 | 25401.1

## #9389.00 Boyd Jones
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524067904 | 2024-03-07 | PO Procore | 15384.14 | 15384.14 |  |  | 15384.14
PRC 3352406PA7904 | 2024-04-10 | Inv. 9389.00-01 |  | 15384.14 | 1482.08 | 1482.08 | 13902.06
PRC 3352406PB7904 | 2024-05-06 | Inv. 9389.00-02 |  | 15384.14 | 1544.08 | 3026.16 | 12357.98
PRC 3352406PC7904 | 2024-05-28 | Inv. 9389.00-03-FINAL | -10953.6 | 4430.54 | 1404.38 | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  |  |  | 4430.54 |  | 4430.54 | 0
|  | Totals: | 4430.54 |  | 4430.54 |  | 0 | FINAL
|  | CM Services | 4368.54 |  | 4368.54 |  | 0
|  | Reimbursables | 62 |  | 62 |  | 0
|  | Totals: | 4430.54 |  | 4430.54 |  | 0

## #9389.00 PM TIME
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E2BM
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15000 | 15000 |  |  | 15000
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 15000 | 107.55 | 107.55 | 14892.45
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 15000 | 541.6 | 649.15 | 14350.85
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 15000 | 69.4 | 718.55 | 14281.45
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 15000 | 523.4 | 1241.95 | 13758.05
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30 2024 |  | 15000 | 111.28 | 1353.23 | 13646.77
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30 2024 |  | 15000 | 988.6 | 2341.83 | 12658.17
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 15000 | 104.4 | 2446.23 | 12553.77
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 15000 | 872.3 | 3318.53 | 11681.47
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 15000 | 31.17 | 3349.7 | 11650.3
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 15000 | 281.2 | 3630.9 | 11369.1
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 15000 | 57.3 | 3688.2 | 11311.8
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 15000 | 622.1 | 4310.3 | 10689.7
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 15000 | 170.28 | 4480.58 | 10519.42
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 15000 | 868.8 | 5349.38 | 9650.62
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 15000 | 113.54 | 5462.92 | 9537.08
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 15000 | 1010.4 | 6473.32 | 8526.68
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 15000 | 193.64 | 6666.96 | 8333.04
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 15000 | 1293 | 7959.96 | 7040.04
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15000 | 159.1 | 8119.06 | 6880.94
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15000 | 1057.7 | 9176.76 | 5823.24
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15000 | 125.87 | 9302.63 | 5697.37
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15000 | 1263.8 | 10566.43 | 4433.57
[5 empty] | 15000 |  | 10566.43 | 4433.57
[5 empty] | 15000 |  | 10566.43 | 4433.57
[5 empty] | 15000 |  | 10566.43 | 4433.57
|  |  | Totals: | 15000 |  | 10566.43 |  | 4433.57

## #9389.00 Misc
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 222001
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525250913 | 2024-09-06 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2596428 | 1487.5 | 1487.5
PRC 33525298905 | 2024-10-22 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV043868 | 339.3 | 1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
1826.8
|  |  |  | Totals: |  | 1826.8

## #9389.00 DCI Group
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  | Major Program 4E01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021 for DCI
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524145801 | 2024-05-24 | PO Procore | 12806.08 | 12806.08 |  |  | 12806.08
PRC 3352414PA5801 | 2024-07-22 | Inv. 24-020 PC 01 |  | 12806.08 | 2401.17 | 2401.17 | 10404.91 | FY24
PO 33525145801 | 2024-07-24 | Roll to FY25 |  | 12806.08 |  | 2401.17 | 10404.91
PRC 3352514PB5801 | 2024-08-15 | Inv. 24-020 PC 02 |  | 12806.08 | 1521.54 | 3922.71 | 8883.37
PRC 3352514PC5801 | 2024-09-19 | Inv. 24-020 PC 03 |  | 12806.08 | 1677.37 | 5600.08 | 7206
PRC 3352514PD5801 | 2024-10-15 | Inv. 24-020 PC 04 |  | 12806.08 | 3579.4 | 9179.48 | 3626.6
PRC 3352514PE5801 | 2024-11-15 | Inv. 24-020 PC 05 FINAL | -1936 | 10870.08 | 1690.6 | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  |  |  | 10870.08 |  | 10870.08 | 0
|  | Totals: | 10870.08 |  | 10870.08 |  | 0 | FINAL
|  | Construction Management Staff Hours | 10870.08 |  | 10870.08 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Totals: | 10870.08 |  | 10870.08 |  | 0

## #9389.00 Innovative Engineers
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  | Major Program 4E01
Innovative Engineers |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 938900-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524150905 | 2024-05-29 | PO Procore | 21535 | 21535 |  |  | 21535
PRC 3352415PA0905 | 2024-07-10 | Inv. 9389.00-01 |  | 21535 | 2612.5 | 2612.5 | 18922.5 | FY24
PO 33525150905 | 2024-07-24 | Roll to FY25 |  | 21535 |  | 2612.5 | 18922.5
PRC 3352515PB0905 | 2024-09-24 | Inv. 9389.00-02 |  | 21535 | 9862.5 | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  |  |  | 21535 |  | 12475 | 9060
|  | Totals: | 21535 |  | 12475 |  | 9060
|  | Design Development Docs | 5225 |  | 5225 |  | 0
|  | Construction Docs | 7250 |  | 7250 |  | 0
|  | Bidding & Negotiation | 2185 |  |  |  | 2185
|  | Construction Phase | 4850 |  |  |  | 4850
|  | Close Out Phase | 2025 |  |  |  | 2025
|  | Totals: | 21535 |  | 12475 |  | 9060

## #9389.00 Baker Group
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  | Major Program 4E01
Baker Group |  |  | Vendor: 00002109043
Acct. Codes-0017-335-MM23-9255 |  |  | RFB 938900-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525310904 | 2024-11-05 | PO Procore | 180783 | 180783 |  |  | 180783
PRC 3352531PA0904 | 2024-12-23 | Inv. 284257 |  | 180783 | 6813.04 | 6813.04 | 173969.96 | 358.58
PRC 3352531PB0904 | 2025-01-10 | Inv. 286995 |  | 180783 | 40850 | 47663.04 | 133119.96 | 2508.58
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  |  |  | 180783 |  | 47663.04 | 133119.96
|  | Totals: | 180783 |  | 47663.04 |  | 133119.96

## #9389.00 DCI Group (2)
DOC 2JD BCRC ERV Replacement
Project # 9389.00
Program code 938900 |  |  | Major Program 4E01
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525313902 | 2024-11-08 | PO Procore | 21539.26 | 21539.26 |  |  | 21539.26
PRC 3352531PA3902 | 2024-12-23 | Inv. 24-020 CA 01 |  | 21539.26 | 2366.84 | 2366.84 | 19172.42
PRC 3352531PB3902 | 2025-01-21 | Inv. 24-020 CA 02 |  | 21539.26 | 2755.12 | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  |  |  | 21539.26 |  | 5121.96 | 16417.3
|  | Totals: | 21539.26 |  | 5121.96 |  | 16417.3
|  | CM | 19539.26 |  | 5121.96 |  | 14417.3
|  | Reimbursables | 2000 |  |  |  | 2000
|  | Totals: | 21539.26 |  | 5121.96 |  | 16417.3

## RECAP #9404.00
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 771024.24
Boyd Jones |  | 17024.52 | 16357.8 | 666.72
PM TIME |  | 25000 | 10471.04 | 14528.96
Misc. |  | 504.66 | 504.66 | 0
Innovative Engineers |  | 14925 | 3245 | 11680
S&S Plumbing |  | 515735 | 0 | 515735
Boyd Jones(2) |  | 46429.69 | 0 | 46429.69
Total Project Cost | 771024.24 | 619618.87 | 30578.5 | 589040.37 | 151405.37

## #9404.00 Boyd Jones
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524134900 | 2024-05-13 | PO Procore | 17024.52 | 17024.52 |  |  | 17024.52
PRC 3352413PA4900 | 2024-07-18 | Inv. 9404.00-01 |  | 17024.52 | 1036.02 | 1036.02 | 15988.5 | FY24
PO 33525134900 | 2024-07-24 | Roll to FY25 |  | 17024.52 |  | 1036.02 | 15988.5
PRC 3352513PB4900 | 2024-08-15 | Inv. 9404.00-02 |  | 17024.52 | 1554.03 | 2590.05 | 14434.47
PRC 3352513PC4900 | 2024-09-23 | Inv. 9404.00-03 |  | 17024.52 | 2916.67 | 5506.72 | 11517.8
PRC 3352513PD4900 | 2024-10-22 | Inv. 9404.00-04 |  | 17024.52 | 5606.02 | 11112.74 | 5911.78
PRC 3352513PE4900 | 2024-11-06 | Inv. 9404.00-05 |  | 17024.52 | 5245.06 | 16357.8 | 666.72
PO 33525134900 | 2025-01-31 | CO #1 (No Cost CO) | 0 | 17024.52 |  | 16357.8 | 666.72
|  |  |  | 17024.52 |  | 16357.8 | 666.72
|  |  |  | 17024.52 |  | 16357.8 | 666.72
|  |  |  | 17024.52 |  | 16357.8 | 666.72
|  |  |  | 17024.52 |  | 16357.8 | 666.72
|  |  |  | 17024.52 |  | 16357.8 | 666.72
|  | Totals: | 17024.52 |  | 16357.8 |  | 666.72
|  | CM Services | 16936.52 |  | 16269.8 |  | 666.72
|  | Reimbursables | 88 |  | 88 |  | 0
|  | CO #1 Moved 412.00 from Reimbursables to CM Service | 0 |  | 0 |  | 0
|  | Totals: | 17024.52 |  | 16357.8 |  | 666.72

## #9404.00 PM TIME
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS E2D6
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 25000 | 25000 |  |  | 25000
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 25000 | 122.69 | 122.69 | 24877.31
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 25000 | 1025.8 | 1148.49 | 23851.51
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 25000 | 20.33 | 1168.82 | 23831.18
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 25000 | 187.3 | 1356.12 | 23643.88
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 25000 | 60.83 | 1416.95 | 23583.05
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 25000 | 661.4 | 2078.35 | 22921.65
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 25000 | 230.42 | 2308.77 | 22691.23
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 25000 | 1173.5 | 3482.27 | 21517.73
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 25000 | 142.84 | 3625.11 | 21374.89
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 25000 | 1273.8 | 4898.91 | 20101.09
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 25000 | 296.92 | 5195.83 | 19804.17
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 25000 | 1977 | 7172.83 | 17827.17
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 25000 | 202.8 | 7375.63 | 17624.37
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 25000 | 1346.2 | 8721.83 | 16278.17
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 25000 | 158.91 | 8880.74 | 16119.26
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 25000 | 1590.3 | 10471.04 | 14528.96
[5 empty] | 25000 |  | 10471.04 | 14528.96
[5 empty] | 25000 |  | 10471.04 | 14528.96
[5 empty] | 25000 |  | 10471.04 | 14528.96
|  |  | Totals: | 25000 |  | 10471.04 |  | 14528.96

## #9404.00 Misc
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 174
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525311900 | 2024-11-06 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1176 | 304.66 | 304.66
PRC 33525024903 | 2025-01-24 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1375 | 200 | 504.66
504.66
504.66
504.66
504.66
504.66
504.66
504.66
504.66
504.66
504.66
|  |  |  | Totals: |  | 504.66

## #9404.00 Innovative Engineers
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Innovative Engineers Inc. |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM23-9260 |  |  | RFP940400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524144800 | 2024-05-23 | PO Procore | 14925 | 14925 |  |  | 14925
PRC 3352414PA4800 | 2024-07-22 | Inv. 9404.00-01 |  | 14925 | 3245 | 3245 | 11680 | FY24
PO 33525144800 | 2024-07-24 | Roll to FY25 |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  |  |  | 14925 |  | 3245 | 11680
|  | Totals: | 14925 |  | 3245 |  | 11680
|  | Design Development Documents | 3245 |  | 3245 |  | 0
|  | Construction Documents | 5600 |  |  |  | 5600
|  | Bidding or Negotiation Assistance | 1280 |  |  |  | 1280
|  | Construction Phase | 3200 |  |  |  | 3200
|  | Closeout Phase | 1600 |  |  |  | 1600
|  | Totals: | 14925 |  | 3245 |  | 11680

## #9404.00 S & S Plumbing
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
S & S Plumbing |  |  | Vendor: 00003036947
Acct. Codes-0017-335-MM23-9255 |  |  | RFP940400-02
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023904 | 2025-01-23 | PO Procore | 515735 | 515735 |  |  | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  |  |  | 515735 |  | 0 | 515735
|  | Totals: | 515735 |  | 0 |  | 515735

## #9404.00 Boyd Jones (2)
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525031907 | 2025-01-31 | PO Procore | 46429.69 | 46429.69 |  |  | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  |  |  | 46429.69 |  | 0 | 46429.69
|  | Totals: | 46429.69 |  | 0 |  | 46429.69
|  | CM Services | 19410.94 |  |  |  | 19410.94
|  | Reimbursables | 1250 |  |  |  | 1250
|  | Fee | 25768.75 |  |  |  | 25768.75
|  | Totals: | 46429.69 |  | 0 |  | 46429.69

## RECAP #9437.00
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
| Program code 943700 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM23
Project Manager -Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 146446
C | Shive Hattery |  | 0 | 0 | 0
| PM TIME |  | 13000 | 3871.16 | 9128.84
| Misc. |  | 0 | 0 | 0
| DCI Group |  | 23746.02 | 0 | 23746.02
| Shive Hattery(2) |  | 34850 | 0 | 34850
| Total Project Cost | 146446 | 71596.02 | 3871.16 | 67724.86 | 74849.98

## #9437.00 Shive Hattery
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
Program code 943700 |  |  | Major Program 4G01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP915500-01
Project Manager -Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525253901 | 2024-09-09 | PO Procore | 7840 | 7840 |  |  | 7840
PO 33525253901 | 2024-12-05 | Moving to X674 | -7840 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9437.00 PM TIME
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
Program code 943700 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 909U
Project Manager -Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 13000 | 13000 |  |  | 13000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 13000 | 59.44 | 59.44 | 12940.56
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 13000 | 304.7 | 364.14 | 12635.86
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 13000 | 177.36 | 541.5 | 12458.5
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 13000 | 1582 | 2123.5 | 10876.5
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 12.22 | 2135.72 | 10864.28
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 86.3 | 2222.02 | 10777.98
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 101.19 | 2323.21 | 10676.79
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 673.1 | 2996.31 | 10003.69
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 79.45 | 3075.76 | 9924.24
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 795.4 | 3871.16 | 9128.84
[5 empty] | 13000 |  | 3871.16 | 9128.84
[5 empty] | 13000 |  | 3871.16 | 9128.84
|  |  | Totals: | 13000 |  | 3871.16 |  | 9128.84

## #9437.00 Misc
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
Program code 943700 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 035
Project Manager -Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9437.00 DCI Group
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
Program code 943700 |  |  | Major Program 4G01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-DCI11012021
Project Manager -Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525340900 | 2024-12-05 | PO Procore | 23746.02 | 23746.02 |  |  | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  |  |  | 23746.02 |  | 0 | 23746.02
|  | Totals: | 23746.02 |  | 0 |  | 23746.02
|  | CM Services | 13746.02 |  |  |  | 13746.02
|  | Reimbursables | 10000 |  |  |  | 10000
|  | Totals: | 23746.02 |  | 0 |  | 23746.02

## #9437.00 Shive Hattery (2)
DAS CC Lot 21 Repairs Phase 3
Project # 9437.00
Program code 943700 |  |  | Major Program 4G01
Shive Hattery (2) |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM23-9260 |  |  | RFP 915500-01
Project Manager -Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525340908 | 2024-12-05 | PO Procore | 34850 | 34850 |  |  | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  |  |  | 34850 |  | 0 | 34850
|  | Totals: | 34850 |  | 0 |  | 34850
|  | Limited Topographic Survey | 4180 |  |  |  | 4180
|  | Parking Lot Design Services | 24030 |  |  |  | 24030
|  | Stair Replacement Design | 4920 |  |  |  | 4920
|  | Bidding Phase Services | 1720 |  |  |  | 1720
|  | Totals: | 34850 |  | 0 |  | 34850

## RECAP #9438.00
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 120000
McGough Construction |  | 13033.04 | 3376.28 | 9656.76
PM TIME |  | 4000 | 1899.18 | 2100.82
Misc. |  | 647.5 | 647.5 | 0
Genesis Architectural |  | 12800 | 0 | 12800
Total Project Cost | 120000 | 30480.54 | 5922.96 | 24557.58 | 89519.46

## #9438.00 McGough Construction
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525276906 | 2024-10-02 | PO Procore | 13033.04 | 13033.04 |  |  | 13033.04
PRC 3352527PA6906 | 2024-11-19 | Inv. 101174.017-PC01 |  | 13033.04 | 1826.29 | 1826.29 | 11206.75
PRC 3352527PB6906 | 2024-12-18 | Inv. 101174.017-PC02 |  | 13033.04 | 861.33 | 2687.62 | 10345.42
PRC 3352527PC6906 | 2025-01-21 | Inv. 101174.017-PC03 |  | 13033.04 | 688.66 | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  |  |  | 13033.04 |  | 3376.28 | 9656.76
|  | Totals: | 13033.04 |  | 3376.28 |  | 9656.76
|  | CM Services | 12833.04 |  | 3246.28 |  | 9586.76
|  | Reimbursables | 200 |  | 130 |  | 70
|  | Totals: | 13033.04 |  | 3376.28 |  | 9656.76

## #9438.00 PM TIME
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 909V
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4000 | 4000 |  |  | 4000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4000 | 55.79 | 55.79 | 3944.21
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4000 | 497.8 | 553.59 | 3446.41
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4000 | 39.77 | 593.36 | 3406.64
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4000 | 264.6 | 857.96 | 3142.04
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 4000 | 103.44 | 961.4 | 3038.6
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 4000 | 687.3 | 1648.7 | 2351.3
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 4000 | 22.78 | 1671.48 | 2328.52
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 4000 | 227.7 | 1899.18 | 2100.82
[5 empty] | 4000 |  | 1899.18 | 2100.82
[5 empty] | 4000 |  | 1899.18 | 2100.82
[5 empty] | 4000 |  | 1899.18 | 2100.82
[5 empty] | 4000 |  | 1899.18 | 2100.82
|  |  | Totals: | 4000 |  | 1899.18 |  | 2100.82
Note on E9: Huggins, Joni [DAS]: DAS Costs Budget for MM23 9438.00 $Joni Kleene, Jennifer Tue, Sep 3, 12:15 PM (1 day ago) to me Please create a DAS Costs budget for $4,000.00 for MM23 9438.00.

## #9438.00 Misc
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525029902 | 2025-01-29 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2623364 | 647.5 | 647.5
647.5
647.5
647.5
647.5
647.5
647.5
647.5
647.5
647.5
647.5
647.5
|  |  |  | Totals: |  | 647.5

## #9438.00 Genesis Architectural
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP945300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327901 | 2024-11-22 | PO Procore | 12800 | 12800 |  |  | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  |  |  | 12800 |  | 0 | 12800
|  | Totals: | 12800 |  | 0 |  | 12800
|  | Construction Docs | 6000 |  |  |  | 6000
|  | Bid Phase | 800 |  |  |  | 800
|  | Construction Phase | 6000 |  |  |  | 6000
|  | Totals: | 12800 |  | 0 |  | 12800

## RECAP #9439.00
DOC FDCF Unit K Pre-Cast Sealant Replacement
Project # 9439.00
Program code 943900 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 100000
McGough Construction |  | 13033.04 | 3341.74 | 9691.3
PM TIME |  | 4000 | 2020.59 | 1979.41
Misc. |  | 562.5 | 562.5 | 0
Genesis Architectural |  | 11300 | 0 | 11300
Total Project Cost | 100000 | 28895.54 | 5924.83 | 22970.71 | 71104.46

## #9439.00 McGough Construction
DOC FDCF Unit K Pre-Cast Sealant Replacement
Project # 9439.00
Program code 943900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525276908 | 2025-10-02 | PO Procore | 13033.04 | 13033.04 |  |  | 13033.04
PRC 3352527PA6908 | 2024-11-19 | Inv. 101174.018PC-01 |  | 13033.04 | 1791.75 | 1791.75 | 11241.29
PRC 3352527PB6908 | 2024-12-18 | Inv. 101174.018PC-02 |  | 13033.04 | 861.33 | 2653.08 | 10379.96
PRC 3352527PC6908 | 2025-01-21 | Inv. 101174.018PC-03 |  | 13033.04 | 688.66 | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  |  |  | 13033.04 |  | 3341.74 | 9691.3
|  | Totals: | 13033.04 |  | 3341.74 |  | 9691.3
|  | CM Services | 12833.04 |  | 3211.74 |  | 9621.3
|  | Reimbursables | 200 |  | 130 |  | 70
|  | Totals: | 13033.04 |  | 3341.74 |  | 9691.3

## #9439.00 PM TIME
DOC FDCF Unit K Pre-Cast Sealant Replacement
Project # 9439.00
Program code 943900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 909W
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4000 | 4000 |  |  | 4000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4000 | 55.79 | 55.79 | 3944.21
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4000 | 497.8 | 553.59 | 3446.41
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4000 | 46.09 | 599.68 | 3400.32
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4000 | 308.8 | 908.48 | 3091.52
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 4000 | 113.13 | 1021.61 | 2978.39
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 4000 | 748.5 | 1770.11 | 2229.89
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 4000 | 22.78 | 1792.89 | 2207.11
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 4000 | 227.7 | 2020.59 | 1979.41
[5 empty] | 4000 |  | 2020.59 | 1979.41
[5 empty] | 4000 |  | 2020.59 | 1979.41
[5 empty] | 4000 |  | 2020.59 | 1979.41
[5 empty] | 4000 |  | 2020.59 | 1979.41
|  |  | Totals: | 4000 |  | 2020.59 |  | 1979.41
Note on E9: Huggins, Joni [DAS]: New DAS Costs Budget for MM23 9439.00 DOC FDCF Unit K Pre-cast Sealant Replacement $Joni Kleene, Jennifer 10:09 AM (10 minutes ago) to me Please create a DAS Costs budget for $4,000.00 for MM23 Project 9439.00. Regards, Jennifer

## #9439.00 Misc
DOC FDCF Unit K Pre-Cast Sealant Replacement
Project # 9439.00
Program code 943900 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525029900 | 2025-01-29 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2623360 | 562.5 | 562.5
562.5
562.5
562.5
562.5
562.5
562.5
562.5
562.5
562.5
562.5
562.5
|  |  |  | Totals: |  | 562.5

## #9439.00 Genesis Architectural
DOC FDCF Unit K Pre-Cast Sealant Replacement
Project # 9439.00
Program code 943900 |  |  | Major Program 4B01
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM23-9260 |  |  | RFP945300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327902 | 2024-11-22 | PO Procore | 11300 | 11300 |  |  | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  |  |  | 11300 |  | 0 | 11300
|  | Totals: | 11300 |  | 0 |  | 11300
|  | Construction Docs | 4500 |  |  |  | 4500
|  | Bidding Phase | 800 |  |  |  | 800
|  | Construction Phase | 6000 |  |  |  | 6000
|  | Totals: | 11300 |  | 0 |  | 11300

## RECAP #9450.00
DOC MPFC North Parking Lot Replacement
Project # 9450.00
Program code 945000 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 370000
McGough Construction |  | 17314.84 | 3258.76 | 14056.08
PM TIME |  | 8000 | 1885.08 | 6114.92
Misc. |  | 0 | 0 | 0
Bolton & Menk |  | 32015 | 0 | 32015
Total Project Cost | 370000 | 57329.84 | 5143.84 | 52186 | 312670.16

## #9450.00 McGough Construction
DOC MPFC North Parking Lot Replacement
Project # 9450.00
Program code 945000 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM23-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525310909 | 2024-11-05 | PO Procore | 17314.84 | 17314.84 |  |  | 17314.84
PRC 3352531PA0909 | 2024-12-19 | Inv. 101368.002-PC01 |  | 17314.84 | 1520.6 | 1520.6 | 15794.24
PRC 3352531PA0909 | 2025-01-14 | Inv. 101368.002-PC02 |  | 17314.84 | 1738.16 | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  |  |  | 17314.84 |  | 3258.76 | 14056.08
|  | Totals: | 17314.84 |  | 3258.76 |  | 14056.08
|  | CM Services | 16474.84 |  | 3164.76 |  | 13310.08
|  | Reimbursables | 840 |  | 94 |  | 746
|  | Totals: | 17314.84 |  | 3258.76 |  | 14056.08

## #9450.00 PM TIME
DOC MPFC North Parking Lot Replacement
Project # 9450.00
Program code 945000 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx |  |  |  | eDAS 909X
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8000 | 45.07 | 45.07 | 7954.93
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8000 | 228.8 | 273.87 | 7726.13
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8000 | 28.45 | 302.32 | 7697.68
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8000 | 251.9 | 554.22 | 7445.78
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 8000 | 14.9 | 569.12 | 7430.88
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8000 | 99.8 | 668.92 | 7331.08
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 8000 | 46.66 | 715.58 | 7284.42
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 8000 | 311.4 | 1026.98 | 6973.02
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 8000 | 77.9 | 1104.88 | 6895.12
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 8000 | 780.2 | 1885.08 | 6114.92
[5 empty] | 8000 |  | 1885.08 | 6114.92
[5 empty] | 8000 |  | 1885.08 | 6114.92
|  |  | Totals: | 8000 |  | 1885.08 |  | 6114.92
Note on E9: Huggins, Joni [DAS]: 9450.00 DOC MPCF North Parking Lot Replacement $Joni Adams, Brandon Aug 27, 2024, 12:48 PM (19 hours ago) to me Finance, Please set the DAS Cost for project MM23 9450.00 at $8,000. Regards, Brandon Adams

## #9450.00 Misc
DOC MPFC North Parking Lot Replacement
Project # 9450.00
Program code 945000 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9450.00 Bolton & Menk
DOC MPFC North Parking Lot Replacement
Project # 9450.00
Program code 945000 |  |  | Major Program 4B01
Bolton & Menk |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM23-9260 |  |  | RFP945000-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023900 | 2025-01-23 | PO Procore | 32015 | 32015 |  |  | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  |  |  | 32015 |  | 0 | 32015
|  | Totals: | 32015 |  | 0 |  | 32015
|  | Design Development Docs | 8637 |  |  |  | 8637
|  | Construction Docs | 10791 |  |  |  | 10791
|  | Bidding/Negoiation | 2602 |  |  |  | 2602
|  | Construction Phase | 9985 |  |  |  | 9985
|  | Totals: | 32015 |  | 0 |  | 32015

## RECAP #9465.00
DAS TMVC Floor Slab Repair Evaluation
Project # 9465.00
Program code 946500 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM23
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 10000
Horizon Architecture |  | 2000 | 0 | 2000
PM TIME |  | 1500 | 114.57 | 1385.43
Misc. |  | 0 | 0 | 0
Total Project Cost | 10000 | 3500 | 114.57 | 3385.43 | 6500

## #9465.00 Horizon Architecture
DAS TMVC Floor Slab Repair Evaluation
Project # 9465.00
Program code 946500 |  |  | Major Program 4E19
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM23-9260 |  |  | SRVV5
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023901 | 2025-01-23 | PO Procore | 2000 | 2000 |  |  | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  |  |  | 2000 |  | 0 | 2000
|  | Totals: | 2000 |  | 0 |  | 2000
|  | Principal Architect 4hrs@150 | 600 |  |  |  | 600
|  | Architecture PM 4 Hrs@120 | 480 |  |  |  | 480
|  | Structural Engineer 8Hrs@115 | 920 |  |  |  | 920
|  | Totals: | 2000 |  | 0 |  | 2000

## #9465.00 PM TIME
DAS TMVC Floor Slab Repair Evaluation
Project # 9465.00
Program code 946500 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 1500 | 1500 |  |  | 1500
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 1500 | 10.27 | 10.27 | 1489.73
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 1500 | 104.3 | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
[5 empty] | 1500 |  | 114.57 | 1385.43
|  |  | Totals: | 1500 |  | 114.57 |  | 1385.43

## #9465.00 Misc
DAS TMVC Floor Slab Repair Evaluation
Project # 9465.00
Program code 946500 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code: 1014
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM23
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 562.5 | 0 | 562.5
Total Project Cost | 0 | 562.5 | 0 | 562.5 | -562.5

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM23-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM23-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM23-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0