## FINANCIAL
Date DAS Processed | Agency | Document number | Document number for Interest Transfer | Project Mgr. | Vertical Infrastructure Project Allocation | Interest | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation |  | 0
|  | Total funds received to date |  | 2000198.35
|  | Sales Tax Refunds |  |  | 0
|  | Total Funds & Sales Tax Refunds |  |  | 2000198.35
|  | Less: Total Assigned |  |  | 2000198.34
|  | Total Unassigned / Unallocated |  |  | 0.01
|  | Routine Maintenance Projects | [9 empty] | Data as of 12/31/2020
[5 empty] | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
2022-10-06 |  | IET 335FY23ILEA |  |  | 7479.53 |  | 7479.53 | 7479.53 | 7479.53 | 0 | 0
2022-10-06 |  | IET 335FY23DOC |  |  | 847782.97 |  | 847782.97 | 847782.97 | 847782.97 | 0 | 0
2022-10-06 |  | IET 335FY23ABD |  |  | 28963.29 |  | 28963.29 | 28963.29 | 28963.29 | 0 | 0
2022-10-06 |  | IET 335FY23DPS |  |  | 25621.37 |  | 25621.37 | 25621.37 | 25621.37 | 0 | 0
2022-10-06 |  | IET 335FY23THILL |  |  | 4968.64 |  | 4968.64 | 4968.64 | 4968.64 | 0 | 0
2022-10-06 |  | IET 335FY231IVH |  |  | 136222.96 |  | 136222.96 | 136222.96 | 136222.96 | 0 | 0
2022-10-06 |  | IET 335FY23IPBS |  |  | 14723.7 |  | 14723.7 | 14723.7 | 14723.7 | 0 | 0
2022-10-07 |  | IET 335FY23DCA |  |  | 15574.45 |  | 15574.45 | 15574.45 | 15574.45 | 0 | 0
2022-10-12 |  | IET 335FY23DAS |  |  | 363370.45 |  | 363370.45 | 363370.45 | 363370.45 | 0 | 0
2022-10-24 |  | IET 335FY23DVA |  |  | 4528.78 |  | 4528.78 | 4528.78 | 4528.78 | 0 | 0
2022-12-08 |  | IET 335FY23DHS |  |  | 550962.2 |  | 550962.2 | 550962.2 | 550962.2 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
|  | Routine Maintenance Totals |  |  | 2000198.34 | 0 | 2000198.34 | 2000198.34 | 2000198.34 | 0 | 0
[7 empty] | Total funds not allocated to the projects listed above |  |  |  | 0.01
|  | For these project the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  |  | Subtotal |  |  |  | 0.01
[7 empty] | Total funds Available |  |  | 2000198.35
[7 empty] | Total obligated by contract or PO |  |  | -2000198.34 | 0.01
[7 empty] | Variance |  |  | . | 0

## #Funds Rec'd
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program 4D03
Funds Rec'd
Acct Code: 0090-335-23RM-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Received Funds for Interest | CDR 00523RMINT | 2022-10-05 | 198.35 | 198.35
|  |  | Transfer funds from RM23 | IET 335FY23RM | 2022-10-06 | 2000000 | 2000000
0
0
0
0
0
0
0
0
0
0
0
0
| Total Requested | 0 | Total Transferred |  |  | 2000198.35 | 2000198.35

## Financial Report
Date DAS Processed | Agency | Document number | Document number for Interest Transfer | Project Mgr. | Vertical Infrastructure Project Allocation | Interest | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation |  | 2000000
|  | Total funds received to date |  | 198.35
|  | Sales Tax Refunds |  |  | 0
|  | Total Funds & Sales Tax Refunds |  |  | 2000198.35
|  | Less: Total Assigned |  |  | 2000198.34
|  | Total Unassigned / Unallocated |  |  | 0.01
|  | Routine Maintenance Projects | [9 empty] | Data as of 12/31/2020
[5 empty] | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
2022-10-06 |  | IET 335FY23ILEA |  |  | 7479.53 |  | 7479.53 | 7479.53 | 7479.53 | 0 | 0
2022-10-06 |  | IET 335FY23DOC |  |  | 847782.97 |  | 847782.97 | 847782.97 | 691288.48 | 156494.49 | 0
2022-10-06 |  | IET 335FY23ABD |  |  | 28963.29 |  | 28963.29 | 28963.29 | 28963.29 | 0 | 0
2022-10-06 |  | IET 335FY23DPS |  |  | 25621.37 |  | 25621.37 | 25621.37 | 25621.37 | 0 | 0
2022-10-06 |  | IET 335FY23THILL |  |  | 4968.64 |  | 4968.64 | 4968.64 | 4968.64 | 0 | 0
2022-10-06 |  | IET 335FY231IVH |  |  | 136222.96 |  | 136222.96 | 136222.96 | 121593.11 | 14629.85 | 0
2022-10-06 |  | IET 335FY23IPBS |  |  | 14723.7 |  | 14723.7 | 14723.7 | 14723.7 | 0 | 0
2022-10-07 |  | IET 335FY23DCA |  |  | 15574.45 |  | 15574.45 | 15574.45 | 15574.45 | 0 | 0
2022-10-12 |  | IET 335FY23DAS |  |  | 363370.45 |  | 363370.45 | 363370.45 | 0 | 363370.45 | 0
2022-10-24 |  | IET 335FY23DVA |  |  | 4528.78 |  | 4528.78 | 4528.78 | 0 | 4528.78 | 0
2022-12-08 |  | IET 335FY23DHS |  |  | 550962.2 |  | 550962.2 | 550962.2 | 550962.2 | 0 | 0
|  | Routine Maintenance Totals |  |  | 2000198.34 | 0 | 2000198.34 | 2000198.34 | 1461174.77 | 539023.57 | 0
[7 empty] | Total funds not allocated to the projects listed above |  |  |  | 0.01
|  | For these project the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  |  | Subtotal |  |  |  | 0.01
[7 empty] | Total funds Available |  |  | 2000198.35
[7 empty] | Total obligated by contract or PO |  |  | -2000198.34 | 0.01
[7 empty] | Variance |  |  | . | 0

## ILEA
ILEA
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 7479.53 | 7479.53 |  |  | 7479.53
FY23 through 12/31/23 |  |  |  | 7479.53 | 6629.44 | 6629.44 | 850.09
FY23 |  |  |  | 7479.53 | 850.09 | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  |  |  | 7479.53 |  | 7479.53 | 1.1369e-13
|  | Totals | 7479.53 |  | 7479.53 |  | 0

## DOC
DOC
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 847782.97 | 847782.97 |  |  | 847782.97
FY23 through 12/31/23 |  |  |  | 847782.97 | 185428.63 | 185428.63 | 662354.34
FY23 |  |  |  | 847782.97 | 505859.85 | 691288.48 | 156494.49
FY24 through 12/31/23 |  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  |  |  | 847782.97 |  | 691288.48 | 156494.49
|  | Totals | 847782.97 |  | 691288.48 |  | 156494.49

## ABD
ABD
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 28963.29 | 28963.29 |  |  | 28963.29
FY23 through 12/31/23 |  |  |  | 28963.29 | 22237.12 | 22237.12 | 6726.17
FY23 |  |  |  | 28963.29 | 6726.17 | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  |  |  | 28963.29 |  | 28963.29 | 1.819e-12
|  | Totals | 28963.29 |  | 28963.29 |  | 0

## DPS
DPS
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 25621.37 | 25621.37 |  |  | 25621.37
FY23 through 12/31/23 |  |  |  | 25621.37 | 9899 | 9899 | 15722.37
FY23 |  |  |  | 25621.37 | 15722.37 | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  |  |  | 25621.37 |  | 25621.37 | 0
|  | Totals | 25621.37 |  | 25621.37 |  | 0

## THILL
THILL
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 4968.64 | 4968.64 |  |  | 4968.64
FY23 through 12/31/23 |  |  |  | 4968.64 | 4968.64 | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  |  |  | 4968.64 |  | 4968.64 | 0
|  | Totals | 4968.64 |  | 4968.64 |  | 0

## IVH
IVH
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 136222.96 | 136222.96 |  |  | 136222.96
FY23 through 12/31/23 |  |  |  | 136222.96 | 66415.16 | 66415.16 | 69807.8
FY23 |  |  |  | 136222.96 | 55177.95 | 121593.11 | 14629.85
FY24 through 12/31/23 |  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  |  |  | 136222.96 |  | 121593.11 | 14629.85
|  | Totals | 136222.96 |  | 121593.11 |  | 14629.85

## IPBS
IPBS
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 14723.7 | 14723.7 |  |  | 14723.7
FY23 through 12/31/23 |  |  |  | 14723.7 | 6250 | 6250 | 8473.7
FY23 |  |  |  | 14723.7 | 8473.7 | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  |  |  | 14723.7 |  | 14723.7 | 0
|  | Totals | 14723.7 |  | 14723.7 |  | 0

## DCA
DCA
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 15574.45 | 15574.45 |  |  | 15574.45
FY23 through 12/31/23 |  |  |  | 15574.45 | 15574.45 | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  |  |  | 15574.45 |  | 15574.45 | 0
|  | Totals | 15574.45 |  | 15574.45 |  | 0

## DAS
DAS
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 363370.45 | 363370.45 |  |  | 363370.45
FY23 through 12/31/23 |  |  |  | 363370.45 | 0 | 0 | 363370.45
FY23 |  |  |  | 363370.45 | 0 | 0 | 363370.45
FY24 through 12/31/23 |  |  |  | 363370.45 | 0 | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  |  |  | 363370.45 |  | 0 | 363370.45
|  | Totals | 363370.45 |  | 0 |  | 363370.45

## DVA
DVA
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 4528.78 | 4528.78 |  |  | 4528.78
FY23 through 12/31/23 |  |  |  | 4528.78 | 0 | 0 | 4528.78
FY23 |  |  |  | 4528.78 | 0 | 0 | 4528.78
FY24 through 12/31/23 |  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  |  |  | 4528.78 |  | 0 | 4528.78
|  | Totals | 4528.78 |  | 0 |  | 4528.78

## DHS
DHS
Doc #
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount | 550962.2 | 550962.2 |  |  | 550962.2
FY23 through 12/31/23 |  |  |  | 550962.2 | 0 | 0 | 550962.2
FY23 |  |  |  | 550962.2 | 550962.2 | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  |  |  | 550962.2 |  | 550962.2 | -1.1642e-10
|  | Totals | 550962.2 |  | 550962.2 |  | 0