## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 200000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 200000
|  | Less: Total Assigned |  | 163752.11
|  | Total Unassigned / Unallocated |  | 36247.89
Capitol Security Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9333.04 | Capitol Complex Camera Repair and Maintenance | Jeff S. | 20000 |  | 20000 | 0 | 0 | 0 | 20000
| 9333.05 | Capitol Complex Camera Project Phase 3 | Jeff S. | 143752.11 |  | 143752.11 | 143752.11 | 105625.89 | 38126.22 | 0
|  | Capitol Security Upgrade Totals |  | 163752.11 | 0 | 163752.11 | 143752.11 | 105625.89 | 38126.22 | 20000
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 36247.89
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 56247.89
[6 empty] | Total funds Available |  |  | 200000
[6 empty] | Total obligated by contract or PO |  |  | -143752.11 | 56247.89
[6 empty] | Variance |  |  |  | 0
Note on E15: Jurgenson, John [DAS]: Re: FY25 - CDE 335FY25SC24TODPS $Brittney Shannon, Jeff 3:01 PM (6 minutes ago) to me, Charlee, Matthew Please increase the budget for 9333.05 by $19,488.51. Thank you, Jeff Shannon Associate Facilities Administrator General Services Enterprise Iowa Department of Administrative Services 109 S.E. 13th St., Des Moines, IA 50319 515-601-5944 Mobile jeff.shannon@iowa.gov https://das.iowa.gov

## RECAP #9333.04
Capitol Complex Camera Repair and Maintenance
Project # 9333.04
Program code 933304 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-SC24
Project Manager - Jeff S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 20000
Vendor A
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 20000 | 0 | 0 | 0 | 20000

## #9333.04 Vendor A
Capitol Complex Camera Repair and Maintenance
Project # 9333.04
Program code 933304 |  |  | Major Program 4E21
Vendor A |  |  | Vendor
Acct. Codes-0017-335-SC24-xxxx
Project Manager - Jeff S. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.04 PM TIME
Capitol Complex Camera Repair and Maintenance
Project # 9333.04
Program code 933304 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-SC24-xxxx |  |  | eDAS 730Y
Project Manager - Jeff S.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.04 Misc
Capitol Complex Camera Repair and Maintenance
Project # 9333.04
Program code 933304 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-SC24-xxxx
Project Manager - Jeff S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals |  | 0

## RECAP #9333.05
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  | Major Program 4E21
Recap
Acct. Codes-0017-335-SC24
Project Manager - Charlee C.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 143752.11
Communication Innovators |  | 92422.14 | 54295.92 | 38126.22
PM TIME |  | 0 | 0 | 0
Misc. |  | 51329.97 | 51329.97 | 0
Total Project Cost | 143752.11 | 143752.11 | 105625.89 | 38126.22 | 0

## #9333.05 Communication Innovato
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  | Major Program 4E21
Communications Innovators |  |  | Vendor: 00002108803
Acct. Codes-0017-335-SC24-2674 |  |  | MA-005-23075
Project Manager - Charlee C. |  |  | Activity code: No Activity Code
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525037905 | 2025-02-06 | DO | 80768.74 | 80768.74 |  |  | 80768.74
PRC 3352503PA7905 | 2025-04-10 | Inv. 121230(100% to CS23) |  | 80768.74 | 0 | 0 | 80768.74
PRC 3352503PB7905 | 2025-04-18 | Inv. 121470(100% to CS23) |  | 80768.74 | 0 | 0 | 80768.74
PRC 3352503PC7905 | 2025-06-03 | Inv. 121949(100% to CS23) |  | 80768.74 | 0 | 0 | 80768.74
DO 33525037905 | 2025-06-30 | CO #1 (100% to CS23) | 0 | 80768.74 |  | 0 | 80768.74
PRC 3352503PD7905 | 2025-06-30 | Inv. 122483(Split w/CS23) |  | 80768.74 | 54295.92 | 54295.92 | 26472.82
DO 33525037905 | 2025-07-08 | CO #2 | 11653.4 | 92422.14 |  | 54295.92 | 38126.22
DO 33525037905 | 2025-07-10 | Closing to update PO Totals | 0 | 92422.14 |  | 54295.92 | 38126.22
DO 33525037905A | 2025-07-10 | Reopening with correct Totals | 0 | 92422.14 |  | 54295.92 | 38126.22
|  |  |  | 92422.14 |  | 54295.92 | 38126.22
|  |  |  | 92422.14 |  | 54295.92 | 38126.22
|  |  |  | 92422.14 |  | 54295.92 | 38126.22
|  |  |  | 92422.14 |  | 54295.92 | 38126.22
|  | Totals | 92422.14 |  | 54295.92 |  | 38126.22
|  | Materials | 80000 |  | 53527.18 |  | 26472.82
|  | Labor | 768.74 |  | 768.74 |  | 0
|  | CO #1 | 0 |  |  |  | 0
|  | CO #2 Materials | 3077.2 |  |  |  | 3077.2
|  | CO #2 Labor | 8576.2 |  |  |  | 8576.2
|  | Totals: | 92422.14 |  | 54295.92 |  | 38126.22
|  | CS23 - Closed 06/30/25 | 248131.81 |  | 248131.81 |  | 0
|  | Totals: | 340553.95 |  | 302427.73 |  | 38126.22

## #9333.05 PM TIME
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  | Major Program 4E21
PM TIME |  |  | Internal documents
Acct. Codes-0017-335-SC24-xxxx |  |  | eDAS: 732M
Project Manager - Charlee C.
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  | Budget amount |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals | 0 |  | 0 |  | 0

## #9333.05 Misc
Capitol Complex Camera Project Phase 3
Project # 9333.05
Program code 933305 |  |  |  | Major Program 4E21
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-SC24-xxxx
Project Manager - Charlee C.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202512115300001 | 2025-07-10 | 2507 |  | Electrical Services June 1-30,2025 | Inv. DAS2025121153 | 31483.57 | 31483.57
CDE 005FY25SC24TODPS | 2025-07-23 | 2674 |  | Reimburse Public Safety Expense |  | 19846.4 | 51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
51329.97
|  |  |  | Totals |  | 51329.97