## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 43316837.63
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 43316837.63
|  | Less: Total Assigned |  | 38481782.93
|  | Total Unassigned / Unallocated |  | 4835054.7
DA24 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9211.01 | DVA IVH Campus Wide Nurse Call Improvements (Fox) | Brad T. | 0 | 347578.09 | 347578.09 | 302070.37 | 294441.6 | 7628.77 | 45507.72
| 9223.00 | DOC CCF New Kitchen & Laundry Addition - Amentment #002 | Brad T. | 0 | 21695793.55 | 21695793.55 | 17988622.13 | 10320103.6 | 7668518.53 | 3707171.42
| 9279.30 | HHS WRC Campus Utility Decentralization Phase 3 | Jennifer K | 0 | 5572736 | 5572736 | 5571970.86 | 4016063.07 | 1555907.79 | 765.14
| 9279.32 | HHS WRC Campus Utility Decentralization Phase 3 Alternates | Jennifer K | 0 | 142000 | 142000 | 141583.31 | 140209.41 | 1373.9 | 416.69
| 9314.01 | DNR HCR Honey Creek Resourt Improvements | Scott G. | 0 | 100000 | 100000 | 8800 | 3652.84 | 5147.16 | 91200
| 9353.00 | DOC IMCC Electrical Service Upgrades | Jennifer K. | 0 | 2800000 | 2800000 | 2413461.52 | 612868.13 | 1800593.39 | 386538.48
C | 9355.00 | DVA IVH Courtyard Sun Shades | Brad T. | 0 | 144953.31 | 144953.31 | 144953.31 | 144953.31 | 0 | 0
| 9356.00 | DOE ISD Girls Dormitory Repairs | Jennie E. | 0 | 5700000 | 5700000 | 5555610.49 | 1779526.79 | 3776083.7 | 144389.51
| 9358.00 | ICN CC Lucas CRAC Replacement | Jennifer K | 0 | 78748.74 | 78748.74 | 78640.36 | 65332.36 | 13308 | 108.38
C | 9360.00 | DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement | Brandon A. | 0 | 43183.8 | 43183.8 | 43183.8 | 43183.8 | 0 | 0
C | 9362.00 | DOC CBC District 2 Marshalltown Geothermal System Replacement | Brad T. | 0 | 361655.16 | 361655.16 | 361655.16 | 361655.16 | 0 | 0
C | 9363.00 | DOE ISD Infirmary Roof Replacement | Jennie E. | 0 | 163663.58 | 163663.58 | 163663.58 | 163663.58 | 0 | 0
C | 9367.00 | DOE IPBS JOH 6535 Corporate Dr Roof Replacement | Brandon A. | 0 | 6600 | 6600 | 6600 | 6600 | 0 | 0
| 9374.00 | HHS CHMHI Gym Ceiling Repair | Jennie E. | 0 | 476200 | 476200 | 402009.91 | 334435.14 | 67574.77 | 74190.09
| 9375.00 | DOC 5JD DM Bldgs 65-66 Renovation | James T. | 0 | 1134000 | 1134000 | 1026942.67 | 354094.2 | 672848.47 | 107057.33
C | 9377.00 | DOC 6JD IC Hope-Stratton HVAC Evaluation | Jennifer K | 0 | 226175.14 | 226175.14 | 226175.14 | 226175.14 | 0 | 0
C | 9378.00 | DOC 6JD CR Hinzman Window Replacement | Jennifer K | 0 | 270558.29 | 270558.29 | 270558.29 | 270558.29 | 0 | 0
C | 9381.00 | DOE ISD Elementary School and Out Reach Fire Alarm | Jennie E. | 0 | 373361.99 | 373361.99 | 373361.99 | 373361.99 | 0 | 0
C | 9382.00 | DOC MPCF 1102 E. Washington Demolition | Brandon A. | 0 | 29211.02 | 29211.02 | 29211.02 | 29211.02 | 0 | 0
C | 9383.00 | DOC MPCF New Apprenticeship Building | Brandon A. | 0 | 1161858.66 | 1161858.66 | 1161858.66 | 1161858.66 | 0 | 0
C | 9384.00 | DOC CBC District 1 DRF N Wing Sm Restroom Renovation | Jennifer K | 0 | 13869.12 | 13869.12 | 13869.12 | 13869.12 | 0 | 0
C | 9385.00 | DOC CBC District 1 WURF Men's Restroom Floor Repair | Jennie E. | 0 | 71062.19 | 71062.19 | 71062.19 | 71062.19 | 0 | 0
C | 9398.00 | DOC CCF Water Supply Study | Brad T. | 0 | 46125.12 | 46125.12 | 46125.12 | 46125.12 | 0 | 0
C | 9399.00 | HHS WRC Med Center Pharmacy Remodel | Jennifer K | 0 | 12003.57 | 12003.57 | 12003.57 | 12003.57 | 0 | 0
C | 9400.00 | DOC 5JD Admin Office BAS Replacement | James T. | 0 | 38663.99 | 38663.99 | 38663.99 | 38663.99 | 0 | 0
| 9401.00 | DOC 3JD Sheldon Administration Building Window Replacements | Jennie E. | 0 | 175000 | 175000 | 165943.9 | 165032 | 911.9 | 9056.1
C | 9402.00 | DOE ISD Mass Notification System | Jennie E. | 0 | 17774.71 | 17774.71 | 17774.71 | 17774.71 | 0 | 0
C | 9403.00 | IVH Dack Fire Repairs (29C20) | Brad T. | 0 | 182912.74 | 182912.74 | 182912.74 | 182912.74 | 0 | 0
C | 9404.00 | DOC NCF CRC Boiler Replacements | Brad T. | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 9405.00 | DOC CBC 2 AMPB Building Renovations | Brad T. | 0 | 200728.05 | 200728.05 | 200728.05 | 200728.05 | 0 | 0
C | 9406.00 | DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement | Brad T. | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9412.00 | DPS CC Oran Pape Levels 2-5 Renovation (SLFRF) | James T. | 0 | 317000 | 317000 | 257263.8 | 239827.19 | 17436.61 | 59736.2
| 9414.00 | DPS DSM New Fleet Building Renovations (SLFRF) | Brandon A. | 0 | 768346.9 | 768346.9 | 616806.54 | 611754.73 | 5051.81 | 151540.36
| 9423.00 | DPS ANK Aircraft Hangar (SLFRF) | Brandon A. | 0 | 617968.19 | 617968.19 | 560590.91 | 555863.68 | 4727.23 | 57377.28
C | 9424.00 | HHS STS Main Electrical Loop Revisions | Jennifer K | 0 | 10701.46 | 10701.46 | 10701.46 | 10701.46 | 0 | 0
C | 9425.00 | HHS STS North Buildings HazMat Survey | Jennifer K | 0 | 16404.26 | 16404.26 | 16404.26 | 16404.26 | 0 | 0
|  | DA24 (MOU) Totals |  | 0 | 43316837.63 | 43316837.63 | 38481782.93 | 22884670.9 | 15597112.03 | 4835054.7
20432166.73

## RECAP #9211.01
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
| Program code 921101 |  |  | Major Program 4E14
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 347578.09
| DCI Group |  | 17641.85 | 10920.65 | 6721.2
| PM TIME |  | 10000 | 9092.43 | 907.57
| Misc. |  | 125815.38 | 125815.38 | 0
C | KCL Engineering |  | 7400 | 7400 | 0
C | Electronic Contracting |  | 141213.14 | 141213.14 | 0
| Total Project Cost | 347578.09 | 302070.37 | 294441.6 | 7628.77 | 45507.72

## #9211.01 Funds Rec'd
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  | Major Program 4E14
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET060624100 | 2024-06-06 | 275000 | 275000
|  |  | Return FY24 Funds to Agency | IET 33524226921 | 2024-08-13 | -264610.14 | -264610.14
|  |  | Return FY24 Funds to Agency Correction | IET 33524226921A | 2024-08-21 | -1444.46 | -1444.46
|  |  | Received FY25 Funds from Agency | IET IET082824100 | 2024-08-29 | 266054.6 | 266054.6
|  |  | Funds Received from Agency | IET IET102524100 | 2024-10-25 | 72578.09 | 72578.09
| Total Requested | 0 | Total Transferred |  |  | 347578.09 | 347578.09

## #9211.01 DCI Group
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  | Major Program 4E14
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524166912 | 2024-06-14 | PO Procore | 17641.85 | 17641.85 |  |  | 17641.85
PRC 3352416PA6912 | 2024-07-18 | Inv. 21-016.01 CA 01 |  | 17641.85 | 2097.38 | 2097.38 | 15544.47 | FY24
PO 33525166912 | 2024-08-27 | Roll to FY25 | 0 | 17641.85 |  | 2097.38 | 15544.47
PRC 3352516PB6912 | 2024-08-29 | Inv. 21-016.01 CA 02 |  | 17641.85 | 879.63 | 2977.01 | 14664.84
PRC 3352516PC6912 | 2024-09-16 | Inv. 21-016.01 CA 03 |  | 17641.85 | 1590.2 | 4567.21 | 13074.64
PRC 3352516PD6912 | 2024-10-15 | Inv. 21-016.01 CA 04 |  | 17641.85 | 2097.38 | 6664.59 | 10977.26
PRC 3352516PE6912 | 2024-12-03 | Inv. 21-016.01 CA 05 |  | 17641.85 | 845.3 | 7509.89 | 10131.96
PRC 3352516PF6912 | 2024-12-30 | Inv. 21-016.01 CA 06 |  | 17641.85 | 507.18 | 8017.07 | 9624.78
PRC 3352516PG6912 | 2025-01-03 | Inv. 21-016.01 CA 07 |  | 17641.85 | 710.57 | 8727.64 | 8914.21
PRC 3352516PH6912 | 2025-02-12 | Inv. 21-016.01 CA 08 |  | 17641.85 | 1041.33 | 9768.97 | 7872.88
PRC 3352516PI6912 | 2025-05-07 | Inv. 21-016.01 CA 09 |  | 17641.85 | 813.56 | 10582.53 | 7059.32
PRC 3352516PJ6912 | 2025-06-11 | Inv. 21-016.01 CA 10 |  | 17641.85 | 338.12 | 10920.65 | 6721.2
|  |  |  | 17641.85 |  | 10920.65 | 6721.2
|  | Totals: | 17641.85 |  | 10920.65 |  | 6721.2
|  | CM Services | 16876.85 |  | 10860.65 |  | 6016.2
|  | Reimbursables | 765 |  | 60 |  | 705
|  | Total: | 17641.85 |  | 10920.65 |  | 6721.2

## #9211.01 PM TIME
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  |  | Major Program 4E14
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T |  |  |  | eDAS E2DE
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10000 | 127.92 | 127.92 | 9872.08
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10000 | 1170.1 | 1298.02 | 8701.98
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10000 | 60.83 | 1358.85 | 8641.15
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10000 | 661.4 | 2020.25 | 7979.75
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10000 | 204.92 | 2225.17 | 7774.83
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10000 | 1043 | 3268.17 | 6731.83
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10000 | 93.54 | 3361.71 | 6638.29
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10000 | 835 | 4196.71 | 5803.29
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10000 | 193.64 | 4390.35 | 5609.65
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10000 | 1292.5 | 5682.85 | 4317.15
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10000 | 79.55 | 5762.4 | 4237.6
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10000 | 529.4 | 6291.8 | 3708.2
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 70.32 | 6362.12 | 3637.88
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 702.6 | 7064.72 | 2935.28
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 43.31 | 7108.03 | 2891.97
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 461.9 | 7569.93 | 2430.07
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 70.63 | 7640.56 | 2359.44
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 303.7 | 7944.26 | 2055.74
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 28.26 | 7972.52 | 2027.48
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 204.1 | 8176.62 | 1823.38
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10000 | 63.55 | 8240.17 | 1759.83
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10000 | 436.6 | 8676.77 | 1323.23
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 10000 | 46.86 | 8723.63 | 1276.37
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 10000 | 368.8 | 9092.43 | 907.57
[5 empty] | 10000 |  | 9092.43 | 907.57
[5 empty] | 10000 |  | 9092.43 | 907.57
[5 empty] | 10000 |  | 9092.43 | 907.57
|  |  | Totals: | 10000 |  | 9092.43 |  | 907.57

## #9211.01 Misc
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  |  | Major Program 4E14
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 33525256905 | 2024-09-12 | 9500 | CNST | Processing CDE to move expense from project 9211.01 to IVH. | Inv. 00007794 | 72578.09 | 72578.09
CDE 33525304905 | 2024-10-30 | 9500 | CNST | Processing CDE to move expense from project 9211.01 to IVH. | Inv. 00007882 | 31031.04 | 103609.13
CDE 33525176900 | 2025-06-25 | 9500 | CNST | Processing CDE to move expense from project 9211.01 to IVH. | Inv. 00008374 | 22206.25 | 125815.38
125815.38
125815.38
125815.38
125815.38
125815.38
125815.38
125815.38
125815.38
125815.38
|  |  |  | Totals: |  | 125815.38

## #9211.01 KCL Engineering
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  | Major Program 4E14
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA24-9260 |  |  | RFP921100-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524178903 | 2024-06-26 | PO Procore | 7400 | 7400 |  |  | 7400
PRC 3352417PA8903 | 2024-07-29 | Inv. 10187 |  | 7400 | 5550 | 5550 | 1850 | FY24
PO 33525178903 | 2024-08-27 | Roll to FY25 |  | 7400 |  | 5550 | 1850
PRC 3352517PB8903 | 2024-09-23 | Inv. 10460 |  | 7400 | 370 | 5920 | 1480
PRC 3352517PC8903 | 2025-01-24 | Inv. 11171 - Final |  | 7400 | 1480 | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  |  |  | 7400 |  | 7400 | 0
|  | Totals: | 7400 |  | 7400 |  | 0 | FINAL
|  | Construction Docs | 5920 |  | 5920 |  | 0
|  | Construction Admin | 1480 |  | 1480 |  | 0
|  | Totals: | 7400 |  | 7400 |  | 0

## #9211.01 Electronic Contracting
DVA IVH Campus Wide Nurse Call Improvements (Fox)
Project # 9211.01
Program code 921101 |  |  | Major Program 4E14
Electronic Contracting |  |  | Vendor: 00003028587
Acct. Codes-0506-335-DA24-9255 |  |  | RFP921100-01
Project Manager - Brad T |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524179902 | 2024-06-27 | PO Procore | 133668.14 | 133668.14 |  |  | 133668.14 |  | FY24
PO 33525179902 | 2024-08-27 | Roll to FY25 |  | 133668.14 |  | 0 | 133668.14
PO 33525179902 | 2024-08-30 | CO #1 | 7545 | 141213.14 |  | 0 | 141213.14
PRC 3352517PA9902 | 2024-09-16 | Inv. 60883 |  | 141213.14 | 76201.84 | 76201.84 | 65011.3 | 4010.62
PRC 3352517PB9902 | 2024-09-25 | Inv. 61630 |  | 141213.14 | 49513.04 | 125714.88 | 15498.26 | 6616.58
PRC 3352517PC9902 | 2024-10-21 | Inv. 63174 |  | 141213.14 | 7167.75 | 132882.63 | 8330.51 | 6993.83
PRC 3352517PD9902 | 2025-01-21 | Inv. 65941 |  | 141213.14 | 1269.85 | 134152.48 | 7060.66 | 7060.66
PRC 3352517PE9902 | 2025-02-12 | Inv. Retainage |  | 141213.14 | 7060.66 | 141213.14 | 0
|  |  |  | 141213.14 |  | 141213.14 | 0
|  |  |  | 141213.14 |  | 141213.14 | 0
|  |  |  | 141213.14 |  | 141213.14 | 0
|  |  |  | 141213.14 |  | 141213.14 | 0
|  |  |  | 141213.14 |  | 141213.14 | 0
|  | Totals: | 141213.14 |  | 141213.14 |  | 0 | FINAL

## RECAP #9223.00
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
| Program code 922300 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 21695793.55
C | Samuels Group |  | 28780.46 | 28780.46 | 0
| PM TIME |  | 40000 | 36492.5 | 3507.5
| Misc. |  | 100561.69 | 100561.69 | 0
| Denovo LLC |  | 26763 | 0 | 26763
| Farnsworth Group |  | 192193 | 157977.5 | 34215.5
| Graphite Construction Group |  | 3441515.78 | 1637923.71 | 1803592.07
| Enterprise Precast Concrete |  | 836990.85 | 784680.27 | 52310.58
| Esco Electric Company |  | 4405774.59 | 1292122.59 | 3113652
| Mahoney Fire Sprinkler |  | 223950 | 39434.5 | 184515.5
| Black Hawk Roof Company |  | 472820 | 400408.85 | 72411.15
| A&W Enterprises |  | 1669941.05 | 1252684.91 | 417256.14
| Rapids FoodService (Paper Contract) |  | 1574365.09 | 1574365.09 | 0
| Samuels Group #157CA |  | 1435798.81 | 1073840.19 | 361958.62
| Proctor Mechanical (Unencumbered) |  | 3383995 | 1938658.53 | 1445336.47
C | Tri-City Electric Co. |  | 2172.81 | 2172.81 | 0
| System Technology Services |  | 153000 | 0 | 153000
| Total Project Cost | 21695793.55 | 17988622.13 | 10320103.6 | 7668518.53 | 3707171.42

## #9223.00 Funds Rec'd
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU Amendment #2 | IET 25561A24001 | 2024-01-31 | 14294297.57 | 14294297.57
|  |  | Return FY24 Funds to Agency | IET 33524226922 | 2024-08-13 | -13589577.01 | -13589577.01
|  |  | Return FY24 Funds to Agency Correction | IET 33524226922A | 2024-08-21 | -4785 | -4785
|  |  | Received FY25 Funds From Agency | IET 25561A25001 | 2024-09-09 | 13594362.01 | 13594362.01
|  |  | MOU Amendment #3 | IET 23812V25008 | 2025-03-19 | 7401495.98 | 7401495.98
| Total Requested | 0 | Total Transferred |  |  | 21695793.55 | 21695793.55

## #9223.00 Samuels Group
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524033908 | 2024-02-01 | PO Procore | 12938.44 | 12938.44 |  |  | 12938.44
PRC 3352403PA3908 | 2024-03-04 | Inv. 7673.01 PC |  | 12938.44 | 9501.07 | 9501.07 | 3437.37
PO 33524033908 | 2024-03-22 | CO #1 | 15843.3 | 28781.74 |  | 9501.07 | 19280.67
PRC 3352403PB3908 | 2024-04-02 | Inv. 7673.02 PC |  | 28781.74 | 5876.8 | 15377.87 | 13403.87
PRC 3352403PC3908 | 2024-05-06 | Inv. 7673.03 PC FINAL | -1.28 | 28780.46 | 13402.59 | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  |  |  | 28780.46 |  | 28780.46 | -1.1642e-12
|  | Totals: | 28780.46 |  | 28780.46 |  | 0 | FINAL
|  | CM Services | 12738.44 |  | 12738.44 |  | 0
|  | Reimbursables | 200 |  | 200 |  | 0
|  | CO #1 | 15842.02 |  | 15842.02 |  | 0
|  | Totals: | 28780.46 |  | 28780.46 |  | 0

## #9223.00 PM TIME
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2BH
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 40000 | 40000 |  |  | 40000
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 40000 | 1842.5 | 1842.5 | 38157.5
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 40000 | 1952.5 | 3795 | 36205
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 40000 | 1870 | 5665 | 34335
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 40000 | 1650 | 7315 | 32685
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 40000 | 1457.5 | 8772.5 | 31227.5
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 40000 | 2392.5 | 11165 | 28835
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 40000 | 2392.5 | 13557.5 | 26442.5
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 40000 | 1842.5 | 15400 | 24600
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 40000 | 3355 | 18755 | 21245
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 40000 | 2200 | 20955 | 19045
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 40000 | 2255 | 23210 | 16790
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 40000 | 3025 | 26235 | 13765
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 40000 | 2365 | 28600 | 11400
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 40000 | 3437.5 | 32037.5 | 7962.5
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 40000 | 2475 | 34512.5 | 5487.5
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 40000 | 1980 | 36492.5 | 3507.5
[5 empty] | 40000 |  | 36492.5 | 3507.5
[5 empty] | 40000 |  | 36492.5 | 3507.5
[5 empty] | 40000 |  | 36492.5 | 3507.5
|  |  | Totals: | 40000 |  | 36492.5 |  | 3507.5
Note on E9: Huggins, Joni [DAS]: PM Time / Budget Adjustments $Joni Tonyan, Brad 1:33 PM (34 minutes ago) to me, Scott, Brad Finance, Please make the following adjustments/set ups: DA22: 9295.00 - Increase PM Time by $5K 9239.01 - Increase PM Time by $5K DA23: 9318.00 - Increase PM Time by $15K DA24: 9223.00 - Setup PM Time budget of $40K

## #9223.00 Misc
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 165
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 412.5 | 412.5
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 412.5 | 825
CDE 33524113910 | 2024-04-19 | 9500 | BRIN | Reimbursement to Clarinda Correctional Facility | Inv. R24071-1 / 35569 / 1011 | 33334.3 | 34159.3
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -825 | 33334.3
PRC 33524137912 | 2024-05-16 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL624 | 1113.67 | 34447.97
PRC 33524170904 | 2024-06-18 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL451 | 2340.26 | 36788.23
CDE 33524170905 | 2024-06-18 | 9500 | BRIN | Reimbursement to Clarinda Correctional Facility | Inv. 515216 | 32448.59 | 69236.82
PRC 33524178905 | 2024-06-26 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 777583 | 16710 | 85946.82
GAX 33524205903 | 2024-07-23 | 9500 | CNST | Team Services V#(00002121153) | Inv. 1819391 | 2393 | 88339.82
GAX 33525255902 | 2024-09-11 | 9500 | CNST | A&W Enterprises V#(00003055532) | Inv. 10386 | 3300 | 91639.82
PRC 33525255905 | 2024-09-11 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL964 | 296.57 | 91936.39
CDE 33525261904 | 2024-09-17 | 9500 | CNST | Reimbursement to Clarinda Correctional Facility | Inv. R26454-1, 133661, 133649, 133635 | 2541.65 | 94478.04
PRC 33525069901 | 2025-03-10 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1508 | 1133.65 | 95611.69
CDE 33525134907 | 2025-05-13 | 9500 | CNST | Reimbursement to Clarinda Correctional Facility | Inv. 10126900 | 4950 | 100561.69
100561.69
|  |  |  | Totals: |  | 100561.69

## #9223.00 Denovo LLC
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Denovo LLC |  |  | Vendor: 00003187582
Acct. Codes-0506-335-DA24-9255 |  |  | RFP922300-02
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524039801 | 2024-02-08 | PO Procore | 26763 | 26763 |  |  | 26763 | FY24
PO 33525039801 | 2024-08-27 | Roll to FY25 | 0 | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  |  |  | 26763 |  | 0 | 26763
|  | Totals: | 26763 |  | 0 |  | 26763
|  | Construction Commissioning | 22045 |  |  |  | 22045
|  | Close Out/Final Report | 4718 |  |  |  | 4718
|  | Total: | 26763 |  | 0 |  | 26763

## #9223.00 Farnsworth Group
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA24-9260 |  |  | RFP922300-02
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524045900 | 2024-02-14 | PO Procore | 187193 | 187193 |  |  | 187193
PRC 3352404PA5900 | 2024-03-20 | Inv. 9223.00-001 |  | 187193 | 11408 | 11408 | 175785
PRC 3352404PB5900 | 2024-04-15 | Inv. 9223.00-002 |  | 187193 | 22734 | 34142 | 153051
PRC 3352404PC5900 | 2024-05-09 | Inv. 9223.00-003 |  | 187193 | 10052.25 | 44194.25 | 142998.75
PRC 3352404PD5900 | 2024-06-11 | Inv. 9223.00-004 |  | 187193 | 7526.25 | 51720.5 | 135472.5
PRC 3352404PE5900 | 2024-07-10 | Inv. 9223.00-005 |  | 187193 | 13547.25 | 65267.75 | 121925.25 | FY24
PO 33525045900 | 2024-08-27 | Roll to FY25 | 0 | 187193 |  | 65267.75 | 121925.25
PRC 3352504PF5900 | 2024-09-11 | Inv. 9223.00-006 |  | 187193 | 9031.5 | 74299.25 | 112893.75
PRC 3352504PG5900 | 2024-09-11 | Inv. 9223.00-007 |  | 187193 | 12042 | 86341.25 | 100851.75
PRC 3352504PH5900 | 2024-10-18 | Inv. 9223.00-008 |  | 187193 | 9031.5 | 95372.75 | 91820.25
PRC 3352504PI5900 | 2024-11-06 | Inv. 9223.00-009 |  | 187193 | 9031.5 | 104404.25 | 82788.75
PRC 3352504PJ5900 | 2024-12-16 | Inv. 9223.00-010 |  | 187193 | 7526.25 | 111930.5 | 75262.5
PRC 3352504PK5900 | 2025-01-09 | Inv. 9223.00-011 |  | 187193 | 9031.5 | 120962 | 66231
PRC 3352504PL5900 | 2025-02-05 | Inv. 9223.00-012 |  | 187193 | 10536.75 | 131498.75 | 55694.25
PO 33525045900 | 2025-02-11 | CO #1 | 5000 | 192193 |  | 131498.75 | 60694.25
PRC 3352504PM5900 | 2024-03-04 | Inv. 9223.00-013 |  | 192193 | 9031.5 | 140530.25 | 51662.75
PRC 3352504PN5900 | 2025-04-09 | Inv. 9223.00-014 |  | 192193 | 11021 | 151551.25 | 40641.75
PRC 3352504PO5900 | 2025-05-07 | Inv. 9223.00-015 |  | 192193 | 6426.25 | 157977.5 | 34215.5
|  |  |  | 192193 |  | 157977.5 | 34215.5
|  | Totals: | 192193 |  | 157977.5 |  | 34215.5
|  | Construction Documents | 11408 |  | 11408 |  | 0
|  | Bidding or Negotiating | 25260 |  | 25260 |  | 0
|  | Construction Administration | 150525 |  | 116309.5 |  | 34215.5
|  | CO #1 | 5000 |  | 5000 |  | 0
|  | Total: | 192193 |  | 157977.5 |  | 34215.5
Vendor used format 9223.00-01 in another tab for this project

## #9223.00 Graphite Construction
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Graphite Construction Group |  |  | Vendor: 00002126776
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524089802 | 2024-03-29 | PO Procore | 3377500 | 3377500 |  |  | 3377500
PRC 3352408PA9802 | 2024-07-16 | Inv. 9223.00 Pay App 1 |  | 3377500 | 73782.27 | 73782.27 | 3303717.73 | 3883.28 | FY24
PO 33525089802 | 2024-08-27 | Roll to FY25 |  | 3377500 |  | 73782.27 | 3303717.73
PRC 3352508PB9802 | 2024-09-11 | Inv. 9223.00 Pay App 2 - July 2024 |  | 3377500 | 58668.2 | 132450.47 | 3245049.53 | 6971.08
PO 33525089802 | 2024-10-04 | CO #1 | 18038.38 | 3395538.38 |  | 132450.47 | 3263087.91
PRC 3352508PC9802 | 2024-10-10 | Inv. 9223.00-03 |  | 3395538.38 | 61117.34 | 193567.81 | 3201970.57 | 10187.79
PRC 3352508PD9802 | 2024-11-05 | Inv. 9223.00-04 |  | 3395538.38 | 200616.14 | 394183.95 | 3001354.43
CW1105247331108225 | 2024-11-08 | Warrant 73311082 Voided |  | 3395538.38 | -200616.14 | 193567.81 | 3201970.57
PRC 3352508PD9802A | 2024-11-12 | Inv. 9223.00-04A |  | 3395538.38 | 200606.14 | 394173.95 | 3001364.43 | 20746.01
PO 33525089802 | 2024-11-21 | Close PO to adjust for voided check |  | 3395538.38 |  | 394173.95 | 3001364.43
PO 33525089802A | 2024-11-22 | Opening new PO with Adjusted balance after voided check | 0 | 3395538.38 |  | 394173.95 | 3001364.43
PO 33525089802A | 2024-12-04 | CO #2 | 19780 | 3415318.38 |  | 394173.95 | 3021144.43
PRC 3352508PE9802A | 2024-12-20 | Inv. 9223.00-05 |  | 3415318.38 | 657785.61 | 1051959.56 | 2363358.82 | 55366.32
PO 33525089802A | 2025-01-14 | CO #3 | 37446.29 | 3452764.67 |  | 1051959.56 | 2400805.11
PRC 3352508PF9802A | 2025-02-21 | Inv. 9223.00-06 |  | 3452764.67 | 184989.02 | 1236948.58 | 2215816.09 | 65102.59
PO 33525089802A | 2025-02-28 | CO #4 | -3122.65 | 3449642.02 |  | 1236948.58 | 2212693.44
PO 33525089802A | 2025-03-05 | CO #5 | 9594.7 | 3459236.72 |  | 1236948.58 | 2222288.14
PRC 3352508PG9802A | 2025-03-18 | Inv. 9223.00-07 |  | 3459236.72 | 109946.83 | 1346895.41 | 2112341.31 | 70889.27
PRC 3352508PH9802A | 2025-04-18 | Inv. 9223.00-08 |  | 3459236.72 | 195163.49 | 1542058.9 | 1917177.82 | 81161.04
PRC 3352508PI9802A | 2025-05-28 | Inv. 9223.00-09 |  | 3459236.72 | 95864.81 | 1637923.71 | 1821313.01 | 86206.56
PO 33525089802A | 2025-06-03 | CO #6 | -17720.94 | 3441515.78 |  | 1637923.71 | 1803592.07
|  |  |  | 3441515.78 |  | 1637923.71 | 1803592.07
|  | Totals: | 3441515.78 |  | 1637923.71 |  | 1803592.07

## #9223.00 Enterprise Precast
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Enterprise Precast Concrete |  |  | Vendor: 00003216431
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524093907 | 2024-04-02 | PO Procore | 837136 | 837136 |  |  | 837136
PRC 3352409PA3907 | 2024-07-10 | Inv. 9223.00-01 |  | 837136 | 142354.5 | 142354.5 | 694781.5 | 7492.34 | FY24
PO 33525093907 | 2024-08-27 | Roll to FY25 | 0 | 837136 |  | 142354.5 | 694781.5
PRC 3352509PB3907 | 2024-09-11 | Inv. 9223.00-02 |  | 837136 | 167448.9 | 309803.4 | 527332.6 | 16305.44
PRC 3352509PC3907 | 2024-09-19 | Inv. 9223.00-03 |  | 837136 | 127580.21 | 437383.61 | 399752.39 | 23020.19
PO 33525093907 | 2025-02-28 | CO #1 | 408.75 | 837544.75 |  | 437383.61 | 400161.14
PRC 3352509PD3907 | 2025-04-10 | Inv. 9223.00-04 |  | 837544.75 | 311374.31 | 748757.92 | 88786.83 | 39408.3
PO 33525093907 | 2025-04-23 | CO #2 | -553.9 | 836990.85 |  | 748757.92 | 88232.93 | 41298.95
PRC 3352509PE3907 | 2025-05-06 | Inv. 9223.00-05 |  | 836990.85 | 35922.35 | 784680.27 | 52310.58
|  |  |  | 836990.85 |  | 784680.27 | 52310.58
|  |  |  | 836990.85 |  | 784680.27 | 52310.58
|  |  |  | 836990.85 |  | 784680.27 | 52310.58
|  |  |  | 836990.85 |  | 784680.27 | 52310.58
|  | Totals: | 836990.85 |  | 784680.27 |  | 52310.58

## #9223.00 Esco Electric Company
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Esco Electric Company |  |  | Vendor: 00002119529
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524093908 | 2024-04-02 | PO Procore | 4380761.24 | 4380761.24 |  |  | 4380761.24
PRC 3352409PA3908 | 2024-06-05 | Inv. 142790 |  | 4380761.24 | 84003.75 | 84003.75 | 4296757.49 | 4421.25
PO 33524093908 | 2024-06-26 | CO #1 | 5593.83 | 4386355.07 |  | 84003.75 | 4302351.32
PRC 3352409PB3908 | 2024-07-10 | Inv. 143390 |  | 4386355.07 | 59137.5 | 143141.25 | 4243213.82 | 7533.75 | FY24
PO 33525093908 | 2024-08-27 | Roll to FY25 | 0 | 4386355.07 |  | 143141.25 | 4243213.82
PRC 3352509PC3908 | 2024-09-11 | Inv. 144365 |  | 4386355.07 | 138462.5 | 281603.75 | 4104751.32 | 14821.25
PO 33525093908 | 2024-10-07 | CO #2 | 24404.06 | 4410759.13 |  | 281603.75 | 4129155.38
PRC 3352509PD3908 | 2024-10-10 | Inv. 145687 |  | 4410759.13 | 141550 | 423153.75 | 3987605.38 | 22271.25
PRC 3352509PE3908 | 2024-11-05 | Inv. 146434 |  | 4410759.13 | 146775 | 569928.75 | 3840830.38 | 29996.25
PO 33525093908 | 2024-12-04 | CO #3 | 15700.35 | 4426459.48 |  | 569928.75 | 3856530.73
PO 33525093908 | 2025-02-17 | CO #4 (No Cost CO) | 0 | 4426459.48 |  | 569928.75 | 3856530.73
PRC 3352509PF3908 | 2025-02-17 | Inv. 1002215 |  | 4426459.48 | 150290.33 | 720219.08 | 3706240.4 | 37906.27
PRC 3352509PG3908 | 2025-02-24 | Inv. 1003080 |  | 4426459.48 | 71725 | 791944.08 | 3634515.4 | 41681.27
PRC 3352509PH3908 | 2025-03-19 | Inv. 1003890 |  | 4426459.48 | 109250 | 901194.08 | 3525265.4 | 47431.27
PO 33525093908 | 2025-03-25 | CO #5 | -68299.07 | 4358160.41 |  | 901194.08 | 3456966.33
PO 33525093908 | 2025-04-04 | CO #6 | 42705.81 | 4400866.22 |  | 901194.08 | 3499672.14
PRC 3352509PI3908 | 2025-04-18 | Inv. 1004663 |  | 4400866.22 | 128871.01 | 1030065.09 | 3370801.13 | 54213.96
PRC 3352509PJ3908 | 2025-05-15 | Inv. 1005510 |  | 4400866.22 | 139507.5 | 1169572.59 | 3231293.63 | 61556.46
PO 33525093908 | 2025-05-19 | CO #7 | 4908.37 | 4405774.59 |  | 1169572.59 | 3236202
PRC 3352509PK3908 | 2025-06-25 | Inv. 1006403 |  | 4405774.59 | 122550 | 1292122.59 | 3113652 | 68006.46
|  |  |  | 4405774.59 |  | 1292122.59 | 3113652
|  |  |  | 4405774.59 |  | 1292122.59 | 3113652
|  | Totals: | 4405774.59 |  | 1292122.59 |  | 3113652

## #9223.00 Mahoney Fire Sprinkler
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Mahoney Fire Sprinkler |  |  | Vendor: 00003035382
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524094908 | 2024-04-03 | PO Procore | 223950 | 223950 |  |  | 223950 |  | FY24
PO 33525094908 | 2024-08-27 | Roll to FY25 | 0 | 223950 |  | 0 | 223950
PRC 3352509PA4908 | 2024-09-11 | Inv. 9223.00-01 |  | 223950 | 18629.5 | 18629.5 | 205320.5 | 980.5
PO 33525094908 | 2025-02-21 | CO #1(No Cost CO) | 0 | 223950 |  | 18629.5 | 205320.5
PRC 3352509PB4908 | 2025-06-16 | Inv. 9223.00-02 |  | 223950 | 20805 | 39434.5 | 184515.5 | 2075.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  |  |  | 223950 |  | 39434.5 | 184515.5
|  | Totals: | 223950 |  | 39434.5 |  | 184515.5

## #9223.00 Black Hawk Roof Co
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Black Hawk Roof Co |  |  | Vendor: 00002120676
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524094910 | 2024-04-03 | PO Procore | 497200 | 497200 |  |  | 497200 |  | FY24
PO 33525094910 | 2024-08-27 | Roll to FY25 | 0 | 497200 |  | 0 | 497200
PO 33525094910 | 2024-10-18 | CO #1 | -24380 | 472820 |  | 0 | 472820
PO 33525094910 | 2025-02-21 | CO #2 (No Cost CO) | 0 | 472820 |  | 0 | 472820
PRC 3352509PA4910 | 2025-03-05 | Inv. 9223.00-01 |  | 472820 | 396132.9 | 396132.9 | 76687.1 | 20849.1
PRC 3352509PB4910 | 2025-04-10 | Inv. 9223.00-02 |  | 472820 | 285.95 | 396418.85 | 76401.15 | 20864.15
PRC 3352509PC4910 | 2025-06-17 | Inv. 9223.00-03 |  | 472820 | 3990 | 400408.85 | 72411.15 | 21074.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  |  |  | 472820 |  | 400408.85 | 72411.15
|  | Totals: | 472820 |  | 400408.85 |  | 72411.15

## #9223.00 A&W Enterprises
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
A&W Enterprises |  |  | Vendor: 00003055532
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524094911 | 2024-04-03 | PO Procore | 1500000 | 1500000 |  |  | 1500000
PRC 3352409PA4911 | 2024-07-16 | Inv. 9223.00-01 |  | 1500000 | 18620 | 18620 | 1481380 | 980 | FY24
PO 33525094911 | 2024-08-27 | Roll to FY25 | 0 | 1500000 |  | 18620 | 1481380
PO 33525094911 | 2024-09-11 | CO #1 | 28992.65 | 1528992.65 |  | 18620 | 1510372.65
PRC 3352509PB4911 | 2024-09-12 | Inv. 9223.00-02 |  | 1528992.65 | 399727.7 | 418347.7 | 1110644.95 | 22018.3
PO 33525094911 | 2024-10-17 | CO #2 | 114120.3 | 1643112.95 |  | 418347.7 | 1224765.25
PO 33525094911 | 2024-11-25 | CO #3 | 19640.6 | 1662753.55 |  | 418347.7 | 1244405.85
PO 33525094911 | 2024-12-05 | CO #4 | -12650 | 1650103.55 |  | 418347.7 | 1231755.85
PRC 3352509PC4911 | 2024-12-19 | Inv. 9223.00-03 |  | 1650103.55 | 834337.21 | 1252684.91 | 397418.64 | 65930.79
PO 33525094911 | 2025-02-11 | CO #5(No Cost CO) | 0 | 1650103.55 |  | 1252684.91 | 397418.64
PO 33525094911 | 2025-03-21 | CO #6 | 19837.5 | 1669941.05 |  | 1252684.91 | 417256.14
|  |  |  | 1669941.05 |  | 1252684.91 | 417256.14
|  |  |  | 1669941.05 |  | 1252684.91 | 417256.14
|  | Totals: | 1669941.05 |  | 1252684.91 |  | 417256.14

## #9223.00 Rapids FoodService
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Rapids Food Service |  |  | Vendor: 00002119782
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524096800 | 2024-04-05 | PO Procore(Paper Contract) |  | 0 |  |  | 0 |  | FY24
PO 33525096800 | 2024-08-27 | Roll to FY25 | 1574365.09 | 1574365.09 |  | 0 | 1574365.09
PO 33525096800 | 2024-09-30 | Changing to Paper Contract |  | 1574365.09 |  | 0 | 1574365.09
GAX 33525297900 | 2024-10-22 | Inv. 9223.00-01 |  | 1574365.09 | 515924.1 | 515924.1 | 1058440.99 | 27153.9
GAX 33525311901 | 2024-11-06 | Inv. 9223.00-02 |  | 1574365.09 | 214035.95 | 729960.05 | 844405.04 | 38418.95
GAX 33525341905 | 2024-12-06 | Inv. 9223.00-03 |  | 1574365.09 | 213484.95 | 943445 | 630920.09 | 49655
GAX 33525013905 | 2025-01-13 | Inv. 9223.00-04 |  | 1574365.09 | 77024.1 | 1020469.1 | 553895.99 | 53708.9
GAX 33525055901 | 2025-02-24 | Inv. 9223.00-05 |  | 1574365.09 | 135789.2 | 1156258.3 | 418106.79 | 60855.7
GAX 33525066901 | 2025-03-07 | Inv. 9223.00-06 |  | 1574365.09 | 50921.9 | 1207180.2 | 367184.89 | 63535.8
GAX 33525115905 | 2025-04-25 | Inv. 9223.00-07 |  | 1574365.09 | 136279.4 | 1343459.6 | 230905.49 | 70708.4
GAX 33525170901 | 2025-06-20 | Inv. 9223.00-08 |  | 1574365.09 | 230905.49 | 1574365.09 | 0 | 82861.33
|  |  |  | 1574365.09 |  | 1574365.09 | 0
|  |  |  | 1574365.09 |  | 1574365.09 | 0
|  | Totals: | 1574365.09 |  | 1574365.09 |  | 0
|  | Paper Contract | 2798332 |  | 1575607.77 |  | 1222724.23
|  | CO #1 02/17/25 | -1308.08 |  | -1242.68 |  | -65.4
|  | CO #2 03/28/25 | 16279.63 |  |  |  | 16279.63
|  | CO #3 05/09/25 | -3400.84 |  |  |  | -3400.84
|  | Total: | 2809902.71 |  | 1574365.09 |  | 1235537.62
This is a paper contract. Nothing is entered in Iowa Adavantage
All Pay apps will be a GAX

## #9223.00 Samuels Group #157CA
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Samuels Group #157CA |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524096801 | 2024-04-05 | PO Procore (Unencumbered) | 67100.66 | 67100.66 |  |  | 67100.66
PRC 3352409PA6801 | 2024-05-10 | Inv. 7679.50 CA |  | 67100.66 | 8082.04 | 8082.04 | 59018.62
PRC 3352409PB6801 | 2024-06-05 | Inv. 7679.51 CA |  | 67100.66 | 22628.06 | 30710.1 | 36390.56
PRC 3352409PC6801 | 2024-07-10 | Inv. 7679.52 CA |  | 67100.66 | 36390.56 | 67100.66 | 0 | FY24
PO 33525096801 | 2024-08-27 | Roll to FY25 | 906507.53 | 973608.19 |  | 67100.66 | 906507.53
PRC 3352509PD6801 | 2024-09-11 | Inv. 7679.53 CA |  | 973608.19 | 69113.78 | 136214.44 | 837393.75
PRC 3352509PE6801 | 2024-09-30 | Inv. 7679.54 CA |  | 973608.19 | 76221.49 | 212435.93 | 761172.26
PRC 3352509PF6801 | 2024-10-07 | Inv. 7679.55 CA |  | 973608.19 | 53763.64 | 266199.57 | 707408.62
PRC 3352509PG6801 | 2024-11-06 | Inv. 7679.56 CA |  | 973608.19 | 85808.62 | 352008.19 | 621600
PRC 3352509PH6801 | 2025-01-03 | Inv. 7679.57 CA |  | 973608.19 | 99973.69 | 451981.88 | 521626.31
PRC 3352509PI6801 | 2025-01-08 | Inv. 7679.58 CA |  | 973608.19 | 96601.2 | 548583.08 | 425025.11
PRC 3352509PJ6801 | 2025-02-06 | Inv. 7679.59 CA |  | 973608.19 | 97943.38 | 646526.46 | 327081.73
PRC 3352509PK6801 | 2025-03-12 | Inv. 7679.60 CA |  | 973608.19 | 106531.42 | 753057.88 | 220550.31
PRC 3352509PL6801 | 2025-04-10 | Inv. 7679.61CA |  | 973608.19 | 115418.68 | 868476.56 | 105131.63
PRC 3352509PM6801 | 2025-05-06 | Inv. 7679.62 CA |  | 973608.19 | 105131.63 | 973608.19 | 0
PO 33525096801 | 2025-05-07 | Closing Unencumbered PO | 0 | 973608.19 |  | 973608.19 | 0
PO 33525096801A | 2025-05-07 | Opening PO as Encumbered | 462190.62 | 1435798.81 |  | 973608.19 | 462190.62
PRC 3352509PN6801A | 2025-06-10 | Inv. 7679.63 CA |  | 1435798.81 | 100232 | 1073840.19 | 361958.62
|  |  |  | 1435798.81 |  | 1073840.19 | 361958.62
|  | Totals: | 1435798.81 |  | 1073840.19 |  | 361958.62
|  | CM Services | 625138.7 |  | 539102.57 |  | 86036.13
|  | Reimbursables | 292078 |  | 158036.57 |  | 134041.43
|  | Fee | 513881.06 |  | 372000 |  | 141881.06
|  | CO #1 03/26/25 | 4701.05 |  | 4701.05 |  | 0
|  | Total: | 1435798.81 |  | 1073840.19 |  | 361958.62

## #9223.00 Proctor Mechanical
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524107801 | 2024-04-16 | PO Procore (Unencumbered) | 63776.35 | 63776.35 |  |  | 63776.35
PRC 3352410PA7801 | 2024-07-16 | Inv. 7604.0/1 |  | 63776.35 | 63776.35 | 63776.35 | 0 | 3356.65 | FY24
PO 33525107801 | 2024-08-27 | Roll to FY25 | 1553207.25 | 1616983.6 |  | 63776.35 | 1553207.25
PRC 3352510PB7801 | 2024-10-07 | Inv. 7604.0/2 |  | 1616983.6 | 57448.02 | 121224.37 | 1495759.23 | 6380.23
PRC 3352510PC7801 | 2024-11-13 | Inv. 7604.0/3 |  | 1616983.6 | 62132.23 | 183356.6 | 1433627 | 9650.35
PRC 3352510PD7801 | 2024-12-10 | Inv. 7604.0/4 |  | 1616983.6 | 206220.39 | 389576.99 | 1227406.61 | 20504.06
PRC 3352510PE7801 | 2025-02-17 | Inv. 7604.0/5 |  | 1616983.6 | 39342.82 | 428919.81 | 1188063.79 | 22574.74
PRC 3352510PF7801 | 2025-03-10 | Inv. 7604.0/6 |  | 1616983.6 | 321386.65 | 750306.46 | 866677.14 | 39489.84
PRC 3352510PG7801 | 2025-04-25 | Inv. 7604.0/7 |  | 1616983.6 | 738604.75 | 1488911.21 | 128072.39 | 78363.79
PRC 3352510PH7801 | 2025-05-06 | Inv. 7604.0/8 |  | 1616983.6 | 128072.39 | 1616983.6 | 0 | 85104.45
PO 33525107801 | 2025-05-07 | Closing Unencumbered PO | 0 | 1616983.6 |  | 1616983.6 | 0
PO 33525107801A | 2025-05-07 | Opening PO as Encumbered | 1767011.4 | 3383995 |  | 1616983.6 | 1767011.4
PRC 3352510PI7801A | 2025-06-17 | Inv. 7604.0/9 |  | 3383995 | 321674.93 | 1938658.53 | 1445336.47 | 102034.72
|  |  |  | 3383995 |  | 1938658.53 | 1445336.47
|  |  |  | 3383995 |  | 1938658.53 | 1445336.47
|  |  |  | 3383995 |  | 1938658.53 | 1445336.47
|  | Totals: | 3383995 |  | 1938658.53 |  | 1445336.47
|  | Contract | 3356650 |  | 1916063.16 |  | 1440586.84
|  | CO #1 10/15/24 | 3271 |  | 1864.47 |  | 1406.53
|  | CO #2 12/11/24 | 21822 |  | 20730.9 |  | 1091.1
|  | CO #3 02/21/25(No Cost CO) | 0 |  |  |  | 0
|  | CO #4 04/23/25 | 2252 |  |  |  | 2252
|  | Total: | 3383995 |  | 1938658.53 |  | 1445336.47

## #9223.00 Tri-City Electric Co.
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
Tri-City Electric Co. |  |  | Vendor: 00002106567
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524145803 | 2024-05-24 | PO Procore | 13697 | 13697 |  |  | 13697 | FY24
PO 33525145803 | 2024-08-27 | Roll to FY25 |  | 13697 |  | 0 | 13697
PRC 3352514PA5803 | 2024-09-11 | Inv. 315511 | -11524.19 | 2172.81 | 2172.81 | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  |  |  | 2172.81 |  | 2172.81 | 0
|  | Totals: | 2172.81 |  | 2172.81 |  | 0 | FINAL

## #9223.00 System Technology
DOC CCF New Kitchen & Laundry Addition - Amendment #002
Project # 9223.00
Program code 922300 |  |  | Major Program 4B01
System Technology Services |  |  | Vendor: 00003226559
Acct. Codes-0506-335-DA24-9255 |  |  | RFB922300-04
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525052902 | 2025-02-21 | PO Procore (Unencumbered) |  | 0 |  |  | 0
PO 33525052902 | 2025-05-07 | Closing Unencumbered PO | 0 | 0 |  | 0 | 0
PO 33525052902A | 2025-05-07 | Opening PO as Encumbered | 153000 | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  |  |  | 153000 |  | 0 | 153000
|  | Totals: | 153000 |  | 0 |  | 153000

## RECAP #9279.30
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
| Program code 927930 |  |  | Major Program 4B02
Recap
| Acct. Codes-0506-335-DA24 |  |  | Wating until 7/01/24 for eDAS code
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 5572736
| Shive Hattery |  | 152001 | 143289 | 8712
| PM TIME |  | 64900 | 43570.05 | 21329.95
| Misc. |  | 4382.12 | 4382.12 | 0
| SystemWorks |  | 40980 | 21833 | 19147
C | ATC Group |  | 14677.5 | 14677.5 | 0
C | ATC Group (2) |  | 3311.25 | 3311.25 | 0
C | Van Maanen Electric |  | 130139.44 | 130139.44 | 0
| Pleva Plumbing & Heating |  | 2921936.21 | 2715391.41 | 206544.8
| Story Construction #W02CA |  | 521253.87 | 375641.8 | 145612.07
C | Story Construction #W02PC |  | 24072.7 | 24072.7 | 0
| Earth Services & Abatement |  | 43825 | 41633.75 | 2191.25
| Hilsabeck Schacht |  | 240630.11 | 240630.11 | 0
C | Black Hills Energy |  | 181690.85 | 181690.85 | 0
| Shive Hattery (2) |  | 60614 | 52243.28 | 8370.72
C | Story Construction #W02.1PC |  | 20722.81 | 20722.81 | 0
C | Mahoney Fire Sprinkler |  | 2834 | 2834 | 0
| Kline Electrical |  | 1144000 | 0 | 1144000
| Total Project Cost | 5572736 | 5571970.86 | 4016063.07 | 1555907.79 | 765.14

## #9279.30 Funds Rec'd
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUDECENTRALIZATION3 | 2023-07-26 | 5572736 | 5572736
|  |  | Returning FY24 Funds to Agency | IET 33524226923 | 2024-08-13 | -3803363.85 | -3803363.85
|  |  | Returning FY24 Funds to Agency Correction | IET 33524226923A | 2024-08-21 | -4225.86 | -4225.86
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525293903 | 2024-09-19 | 3807589.71 | 3807589.71
| Total Requested | 0 | Total Transferred |  |  | 5572736 | 5572736

## #9279.30 Shive Hattery
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA24-9260 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Split with MM22 & MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524116902 | 2023-08-04 | CO #2 | 89300 | 89300 |  |  | 89300
PRC 3352411PD6902 | 2023-08-31 | Inv. 2142203394-4 (Split between MM22 and DA24) |  | 89300 | 21375 | 21375 | 67925
PRC 3352411PE6902 | 2023-10-04 | Inv. 2142203394-5 (Split between MM22 and DA24) |  | 89300 | 59850 | 81225 | 8075
PO 33524116902 | 2023-11-29 | CO #3 (100% DA24) | 4621 | 93921 |  | 81225 | 12696
PRC 3352411PF6902 | 2023-12-06 | Inv. 2142203394-6 (Split between MM22 and DA24) |  | 93921 | 4275 | 85500 | 8421
PO 33524116902 | 2024-01-19 | CO #4 (Split between MM24 and DA24) | 58080 | 152001 |  | 85500 | 66501
PRC 3352411PG6902 | 2024-01-20 | Inv. 2142203394-7(Split between MM22 and DA24) |  | 152001 | 8421 | 93921 | 58080
PRC 3352411PH6902 | 2024-04-10 | Inv. 2142203394-8(Split between DA24 and MM24) |  | 152001 | 2904 | 96825 | 55176
PRC 3352411PI6902 | 2024-05-07 | Inv. 2142203394-9(Split between DA24 and MM24) |  | 152001 | 2904 | 99729 | 52272
PRC 3352411PJ6902 | 2024-07-11 | Inv. 2142203394-10(Split between MM24 and DA24) |  | 152001 | 14043.5 | 113772.5 | 38228.5 | FY24
PO 33525116902 | 2024-08-28 | Roll to FY25 | 0 | 152001 |  | 113772.5 | 38228.5
PRC 3352511PK6902 | 2024-10-30 | Inv. 2142203394-11(Split between DA24 and MM24) |  | 152001 | 23708.5 | 137481 | 14520
PRC 3352511PL6902 | 2024-11-21 | Inv. 2142203394-12(Split between DA24 and MM24) |  | 152001 | 5808 | 143289 | 8712
|  |  |  | 152001 |  | 143289 | 8712
|  |  |  | 152001 |  | 143289 | 8712
|  |  |  | 152001 |  | 143289 | 8712
|  | Totals: | 152001 |  | 143289 |  | 8712
|  | MM22 (Closed 01/20/24) | 217100 |  | 217100 |  | 0
|  | MM24 | 25969 |  | 18402.5 |  | 7566.5
|  | Total Contrat: | 395070 |  | 378791.5 |  | 16278.5

## #9279.30 PM TIME
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K |  |  |  | eDAS E27A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 64900 | 64900 |  |  | 64900
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 64900 | 175.04 | 175.04 | 64724.96
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 64900 | 1115.8 | 1290.84 | 63609.16
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 64900 | 75.74 | 1366.58 | 63533.42
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 64900 | 424.1 | 1790.68 | 63109.32
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 64900 | 566.74 | 2357.42 | 62542.58
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 64900 | 3933 | 6290.42 | 58609.58
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 64900 | 124.29 | 6414.71 | 58485.29
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 64900 | 1001.5 | 7416.21 | 57483.79
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 64900 | 233.38 | 7649.59 | 57250.41
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 64900 | 1764.7 | 9414.29 | 55485.71
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 64900 | 177.44 | 9591.73 | 55308.27
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 64900 | 1305.9 | 10897.63 | 54002.37
IET DAS202407115300001 | 2024-02-07 |  | Finance Support for January 1-31, 2024 |  | 64900 | 308.02 | 11205.65 | 53694.35
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 64900 | 2715.9 | 13921.55 | 50978.45
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 64900 | 481.26 | 14402.81 | 50497.19
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 64900 | 2425.8 | 16828.61 | 48071.39
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 64900 | 333.94 | 17162.55 | 47737.45
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 64900 | 2532.9 | 19695.45 | 45204.55
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 64900 | 300.39 | 19995.84 | 44904.16
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 64900 | 2668 | 22663.84 | 42236.16
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 64900 | 300.5 | 22964.34 | 41935.66
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 64900 | 2485.2 | 25449.54 | 39450.46
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 64900 | 381.15 | 25830.69 | 39069.31
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 64900 | 3486.3 | 29316.99 | 35583.01
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 64900 | 177.13 | 29494.12 | 35405.88
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 64900 | 1936.1 | 31430.22 | 33469.78
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 64900 | 332.53 | 31762.75 | 33137.25
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 64900 | 1693.9 | 33456.65 | 31443.35
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 64900 | 261.17 | 33717.82 | 31182.18
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 64900 | 2324.1 | 36041.92 | 28858.08
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 64900 | 276.13 | 36318.05 | 28581.95
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 64900 | 1846.7 | 38164.75 | 26735.25
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 64900 | 188.19 | 38352.94 | 26547.06
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 64900 | 1248.4 | 39601.34 | 25298.66
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 64900 | 104.91 | 39706.25 | 25193.75
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 64900 | 1046.3 | 40752.55 | 24147.45
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 64900 | 90 | 40842.55 | 24057.45
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 64900 | 959.9 | 41802.45 | 23097.55
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 64900 | 146.32 | 41948.77 | 22951.23
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 64900 | 632.5 | 42581.27 | 22318.73
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 64900 | 65.94 | 42647.21 | 22252.79
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 64900 | 471.5 | 43118.71 | 21781.29
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 64900 | 17.44 | 43136.15 | 21763.85
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 64900 | 120.6 | 43256.75 | 21643.25
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 64900 | 35.6 | 43292.35 | 21607.65
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 64900 | 277.7 | 43570.05 | 21329.95
[5 empty] | 64900 |  | 43570.05 | 21329.95
[5 empty] | 64900 |  | 43570.05 | 21329.95
[5 empty] | 64900 |  | 43570.05 | 21329.95
|  |  | Totals: | 64900 |  | 43570.05 |  | 21329.95
Note on E9: Huggins, Joni [DAS]: PM Time Budget for DA24 9279.30 $Joni Kleene, Jennifer 2:13 PM (52 minutes ago) to me Please create a PM Time budget for $8,800.00 for DA24 9279.30. Regards, Jennifer Jennifer Kleene, Owner’s Representative Re: PM Time $Joni Kleene, Jennifer Dec 11, 2023, 5:17 PM (14 hours ago) to me Please increase the PM Time budget for 9289.00 by $3,740.00. Please increase the PM time budget for 9279.30 in DA24 by $56,100.00. Please increase the PM time budget for 9244 in MM22 by $3,740.00. Please increase the PM time budget for 9268.01 in R22M by $2,138.40. Regards, Jennifer

## #9279.30 Misc
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 330 | 330
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 330 | 660
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2024 | DAS2024071153 | 55 | 715
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 192.5 | 907.5
PRC 33524080811 | 2024-03-20 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL436 | 1000.05 | 1907.55
GAX 33524082922 | 2024-03-22 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 759580(Split w/MM24) | 2660 | 4567.55
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -907.5 | 3660.05
PRC 33524199901 | 2024-07-17 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL767 | 722.07 | 4382.12
4382.12
4382.12
4382.12
4382.12
|  |  |  | Totals: |  | 4382.12

## #9279.30 SystemWorks
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
SystemWorks |  |  | Vendor:00002144353
Acct. Codes-0506-335-DA24-9255 |  |  | RFP927900-02
Project Manager - Jennifer K |  |  | Activity code: CNST
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524233802 | 2023-08-21 | PO Procore | 40980 | 40980 |  |  | 40980
PRC 3352423PA3802 | 2024-03-18 | Inv. 11688(100% to DA24) |  | 40980 | 2965 | 2965 | 38015
PRC 3352423PB3802 | 2024-07-03 | Inv. 11873(Split between MM22 and DA24) |  | 40980 | 6000 | 8965 | 32015 | FY24
PO 33525233802 | 2024-08-28 | Roll to FY25 | 0 | 40980 |  | 8965 | 32015
PRC 3352523PC3802 | 2025-03-21 | Inv. 12279 |  | 40980 | 12868 | 21833 | 19147
PO 33525233802 | 2025-05-02 | CO #1 - Moving MM22 to MM24 | 0 | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  |  |  | 40980 |  | 21833 | 19147
|  | Totals: | 40980 |  | 21833 |  | 19147
|  | MM22 Closed 05/02/25 | 7612 |  | 7612 |  | 0
|  | MM24 | 1903 |  | 0 |  | 1903
|  | Total Contract: | 50495 |  | 29445 |  | 21050

## #9279.30 ATC Group
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
ATC Group |  |  | Vendor:00002134218
Acct. Codes-0506-335-DA24-9255 |  |  | MA00520262C
Project Manager - Jennifer K |  |  | Activity code: CNST
Split with DA23 and MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524264800 | 2023-09-21 | DO Procore | 14560 | 14560 |  |  | 14560
DO 33524264800 | 2024-04-16 | CO #1 | 117.5 | 14677.5 |  | 0 | 14677.5
PRC 3352426PA4800 | 2024-04-26 | Inv. 9279.31-001(Split w/DA23 & MM22) |  | 14677.5 |  | 0 | 14677.5
|  |  |  | 14677.5 | 14677.5 | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  |  |  | 14677.5 |  | 14677.5 | 0
|  | Totals: | 14677.5 |  | 14677.5 |  | 0
|  | Contract Line 7 - Field Technician Hourly Rate (67 hours at $75.00/hr) | 5025 |  | 5025 |  | 0
|  | Contract Line 8 - Hygienist Hourly Rate (67 hours at $95.00/hr) | 6365 |  | 6365 |  | 0
|  | Contract Line 5 - Adminstrative Hourly Rate (11 hours at $45.00/hr) | 495 |  | 495 |  | 0
|  | Contract Line 2 - Asbestos Per Sample Fee (170 samples at $10.00/ea) | 1700 |  | 1700 |  | 0
|  | Contract Line 3 - Lead Per Sample Fee (65 samples at $15.00/ea) | 975 |  | 975 |  | 0
|  | CO #1 | 117.5 |  | 117.5 |  | 0
|  | Total: | 14677.5 |  | 14677.5 |  | 0
|  | MM22 | #N/A |  | #N/A |  | #N/A
|  | DA23 | 2737.5 |  | 2737.5 |  | 0
|  | Total: | #N/A |  | #N/A |  | #N/A

## #9279.30 ATC Group (2)
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
ATC Group (2) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA24-9255 |  |  | MA00520262C
Project Manager - Jennifer K |  |  | Activity code: CNST
Split with MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524349800 | 2023-12-15 | DO Procore | 10516.25 | 10516.25 |  |  | 10516.25
DO 33524349800 | 2024-02-08 | CO #1(100% to DA24) | 965 | 11481.25 |  | 0 | 11481.25
DO 3352434PA9800 | 2024-04-15 | Inv. 2559085(Split with MM22) |  | 11481.25 | 1782.5 | 1782.5 | 9698.75
DO 33524349800 | 2024-06-28 | Closing DO to Apply CO#2 |  | 11481.25 |  | 1782.5 | 9698.75
DO 33524349800A | 2024-06-28 | Opeing DO W/4th Commodity Line | 200 | 11681.25 |  | 1782.5 | 9898.75
DO 3352434PB9800A | 2024-07-25 | Inv. 9279.30-002(Split with MM22) |  | 11681.25 | 1528.75 | 3311.25 | 8370 | FY24
DO 33525349800A | 2024-08-28 | Roll to FY25 | 0 | 11681.25 |  | 3311.25 | 8370
DO 33525349800A | 2025-05-15 | Closing PO Per Vendor and PM Email | -8370 | 3311.25 |  | 3311.25 | 0
|  |  |  | 3311.25 |  | 3311.25 | 0
|  |  |  | 3311.25 |  | 3311.25 | 0
|  |  |  | 3311.25 |  | 3311.25 | 0
|  |  |  | 3311.25 |  | 3311.25 | 0
|  |  |  | 3311.25 |  | 3311.25 | 0
|  | Totals: | 3311.25 |  | 3311.25 |  | 0
|  | Contract Line 7 - Field Technician Hourly Rate (87.5 hours at $75.00/hr) | 1762.5 |  | 1762.5 |  | 0
|  | Contract Line 8 - Hygienist Hourly Rate (34.75 hours at $95.00/hr) | 1377.5 |  | 1377.5 |  | 0
|  | Contract Line 5 - Adminstrative Hourly Rate (14.5 hours at $45.00/hr) | 101.25 |  | 101.25 |  | 0
|  | Contract Line 4 Asbestos 20Samples @10 | 70 |  | 70 |  | 0
|  | Total: | 3311.25 |  | 3311.25 |  | 0
|  | MM22 | 1883.75 |  | 1883.75 |  | 0
|  | Total Contract: | 5195 |  | 5195 |  | 0

## #9279.30 Van Maanen Electric
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Van Maanen Electric |  |  | Vendor:00002091370
Acct. Codes-0506-335-DA24-9255 |  |  | RFP927900-02
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split with MM24 & DA23 9279.31
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524018905 | 2024-01-18 | PO Procore | 110000 | 110000 |  |  | 110000
PRC 3352401PA8905 | 2024-07-09 | Inv. 2391-01B(Split w/MM24) |  | 110000 | 21316.56 | 21316.56 | 88683.44 | 1121.92 | FY24
PO 33525018905 | 2024-08-28 | Roll to FY25 | 0 | 110000 |  | 21316.56 | 88683.44
PO 33525018905 | 2024-11-18 | CO #1 (Split with DA23 9279.31) | 20139.44 | 130139.44 |  | 21316.56 | 108822.88
PRC 3352501PB8905 | 2024-11-21 | Inv. 2394-02B(Split w/MM24 & DA24) |  | 130139.44 | 74863.54 | 96180.1 | 33959.34 | 5062.11
PO 33525018905 | 2024-12-06 | CO #2 (No Cost CO) | 0 | 130139.44 |  | 96180.1 | 33959.34
PO 33525018905 | 2025-03-05 | CO #3 (No Cost CO) | 0 | 130139.44 |  | 96180.1 | 33959.34
PRC 3352501PC8905 | 2025-05-08 | Inv. 2394-03B(Split w/MM24, DA24, & DA23) |  | 130139.44 | 24317.27 | 120497.37 | 9642.07 | 6341.99
PRC 3352501PD8905 | 2025-06-26 | Inv. 2394.04B(Split w/MM24 & DA24) |  | 130139.44 | 3135.08 | 123632.45 | 6506.99 | 6506.99
PRC 3352501PE8905 | 2025-06-30 | Inv. 2394-05B Retainage(Split w/MM24, DA24 & DA23) |  | 130139.44 | 6506.99 | 130139.44 | 0
|  |  |  | 130139.44 |  | 130139.44 | 0
|  |  |  | 130139.44 |  | 130139.44 | 0
|  |  |  | 130139.44 |  | 130139.44 | 0
|  | Totals: | 130139.44 |  | 130139.44 |  | 0
|  | MM24 9279.30 | 30000 |  | 30000 |  | 0
|  | DA23 9279.31 | 3351.89 |  | 3351.89 |  | 0
|  | Total Contract: | 163491.33 |  | 163491.33 |  | 0
Vendor used Inv. 2394-0X in a previous tab, please add a B after the invoice

## #9279.30 Pleva Plumbing
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Pleva Plumbing & Heating |  |  | Vendor:00003054699
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927930-01
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524019906 | 2024-01-19 | PO Procore | 2821338 | 2821338 |  |  | 2821338
PRC 3352401PA9906 | 2024-05-13 | Inv. 9279.30-01(100% to DA24) |  | 2821338 | 625385 | 625385 | 2195953 | 32915
PO 33524019906 | 2024-05-16 | CO #1 | 27759.75 | 2849097.75 |  | 625385 | 2223712.75
PRC 3352401PB9906 | 2024-06-17 | Inv. 9279.30-02(Split Between MM24 & DA24) |  | 2849097.75 | 333490.85 | 958875.85 | 1890221.9 | 50467.15
PRC 3352401PC9906 | 2024-07-03 | Inv. 9279.30-03(Split Between MM24 & DA24) |  | 2849097.75 | 253650 | 1212525.85 | 1636571.9 | 63817.15 | FY24
PO 33525019906 | 2024-08-28 | Roll to FY25 | 0 | 2849097.75 |  | 1212525.85 | 1636571.9
PRC 3352501PD9906 | 2024-09-19 | Inv. 9279.30-04(Split Between MM24 & DA24) |  | 2849097.75 | 386916 | 1599441.85 | 1249655.9 | 84181.15
PO 33525019906 | 2024-09-26 | CO #2(Split Between MM24 & DA24) | 74256.14 | 2923353.89 |  | 1599441.85 | 1323912.04
PRC 3352501PE9906 | 2024-10-07 | Inv. 9279.30-05(Split Between MM24 & DA24) |  | 2923353.89 | 387012.9 | 1986454.75 | 936899.14 | 104550.25
PRC 3352501PF9906 | 2024-10-22 | Inv. 9279.30-06(Split Between MM24 & DA24) |  | 2923353.89 | 123500 | 2109954.75 | 813399.14 | 111050.25
CDE 33525323902 | 2024-11-18 | Correct previous payment distribution |  | 2923353.89 | -123500 | 1986454.75 | 936899.14 | 104550.25
CDE 33525323902 | 2024-11-18 | Correct previous payment distribution |  | 2923353.89 | 276469.95 | 2262924.7 | 660429.19 | 119101.3
PRC 3352501PG9906 | 2024-11-19 | Inv. 9279.30-07(Split Between MM24 & DA24) |  | 2923353.89 | 258088.16 | 2521012.86 | 402341.03 | 132684.89
PO 33525019906 | 2024-11-20 | Close PO to correct balance division amounts after CDE33525323902 | 0 | 2923353.89 |  | 2521012.86 | 402341.03
PO 33525019906A | 2024-11-20 | PO Procore | 0 | 2923353.89 |  | 2521012.86 | 402341.03
PO 33525019906A | 2024-12-05 | CO #3(100% to DA24) | 7473.41 | 2930827.3 |  | 2521012.86 | 409814.44
PO 3352501PH9906A | 2024-12-12 | Inv. 9279.30-08(Split Between MM24 & DA24) |  | 2930827.3 | 192003.55 | 2713016.41 | 217810.89 | 142790.34
PO 3352501PI9906A | 2025-01-14 | Inv. 9279.30-09(100% to DA24) |  | 2930827.3 | 2375 | 2715391.41 | 215435.89 | 142915.34
PO 33525019906A | 2025-03-18 | CO #4(Split with MM24) | -8891.09 | 2921936.21 |  | 2715391.41 | 206544.8
|  |  |  | 2921936.21 |  | 2715391.41 | 206544.8
|  | Totals: | 2921936.21 |  | 2715391.41 |  | 206544.8
|  | MM24 | 1522329.55 |  | 1385205.45 |  | 137124.1
|  | Total Contract: | 4444265.76 |  | 4100596.86 |  | 343668.9

## #9279.30 Story Construction
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Story Construction #W02CA |  |  | Vendor:00002110695
Acct. Codes-0506-335-DA24-9255 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: CMGR
Split with 9279.30 MM24 and 9279.32 DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524026800 | 2024-01-26 | PO Procore | 508470.46 | 508470.46 |  |  | 508470.46
PO 33524026800 | 2024-02-27 | CO #1 | 7786.91 | 516257.37 |  | 0 | 516257.37
PRC 3352402PA6800 | 2024-03-19 | Inv. 34287 (Split between MM24 and DA24 9279.32) |  | 516257.37 | 9515.11 | 9515.11 | 506742.26
PRC 3352402PB6800 | 2024-04-26 | Inv. 34326 (Split between MM24 and DA24 9279.32) |  | 516257.37 | 26404.99 | 35920.1 | 480337.27
PRC 3352402PC6800 | 2024-05-21 | Inv. 34360 (Split between MM24 and DA24 9279.32) |  | 516257.37 | 20518.4 | 56438.5 | 459818.87
PRC 3352402PD6800 | 2024-05-13 | Inv. 34398(Split Between MM24 and DA24 9279.30) |  | 516257.37 | 34123.07 | 90561.57 | 425695.8
PRC 3352402PE6800 | 2024-07-29 | Inv. 34448(Split Between MM24, DA24 9279.32, 9279.30) |  | 516257.37 | 30921.18 | 121482.75 | 394774.62 | FY24
PO 33525026800 | 2024-08-28 | Roll to FY25 | 0 | 516257.37 |  | 121482.75 | 394774.62
PRC 3352502PF6800 | 2024-09-19 | Inv. 34488(Split Between MM24, DA24 9279.30) |  | 516257.37 | 22420.29 | 143903.04 | 372354.33
PRC 3352502PG6800 | 2024-10-02 | Inv. 34518(Split Between MM24, DA24 9279.30) |  | 516257.37 | 36600.94 | 180503.98 | 335753.39
PRC 3352502PH6800 | 2024-10-18 | Inv. 34565(Split Between MM24, DA24 9279.30) |  | 516257.37 | 22487.31 | 202991.29 | 313266.08
PO 33525026800 | 2024-11-18 | CO #2(Split with MM24 & DA24 9279.30) | 4996.5 | 521253.87 |  | 202991.29 | 318262.58
PRC 3352502PI6800 | 2024-11-19 | Inv. 34608(Split Between MM24, DA24 9279.30) |  | 521253.87 | 30566.68 | 233557.97 | 287695.9
PRC 3352502PJ6800 | 2024-12-17 | Inv. 34659(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 25447.29 | 259005.26 | 262248.61
PRC 3352502PK6800 | 2025-01-23 | Inv. 34698(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 23904.99 | 282910.25 | 238343.62
PRC 3352502PL6800 | 2025-02-17 | Inv. 34731(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 31185.71 | 314095.96 | 207157.91
PRC 3352502PM6800 | 2025-03-21 | Inv. 34765(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 19514.37 | 333610.33 | 187643.54
PRC 3352502PN6800 | 2025-04-18 | Inv. 34799(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 16464.21 | 350074.54 | 171179.33
PRC 3352502PO6800 | 2025-05-21 | Inv. 34836(Split Between MM24 & DA24 9279.30) |  | 521253.87 | 13883.39 | 363957.93 | 157295.94
PRC 3352502PP6800 | 2025-06-16 | Inv. 34864(Split Between MM24, DA24 9279.30 & 9279.32) |  | 521253.87 | 11683.87 | 375641.8 | 145612.07
|  |  |  | 521253.87 |  | 375641.8 | 145612.07
|  |  |  | 521253.87 |  | 375641.8 | 145612.07
|  |  |  | 521253.87 |  | 375641.8 | 145612.07
|  | Totals: | 521253.87 |  | 375641.8 |  | 145612.07
|  | MM24 9279.30 | 259272.09 |  | 224712.58 |  | 34559.51
|  | DA24 9279.32 Closed 06/16/25 | 3604.98 |  | 3604.98 |  | 0
|  | Total Contract: | 784130.94 |  | 603959.36 |  | 180171.58

## #9279.30 Story Construction (2)
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Story Construction #W02PC |  |  | Vendor:00002110695
Acct. Codes-0506-335-DA24-9255 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: CMGR
Split with MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524111901 | 2024-02-08 | CO #2 | 24072.7 | 24072.7 |  |  | 24072.7
CDE 33524039803 | 2024-02-08 | Move expense from MM22 |  | 24072.7 | 13783.37 | 13783.37 | 10289.33
PRC 3352411PG1901 | 2024-02-15 | Inv. 34253-FINAL(Split with MM22) |  | 24072.7 | 10289.33 | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  |  |  | 24072.7 |  | 24072.7 | 0
|  | Totals: | 24072.7 |  | 24072.7 |  | 0 | FINAL
|  | CM Services | 24072.7 |  | 24072.7 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Totals: | 24072.7 |  | 24072.7 |  | 0
|  | MM22 | 15505.28 |  | 15505.28 |  | 0
|  | Total: | 39577.98 |  | 39577.98 |  | 0

## #9279.30 Earth Services & Abate
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Earth Services & Abatement |  |  | Vendor:VS000007582
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927930-02
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524057802 | 2024-02-26 | PO Procore | 51150 | 51150 |  |  | 51150
PRC 3352405PA7802 | 2024-05-03 | Inv. 9279.30-001(100% to MM24) |  | 51150 | 23560 | 23560 | 27590 | 1240
PO 33524057802 | 2024-05-16 | CO #1 | 1950 | 53100 |  | 23560 | 29540
PRC 3352405PB7802 | 2024-05-23 | Inv. 9279.30-002(Split Between MM24 and DA24) |  | 53100 | 13347.5 | 36907.5 | 16192.5 | 1942.5
PRC 3352405PC7802 | 2024-06-05 | Inv. AIA 3 (100% to DA24) |  | 53100 | 1852.5 | 38760 | 14340 | 2040
PO 33524057802 | 2024-06-19 | CO #2 (100% to DA24) | 625 | 53725 |  | 38760 | 14965
PRC 3352405PD7802 | 2024-07-05 | Inv. AIA 4(Split With MM24) |  | 53725 | 593.75 | 39353.75 | 14371.25 | 2071.25 | FY24
PO 33525057802 | 2024-08-28 | Roll to FY25 | 0 | 53725 |  | 39353.75 | 14371.25
PO 33525057802 | 2024-09-19 | CO #3 (100% to DA24) | 1025 | 54750 |  | 39353.75 | 15396.25
PRC 3352505PE7802 | 2024-10-30 | Inv. 9279.30-016 - Billing 5 (100% to DA24) |  | 54750 | 1330 | 40683.75 | 14066.25 | 2141.25
PO 33525057802 | 2024-12-23 | CO #4 (Split with MM24) | -10925 | 43825 |  | 40683.75 | 3141.25
PRC 3352505PF7802 | 2025-04-08 | Inv. AIA 6 (100% to DA24) |  | 43825 | 950 | 41633.75 | 2191.25 | 2191.25
|  |  |  | 43825 |  | 41633.75 | 2191.25
|  | Totals: | 43825 |  | 41633.75 |  | 2191.25
|  | MM24 | 2800 |  | 2660 |  | 140
|  | Total Contract: | 46625 |  | 44293.75 |  | 2331.25

## #9279.30 Hilsabeck Schacht
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927930-02
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split with MM24, DA23.31,DA24.32
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524058912 | 2024-02-27 | PO Procore | 232010 | 232010 |  |  | 232010
PRC 3352405PA8912 | 2024-05-14 | Inv. 9279.30&.32-01(Split W/DA23 & MM24) |  | 232010 | 34407.56 | 34407.56 | 197602.44 | 1810.94
PO 33524058912 | 2024-06-19 | CO #1 | 8620.11 | 240630.11 |  | 34407.56 | 206222.55
PRC 3352405PB8912 | 2024-06-28 | Inv. 9279.30&.32-02(100% to DA24) |  | 240630.11 | 12693.42 | 47100.98 | 193529.13 | 2479.02
PRC 3352405PC8912 | 2024-07-24 | Inv. 9279.30&.32-03(100% to DA24) |  | 240630.11 | 104872.64 | 151973.62 | 88656.49 | 7998.65 | FY24
PO 33525058912 | 2024-08-27 | Roll to FY25 | 0 | 240630.11 |  | 151973.62 | 88656.49
PRC 3352505PD8912 | 2024-10-14 | Inv. 9279.30&.32-04(Split W/MM24, DA23 &DA24) |  | 240630.11 | 36662.69 | 188636.31 | 51993.8 | 9928.28
PO 33525058912 | 2024-12-09 | CO #2 No Cost CO | 0 | 240630.11 |  | 188636.31 | 51993.8
PRC 3352505PE8912 | 2025-01-28 | Inv. 9279.30~32-05(Split W/MM24, 927930DA24, 927932DA24) |  | 240630.11 | 36009.75 | 224646.06 | 15984.05 | 11823.53
PRC 3352505PF8912 | 2025-02-06 | Inv. 9279.30~32-06(Split W/MM24, 927930DA24, 927932DA24) |  | 240630.11 | 896.04 | 225542.1 | 15088.01 | 11870.71
PO 3352505PG8912 | 2025-05-09 | Inv. 9279.30~32-07(100% to 927930DA24) |  | 240630.11 | 1335.7 | 226877.8 | 13752.31 | 11941.01
PO 3352505PH8912 | 2025-06-18 | Inv. 9279.30~32-08(Split W/MM24, 927930DA24, 927931DA23, 927932DA24) |  | 240630.11 | 1720.71 | 228598.51 | 12031.6 | 12031.6
PO 3352505PI8912 | 2025-06-23 | Inv. 9279.30~32-09-Retention(Split W/MM24, 927930DA24, 927931DA23, 927932DA24) |  | 240630.11 | 12031.6 | 240630.11 | 0
|  | Totals: | 240630.11 |  | 240630.11 |  | 0 | FINAL
|  | MM24 | 23081.28 |  | 23081.28 |  | 0
|  | DA23 9279.31 | 4750 |  | 4750 |  | 0
|  | DA24 9279.32 | 134386.31 |  | 134386.31 |  | 0
|  | Total Contract: | 402847.7 |  | 402847.7 |  | 0

## #9279.30 Black Hills Enegery
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Black Hills Energy |  |  | Vendor: 00002096383
Acct. Codes-0506-335-DA24-9255 |  |  | Sole Source
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524127902 | 2024-05-06 | PO Procore | 147050 | 147050 |  |  | 147050 | FY24
PO 33525127902 | 2024-08-28 | Roll to FY25 |  | 147050 |  | 0 | 147050
PO 33525127902 | 2024-09-19 | CO #1(100% to DA24) | 37000 | 184050 |  | 0 | 184050
PRC 3352512PA7902 | 2024-11-04 | Inv. BHE Invoice 7963827001-Final | -2359.15 | 181690.85 | 181690.85 | 181690.85 | 0
|  |  |  | 181690.85 |  | 181690.85 | 0
|  |  |  | 181690.85 |  | 181690.85 | 0
|  |  |  | 181690.85 |  | 181690.85 | 0
|  |  |  | 181690.85 |  | 181690.85 | 0
|  |  |  | 181690.85 |  | 181690.85 | 0
|  | Totals: | 181690.85 |  | 181690.85 |  | 0 | FINAL
|  |  | 73526 |  | 73526 |  | 0
|  | Total | 255216.85 |  | 255216.85 |  | 0

## #9279.30 Shive Hattery (2)
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA24-9260 |  |  | RFP927900-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524156901 | 2024-06-04 | PO Procore | 60614 | 60614 |  |  | 60614
PRC 3352415PA6901 | 2024-07-12 | Inv. 2240007040-1 |  | 60614 | 19995.7 | 19995.7 | 40618.3 | FY24
PO 33525156901 | 2024-08-28 | Roll to FY25 | 0 | 60614 |  | 19995.7 | 40618.3
PRC 3352515PB6901 | 2025-01-07 | Inv. 2240007040-2 |  | 60614 | 32247.58 | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  |  |  | 60614 |  | 52243.28 | 8370.72
|  | Totals: | 60614 |  | 52243.28 |  | 8370.72

## #9279.30 Story Construction(3)
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Story Construction #W02.1PC |  |  | Vendor:00002110695
Acct. Codes-0506-335-DA24-9255 |  |  | 27900-01
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524178901 | 2024-06-26 | PO Procore | 46123.03 | 46123.03 |  |  | 46123.03 | FY24
PO 33525178901 | 2024-08-28 | Roll to FY25 |  | 46123.03 |  | 0 | 46123.03
PRC 3352517PA8901 | 2024-09-19 | Inv. 34491 |  | 46123.03 | 948.96 | 948.96 | 45174.07
PRC 3352517PB8901 | 2024-09-24 | Inv. 34521 |  | 46123.03 | 15278.72 | 16227.68 | 29895.35
PRC 3352517PC8901 | 2024-10-17 | Inv. 34568 |  | 46123.03 | 1592.89 | 17820.57 | 28302.46
PRC 3352517PD8901 | 2024-11-18 | Inv. 34612 Final | -25400.22 | 20722.81 | 2902.24 | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  |  |  | 20722.81 |  | 20722.81 | 0
|  | Totals: | 20722.81 |  | 20722.81 |  | 0 | FINAL
|  | CM Services | 7162.81 |  | 7162.81 |  | 0
|  | Exploratory Contractor Allowance | 13560 |  | 13560 |  | 0
|  | Totals: | 20722.81 |  | 20722.81 |  | 0

## #9279.30 Mahoney Fire Sprinkler
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Mahoney Fire Sprinkler |  |  | Vendor:00003035382
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927930-01
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split w/ DA24 9279.30 &DA24 9279.32
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525023905 | 2024-12-30 | CO #2(Split between DA24 9279.30 & 9279.32) | 2834 | 2834 |  |  | 2834
PRC 3352502PD3905 | 2025-01-14 | Inv. 9279.31-04(Split between DA24 9279.30 & 9279.32) |  | 2834 | 2692.3 | 2692.3 | 141.7 | 141.7
PRC 3352502PE3905 | 2025-02-21 | Inv. 9279.31-05(100% to 9279.31) |  | 2834 | 0 | 2692.3 | 141.7
PRC 3352502PF3905 | 2025-02-24 | Inv. 9279.31-06 - Retainage (Split between DA23, DA24 9279.30 & 9279.32) |  | 2834 | 141.7 | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  |  |  | 2834 |  | 2834 | 0
|  | Totals: | 2834 |  | 2834 |  | 0 | FINAL
|  | DA23 9279.31 | 320140 |  | 320140 |  | 0
|  | DA24 9279.32 | 1396 |  | 1396 |  | 0
|  | Total: | 324370 |  | 324370 |  | 0

## #9279.30 Kline Electrical
HHS WRC Campus Utility Decentralization Phase 3
Project # 9279.30
Program code 927930 |  |  | Major Program 4B02
Kline Electrical |  |  | Vendor:00003038115
Acct. Codes-0506-335-DA24-9255 |  |  | 927940-02
Project Manager - Jennifer K |  |  | Activity code: BRIN
Split w/ DA25 9279.40
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525169910 | 2025-06-18 | PO Procore | 1144000 | 1144000 |  |  | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  |  |  | 1144000 |  | 0 | 1144000
|  | Totals: | 1144000 |  | 0 |  | 1144000
|  | DA25 9279.40 | 146831 |  | 0 |  | 146831
|  | Total Contract: | 1290831 |  | 0 |  | 1290831

## RECAP #9279.32
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
| Program code 927932 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 142000
| Hilsabeck Schacht |  | 134386.31 | 134386.31 | 0
| PM TIME |  | 2196.02 | 822.12 | 1373.9
| Misc. |  | 0 | 0 | 0
| Story Construction |  | 3604.98 | 3604.98 | 0
C | Mahoney Fire Sprinkler |  | 1396 | 1396 | 0
| Total Project Cost | 142000 | 141583.31 | 140209.41 | 1373.9 | 416.69

## #9279.32 Funds Rec'd
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUDECENTRALIZATION4 | 2024-02-19 | 150000 | 150000
|  |  | Returning FY24 Funds to Agency | IET 33524227905 | 2024-08-14 | -97430.47 | -97430.47
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227905A | 2024-08-21 | -281.26 | -281.26
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263905 | 2024-09-19 | 97711.73 | 97711.73
|  |  | Returning Funds to Agency Per PM | IET 33525136912 | 2025-05-16 | -8000 | -8000
`
| Total Requested | 0 | Total Transferred |  |  | 142000 | 142000

## #9279.32 Hilsabeck Schacht
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  | Major Program 4B02
Hilsabeck Schacht |  |  | Vendor: 0003178029
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927900-02
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Split w/DA23 & MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524058912 | 2024-02-26 | PO Procore | 131090 | 131090 |  |  | 131090
PRC 3352405PA8912 | 2024-05-14 | Inv. 9279.30&.32-01(Split W/DA24 & MM24) |  | 131090 | 0 | 0 | 131090
PO 33524058912 | 2024-06-19 | CO #1 | 3296.31 | 134386.31 |  | 0 | 134386.31
PRC 3352405PB8912 | 2024-06-28 | Inv. 9279.30&.32-02(100% to DA24) |  | 134386.31 | 29367.82 | 29367.82 | 105018.49 | 1545.68
PRC 3352405PC8912 | 2024-07-24 | Inv. 9279.30&.32-03(100% to DA24) |  | 134386.31 | 21070.28 | 50438.1 | 83948.21 | 2654.65 | FY24
PO 33525058912 | 2024-08-27 | Roll to FY25 | 0 | 134386.31 |  | 50438.1 | 83948.21
PRC 3352505PD8912 | 2024-10-14 | Inv. 9279.30&.32-04(Split W/MM24, DA23 &DA24) |  | 134386.31 | 46258.2 | 96696.3 | 37690.01 | 5089.3
PO 33525058912 | 2024-12-09 | CO #2 No Cost CO | 0 | 134386.31 |  | 96696.3 | 37690.01
PRC 3352505PE8912 | 2025-01-28 | Inv. 9279.30~32-05(Split W/MM24, 927930DA24, 927932DA24) |  | 134386.31 | 21948.8 | 118645.1 | 15741.21 | 6244.5
PRC 3352505PF8912 | 2025-02-06 | Inv. 9279.30~32-06(Split W/MM24, 927930DA24, 927932DA24) |  | 134386.31 | 7438.5 | 126083.6 | 8302.71 | 6636
PO 3352505PG8912 | 2025-05-09 | Inv. 9279.30~32-07(100% to 927930DA24) |  | 134386.31 | 0 | 126083.6 | 8302.71
PO 3352505PH8912 | 2025-06-18 | Inv. 9279.30~32-08(Split W/MM24, 927930DA24, 927931DA23, 927932DA24) |  | 134386.31 | 1583.39 | 127666.99 | 6719.32 | 6719.32
PO 3352505PI8912 | 2025-06-23 | Inv. 9279.30~32-09-Retention(Split W/MM24, 927930DA24, 927931DA23, 927932DA24) |  | 134386.31 | 6719.32 | 134386.31 | 0
|  | Totals: | 134386.31 |  | 134386.31 |  | 0 | FINAL
|  | MM24 9279.30 | 23081.28 |  | 23081.28 |  | 0
|  | DA23 9279.31 | 4750 |  | 4750 |  | 0
|  | DA24 9279.30 | 240630.11 |  | 240630.11 |  | 0
|  | Total Contract: | 402847.7 |  | 402847.7 |  | 0

## #9279.32 PM TIME
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2196.02 | 2196.02 |  |  | 2196.02
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 2196.02 | 43.52 | 43.52 | 2152.5
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 2196.02 | 220.6 | 264.12 | 1931.9
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 2196.02 | 16.01 | 280.13 | 1915.89
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 2196.02 | 145.8 | 425.93 | 1770.09
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 2196.02 | 11.83 | 437.76 | 1758.26
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 2196.02 | 128.8 | 566.56 | 1629.46
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 2196.02 | 13.35 | 579.91 | 1616.11
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 2196.02 | 87.9 | 667.81 | 1528.21
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 2196.02 | 3.79 | 671.6 | 1524.42
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 2196.02 | 41 | 712.6 | 1483.42
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 2196.02 | 10.53 | 723.13 | 1472.89
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 2196.02 | 45.9 | 769.03 | 1426.99
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 2196.02 | 6.19 | 775.22 | 1420.8
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 2196.02 | 46.9 | 822.12 | 1373.9
[5 empty] | 2196.02 |  | 822.12 | 1373.9
[5 empty] | 2196.02 |  | 822.12 | 1373.9
|  |  | Totals: | 2196.02 |  | 822.12 |  | 1373.9

## #9279.32 Misc
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9279.32 Story Construction
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA24-9255 |  |  | RFP927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Split with 9279.30 MM24 and 9279.30 DA24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524026800 | 2024-02-27 | PO Procore | 3604.98 | 3604.98 |  |  | 3604.98
PRC 3352402PA6800 | 2024-03-19 | Inv. 34287 (Split between MM24 and DA24 9279.30) |  | 3604.98 | 0 | 0 | 3604.98
PRC 3352402PB6800 | 2024-04-26 | Inv. 34326 (Split between MM24 and DA24 9279.30) |  | 3604.98 | 0 | 0 | 3604.98
PRC 3352402PC6800 | 2024-05-21 | Inv. 34360 (Split between MM24 and DA24 9279.30) |  | 3604.98 | 0 | 0 | 3604.98
PRC 3352402PD6800 | 2024-05-13 | Inv. 34398(Split Between MM24 and DA24 9279.30) |  | 3604.98 | 0 | 0 | 3604.98
PRC 3352402PE6800 | 2024-07-29 | Inv. 34448(Split Between MM24, DA24 9279.32, 9279.30) |  | 3604.98 | 1424.24 | 1424.24 | 2180.74 | FY24
PO 33525026800 | 2024-08-28 | Roll to FY25 | 0 | 3604.98 |  | 1424.24 | 2180.74
PRC 3352502PF6800 | 2024-09-19 | Inv. 34488(Split Between MM24, DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PG6800 | 2024-10-02 | Inv. 34518(Split Between MM24, DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PH6800 | 2024-10-18 | Inv. 34565(Split Between MM24, DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PO 33525026800 | 2024-11-18 | CO #2(Split with MM24 & DA24 9279.30) | 0 | 3604.98 |  | 1424.24 | 2180.74
PRC 3352502PI6800 | 2024-11-19 | Inv. 34608(Split Between MM24, DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PJ6800 | 2024-12-17 | Inv. 34659(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PK6800 | 2025-01-23 | Inv. 34698(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PL6800 | 2025-02-17 | Inv. 34731(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PM6800 | 2025-03-21 | Inv. 34765(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PN6800 | 2025-04-18 | Inv. 34799(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PO6800 | 2025-05-21 | Inv. 34836(Split Between MM24 & DA24 9279.30) |  | 3604.98 | 0 | 1424.24 | 2180.74
PRC 3352502PP6800 | 2025-06-16 | Inv. 34864(Split Between MM24, DA24 9279.30 & 9279.32) |  | 3604.98 | 2180.74 | 3604.98 | 0
|  |  |  | 3604.98 |  | 3604.98 | 0
|  |  |  | 3604.98 |  | 3604.98 | 0
|  | Totals: | 3604.98 |  | 3604.98 |  | 0
|  | MM24 9279.30 | 259272.09 |  | 224712.58 |  | 34559.51
|  | DA24 9279.30 | 521253.87 |  | 375641.8 |  | 145612.07
|  | Total Contract: | 784130.94 |  | 603959.36 |  | 180171.58

## #9279.32 Mahoney Fire Sprinkler
HHS WRC Campus Utility Decentralization Phase 3 Alternates
Project # 9279.32
Program code 927932 |  |  | Major Program 4B02
Mahoney Fire Sprinkler |  |  | Vendor:00003035382
Acct. Codes-0506-335-DA24-9255 |  |  | RFB927930-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Split w/ DA24 9279.30 &DA24 9279.32
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525023905 | 2024-12-30 | CO #2(Split between DA24 9279.30 & 9279.32) | 1396 | 1396 |  |  | 1396
PRC 3352502PD3905 | 2025-01-14 | Inv. 9279.31-04(Split between DA24 9279.30 & 9279.32) |  | 1396 | 1326.2 | 1326.2 | 69.8 | 69.8
PRC 3352502PE3905 | 2025-02-21 | Inv. 9279.31-05(100% to 9279.31) |  | 1396 | 0 | 1326.2 | 69.8
PRC 3352502PF3905 | 2025-02-24 | Inv. 9279.31-06 - Retainage (Split between DA23, DA24 9279.30 & 9279.32) |  | 1396 | 69.8 | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  |  |  | 1396 |  | 1396 | 0
|  | Totals: | 1396 |  | 1396 |  | 0 | FINAL
|  | DA23 9279.31 | 320140 |  | 320140 |  | 0
|  | DA24 9279.30 | 2834 |  | 2834 |  | 0
|  | Total: | 324370 |  | 324370 |  | 0

## RECAP #9314.01
DNR HCR Honey Creek Resort Improvements
Project # 9314.01
Program code 931401 |  |  | Major Program 4H05
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 100000
VendorA |  | 0 | 0 | 0
PM TIME |  | 8800 | 3652.84 | 5147.16
Misc. |  | 0 | 0
Total Project Cost | 100000 | 8800 | 3652.84 | 5147.16 | 91200

## #9314.01 Funds Rec'd
DNR HCR Honey Creek Resort Improvements
Project # 9314.01
Program code 931401 |  |  | Major Program 4H05
Funds Rec'd
Acct Code: 0506-335-DA24-0285
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 005FY24PROJ931401 | 2023-07-31 | 100000 | 100000
|  |  | Returning FY24 Funds to Agency | IET 33524227906 | 2024-08-14 | -96347.16 | -96347.16
|  |  | Moving FY25 Funds from 566A to DA24 | CDR 33525224902 | 2024-08-21 | 96347.16 | 96347.16
| Total Requested | 0 | Total Transferred |  |  | 100000 | 100000

## #9314.01 Vendor A
DNR HCR Honey Creek Resort Improvements
Project # 9314.01
Program code 931401 |  |  | Major Program 4H05
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9314.01 PM TIME
DNR HCR Honey Creek Resort Improvements
Project # 9314.01
Program code 931401 |  |  |  | Major Program 4H05
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E27P
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8800 | 8800 |  |  | 8800
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 8800 | 110.06 | 110.06 | 8689.94
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 8800 | 702.8 | 812.86 | 7987.14
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 8800 | 355.39 | 1168.25 | 7631.75
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 8800 | 1982.8 | 3151.05 | 5648.95
CDE 33524282800 | 2023-10-09 | 2507 | Move PM Time From 9314.01 DA23 |  | 8800 | 45.08 | 3196.13 | 5603.87
CDE 33524282800 | 2023-10-09 | 9500 | Move PM Time From 9314.01 DA23 |  | 8800 | 310.1 | 3506.23 | 5293.77
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 8800 | 16.01 | 3522.24 | 5277.76
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8800 | 130.6 | 3652.84 | 5147.16
[5 empty] | 8800 |  | 3652.84 | 5147.16
[5 empty] | 8800 |  | 3652.84 | 5147.16
[5 empty] | 8800 |  | 3652.84 | 5147.16
[5 empty] | 8800 |  | 3652.84 | 5147.16
|  |  | Totals: | 8800 |  | 3652.84 |  | 5147.16
Note on E9: Jurgenson, John [DAS]: Re: PM Time $John Kleene, Jennifer 11:04 AM (1 hour ago) to me Yes, please set it up for $8,800.00. Regards, Jennifer

## #9314.01 Misc
DNR HCR Honey Creek Resort Improvements
Project # 9314.01
Program code 931401 |  |  |  | Major Program 4H05
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9353.00
DOC IMCC Electrical Service Upgrades
Project # 9353.00
| Program code 935300 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 2800000
| Samuels Group |  | 21090.12 | 20372.6 | 717.52
| PM TIME |  | 56000 | 30056.47 | 25943.53
| Misc. |  | 1450.43 | 1450.43 | 0
| KCL Engineering |  | 169240 | 147036 | 22204
| Cummins Inc |  | 255158.7 | 0 | 255158.7
C | Terracon Consultants |  | 12475 | 12475 | 0
| Grainger Lighting |  | 9499.76 | 9307.32 | 192.44
| Gerard Electric |  | 1522647 | 369999.35 | 1152647.65
| Samuels Group (2) |  | 318749.48 | 15239.76 | 303509.72
| Nelson Electric Co |  | 36825 | 0 | 36825
C | Graybar- Electrical |  | 71.18 | 71.18 | 0
C | Grainger - Conduit & Wire |  | 6860.02 | 6860.02 | 0
| Graybar- Electrical(2) |  | 3394.83 | 0 | 3394.83
| Total Project Cost | 2800000 | 2413461.52 | 612868.13 | 1800593.39 | 386538.48

## #9353.00 Funds Rec'd
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25544A24001 | 2023-10-16 | 2800 | 2800
|  |  | Funds Transferred without Program Code | CDR 33524290904 | 2023-10-17 | 0 | 0
|  |  | MOU | IET 25544A24002 | 2023-10-17 | 2797200 | 2797200
|  |  | Funds Transferred without Program Code | CDR 33524291900 | 2023-10-18 | 0 | 0
|  |  | Returning FY24 Funds to Agency | IET 33524227907 | 2024-08-14 | -2752263.77 | -2752263.77
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227907A | 2024-08-26 | -1032.38 | -1032.38
|  |  | Received FY25 Funds From Agency | IET 25544A25001 | 2024-09-09 | 2753296.15 | 2753296.15
| Total Requested | 0 | Total Transferred |  |  | 2800000 | 2800000

## #9353.00 Samuels Group
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524335901 | 2023-12-01 | PO Procore | 21090.12 | 21090.12 |  |  | 21090.12
PRC 3352433PA5901 | 2024-01-05 | Inv. 7559.01 PC |  | 21090.12 | 4337.36 | 4337.36 | 16752.76
PRC 3352433PB5901 | 2024-02-12 | Inv. 7559.02 PC |  | 21090.12 | 2650.93 | 6988.29 | 14101.83
PRC 3352433PC5901 | 2024-04-02 | Inv. 7559.03 PC |  | 21090.12 | 1937.24 | 8925.53 | 12164.59
PRC 3352433PD5901 | 2024-05-09 | Inv. 7559.04 PC |  | 21090.12 | 1577.36 | 10502.89 | 10587.23
PRC 3352433PE5901 | 2024-05-30 | Inv. 7559.05 PC |  | 21090.12 | 560.36 | 11063.25 | 10026.87
PRC 3352433PF5901 | 2024-07-08 | Inv. 7559.06 PC |  | 21090.12 | 480 | 11543.25 | 9546.87 | FY24
PO 33525335901 | 2024-08-28 | Roll to FY25 | 0 | 21090.12 |  | 11543.25 | 9546.87
PRC 3352533PG5901 | 2024-09-11 | Inv. 7559.07 PC |  | 21090.12 | 480 | 12023.25 | 9066.87
PRC 3352533PH5901 | 2024-09-12 | Inv. 7559.08 PC |  | 21090.12 | 960 | 12983.25 | 8106.87
PRC 3352533PI5901 | 2024-10-02 | Inv. 7559.09 PC |  | 21090.12 | 960 | 13943.25 | 7146.87
PRC 3352533PJ5901 | 2024-11-05 | Inv. 7559.10PC |  | 21090.12 | 2037 | 15980.25 | 5109.87
PRC 3352533PK5901 | 2024-12-06 | Inv. 7559.11 PC |  | 21090.12 | 480 | 16460.25 | 4629.87
PRC 3352533PL5901 | 2025-11-24 | Inv. 7559.12PC |  | 21090.12 | 1868.28 | 18328.53 | 2761.59
PRC 3352533PM5901 | 2025-03-10 | Inv. 7559.13 PC |  | 21090.12 | 1292.9 | 19621.43 | 1468.69
PRC 3352533PN5901 | 2025-04-11 | Inv. 7559.14PC |  | 21090.12 | 751.17 | 20372.6 | 717.52
|  |  |  | 21090.12 |  | 20372.6 | 717.52
|  |  |  | 21090.12 |  | 20372.6 | 717.52
|  | Totals: | 21090.12 |  | 20372.6 |  | 717.52
|  | CM Services | 20590.12 |  | 19904.6 |  | 685.52
|  | Reimbursables | 500 |  | 468 |  | 32
|  | Total: | 21090.12 |  | 20372.6 |  | 717.52

## #9353.00 PM TIME
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K |  |  |  | eDAS E27B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 56000 | 56000 |  |  | 56000
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 56000 | 27.28 | 27.28 | 55972.72
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 56000 | 216.9 | 244.18 | 55755.82
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 56000 | 105.97 | 350.15 | 55649.85
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 56000 | 802.4 | 1152.55 | 54847.45
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 56000 | 196.76 | 1349.31 | 54650.69
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 56000 | 1445.1 | 2794.41 | 53205.59
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 56000 | 253.43 | 3047.84 | 52952.16
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 56000 | 2781.7 | 5829.54 | 50170.46
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 56000 | 9.06 | 5838.6 | 50161.4
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 56000 | 43.7 | 5882.3 | 50117.7
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 56000 | 79.14 | 5961.44 | 50038.56
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 56000 | 818.7 | 6780.14 | 49219.86
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 56000 | 193.43 | 6973.57 | 49026.43
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 56000 | 2323.2 | 9296.77 | 46703.23
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 56000 | 218.72 | 9515.49 | 46484.51
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 56000 | 1808.3 | 11323.79 | 44676.21
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 56000 | 16.01 | 11339.8 | 44660.2
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 56000 | 200.8 | 11540.6 | 44459.4
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 56000 | 43.09 | 11583.69 | 44416.31
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 56000 | 473.1 | 12056.79 | 43943.21
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 56000 | 351.69 | 12408.48 | 43591.52
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 56000 | 1900 | 14308.48 | 41691.52
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 56000 | 167.36 | 14475.84 | 41524.16
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 56000 | 1714 | 16189.84 | 39810.16
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 56000 | 230.03 | 16419.87 | 39580.13
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 56000 | 1758.5 | 18178.37 | 37821.63
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 56000 | 84.74 | 18263.11 | 37736.89
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 56000 | 726.1 | 18989.21 | 37010.79
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 56000 | 63.84 | 19053.05 | 36946.95
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 56000 | 856.2 | 19909.25 | 36090.75
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 56000 | 226.68 | 20135.93 | 35864.07
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 56000 | 2778 | 22913.93 | 33086.07
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 56000 | 135.79 | 23049.72 | 32950.28
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 56000 | 807.7 | 23857.42 | 32142.58
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 56000 | 387.46 | 24244.88 | 31755.12
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 56000 | 3023.1 | 27267.98 | 28732.02
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 56000 | 145.67 | 27413.65 | 28586.35
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 56000 | 1000.9 | 28414.55 | 27585.45
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 56000 | 135.92 | 28550.47 | 27449.53
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 56000 | 1506 | 30056.47 | 25943.53
[5 empty] | 56000 |  | 30056.47 | 25943.53
[5 empty] | 56000 |  | 30056.47 | 25943.53
[5 empty] | 56000 |  | 30056.47 | 25943.53
|  |  | Totals: | 56000 |  | 30056.47 |  | 25943.53
Note on E9: Huggins, Joni [DAS]: PM Time Budget for 9353.00 Inbox Kleene, Jennifer Oct 31, 2023, 3:42 PM (2 days ago) to me Please create a PM Time budget for $56,000.00. Regards, Jennifer

## #9353.00 Misc
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K |  |  |  | Shipping code 175
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 82.5 | 82.5
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 55 | 137.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -137.5 | 0
PRC 33525132906 | 0509/25 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1695 | 484.33 | 484.33
GAX 33525132907 | 2025-05-09 | 9500 | CNST | GPRS V#(00003035582) | Inv. 876223 | 1100 | 1584.33
CDE 33525150900 | 2025-05-30 | 9500 | BRUM | IMCC V#(00000024400) | Inv. 9353.00-01 | 345 | 1929.33
CDE 33525150903 | 2025-05-30 | 9500 | CNST | Moving Expense to MM24 9395.00 (GPRS Inv. 876223) |  | -1100 | 829.33
CDE 33525164902 | 2025-06-13 | 9500 | BRUM | IMCC V#(00000024400) | Inv. 9353.00-01A | 621.1 | 1450.43 | Inv. 9353.00-01 Previously used, adding A
1450.43
1450.43
1450.43
1450.43
|  |  |  | Totals: |  | 1450.43

## #9353.00 KCL Engineering
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA24-9260 |  |  | RFP935300-01
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524023902 | 2023-01-23 | PO Procore | 19720 | 19720 |  |  | 19720
PRC 3352402PA3902 | 2024-03-26 | Inv. 9778 |  | 19720 | 11900 | 11900 | 7820
PRC 3352402PB3902 | 2024-04-22 | Inv. 9908 |  | 19720 | 7429 | 19329 | 391
PO 33524023902 | 2024-05-30 | CO #1 | 58000 | 77720 |  | 19329 | 58391
PRC 3352402PC3902 | 2024-06-26 | Inv. 10017 |  | 77720 | 391 | 19720 | 58000
PRC 3352402PD3902 | 2024-07-05 | Inv. 10221 |  | 77720 | 3900 | 23620 | 54100 | FY24
PO 33525023902 | 2024-08-28 | Roll to FY25 | 0 | 77720 |  | 23620 | 54100
PRC 3352502PE3902 | 2024-09-11 | Inv. 10384 |  | 77720 | 35130 | 58750 | 18970
PO 33525023902 | 2024-09-13 | CO #2 | 91520 | 169240 |  | 58750 | 110490
PRC 3352502PF3902 | 2024-10-18 | Inv. 10510 |  | 169240 | 18970 | 77720 | 91520
PRC 3352502PG3902 | 2024-10-22 | Inv. 10761 |  | 169240 | 16880 | 94600 | 74640
PRC 3352502PH3902 | 2024-11-19 | Inv. 10919 |  | 169240 | 4700 | 99300 | 69940
PRC 3352502PI3902 | 2024-12-20 | Inv. 11072 |  | 169240 | 9588 | 108888 | 60352
PRC 3352502PJ3902 | 2025-01-16 | Inv. 11170 |  | 169240 | 24632 | 133520 | 35720
PRC 3352502PK3902 | 2025-02-27 | Inv. 11380 |  | 169240 | 5260 | 138780 | 30460
PRC 3352502PL3902 | 2025-04-11 | Inv. 11680 |  | 169240 | 4600 | 143380 | 25860
PRC 3352502PM3902 | 2025-05-15 | Inv. 11964 |  | 169240 | 3656 | 147036 | 22204
|  |  |  | 169240 |  | 147036 | 22204
|  |  |  | 169240 |  | 147036 | 22204
|  | Totals: | 169240 |  | 147036 |  | 22204
|  | 50% Schematic Design | 11900 |  | 11900 |  | 0
|  | 100% Schematic Design | 7820 |  | 7820 |  | 0
|  | CO #1 | 58000 |  | 58000 |  | 0
|  | CO #2 | 91520 |  | 69316 |  | 22204
|  | Total: | 169240 |  | 147036 |  | 22204

## #9353.00 Cummins Inc
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Cummins Inc |  |  | Vendor: 00003104792
Acct. Codes-0506-335-DA24-9255 |  |  | MA-23133
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298902 | 2024-10-22 | PO Procore | 201655.37 | 201655.37 |  |  | 201655.37
PO 33525298902 | 2025-06-27 | CO #1 | 53503.33 | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  |  |  | 255158.7 |  | 0 | 255158.7
|  | Totals: | 255158.7 |  | 0 |  | 255158.7
|  | SPCL Switchgear - Special Build | 148077.69 |  |  |  | 148077.69
|  | Generator on-Board Paralleling Kit | 47161.42 |  |  |  | 47161.42
|  | Cover -HMI For Exsisting Generator Control | 1495.11 |  |  |  | 1495.11
|  | Remote Annunicator | 768.5 |  |  |  | 768.5
|  | Network Card | 846.86 |  |  |  | 846.86
|  | Performance & Payment Bond | 3305.79 |  |  |  | 3305.79
|  | CO #1 | 53503.33 |  |  |  | 53503.33
|  | Total: | 255158.7 |  | 0 |  | 255158.7

## #9353.00 Terracon Consultants
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0506-335-DA24-9255 |  |  | MA00525049
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525024906 | 2025-01-24 | DO Procore | 13775 | 13775 |  |  | 13775
PRC 3352502PA4906 | 2025-04-07 | Inv. TN65153 | -1300 | 12475 | 12475 | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  |  |  | 12475 |  | 12475 | 0
|  | Totals: | 12475 |  | 12475 |  | 0 | FINAL
|  | Construction Services Line 4 | 11580 |  | 11580 |  | 0
|  | Labor Line 5 (6hrs@$130) | 780 |  | 780 |  | 0
|  | Travel Line 7 (560 miles@ .5/mile) | 115 |  | 115 |  | 0
|  | Total: | 12475 |  | 12475 |  | 0

## #9353.00 Grainger Lighting
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Grainger Lighting |  |  | Vendor: 00002099406
Acct. Codes-0506-335-DA24-9255 |  |  | MA00525080
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525071902 | 2025-03-14 | DO Procore | 9499.76 | 9499.76 |  |  | 9499.76
PRC 3352507PA1902 | 2025-03-26 | Inv. 9439158784 |  | 9499.76 | 1545.4 | 1545.4 | 7954.36
PRC 3352507PB1902 | 2025-03-27 | Inv. 9439846685 |  | 9499.76 | 7761.92 | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  |  |  | 9499.76 |  | 9307.32 | 192.44
|  | Totals: | 9499.76 |  | 9307.32 |  | 192.44

## #9353.00 Gerad Electric
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Gerad Electric |  |  | Vendor: 00002110928
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935300-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525098904 | 2025-04-08 | PO Procore | 1522647 | 1522647 |  |  | 1522647
PRC 3352509PA8904 | 2025-06-23 | Inv. 25M001-R1 |  | 1522647 | 369999.35 | 369999.35 | 1152647.65 | 19473.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  |  |  | 1522647 |  | 369999.35 | 1152647.65
|  | Totals: | 1522647 |  | 369999.35 |  | 1152647.65

## #9353.00 Samuels Group (2)
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525133905 | 2025-05-09 | PO Procore | 316074.31 | 316074.31 |  |  | 316074.31
PRC 3352513PA3905 | 2025-06-05 | Inv. 7760.01935300 |  | 316074.31 | 15239.76 | 15239.76 | 300834.55
PO 33525133905 | 2025-06-27 | CO #1 | 2675.17 | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  |  |  | 318749.48 |  | 15239.76 | 303509.72
|  | Totals: | 318749.48 |  | 15239.76 |  | 303509.72
|  | CM Services | 216100.71 |  | 9273.26 |  | 206827.45
|  | Reimbursables | 22000 |  | 526.5 |  | 21473.5
|  | Fees | 77973.6 |  | 5440 |  | 72533.6
|  | CO #1 | 2675.17 |  |  |  | 2675.17
|  | Total: | 318749.48 |  | 15239.76 |  | 303509.72

## #9353.00 Nelson Electric
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Nelson Electric |  |  | Vendor: 00002109823
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935300-01
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525133908 | 2025-05-12 | PO Procore | 36825 | 36825 |  |  | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  |  |  | 36825 |  | 0 | 36825
|  | Totals: | 36825 |  | 0 |  | 36825

## #9353.00 Graybar - Electrical
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Graybar - Electrical |  |  | Vendor: 00002089641
Acct. Codes-0506-335-DA24-9255 |  |  | MA00518182B
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525136903 | 2025-05-15 | DO Procore | 71.18 | 71.18 |  |  | 71.18
PRC 3352513PA6903 | 2025-06-13 | Inv. 9342126814 |  | 71.18 | 71.18 | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  |  |  | 71.18 |  | 71.18 | 0
|  | Totals: | 71.18 |  | 71.18 |  | 0 | FINAL

## #9353.00 Grainger-Conduit&Wire
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Grainger - Conduit & Wire |  |  | Vendor: 00002099406
Acct. Codes-0506-335-DA24-9255 |  |  | MA00525080
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525136904 | 2025-05-15 | DO Procore | 11164.1 | 11164.1 |  |  | 11164.1
PRC 3352513PA6904 | 2025-06-13 | Inv. 9511564339, 9511830037, 9512090045,9512090060 |  | 11164.1 | 5663.28 | 5663.28 | 5500.82
PRC 3352513PB6904 | 2025-06-13 | Inv. 9523840487, 9514213520, 9513325895 |  | 11164.1 | 1196.74 | 6860.02 | 4304.08
DO 33525136904 | 2025-06-16 | Closing DO per PM | -4304.08 | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  |  |  | 6860.02 |  | 6860.02 | 0
|  | Totals: | 6860.02 |  | 6860.02 |  | 0

## #9353.00 Graybar-Electrical(2)
DOC IMCC Electrical Service Upgrades
Project # 9353.00
Program code 935300 |  |  | Major Program 4E01
Graybar - Electrical (2) |  |  | Vendor: 00002089641
Acct. Codes-0506-335-DA24-9255 |  |  | MA00518182B
Project Manager - Jennifer K |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525169905 | 2025-06-18 | DO Procore | 3394.83 | 3394.83 |  |  | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  |  |  | 3394.83 |  | 0 | 3394.83
|  | Totals: | 3394.83 |  | 0 |  | 3394.83

## RECAP #9355.00
DVA IVH Courtyard Sun Shades
Project # 9355.00
| Program code 935500 |  |  | Major Program 4E03
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 144953.31
C | DCI Group |  | 6965.72 | 6965.72 | 0
C | PM TIME |  | 8059.93 | 8059.93 | 0
C | Misc. |  | 339.49 | 339.49 | 0
C | Shive Hattery |  | 13360 | 13360 | 0
C | Henley Group |  | 100200 | 100200 | 0
C | DCI Group |  | 12228.17 | 12228.17 | 0
C | Sabus Concrete |  | 3800 | 3800 | 0
| Total Project Cost | 144953.31 | 144953.31 | 144953.31 | 0 | 0
Closed 05/28/25

## #9355.00 Funds Rec'd
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524206101 | 2023-07-25 | 175000 | 175000
|  |  | Closing project/returning funds | IET 33525148903 | 2025-05-28 | -30046.69 | -30046.69
| Total Requested | 0 | Total Transferred |  |  | 144953.31 | 144953.31

## #9355.00 DCI Group
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524235801 | 2023-08-23 | PO Procore | 6969.92 | 6969.92 |  |  | 6969.92
PRC 3352423PA5801 | 2023-11-16 | Inv. 23-035 PC-01 |  | 6969.92 | 2975.01 | 2975.01 | 3994.91
PRC 3352423PB5801 | 2023-12-19 | Inv. 23-035 PC-02 |  | 6969.92 | 793.4 | 3768.41 | 3201.51
PRC 3352423PC5801 | 2024-01-24 | Inv. 23-035 PC-03 |  | 6969.92 | 1493.24 | 5261.65 | 1708.27
PRC 3352423PD5801 | 2024-03-05 | Inv. 23-035 PC 04 FINAL | -4.2 | 6965.72 | 1704.07 | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  |  |  | 6965.72 |  | 6965.72 | -1.8208e-13
|  | Totals: | 6965.72 |  | 6965.72 |  | 0 | FINAL
|  | Construction Management Staff Hours | 6815.72 |  | 6815.72 |  | 0
|  | Reimbursable Expenses | 150 |  | 150 |  | 0
|  | Total: | 6965.72 |  | 6965.72 |  | 0

## #9355.00 PM TIME
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  |  | Major Program 4E03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E27C
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8059.93 | 8059.93 |  |  | 8059.93
IET DAS202401115300001 | 2023-08-07 | 2507 | Finance Support for July 1-31, 2023 |  | 8059.93 | 30.75 | 30.75 | 8029.18
IET DAS202401115300001 | 2023-08-07 | 9500 | DAS Services for July 1-31, 2023 |  | 8059.93 | 195.9 | 226.65 | 7833.28
IET DAS202402115300001 | 2023-09-07 | 2507 | Finance Support for August 1-31, 2023 |  | 8059.93 | 110.38 | 337.03 | 7722.9
IET DAS202402115300001 | 2023-09-07 | 9500 | DAS Services for August 1-31, 2023 |  | 8059.93 | 616.5 | 953.53 | 7106.4
IET DAS202403115300001 | 2023-10-08 | 2507 | Finance Support for September 1-30, 2023 |  | 8059.93 | 114.38 | 1067.91 | 6992.02
IET DAS202403115300001 | 2023-10-08 | 9500 | DAS Services for September 1-30, 2023 |  | 8059.93 | 796.9 | 1864.81 | 6195.12
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 8059.93 | 51.77 | 1916.58 | 6143.35
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8059.93 | 414.7 | 2331.28 | 5728.65
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 8059.93 | 93.86 | 2425.14 | 5634.79
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 8059.93 | 710.7 | 3135.84 | 4924.09
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 8059.93 | 79.4 | 3215.24 | 4844.69
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 8059.93 | 582 | 3797.24 | 4262.69
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 8059.93 | 89.84 | 3887.08 | 4172.85
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 8059.93 | 790.5 | 4677.58 | 3382.35
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 8059.93 | 98.48 | 4776.06 | 3283.87
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 8059.93 | 496.3 | 5272.36 | 2787.57
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 8059.93 | 31.43 | 5303.79 | 2756.14
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 8059.93 | 240.7 | 5544.49 | 2515.44
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 8059.93 | 23.71 | 5568.2 | 2491.73
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 8059.93 | 215.3 | 5783.5 | 2276.43
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8059.93 | 79.84 | 5863.34 | 2196.59
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8059.93 | 667.5 | 6530.84 | 1529.09
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8059.93 | 25.75 | 6556.59 | 1503.34
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8059.93 | 233.7 | 6790.29 | 1269.64
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 8059.93 | 20.98 | 6811.27 | 1248.66
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 8059.93 | 233 | 7044.27 | 1015.66
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8059.93 | 25.49 | 7069.76 | 990.17
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8059.93 | 130.5 | 7200.26 | 859.67
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8059.93 | 34.52 | 7234.78 | 825.15
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8059.93 | 307.1 | 7541.88 | 518.05
IET DAS202504115300001 | 2024-11-07 | 2507 | DAS Services for October 1-31,2024 |  | 8059.93 | 1 | 7542.88 | 517.05
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 8059.93 | 15.61 | 7558.49 | 501.44
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 8059.93 | 167.8 | 7726.29 | 333.64
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 8059.93 | 42.74 | 7769.03 | 290.9
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 8059.93 | 290.9 | 8059.93 | 0
[5 empty] | 8059.93 |  | 8059.93 | 0
|  |  | Totals: | 8059.93 |  | 8059.93 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: MOU & Proof of Check attached-Project 9355.00 Inbox Tonyan, Brad 10:37 AM (3 minutes ago) to me Finance, Please set up PM time for project 9355.00 under DA24 at $6,500. Thank you, Re: PM Time Inbox Tonyan, Brad 9:24 AM (12 minutes ago) to me John, For project 9355.00 please higher the overall PM time budget to $1,000 to a new overall budget of $7,5000 on this project. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov Re: April PM Time $Joni Tonyan, Brad 2:40 PM (6 minutes ago) to me, Joni Finance, Please raise the following projects PM time budgets: DA24 9355.00 60.93 DA24 9362.00 173.39 (This one is not my project but is James Trower) DA24 9412.00 365.13 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9355.00 Misc
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  |  | Major Program 4E03
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 27.5 | 27.5
PRC 33524031901 | 2024-01-31 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV036731 | 339.49 | 366.99
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 385 | 751.99
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -412.5 | 339.49
339.49
339.49
339.49
339.49
339.49
339.49
339.49
339.49
|  |  |  | Totals: |  | 339.49

## #9355.00 Shive Hattery
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524256800 | 2023-09-13 | PO Procore | 10460 | 10460 |  |  | 10460
PRC 3352425PA6800 | 2023-09-28 | Inv. 214234860-1 |  | 10460 | 1141.5 | 1141.5 | 9318.5
PRC 3352425PB6800 | 2023-11-09 | Inv. 2142304860-2 |  | 10460 | 2663.5 | 3805 | 6655
PRC 3352425PC6800 | 2023-12-18 | Inv. 2142304860-3 |  | 10460 | 3044 | 6849 | 3611
PRC 3352425PD6800 | 2024-02-08 | Inv. 2142304860-4 |  | 10460 | 1001 | 7850 | 2610
PRC 3352425PE6800 | 2024-03-18 | Inv. 2142304860-5 |  | 10460 | 313.2 | 8163.2 | 2296.8
PRC 3352425PF6800 | 2024-07-08 | Inv. 2142304860-6 |  | 10460 | 1853.1 | 10016.3 | 443.7 | FY24
PO 33525256800 | 2024-08-16 | Roll to FY25 | 0 | 10460 |  | 10016.3 | 443.7
PO 33525256800 | 2024-09-09 | CO #1 | 2900 | 13360 |  | 10016.3 | 3343.7
PRC 3352525PG6800 | 2024-09-19 | Inv. 2142304860-7 |  | 13360 | 3134.9 | 13151.2 | 208.8
PRC 3352525PH6800 | 2025-05-21 | Inv. 2142304860-8FINAL |  | 13360 | 208.8 | 13360 | 0
|  |  |  | 13360 |  | 13360 | 0
|  |  |  | 13360 |  | 13360 | 0
|  | Totals: | 13360 |  | 13360 |  | 0 | FINAL
|  | Sun Shade Design Services | 7610 |  | 7610 |  | 0
|  | Limited Bidding/Quoting Phase Services | 240 |  | 240 |  | 0
|  | Limited Construction Phase Services | 2610 |  | 2610 |  | 0
|  | CO #1 | 2900 |  | 2900 |  | 0
|  | Total: | 13360 |  | 13360 |  | 0

## #9355.00 Henley Group
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
Henley Group |  |  | Vendor: VS000008944
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935500-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524036900 | 2024-02-05 | PO Procore | 100200 | 100200 |  |  | 100200
PO 3352403PA6900 | 2024-06-28 | Inv. 9355.00-01 |  | 100200 | 87826.74 | 87826.74 | 12373.26 | 4622.46 | FY24
PO 33525036900 | 2024-08-16 | Roll to FY25 | 0 | 100200 |  | 87826.74 | 12373.26
PRC 3352503PB6900 | 2025-05-06 | Inv. 9355.00-02 |  | 100200 | 6394.26 | 94221 | 5979 | 4959
PRC 3352503PC6900 | 2025-05-15 | Inv. 9355.00-03 |  | 100200 | 969 | 95190 | 5010 | 5010
PRC 3352503PD6900 | 2025-05-21 | Inv. 4 - Retainage |  | 100200 | 5010 | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  |  |  | 100200 |  | 100200 | 0
|  | Totals: | 100200 |  | 100200 |  | 0 | FINAL

## #9355.00 DCI Group 2
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
DCI Group 2 |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524036901 | 2024-02-05 | PO Procore | 12581.52 | 12581.52 |  |  | 12581.52
PRC 3352403PA6901 | 2024-03-05 | Inv. 23-035 CA-01 |  | 12581.52 | 2424.35 | 2424.35 | 10157.17
PRC 3352403PB6901 | 2024-05-02 | Inv. 23-035 CA 02 |  | 12581.52 | 1293.07 | 3717.42 | 8864.1
PRC 3352403PC6901 | 2024-06-19 | Inv. 23-035 CA 03 |  | 12581.52 | 2923.16 | 6640.58 | 5940.94
PRC 3352403PD6901 | 2024-07-18 | Inv. 23-035 CA 04 |  | 12581.52 | 2510.41 | 9150.99 | 3430.53 | FY24
PO 33525036901 | 2024-08-16 | Roll to FY25 | 0 | 12581.52 |  | 9150.99 | 3430.53
PRC 3352503PE6901 | 2024-08-29 | Inv. 23-035 CA 05 |  | 12581.52 | 422.65 | 9573.64 | 3007.88
PRC 3352503PF6901 | 2024-10-02 | Inv. 23-035 CA 06 |  | 12581.52 | 1741.6 | 11315.24 | 1266.28
PRC 3352503PG6901 | 2024-12-03 | Inv. 23-035 CA 07 |  | 12581.52 | 338.12 | 11653.36 | 928.16
PRC 3352503PH6901 | 2025-05-23 | Inv. 23-035 CA 08 FINAL | -353.35 | 12228.17 | 574.81 | 12228.17 | 0
|  |  |  | 12228.17 |  | 12228.17 | 0
|  |  |  | 12228.17 |  | 12228.17 | 0
|  |  |  | 12228.17 |  | 12228.17 | 0
|  | Totals: | 12228.17 |  | 12228.17 |  | 0 | FINAL
|  | CM Staff Hours | 12075.17 |  | 12075.17 |  | 0
|  | Reimbursables | 153 |  | 153 |  | 0
|  | Total: | 12228.17 |  | 12228.17 |  | 0

## #9355.00 Sabus Concrete
DVA IVH Courtyard Sun Shades
Project # 9355.00
Program code 935500 |  |  | Major Program 4E03
Sabus Concrete |  |  | Vendor: 00003200420
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525015900 | 2025-01-15 | PO Procore | 3800 | 3800 |  |  | 3800
PRC 3352501PA5900 | 2025-04-18 | Inv. 9355.00-01 |  | 3800 | 3800 | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  |  |  | 3800 |  | 3800 | 0
|  | Totals: | 3800 |  | 3800 |  | 0 | FINAL

## RECAP #9356.00
DOE ISD Girls Dormitory Repairs
Project # 9356.00
| Program code 935600 |  |  | Major Program 4F03
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 5700000
C | Samuels Group |  | 33812.9 | 33812.9 | 0
| PM TIME |  | 225000 | 34568.44 | 190431.56
| Misc. |  | 17741.89 | 17741.89 | 0
| HGM Associates |  | 247500 | 216552.5 | 30947.5
| Andersen Construction |  | 1336107.25 | 241883.99 | 1094223.26
| Earth Services |  | 37330 | 24225 | 13105
| Oneal Electric |  | 708146.06 | 232875.7 | 475270.36
| B&K Mechanical dba Grunwald Mechanical |  | 2274127 | 692683.51 | 1581443.49
| Samuels Group (2) |  | 675845.39 | 285182.86 | 390662.53
| Total Project Cost | 5700000 | 5555610.49 | 1779526.79 | 3776083.7 | 144389.51

## #9356.00 Funds Rec'd
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 120523AJ002 | 2023-12-06 | 5700000 | 5700000
|  |  | Returning FY24 Funds to Agency | IET 33524227909 | 2024-08-14 | -5516060.83 | -5516060.83
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227909A | 2024-08-21 | -5600.88 | -5600.88
|  |  | Received FY25 Funds From Agency | IET 082924AJ009 | 2024-08-29 | 5521661.71 | 5521661.71
| Total Requested | 0 | Total Transferred |  |  | 5700000 | 5700000

## #9356.00 Samuels Group
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524005903 | 2024-01-05 | PO Procore | 33812.9 | 33812.9 |  |  | 33812.9
PRC 3352400PA5903 | 2024-03-06 | Inv. 7665.01935600 |  | 33812.9 | 3040.71 | 3040.71 | 30772.19
PRC 3352400PB5903 | 2024-04-15 | Inv. 7665.02935600 |  | 33812.9 | 1640.36 | 4681.07 | 29131.83
PRC 3352400PC5903 | 2024-05-13 | Inv. 7665.03935600 |  | 33812.9 | 1882.36 | 6563.43 | 27249.47
PRC 3352400PD5903 | 2024-06-01 | Inv. 7665.04935600 |  | 33812.9 | 1309.14 | 7872.57 | 25940.33
PRC 3352400PE5903 | 2024-07-11 | Inv. 7665.05935600 |  | 33812.9 | 3888.28 | 11760.85 | 22052.05 | FY24
PO 33525005903 | 2024-08-28 | Roll to FY25 |  | 33812.9 |  | 11760.85 | 22052.05
PRC 3352500PF5903 | 2024-08-30 | Inv. 7665.06935600 |  | 33812.9 | 8430.4 | 20191.25 | 13621.65
PRC 3352500PG5903 | 2024-09-13 | Inv. 7665.07935600 |  | 33812.9 | 4107.85 | 24299.1 | 9513.8
PRC 3352500PH5903 | 2024-10-02 | Inv. 7665.08935600 |  | 33812.9 | 2877.85 | 27176.95 | 6635.95
PRC 3352500PI5903 | 2024-11-13 | Inv. 7665.09935600 |  | 33812.9 | 5602.49 | 32779.44 | 1033.46
PRC 3352500PJ5903 | 2024-12-03 | Inv. 7665.10935600-FINAL |  | 33812.9 | 1033.46 | 33812.9 | 0
|  |  |  | 33812.9 |  | 33812.9 | 0
|  | Totals: | 33812.9 |  | 33812.9 |  | 0 | FINAL
|  | CM Services | 32812.9 |  | 32812.9 |  | 0
|  | Reimbursables | 1000 |  | 1000 |  | 0
|  | Total: | 33812.9 |  | 33812.9 |  | 0

## #9356.00 PM TIME
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E27N
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 225000 | 225000 |  |  | 225000
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 225000 | 236.91 | 236.91 | 224763.09
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 225000 | 2085.4 | 2322.31 | 222677.69
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 225000 | 331.03 | 2653.34 | 222346.66
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 225000 | 1669.1 | 4322.44 | 220677.56
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 225000 | 196.25 | 4518.69 | 220481.31
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 225000 | 1488.3 | 6006.99 | 218993.01
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 225000 | 55.64 | 6062.63 | 218937.37
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 225000 | 493.5 | 6556.13 | 218443.87
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 225000 | 308.89 | 6865.02 | 218134.98
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 225000 | 2558.9 | 9423.92 | 215576.08
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 225000 | 264.07 | 9687.99 | 215312.01
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 225000 | 2411.2 | 12099.19 | 212900.81
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 225000 | 235.14 | 12334.33 | 212665.67
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 225000 | 2565.3 | 14899.63 | 210100.37
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 225000 | 94.93 | 14994.56 | 210005.44
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 225000 | 486 | 15480.56 | 209519.44
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 225000 | 333.02 | 15813.58 | 209186.42
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 225000 | 2964 | 18777.58 | 206222.42
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 225000 | 161.32 | 18938.9 | 206061.1
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 225000 | 1084.9 | 20023.8 | 204976.2
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 225000 | 96.7 | 20120.5 | 204879.5
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 225000 | 640.3 | 20760.8 | 204239.2
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 225000 | 275.63 | 21036.43 | 203963.57
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 225000 | 2749 | 23785.43 | 201214.57
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 225000 | 255.08 | 24040.51 | 200959.49
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 225000 | 2719 | 26759.51 | 198240.49
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 225000 | 367.35 | 27126.86 | 197873.14
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 225000 | 1587.8 | 28714.66 | 196285.34
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 225000 | 119.08 | 28833.74 | 196166.26
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 225000 | 853.5 | 29687.24 | 195312.76
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 225000 | 452.46 | 30139.7 | 194860.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 225000 | 3109.1 | 33248.8 | 191751.2
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 225000 | 149.44 | 33398.24 | 191601.76
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 225000 | 1170.2 | 34568.44 | 190431.56
[5 empty] | 225000 |  | 34568.44 | 190431.56
[5 empty] | 225000 |  | 34568.44 | 190431.56
[5 empty] | 225000 |  | 34568.44 | 190431.56
[5 empty] | 225000 |  | 34568.44 | 190431.56
[5 empty] | 225000 |  | 34568.44 | 190431.56
|  |  | Totals: | 225000 |  | 34568.44 |  | 190431.56
Note on E9: Jurgenson, John [DAS]: 9356.00 - PM Time Inbox Elliott, Jennie 11:56 AM (24 minutes ago) to me Can you please set up PM time for $225,000.00 in 9356.00 DOE ISD Girls Dormitory Repairs. Thank you, Jennie Elliott

## #9356.00 Misc
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  |  | Major Program 4F03
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code B90
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524361803 | 2023-12-27 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV036082 | 57 | 57
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2024 | DAS2024071153 | 192.5 | 249.5
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 247.5 | 497
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -440 | 57
PRC 33524194901 | 2024-07-12 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2583856 | 2381.25 | 2438.25
PRC 33525318907 | 2024-11-13 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV043745 | 863.7 | 3301.95
PRC 33525318908 | 2024-11-13 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV044107 | 691.76 | 3993.71
PRC 33525339907 | 2024-12-04 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 801657 | 10568 | 14561.71
PRC 33525351908 | 2024-12-16 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2610685 | 567.5 | 15129.21
PRC 33525048905 | 2025-02-17 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2622055 | 1587.5 | 16716.71
GAX 33525090910 | 2025-03-31 | 9500 | CNST | Johnson Controls V#(00002102328) | Inv. 52777668 | 1025.18 | 17741.89
17741.89
|  |  |  | Totals: |  | 17741.89

## #9356.00 HGM Associates
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
HGM Associates |  |  | Vendor: 00002109941
Acct. Codes-0506-335-DA24-9260 |  |  | RFP935600-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524065902 | 2024-03-05 | PO Procore | 247500 | 247500 |  |  | 247500
PO 3352406PA5902 | 2024-05-15 | Inv. 105023A-1,2 |  | 247500 | 12660 | 12660 | 234840
PO 3352406PB5902 | 2024-07-03 | Inv. 105023A-3 |  | 247500 | 81960 | 94620 | 152880
PO 3352406PC5902 | 2024-07-12 | Inv. 105023A-4 |  | 247500 | 57420 | 152040 | 95460 | FY24
PO 33525065902 | 2024-08-28 | Roll to FY25 | 0 | 247500 |  | 152040 | 95460
PRC 3352506PD5902 | 2024-09-16 | Inv. 105023A-5 |  | 247500 | 10440 | 162480 | 85020
PRC 3352506PE5902 | 2024-10-22 | Inv. 105023A-6 |  | 247500 | 5220 | 167700 | 79800
PRC 3352506PF5902 | 2024-10-31 | Inv. 105023A-7 |  | 247500 | 6125 | 173825 | 73675
PRC 3352506PG5902 | 2024-11-21 | Inv. 105023A-8 |  | 247500 | 6125 | 179950 | 67550
PRC 3352506PH5902 | 2024-12-18 | Inv. 105023A-9 |  | 247500 | 6655 | 186605 | 60895
PRC 3352506PI5902 | 2025-01-27 | Inv. 105023A-10 |  | 247500 | 3327.5 | 189932.5 | 57567.5
PRC 3352506PJ5902 | 2025-02-19 | Inv. 105023A-11 |  | 247500 | 3327.5 | 193260 | 54240
PRC 3352506PK5902 | 2025-03-17 | Inv. 105023A-12 |  | 247500 | 6655 | 199915 | 47585
PRC 3352506PL5902 | 2025-04-28 | Inv. 105023A-13 |  | 247500 | 3327.5 | 203242.5 | 44257.5
PRC 3352506PM5902 | 2025-05-09 | Inv. 105023A-14 |  | 247500 | 6655 | 209897.5 | 37602.5
PRC 3352506PN5902 | 2025-06-10 | Inv. 105023A-15 |  | 247500 | 6655 | 216552.5 | 30947.5
|  |  |  | 247500 |  | 216552.5 | 30947.5
|  |  |  | 247500 |  | 216552.5 | 30947.5
|  | Totals: | 247500 |  | 216552.5 |  | 30947.5
|  | Design Development | 63300 |  | 63300 |  | 0
|  | Construction Development | 104400 |  | 104400 |  | 0
|  | Bidding Assistance | 12250 |  | 12250 |  | 0
|  | Construction Phase | 66550 |  | 36602.5 |  | 29947.5
|  | Reimbursables | 1000 |  |  |  | 1000
|  | Total: | 247500 |  | 216552.5 |  | 30947.5

## #9356.00 Andersen Construction
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
Andersen Construction |  |  | Vendor: 00003032147
Acct. Codes-0506-335-DA24-9255 |  |  | RFP935600-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525298910 | 2024-10-24 | PO Procore | 1295200 | 1295200 |  |  | 1295200
PRC 3352529PA8910 | 2025-02-11 | Inv. 9356.00-01 |  | 1295200 | 55777.67 | 55777.67 | 1239422.33 | 2935.66
PO 33525298910 | 2025-03-27 | CO #1 | 7928.55 | 1303128.55 |  | 55777.67 | 1247350.88
PRC 3352529PB8910 | 2025-04-25 | Inv. 9356.00-02 |  | 1303128.55 | 56998.47 | 112776.14 | 1190352.41 | 5935.58
PO 33525298910 | 2025-05-29 | CO #2 | 6069 | 1309197.55 |  | 112776.14 | 1196421.41
PRC 3352529PC8910 | 2025-06-13 | Inv. 9356.00-03 |  | 1309197.55 | 129107.85 | 241883.99 | 1067313.56 | 12730.73
PO 33525298910 | 2025-06-18 | CO #3 | 20090.95 | 1329288.5 |  | 241883.99 | 1087404.51
PO 33525298910 | 2025-06-30 | CO #4 | 6818.75 | 1336107.25 |  | 241883.99 | 1094223.26
|  |  |  | 1336107.25 |  | 241883.99 | 1094223.26
|  |  |  | 1336107.25 |  | 241883.99 | 1094223.26
|  |  |  | 1336107.25 |  | 241883.99 | 1094223.26
|  |  |  | 1336107.25 |  | 241883.99 | 1094223.26
|  |  |  | 1336107.25 |  | 241883.99 | 1094223.26
|  | Totals: | 1336107.25 |  | 241883.99 |  | 1094223.26

## #9356.00 Earth Services
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
Earth Services |  |  | Vendor: VS000007582
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935600-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525302901 | 2024-10-28 | PO Procore | 34995 | 34995 |  |  | 34995
PRC 3352530PA2901 | 2025-01-27 | Inv. 1 (DES-i002385) |  | 34995 | 9500 | 9500 | 25495 | 500
PRC 3352530PB2901 | 2025-04-08 | Inv. 9356.00-02 |  | 34995 | 14725 | 24225 | 10770 | 1275
PO 33525302901 | 2025-06-10 | CO #1 | 2335 | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  |  |  | 37330 |  | 24225 | 13105
|  | Totals: | 37330 |  | 24225 |  | 13105

## #9356.00 ONeal Electric
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
ONeal Electric |  |  | Vendor: 00002115025
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935600-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525302902 | 2024-10-28 | PO Procore | 651522 | 651522 |  |  | 651522
PRC 3352530PA2902 | 2025-01-27 | Inv. 10460-1 |  | 651522 | 35663 | 35663 | 615859 | 1877
PRC 3352530PB2902 | 2025-02-17 | Inv. 10460-2 |  | 651522 | 43982.15 | 79645.15 | 571876.85 | 4191.85
PO 33525302902 | 2025-02-21 | CO #1 | 5351 | 656873 |  | 79645.15 | 577227.85
PO 33525302902 | 2025-03-05 | CO #2 | 1440.32 | 658313.32 |  | 79645.15 | 578668.17
PRC 3352530PC2902 | 2025-03-21 | Inv. 10460-3 |  | 658313.32 | 85091.8 | 164736.95 | 493576.37 | 8670.37
PO 33525302902 | 2025-04-10 | CO #3 | 3179 | 661492.32 |  | 164736.95 | 496755.37
PO 33525302902 | 2025-05-20 | CO #4 | 45911.79 | 707404.11 |  | 164736.95 | 542667.16
PRC 3352530PD2902 | 2025-05-29 | Inv. 10460-4 |  | 707404.11 | 68138.75 | 232875.7 | 474528.41 | 12256.62
PO 33525302902 | 2025-06-19 | CO #5 | 741.95 | 708146.06 |  | 232875.7 | 475270.36
|  |  |  | 708146.06 |  | 232875.7 | 475270.36
|  |  |  | 708146.06 |  | 232875.7 | 475270.36
|  |  |  | 708146.06 |  | 232875.7 | 475270.36
|  | Totals: | 708146.06 |  | 232875.7 |  | 475270.36

## #9356.00 B&K Mechanical
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
B&K Mechanical |  |  | Vendor: 00003114353
Acct. Codes-0506-335-DA24-9255 |  |  | RFB935600-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525309906 | 2024-11-04 | PO Procore | 2229500 | 2229500 |  |  | 2229500
PRC 3352530PA9906 | 2025-02-17 | Inv. 6064 |  | 2229500 | 161680.86 | 161680.86 | 2067819.14 | 8509.54
PO 33525309906 | 2025-02-21 | CO #1 | 9674 | 2239174 |  | 161680.86 | 2077493.14
PRC 3352530PB9906 | 2025-04-08 | Inv. 6441 |  | 2239174 | 197866.31 | 359547.17 | 1879626.83 | 18923.58
PO 33525309906 | 2025-04-14 | CO #2 | 13468 | 2252642 |  | 359547.17 | 1893094.83
PO 33525309906 | 2025-05-16 | CO #3 | 4197 | 2256839 |  | 359547.17 | 1897291.83
PO 33525309906 | 2025-06-27 | CO #4 | 17288 | 2274127 |  | 359547.17 | 1914579.83
PRC 3352530PC9906 | 2025-06-30 | Inv.6833 |  | 2274127 | 333136.34 | 692683.51 | 1581443.49 | 36457.09
|  |  |  | 2274127 |  | 692683.51 | 1581443.49
|  |  |  | 2274127 |  | 692683.51 | 1581443.49
|  |  |  | 2274127 |  | 692683.51 | 1581443.49
|  |  |  | 2274127 |  | 692683.51 | 1581443.49
|  |  |  | 2274127 |  | 692683.51 | 1581443.49
|  | Totals: | 2274127 |  | 692683.51 |  | 1581443.49

## #9356.00 Samuels Group (2)
DOE ISD Girls Dormitory Repairs
Project # 9356.00
Program code 935600 |  |  | Major Program 4F03
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525317903 | 2024-11-12 | PO Procore | 665845.39 | 665845.39 |  |  | 665845.39
PRC 3352531PA7903 | 2024-12-06 | Inv. 7737.51935600 |  | 665845.39 | 8604.29 | 8604.29 | 657241.1
PO 33525317903 | 2025-01-14 | CO #1 | 10000 | 675845.39 |  | 8604.29 | 667241.1
PRC 3352531PB7903 | 2025-01-27 | Inv. 7737.52935600 |  | 675845.39 | 42462.4 | 51066.69 | 624778.7
PRC 3352531PC7903 | 2025-02-05 | Inv. 7737.53935600 |  | 675845.39 | 41295.08 | 92361.77 | 583483.62
PRC 3352531PD7903 | 2025-03-10 | Inv. 7737.54935600 |  | 675845.39 | 44198.34 | 136560.11 | 539285.28
PRC 3352531PE7903 | 2025-04-14 | Inv. 7737.55935600 |  | 675845.39 | 47517.53 | 184077.64 | 491767.75
PRC 3352531PF7903 | 2025-05-12 | Inv. 7737.56935600 |  | 675845.39 | 43788.76 | 227866.4 | 447978.99
PRC 3352531PG7903 | 2025-06-10 | Inv. 7737.57935600 |  | 675845.39 | 57316.46 | 285182.86 | 390662.53
|  |  |  | 675845.39 |  | 285182.86 | 390662.53
|  |  |  | 675845.39 |  | 285182.86 | 390662.53
|  |  |  | 675845.39 |  | 285182.86 | 390662.53
|  |  |  | 675845.39 |  | 285182.86 | 390662.53
|  | Totals: | 675845.39 |  | 285182.86 |  | 390662.53
|  | CM Services | 426758.88 |  | 184089.2 |  | 242669.68
|  | Temp Partitions/Fence | 14000 |  | 9183.34 |  | 4816.66
|  | Dumpsters, GPR | 14500 |  | 9068.5 |  | 5431.5
|  | Commissioning | 38250 |  | 15300 |  | 22950
|  | Miles, Hotels,Meals | 46000 |  | 14799.62 |  | 31200.38
|  | Fee | 126336.51 |  | 50633.65 |  | 75702.86
|  | CO #1 | 10000 |  | 2108.55 |  | 7891.45
|  | Total: | 675845.39 |  | 285182.86 |  | 390662.53

## RECAP #9358.00
ICN CC Lucas CRAC Replacement
Project # 9358.00
| Program code 935800 |  |  | Major Program 4F02
Recap
Acct. Codes-0506-335-DA24
Project Manager -Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 78748.74
C | DCI Group |  | 14204.32 | 14204.32 | 0
C | PM TIME |  | 12334.12 | 12334.12 | 0
| Misc. |  | 2266.92 | 2266.92 | 0
| System Works LLC |  | 11745 | 1350 | 10395
| KCL Engineering |  | 38090 | 35177 | 2913
| Total Project Cost | 78748.74 | 78640.36 | 65332.36 | 13308 | 108.38

## #9358.00 Funds Rec'd
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  | Major Program 4F02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager -Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 336DAS9358 | 2023-11-09 | 578412 | 578412
|  |  | Returning Funds to Agency | IET 33524208902 | 2024-07-26 | -499663.26 | -499663.26
|  |  | Returning FY24 Funds to Agency | IET 33524227908 | 2024-08-14 | -22873.1 | -22873.1
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227908A | 2024-08-14 | -2536.2 | -2536.2
|  |  | Received FY25 Funds from Agency | IET 25EH022456 | 2024-09-06 | 25409.3 | 25409.3
| Total Requested | 0 | Total Transferred |  |  | 78748.74 | 78748.74

## #9358.00 DCI Group
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  | Major Program 4F02
DCI Group |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager -Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524318800 | 2023-11-14 | PO Procore | 18075.8 | 18075.8 |  |  | 18075.8
PRC 3352431PA8800 | 2023-12-21 | Inv. 23-049 PC-01 |  | 18075.8 | 3342.89 | 3342.89 | 14732.91
PRC 3352431PB8800 | 2024-01-24 | Inv. 23-049 PC-02 |  | 18075.8 | 2953.44 | 6296.33 | 11779.47
PRC 3352431PC8800 | 2024-03-05 | Inv. 23-049 PC 03 |  | 18075.8 | 3637.55 | 9933.88 | 8141.92
PRC 3352431PD8800 | 2024-05-02 | Inv. 23-049 PC 04 |  | 18075.8 | 3180.05 | 13113.93 | 4961.87
PO 33524318800 | 2024-06-21 | CO #1 | -3827.76 | 14248.04 |  | 13113.93 | 1134.11
PRC 3352431PE8800 | 2024-06-25 | Inv. 23-049 PC 05 |  | 14248.04 | 46.25 | 13160.18 | 1087.86
PRC 3352431PF8800 | 2024-07-19 | Inv. 23-049 PC 06 Final | -43.72 | 14204.32 | 1044.14 | 14204.32 | -1.3358e-12
|  |  |  | 14204.32 |  | 14204.32 | -1.3358e-12
|  |  |  | 14204.32 |  | 14204.32 | -1.3358e-12
|  |  |  | 14204.32 |  | 14204.32 | -1.3358e-12
|  |  |  | 14204.32 |  | 14204.32 | -1.3358e-12
|  |  |  | 14204.32 |  | 14204.32 | -1.3358e-12
|  | Totals: | 14204.32 |  | 14204.32 |  | 0 | FINAL

## #9358.00 PM TIME
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  |  | Major Program 4F02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager -Jennifer K. |  |  |  | eDAS E29S
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 12334.12 | 12334.12 |  |  | 12334.12
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 12334.12 | 105.97 | 105.97 | 12228.15
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 12334.12 | 802.4 | 908.37 | 11425.75
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 12334.12 | 82.88 | 991.25 | 11342.87
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 12334.12 | 606.1 | 1597.35 | 10736.77
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 12334.12 | 82.22 | 1679.57 | 10654.55
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 12334.12 | 726.6 | 2406.17 | 9927.95
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 12334.12 | 87.05 | 2493.22 | 9840.9
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12334.12 | 440.6 | 2933.82 | 9400.3
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12334.12 | 54.65 | 2988.47 | 9345.65
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12334.12 | 414.8 | 3403.27 | 8930.85
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 12334.12 | 71.39 | 3474.66 | 8859.46
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 12334.12 | 633.4 | 4108.06 | 8226.06
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 12334.12 | 152.84 | 4260.9 | 8073.22
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12334.12 | 1265.8 | 5526.7 | 6807.42
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 12334.12 | 159.1 | 5685.8 | 6648.32
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12334.12 | 1452.4 | 7138.2 | 5195.92
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 12334.12 | 106.3 | 7244.5 | 5089.62
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12334.12 | 1161.8 | 8406.3 | 3927.82
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12334.12 | 199.71 | 8606.01 | 3728.11
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12334.12 | 1015.7 | 9621.71 | 2712.41
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12334.12 | 24.51 | 9646.22 | 2687.9
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12334.12 | 221.3 | 9867.52 | 2466.6
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12334.12 | 26 | 9893.52 | 2440.6
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12334.12 | 176.8 | 10070.32 | 2263.8
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12334.12 | 9.7 | 10080.02 | 2254.1
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12334.12 | 62.3 | 10142.32 | 2191.8
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12334.12 | 45.98 | 10188.3 | 2145.82
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12334.12 | 454.9 | 10643.2 | 1690.92
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12334.12 | 27.71 | 10670.91 | 1663.21
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12334.12 | 291.9 | 10962.81 | 1371.31
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12334.12 | 156.57 | 11119.38 | 1214.74
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12334.12 | 677.3 | 11796.68 | 537.44
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 12334.12 | 65.94 | 11862.62 | 471.5
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 12334.12 | 471.5 | 12334.12 | 2.7853e-12
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 12334.12 | 70.02 | 12404.14 | -70.02
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 12334.12 | 480.8 | 12884.94 | -550.82
CDE 33525132908 | 2025-05-12 | 2507 | Moving PM Time to 9358.01 DA25 |  | 12334.12 | -70.02 | 12814.92 | -480.8
CDE 33525132908 | 2025-05-12 | 9500 | Moving PM Time to 9358.01 DA25 |  | 12334.12 | -480.8 | 12334.12 | 2.7853e-12
[5 empty] | 12334.12 |  | 12334.12 | 2.7853e-12
|  |  | Totals: | 12334.12 |  | 12334.12 |  | 0
Note on E9: Jurgenson, John [DAS]: PM Time Budget for DA24 9358.00 Inbox Kleene, Jennifer 4:07 PM (0 minutes ago) to me Please create a PM Time budget of $12,442.50 for DA24 9358.00. Regards, Jennifer Re: April PM Time $Joni Kleene, Jennifer 1:22 PM (19 minutes ago) to me, Oliver Please increase the budget for MM22 9180.01 by $5.20. Please apply the $442.44 in PM time to DA25 9358.01 instead of DA24 9358.00 and remove DA24 9358.00 from the billables as all future PM time will go to DA25 9358.01. Regards, Jennifer Jennifer Kleene

## #9358.00 Misc
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  |  | Major Program 4F02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager -Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 192.5 | 192.5
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 192.5 | 385
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 82.5 | 467.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -467.5 | 0
PRC 33524179901 | 2024-06-27 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2580475 | 1951.25 | 1951.25
PRC 33524207910 | 2024-07-25 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL805 | 315.67 | 2266.92
2266.92
2266.92
2266.92
2266.92
2266.92
2266.92
|  |  |  | Totals: |  | 2266.92

## #9358.00 System Works LLC
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  | Major Program 4F02
System Works LLC |  |  | Vendor:00002144353
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager -Jennifer K. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524005808 | 2024-01-05 | PO Procore | 11745 | 11745 |  |  | 11745
PRC 3352400PA5808 | 2024-07-05 | Inv. 11874 |  | 11745 | 1350 | 1350 | 10395 | FY24
PO 33525005808 | 2024-08-28 | Roll to FY25 | 0 | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  |  |  | 11745 |  | 1350 | 10395
|  | Totals: | 11745 |  | 1350 |  | 10395

## #9358.00 KCL Engineering
ICN CC Lucas CRAC Replacement
Project # 9358.00
Program code 935800 |  |  | Major Program 4F02
KCL Engineering |  |  | Vendor:00002103747
Acct. Codes-0506-335-DA24-9260 |  |  | RFP935800-01
Project Manager -Jennifer K. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524016901 | 2024-01-12 | PO Procore | 36170 | 36170 |  |  | 36170
PRC 3352401PA6901 | 2024-04-18 | Inv. 9659 |  | 36170 | 13870 | 13870 | 22300
PO 33524016901 | 2024-05-21 | CO #1 | 1920 | 38090 |  | 13870 | 24220
PRC 3352401PB6901 | 2024-05-29 | Inv. 10060 |  | 38090 | 10910 | 24780 | 13310
PRC 3352401PC6901 | 2024-07-03 | Inv. 10219 |  | 38090 | 3600 | 28380 | 9710 | FY24
PO 33525016901 | 2024-08-28 | Roll to FY25 | 0 | 38090 |  | 28380 | 9710
PRC 3352501PD6901 | 2024-09-06 | Inv. 10420 |  | 38090 | 971 | 29351 | 8739
PRC 3352501PE6901 | 2024-09-16 | Inv. 10587 |  | 38090 | 971 | 30322 | 7768
PRC 3352501PF6901 | 2024-10-15 | Inv. 10740 |  | 38090 | 971 | 31293 | 6797
PRC 3352501PG6901 | 2024-12-16 | Inv. 10853 |  | 38090 | 971 | 32264 | 5826
PRC 3352501PH6901 | 2025-04-14 | Inv. 11032 |  | 38090 | 971 | 33235 | 4855
PRC 3352501PI6901 | 2025-04-21 | Inv. 11734 |  | 38090 | 1942 | 35177 | 2913
|  |  |  | 38090 |  | 35177 | 2913
|  | Totals: | 38090 |  | 35177 |  | 2913
|  | 50% Construction Documents | 13870 |  | 13870 |  | 0
|  | 100% Construction Documents | 10910 |  | 10910 |  | 0
|  | Bidding or Neogotiation | 1680 |  | 1680 |  | 0
|  | Construction Phase | 9710 |  | 6797 |  | 2913
|  | CO #1 | 1920 |  | 1920 |  | 0
|  | Total: | 38090 |  | 35177 |  | 2913

## RECAP #9360.00
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
| Program code 936000 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 43183.8
C | McGough Construction |  | 12880.01 | 12880.01 | 0
C | PM TIME |  | 8009.54 | 8009.54 | 0
C | Misc. |  | 2364.25 | 2364.25 | 0
C | KCL Engineering |  | 19930 | 19930 | 0
| Total Project Cost | 43183.8 | 43183.8 | 43183.8 | 0 | 0
Closed 08/15/2024

## #9360.00 Funds Rec'd
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
Program code 936000 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU funds Received | IET 10062300051 | 2023-10-09 | 200000 | 200000
|  |  | Returning FY24 Funds to Agency | IET 33524228906 | 2024-08-15 | -156816.2 | -156816.2
| Total Requested | 0 | Total Transferred |  |  | 43183.8 | 43183.8
WHEN RETURNING FUNDS, PLEASE SEE & ATTACH EMAIL BELOW

## #9360.00 McGough
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
Program code 936000 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor:00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524283800 | 2023-10-10 | PO Procore | 8723.6 | 8723.6 |  |  | 8723.6
PRC 3352428PA3800 | 2023-11-14 | Inv. 101031.006-01 |  | 8723.6 | 821.24 | 821.24 | 7902.36
PRC 3352428PB3800 | 2023-12-12 | Inv. 101031.006-02 |  | 8723.6 | 931.85 | 1753.09 | 6970.51
PRC 3352428PC3800 | 2024-01-12 | Inv. 101031.006-03 |  | 8723.6 | 1526.99 | 3280.08 | 5443.52
PRC 3352428PD3800 | 2024-02-08 | Inv. 101031.006-04 |  | 8723.6 | 1823.52 | 5103.6 | 3620
PRC 3352428PE3800 | 2024-03-18 | Inv. 101031.006-PC05 |  | 8723.6 | 1856.41 | 6960.01 | 1763.59
PO 33524283800 | 2024-03-22 | CO #1 | 2705.01 | 11428.61 |  | 6960.01 | 4468.6
PRC 3352428PF3800 | 2024-04-08 | Inv. 101031.006-PC06 |  | 11428.61 | 1288.8 | 8248.81 | 3179.8
PRC 3352428PG3800 | 2024-05-08 | Inv. 101031.006-PC07 |  | 11428.61 | 684.11 | 8932.92 | 2495.69
PRC 3352428PH3800 | 2024-06-12 | Inv. 101031.006-PC08 |  | 11428.61 | 1985.08 | 10918 | 510.61
PO 33524283800 | 2024-06-26 | CO#2 | 2357.82 | 13786.43 |  | 10918 | 2868.43
PRC 3352428PI3800 | 2024-07-08 | Inv. 101031.006-PC09 |  | 13786.43 | 1962.01 | 12880.01 | 906.42
PO 33524283800 | 2024-08-15 | Moved to DA25 | -906.42 | 12880.01 |  | 12880.01 | 0
|  |  |  | 12880.01 |  | 12880.01 | 0
|  |  |  | 12880.01 |  | 12880.01 | 0
|  | Totals: | 12880.01 |  | 12880.01 |  | 0
|  | CM Services | 8573.6 |  | 8573.6 |  | 0
|  | Reimbursables | 98 |  | 98 |  | 0
|  | CO #1 | 2675.01 |  | 2675.01 |  | 0
|  | CO #2 | 1533.4 |  | 1533.4 |  | 0
|  | Total: | 12880.01 |  | 12880.01 |  | 0
|  | DA25 | 696.29 |  | 696.29 |  | 0
|  | Total Contract | 13576.3 |  | 13576.3 |  | 0

## #9360.00 PM TIME
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
Program code 936000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A. |  |  |  | eDAS E29W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8009.54 | 8009.54 |  |  | 8009.54
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 8009.54 | 522.5 | 522.5 | 7487.04
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 8009.54 | 241.61 | 764.11 | 7245.43
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 8009.54 | 1992.5 | 2756.61 | 5252.93
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 8009.54 | 220.83 | 2977.44 | 5032.1
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 8009.54 | 1814.6 | 4792.04 | 3217.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 8009.54 | 1182.5 | 5974.54 | 2035
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 8009.54 | 660 | 6634.54 | 1375
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 8009.54 | 357.5 | 6992.04 | 1017.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 8009.54 | 165 | 7157.04 | 852.5
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8009.54 | 550 | 7707.04 | 302.5
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8009.54 | 302.5 | 8009.54 | 0
[5 empty] | 8009.54 |  | 8009.54 | 0
|  |  | Totals: | 8009.54 |  | 8009.54 |  | 0
Note on E9: Jurgenson, John [DAS]: 9360.00 IPBS JOH 6450 Fire Alarm Replacement Inbox Adams, Brandon 10:03 AM (3 hours ago) to me Finance, Please set my PM budget to $4000.00 for 9360.00. Thanks, Re: PM TIme $John Adams, Brandon 1:37 PM (16 minutes ago) to me Please increase, MM22 9302.00 - $6,000 DA24 9360.00 - $4,000 Regards, Brandon Adams Re: PM Time Postings Inbox Adams, Brandon 9:58 AM (1 minute ago) to me Finance, Please increase my PM time by $1000.00 for DA24 9360.00. Regards, Brandon Adams Adams, Brandon 9:18 AM (7 minutes ago) to me Finance, Please set my PM budget to $5000 for DA25 9360.00-.01. Please close my PM time for DA24 9360.00 all time for July will go to 9360.00-.01 Please change DA25 9360.00-.01 to not charge admin time. Regards, Brandon Adams Owner's Representative, State Design & Construction Resources

## #9360.00 Misc
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
Program code 936000 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 412.5 | 412.5
GAX 33524050909 | 2024-02-19 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2555639 | 1902.5 | 2315
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 220 | 2535
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 137.5 | 2672.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -770 | 1902.5
PRC 33524164900 | 2024-06-12 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL454 | 216.5 | 2119
PRC 33524208910 | 2024-07-26 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL804 | 245.25 | 2364.25
2364.25
2364.25
2364.25
2364.25
2364.25
|  |  |  | Totals: |  | 2364.25

## #9360.00 KCL Engineering
DOE IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.00
Program code 936000 |  |  | Major Program 4E02
KCL Engineering |  |  | Vendor:00002103747
Acct. Codes-0506-335-DA24-9260 |  |  | RFP936000-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524334912 | 2023-11-30 | PO Procore | 25815 | 25815 |  |  | 25815
PRC 3352433PA4912 | 2024-01-04 | Inv. 9445 |  | 25815 | 11495 | 11495 | 14320
PRC 3352433PB4912 | 2024-01-22 | Inv. 9527 |  | 25815 | 3600 | 15095 | 10720
PRC 3352433PC4912 | 2024-02-12 | Inv. 9579 |  | 25815 | 3695 | 18790 | 7025
PRC 3352433PD4912 | 2024-03-18 | Inv. 9727 |  | 25815 | 1140 | 19930 | 5885
PO 33524334912 | 2024-08-15 | Moved to DA25 | -5885 | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  |  |  | 19930 |  | 19930 | 0
|  | Totals: | 19930 |  | 19930 |  | 0
|  | Design Development | 11495 |  | 11495 |  | 0
|  | Construction Documents | 7295 |  | 7295 |  | 0
|  | Bid/Negotiation | 1140 |  | 1140 |  | 0
|  | Construction Phase | 0 |  |  |  | 0
|  | Total: | 19930 |  | 19930 |  | 0

## RECAP #9362.00
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
| Program code 936200 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 361655.16
C | DCI Group #23-045 PC |  | 15372.93 | 15372.93 | 0
C | PM TIME |  | 15173.39 | 15173.39 | 0
C | Misc. |  | 8202.92 | 8202.92 | 0
C | Shive Hattery |  | 14000 | 14000 | 0
C | System Works LLC |  | 13990 | 13990 | 0
C | The Baker Group |  | 292553.63 | 292553.63 | 0
C | Van Maanen Electric |  | 2362.29 | 2362.29 | 0
| Total Project Cost | 361655.16 | 361655.16 | 361655.16 | 0 | 0
Closing 05/29/25

## #9362.00 Funds Rec'd
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CDR 00524292101 | 2023-10-19 | 300000 | 300000
|  |  | MOU Amend 1 | IET 23812Y24007 | 2024-02-07 | 81500 | 81500
|  |  | Reimbursement from DOC for Beeline & Blue Invoices | IET 23812V24009 | 2024-04-19 | 25.75 | 25.75
|  |  | Reimbursement from DOC for Beeline & Blue Invoices | CDE 23812V24012 | 2024-06-17 | 25.75 | 25.75
|  |  | Returning FY24 Funds to Agency | IET 33524227910 | 2024-08-14 | -334806.29 | -334806.29
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227910A | 2024-08-21 | -255.02 | -255.02
|  |  | Received FY25 Funds From Agency | IET 23812Y25003 | 2024-09-10 | 335061.31 | 335061.31
|  |  | Closing Project-Returning Funds to Agency | IET 33525149901 | 2025-05-29 | -19896.34 | -19896.34
| Total Requested | 0 | Total Transferred |  |  | 361655.16 | 361655.16

## #9362.00 DCI Group
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
DCI Group #23-045 PC |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524293801 | 2023-10-20 | PO Procore | 15452.93 | 15452.93 |  |  | 15452.93
PRC 3352429PA3801 | 2023-12-19 | Inv. 23-045 PC-01 |  | 15452.93 | 3078.06 | 3078.06 | 12374.87
PRC 3352429PB3801 | 2024-01-24 | Inv. 23-045 PC-02 |  | 15452.93 | 2754.63 | 5832.69 | 9620.24
PRC 3352429PC3801 | 2024-03-05 | Inv. 23-045 PC 3 |  | 15452.93 | 7296.15 | 13128.84 | 2324.09
PRC 3352429PD3801 | 2024-05-02 | Inv. 23-045 PC 4 FINAL | -80 | 15372.93 | 2244.09 | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  |  |  | 15372.93 |  | 15372.93 | 1.819e-12
|  | Totals: | 15372.93 |  | 15372.93 |  | 0 | FINAL
|  | CM Services | 15252.93 |  | 15252.93 |  | 0
|  | Reimbursables | 120 |  | 120 |  | 0
|  | Total: | 15372.93 |  | 15372.93 |  | 0

## #9362.00 PM TIME
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2A7
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15173.39 | 15173.39 |  |  | 15173.39
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 15173.39 | 32.7 | 32.7 | 15140.69
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 15173.39 | 259.5 | 292.2 | 14881.19
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 15173.39 | 109.02 | 401.22 | 14772.17
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 15173.39 | 820.4 | 1221.62 | 13951.77
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 15173.39 | 119.31 | 1340.93 | 13832.46
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 15173.39 | 873 | 2213.93 | 12959.46
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 15173.39 | 68.74 | 2282.67 | 12890.72
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 15173.39 | 605.4 | 2888.07 | 12285.32
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 15173.39 | 187.49 | 3075.56 | 12097.83
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 15173.39 | 947.3 | 4022.86 | 11150.53
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 15173.39 | 58.56 | 4081.42 | 11091.97
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 15173.39 | 442.6 | 4524.02 | 10649.37
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 15173.39 | 62.75 | 4586.77 | 10586.62
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 15173.39 | 558.5 | 5145.27 | 10028.12
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 15173.39 | 104.4 | 5249.67 | 9923.72
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 15173.39 | 872.3 | 6121.97 | 9051.42
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 15173.39 | 31.17 | 6153.14 | 9020.25
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 15173.39 | 281.2 | 6434.34 | 8739.05
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 15173.39 | 10.71 | 6445.05 | 8728.34
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 15173.39 | 116.8 | 6561.85 | 8611.54
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 15173.39 | 76.9 | 6638.75 | 8534.64
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 15173.39 | 391 | 7029.75 | 8143.64
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 15173.39 | 113.54 | 7143.29 | 8030.1
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 15173.39 | 1010.4 | 8153.69 | 7019.7
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 15173.39 | 217.39 | 8371.08 | 6802.31
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 15173.39 | 1453.5 | 9824.58 | 5348.81
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15173.39 | 210.25 | 10034.83 | 5138.56
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15173.39 | 1394.8 | 11429.63 | 3743.76
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15173.39 | 135.71 | 11565.34 | 3608.05
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15173.39 | 1356.1 | 12921.44 | 2251.95
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 15173.39 | 59.2 | 12980.64 | 2192.75
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 15173.39 | 631.9 | 13612.54 | 1560.85
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 15173.39 | 130.32 | 13742.86 | 1430.53
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 15173.39 | 562.6 | 14305.46 | 867.93
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 15173.39 | 39.93 | 14345.39 | 828
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 15173.39 | 285.4 | 14630.79 | 542.6
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 15173.39 | 68.9 | 14699.69 | 473.7
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 15173.39 | 473.7 | 15173.39 | 3.2401e-12
[5 empty] | 15173.39 |  | 15173.39 | 3.2401e-12
|  |  | Totals: | 15173.39 |  | 15173.39 |  | 0
Note on E9: Jurgenson, John [DAS]: PM Time/Project Budget Adjustments $John Tonyan, Brad 2:05 PM (50 minutes ago) to me, Scott, Brad Finance, Please make the following changes: DA21 - 9211.00 - Please close PM time and shift remaining funds ($437.95) to the general fund on this project. MM22 - 9245.00 - Please increase PM time by $4k and reduce budget on project by $30K MM22 - 9272.00 - Please increase PM time by $3K and reduce budget on project by $25K MM22 - 9291.00 - Please increase PM time by $3k and reduce budget on project by $35K Totals back to MM22 - $90K MM23 - 9255.00 - Please increase PM time by $2K and reduce budget on project by $20K MM23 - 9324.00 - Please increase PM time by $2k and reduce budget on project by $20K MM23 - 9330.00 - Please increase PM time by $2k and reduce budget on project by $30K Totals back to MM23 - $70K DA22 - 9282.00 - Please increase PM time by $2K MM24 - 9282.00 - Please setup PM time budget of $45K MM24 - 9282.00 - Please reduce overall budget by $500K and put funds back into general MM24 funds for other projects. More of a reduction might happen but want updated CMCA from DCI Group. MM24 - 9306.00 - Please setup PM time budget of $30K Totals back to MM24 - $545,000 DA24 - 9362.00 - Please setup PM time budget of $10K PM Time Budget Increases Inbox Tonyan, Brad 2:56 PM (1 minute ago) to me, Brad Finance, Please make the following adjustments to ensure coverage on November PM time: MM22 - 9245.00 - Increase PM Time $2,000 MM24 - 9306.00 - Increase PM Time $10,000 MM24 - 9376.00 - Increase PM Time $2,500 DA24 - 9362.00 - Increase PM Time $2,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Tonyan, Brad 12:00 PM (10 minutes ago) to me Joni, Looking back on this I did ask for a PM time budget increase back in November below but it looks like that increase didn't happen? Please make the following adjustments below and disregard the old email now: DA24 - 9362.00 - Increase PM Time budget by $3K to a total of $15K MM24 - 9376.00 - Increase PM Time budget by $2K to ensure we are covered as this one will be tight as well for Dec/Jan postings Re: April PM Time $Joni Tonyan, Brad 2:40 PM (6 minutes ago) to me, Joni Finance, Please raise the following projects PM time budgets: DA24 9355.00 60.93 DA24 9362.00 173.39 (This one is not my project but is James Trower) DA24 9412.00 365.13 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9362.00 Misc
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524361804 | 2023-12-27 | 9500 | CNST | Allender Butzke Engineer V#(00002119950) | Inv. 231408A | 4082.5 | 4082.5
GAX 33524024908 | 2024-01-24 | 9500 | CNST | Clapsaddle-Garber Associates V#(00002109548) | Inv. 500691 | 2500 | 6582.5
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 110 | 6692.5
PRC 33524085802 | 2024-03-25 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL423 | 282.92 | 6975.42
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 192.5 | 7167.92
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -302.5 | 6865.42
GAX 33524191902 | 2024-07-08 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2580479 | 1337.5 | 8202.92
8202.92
8202.92
8202.92
8202.92
8202.92
|  |  |  | Totals: |  | 8202.92

## #9362.00 Shive Hattery
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524319804 | 2023-11-15 | PO Procore | 14000 | 14000 |  |  | 14000
PRC 3352431PA9804 | 2023-12-19 | Inv. 9362.00-001 |  | 14000 | 6000 | 6000 | 8000
PRC 3352431PB9804 | 2024-01-24 | Inv. 2112309630-2 |  | 14000 | 2000 | 8000 | 6000
PRC 3352431PC9804 | 2024-02-29 | Inv. 9362.00-003 |  | 14000 | 2000 | 10000 | 4000
PRC 3352431PD9804 | 2024-05-17 | Inv. 9362.00-004 |  | 14000 | 750 | 10750 | 3250
PRC 3352431PE9804 | 2024-07-16 | Inv. 9362.00-005 |  | 14000 | 1950 | 12700 | 1300 | FY24
PO 33525319804 | 2024-08-28 | Roll to FY25 |  | 14000 |  | 12700 | 1300
PRC 3352531PF9804 | 2024-11-19 | Inv. 9362.00-006 |  | 14000 | 1137.5 | 13837.5 | 162.5
PRC 3352531PG9804 | 2025-01-08 | Inv. 9362.00-07 - Final |  | 14000 | 162.5 | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  |  |  | 14000 |  | 14000 | 0
|  | Totals: | 14000 |  | 14000 |  | 0 | FINAL
|  | Design Phase Services | 10000 |  | 10000 |  | 0
|  | Bid phase Services | 750 |  | 750 |  | 0
|  | Construction Phase Services | 3250 |  | 3250 |  | 0
|  | Total: | 14000 |  | 14000 |  | 0

## #9362.00 System Works LLC
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
System Works LLC |  |  | Vendor:00002144353
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524355803 | 2023-12-21 | PO Procore | 13990 | 13990 |  |  | 13990
PRC 3352435PA5803 | 2024-07-16 | Inv. 11869 |  | 13990 | 3780 | 3780 | 10210 | FY24
PO 33525355803 | 2024-08-28 | Roll to FY25 |  | 13990 |  | 3780 | 10210
PRC 3352535PB5803 | 2024-10-14 | Inv. 11998 |  | 13990 | 4320 | 8100 | 5890
PRC 3352535PC5803 | 2024-12-30 | Inv. 12126 - FINAL |  | 13990 | 5890 | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  |  |  | 13990 |  | 13990 | 0
|  | Totals: | 13990 |  | 13990 |  | 0 | FINAL

## #9362.00 Baker Group
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
The Baker Group |  |  | Vendor:00002109043
Acct. Codes-0506-335-DA24-9255 |  |  | RFB#936200-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524124802 | 2024-05-03 | PO Procore | 298639.63 | 298639.63 |  |  | 298639.63
PO 33524124802 | 2024-06-01 | CO #1 (100% to MM24) | 0 | 298639.63 |  | 0 | 298639.63
PRC 3352412PA4802 | 2024-07-11 | Inv. 273126 (100% to MM24) |  | 298639.63 | 0 | 0 | 298639.63 | 0 | FY24
PO 33525124802 | 2024-08-28 | Roll to FY25 |  | 298639.63 |  | 0 | 298639.63
PRC 3352512PB4802 | 2024-09-11 | Inv. 275139 (100% to DA24) |  | 298639.63 | 153223.12 | 153223.12 | 145416.51 | 8064.38
PO 33525124802 | 2024-09-17 | CO #2 (100% to MM24-No Cost CO) | 0 | 298639.63 |  | 153223.12 | 145416.51
PRC 3352512PC4802 | 2024-09-25 | Inv. 278550(Split w/MM24) |  | 298639.63 | 103667.13 | 256890.25 | 41749.38 | 13520.55
PRC 3352512PD4802 | 2024-10-15 | Inv. 281049(Split w/MM24) |  | 298639.63 | 18675.1 | 275565.35 | 23074.28 | 14503.45
PO 33525124802 | 2024-10-15 | CO #3 (100% to MM24) | 0 | 298639.63 |  | 275565.35 | 23074.28
PO 33525124802 | 2024-11-20 | Correcting CO #1 - Move to DA24-100% | 14154 | 312793.63 |  | 275565.35 | 37228.28
PO 33525124802 | 2024-12-05 | Correcting CO #3 - Move to DA24-100% | -20240 | 292553.63 |  | 275565.35 | 16988.28
PRC 3352512PE4802 | 2024-12-05 | Inv. 283124A(Split With MM24) |  | 292553.63 | 2399.87 | 277965.22 | 14588.41 | 14588.41
PRC 3352512PF4802 | 2025-02-12 | Inv. 290119 - Retainage(Split With DA24) |  | 292553.63 | 14588.41 | 292553.63 | 0
|  | Totals: | 292553.63 |  | 292553.63 |  | 0
|  | MM24 | 139604.37 |  | 139604.37 |  | 0
|  | Total: | 432158 |  | 432158 |  | 0

## #9362.00 Van Maanen
DOC CBC District 2 Marshalltown Geothermal System Replacement
Project # 9362.00
Program code 936200 |  |  | Major Program 4B01
Van Maanen Electric |  |  | Vendor:00002109043
Acct. Codes-0506-335-DA24-9255 |  |  | RFB#936200-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split with MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525124808 | 2024-09-26 | CO #2 (100% to DA24) | 2362.29 | 2362.29 |  |  | 2362.29
PRC 3352512PA4808 | 2024-10-15 | Inv. 2450-01 (100% to MM24) |  | 2362.29 | 0 | 0 | 2362.29
PRC 3352512PB4808 | 2024-11-22 | Inv. 2450-02 (100% to DA24) |  | 2362.29 | 2244.18 | 2244.18 | 118.11 | 118.11
PRC 3352512PC4808 | 2025-01-03 | Inv. 2450-03 (100% to MM24) |  | 2362.29 | 0 | 2244.18 | 118.11
PRC 3352512PD4808 | 2025-02-06 | Inv. 2450-04 Retainage (Split W/ MM24) |  | 2362.29 | 118.11 | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  |  |  | 2362.29 |  | 2362.29 | 0
|  | Totals: | 2362.29 |  | 2362.29 |  | 0 | FINAL
|  | MM24 | 19900 |  | 19900 |  | 0
|  | Total: | 22262.29 |  | 22262.29 |  | 0

## RECAP #9363.00
DOE ISD Infirmary Roof Replacement
Project # 9363.00
| Program code 936300 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 163663.58
C | Samuels Group |  | 16892.52 | 16892.52 | 0
C | PM TIME |  | 10305.64 | 10305.64 | 0
C | Misc. |  | 16109.63 | 16109.63 | 0
C | Modern Design |  | 8850 | 8850 | 0
C | Samuels Group(2) |  | 15960.44 | 15960.44 | 0
C | McKinnis Roofing & Sheet Metal |  | 95545.35 | 95545.35 | 0
| Total Project Cost | 163663.58 | 163663.58 | 163663.58 | 0 | 0
Closed 03/11/25

## #9363.00 Funds Rec'd
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524297101 | 2023-10-25 | 215000 | 215000
|  |  | Clsoing Project per PM | IET 33525070901 | 2025-03-11 | -51336.42 | -51336.42
| Total Requested | 0 | Total Transferred |  |  | 163663.58 | 163663.58

## #9363.00 Samuels Group
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524299806 | 2023-10-26 | PO Procore | 16892.52 | 16892.52 |  |  | 16892.52
PRC 3352429PA9806 | 2023-12-20 | Inv. 7550.01936300 |  | 16892.52 | 631.59 | 631.59 | 16260.93
PRC 3352429PB9806 | 2024-01-08 | Inv. 7550.02936300 |  | 16892.52 | 2912.57 | 3544.16 | 13348.36
PRC 3352429PC9806 | 2024-02-05 | Inv. 7550.03936300 |  | 16892.52 | 1993.29 | 5537.45 | 11355.07
PRC 3352429PD9806 | 2024-03-06 | Inv. 7550.04936300 |  | 16892.52 | 2362.92 | 7900.37 | 8992.15
PRC 3352429PE9806 | 2024-04-12 | Inv. 7550.05936300 |  | 16892.52 | 1765.72 | 9666.09 | 7226.43
PRC 3352429PF9806 | 2024-05-07 | Inv. 7550.06936300 |  | 16892.52 | 3553.21 | 13219.3 | 3673.22
PRC 3352429PG9806 | 2024-06-01 | Inv. 7550.07936300 PC FINAL |  | 16892.52 | 3673.22 | 16892.52 | 0
|  |  |  | 16892.52 |  | 16892.52 | 0
|  |  |  | 16892.52 |  | 16892.52 | 0
|  |  |  | 16892.52 |  | 16892.52 | 0
|  |  |  | 16892.52 |  | 16892.52 | 0
|  |  |  | 16892.52 |  | 16892.52 | 0
|  | Totals: | 16892.52 |  | 16892.52 |  | 0 | FINAL
|  | CM Services | 16332.52 |  | 16332.52 |  | 0
|  | Reimbursables | 560 |  | 560 |  | 0
|  | Total: | 16892.52 |  | 16892.52 |  | 0

## #9363.00 PM TIME
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E2A9
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10305.64 | 10305.64 |  |  | 10305.64
IET DAS202404115300001 | 2023-11-08 | 2507 | Finance Support for October 1-31, 2023 |  | 10305.64 | 84.9 | 84.9 | 10220.74
IET DAS202404115300001 | 2023-11-08 | 9500 | DAS Services for October 1-31, 2023 |  | 10305.64 | 682.4 | 767.3 | 9538.34
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10305.64 | 54.72 | 822.02 | 9483.62
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10305.64 | 414.3 | 1236.32 | 9069.32
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 10305.64 | 134.05 | 1370.37 | 8935.27
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 10305.64 | 986.4 | 2356.77 | 7948.87
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10305.64 | 106.37 | 2463.14 | 7842.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10305.64 | 935.7 | 3398.84 | 6906.8
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10305.64 | 157.34 | 3556.18 | 6749.46
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10305.64 | 792.2 | 4348.38 | 5957.26
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10305.64 | 95.41 | 4443.79 | 5861.85
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10305.64 | 723.7 | 5167.49 | 5138.15
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 10305.64 | 100.69 | 5268.18 | 5037.46
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 10305.64 | 896.8 | 6164.98 | 4140.66
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 10305.64 | 35.31 | 6200.29 | 4105.35
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10305.64 | 293.9 | 6494.19 | 3811.45
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10305.64 | 57.35 | 6551.54 | 3754.1
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10305.64 | 526.9 | 7078.44 | 3227.2
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10305.64 | 72.37 | 7150.81 | 3154.83
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10305.64 | 791.8 | 7942.61 | 2363.03
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10305.64 | 79.72 | 8022.33 | 2283.31
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10305.64 | 405.2 | 8427.53 | 1878.11
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10305.64 | 103.97 | 8531.5 | 1774.14
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10305.64 | 926.8 | 9458.3 | 847.34
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10305.64 | 103.71 | 9562.01 | 743.63
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10305.64 | 694.1 | 10256.11 | 49.53
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10305.64 | 9.13 | 10265.24 | 40.4
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10305.64 | 40.4 | 10305.64 | 3.503e-12
[5 empty] | 10305.64 |  | 10305.64 | 3.503e-12
|  |  | Totals: | 10305.64 |  | 10305.64 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie Thu, Aug 1, 8:43 AM (4 days ago) to me Please Increase PM Time on the following projects. 9363.00 - Please increase to a total "Contracted" of $12,000 9381.00 - Please increase to a total "Contracted" of $14,000

## #9363.00 Misc
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202405115300001 | 2023-12-07 | 2507 |  | Central Procurement Hourly Rate for November 1-30, 2023 | DAS2024051153 | 137.5 | 137.5
IET DAS202406115300001 | 2024-01-08 | 2507 |  | Central Procurement Hourly Rate for December 1-31, 2023 | DAS2024061153 | 275 | 412.5
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 82.5 | 495
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 27.5 | 522.5
GAX 33524078900 | 2024-03-18 | 9500 | CNST | McKinnis Inc V#(00003003781) | Inv. 44309 | 407.23 | 929.73
GAX 33524078901 | 2024-03-18 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2555629 | 966.25 | 1895.98
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -522.5 | 1373.48
PRC 33524169900 | 2024-06-17 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL625 | 262.72 | 1636.2
GAX 33525250904 | 2024-09-06 | 9500 | CNST | Earth Services V#(VS000007582) | Inv. DES-I002095 | 3342.72 | 4978.92
CDE 33525260906 | 2024-09-16 | 9500 | CNST | Move expense from 9363.00 to 9381.00 | Inv. DES-I002095 | -3342.72 | 1636.2
GAX 33525260907 | 2024-09-16 | 9500 | CNST | Earth Services V#(VS000007582) | Inv. DES-I002099 | 14473.43 | 16109.63
16109.63
16109.63
16109.63
|  |  |  | Totals: |  | 16109.63

## #9363.00 Modern Design
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  | Major Program 4E02
Modern Design |  |  | Vendor:00003214686
Acct. Codes-0506-335-DA24-9260 |  |  | RFP936300-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010906 | 2024-01-10 | PO Procore | 8850 | 8850 |  |  | 8850
PO 33524010906 | 2024-02-15 | CO #1(No Cost CO) | 0 | 8850 |  | 0 | 8850
PRC 3352401PA0906 | 2024-06-01 | Inv. 34295 |  | 8850 | 4650 | 4650 | 4200 | FY24
PO 33525010906 | 2024-08-16 | Roll to FY25 |  | 8850 |  | 4650 | 4200
PRC 3352501PB0906 | 2024-08-22 | Inv. 34409 |  | 8850 | 3150 | 7800 | 1050
PRC 3352501PC0906 | 2024-10-22 | Inv. 34450-Final |  | 8850 | 1050 | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  |  |  | 8850 |  | 8850 | 0
|  | Totals: | 8850 |  | 8850 |  | 0 | FINAL
|  | Design Development | 900 |  | 900 |  | 0
|  | Constructions Documents | 3000 |  | 3000 |  | 0
|  | Bidding | 750 |  | 750 |  | 0
|  | Construction Phase | 4200 |  | 4200 |  | 0
|  | Total: | 8850 |  | 8850 |  | 0

## #9363.00 Samuels Group (2)
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  | Major Program 4E02
Samuels Group(2) |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524123906 | 2023-10-26 | PO Procore | 15960.44 | 15960.44 |  |  | 15960.44
PRC 3352412PA3906 | 2024-07-11 | Inv. 7688.51936300 |  | 15960.44 | 1102.14 | 1102.14 | 14858.3 | FY24
PO 33525123906 | 2024-08-16 | Roll to FY25 |  | 15960.44 |  | 1102.14 | 14858.3
PRC 3352512PB3906 | 2024-09-04 | Inv. 7688.52936300 |  | 15960.44 | 6210.03 | 7312.17 | 8648.27
PRC 3352512PC3906 | 2024-09-12 | Inv. 7688.53936300 |  | 15960.44 | 2069.2 | 9381.37 | 6579.07
PRC 3352512PD3906 | 2024-10-02 | Inv. 7688.54936300 |  | 15960.44 | 3051.95 | 12433.32 | 3527.12
PRC 3352512PE3906 | 2024-10-22 | Inv. 7688.55936300-FINAL |  | 15960.44 | 3527.12 | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  |  |  | 15960.44 |  | 15960.44 | 0
|  | Totals: | 15960.44 |  | 15960.44 |  | 0 | FINAL
|  | CM Services | 15160.44 |  | 15160.44 |  | 0
|  | Reimbursables | 800 |  | 800 |  | 0
|  | Total: | 15960.44 |  | 15960.44 |  | 0

## #9363.00 McKinnis Roofing
DOE ISD Infirmary Roof Replacement
Project # 9363.00
Program code 936300 |  |  | Major Program 4E02
McKinnis Roofing |  |  | Vendor:00003217305
Acct. Codes-0506-335-DA24-9255 |  |  | RFB936300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524134902 | 2024-05-13 | PO Procore | 93326 | 93326 |  |  | 93326 |  | FY24
PO 33525134902 | 2024-08-16 | Roll to FY25 |  | 93326 |  | 0 | 93326
PO 33525134902 | 2024-08-29 | CO #1 | 2219.35 | 95545.35 |  | 0 | 95545.35
PRC 3352513PA4902 | 2024-09-04 | Inv. 9363.00-01 |  | 95545.35 | 79644.19 | 79644.19 | 15901.16 | 4191.8
PRC 3352513PB4902 | 2024-10-07 | Inv. 9363.00-02 |  | 95545.35 | 10237.29 | 89881.48 | 5663.87 | 4730.61
PRC 3352513PC4902 | 2024-10-08 | Inv. 9363.00-03 |  | 95545.35 | 886.6 | 90768.08 | 4777.27 | 4777.27
PRC 3352513PD4902 | 2024-10-22 | Inv. 9363.00-04 Retainage |  | 95545.35 | 4777.27 | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  |  |  | 95545.35 |  | 95545.35 | 0
|  | Totals: | 95545.35 |  | 95545.35 |  | 0 | FINAL

## RECAP #9367.00
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
| Program code 936700 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 6600
C | BlackHawk Roofing |  | 6600 | 6600 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 6600 | 6600 | 6600 | 0 | 0
Closed 04/16/25

## #9367.00 Funds Rec'd
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 04242400089 | 2024-04-30 | 6600 | 6600
|  |  | Returning FY24 Funds to Agency | IET 33524227911 | 2024-08-14 | -6600 | -6600
|  |  | Received FY25 Funds From Agency | IET 33524227911 | 2024-08-16 | 6600 | 6600
| Total Requested | 0 | Total Transferred |  |  | 6600 | 6600

## #9367.00 Black Hawk Roofing
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  | Major Program 4E02
Black Hawk Roofing |  |  | Vendor: 00002120676
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 936700-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Split w/MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524123900 | 2024-05-02 | PO Procore | 6600 | 6600 |  |  | 6600 |  | FY24
PO 33525123900 | 2024-08-19 | Roll to FY25 |  | 6600 |  | 0 | 6600
PRC 3352512PA3900 | 2024-12-19 | Inv. 9367.00-01(Split w/MM22) |  | 6600 | 5643 | 5643 | 957 | 297
PRC 3352512PB3900 | 2025-03-25 | Inv. 9367.00-02(Split w/MM22) |  | 6600 | 627 | 6270 | 330 | 330
PRC 3352512PC3900 | 2025-03-26 | Inv. 9367.00-03-Retainage(Split w/MM22) |  | 6600 | 330 | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  |  |  | 6600 |  | 6600 | 0
|  | Totals: | 6600 |  | 6600 |  | 0
|  | MM22 | 203400 |  | 203400 |  | 0
|  | Total | 210000 |  | 210000 |  | 0

## #9367.00 PM TIME
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A. |  |  |  | eDAS: E2D7
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 0 | 27.14 | 27.14 | -27.14
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 0 | 197 | 224.14 | -224.14
CDE 33525106901 | 2025-04-15 | 2507 | Move expenses to 999725 due to billable file error |  | 0 | -27.14 | 197 | -197
CDE 33525106901 | 2025-04-15 | 9500 | Move expenses to 999725 due to billable file error |  | 0 | -197 | 0 | 0
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 0 | -27.14 | -27.14 | 27.14
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 0 | -197 | -224.14 | 224.14
CDE 33525134911 | 2025-05-13 | 2507 | Move expenses From 999725 due to billable file error |  | 0 | 27.14 | -197 | 197
CDE 33525134911 | 2025-05-13 | 9500 | Move expenses From 999725 due to billable file error |  | 0 | 197 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9367.00 Misc
DOE IPBS JOH 6535 Corporate Dr Roof Replacement
Project # 9367.00
Program code 936700 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9374.00
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
| Program code 937400 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 476200
C | Genesis Architectural |  | 850 | 850 | 0
| PM TIME |  | 20000 | 12869.96 | 7130.04
| Misc. |  | 1354.46 | 1354.46 | 0
C | DCI Group #24-014 PC |  | 13960.54 | 13960.54 | 0
| Genesis Architectural |  | 44100 | 34560 | 9540
| L&L Builders |  | 279217 | 253449.55 | 25767.45
| DCI Group #24-014 CA |  | 42527.91 | 17390.63 | 25137.28
| Total Project Cost | 476200 | 402009.91 | 334435.14 | 67574.77 | 74190.09

## #9374.00 Funds Rec'd
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA24-0234
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 407JP2411022301 | 2023-11-03 | 1200 | 1200
|  |  | Move Revenue from DA23 to DA24 | CDR 33524088900 | 2024-03-28 | 625000 | 625000
|  |  | Returning FY24 Funds to Agency | IET 33524227912 | 2024-08-14 | -616417.51 | -616417.51
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227912A | 2024-08-20 | -1069.12 | -1069.12
|  |  | Move funds to correct unit - DA22 to DA24 | CDR 33525271900 | 2024-09-27 | 617486.63 | 617486.63
|  |  | Returning Partial Funds to Agency | IET 33525048903 | 2025-02-17 | -150000 | -150000
| Total Requested | 0 | Total Transferred |  |  | 476200 | 476200

## #9374.00 Genesis Architectural
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524334911 | 2023-11-30 | PO Procore | 850 | 850 |  |  | 850
PRC 3352433PA4911 | 2024-04-15 | Inv. 2313-01 |  | 850 | 850 | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  |  |  | 850 |  | 850 | 0
|  | Totals: | 850 |  | 850 |  | 0

## #9374.00 PM TIME
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 908R
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 20000 | 12.11 | 12.11 | 19987.89
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 20000 | 92.8 | 104.91 | 19895.09
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 20000 | 11.26 | 116.17 | 19883.83
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 20000 | 82.2 | 198.37 | 19801.63
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 20000 | 9.57 | 207.94 | 19792.06
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 20000 | 84.6 | 292.54 | 19707.46
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 20000 | 7.96 | 300.5 | 19699.5
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 20000 | 41.5 | 342 | 19658
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 20000 | 26.01 | 368.01 | 19631.99
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 20000 | 201.4 | 569.41 | 19430.59
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 20000 | 25.24 | 594.65 | 19405.35
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 20000 | 224.6 | 819.25 | 19180.75
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 20000 | 152.42 | 971.67 | 19028.33
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 20000 | 1257.6 | 2229.27 | 17770.73
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 20000 | 124.45 | 2353.72 | 17646.28
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 20000 | 1140.6 | 3494.32 | 16505.68
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 20000 | 45.06 | 3539.38 | 16460.62
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 20000 | 489.5 | 4028.88 | 15971.12
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 20000 | 143.09 | 4171.97 | 15828.03
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 20000 | 727.9 | 4899.87 | 15100.13
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 41.7 | 4941.57 | 15058.43
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 369.4 | 5310.97 | 14689.03
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 178.75 | 5489.72 | 14510.28
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 1191.1 | 6680.82 | 13319.18
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 56.36 | 6737.18 | 13262.82
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 373.7 | 7110.88 | 12889.12
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 90.14 | 7201.02 | 12798.98
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 902.7 | 8103.72 | 11896.28
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 88.45 | 8192.17 | 11807.83
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 945.7 | 9137.87 | 10862.13
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 119.08 | 9256.95 | 10743.05
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 515.6 | 9772.55 | 10227.45
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 173.35 | 9945.9 | 10054.1
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 1241 | 11186.9 | 8813.1
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 145.67 | 11332.57 | 8667.43
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 1000.9 | 12333.47 | 7666.53
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 60.79 | 12394.26 | 7605.74
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 475.7 | 12869.96 | 7130.04
[5 empty] | 20000 |  | 12869.96 | 7130.04
[5 empty] | 20000 |  | 12869.96 | 7130.04
[5 empty] | 20000 |  | 12869.96 | 7130.04
|  |  | Totals: | 20000 |  | 12869.96 |  | 7130.04
Note on E9: Huggins, Joni [DAS]: Elliott, Jennie 8:35 AM (5 hours ago) to me Can you please establish a PM Time budget of $350.00 in project 9374.00 HHS CHMHI Gym Ceiling Repair - DA24. Thank you, Jennie Elliott

## #9374.00 Misc
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code: 548
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525318909 | 2024-11-13 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1177 | 338.21 | 338.21
PRC 33525344900 | 2024-12-09 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2610688 | 1016.25 | 1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
1354.46
|  |  |  | Totals: |  | 1354.46

## #9374.00 DCI Group
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
DCI Group #24-014 PC |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524123802 | 2024-05-02 | PO Procore | 16901.09 | 16901.09 |  |  | 16901.09
PRC 3352412PA3802 | 2024-07-03 | Inv. 24-014 PC-01 |  | 16901.09 | 3633.36 | 3633.36 | 13267.73
PRC 3352412PB3802 | 2024-07-18 | Inv. 24-014 PC 02 |  | 16901.09 | 735.69 | 4369.05 | 12532.04 | FY24
PO 33525123802 | 2024-08-19 | Roll to FY25 |  | 16901.09 |  | 4369.05 | 12532.04
PRC 3352512PC3802 | 2024-09-27 | Inv. 24-014 PC 03 |  | 16901.09 | 760.77 | 5129.82 | 11771.27
PRC 3352512PD3802 | 2024-09-30 | Inv. 24-014 PC 04 |  | 16901.09 | 2028.72 | 7158.54 | 9742.55
PRC 3352512PE3802 | 2024-12-03 | Inv. 24-014 PC 05 |  | 16901.09 | 4122.12 | 11280.66 | 5620.43
PRC 3352512PF3802 | 2024-12-20 | Inv. 24-014 PC 06 |  | 16901.09 | 1014.36 | 12295.02 | 4606.07
PRC 3352512PG3802 | 2025-01-13 | Inv. 24-014 PC 07-Final | -2940.55 | 13960.54 | 1665.52 | 13960.54 | 0
|  |  |  | 13960.54 |  | 13960.54 | 0
|  |  |  | 13960.54 |  | 13960.54 | 0
|  |  |  | 13960.54 |  | 13960.54 | 0
|  |  |  | 13960.54 |  | 13960.54 | 0
|  | Totals: | 13960.54 |  | 13960.54 |  | 0 | FINAL
|  | CM Staff Hours | 13593.54 |  | 13593.54 |  | 0
|  | Reimbursable Expenses | 367 |  | 367 |  | 0
|  | Total: | 13960.54 |  | 13960.54 |  | 0

## #9374.00 Genesis Architectural2
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
Genesis Architectural (2) |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA24-9260 |  |  | RFP937400-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525271909 | 2024-09-27 | PO Procore | 44100 | 44100 |  |  | 44100
PRC 3352527PA1909 | 2024-10-02 | Inv. 2409-02 |  | 44100 | 22900 | 22900 | 21200
PRC 3352527PB1909 | 2025-05-09 | Inv. 2409-03 |  | 44100 | 11660 | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  |  |  | 44100 |  | 34560 | 9540
|  | Totals: | 44100 |  | 34560 |  | 9540
|  | Design Development | 10700 |  | 10700 |  | 0
|  | Construction Docs | 12200 |  | 12200 |  | 0
|  | Bid Phase | 5300 |  | 5300 |  | 0
|  | Construction Phase | 15900 |  | 6360 |  | 9540
|  | Total: | 44100 |  | 34560 |  | 9540

## #9374.00 L & L Builders
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
L & L Builders |  |  | Vendor: 00003226164
Acct. Codes-0506-335-DA24-9255 |  |  | RFB937400-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525330900 | 2024-11-25 | PO Procore | 282930 | 282930 |  |  | 282930
PO 33525330900A | 2025-03-17 | Open new PO to change vendor code |  | 282930 |  | 0 | 282930
PRC 3352533PA0900A | 2025-03-17 | Inv. 10008 |  | 282930 | 67192.55 | 67192.55 | 215737.45 | 3536.45
PO 33525330900A | 2025-03-17 | CO #1 No Cost CO | 0 | 282930 |  | 67192.55 | 215737.45
PO 33525330900A | 2025-04-03 | CO #2 | -6294 | 276636 |  | 67192.55 | 209443.45
PRC 3352533PB0900A | 2025-04-07 | Inv. 10023 |  | 276636 | 26931.55 | 94124.1 | 182511.9 | 4953.9
PO 33525330900A | 2025-04-10 | CO #3 | 2116 | 278752 |  | 94124.1 | 184627.9
PO 33525330900A | 2025-05-05 | CO #4 | 465 | 279217 |  | 94124.1 | 185092.9
PO 3352533PC0900A | 2025-05-09 | Inv. 10036 |  | 279217 | 41806.08 | 135930.18 | 143286.82 | 7154.22
PO 3352533PD0900A | 2025-06-10 | Inv. 10056 |  | 279217 | 117519.37 | 253449.55 | 25767.45 | 13339.45
|  |  |  | 279217 |  | 253449.55 | 25767.45
|  |  |  | 279217 |  | 253449.55 | 25767.45
|  |  |  | 279217 |  | 253449.55 | 25767.45
|  | Totals: | 279217 |  | 253449.55 |  | 25767.45

## #9374.00 DCI Group (2)
HHS CHMHI Gym Ceiling Repair
Project # 9374.00
Program code 937400 |  |  | Major Program 4B02
DCI Group #24-014 CA |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFB937400-01
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525366900 | 2024-12-31 | PO Procore | 42527.91 | 42527.91 |  |  | 42527.91
PRC 3352536PA6900 | 2025-02-06 | Inv. 24-014 CA 01 |  | 42527.91 | 1658.84 | 1658.84 | 40869.07
PRC 3352536PB6900 | 2025-03-17 | Inv. 24-014 CA 02 |  | 42527.91 | 4738.85 | 6397.69 | 36130.22
PRC 3352536PC6900 | 2025-04-21 | Inv. 24-014 CA 03 |  | 42527.91 | 4406.72 | 10804.41 | 31723.5
PRC 3352536PD6900 | 2025-05-09 | Inv. 24-014 CA 04 |  | 42527.91 | 3647.52 | 14451.93 | 28075.98
PRC 3352536PE6900 | 2025-06-10 | Inv. 24-014 CA 05 |  | 42527.91 | 2938.7 | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  |  |  | 42527.91 |  | 17390.63 | 25137.28
|  | Totals: | 42527.91 |  | 17390.63 |  | 25137.28
|  | CM Staff Hours | 39027.91 |  | 17024.53 |  | 22003.38
|  | Reimbursable Expenses | 3500 |  | 366.1 |  | 3133.9
|  | Total: | 42527.91 |  | 17390.63 |  | 25137.28

## RECAP #9375.00
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
| Program code 937500 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1134000
| The Samuels Group |  | 17305.72 | 17048.28 | 257.44
| PM TIME |  | 50000 | 31784.52 | 18215.48
| Misc. |  | 5116.28 | 5116.28 | 0
C | OPN Architects |  | 23990 | 23990 | 0
C | The Samuels Group (2) |  | 12155.24 | 12155.24 | 0
| OPN Architects (2) |  | 96121 | 86271 | 9850
C | For Sure Roofing |  | 34723 | 34723 | 0
C | Samuels Group(3) |  | 9407.21 | 9407.21 | 0
| Samuels Group(4) |  | 144488.47 | 50307.09 | 94181.38
| Azcon Inc. |  | 633635.75 | 83291.58 | 550344.17
| Total Project Cost | 1134000 | 1026942.67 | 354094.2 | 672848.47 | 107057.33

## #9375.00 Funds Rec'd
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 00524311101 | 2023-11-08 | 71000 | 71000
|  |  | MOU Amendment #1 | CR 00524128101 | 2024-05-07 | 800000 | 800000
|  |  | MOU Amendment #2 | IET 225A05251498 | 2025-02-18 | 263000 | 263000
| Total Requested | 0 | Total Transferred |  |  | 1134000 | 1134000

## #9375.00 Samuels Group
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524325802 | 2023-11-21 | PO Procore | 13584.26 | 13584.26 |  |  | 13584.26
PRC 3352432PA5802 | 2024-02-07 | Inv. 9375.01 PC |  | 13584.26 | 6884.58 | 6884.58 | 6699.68
PO 33524325802 | 2024-04-03 | CO #1 | 3721.46 | 17305.72 |  | 6884.58 | 10421.14
PRC 3352432PB5802 | 2024-05-02 | Inv. 7549.52937500 |  | 17305.72 | 4113.44 | 10998.02 | 6307.7 | FY24
PO 33525325802 | 2024-08-16 | Roll to FY25 | 0 | 17305.72 |  | 10998.02 | 6307.7
PRC 3352532PC5802 | 2024-08-23 | Inv. 7549.53937500 |  | 17305.72 | 587.68 | 11585.7 | 5720.02
PRC 3352532PD5802 | 2024-10-03 | Inv. 7549.54937500 |  | 17305.72 | 5134.52 | 16720.22 | 585.5
PRC 3352532PE5802 | 2024-11-12 | Inv. 7549.55937500 |  | 17305.72 | 328.06 | 17048.28 | 257.44
|  |  |  | 17305.72 |  | 17048.28 | 257.44
|  |  |  | 17305.72 |  | 17048.28 | 257.44
|  |  |  | 17305.72 |  | 17048.28 | 257.44
|  |  |  | 17305.72 |  | 17048.28 | 257.44
|  |  |  | 17305.72 |  | 17048.28 | 257.44
|  | Totals: | 17305.72 |  | 17048.28 |  | 257.44
|  | CM Services | 13284.26 |  | 13284.26 |  | 0
|  | Reimbursables | 300 |  | 91 |  | 209
|  | CO #1 | 3721.46 |  | 3673.02 |  | 48.44
|  | Total: | 17305.72 |  | 17048.28 |  | 257.44

## #9375.00 PM TIME
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - James T. |  |  |  | eDAS E2AQ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 50000 | 50000 |  |  | 50000
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 50000 | 123.94 | 123.94 | 49876.06
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 50000 | 934.5 | 1058.44 | 48941.56
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 50000 | 88.72 | 1147.16 | 48852.84
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 50000 | 650.5 | 1797.66 | 48202.34
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 50000 | 201.22 | 1998.88 | 48001.12
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 50000 | 1776.4 | 3775.28 | 46224.72
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 50000 | 311.63 | 4086.91 | 45913.09
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 50000 | 1569.7 | 5656.61 | 44343.39
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 50000 | 258.69 | 5915.3 | 44084.7
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 50000 | 1964.2 | 7879.5 | 42120.5
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 50000 | 248.65 | 8128.15 | 41871.85
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 50000 | 2209.5 | 10337.65 | 39662.35
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 50000 | 117.95 | 10455.6 | 39544.4
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 50000 | 977.9 | 11433.5 | 38566.5
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 50000 | 127.92 | 11561.42 | 38438.58
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 50000 | 1166.8 | 12728.22 | 37271.78
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 50000 | 83.78 | 12812 | 37188
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 50000 | 912.4 | 13724.4 | 36275.6
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 50000 | 288.31 | 14012.71 | 35987.29
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 50000 | 1467.3 | 15480.01 | 34519.99
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 50000 | 101.15 | 15581.16 | 34418.84
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 50000 | 900 | 16481.16 | 33518.84
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 50000 | 257.16 | 16738.32 | 33261.68
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 50000 | 1711.8 | 18450.12 | 31549.88
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 50000 | 203.5 | 18653.62 | 31346.38
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 50000 | 1353.3 | 20006.92 | 29993.08
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 50000 | 99.56 | 20106.48 | 29893.52
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 50000 | 992.8 | 21099.28 | 28900.72
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 50000 | 283.21 | 21382.49 | 28617.51
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 50000 | 3015.8 | 24398.29 | 25601.71
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 50000 | 390.66 | 24788.95 | 25211.05
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 50000 | 1688.3 | 26477.25 | 23522.75
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 50000 | 134.97 | 26612.22 | 23387.78
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 50000 | 967.6 | 27579.82 | 22420.18
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 50000 | 210.77 | 27790.59 | 22209.41
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 50000 | 1449.5 | 29240.09 | 20759.91
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 50000 | 288.03 | 29528.12 | 20471.88
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 50000 | 2256.4 | 31784.52 | 18215.48
[5 empty] | 50000 |  | 31784.52 | 18215.48
[5 empty] | 50000 |  | 31784.52 | 18215.48
[5 empty] | 50000 |  | 31784.52 | 18215.48
[5 empty] | 50000 |  | 31784.52 | 18215.48
[5 empty] | 50000 |  | 31784.52 | 18215.48
|  |  | Totals: | 50000 |  | 31784.52 |  | 18215.48
Note on E9: Jurgenson, John [DAS]: From: Trower, James <james.trower@iowa.gov> Date: Thu, Nov 9, 2023 at 8:09 AM Subject: Re: DA24 9375.00 To: Huggins, Joni <joni.huggins@iowa.gov> Joni - Can you please set up $8,000 in PM time for project 9375.00? Thanks, James Re: PM TIme $John Trower, James May 8, 2024, 4:35 PM (15 hours ago) to me Finance - See below modifications in RED. On Wed, May 8, 2024 at 11:20 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello James Can you please review the following projects to see if the budget can be increases to allow us to post the April PM time? 9338.00 in DA23 Amount is $155.51 Increase the PM Time by $3,000. 9375.00 in DA24 Amount is $2337.65 Increase the PM Time by $14,000 9342.00 in MM21 Amount is $1042.99 Increase the PM Time by $1,042.99 9407.00 in MM22 Amount is $1014.75 Set up $8,000 in PM Time 9305.00 in MM23 Amount is $631.96 A previous email was sent on 5/8/24 stating to increase the PM Time by $20,000. Budget Modifications - James Trower $Joni Trower, James Feb 10, 2025, 4:13 PM (15 hours ago) to me Finance - Please see below budget modifications: 9449.00 - DAS TH Carriage House Roof Replacement Increase MM25 budget by $125,000.00 9375.00 - DOC 5JD DM Bldgs 65-66 Renovation Increase PM Time (DA24) by $28,000.00

## #9375.00 Misc
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T. |  |  |  | Shipping Code: 1122
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2023 | DAS2024071153 | 137.5 | 137.5
PRC 33524059800 | 2024-02-28 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV037555 | 44 | 181.5
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 137.5 | 319
PRC 33524117924 | 2024-04-26 | 9500 | CNST | Brockway Mechanical V#(00002116146) | Inv. R8339 | 509.86 | 828.86
GAX 33524117925 | 2024-04-26 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2568822 | 960 | 1788.86
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -275 | 1513.86
GAX 33524208900 | 2024-07-25 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2573144 | 1456.25 | 2970.11
PRC 33525236901 | 2024-08-23 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV041474 | 389.91 | 3360.02
PRC 33525114907 | 2025-04-23 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV046704 | 1346.1 | 4706.12
PRC 33525114909 | 2025-04-23 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048070 | 410.16 | 5116.28
5116.28
5116.28
|  |  |  | Totals: |  | 5116.28

## #9375.00 OPN Architects
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
OPN Architects |  |  | Vendor:00003035830
Acct. Codes-0506-335-DA24-9260 |  |  | RFP937500-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524053901 | 2024-02-22 | PO Procore | 19410 | 19410 |  |  | 19410
PO 33524053901 | 2024-04-16 | CO #1 | 4580 | 23990 |  | 0 | 23990
PRC 3352405PA3901 | 2024-05-06 | Inv. 24805000-1 |  | 23990 | 19410 | 19410 | 4580
PRC 3352405PB3901 | 2024-07-22 | Inv. 24805000-2 |  | 23990 | 4580 | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  |  |  | 23990 |  | 23990 | 0
|  | Totals: | 23990 |  | 23990 |  | 0

## #9375.00 The Samuels Group (2)
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
The Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524124803 | 2024-05-03 | PO Procore | 12391.14 | 12391.14 |  |  | 12391.14
PRC 3352412PA4803 | 2024-06-01 | Inv. 9375.01 PCA |  | 12391.14 | 1189.5 | 1189.5 | 11201.64
PRC 3352412PB4803 | 2024-07-05 | Inv. 9375.02 PCA |  | 12391.14 | 5659.38 | 6848.88 | 5542.26 | FY24
PO 33525124803 | 2024-08-16 | Roll to FY25 |  | 12391.14 |  | 6848.88 | 5542.26
PRC 3352512PC4803 | 2024-08-23 | Inv. 9375.03 PC |  | 12391.14 | 1837.16 | 8686.04 | 3705.1
PRC 3352512PD4803 | 2024-10-03 | Inv. 9375.04 PC |  | 12391.14 | 508.92 | 9194.96 | 3196.18
PRC 3352512PE4803 | 2024-11-12 | Inv. 9375.05 PC |  | 12391.14 | 2934.28 | 12129.24 | 261.9
PRC 3352512PF4803 | 2025-01-16 | Inv. 9375.06 PC FINAL | -235.9 | 12155.24 | 26 | 12155.24 | 0
|  |  |  | 12155.24 |  | 12155.24 | 0
|  |  |  | 12155.24 |  | 12155.24 | 0
|  |  |  | 12155.24 |  | 12155.24 | 0
|  |  |  | 12155.24 |  | 12155.24 | 0
|  |  |  | 12155.24 |  | 12155.24 | 0
|  | Totals: | 12155.24 |  | 12155.24 |  | 0 | FINAL
|  | CM Services | 12129.24 |  | 12129.24 |  | 0
|  | Reimbursables | 26 |  | 26 |  | 0
|  | Total: | 12155.24 |  | 12155.24 |  | 0
Invoice number 9375.01 PC used already in this project, adding an A at the end of Inv. 1 & 2

## #9375.00 OPN Architects (2)
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
OPN Architects |  |  | Vendor:00003035830
Acct. Codes-0506-335-DA24-9260 |  |  | RFP937500-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524129802 | 2024-05-08 | PO Procore | 96121 | 96121 |  |  | 96121
PRC 3352412PA9802 | 2024-06-11 | Inv. 24805000-1A |  | 96121 | 16741.54 | 16741.54 | 79379.46
PRC 3352412PB9802 | 2024-06-25 | Inv. 24805000-2A |  | 96121 | 23916.49 | 40658.03 | 55462.97 | FY24
PO 33525129802 | 2024-08-16 | Roll to FY25 | 0 | 96121 |  | 40658.03 | 55462.97
PRC 3352512PC9802 | 2024-10-03 | Inv. 24805000-3 |  | 96121 | 4182.42 | 44840.45 | 51280.55
PRC 3352512PD9802 | 2024-11-05 | Inv. 24805000-4 |  | 96121 | 17638.2 | 62478.65 | 33642.35
PRC 3352512PE9802 | 2024-12-11 | Inv. 24805000-5 |  | 96121 | 3676.63 | 66155.28 | 29965.72
PRC 3352512PF9802 | 2025-01-21 | Inv. 24805000-6 |  | 96121 | 6293.52 | 72448.8 | 23672.2
PRC 3352512PG9802 | 2025-02-11 | Inv. 24805000-7 |  | 96121 | 1420.19 | 73868.99 | 22252.01
PRC 3352512PH9802 | 2025-04-03 | Inv. 24805000-8 |  | 96121 | 2590.46 | 76459.45 | 19661.55
PRC 3352512PI9802 | 2025-05-05 | Inv. 24805000-9 |  | 96121 | 4282.19 | 80741.64 | 15379.36
PRC 3352512PJ9802 | 2025-06-03 | Inv. 24805000-11 |  | 96121 | 3378.65 | 84120.29 | 12000.71
PRC 3352512PK9802 | 2025-06-30 | Inv. 24805000-12 |  | 96121 | 2150.71 | 86271 | 9850
|  | Totals: | 96121 |  | 86271 |  | 9850
Inv. 24805000-1 was used on another tab in this project

## #9375.00 For Sure Roofing
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
For Sure Roofing |  |  | Vendor:00003081739
Acct. Codes-0506-335-DA24-9255 |  |  | RFB937500-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525236902 | 2024-08-23 | PO Procore | 34723 | 34723 |  |  | 34723
PRC 3352523PA6902 | 2024-11-15 | Inv. 9375.00-01 |  | 34723 | 32657.2 | 32657.2 | 2065.8 | 1718.8
PRC 3352523PB6902 | 2025-01-03 | Inv. 9375.00-02 |  | 34723 | 329.65 | 32986.85 | 1736.15 | 1736.15
PRC 3352523PC6902 | 2025-01-10 | Inv. 9375.00-03 - Retainage |  | 34723 | 1736.15 | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  |  |  | 34723 |  | 34723 | 0
|  | Totals: | 34723 |  | 34723 |  | 0 | FINAL

## #9375.00 Samuels Group (3)
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
Samuels Group (3) |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525284901 | 2024-10-10 | PO Procore | 9909.08 | 9909.08 |  |  | 9909.08
PRC 3352528PA4901 | 2024-11-06 | Inv. 7730.519375 CA |  | 9909.08 | 3905.84 | 3905.84 | 6003.24
PRC 3352528PB4901 | 2025-01-08 | Inv. 7730.529375 CA FINAL | -501.87 | 9407.21 | 5501.37 | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  |  |  | 9407.21 |  | 9407.21 | 0
|  | Totals: | 9407.21 |  | 9407.21 |  | 0 | FINAL
|  | CM Services | 9407.21 |  | 9407.21 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 9407.21 |  | 9407.21 |  | 0

## #9375.00 Samuels Group (4)
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
Samuels Group (4) |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525043908 | 2025-02-11 | PO Procore | 144488.47 | 144488.47 |  |  | 144488.47
PRC 3352504PA3908 | 2025-03-07 | Inv. 7758.01 CA |  | 144488.47 | 4619.23 | 4619.23 | 139869.24
PRC 3352504PB3908 | 2025-04-04 | Inv. 7758.02 CA |  | 144488.47 | 6258.24 | 10877.47 | 133611
PRC 3352504PC3908 | 2025-05-05 | Inv. 7758.03 CA |  | 144488.47 | 23775.4 | 34652.87 | 109835.6
PRC 3352504PD3908 | 2025-06-10 | Inv. 7758.04 CA |  | 144488.47 | 15654.22 | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  |  |  | 144488.47 |  | 50307.09 | 94181.38
|  | Totals: | 144488.47 |  | 50307.09 |  | 94181.38
|  | CM Services | 114927.32 |  | 34295.09 |  | 80632.23
|  | Reimbursables | 1000 |  | 12 |  | 988
|  | Fee | 28561.15 |  | 16000 |  | 12561.15
|  | Total: | 144488.47 |  | 50307.09 |  | 94181.38

## #9375.00 Azcon Inc
DOC 5JD DM Bldgs 65-66 Renovation
Project # 9375.00
Program code 937500 |  |  | Major Program 4B01
Azcon Inc |  |  | Vendor:00002122784
Acct. Codes-0506-335-DA24-9255 |  |  | RFB937500-02
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525055904 | 2025-02-24 | PO Procore | 571223 | 571223 |  |  | 571223
PO 33525055904 | 2025-05-21 | CO #1 | 19993.1 | 591216.1 |  | 0 | 591216.1
PRC 3352505PA5904 | 2025-06-10 | Inv. 9375.00-01 |  | 591216.1 | 83291.58 | 83291.58 | 507924.52 | 4383.78
PO 33525055904 | 2025-06-25 | CO #2 | 42419.65 | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  |  |  | 633635.75 |  | 83291.58 | 550344.17
|  | Totals: | 633635.75 |  | 83291.58 |  | 550344.17
|  | Demoliton & Remodel | 558000 |  | 83291.58 |  | 474708.42
|  | Demolition & Removal of Windows | 13223 |  |  |  | 13223
|  | CO #1 | 19993.1 |  |  |  | 19993.1
|  | CO #2 | 42419.65 |  |  |  | 42419.65
|  | Total: | 633635.75 |  | 83291.58 |  | 550344.17

## RECAP #9377.00
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
| Program code 937700 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 226175.14
C | McGough Construction |  | 18724.37 | 18724.37 | 0
C | PM TIME |  | 13013.34 | 13013.34 | 0
C | Misc. |  | 1955.39 | 1955.39 | 0
C | West Plains Engineering |  | 5000 | 5000 | 0
C | SystemWorks |  | 5185 | 5185 | 0
C | West Plains Engineering (2) |  | 20000 | 20000 | 0
C | Colony HVAC |  | 133665 | 133665 | 0
C | McGough Construction (2) |  | 28632.04 | 28632.04 | 0
| Total Project Cost | 226175.14 | 226175.14 | 226175.14 | 0 | 0
Closed 05/16/25

## #9377.00 Funds Rec'd
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524325101 | 2023-11-21 | 50000 | 50000
|  |  | MOU Amendment #1 | IET 23812Y24030 | 2024-06-10 | 257000 | 257000
|  |  | Returning FY24 Funds to Agency | IET 33524227913 | 2024-08-14 | -278643.33 | -278643.33
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227913A | 2024-08-20 | -2723.04 | -2723.04
|  |  | Received FY25 Funds From Agency | IET 23812Y25003 | 2024-09-10 | 281366.37 | 281366.37
|  |  | Returning Funds to Agency | IET 33525136900 | 2025-05-16 | -80824.86 | -80824.86
| Total Requested | 0 | Total Transferred |  |  | 226175.14 | 226175.14

## #9377.00 McGough Construction
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524331900 | 2023-11-27 | PO Procre | 7012.95 | 7012.95 |  |  | 7012.95
PRC 3352433PA1900 | 2023-12-13 | Inv. 101174.002-PC01 |  | 7012.95 | 2050.55 | 2050.55 | 4962.4
PRC 3352433PB1900 | 2024-01-17 | Inv. 101174.002-PC02 |  | 7012.95 | 112.81 | 2163.36 | 4849.59
PRC 3352433PC1900 | 2024-03-18 | Inv. 101174.002-PC03 |  | 7012.95 | 1025.66 | 3189.02 | 3823.93
PRC 3352433PD1900 | 2024-04-10 | Inv. 101174.002-PC04 |  | 7012.95 | 1059.04 | 4248.06 | 2764.89
PO 33524331900 | 2024-05-02 | CO #1 | 12627.22 | 19640.17 |  | 4248.06 | 15392.11
PRC 3352433PE1900 | 2024-05-13 | Inv. 101174.002-PC05 |  | 19640.17 | 567.51 | 4815.57 | 14824.6
PRC 3352433PF1900 | 2024-06-11 | Inv. 101174.002-PC06 |  | 19640.17 | 1459.12 | 6274.69 | 13365.48
PRC 3352433PG1900 | 2024-07-08 | Inv. 101174.002-PC07 |  | 19640.17 | 1297.9 | 7572.59 | 12067.58 | FY24
PO 33525331900 | 2024-08-28 | Roll to FY25 |  | 19640.17 |  | 7572.59 | 12067.58
PRC 3352533PH1900 | 2024-09-11 | Inv. 101174.002-PC08 |  | 19640.17 | 1345.17 | 8917.76 | 10722.41
PRC 3352533PI1900 | 2024-09-13 | Inv. 101174.002-PC09 |  | 19640.17 | 2126.16 | 11043.92 | 8596.25
PRC 3352533PJ1900 | 2024-10-14 | Inv. 101174.002-PC10 |  | 19640.17 | 3834.54 | 14878.46 | 4761.71
PRC 3352533PK1900 | 2024-11-18 | Inv. 101174.002-PC11-Final | -915.8 | 18724.37 | 3845.91 | 18724.37 | 0
|  |  |  | 18724.37 |  | 18724.37 | 0
|  |  |  | 18724.37 |  | 18724.37 | 0
|  | Totals: | 18724.37 |  | 18724.37 |  | 0 | FINAL
|  | CM Services | 6572.95 |  | 6572.95 |  | 0
|  | Reimbursables | 440 |  | 440 |  | 0
|  | CO #1 | 11711.42 |  | 11711.42 |  | 0
|  | Total: | 18724.37 |  | 18724.37 |  | 0

## #9377.00 PM TIME
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: E2AS
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 13013.34 | 13013.34 |  |  | 13013.34
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 13013.34 | 91.92 | 91.92 | 12921.42
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 13013.34 | 695.4 | 787.32 | 12226.02
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 13013.34 | 6.52 | 793.84 | 12219.5
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 13013.34 | 46.6 | 840.44 | 12172.9
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 13013.34 | 16.53 | 856.97 | 12156.37
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 13013.34 | 146.3 | 1003.27 | 12010.07
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 13013.34 | 78.68 | 1081.95 | 11931.39
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 13013.34 | 397.5 | 1479.45 | 11533.89
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 13013.34 | 48.13 | 1527.58 | 11485.76
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 13013.34 | 368.4 | 1895.98 | 11117.36
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 13013.34 | 50.9 | 1946.88 | 11066.46
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 13013.34 | 452.5 | 2399.38 | 10613.96
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 13013.34 | 175.03 | 2574.41 | 10438.93
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 13013.34 | 1446.1 | 4020.51 | 8992.83
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 13013.34 | 37.03 | 4057.54 | 8955.8
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 13013.34 | 338.5 | 4396.04 | 8617.3
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 13013.34 | 114.62 | 4510.66 | 8502.68
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 13013.34 | 1246.9 | 5757.56 | 7255.78
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 13013.34 | 161.82 | 5919.38 | 7093.96
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 13013.34 | 821.3 | 6740.68 | 6272.66
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 13013.34 | 118.33 | 6859.01 | 6154.33
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 13013.34 | 1051.4 | 7910.41 | 5102.93
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13013.34 | 217.39 | 8127.8 | 4885.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13013.34 | 1449.1 | 9576.9 | 3436.44
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13013.34 | 56.36 | 9633.26 | 3380.08
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13013.34 | 374.8 | 10008.06 | 3005.28
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13013.34 | 27.01 | 10035.07 | 2978.27
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13013.34 | 272.5 | 10307.57 | 2705.77
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13013.34 | 31.5 | 10339.07 | 2674.27
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13013.34 | 334 | 10673.07 | 2340.27
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13013.34 | 261.05 | 10934.12 | 2079.22
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13013.34 | 1129 | 12063.12 | 950.22
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13013.34 | 65.94 | 12129.06 | 884.28
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13013.34 | 471.5 | 12600.56 | 412.78
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13013.34 | 52.58 | 12653.14 | 360.2
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13013.34 | 360.2 | 13013.34 | -2.5011e-12
[5 empty] | 13013.34 |  | 13013.34 | -2.5011e-12
|  |  | Totals: | 13013.34 |  | 13013.34 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Changes $Joni Kleene, Jennifer 11:59 AM (33 minutes ago) to me, Scott For MM22 9244.00, please increase the PM Time budget by $4,000.00 For MM23 9268.01, please increase the PM Time budget by $8,800.00 For DA22 9216.00, please increase the PM Time budget by $4,000.00 For DA23 9293.00, please increase the PM Time budget by $3,500.00 For DA24 9377.00, please increase the PM Time budget by $4,400.00 From: Kleene, Jennifer <jennifer.kleene@iowa.gov> Date: Tue, Nov 12, 2024 at 7:48 AM Subject: Re: October PM Time Posting Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Sorry about that! Please increase the DAS Cost budgets as follows: DA24 9377.00 Increase budget by $4,400.00 DA24 9378.00 Increase budget by $298.43 DA25 9245.01 Create a budget for $14,370.00 MM23 9279.20 Increase budget by $2200.00

## #9377.00 Misc
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525255907 | 2024-09-11 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2596426 | 1595 | 1595
PRC 33525304901 | 2024-10-30 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1140 | 360.39 | 1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
1955.39
|  |  |  | Totals: |  | 1955.39

## #9377.00 West Plains
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
West Plains Engineering |  |  | Vendor: 00003073483
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524331803 | 2023-11-27 | PO Procre | 5000 | 5000 |  |  | 5000
PRC 3352433PA1803 | 2024-04-03 | Inv. 9377.00-01 |  | 5000 | 5000 | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  |  |  | 5000 |  | 5000 | 0
|  | Totals: | 5000 |  | 5000 |  | 0 | FINAL

## #9377.00 SystemWorks
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524010905 | 2024-01-10 | PO Procore | 6750 | 6750 |  |  | 6750
PRC 3352401PA0905 | 2024-04-23 | Inv. 11639-Final | -1565 | 5185 | 5185 | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  |  |  | 5185 |  | 5185 | 0
|  | Totals: | 5185 |  | 5185 |  | 0 | FINAL

## #9377.00 West Plains Engineerin
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
Western Plains Engineering |  |  | Vendor: 00003073483
Acct. Codes-0506-335-DA24-9260 |  |  | RPF937700-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524165905 | 2024-06-13 | PO Procre | 20000 | 20000 |  |  | 20000
PRC 3352416PA5905 | 2024-07-08 | Inv. 9377.00-01A* |  | 20000 | 3480 | 3480 | 16520 | FY24
PO 33525165905 | 2024-08-28 | Roll to FY25 |  | 20000 |  | 3480 | 16520
PRC 3352516PB5905 | 2024-09-11 | Inv. 9377.00-02A* |  | 20000 | 8270 | 11750 | 8250
PRC 3352516PC5905 | 2024-10-04 | Inv. 9377.00-03 |  | 20000 | 2550 | 14300 | 5700
PRC 3352516PD5905 | 2024-11-14 | Inv. 9377.00-04 |  | 20000 | 1200 | 15500 | 4500
PRC 3352516PE5905 | 2024-12-06 | Inv. 9377.00-05 |  | 20000 | 900 | 16400 | 3600
PRC 3352516PF5905 | 2025-01-15 | Inv. 9377.00-06 |  | 20000 | 900 | 17300 | 2700
PRC 3352516PG5905 | 2025-03-13 | Inv. 9377.00-07 |  | 20000 | 1800 | 19100 | 900
PRC 3352516PH5905 | 2025-04-25 | Inv. 9377.00-08 |  | 20000 | 900 | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  |  |  | 20000 |  | 20000 | 0
|  | Totals: | 20000 |  | 20000 |  | 0 | FINAL
|  | Design Development | 5800 |  | 5800 |  | 0
|  | Construction Socuments | 8500 |  | 8500 |  | 0
|  | Bid/Negotiation | 1200 |  | 1200 |  | 0
|  | Construction Phase | 4500 |  | 4500 |  | 0
|  | Total: | 20000 |  | 20000 |  | 0
*Invoice format 9377.00-01 already used by this vendor in another tab

## #9377.00 Colony HVAC
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
Colony HVAC |  |  | Vendor: 00002110708
Acct. Codes-0506-335-DA24-9255 |  |  | RPB 937700-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525289901 | 2024-10-15 | PO Procre | 133350 | 133350 |  |  | 133350
PRC 3352528PA9901 | 2025-01-24 | Inv. 9377.00-01 |  | 133350 | 45372.47 | 45372.47 | 87977.53 | 2388.03
PO 33525289901 | 2025-03-07 | CO #1 | 315 | 133665 |  | 45372.47 | 88292.53
PRC 3352528PB9901 | 2025-03-27 | Inv. 9377.00-02 |  | 133665 | 80041.77 | 125414.24 | 8250.76 | 6600.76
PRC 3352528PC9901 | 2025-04-11 | Inv. 9377.00-03 |  | 133665 | 1567.5 | 126981.74 | 6683.26 | 6683.26
PRC 3352528PD9901 | 2025-04-24 | Inv. 9377.00-04 Retainage |  | 133665 | 6683.26 | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  |  |  | 133665 |  | 133665 | 0
|  | Totals: | 133665 |  | 133665 |  | 0 | FINAL

## #9377.00 McGough Constructi (2)
DOC 6JD IC Hope-Stratton HVAC Evaluation
Project # 9377.00
Program code 937700 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525292900 | 2024-10-18 | PO Procre | 37693.45 | 37693.45 |  |  | 37693.45
PRC 3352529PA2900 | 2024-12-18 | Inv. 101174.002-CA01 |  | 37693.45 | 7677.64 | 7677.64 | 30015.81
PRC 3352529PB2900 | 2025-01-14 | Inv. 101174.002-CA02 |  | 37693.45 | 5466.07 | 13143.71 | 24549.74
PRC 3352529PC2900 | 2025-02-18 | Inv. 101174.002-CA03 |  | 37693.45 | 5334.19 | 18477.9 | 19215.55
PRC 3352529PD2900 | 2025-03-24 | Inv. 101174.002-CA04 |  | 37693.45 | 5204.1 | 23682 | 14011.45
PRC 3352529PE2900 | 2025-04-11 | Inv. 101174.002-CA05 |  | 37693.45 | 4591.46 | 28273.46 | 9419.99
PRC 3352529PF2900 | 2025-05-12 | Inv. 101174.002-CA06 - Final | -9061.41 | 28632.04 | 358.58 | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  |  |  | 28632.04 |  | 28632.04 | 0
|  | Totals: | 28632.04 |  | 28632.04 |  | 0 | FINAL
|  | CM Services | 26937.04 |  | 26937.04 |  | 0
|  | Reimbursables | 1695 |  | 1695 |  | 0
|  | Total: | 28632.04 |  | 28632.04 |  | 0

## RECAP #9378.00
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
| Program code 937800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 270558.29
C | Horizon Architecture |  | 14900 | 14900 | 0
C | PM TIME |  | 10098.43 | 10098.43 | 0
C | Misc. |  | 2196.37 | 2196.37 | 0
C | McGough Construction |  | 13151.24 | 13151.24 | 0
C | McGough Construction CA |  | 20093.46 | 20093.46 | 0
C | Garling Construction |  | 207555.79 | 207555.79 | 0
C | SystemWorks |  | 2563 | 2563 | 0
| Total Project Cost | 270558.29 | 270558.29 | 270558.29 | 0 | 0
Closed 11/13/24

## #9378.00 Funds Rec'd
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524325101 | 2023-11-21 | 50000 | 50000
|  |  | MOU Amend #1 | CR 00524079101 | 2024-03-19 | 280000 | 280000
|  |  | Return Funds to Agency-closing project | IET 33525318905 | 2024-11-13 | -59441.71 | -59441.71
| Total Requested | 0 | Total Transferred |  |  | 270558.29 | 270558.29

## #9378.00 Horizon Architecture
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
Horizon Architecture |  |  | Vendor:00003108847
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524331800 | 2023-11-27 | PO Procore | 14900 | 14900 |  |  | 14900
PRC 3352433PA1800 | 2024-01-12 | Inv. 9378.00-01 |  | 14900 | 8675 | 8675 | 6225
PRC 3352433PB1800 | 2024-04-12 | Inv. 9378.00-02 |  | 14900 | 1725 | 10400 | 4500
PRC 3352433PC1800 | 2024-05-07 | Inv. 9378.00-03 |  | 14900 | 1125 | 11525 | 3375
PRC 3352433PD1800 | 2024-07-03 | Inv. 9378.00-04 |  | 14900 | 1125 | 12650 | 2250 | FY24
PO 33525331800 | 2024-08-16 | Roll to FY25 |  | 14900 |  | 12650 | 2250
PRC 3352533PE1800 | 2024-08-23 | Inv. 9378.00-05 |  | 14900 | 1800 | 14450 | 450
PRC 3352533PF1800 | 2024-09-30 | Inv. 9378.00-06 - Final |  | 14900 | 450 | 14900 | 0
|  |  |  | 14900 |  | 14900 | 0
|  |  |  | 14900 |  | 14900 | 0
|  |  |  | 14900 |  | 14900 | 0
|  |  |  | 14900 |  | 14900 | 0
|  |  |  | 14900 |  | 14900 | 0
|  | Totals: | 14900 |  | 14900 |  | 0 | FINAL
|  | Design Development | 4400 |  | 4400 |  | 0
|  | Construction Documents | 4500 |  | 4500 |  | 0
|  | Bid/Negotiation Phase | 1500 |  | 1500 |  | 0
|  | Construction Phase | 4500 |  | 4500 |  | 0
|  | Total: | 14900 |  | 14900 |  | 0

## #9378.00 PM TIME
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: E2AT
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10098.43 | 10098.43 |  |  | 10098.43
IET DAS202405115300001 | 2023-12-07 | 2507 | Finance Support for November 1-30, 2023 |  | 10098.43 | 127.41 | 127.41 | 9971.02
IET DAS202405115300001 | 2023-12-07 | 9500 | DAS Services for November 1-30, 2023 |  | 10098.43 | 962.3 | 1089.71 | 9008.72
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 10098.43 | 70.08 | 1159.79 | 8938.64
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 10098.43 | 512.4 | 1672.19 | 8426.24
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 10098.43 | 76.8 | 1748.99 | 8349.44
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 10098.43 | 679.1 | 2428.09 | 7670.34
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 10098.43 | 314.85 | 2742.94 | 7355.49
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 10098.43 | 1587.2 | 4330.14 | 5768.29
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 10098.43 | 127.95 | 4458.09 | 5640.34
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 10098.43 | 968.2 | 5426.29 | 4672.14
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 10098.43 | 56.06 | 5482.35 | 4616.08
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 10098.43 | 497.3 | 5979.65 | 4118.78
IET DAS202411115300001 | 2024-06-10 |  | Finance Support for May 1-31 2024 |  | 10098.43 | 38.1 | 6017.75 | 4080.68
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 10098.43 | 316.3 | 6334.05 | 3764.38
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 10098.43 | 47.61 | 6381.66 | 3716.77
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 10098.43 | 435.7 | 6817.36 | 3281.07
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 10098.43 | 39.14 | 6856.5 | 3241.93
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 10098.43 | 431.1 | 7287.6 | 2810.83
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 10098.43 | 304.22 | 7591.82 | 2506.61
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 10098.43 | 1548.1 | 9139.92 | 958.51
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 10098.43 | 55.79 | 9195.71 | 902.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 10098.43 | 497.8 | 9693.51 | 404.92
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10098.43 | 52.42 | 9745.93 | 352.5
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10098.43 | 352.5 | 10098.43 | 1.5916e-12
[5 empty] | 10098.43 |  | 10098.43 | 1.5916e-12
|  |  | Totals: | 10098.43 |  | 10098.43 |  | 0
Note on E9: Huggins, Joni [DAS]: DAS Cost Budget Increases $Joni Kleene, Jennifer 2:34 PM (3 minutes ago) to me Please make the following DAS Cost/PM Time budget increases: Increase MM22 9277.00 by $1,870.00. Increase DA24 9378.00 by $1,000.00. Regards, Jennifer From: Kleene, Jennifer <jennifer.kleene@iowa.gov> Date: Tue, Nov 12, 2024 at 7:48 AM Subject: Re: October PM Time Posting Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Sorry about that! Please increase the DAS Cost budgets as follows: DA24 9377.00 Increase budget by $4,400.00 DA24 9378.00 Increase budget by $298.43 DA25 9245.01 Create a budget for $14,370.00 MM23 9279.20 Increase budget by $2200.00

## #9378.00 Misc
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524039800 | 2024-02-08 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2551540 | 1542.5 | 1542.5
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 357.5 | 1900
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 165 | 2065
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -522.5 | 1542.5
PRC 33524207900 | 2024-07-25 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCR3255 | 653.87 | 2196.37
2196.37
2196.37
2196.37
2196.37
2196.37
2196.37
2196.37
|  |  |  | Totals: |  | 2196.37

## #9378.00 McGough Construction
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor:00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524331801 | 2023-11-27 | PO Procore | 13693.32 | 13693.32 |  |  | 13693.32
PRC 3352433PA1801 | 2023-12-13 | Inv. 101174.003-PC01 |  | 13693.32 | 1685.21 | 1685.21 | 12008.11
PRC 3352433PB1801 | 2024-01-17 | Inv. 101174.003-PC02 |  | 13693.32 | 1742.81 | 3428.02 | 10265.3
PRC 3352433PC1801 | 2024-02-13 | Inv. 101174.003-PC03 |  | 13693.32 | 3379.14 | 6807.16 | 6886.16
PRC 3352433PD1801 | 2024-03-18 | Inv. 101174.003-PC04 |  | 13693.32 | 4296.22 | 11103.38 | 2589.94
PRC 3352433PE1801 | 2024-04-10 | Inv. 101174.003-PC05 FINAL | -542.08 | 13151.24 | 2047.86 | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  |  |  | 13151.24 |  | 13151.24 | 0
|  | Totals: | 13151.24 |  | 13151.24 |  | 0 | FINAL
|  | CM Services | 12756.24 |  | 12756.24 |  | 0
|  | Reimbursables | 395 |  | 395 |  | 0
|  | Total: | 13151.24 |  | 13151.24 |  | 0

## #9378.00 McGough Constructi (2)
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
McGough Construction CA |  |  | Vendor:00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524080803 | 2024-03-20 | PO Procore | 39137.09 | 39137.09 |  |  | 39137.09
PRC 3352408PA0803 | 2024-05-13 | Inv. 101174.003-CA01 |  | 39137.09 | 2496.22 | 2496.22 | 36640.87
PRC 3352408PB0803 | 2024-06-12 | Inv. 101174.003-CA02 |  | 39137.09 | 2009.4 | 4505.62 | 34631.47
PRC 3352408PC0803 | 2024-07-08 | Inv. 101174.003-CA03 |  | 39137.09 | 7295.72 | 11801.34 | 27335.75 | FY24
PO 33525080803 | 2024-08-16 | Roll to FY25 |  | 39137.09 |  | 11801.34 | 27335.75
PRC 3352508PD0803 | 2024-08-19 | Inv. 101174.003-CA04 |  | 39137.09 | 4864.53 | 16665.87 | 22471.22
PRC 3352508PE0803 | 2024-09-12 | Inv. 101174.003-CA05 |  | 39137.09 | 2491.72 | 19157.59 | 19979.5
PRC 3352508PF0803 | 2024-10-14 | Inv. 101174.003-CA06 - Final | -19043.63 | 20093.46 | 935.87 | 20093.46 | 0
|  |  |  | 20093.46 |  | 20093.46 | 0
|  |  |  | 20093.46 |  | 20093.46 | 0
|  |  |  | 20093.46 |  | 20093.46 | 0
|  |  |  | 20093.46 |  | 20093.46 | 0
|  |  |  | 20093.46 |  | 20093.46 | 0
|  | Totals: | 20093.46 |  | 20093.46 |  | 0 | FINAL
|  | CM Services | 18843.46 |  | 18843.46 |  | 0
|  | Reimbursables | 1250 |  | 1250 |  | 0
|  | Total: | 20093.46 |  | 20093.46 |  | 0

## #9378.00 Garling Construction
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
Garling Construction Inc. |  |  | Vendor:00002112990
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 937800-01
Project Manager - Jennifer K. |  |  | Activity code:BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524080812 | 2024-03-20 | PO Procore | 215200 | 215200 |  |  | 215200 |  |  | z
PO 33524080812 | 2024-05-03 | CO #1 | -5095.36 | 210104.64 |  | 0 | 210104.64
PRC 3352408PA0812 | 2024-05-16 | Inv. 3144 |  | 210104.64 | 5890 | 5890 | 204214.64 | 310
PRC 3352408PB0812 | 2024-06-11 | Inv. 3184 |  | 210104.64 | 26932.5 | 32822.5 | 177282.14 | 1727.5
PO 33524080812 | 2024-06-24 | CO #2 | 2451.15 | 212555.79 |  | 32822.5 | 179733.29
PRC 3352408PC0812 | 2024-07-08 | Inv. 3203 |  | 212555.79 | 103625.61 | 136448.11 | 76107.68 | 7181.48 | FY24
PO 33525080812 | 2024-08-16 | Roll to FY25 |  | 212555.79 |  | 136448.11 | 76107.68
PRC 3352508PD0812 | 2024-08-19 | Inv. 3235 |  | 212555.79 | 58685.49 | 195133.6 | 17422.19 | 10270.19
PO 33525080812 | 2024-08-22 | CO #3 | -5000 | 207555.79 |  | 195133.6 | 12422.19
PRC 3352508PE0812 | 2024-09-13 | Inv. 3277 |  | 207555.79 | 2044.4 | 197178 | 10377.79 | 10377.79
PRC 3352508PF0812 | 2024-09-19 | Inv. 3284-Retainage |  | 207555.79 | 10377.79 | 207555.79 | 0
|  |  |  | 207555.79 |  | 207555.79 | 0
|  |  |  | 207555.79 |  | 207555.79 | 0
|  | Totals: | 207555.79 |  | 207555.79 |  | 0

## #9378.00 SystemWorks
DOC 6JD CR Hinzman Window Replacement
Project # 9378.00
Program code 937800 |  |  | Major Program 4B01
SystemWorks |  |  | Vendor:00002144353
Acct. Codes-0506-335-DA24-9255 |  |  | MA00521396B
Project Manager - Jennifer K. |  |  | Activity code: CNST
`
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524115920 | 2024-04-25 | PO Procore | 4046 | 4046 |  |  | 4046
PRC 3352411PA5920 | 2024-08-06 | Inv. 11896 |  | 4046 | 2023 | 2023 | 2023 | FY24
PO 33525115920A | 2024-08-16 | Roll to FY25 |  | 4046 |  | 2023 | 2023
PRC 3352511PB5920A | 2024-08-23 | Inv. 11906-Final | -1483 | 2563 | 540 | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  |  |  | 2563 |  | 2563 | 0
|  | Totals: | 2563 |  | 2563 |  | 0 | FINAL

## RECAP #9381.00
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
| Program code 938100 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 373361.99
C | Samuels Group #150CA |  | 41861.07 | 41861.07 | 0
C | PM TIME |  | 12238.17 | 12238.17 | 0
C | Misc. |  | 6300.18 | 6300.18 | 0
C | Downs Electric Inc. |  | 307562.57 | 307562.57 | 0
C | Morrissey Engineering |  | 5400 | 5400 | 0
| Total Project Cost | 373361.99 | 373361.99 | 373361.99 | 0 | 0
Closed 01/13/25

## #9381.00 Funds Rec'd
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524353101 | 2023-12-19 | 255000 | 255000
|  |  | MOU Amendment #1 | CR 00524107101 | 2024-04-16 | 160000 | 160000
|  |  | Returning funds to Agency-Closing Project | IET 33525013901 | 2025-01-13 | -41638.01 | -41638.01
| Total Requested | 0 | Total Transferred |  |  | 373361.99 | 373361.99

## #9381.00 Samuels Group #150CA
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  | Major Program 4E02
Samuels Group #150CA |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524355802 | 2023-12-21 | PO Procore | 42447.28 | 42447.28 |  |  | 42447.28
PRC 3352435PA5802 | 2024-01-08 | Inv. 7662.01938100 |  | 42447.28 | 1536.18 | 1536.18 | 40911.1
PRC 3352435PB5802 | 2024-02-12 | Inv. 7662.02938100 |  | 42447.28 | 2655.76 | 4191.94 | 38255.34
PRC 3352435PC5802 | 2024-03-06 | Inv. 7662.03938100 |  | 42447.28 | 4168.45 | 8360.39 | 34086.89
PRC 3352435PD5802 | 2024-04-15 | Inv. 7662.04938100 |  | 42447.28 | 2334.08 | 10694.47 | 31752.81
PRC 3352435PE5802 | 2024-05-07 | Inv. 7662.05938100 |  | 42447.28 | 1560.02 | 12254.49 | 30192.79
PRC 3352435PF5802 | 2024-06-04 | Inv. 7662.06938100 |  | 42447.28 | 1719.4 | 13973.89 | 28473.39
PRC 3352435PG5802 | 2024-07-11 | Inv. 7662.07938100 |  | 42447.28 | 6893.33 | 20867.22 | 21580.06 | FY24
PO 33525355802 | 2024-08-16 | Roll to FY25 |  | 42447.28 |  | 20867.22 | 21580.06
PRC 3352535PH5802 | 2024-09-04 | Inv. 7662.08938100 |  | 42447.28 | 10615.71 | 31482.93 | 10964.35
PRC 3352535PI5802 | 2024-09-13 | Inv. 7662.09938100 |  | 42447.28 | 5293.49 | 36776.42 | 5670.86
PRC 3352535PJ5802 | 2024-09-27 | Inv. 7662.10938100-Final | -586.21 | 41861.07 | 5084.65 | 41861.07 | 0
|  |  |  | 41861.07 |  | 41861.07 | 0
|  | Totals: | 41861.07 |  | 41861.07 |  | 0 | FINAL
|  | CM Services | 39404.68 |  | 39404.68 |  | 0
|  | Reimbursables | 2456.39 |  | 2456.39 |  | 0
|  | Total: | 41861.07 |  | 41861.07 |  | 0

## #9381.00 PM TIME
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS E2B1
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 12238.17 | 12238.17 |  |  | 12238.17
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 12238.17 | 123.2 | 123.2 | 12114.97
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 12238.17 | 904.2 | 1027.4 | 11210.77
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 12238.17 | 140.11 | 1167.51 | 11070.66
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 12238.17 | 1233.2 | 2400.71 | 9837.46
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 12238.17 | 479.73 | 2880.44 | 9357.73
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12238.17 | 2419.8 | 5300.24 | 6937.93
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 12238.17 | 127.27 | 5427.51 | 6810.66
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12238.17 | 966 | 6393.51 | 5844.66
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 12238.17 | 80.88 | 6474.39 | 5763.78
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 12238.17 | 718.1 | 7192.49 | 5045.68
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 12238.17 | 45.64 | 7238.13 | 5000.04
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12238.17 | 377.5 | 7615.63 | 4622.54
IET DAS202412115300001 | 2024-07-10 |  | Finance Support for June 1-30 2024 |  | 12238.17 | 23.81 | 7639.44 | 4598.73
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12238.17 | 219.5 | 7858.94 | 4379.23
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 12238.17 | 110.67 | 7969.61 | 4268.56
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12238.17 | 1206.5 | 9176.11 | 3062.06
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12238.17 | 119.57 | 9295.68 | 2942.49
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12238.17 | 605.6 | 9901.28 | 2336.89
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12238.17 | 98.75 | 10000.03 | 2238.14
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12238.17 | 879.8 | 10879.83 | 1358.34
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12238.17 | 115.23 | 10995.06 | 1243.11
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12238.17 | 770.6 | 11765.66 | 472.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12238.17 | 43.31 | 11808.97 | 429.2
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12238.17 | 429.2 | 12238.17 | -4.2064e-12
[5 empty] | 12238.17 |  | 12238.17 | -4.2064e-12
|  |  | Totals: | 12238.17 |  | 12238.17 |  | 0
Note on E9: Jurgenson, John [DAS]: 9381.00 DOE ISD Elementary School & Out Reach Fire Alarm - PM Time Budget $John Elliott, Jennie 2:48 PM (5 minutes ago) to me Please establish PM Time budget for Project 9381.00 in DA 24 for $9,000.00 Thank you, Jennie Elliott Elliott, Jennie Thu, Aug 1, 8:43 AM (4 days ago) to me Please Increase PM Time on the following projects. 9363.00 - Please increase to a total "Contracted" of $12,000 9381.00 - Please increase to a total "Contracted" of $14,000 9381.00 -DOE ISD Elem School and Out Reach Fire Alarm - Close out External $Joni Elliott, Jennie Sat, Jan 11, 1:36 PM (2 days ago) to me, Scott, Mark Please reduce PM time to $12,238.17 and close out project 9381.00 in DA 24. This should return $41,638.01 to the agency. Thank you, Jennie Elliott

## #9381.00 Misc
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 165 | 165
GAX 33524078906 | 2024-03-18 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2559036 | 1318.75 | 1483.75
GAX 33524078802 | 2024-03-18 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2556335 | 1360 | 2843.75
GAX 33524079809 | 2024-03-19 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL435 | 278.71 | 3122.46
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 110 | 3232.46
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -275 | 2957.46
CDE 33525260906 | 2024-09-16 | 9500 | CNST | Move expense from 9363.00 to 9381.00 | Inv. DES-I002095 | 3342.72 | 6300.18
6300.18
6300.18
6300.18
6300.18
6300.18
|  |  |  | Totals: |  | 6300.18

## #9381.00 Downs Electric Inc.
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  | Major Program 4E02
Downs Electric Inc. |  |  | Vendor:00003216356
Acct. Codes-0506-335-DA24-9255 |  |  | RFB938100-01
Project Manager - Jennie E. |  |  | Activity code:BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33524108801 | 2024-04-11 | PO Procore | 303300 | 303300 |  |  | 303300
PRC 3352410PA8801 | 2024-06-01 | Inv. 9381.00-01 |  | 303300 | 98454.2 | 98454.2 | 204845.8 | 5181.8
PRC 3352410PB8801 | 2024-07-11 | Inv. 9381.00-02 |  | 303300 | 59375 | 157829.2 | 145470.8 | 8306.8
PO 33524108801 | 2024-07-16 | CO #1 | 3661.91 | 306961.91 |  | 157829.2 | 149132.71 |  | FY24
PO 33525108801 | 2024-08-16 | Roll to FY25 |  | 306961.91 |  | 157829.2 | 149132.71
PRC 3352510PC8801 | 2024-08-29 | Inv. 9381.00-03 |  | 306961.91 | 130903.27 | 288732.47 | 18229.44 | 15196.44
PO 33525108801 | 2024-09-04 | CO #2 | 600.66 | 307562.57 |  | 288732.47 | 18830.1
PRC 3352510PD8801 | 2024-09-16 | Inv. 9381.00-04 |  | 307562.57 | 570.62 | 289303.09 | 18259.48 | 15226.48
PRC 3352510PE8801 | 2024-09-26 | Inv. 9381.00-05 |  | 307562.57 | 2881.35 | 292184.44 | 15378.13 | 15378.13
PRC 3352510PF8801 | 2024-09-27 | Inv. 9381.00-06 -Retainage |  | 307562.57 | 15378.13 | 307562.57 | 0
|  |  |  | 307562.57 |  | 307562.57 | 0
|  |  |  | 307562.57 |  | 307562.57 | 0
|  |  |  | 307562.57 |  | 307562.57 | 0
|  | Totals: | 307562.57 |  | 307562.57 |  | 0 | FINAL

## #9381.00 Morrissey Engineering
DOE ISD Elementary School and Out Reach Fire Alarm
Project # 9381.00
Program code 938100 |  |  | Major Program 4E02
Morrissey Engineering |  |  | Vendor: 00003214256
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance |  | `
PO 33524117914 | 2024-04-26 | PO Procore | 5400 | 5400 |  |  | 5400
PRC 3352411PA7914 | 2024-06-01 | Inv. 24533 |  | 5400 | 1012.5 | 1012.5 | 4387.5
PRC 3352411PB7914 | 2024-07-11 | Inv. 24722 |  | 5400 | 1012.5 | 2025 | 3375 | FY24
PO 33525117914 | 2024-08-16 | Roll to FY25 |  | 5400 |  | 2025 | 3375
PRC 3352511PC7914 | 2024-08-29 | Inv. 25030 |  | 5400 | 1012.5 | 3037.5 | 2362.5
PRC 3352511PD7914 | 2024-09-12 | Inv. 25130 |  | 5400 | 2160 | 5197.5 | 202.5
PRC 3352511PE7914 | 2024-09-26 | Inv. 25251-Final |  | 5400 | 202.5 | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  | Totals: | 5400 |  | 5400 |  | 0 | FINAL

## RECAP #9382.00
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
| Program code 938200 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 29211.02
C | Terracon Consultants |  | 4500 | 4500 | 0
C | PM TIME |  | 2653.01 | 2653.01 | 0
C | Misc. |  | 0 | 0 | 0
C | Controlled Asbestos |  | 22058.01 | 22058.01 | 0
| Total Project Cost | 29211.02 | 29211.02 | 29211.02 | 0 | 0
Closed 07/10/2024

## #9382.00 Funds Rec'd
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
Program code 938200 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 2462412117 | 2023-12-18 | 10000 | 10000
|  |  | MOU Amendment #1 | IET 2462403069 | 2024-03-08 | 25000 | 25000
|  |  | MOU Amendment #2 | IET 2462405148 | 2024-05-20 | 3000 | 3000
|  |  | Returning Funds to Agency | IET 33524192913 | 2024-07-10 | -8788.98 | -8788.98
| Total Requested | 0 | Total Transferred |  |  | 29211.02 | 29211.02

## #9382.00 Terracon Consultants
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
Program code 938200 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116512
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524005902 | 2024-01-05 | PO Procore | 4500 | 4500 |  |  | 4500
PRC 3352400PA5902 | 2024-02-23 | Inv. TK75180 |  | 4500 | 4500 | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  |  |  | 4500 |  | 4500 | 0
|  | Totals: | 4500 |  | 4500 |  | 0

## #9382.00 PM TIME
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
Program code 938200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A. |  |  |  | eDAS 908T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2653.01 | 2653.01 |  |  | 2653.01
IET DAS202406115300001 | 2024-01-08 | 2507 | Finance Support for December 1-31, 2023 |  | 2653.01 | 137.11 | 137.11 | 2515.9
IET DAS202406115300001 | 2024-01-08 | 9500 | DAS Services for December 1-31, 2023 |  | 2653.01 | 1003.4 | 1140.51 | 1512.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 2653.01 | 275 | 1415.51 | 1237.5
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 2653.01 | 330 | 1745.51 | 907.5
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 2653.01 | 275 | 2020.51 | 632.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 2653.01 | 302.5 | 2323.01 | 330
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 2653.01 | 137.5 | 2460.51 | 192.5
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 2653.01 | 192.5 | 2653.01 | 0
[5 empty] | 2653.01 |  | 2653.01 | 0
[5 empty] | 2653.01 |  | 2653.01 | 0
[5 empty] | 2653.01 |  | 2653.01 | 0
[5 empty] | 2653.01 |  | 2653.01 | 0
|  |  | Totals: | 2653.01 |  | 2653.01 |  | 0
Note on E9: Jurgenson, John [DAS]: 9382.00 DOC MPCF 1102 E Washington Demo $John Adams, Brandon 9:24 AM (16 minutes ago) to me Finance, Please set my PM budget to $3,500 for project 9382.00 - DA24 Regards, 9382.00 DOC MPCF 1102 E. Washington Demolition $Joni Adams, Brandon Mon, Jul 1, 8:46 AM (9 days ago) to me Finance, Please close PM Time for 9382.00 when June PM time posts. This project can be closed, please return remaining funds to DOC. Regards, Brandon Adams Owner's Representative, State Design & Construction Resources Bureau

## #9382.00 Misc
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
Program code 938200 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9382.00 Controlled Asbestos
DOC MPCF 1102 E. Washington Demolition
Project # 9382.00
Program code 938200 |  |  | Major Program 4E01
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0506-335-DA24-9255 |  |  | MA21060A
Project Manager - Brandon A. |  |  | Activity code:CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524079803 | 2024-03-19 | DO Procore | 22427.3 | 22427.3 |  |  | 22427.3
DO 33524079803 | 2024-05-28 | CO #1 | 7270 | 29697.3 |  | 0 | 29697.3
PRC 3352407PA9803 | 2024-06-11 | Inv. 0010776-IN- Final | -7639.29 | 22058.01 | 22058.01 | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  |  |  | 22058.01 |  | 22058.01 | 0
|  | Totals: | 22058.01 |  | 22058.01 |  | 0 | FINAL
|  | Line 1 Labor 170 hrs x $65hr | 10920 |  | 10920 |  | 0
|  | Line 1 travel 198 hrs x $65 | 6825 |  | 6825 |  | 0
|  | Line 7 (air, dnr,) | 244.26 |  | 244.26 |  | 0
|  | Line 8 (other, rentals) Dumpster fee | 603.75 |  | 603.75 |  | 0
|  | Line 8 9other, rentals) Generator rental @ $60 / day x 7d | 420 |  | 420 |  | 0
|  | Line 10 frriable $90 x 2t | 0 |  |  |  | 0
|  | Line 12(mileage, meals, lodging) 50 cents/mile x 8410 miles | 3045 |  | 3045 |  | 0
|  | Total: | 22058.01 |  | 22058.01 |  | 0

## RECAP #9383.00
DOC MPCF New Apprenticeship Building
Project # 9383.00
| Program code 938300 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1161858.66
C | Samuels Group |  | 25933.15 | 25933.15 | 0
C | PM TIME |  | 12842.5 | 12842.5 | 0
C | Misc. |  | 13271.1 | 13271.1 | 0
C | Horizon Architecture |  | 89500 | 89500 | 0
C | Samuels Group |  | 73392.85 | 73392.85 | 0
C | Schickedanz Construction |  | 946919.06 | 946919.06 | 0
| Total Project Cost | 1161858.66 | 1161858.66 | 1161858.66 | 0 | 0
Closed 06/10/25

## #9383.00 Funds Rec'd
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A24001 | 2024-01-05 | 1200000 | 1200000
|  |  | Returning FY24 Funds to Agency | IET 33524227915 | 2024-08-14 | -1102168.75 | -1102168.75
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227915A | 2024-08-20 | -1485 | -1485
|  |  | Received FY25 Funds From Agency | IET 25543A25001 | 2024-09-09 | 1103653.75 | 1103653.75
|  |  | Returning Funds to Agency - Closing Project | IET 33525161900 | 2025-06-10 | -38141.34 | -38141.34
| Total Requested | 0 | Total Transferred |  |  | 1161858.66 | 1161858.66

## #9383.00 Samuels Group
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524012805 | 2024-01-12 | PO Procore | 29673.92 | 29673.92 |  |  | 29673.92
PRC 3352401PA2805 | 2024-03-06 | Inv. 9383.01 PC |  | 29673.92 | 2436.93 | 2436.93 | 27236.99
PRC 3352401PB2805 | 2024-04-09 | Inv. 9383.02 PC |  | 29673.92 | 827.14 | 3264.07 | 26409.85
PRC 3352401PC2805 | 2024-05-07 | Inv. 9383.03 PC |  | 29673.92 | 2507.14 | 5771.21 | 23902.71
PRC 3352401PD2805 | 2024-05-30 | Inv. 9383.04 PC |  | 29673.92 | 2507.14 | 8278.35 | 21395.57
PRC 3352401PE2805 | 2024-07-08 | Inv. 9383.05 PC |  | 29673.92 | 8760.4 | 17038.75 | 12635.17 | FY24
PO 33525012805 | 2024-08-28 | Roll to FY25 |  | 29673.92 |  | 17038.75 | 12635.17
PRC 3352501PF2805 | 2024-09-11 | Inv. 9383.06 PC |  | 29673.92 | 5478.7 | 22517.45 | 7156.47
PRC 3352501PG2805 | 2024-09-12 | Inv. 9383.07 PC FINAL | -3740.77 | 25933.15 | 3415.7 | 25933.15 | 0
|  |  |  | 25933.15 |  | 25933.15 | 0
|  |  |  | 25933.15 |  | 25933.15 | 0
|  |  |  | 25933.15 |  | 25933.15 | 0
|  |  |  | 25933.15 |  | 25933.15 | 0
|  | Totals: | 25933.15 |  | 25933.15 |  | 0 | FINAL
|  | CM Services | 25647.15 |  | 25647.15 |  | 0
|  | Reimbursables | 286 |  | 286 |  | 0
|  | Total: | 25933.15 |  | 25933.15 |  | 0

## #9383.00 PM TIME
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A |  |  |  | eDAS 908V
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 12842.5 | 12842.5 |  |  | 12842.5
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 12842.5 | 1017.5 | 1017.5 | 11825
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 12842.5 | 1155 | 2172.5 | 10670
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 12842.5 | 247.5 | 2420 | 10422.5
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 12842.5 | 605 | 3025 | 9817.5
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 12842.5 | 522.5 | 3547.5 | 9295
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 12842.5 | 660 | 4207.5 | 8635
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 12842.5 | 742.5 | 4950 | 7892.5
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12842.5 | 687.5 | 5637.5 | 7205
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12842.5 | 687.5 | 6325 | 6517.5
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12842.5 | 687.5 | 7012.5 | 5830
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12842.5 | 412.5 | 7425 | 5417.5
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12842.5 | 577.5 | 8002.5 | 4840
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12842.5 | 1045 | 9047.5 | 3795
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12842.5 | 797.5 | 9845 | 2997.5
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 12842.5 | 495 | 10340 | 2502.5
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 12842.5 | 1100 | 11440 | 1402.5
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 12842.5 | 1402.5 | 12842.5 | 0
[5 empty] | 12842.5 |  | 12842.5 | 0
|  |  | Totals: | 12842.5 |  | 12842.5 |  | 0
Note on E9: Huggins, Joni [DAS]: 9383.00 DOC MPCF New Apprenticeship Building Inbox Adams, Brandon 7:51 AM (31 minutes ago) to me Finance, Please set my PM budget for DA24 9383.00 at $20,000. Regards, Brandon Adams Owner's Representative, State Design & Construction Resources Bureau

## #9383.00 Misc
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202407115300001 | 2024-02-07 | 2507 |  | Central Procurement Hourly Rate for January 1-31, 2024 | DAS2024071153 | 137.5 | 137.5
IET DAS202408115300001 | 2024-03-05 | 2507 |  | Central Procurement Hourly Rate for February 1-29, 2024 | DAS2024081153 | 220 | 357.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -357.5 | 0
PRC 33525255903 | 2024-09-11 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV042252 | 1466.35 | 1466.35
GAX 33525309900 | 2024-11-04 | 9500 | CNST | Hickenbottom Inc V#(00002113955) | Inv. 528116 | 11804.75 | 13271.1
13271.1
13271.1
13271.1
13271.1
13271.1
13271.1
13271.1
|  |  |  | Totals: |  | 13271.1

## #9383.00 Horizon Architecture
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor:00003108847
Acct. Codes-0506-335-DA24-9260 |  |  | RFP938300-01
Project Manager - Brandon A |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524051800 | 2024-02-20 | PO Procore | 82000 | 82000 |  |  | 82000
PRC 3352405PA1800 | 2024-04-09 | Inv. 9383.00-01 |  | 82000 | 22900 | 22900 | 59100
PO 33524051800 | 2024-05-02 | CO #1 | 9500 | 91500 |  | 22900 | 68600
PRC 3352405PB1800 | 2024-05-07 | Inv. 9383.00-02 |  | 91500 | 26500 | 49400 | 42100
PRC 3352405PC1800 | 2024-06-13 | Inv. 9383.00-03 |  | 91500 | 25700 | 75100 | 16400 | FY24
PO 33525051800 | 2024-08-28 | Roll to FY25 | 0 | 91500 |  | 75100 | 16400
PRC 3352505PD1800 | 2024-09-11 | Inv. 9383.00-04 |  | 91500 | 3600 | 78700 | 12800
PRC 3352505PE1800 | 2024-10-14 | Inv. 9383.00-05 |  | 91500 | 2160 | 80860 | 10640
PRC 3352505PF1800 | 2024-11-06 | Inv. 9383.00-06 |  | 91500 | 2160 | 83020 | 8480
PRC 3352505PG1800 | 2025-01-06 | Inv. 9383.00-07 |  | 91500 | 2160 | 85180 | 6320
PRC 3352505PH1800 | 2025-02-12 | Inv. 9383.00-08 |  | 91500 | 1610 | 86790 | 4710
PRC 3352505PI1800 | 2025-03-04 | Inv. 9383.00-09 |  | 91500 | 972 | 87762 | 3738
PRC 3352505PJ1800 | 2025-06-03 | Inv. 9383.00-10 - Final | -2000 | 89500 | 1738 | 89500 | 0
|  | Totals: | 89500 |  | 89500 |  | 0 | FINAL
|  | Survey/Geotechnical Investigation | 8000 |  | 8000 |  | 0
|  | Design Development Phase | 25200 |  | 25200 |  | 0
|  | Construction Documentation | 32400 |  | 32400 |  | 0
|  | Bidding/Negotiation | 3600 |  | 3600 |  | 0
|  | Construction Phase | 10800 |  | 10800 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | CO #1 | 9500 |  | 9500 |  | 0
|  | Total: | 89500 |  | 89500 |  | 0

## #9383.00 Samuels Group
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525255900 | 2024-09-11 | PO Procore | 70804.75 | 70804.75 |  |  | 70804.75
PRC 3352525PA5900 | 2024-10-02 | Inv. 9383.01 CA |  | 70804.75 | 7700.4 | 7700.4 | 63104.35
PO 33525255900 | 2024-10-03 | CO #1 | 5000 | 75804.75 |  | 7700.4 | 68104.35
PRC 3352525PB5900 | 2024-11-12 | Inv. 9383.02 CA |  | 75804.75 | 10941.96 | 18642.36 | 57162.39
PRC 3352525PC5900 | 2024-12-11 | Inv. 9383.03 CA |  | 75804.75 | 3656.68 | 22299.04 | 53505.71
PRC 3352525PD5900 | 2025-01-06 | Inv. 9383.04 CA |  | 75804.75 | 2693.46 | 24992.5 | 50812.25
PRC 3352525PE5900 | 2025-02-26 | Inv. 9383.05 |  | 75804.75 | 22797.77 | 47790.27 | 28014.48
PRC 3352525PF5900 | 2025-03-04 | Inv. 9383.06 CA |  | 75804.75 | 12892.69 | 60682.96 | 15121.79
PRC 3352525PG5900 | 2025-04-07 | Inv. 9383.07 CA |  | 75804.75 | 8261.62 | 68944.58 | 6860.17
PRC 3352525PH5900 | 2025-06-03 | Inv. 9383.08 CA FINAL | -2411.9 | 73392.85 | 4448.27 | 73392.85 | 0
|  |  |  | 73392.85 |  | 73392.85 | 0
|  |  |  | 73392.85 |  | 73392.85 | 0
|  |  |  | 73392.85 |  | 73392.85 | 0
|  | Totals: | 73392.85 |  | 73392.85 |  | 0 | FINAL
|  | CM Services | 32947.8 |  | 32947.8 |  | 0
|  | Reimbursable Expenses | 2605.7 |  | 2605.7 |  | 0
|  | Fees | 32839.35 |  | 32839.35 |  | 0
|  | CO #1 | 5000 |  | 5000 |  | 0
|  | Total: | 73392.85 |  | 73392.85 |  | 0

## #9383.00 Schickedanz Constr
DOC MPCF New Apprenticeship Building
Project # 9383.00
Program code 938300 |  |  | Major Program 4E01
Schickedanz Construction |  |  | Vendor: VS000004775
Acct. Codes-0506-335-DA24-9255 |  |  | RFB938300-01
Project Manager - Brandon A |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525255901 | 2024-09-11 | PO Procore | 938267 | 938267 |  |  | 938267
PRC 3352525PA5901 | 2024-10-17 | Inv. 9383.00-01 |  | 938267 | 22801.7 | 22801.7 | 915465.3 | 1200.09
PRC 3352525PB5901 | 2024-12-19 | Inv. 9383.00-02 |  | 938267 | 277292.3 | 300094 | 638173 | 15794.42
PO 33525255901 | 2025-01-23 | CO #01 | 1548.17 | 939815.17 |  | 300094 | 639721.17
PRC 3352525PC5901 | 2025-01-31 | Inv. 9383.00-03 |  | 939815.17 | 173759.37 | 473853.37 | 465961.8 | 24939.65
PO 33525255901 | 2025-01-31 | CO #2(No Cost CO) | 0 | 939815.17 |  | 473853.37 | 465961.8
PO 33525255901 | 2025-01-31 | CO #3 | 3222.45 | 943037.62 |  | 473853.37 | 469184.25
PO 33525255901 | 2025-02-21 | CO #4 | 3881.44 | 946919.06 |  | 473853.37 | 473065.69
PRC 3352525PD5901 | 2025-03-06 | Inv. 9383.00-04 |  | 946919.06 | 277970.11 | 751823.48 | 195095.58 | 39569.65
PRC 3352525PE5901 | 2025-04-28 | Inv. 9383.00-05 |  | 946919.06 | 138835.78 | 890659.26 | 56259.8 | 46876.8
PRC 3352525PF5901 | 2025-05-20 | Inv. 9383.00-06 |  | 946919.06 | 8913.85 | 899573.11 | 47345.95 | 47345.95
PRC 3352525PG5901 | 2025-06-03 | Inv. 9383.00-07-retainage |  | 946919.06 | 47345.95 | 946919.06 | 0
|  |  |  | 946919.06 |  | 946919.06 | 0
|  | Totals: | 946919.06 |  | 946919.06 |  | 0 | FINAL

## RECAP #9384.00
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
| Program code 938400 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 13869.12
C | Boyd Jones |  | 3042.14 | 3042.14 | 0
C | PM TIME |  | 2691.98 | 2691.98 | 0
C | Misc. |  | 925 | 925 | 0
C | Horizon Architecture |  | 7210 | 7210 | 0
| Total Project Cost | 13869.12 | 13869.12 | 13869.12 | 0 | 0
Closed 02/21/25

## #9384.00 Funds Rec'd
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
Program code 938400 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524023101 | 2024-01-23 | 50000 | 50000
|  |  | Returning Funds Per PM | IET 33524190900 | 2024-07-08 | -30000 | -30000
|  |  | Received FY25 Funds From Agency | IET 23812Y25003 | 2024-09-10 | 30000 | 30000
|  |  | Returning Funds to Agency-Closing Project | IET 33525052906 | 2025-02-21 | -36130.88 | -36130.88
| Total Requested | 0 | Total Transferred |  |  | 13869.12 | 13869.12

## #9384.00 Boyd Jones
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
Program code 938400 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA24-9255 |  |  | RPF1821335228-BoydJones11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524032903 | 2024-02-01 | PO Procre | 4385.65 | 4385.65 |  |  | 4385.65
PRC 3352403PA2903 | 2024-04-11 | Inv. 9384.00-01 |  | 4385.65 | 670.81 | 670.81 | 3714.84
PRC 3352403PB2903 | 2024-05-09 | Inv. 9384.00-02 |  | 4385.65 | 1669.14 | 2339.95 | 2045.7
PRC 3352403PC2903 | 2024-06-12 | Inv. 9384.00-03-FINAL | -1343.51 | 3042.14 | 702.19 | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  |  |  | 3042.14 |  | 3042.14 | 0
|  | Totals: | 3042.14 |  | 3042.14 |  | 0 | FINAL
|  | CM Services | 3042.14 |  | 3042.14 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 3042.14 |  | 3042.14 |  | 0

## #9384.00 PM TIME
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
Program code 938400 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E2BA
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2691.98 | 2691.98 |  |  | 2691.98
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 2691.98 | 38.74 | 38.74 | 2653.24
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 2691.98 | 340.1 | 378.84 | 2313.14
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 2691.98 | 9.06 | 387.9 | 2304.08
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 2691.98 | 75.6 | 463.5 | 2228.48
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 2691.98 | 109.73 | 573.23 | 2118.75
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 2691.98 | 830.1 | 1403.33 | 1288.65
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 2691.98 | 20.5 | 1423.83 | 1268.15
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 2691.98 | 179.8 | 1603.63 | 1088.35
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 2691.98 | 38.1 | 1641.73 | 1050.25
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 2691.98 | 316.3 | 1958.03 | 733.95
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 2691.98 | 10.16 | 1968.19 | 723.79
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 2691.98 | 97.2 | 2065.39 | 626.59
IET DAS202501115300001 | 2024-08-07 |  | Finance Support for July 1-31,2024 |  | 2691.98 | 7.88 | 2073.27 | 618.71
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 2691.98 | 86.2 | 2159.47 | 532.51
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 2691.98 | 9.7 | 2169.17 | 522.81
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 2691.98 | 62.3 | 2231.47 | 460.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 2691.98 | 4.92 | 2236.39 | 455.59
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 2691.98 | 45.3 | 2281.69 | 410.29
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 2691.98 | 35.29 | 2316.98 | 375
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 2691.98 | 375 | 2691.98 | 0
[5 empty] | 2691.98 |  | 2691.98 | 0
|  |  | Totals: | 2691.98 |  | 2691.98 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie 1:23 PM (6 minutes ago) to me Sorry about that. Please establish PM time budgets in 9384.00 and 9385.00 as follows. 9384.00 - PM Time - $5,500.00 9385.00 - PM Time - $5,000.00

## #9384.00 Misc
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
Program code 938400 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524187902 | 2024-07-05 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2583842 | 925 | 925
925
925
925
925
925
925
925
925
925
925
925
|  |  |  | Totals: |  | 925

## #9384.00 Horizon Architecture
DOC CBC District 1 DRF N Wing Sm Restroom Renovation
Project # 9384.00
Program code 938400 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA24-9260 |  |  | TSB
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524068802 | 2024-03-08 | PO Procre | 9820 | 9820 |  |  | 9820
PRC 3352406PA8802 | 2024-05-09 | Inv. 9384.00-01 |  | 9820 | 6630 | 6630 | 3190 | FY24
PO 33525068802 | 2024-08-16 | Roll to FY25 |  | 9820 |  | 6630 | 3190
PRC 3352506PB8802 | 2025-01-28 | Inv. 9384.00-02 - Final | -2610 | 7210 | 580 | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  |  |  | 7210 |  | 7210 | 0
|  | Totals: | 7210 |  | 7210 |  | 0 | FINAL
|  | Design Development Documents | 3770 |  | 3770 |  | 0
|  | Construction Documents | 2860 |  | 2860 |  | 0
|  | Bidding or Negotiation Phase | 0 |  |  |  | 0
|  | Construction Phase | 580 |  | 580 |  | 0
|  | Total: | 7210 |  | 7210 |  | 0

## RECAP #9385.00
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
| Program code 938500 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie Elliott
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 71062.19
C | Boyd Jones |  | 3541.45 | 3541.45 | 0
C | PM TIME |  | 4883.28 | 4883.28 | 0
C | Misc. |  | 2002.11 | 2002.11 | 0
C | Horizon Architecture |  | 5400 | 5400 | 0
C | Steege Construction |  | 48748 | 48748 | 0
C | Boyd Jones (2) |  | 6487.35 | 6487.35 | 0
| Total Project Cost | 71062.19 | 71062.19 | 71062.19 | 0 | 0
CLOSED 03/11/25

## #9385.00 Funds Rec'd
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennie Elliott
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524023101 | 2024-01-23 | 40000 | 40000
|  |  | MOU Amendment #1 | IET 23812Y25002 | 2024-09-09 | 27000 | 27000
|  |  | MOU Amendment #2 | IET 23812Y25011 | 2024-12-03 | 8000 | 8000
|  |  | Closing Project Per PM | IET 33525070903 | 2025-03-11 | -3937.81 | -3937.81
| Total Requested | 0 | Total Transferred |  |  | 71062.19 | 71062.19

## #9385.00 Boyd Jones
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA24-9255 |  |  | RPF1821335228-BoydJones11012021
Project Manager - Jennie Elliott |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524032902 | 2024-02-01 | PO Procore | 3542.88 | 3542.88 |  |  | 3542.88
PRC 3352403PA2902 | 2024-04-15 | Inv. 9385.00-01 |  | 3542.88 | 670.81 | 670.81 | 2872.07
PRC 3352403PB2902 | 2024-05-24 | Inv. 9385.00-02 |  | 3542.88 | 1404.38 | 2075.19 | 1467.69
PRC 3352403PC2902 | 2024-07-18 | Inv. 9385.00-03 |  | 3542.88 | 690.68 | 2765.87 | 777.01 | FY24
PO 33525032902 | 2024-08-16 | Roll to FY 25 |  | 3542.88 |  | 2765.87 | 777.01
PRC 3352503PD2902 | 2024-08-22 | Inv. 9385.00-04 |  | 3542.88 | 172.67 | 2938.54 | 604.34
PO 33525032902 | 2024-10-10 | CO #1 | 358.57 | 3901.45 |  | 2938.54 | 962.91
PRC 3352503PE2902 | 2024-10-23 | Inv. 9385.00-05- Final | -360 | 3541.45 | 602.91 | 3541.45 | 0
|  |  |  | 3541.45 |  | 3541.45 | 0
|  |  |  | 3541.45 |  | 3541.45 | 0
|  |  |  | 3541.45 |  | 3541.45 | 0
|  |  |  | 3541.45 |  | 3541.45 | 0
|  |  |  | 3541.45 |  | 3541.45 | 0
|  | Totals: | 3541.45 |  | 3541.45 |  | 0 | FINAL
|  | CM Services | 3182.88 |  | 3182.88 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | CO #1 | 358.57 |  | 358.57 |  | 0
|  | Total: | 3541.45 |  | 3541.45 |  | 0

## #9385.00 PM TIME
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie Elliott |  |  |  | eDAS E2BB
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4883.28 | 4883.28 |  |  | 4883.28
IET DAS202407115300001 | 2024-02-07 | 2507 | Finance Support for January 1-31, 2024 |  | 4883.28 | 38.74 | 38.74 | 4844.54
IET DAS202407115300001 | 2024-02-07 | 9500 | DAS Services for January 1-31, 2024 |  | 4883.28 | 340.1 | 378.84 | 4504.44
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 4883.28 | 16.6 | 395.44 | 4487.84
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 4883.28 | 83 | 478.44 | 4404.84
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 4883.28 | 47.7 | 526.14 | 4357.14
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 4883.28 | 361.3 | 887.44 | 3995.84
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 4883.28 | 40.31 | 927.75 | 3955.53
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 4883.28 | 358.5 | 1286.25 | 3597.03
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 4883.28 | 20.24 | 1306.49 | 3576.79
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 4883.28 | 168.8 | 1475.29 | 3407.99
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 4883.28 | 33.55 | 1508.84 | 3374.44
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 4883.28 | 307.4 | 1816.24 | 3067.04
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 4883.28 | 30.84 | 1847.08 | 3036.2
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 4883.28 | 339.4 | 2186.48 | 2696.8
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 4883.28 | 270.28 | 2456.76 | 2426.52
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 4883.28 | 1375 | 3831.76 | 1051.52
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4883.28 | 26.06 | 3857.82 | 1025.46
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4883.28 | 230.6 | 4088.42 | 794.86
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4883.28 | 5.9 | 4094.32 | 788.96
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4883.28 | 39.2 | 4133.52 | 749.76
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 4883.28 | 23.9 | 4157.42 | 725.86
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 4883.28 | 160.1 | 4317.52 | 565.76
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 4883.28 | 21.66 | 4339.18 | 544.1
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 4883.28 | 214.6 | 4553.78 | 329.5
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 4883.28 | 7.6 | 4561.38 | 321.9
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 4883.28 | 78.7 | 4640.08 | 243.2
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 4883.28 | 45.5 | 4685.58 | 197.7
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 4883.28 | 197.7 | 4883.28 | -1.3642e-12
[5 empty] | 4883.28 |  | 4883.28 | -1.3642e-12
|  |  | Totals: | 4883.28 |  | 4883.28 |  | 0
Note on E9: Jurgenson, John [DAS]: Elliott, Jennie 1:23 PM (6 minutes ago) to me Sorry about that. Please establish PM time budgets in 9384.00 and 9385.00 as follows. 9384.00 - PM Time - $5,500.00 9385.00 - PM Time - $5,000.00 Re: 9385.00 - DOC CBC District 1 WURF Men's Restroom Floor Repair - DA24 $Joni Elliott, Jennie 7:47 AM (5 minutes ago) to me Yes please! On Tue, Mar 11, 2025, 7:25 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: After posting February PM time there is only $116.72 left in PM Time I can reduce the PM time by the 116.72 and return $3,937.81 Please advise ~Joni On Sat, Mar 8, 2025 at 9:50 AM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: DAS Finance, Please reduce PM Time in 9385.00 - DOC CBC District 1 WURF Men's Restroom Floor Repair to $4,640.08 in the Contracted Line. Then please close the project and return $4,181.01 in funds to the Agency. Thank you, Jennie Elliott

## #9385.00 Misc
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie Elliott
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524200901 | 2024-07-18 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2580476 | 1676.25 | 1676.25
PRC 33525250905 | 2024-09-06 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV042539 | 325.86 | 2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
2002.11
|  |  |  | Totals: |  | 2002.11

## #9385.00 Horizon Architecture
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA24-9260 |  |  | TSB
Project Manager - Jennie Elliott |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524080901 | 2024-03-20 | PO Procore | 5400 | 5400 |  |  | 5400
PRC 3352408PA0901 | 2024-05-13 | Inv. 9385.00-01 |  | 5400 | 1630 | 1630 | 3770
PRC 3352408PB0901 | 2024-07-17 | Inv. 9385.00-02 |  | 5400 | 435 | 2065 | 3335 | FY24
PO 33525080901 | 2024-08-16 | Roll to FY25 |  | 5400 |  | 2065 | 3335
PRC 3352508PC0901 | 2024-10-07 | Inv. 9385.00-03 |  | 5400 | 435 | 2500 | 2900
PRC 3352508PD0901 | 2024-11-05 | Inv. 9385.00-04 |  | 5400 | 1015 | 3515 | 1885
PRC 3352508PE0901 | 2025-01-14 | Inv. 9385.00-05 - FINAL |  | 5400 | 1885 | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  |  |  | 5400 |  | 5400 | 0
|  | Totals: | 5400 |  | 5400 |  | 0 | FINAL
|  | Design Development | 1050 |  | 1050 |  | 0
|  | Construction Documents | 580 |  | 580 |  | 0
|  | Bidding/Negotiation | 870 |  | 870 |  | 0
|  | Construction Phase | 2900 |  | 2900 |  | 0
|  | Total: | 5400 |  | 5400 |  | 0

## #9385.00 Steege Construction
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  | Major Program 4E01
Steege Construction |  |  | Vendor: 00002140654
Acct. Codes-0506-335-DA24-9255 |  |  | 938500-01
Project Manager - Jennie Elliott |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525276909 | 2024-10-02 | PO Procore | 40150 | 40150 |  |  | 40150
PO 33525276909 | 2024-12-23 | CO #1 | 8598 | 48748 |  | 0 | 48748
PRC 3352527PA6909 | 2024-01-08 | Inv. 9385.00-01 |  | 48748 | 38142.5 | 38142.5 | 10605.5 | 2007.5
PRC 3352527PB6909 | 2025-01-21 | Inv. 9385.00-02 |  | 48748 | 8168.1 | 46310.6 | 2437.4 | 2437.4
PRC 3352527PC6909 | 2025-02-10 | Inv. 9385.00-03: -Retainage |  | 48748 | 2437.4 | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  |  |  | 48748 |  | 48748 | 0
|  | Totals: | 48748 |  | 48748 |  | 0

## #9385.00 Boyd Jones (2)
DOC CBC District 1 WURF Men's Restroom Floor Repair
Project # 9385.00
Program code 938500 |  |  | Major Program 4E01
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA24-9255 |  |  | RPF1821335228-BoydJones11012021
Project Manager - Jennie Elliott |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525302903 | 2024-10-28 | PO Procore | 6492.35 | 6492.35 |  |  | 6492.35
PRC 3352530PA2903 | 2024-10-31 | Inv. 9385.00-001* |  | 6492.35 | 2046.13 | 2046.13 | 4446.22
PRC 3352530PB2903 | 2024-11-07 | Inv. 9385.00-002* |  | 6492.35 | 1873.46 | 3919.59 | 2572.76
PRC 3352530PC2903 | 2024-12-23 | Inv. 9385.00-003* |  | 6492.35 | 1908.74 | 5828.33 | 664.02
PRC 3352530PD2903 | 2025-01-14 | Inv. 9385.00-004 - FINAL* | -5 | 6487.35 | 659.02 | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  |  |  | 6487.35 |  | 6487.35 | 2.2737e-13
|  | Totals: | 6487.35 |  | 6487.35 |  | 0 | FINAL
|  | CM Services | 6292.35 |  | 6292.35 |  | 0
|  | Reimbursables | 195 |  | 195 |  | 0
|  | Total: | 6487.35 |  | 6487.35 |  | 0
*Vendor has used Inv. 9385.00-01 in another tab, please use Inv. 9385.00-00X

## RECAP #9398.00
DOC CCF Water Supply Study
Project # 9398.00
| Program code 939800 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 46125.12
C | Samuels Group |  | 9234.1 | 9234.1 | 0
C | PM TIME |  | 4194.52 | 4194.52 | 0
C | Misc. |  | 346.5 | 346.5 | 0
C | MSA Professional Services - Water Study |  | 32350 | 32350 | 0
| Total Project Cost | 46125.12 | 46125.12 | 46125.12 | 0 | 0
Closed 11/14/24

## #9398.00 Funds Rec'd
DOC CCF Water Supply Study
Project # 9398.00
Program code 939800 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 24824IET0220241 | 2024-02-20 | 100000 | 100000
|  |  | Funds Received in without program code | CDR 33524061900 | 2024-03-01 | 0 | 0
|  |  | Returning funds to Agency Per PM | IET 33524120912 | 2024-04-29 | -45000 | -45000
|  |  | Returning FY24 Funds to Agency | IET 33524227914 | 2024-08-14 | -30605.22 | -30605.22
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227914A | 2024-08-21 | -677.9 | -677.9
|  |  | Received FY25 Funds from Agency | IET 24825IET0912241 | 2024-09-12 | 31283.12 | 31283.12
|  |  | Funds Received in without program code | CDR 33525257900 | 2024-09-12 | 0 | 0
|  |  | Returning Funds to Agency-Closing Project | IET 33525319905 | 2024-11-14 | -8874.88 | -8874.88 | `
| Total Requested | 0 | Total Transferred |  |  | 46125.12 | 46125.12

## #9398.00 Samuels Group
DOC CCF Water Supply Study
Project # 9398.00
Program code 939800 |  |  | Major Program 4E01
Samuels Group #158PC |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524079801 | 2024-03-19 | PO Procore | 10240.37 | 10240.37 |  |  | 10240.37
PRC 3352407PA9801 | 2024-04-08 | Inv. 7675.01939800 |  | 10240.37 | 686.55 | 686.55 | 9553.82
PRC 3352407PB9801 | 2024-05-06 | Inv. 7675.02939800 |  | 10240.37 | 918.7 | 1605.25 | 8635.12
PRC 3352407PC9801 | 2024-05-30 | Inv. 7675.03939800 |  | 10240.37 | 2541.6 | 4146.85 | 6093.52
PRC 3352407PD9801 | 2024-07-08 | Inv. 7675.04939800 |  | 10240.37 | 923.61 | 5070.46 | 5169.91 | FY24
PO 33525079801 | 2024-08-28 | Roll to FY25 |  | 10240.37 |  | 5070.46 | 5169.91
PRC 3352507PE9801 | 2024-09-17 | Inv. 7675.05939800 |  | 10240.37 | 112.16 | 5182.62 | 5057.75
PRC 3352507PF9801 | 2024-09-17 | Inv. 7675.06939800 |  | 10240.37 | 1198.05 | 6380.67 | 3859.7
PRC 3352507PG9801 | 2024-10-02 | Inv. 7675.07939800 |  | 10240.37 | 1480.34 | 7861.01 | 2379.36
PRC 3352507PH9801 | 2024-11-06 | Inv. 7675.08939800-FINAL | -1006.27 | 9234.1 | 1373.09 | 9234.1 | 0
|  |  |  | 9234.1 |  | 9234.1 | 0
|  |  |  | 9234.1 |  | 9234.1 | 0
|  |  |  | 9234.1 |  | 9234.1 | 0
|  | Totals: | 9234.1 |  | 9234.1 |  | 0 | FINAL
|  | CM Services | 8874.1 |  | 8874.1 |  | 0
|  | Reimbursables | 360 |  | 360 |  | 0
|  | Total: | 9234.1 |  | 9234.1 |  | 0

## #9398.00 PM TIME
DOC CCF Water Supply Study
Project # 9398.00
Program code 939800 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T |  |  |  | eDAS E2BX
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4194.52 | 4194.52 |  |  | 4194.52
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 4194.52 | 107.55 | 107.55 | 4086.97
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 4194.52 | 541.6 | 649.15 | 3545.37
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 4194.52 | 42.28 | 691.43 | 3503.09
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 4194.52 | 322 | 1013.43 | 3181.09
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 4194.52 | 101.8 | 1115.23 | 3079.29
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 4194.52 | 902.8 | 2018.03 | 2176.49
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 4194.52 | 37.26 | 2055.29 | 2139.23
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 4194.52 | 307.5 | 2362.79 | 1831.73
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 4194.52 | 20.33 | 2383.12 | 1811.4
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 4194.52 | 187.3 | 2570.42 | 1624.1
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 4194.52 | 28.45 | 2598.87 | 1595.65
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 4194.52 | 310.5 | 2909.37 | 1285.15
IET DAS202502115300001 | 2024-09-09 |  | Finance Support for August 1-31,2024 |  | 4194.52 | 59.44 | 2968.81 | 1225.71
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 4194.52 | 304.7 | 3273.51 | 921.01
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4194.52 | 74.24 | 3347.75 | 846.77
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4194.52 | 658.5 | 4006.25 | 188.27
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4194.52 | 24.17 | 4030.42 | 164.1
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4194.52 | 164.1 | 4194.52 | 0
[5 empty] | 4194.52 |  | 4194.52 | 0
|  |  | Totals: | 4194.52 |  | 4194.52 |  | 0
Note on E9: Huggins, Joni [DAS]: Tonyan, Brad Nov 13, 2024, 3:33 PM (18 hours ago) to me, Chris, Jerry, Gregory, Steve Finance, Project 9398.00 or DOC CCF Water Study Supply has been completed and all phases of the evaluation are closed. The final invoices have been paid and the remaining balance or funds of $8,874.88 can be returned to the client as these were done under MOU DA24.

## #9398.00 Misc
DOC CCF Water Supply Study
Project # 9398.00
Program code 939800 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 55 | 55
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -55 | 0
GAX 33525261903 | 2024-09-17 | 9500 | DSGN | MircobacLaboratories V#(00003198168) | Inv. NT2408307 | 346.5 | 346.5
346.5
346.5
346.5
346.5
346.5
346.5
346.5
346.5
346.5
|  |  |  | Totals: |  | 346.5

## #9398.00 MSA Professional Serv.
DOC CCF Water Supply Study
Project # 9398.00
Program code 939800 |  |  | Major Program 4E01
MSA Professional Services - Water Study |  |  | Vendor:00002102484
Acct. Codes-0506-335-DA24-9260 |  |  | RFP939800-01
Project Manager - Brad T |  |  | Activity code:DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524123804 | 2024-05-02 | PO Procore | 32350 | 32350 |  |  | 32350
PRC 3352412PA3804 | 2024-07-08 | Inv. 9398.00-01 |  | 32350 | 16076 | 16076 | 16274 | FY24
PO 33525123804 | 2024-08-28 | Roll to FY25 |  | 32350 |  | 16076 | 16274
PRC 3352512PB3804 | 2024-09-17 | Inv. 9398.00-02 |  | 32350 | 11416 | 27492 | 4858
PRC 3352512PC3804 | 2024-09-17 | Inv. 9398.00-03 |  | 32350 | 4834 | 32326 | 24
PRC 3352512PD3804 | 2024-10-07 | Inv. 9398.00-04 (FINAL) |  | 32350 | 24 | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  |  |  | 32350 |  | 32350 | 0
|  | Totals: | 32350 |  | 32350 |  | 0 | FINAL
|  | Initial Report and Evaluation Summary | 15800 |  | 15800 |  | 0
|  | 50% Report and Cost Opinion | 4270 |  | 4270 |  | 0
|  | 95% Report and Cost Opinion | 7940 |  | 7940 |  | 0
|  | Final Report and Cost Opinion | 3890 |  | 3890 |  | 0
|  | Reimbursables | 450 |  | 450 |  | 0
|  | Total: | 32350 |  | 32350 |  | 0

## RECAP #9399.00
HHS WRC Med Center Pharmacy Remodel
Project # 9399.00
| Program code 939900 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 12003.57
C | Genesis Architectural |  | 11370 | 11370 | 0
C | PM TIME |  | 633.57 | 633.57 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 12003.57 | 12003.57 | 12003.57 | 0 | 0
Closed 08/13/2024

## #9399.00 Funds Rec'd
HHS WRC Med Center Pharmacy Remodel
Project # 9399.00
Program code 939900 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Jennifer K. | [8 empty] | `
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUMEDCTRPHARMACY | 2024-03-19 | 13000 | 13000
|  |  | Returning Funds to Agency | IET 33524226903 | 2024-08-13 | -996.43 | -996.43
`
| Total Requested | 0 | Total Transferred |  |  | 12003.57 | 12003.57

## #9399.00 Genesis Architectural
HHS WRC Med Center Pharmacy Remodel
Project # 9399.00
Program code 939900 |  |  | Major Program 4B02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA24-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524099902 | 2024-04-09 | PO Procore | 11370 | 11370 |  |  | 11370
PRC 3352409PA9902 | 2024-05-13 | Inv. 2403-01 |  | 11370 | 5168 | 5168 | 6202
PRC 3352409PB9902 | 2024-07-29 | Inv. 2403-02 FINAL |  | 11370 | 6202 | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  |  |  | 11370 |  | 11370 | 0
|  | Totals: | 11370 |  | 11370 |  | 0 | FINAL
|  | CM Services | 5330 |  | 5330 |  | 0
|  | Reimbursables | 6040 |  | 6040 |  | 0
|  | Total: | 11370 |  | 11370 |  | 0

## #9399.00 PM TIME
HHS WRC Med Center Pharmacy Remodel
Project # 9399.00
Program code 939900 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E2BZ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 633.57 | 633.57 |  |  | 633.57
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 633.57 | 36.44 | 36.44 | 597.13
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 633.57 | 165 | 201.44 | 432.13
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 633.57 | 35.57 | 237.01 | 396.56
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 633.57 | 192.5 | 429.51 | 204.06
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 633.57 | 10.75 | 440.26 | 193.31
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 633.57 | 55 | 495.26 | 138.31
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 633.57 | 110.81 | 606.07 | 27.5
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 633.57 | 577.5 | 1183.57 | -550
CDE 33524192912 | 2024-07-10 | 9500 | Moving 5 hours pm time from 939900 DA24 to 939000 MM24 |  | 633.57 | -550 | 633.57 | 0
[5 empty] | 633.57 |  | 633.57 | 0
[5 empty] | 633.57 |  | 633.57 | 0
[5 empty] | 633.57 |  | 633.57 | 0
|  |  | Totals: | 633.57 |  | 633.57 |  | 0

## #9399.00 Misc
HHS WRC Med Center Pharmacy Remodel
Project # 9399.00
Program code 939900 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9400.00
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
| Program code 940000 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 38663.99
C | Samuels Group #159PC |  | 9161.28 | 9161.28 | 0
C | PM TIME |  | 8363.71 | 8363.71 | 0
C | Misc. |  | 49.5 | 49.5 | 0
C | Shive Hattery |  | 21089.5 | 21089.5 | 0
| Total Project Cost | 38663.99 | 38663.99 | 38663.99 | 0 | 0
Closed 06/12/25

## #9400.00 Funds Rec'd
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524059101 | 2024-02-28 | 60000 | 60000
|  |  | Returning Funds to Agency - Closing Project | IET 33525163912 | 2025-06-12 | -21336.01 | -21336.01
| Total Requested | 0 | Total Transferred |  |  | 38663.99 | 38663.99

## #9400.00 Samuels Group #159PC
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  | Major Program 4E01
Samuels Group #159PC |  |  | Vendor:00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code:CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524067801 | 2024-03-07 | PO Procore | 14108.28 | 14108.28 |  |  | 14108.28
PRC 3352406PA7801 | 2024-05-09 | Inv. 9400.01 PC |  | 14108.28 | 2820.95 | 2820.95 | 11287.33
PRC 3352406PB7801 | 2024-07-17 | Inv. 9400.02 PC |  | 14108.28 | 1373.09 | 4194.04 | 9914.24 | FY24
PO 33525067801 | 2024-08-16 | Roll to FY25 |  | 14108.28 |  | 4194.04 | 9914.24
PRC 3352506PC7801 | 2024-08-23 | Inv. 9400.03 PC |  | 14108.28 | 1298.32 | 5492.36 | 8615.92
PRC 3352506PD7801 | 2024-09-18 | Inv. 9400.04 PC FINAL | -4947 | 9161.28 | 3668.92 | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  |  |  | 9161.28 |  | 9161.28 | 0
|  | Totals: | 9161.28 |  | 9161.28 |  | 0 | FINAL
|  | CM Services | 9161.28 |  | 9161.28 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 9161.28 |  | 9161.28 |  | 0

## #9400.00 PM TIME
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - James T. |  |  |  | eDAS E2C1
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8363.71 | 8363.71 |  |  | 8363.71
IET DAS202408115300001 | 2024-03-05 | 2507 | Finance Support for February 1-29, 2024 |  | 8363.71 | 60.55 | 60.55 | 8303.16
IET DAS202408115300001 | 2024-03-05 | 9500 | DAS Services for February 1-29, 2024 |  | 8363.71 | 305.2 | 365.75 | 7997.96
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 8363.71 | 202.52 | 568.27 | 7795.44
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 8363.71 | 1535.8 | 2104.07 | 6259.64
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 8363.71 | 129.82 | 2233.89 | 6129.82
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 8363.71 | 1153.1 | 3386.99 | 4976.72
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8363.71 | 106.77 | 3493.76 | 4869.95
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8363.71 | 884.5 | 4378.26 | 3985.45
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8363.71 | 53.03 | 4431.29 | 3932.42
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8363.71 | 486.5 | 4917.79 | 3445.92
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 8363.71 | 76.31 | 4994.1 | 3369.61
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 8363.71 | 833.8 | 5827.9 | 2535.81
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8363.71 | 165.06 | 5992.96 | 2370.75
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8363.71 | 839.3 | 6832.26 | 1531.45
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8363.71 | 105.94 | 6938.2 | 1425.51
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8363.71 | 941 | 7879.2 | 484.51
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 8363.71 | 62.81 | 7942.01 | 421.7
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8363.71 | 421.7 | 8363.71 | 0
[5 empty] | 8363.71 |  | 8363.71 | 0
[5 empty] | 8363.71 |  | 8363.71 | 0
[5 empty] | 8363.71 |  | 8363.71 | 0
|  |  | Totals: | 8363.71 |  | 8363.71 |  | 0
Note on E9: Jurgenson, John [DAS]: Trower, James 3:14 PM (0 minutes ago) to me Finance - Please set up $7,000 in PM Time for project 9400.00. I need to invoice PM Time for this project in February. Thanks, Trower, James Oct 10, 2024, 5:11 PM (14 hours ago) to me Finance - DA24 9400.00 -879.20 INCREASE PM TIME BY $2,000. DA24 9412.00 -300.56 INCREASE PM TIME BY $2,000.

## #9400.00 Misc
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524078902 | 2024-03-18 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV037731 | 49.5 | 49.5
IET DAS202409115300001 | 2024-04-05 | 2507 |  | Central Procurement Hourly Rate for March 1-31, 2023 | DAS2024091153 | 55 | 104.5
IET DAS202410115300001 | 2024-05-07 | 2507 |  | Central Procurement Hourly Rate for April 1-30, 2024 | DAS2024101153 | -55 | 49.5
GAX 33524103912 | 2024-04-12 | 9500 | CNST | Marshall Glass V#(00003172527) | Inv. I052575 | 942.62 | 992.12
CDE 33525013900 | 2025-01-13 | 9500 | CNST | Moving Expense from 940000 to 940300 for Marshall Glass V#(00003172527) | Inv. I052575 | -942.62 | 49.5
49.5
49.5
49.5
49.5
49.5
49.5
49.5
|  |  |  | Totals: |  | 49.5

## #9400.00 Shive Hattery
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0506-335-DA24-9260 |  |  | RFP940000-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524156907 | 2024-06-01 | PO Procore | 32600 | 32600 |  |  | 32600
PRC 3352415PA6907 | 2024-07-16 | Inv. 2240005600-1 |  | 32600 | 8692 | 8692 | 23908 | FY24
PO 33525156907 | 2024-08-16 | Roll to FY25 |  | 32600 |  | 8692 | 23908
PRC 3352515PB6907 | 2024-09-17 | Inv. 2240005600-FINAL | -11510.5 | 21089.5 | 12397.5 | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  |  |  | 21089.5 |  | 21089.5 | 0
|  | Totals: | 21089.5 |  | 21089.5 |  | 0 | FINAL
|  | Design Development Docs | 10600 |  | 10600 |  | 0
|  | Construction Docs | 10489.5 |  | 10489.5 |  | 0
|  | Bidding/Negotation Assistance | 0 |  |  |  | 0
|  | Construction Phase | 0 |  |  |  | 0
|  | Total: | 21089.5 |  | 21089.5 |  | 0

## RECAP #9401.00
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
| Program code 940100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 175000
C | Boyd Jones |  | 8361.91 | 8361.91 | 0
| PM TIME |  | 9000 | 8088.1 | 911.9
| Misc. |  | 7851.74 | 7851.74 | 0
C | Cannon Moss Brygger Architects(CMB) |  | 12800 | 12800 | 0
C | Boyd Jones (2) |  | 22786.51 | 22786.51 | 0
C | SCH Ventures |  | 105143.74 | 105143.74 | 0
| Total Project Cost | 175000 | 165943.9 | 165032 | 911.9 | 9056.1

## #9401.00 Funds Rec'd
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812Y24016 | 2024-03-04 | 145000 | 145000
|  |  | Returning FY24 Funds to Agency | IET 33524227916 | 2024-08-14 | -130427.5 | -130427.5
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227916A | 2024-08-21 | -822.56 | -822.56
|  |  | Received FY25 Funds From Agency | IET 23812Y25003 | 2024-09-10 | 131250.06 | 131250.06
|  |  | MOU Amendment #1 | IET 23812Y25009 | 2024-09-12 | 30000 | 30000
| Total Requested | 0 | Total Transferred |  |  | 175000 | 175000

## #9401.00 Boyd Jones
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor:00003193325
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524087800 | 2024-03-27 | PO Procore | 13702.77 | 13702.77 |  |  | 13702.77
PRC 3352408PA7800 | 2024-05-07 | Inv. 9401.00-01 |  | 13702.77 | 2142.9 | 2142.9 | 11559.87
PRC 3352408PB7800 | 2024-07-17 | Inv. 9401.00-02 |  | 13702.77 | 1036.02 | 3178.92 | 10523.85 | FY24
PO 33525087800 | 2024-08-28 | Roll to FY25 |  | 13702.77 |  | 3178.92 | 10523.85
PRC 3352508PC7800 | 2024-09-11 | Inv. 9401.00-03 |  | 13702.77 | 2072.04 | 5250.96 | 8451.81
PRC 3352508PD7800 | 2024-09-27 | Inv. 9401.00-04 - Final | -5340.86 | 8361.91 | 3110.95 | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  |  |  | 8361.91 |  | 8361.91 | 0
|  | Totals: | 8361.91 |  | 8361.91 |  | 0 | FINAL
|  | CM Services | 8152.91 |  | 8152.91 |  | 0
|  | Reimbursables | 209 |  | 209 |  | 0
|  | Total: | 8361.91 |  | 8361.91 |  | 0

## #9401.00 PM TIME
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 908X
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 9000 | 9000 |  |  | 9000
IET DAS202409115300001 | 2024-04-05 | 2507 | Finance Support for March 1-31, 2024 |  | 9000 | 47.7 | 47.7 | 8952.3
IET DAS202409115300001 | 2024-04-05 | 9500 | DAS Services for March 1-31, 2024 |  | 9000 | 361.3 | 409 | 8591
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 9000 | 100.69 | 509.69 | 8490.31
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 9000 | 896.8 | 1406.49 | 7593.51
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 9000 | 65.88 | 1472.37 | 7527.63
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 9000 | 545.2 | 2017.57 | 6982.43
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 9000 | 33.55 | 2051.12 | 6948.88
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 9000 | 307.4 | 2358.52 | 6641.48
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 9000 | 34.78 | 2393.3 | 6606.7
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 9000 | 376.5 | 2769.8 | 6230.2
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 9000 | 143.09 | 2912.89 | 6087.11
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 9000 | 727.9 | 3640.79 | 5359.21
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 9000 | 62.55 | 3703.34 | 5296.66
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 9000 | 555.2 | 4258.54 | 4741.46
IET DAS202504115300001 | 2024-11-09 | 2507 | Finance Support for October 1-31 2024 |  | 9000 | 17.42 | 4275.96 | 4724.04
IET DAS202504115300001 | 2024-11-09 | 9500 | DAS Support for Ocotber 1-31 2024 |  | 9000 | 117.2 | 4393.16 | 4606.84
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 9000 | 7.87 | 4401.03 | 4598.97
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 9000 | 53 | 4454.03 | 4545.97
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 9000 | 29.68 | 4483.71 | 4516.29
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 9000 | 299.8 | 4783.51 | 4216.49
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 9000 | 66.79 | 4850.3 | 4149.7
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 9000 | 709 | 5559.3 | 3440.7
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 9000 | 339.69 | 5898.99 | 3101.01
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 9000 | 1468.2 | 7367.19 | 1632.81
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 9000 | 10.54 | 7377.73 | 1622.27
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 9000 | 77.5 | 7455.23 | 1544.77
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 9000 | 80.57 | 7535.8 | 1464.2
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 9000 | 552.3 | 8088.1 | 911.9
[5 empty] | 9000 |  | 8088.1 | 911.9
[5 empty] | 9000 |  | 8088.1 | 911.9
[5 empty] | 9000 |  | 8088.1 | 911.9
[5 empty] | 9000 |  | 8088.1 | 911.9
[5 empty] | 9000 |  | 8088.1 | 911.9
|  |  | Totals: | 9000 |  | 8088.1 |  | 911.9
Note on E9: Huggins, Joni [DAS]: 9401.00 - Increase PM Time Budget $Joni Elliott, Jennie 12:21 PM (1 hour ago) to me Please increase the PM Time Budget to a total "Contracted" value of $8,000 in 9401.00 DA24. Thank you Jennie Elliott Changes for PM Time $Joni Elliott, Jennie May 4, 2025, 3:12 PM (15 hours ago) to me Can you please make the following change for PM time, thank you! 9388.00 - Please increase PM Time in the "Contracted" line to $15,000.00 9401.00 - Please increase PM Time in the "Contracted" line to $9,000.00 9475.00 - Please Establish a PM Time budget of $7,500.00 9474.00 - Please Establish a PM Time budget of $10,000.00

## #9401.00 Misc
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  |  | Major Program 4E01
Misc |  |  |  | Shipping Code 035
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33524200900 | 2024-07-18 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2580478 | 962.5 | 962.5
PRC 33525255904 | 2024-09-11 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV042511 | 330.33 | 1292.83
GAX 33525118903 | 2025-04-28 | 9500 | CNST | Vogel Paint V#(00002124622) | Inv. 19532375 | 6558.91 | 7851.74
7851.74
7851.74
7851.74
7851.74
7851.74
7851.74
7851.74
7851.74
7851.74
|  |  |  | Totals: |  | 7851.74

## #9401.00 CMB Architects
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  | Major Program 4E01
Cannon Moss Brygger Architects |  |  | Vendor: 00003050901
Acct. Codes-0506-335-DA24-9260 |  |  | TSB
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524117912 | 2024-04-26 | PO Procore | 12800 | 12800 |  |  | 12800
PRC 3352411PA7912 | 2024-07-18 | Inv. 9401.00-01 |  | 12800 | 7250 | 7250 | 5550 | FY24
PO 33525117912 | 2024-08-28 | Roll to FY25 |  | 12800 |  | 7250 | 5550
PRC 3352511PB7912 | 2024-09-11 | Inv. 64394 |  | 12800 | 625 | 7875 | 4925
PRC 3352511PC7912 | 2024-09-17 | Inv. 64633 |  | 12800 | 975 | 8850 | 3950
PRC 3352511PD7912 | 2024-10-16 | Inv. 64700 |  | 12800 | 650 | 9500 | 3300
PRC 3352511PE7912 | 2024-11-20 | Inv. 64836 |  | 12800 | 1000 | 10500 | 2300
PRC 3352511PF7912 | 2025-02-17 | Inv. 65102 |  | 12800 | 500 | 11000 | 1800
PRC 3352511PG7912 | 2025-03-17 | Inv. 65250 |  | 12800 | 1000 | 12000 | 800
PRC 3352511PH7912 | 2025-03-31 | Inv. 65311 |  | 12800 | 800 | 12800 | 0
|  |  |  | 12800 |  | 12800 | 0
|  |  |  | 12800 |  | 12800 | 0
|  |  |  | 12800 |  | 12800 | 0
|  | Totals: | 12800 |  | 12800 |  | 0 | FINAL
|  | Design Development | 2500 |  | 2500 |  | 0
|  | Construction Documents | 5000 |  | 5000 |  | 0
|  | Bidding/Negoiation | 1500 |  | 1500 |  | 0
|  | Construction Phase | 3000 |  | 3000 |  | 0
|  | Closeout | 800 |  | 800 |  | 0
|  | Total: | 12800 |  | 12800 |  | 0

## #9401.00 Boyd Jones (2)
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  | Major Program 4E01
Boyd Jones (2) |  |  | Vendor:00003193325
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525267900 | 2024-09-23 | PO Procore | 23248.45 | 23248.45 |  |  | 23248.45
PRC 3352526PA7900 | 2024-10-23 | Inv. 9401.00-001* |  | 23248.45 | 4190.12 | 4190.12 | 19058.33
PRC 3352526PB7900 | 2024-11-07 | Inv. 9401.00-002* |  | 23248.45 | 4964.24 | 9154.36 | 14094.09
PRC 3352526PC7900 | 2024-12-23 | Inv. 9401.00-003* |  | 23248.45 | 1028.82 | 10183.18 | 13065.27
PRC 3352526PD7900 | 2025-01-14 | Inv. 9401.00-004* |  | 23248.45 | 2231.75 | 12414.93 | 10833.52
PRC 3352526PE7900 | 2025-02-06 | Inv. 9401.00-005* |  | 23248.45 | 7452.28 | 19867.21 | 3381.24
PRC 3352526PF7900 | 2025-03-10 | Inv. 9401.00-006* |  | 23248.45 | 1293.87 | 21161.08 | 2087.37
PO 33525267900 | 2025-04-10 | CO #1(No cost CO) | 0 | 23248.45 |  | 21161.08 | 2087.37
PRC 3352526PG7900 | 2025-04-25 | Inv. 9401.00-007 - FINAL* | -461.94 | 22786.51 | 1625.43 | 22786.51 | 2.558e-12
|  |  |  | 22786.51 |  | 22786.51 | 2.558e-12
|  |  |  | 22786.51 |  | 22786.51 | 2.558e-12
|  |  |  | 22786.51 |  | 22786.51 | 2.558e-12
|  |  |  | 22786.51 |  | 22786.51 | 2.558e-12
|  | Totals: | 22786.51 |  | 22786.51 |  | 0 | FINAL
|  | CM Services | 21248.45 |  | 21248.45 |  | 0
|  | Reimbursables | 1538.06 |  | 1538.06 |  | 0
|  | CO #1(Moves funds from Reimbursables to CM) | 0 |  | 0 |  | 0
|  | Total: | 22786.51 |  | 22786.51 |  | 0
*Invoice format 9401.00-0X was used in a previous tab for this project
Please use 9401.00-00X

## #9401.00 SCH Ventures
DOC 3JD Sheldon Administration Building Window Replacements
Project # 9401.00
Program code 940100 |  |  | Major Program 4E01
SCH Ventures |  |  | Vendor:00003222583
Acct. Codes-0506-335-DA24-9255 |  |  | 940100-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525267901 | 2024-09-23 | PO Procore | 102534.74 | 102534.74 |  |  | 102534.74
PRC 3352526PA7901 | 2025-01-24 | Inv. 9401.00-01 |  | 102534.74 | 63568.5 | 63568.5 | 38966.24 | 3345.72
PO 33525267901 | 2025-02-17 | CO #1 | 2609 | 105143.74 |  | 63568.5 | 41575.24
PRC 3352526PB7901 | 2025-03-10 | Inv. 9401.00-02 |  | 105143.74 | 32865.41 | 96433.91 | 8709.83 | 5075.48
PRC 3352526PC7901 | 2025-03-10 | Inv. 9401.00-03 |  | 105143.74 | 2478.55 | 98912.46 | 6231.28 | 5205.93
PRC 3352526PD7901 | 2025-03-24 | Inv. 9401.00-04 |  | 105143.74 | 974.08 | 99886.54 | 5257.2 | 5257.2
PRC 3352526PE7901 | 2025-03-31 | Inv. 9401.00-05 - Retainage |  | 105143.74 | 5257.2 | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  |  |  | 105143.74 |  | 105143.74 | 0
|  | Totals: | 105143.74 |  | 105143.74 |  | 0 | FINAL

## RECAP #9402.00
DOE ISD Mass Notification System
Project # 9402.00
| Program code 940200 |  |  | Major Program 1E01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 17774.71
C | Samuels Group |  | 4786.4 | 4786.4 | 0
C | PM TIME |  | 4188.31 | 4188.31 | 0
C | Misc. |  | 0 | 0 | 0
C | Morrissey Engineering |  | 8800 | 8800 | 0
| Total Project Cost | 17774.71 | 17774.71 | 17774.71 | 0 | 0
Closed 03/11/25

## #9402.00 Funds Rec'd
DOE ISD Mass Notification System
Project # 9402.00
Program code 940200 |  |  | Major Program 1E01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | CR 00524107101 | 2024-04-16 | 18500 | 18500
|  |  | Closing Project per PM | IET 33525070900 | 2025-03-11 | -725.29 | -725.29
| Total Requested | 0 | Total Transferred |  |  | 17774.71 | 17774.71

## #9402.00 Samuels Group
DOE ISD Mass Notification System
Project # 9402.00
Program code 940200 |  |  | Major Program 1E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524123902 | 2024-05-02 | PO Procore | 5466.28 | 5466.28 |  |  | 5466.28
PRC 3352412PA3902 | 2024-06-01 | Inv. 7686.01940200 |  | 5466.28 | 1569.86 | 1569.86 | 3896.42
PRC 3352412PB3902 | 2024-07-11 | Inv. 7686.02940200 |  | 5466.28 | 1285.57 | 2855.43 | 2610.85 | FY24
PO 33525123902 | 2024-08-16 | Roll to FY25 |  | 5466.28 |  | 2855.43 | 2610.85
PRC 3352512PC3902 | 2024-09-04 | Inv. 7686.03940200 |  | 5466.28 | 361.97 | 3217.4 | 2248.88
PRC 3352512PD3902 | 2024-10-02 | Inv. 7686.04940200 |  | 5466.28 | 1020.11 | 4237.51 | 1228.77
PRC 3352512PE3902 | 2024-10-08 | Inv. 7686.05940200-FINAL | -679.88 | 4786.4 | 548.89 | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  |  |  | 4786.4 |  | 4786.4 | 0
|  | Totals: | 4786.4 |  | 4786.4 |  | 0 | FINAL
|  | CM Services | 4542.4 |  | 4542.4 |  | 0
|  | Reimbursables | 244 |  | 244 |  | 0
|  | Total: | 4786.4 |  | 4786.4 |  | 0

## #9402.00 PM TIME
DOE ISD Mass Notification System
Project # 9402.00
Program code 940200 |  |  |  | Major Program 1E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennie E. |  |  |  | eDAS 908Y
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4188.31 | 4188.31 |  |  | 4188.31
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 4188.31 | 40.31 | 40.31 | 4148
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 4188.31 | 358.5 | 398.81 | 3789.5
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 4188.31 | 187.72 | 586.53 | 3601.78
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 4188.31 | 1552.82 | 2139.35 | 2048.96
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 4188.31 | 14.07 | 2153.42 | 2034.89
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 4188.31 | 130.5 | 2283.92 | 1904.39
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 4188.31 | 17.04 | 2300.96 | 1887.35
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 4188.31 | 188.8 | 2489.76 | 1698.55
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 4188.31 | 47.46 | 2537.22 | 1651.09
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 4188.31 | 243 | 2780.22 | 1408.09
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 4188.31 | 78.19 | 2858.41 | 1329.9
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 4188.31 | 694 | 3552.41 | 635.9
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 4188.31 | 69.14 | 3621.55 | 566.76
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 4188.31 | 462.2 | 4083.75 | 104.56
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 4188.31 | 7.87 | 4091.62 | 96.69
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 4188.31 | 53 | 4144.62 | 43.69
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 4188.31 | 3.79 | 4148.41 | 39.9
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 4188.31 | 39.9 | 4188.31 | 0
[5 empty] | 4188.31 |  | 4188.31 | 0
[5 empty] | 4188.31 |  | 4188.31 | 0
[5 empty] | 4188.31 |  | 4188.31 | 0
|  |  | Totals: | 4188.31 |  | 4188.31 |  | 0
Note on E9: Huggins, Joni [DAS]: 9402.00 - DOE ISD Mass Notification System - DA24 External $Joni Elliott, Jennie Sat, Mar 8, 10:24 AM (3 days ago) to me, Scott, Mark DAS Finance, Please reduce PM Time in 9402.00 - DOE ISD Mass Notification System to $4,188.31 in the Contracted Line. Then please close the project and return $725.29 in funds to the Agency. Thank you, Jennie Elliott

## #9402.00 Misc
DOC 5JD Admin Office BAS Replacement
Project # 9400.00
Program code 940000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9402.00 Morrissey Engineering
DOE ISD Mass Notification System
Project # 9402.00
Program code 940200 |  |  | Major Program 1E01
Morrissey Engineering |  |  | Vendor: 00003214256
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524134800 | 2024-05-13 | PO Procore | 8800 | 8800 |  |  | 8800
PRC 3352413PA4800 | 2024-07-11 | Inv. 24723 |  | 8800 | 3080 | 3080 | 5720 | FY24
PO 33525134800 | 2024-08-16 | Roll to FY25 |  | 8800 |  | 3080 | 5720
PRC 3352513PB4800 | 2024-09-05 | Inv. 25031 |  | 8800 | 1320 | 4400 | 4400
PRC 3352513PC4800 | 2024-10-08 | Inv. 25131-Final |  | 8800 | 4400 | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  |  |  | 8800 |  | 8800 | 0
|  | Totals: | 8800 |  | 8800 |  | 0 | FINAL

## RECAP #9403.00
IVH Dack Fire Repairs (29C20)
Project # 9403.00
| Program code 940300 |  |  | Major Program 4E03
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 182912.74
C | DCI Group |  | 12711.51 | 12711.51 | 0
C | PM TIME |  | 8981.12 | 8981.12 | 0
C | Misc. |  | 137131.11 | 137131.11 | 0
C | Architectural Arts Millwork |  | 8990 | 8990 | 0
C | Ideacom Mid-America |  | 1232 | 1232 | 0
C | Baker Electric |  | 3450 | 3450 | 0
C | Waldinger Corp |  | 7117 | 7117 | 0
C | Commercial Shading System |  | 3300 | 3300 | 0
| Total Project Cost | 182912.74 | 182912.74 | 182912.74 | 0 | 0
Closed 01/10/25

## #9403.00 Funds Rec'd
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET040324100 | 2024-04-03 | 100000 | 100000
|  |  | Funds transferred without a program code | CDR 33524095800 | 2024-04-03 | 0 | 0
|  |  | MOU Amendment #1 | IET IET060524101 | 2024-06-05 | 75000 | 75000
|  |  | Funds transferred without a program code | CDR 33524158900 | 2024-06-05 | 0 | 0
|  |  | Returning FY24 Funds to Agency | IET 33524227917 | 2024-08-14 | -47822.74 | -47822.74
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227917A | 2024-08-21 | -1782.48 | -1782.48
|  |  | Received FY25 Funds from Agency | IET IET082624101 | 2024-08-27 | 49605.22 | 49605.22
|  |  | Funds transferred without a program code | CDR 33525241900 | 2024-08-28 | 0 | 0
|  |  | MOU Amend #2 | IET092624400 | 2024-09-26 | 15000 | 15000
|  |  | Funds transferred without a program code | CDR 33525271902 | 2024-09-27 | 0 | 0
|  |  | Returning Funds to Agency-closing project | IET 33525010914 | 2025-01-10 | -7087.26 | -7087.26
| Total Requested | 0 | Total Transferred |  |  | 182912.74 | 182912.74

## #9403.00 DCI Group
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524110902 | 2024-04-19 | PO Procore | 10576.06 | 10576.06 |  |  | 10576.06
PRC 3352411PA0902 | 2024-05-06 | Inv. 24-011 CA 01 |  | 10576.06 | 3649.28 | 3649.28 | 6926.78
PRC 3352411PB0902 | 2024-06-18 | Inv. 24-011 CA 02 |  | 10576.06 | 5169.08 | 8818.36 | 1757.7
PRC 3352411PC0902 | 2024-07-19 | Inv. 24-011 CA 03 |  | 10576.06 | 878.3 | 9696.66 | 879.4 | FY24
PO 33525110902 | 2024-08-28 | Roll to FY25 |  | 10576.06 |  | 9696.66 | 879.4
PRC 3352511PD0902 | 2024-09-16 | Inv. 24-011 CA 04 |  | 10576.06 | 526.98 | 10223.64 | 352.42
PRC 3352511PE0902 | 2024-09-17 | Inv. 24-011 CA 05 |  | 10576.06 | 351.32 | 10574.96 | 1.1
PO 33525110902 | 2024-10-04 | CO #1 | 2311.92 | 12887.98 |  | 10574.96 | 2313.02
PRC 3352511PF0902 | 2024-12-05 | Inv. 24-011 CA 06 |  | 12887.98 | 1053.96 | 11628.92 | 1259.06
PRC 3352511PG0902 | 2024-12-30 | Inv. 24-011 CA 07 |  | 12887.98 | 504.61 | 12133.53 | 754.45
PRC 3352511PH0902 | 2025-01-03 | Inv. 24-011 CA 08 FINAL | -176.47 | 12711.51 | 577.98 | 12711.51 | -9.9476e-13
|  |  |  | 12711.51 |  | 12711.51 | -9.9476e-13
|  |  |  | 12711.51 |  | 12711.51 | -9.9476e-13
|  | Totals: | 12711.51 |  | 12711.51 |  | 0 | FINAL
|  | CM Services | 10270.06 |  | 10270.06 |  | 0
|  | Reimbursables | 306 |  | 306 |  | 0
|  | CO #1 | 2135.45 |  | 2135.45 |  | 0
|  | Total: | 12711.51 |  | 12711.51 |  | 0

## #9403.00 PM TIME
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  |  | Major Program 4E03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2CI
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8981.12 | 8981.12 |  |  | 8981.12
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 8981.12 | 154.38 | 154.38 | 8826.74
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 8981.12 | 1375 | 1529.38 | 7451.74
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 8981.12 | 172.65 | 1702.03 | 7279.09
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 8981.12 | 1436 | 3138.03 | 5843.09
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 8981.12 | 143.52 | 3281.55 | 5699.57
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 8981.12 | 1311 | 4592.55 | 4388.57
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 8981.12 | 74.34 | 4666.89 | 4314.23
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 8981.12 | 816.9 | 5483.79 | 3497.33
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8981.12 | 102.11 | 5585.9 | 3395.22
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8981.12 | 521.5 | 6107.4 | 2873.72
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8981.12 | 63.82 | 6171.22 | 2809.9
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8981.12 | 570.5 | 6741.72 | 2239.4
IET DAS202504115300001 | 2024-11-07 |  | Finance Support for October 1-31,2024 |  | 8981.12 | 102.58 | 6844.3 | 2136.82
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8981.12 | 686.6 | 7530.9 | 1450.22
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 8981.12 | 115.39 | 7646.29 | 1334.83
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 8981.12 | 768.7 | 8414.99 | 566.13
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 8981.12 | 51.33 | 8466.32 | 514.8
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 8981.12 | 514.8 | 8981.12 | 0
[5 empty] | 8981.12 |  | 8981.12 | 0
|  |  | Totals: | 8981.12 |  | 8981.12 |  | 0
Note on E9: Jurgenson, John [DAS]: 9403 - DVA IVH Dack Fire Repairs (29C20) Inbox Tonyan, Brad 3:18 PM (0 minutes ago) to me Finance, Please set up PM time on the following project 9403.00 - DA24 for $10,000. Thank you, Tonyan, Brad 2:45 PM (6 minutes ago) to me, Brad, Scott, David, Nathan, Michael Finance, I just completed a "dummy invoice" for the balancing of PM time on project 9403.00 (29C20). Please closeout the misc./PM Time as no additional invoices will occur on this project but keep the project open until the (29C20) reimbursement is received. Finance can you please compile all the backup invoices as needed for IVH to submit the (29C20) reimbursement to the State. Note that I will be on vacation next week if you could copy all of those on this email once they are compiled so we keep this moving forward and return the unspent funds of $7,087.26 back to IVH.

## #9403.00 Misc
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  |  | Major Program 4E03
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33524120900 | 2024-04-26 | 9500 | CNST | ServiceMaster V#(00002111536) | Inv. AME-0074-WTR | 56013.87 | -56013.87
GAX 33524134910 | 2024-05-13 | 9500 | CNST | ForSureRoofing V#(00003081739) | Inv. 002812 | 3799 | -52214.87
CDE 33524165907 | 2024-06-13 | 9500 | CNST | Processing CDE to move expense from project 9403.00 to IVH. IVH purchashed material with P-Card | Inv. 21944913 | 311.37 | -51903.5
GAX 33524170901 | 2024-06-18 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-3 | 16516.98 | -35386.52
CDE 33524205901 | 2024-07-23 | 9500 | CNST | Processing CDE to move expense from project 9403.00 to IVH. IVH purchashed material with P-Card | Inv. 1101181718 | 14934.61 | -20451.91
GAX 335242079011 | 2024-07-25 | 9500 | CNST | Ralph N Smith Inc V#(00002106937) | Inv. 30691 | 12900 | -7551.91
GAX 33524211903 | 2024-07-29 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-6 | 4455.12 | -3096.79
GAX 33525255908 | 2024-09-11 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-7 | 1204.04 | -1892.75
GAXN 33525276900 | 2024-10-02 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-5 | 17073.64 | 15180.89
GAX 33525338901 | 2024-12-03 | 9500 | CNST | Baker Electric V#(00002108328) | Inv. 102301-01 | 1516 | 16696.89
GAX 33525347902 | 2024-12-12 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-8 | 5261.07 | 21957.96
GAX 33525347903 | 2024-12-12 | 9500 | CNST | Ralph N Smith Inc V#(00002106937) | Inv. 30966 | 1256 | 23213.96
GAX 335525003903 | 2025-01-03 | 9500 | CNST | Bergstrom Construction V#(00002110114) | Inv. 8581-9 | 258.74 | 23472.7
PRC 33525006905 | 2025-01-06 | 9500 | CNST | Johnson Controls V#(00002139022) | Inv. 52491623 | 688.05 | 24160.75
CDE 33525013900 | 2025-01-13 | 9500 | CNST | Moving Expense from 940000 to 940300 for Marshall Glass V#(00003172527) | Inv. I052575 | 942.62 | 25103.37
25103.37
|  |  |  | Totals: |  | 137131.11

## #9403.00 Architectural Arts
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Architectural Arts MillWork |  |  | Vendor: 00003202601
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524134905 | 2024-05-13 | PO Procore | 8990 | 8990 |  |  | 8990 | FY24
PO 33525134905 | 2024-08-28 | Roll to FY25 |  | 8990 |  | 0 | 8990
PO 3352513PA4905 | 2024-12-05 | Inv. 8529-1 |  | 8990 | 8990 | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  |  |  | 8990 |  | 8990 | 0
|  | Totals: | 8990 |  | 8990 |  | 0

## #9403.00 Ideacom Mid-America
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Ideacom Mid-America |  |  | Vendor: 00003006128
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524142800 | 2024-05-21 | PO Procore | 1232 | 1232 |  |  | 1232
PRC 3352414PA2800 | 2024-07-26 | Inv. 502263 |  | 1232 | 1232 | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  |  |  | 1232 |  | 1232 | 0
|  | Totals: | 1232 |  | 1232 |  | 0 | FINAL

## #9403.00 Baker Electric
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Baker Electric |  |  | Vendor: 00002108328
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524142802 | 2024-05-21 | PO Procore | 3450 | 3450 |  |  | 3450 | FY24
PO 33525142802 | 2024-08-28 | Roll to FY25 |  | 3450 |  | 0 | 3450
PRC 3352514PA2802 | 2024-10-04 | Inv. 102086-01 |  | 3450 | 1897 | 1897 | 1553
PRC 3352514PB2802 | 2024-11-25 | Inv. 102086-02 |  | 3450 | 1553 | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  |  |  | 3450 |  | 3450 | 0
|  | Totals: | 3450 |  | 3450 |  | 0 | FINAL

## #9403.00 Waldinger Corp
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Waldinger Corp |  |  | Vendor: 00002116105
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524166900 | 2024-06-14 | PO Procore | 7117 | 7117 |  |  | 7117 | FY24
PO 33525166900 | 2024-08-28 | Roll to FY25 |  | 7117 |  | 0 | 7117
PRC 3352516PA6900 | 2024-11-18 | Inv. 80953P-001 |  | 7117 | 7117 | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  |  |  | 7117 |  | 7117 | 0
|  | Totals: | 7117 |  | 7117 |  | 0 | FINAL

## #9403.00 Commercial Shading
IVH Dack Fire Repairs (29C20)
Project # 9403.00
Program code 940300 |  |  | Major Program 4E03
Commercial Shading |  |  | Vendor: 00003214464
Acct. Codes-0506-335-DA24-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524185913 | 2024-07-03 | PO Procore | 3300 | 3300 |  |  | 3300 | FY24
PO 33525185913 | 2024-08-28 | Roll to FY25 |  | 3300 |  | 0 | 3300
PRC 3352518PA5913 | 2024-10-04 | Inv. 42814-01 |  | 3300 | 3300 | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  |  |  | 3300 |  | 3300 | 0
|  | Totals: | 3300 |  | 3300 |  | 0 | FINAL

## RECAP #9404.00
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 04/30/24

## #9404.00 Funds Rec'd
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9404.00 Vendor A
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9404.00 PM TIME
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2CJ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9404.00 Misc
DOC NCF CRC Boiler Replacements
Project # 9404.00
Program code 940400 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24 |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9405.00
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
| Program code 940500 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 200728.05
C | DCI Group |  | 11957.37 | 11957.37 | 0
C | PM TIME |  | 7865.13 | 7865.13 | 0
C | Misc. |  | 351.47 | 351.47 | 0
C | Horizon Architecture |  | 24270 | 24270 | 0
C | TMJ Construction Services |  | 54322.6 | 54322.6 | 0
C | Edge Commercial |  | 97000 | 97000 | 0
C | DCI Group #24-013 CA |  | 4961.48 | 4961.48 | 0
| Total Project Cost | 200728.05 | 200728.05 | 200728.05 | 0 | 0
Closed 06/23/25

## #9405.00 Funds Rec'd
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812Y24031 | 2024-06-13 | 200000 | 200000
|  |  | Returning FY24 Funds to Agency | IET 33524227918 | 2024-08-14 | -196521.63 | -196521.63
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227918A | 2024-08-21 | -933.88 | -933.88
|  |  | MOU Amendment 1 | IET 23812Y25001 | 2024-09-04 | 5925.43 | 5925.43
|  |  | Received FY25 Funds From Agency | IET 23812Y25003 | 2024-09-10 | 197455.51 | 197455.51
|  |  | Returning Funds to Agency-Closing Project | IET 33525174907 | 2025-06-23 | -5197.38 | -5197.38
| Total Requested | 0 | Total Transferred |  |  | 200728.05 | 200728.05

## #9405.00 DCI Group
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524170900 | 2024-06-18 | PO Procore | 12239.7 | 12239.7 |  |  | 12239.7
PRC 3352417PA0900 | 2024-07-22 | Inv. 24-013 PC 01 |  | 12239.7 | 2336.86 | 2336.86 | 9902.84 | FY24
PO 33525170900 | 2024-08-28 | Roll to FY25 |  | 12239.7 |  | 2336.86 | 9902.84
PRC 3352517PB0900 | 2024-09-11 | Inv. 24-013 PC 02 |  | 12239.7 | 1386.81 | 3723.67 | 8516.03
PRC 3352517PC0900 | 2024-09-19 | Inv. 24-013 PC 03 |  | 12239.7 | 1666.82 | 5390.49 | 6849.21
PRC 3352517PD0900 | 2024-10-18 | Inv. 24-013 PC 04 |  | 12239.7 | 2488.34 | 7878.83 | 4360.87
PRC 3352517PE0900 | 2024-12-03 | Inv. 24-013 PC 05 |  | 12239.7 | 3402.3 | 11281.13 | 958.57
PRC 3352517PF0900 | 2025-02-12 | Inv. 24-013 PC 06 FINAL | -282.33 | 11957.37 | 676.24 | 11957.37 | 0
|  |  |  | 11957.37 |  | 11957.37 | 0
|  |  |  | 11957.37 |  | 11957.37 | 0
|  |  |  | 11957.37 |  | 11957.37 | 0
|  |  |  | 11957.37 |  | 11957.37 | 0
|  |  |  | 11957.37 |  | 11957.37 | 0
|  | Totals: | 11957.37 |  | 11957.37 |  | 0 | FINAL
|  | CM Services | 11923.87 |  | 11923.87 |  | 0
|  | Reimbursables | 33.5 |  | 33.5 |  | 0
|  | Total: | 11957.37 |  | 11957.37 |  | 0

## #9405.00 PM TIME
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2CK
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 7865.13 | 7865.13 |  |  | 7865.13
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 7865.13 | 20.33 | 20.33 | 7844.8
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 7865.13 | 187.3 | 207.63 | 7657.5
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 7865.13 | 39.14 | 246.77 | 7618.36
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 7865.13 | 427.8 | 674.57 | 7190.56
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 7865.13 | 102.11 | 776.68 | 7088.45
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 7865.13 | 521.5 | 1298.18 | 6566.95
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 7865.13 | 74.24 | 1372.42 | 6492.71
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 7865.13 | 658.5 | 2030.92 | 5834.21
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 7865.13 | 157.52 | 2188.44 | 5676.69
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 7865.13 | 1049.6 | 3238.04 | 4627.09
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 7865.13 | 130.7 | 3368.74 | 4496.39
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 7865.13 | 865.4 | 4234.14 | 3630.99
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 7865.13 | 93.52 | 4327.66 | 3537.47
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 7865.13 | 934.6 | 5262.26 | 2602.87
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 7865.13 | 47.1 | 5309.36 | 2555.77
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 7865.13 | 505.1 | 5814.46 | 2050.67
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 7865.13 | 109.95 | 5924.41 | 1940.72
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 7865.13 | 477.4 | 6401.81 | 1463.32
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 7865.13 | 102.48 | 6504.29 | 1360.84
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 7865.13 | 735.1 | 7239.39 | 625.74
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 7865.13 | 79.44 | 7318.83 | 546.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 7865.13 | 546.3 | 7865.13 | 0
[5 empty] | 7865.13 |  | 7865.13 | 0
[5 empty] | 7865.13 |  | 7865.13 | 0
[5 empty] | 7865.13 |  | 7865.13 | 0
|  |  | Totals: | 7865.13 |  | 7865.13 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: April PM Time $Joni Tonyan, Brad 3:04 PM (5 minutes ago) to me, Joni Joni, Please raise the following PM time on DA24 9405.00 by $365.13. Brad Tonyan, CPM, LEED Green Associate Owner Representative

## #9405.00 Misc
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Shipping Code 222004
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC33525340906 | 2024-12-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV045022 | 351.47 | 351.47
351.47
351.47
351.47
351.47
351.47
351.47
351.47
351.47
351.47
351.47
351.47
|  |  |  | Totals: |  | 351.47

## #9405.00 Horizon Architecture
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA24-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524177900 | 2024-06-25 | PO Procore | 24770 | 24770 |  |  | 24770 | FY24
PO 33525177900 | 2024-08-28 | Roll to FY25 |  | 24770 |  | 0 | 24770
PRC 3352517PA7900 | 2024-09-11 | Inv. 9405.00-01 |  | 24770 | 10730 | 10730 | 14040
PRC 3352517PB7900 | 2024-10-14 | Inv. 9405.00-02 |  | 24770 | 5952.5 | 16682.5 | 8087.5
PRC 3352517PC7900 | 2024-12-05 | Inv. 9405.00-03 |  | 24770 | 832.5 | 17515 | 7255
PRC 3352517PD7900 | 2025-01-14 | Inv. 9405.00-04 |  | 24770 | 2364.25 | 19879.25 | 4890.75
PRC 3352517PE7900 | 2025-02-12 | Inv. 9405.00-05 |  | 24770 | 675.5 | 20554.75 | 4215.25
PRC 3352517PF7900 | 2025-04-16 | Inv. 9405.00-06 |  | 24770 | 2702 | 23256.75 | 1513.25
PRC 3352517PG7900 | 2025-06-18 | Inv. 9405.00-07 |  | 24770 | 1013.25 | 24270 | 500
PO 33525177900 | 2025-06-23 | Closing per PM email | -500 | 24270 |  | 24270 | 0
|  |  |  | 24270 |  | 24270 | 0
|  |  |  | 24270 |  | 24270 | 0
|  |  |  | 24270 |  | 24270 | 0
|  | Totals: | 24270 |  | 24270 |  | 0
|  | Schematic Design | 6440 |  | 6440 |  | 0
|  | Design Development | 4290 |  | 4290 |  | 0
|  | Construction Documents | 5120 |  | 5120 |  | 0
|  | Bidding | 1665 |  | 1665 |  | 0
|  | Contract Administration | 6755 |  | 6755 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 24270 |  | 24270 |  | 0

## #9405.00 TMJ Construction
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
TMJ Construction |  |  | Vendor: 00003078324
Acct. Codes-0506-335-DA24-9255 |  |  | RFQ 940500-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525298904 | 2024-10-22 | PO Procore | 54322.6 | 54322.6 |  |  | 54322.6
PRC 3352529PA8904 | 2025-01-03 | Inv. 29388 |  | 54322.6 | 50656.47 | 50656.47 | 3666.13 | 2666.13
PRC 3352529PB8904 | 2025-02-18 | Inv. 29612 - Closeout |  | 54322.6 | 950 | 51606.47 | 2716.13 | 2716.13
PRC 3352529PC8904 | 2025-05-30 | Inv. INV29837 - Retainage |  | 54322.6 | 2716.13 | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  |  |  | 54322.6 |  | 54322.6 | 0
|  | Totals: | 54322.6 |  | 54322.6 |  | 0 | FINAL

## #9405.00 Egde Commercial
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
Edge Commercial |  |  | Vendor: 00002096995
Acct. Codes-0506-335-DA24-9255 |  |  | RFQ 940500-02
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525352903 | 2024-12-17 | PO Procore | 97000 | 97000 |  |  | 97000
PRC 3352535PA2903 | 2025-05-12 | Inv. 1415224010 |  | 97000 | 91200 | 91200 | 5800 | 4800
PRC 3352535PB2903 | 2025-06-13 | Inv. 141522402 |  | 97000 | 950 | 92150 | 4850 | 4850
PRC 3352535PC2903 | 2025-06-20 | Inv. 141522403 - Retainage |  | 97000 | 4850 | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  |  |  | 97000 |  | 97000 | 0
|  | Totals: | 97000 |  | 97000 |  | 0

## #9405.00 DCI Group #24-013 CA
DOC CBC 2 AMPB Building Renovations
Project # 9405.00
Program code 940500 |  |  | Major Program 4B01
DCI Group #24-013 CA |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525090913 | 2025-03-31 | PO Procore | 4999.63 | 4999.63 |  |  | 4999.63
PRC 3352509PA0913 | 2025-04-15 | Inv. 24-013 CA 01 |  | 4999.63 | 2867.83 | 2867.83 | 2131.8
PRC 3352509PB0913 | 2025-05-19 | Inv. 24-013 CA 02 |  | 4999.63 | 1483 | 4350.83 | 648.8
PRC 3352509PC0913 | 2025-06-17 | Inv. 24-013 CA 03 FINAL | -38.15 | 4961.48 | 610.65 | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  |  |  | 4961.48 |  | 4961.48 | 2.0606e-13
|  | Totals: | 4961.48 |  | 4961.48 |  | 0 | FINAL

## RECAP #9406.00
DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement
Project # 9406.00
Program code 940600 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 04/30/24

## #9406.00 Funds Rec'd
DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement
Project # 9406.00
Program code 940600 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9406.00 Vendor A
DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement
Project # 9406.00
Program code 940600 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9406.00 PM TIME
DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement
Project # 9406.00
Program code 940600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brad T. |  |  |  | eDAS E2CL
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9406.00 Misc
DOC CBC District 2 AMPB Furnace, AC and IT Cooling Replacement
Project # 9406.00
Program code 940600 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9412.00
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
| Program code 941200 |  |  | Major Program 4E12
Recap
Acct. Codes-0506-335-DA24
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 317000
C | DCI GROUP |  | 7012 | 7012 | 0
| PM TIME |  | 15711.18 | 15711.18 | 0
| Misc. |  | 11335.29 | 11335.29 | 0
| MA Architecture |  | 24990 | 24538 | 452
C | Bergstrom Construction |  | 43419.91 | 43419.91 | 0
| DCI Group (2) |  | 24455.46 | 22455.46 | 2000
C | Siemens Industry |  | 0 | 0 | 0
C | Proctor Mechanical |  | 38121.93 | 38121.93 | 0
C | Johnson Controls |  | 9888 | 9888 | 0
C | Walsh Doors |  | 17044.27 | 17044.27 | 0
C | Commonwealth Electric |  | 50301.15 | 50301.15 | 0
| Johnson Controls (2) |  | 14984.61 | 0 | 14984.61
| Total Project Cost | 317000 | 257263.8 | 239827.19 | 17436.61 | 59736.2

## #9412.00 Funds Rec'd
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 041224TLG09DAS | 2024-04-16 | 50000 | 50000
|  |  | MOU Amend #1 | IET 062024TLG03DAS | 2024-06-20 | 160000 | 160000
|  |  | Return FY24 Funds to Agency | IET 33524240900 | 2024-08-27 | -178247.63 | -178247.63
|  |  | Received FY25 Funds From Agency | IET 33530AU24TLG1325 | 2024-09-04 | 285247.63 | 285247.63
| Total Requested | 0 | Total Transferred |  |  | 317000 | 317000

## #9412.00 DCI Group
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524115902 | 2024-04-24 | PO Procore | 7062.61 | 7062.61 |  |  | 7062.61
PRC 3352411PA5902 | 2024-05-02 | Inv. 24-016 PC 01 |  | 7062.61 | 1320.74 | 1320.74 | 5741.87
PRC 3352411PB5902 | 2024-06-19 | Inv. 24-016 PC 02 |  | 7062.61 | 3155.36 | 4476.1 | 2586.51
PRC 3352411PC5902 | 2024-07-22 | Inv. 24-016 PC 03 FINAL | -50.61 | 7012 | 2535.9 | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  |  |  | 7012 |  | 7012 | -3.2685e-13
|  | Totals: | 7012 |  | 7012 |  | 0 | FINAL

## #9412.00 PM TIME
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - James T. |  |  |  | eDAS: E2CQ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15711.18 | 15711.18 |  |  | 15711.18
IET DAS202410115300001 | 2024-05-07 | 2507 | Finance Support for April 1-30, 2024 |  | 15711.18 | 97.47 | 97.47 | 15613.71
IET DAS202410115300001 | 2024-05-07 | 9500 | DAS Services for April 1-30, 2024 |  | 15711.18 | 865.1 | 962.57 | 14748.61
IET DAS202411115300001 | 2024-06-10 | 2507 | Finance Support for May 1-31 2024 |  | 15711.18 | 157.58 | 1120.15 | 14591.03
IET DAS202411115300001 | 2024-06-10 | 9500 | DAS Services for May 1-31 2024 |  | 15711.18 | 1303.5 | 2423.65 | 13287.53
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 15711.18 | 196.97 | 2620.62 | 13090.56
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 15711.18 | 1799.1 | 4419.72 | 11291.46
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 15711.18 | 160.09 | 4579.81 | 11131.37
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 15711.18 | 1746.2 | 6326.01 | 9385.17
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 15711.18 | 189.44 | 6515.45 | 9195.73
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 15711.18 | 964.9 | 7480.35 | 8230.83
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 15711.18 | 184.11 | 7664.46 | 8046.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 15711.18 | 1636.1 | 9300.56 | 6410.62
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 15711.18 | 325.16 | 9625.72 | 6085.46
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 15711.18 | 2170.1 | 11795.82 | 3915.36
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15711.18 | 269.99 | 12065.81 | 3645.37
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15711.18 | 1790.9 | 13856.71 | 1854.47
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15711.18 | 95.07 | 13951.78 | 1759.4
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15711.18 | 950.2 | 14901.98 | 809.2
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 15711.18 | 11.67 | 14913.65 | 797.53
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 15711.18 | 80.2 | 14993.85 | 717.33
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 15711.18 | 90.83 | 15084.68 | 626.5
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 15711.18 | 626.5 | 15711.18 | 0
[5 empty] | 15711.18 |  | 15711.18 | 0
[5 empty] | 15711.18 |  | 15711.18 | 0
[5 empty] | 15711.18 |  | 15711.18 | 0
[5 empty] | 15711.18 |  | 15711.18 | 0
[5 empty] | 15711.18 |  | 15711.18 | 0
|  |  | Totals: | 15711.18 |  | 15711.18 |  | 0
Note on E9: Huggins, Joni [DAS]: Fwd: PM Time Posted $Joni Trower, James 10:41 AM (4 minutes ago) to me Finance: See below in red: Thanks, James ---------- Forwarded message --------- From: Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> Date: Thu, Sep 19, 2024 at 9:45 AM Subject: PM Time Posted To: James Trower <james.trower@iowa.gov> Good morning Pm Time posted and the following projects need attention: DA23 9346.00 -745.45 Increase PM Time by $2,000 DA24 9412.00 -480.35 Increase PM Time by $2,000 MM22 9226.00 -21.02 Increase PM Time by $6,000 PARK 9411.00 -1557.83 Increase PM Time by $10,000 Trower, James Oct 10, 2024, 5:11 PM (14 hours ago) to me Finance - DA24 9400.00 -879.20 INCREASE PM TIME BY $2,000. DA24 9412.00 -300.56 INCREASE PM TIME BY $2,000. Please see below: On Tue, Nov 12, 2024 at 7:19 AM Huggins, Joni <joni.huggins@iowa.gov> wrote: DA23 9344.00 (1407.82) Increase PM Time by $4,000 DA24 9412.00 (795.82) Increase PM Time by $2,000 MM22 9364.00 (650.47) Increase PM Time by $650.47 MM22 9407.00 (633.47) Increase PM Time by $3,000 Re: November PM Time - $Joni Trower, James Thu, Dec 12, 3:31 PM (4 days ago) to me Please see below in red: On Tue, Dec 10, 2024 at 10:08 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Good morning DA24 9412.00 -856.71 Increase PM Time by $2,000 MM22 9364.00 -91.14 Increase PM Time by $2,000 MM23 9373.00 -340.15 Increase PM Time by $3,000 PARK 9411.0 -1,407.60 Increase PM Time by $10,000 Re: April PM Time $Joni Trower, James 1:21 PM (6 minutes ago) to me Finance - See below: DA23 9344.00 -329.40 Increase PM Time by 329.40 DA24 9412.00 -711.18 Increase PM Time by 711.18 Thanks, James

## #9412.00 Misc
DOC 5JD Admin Office BAS Replacement
Project # 9412.00
Program code 941200 |  |  |  | Major Program 4E12
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T. |  |  |  | Shipping Code: 035
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202412115300001 | 2024-07-10 | 2507 |  | Electric Services June 01-30, 2024 | DAS2024121153 | 91.94 | 91.94
GAX 33524204903 | 2024-07-22 | 9500 | BRUM | Commonwealth Electic V#(00002135378) | Inv. 73141 | 2503.71 | 2595.65
IET DAS202501115300001 | 2024-08-07 | 2507 |  | Fire Watch Services July 1-31, 2024 | DAS2025011153 | 192.2 | 2787.85
IET DAS202503115300001 | 2024-10-09 | 2507 |  | Space Planning September 1-30,2024 | DAS2025031153 | 285 | 3072.85
GAX 33525289904 | 2024-10-15 | 9500 | BRUM | Ralph N Smith Inc V#(00002106937) | Inv. 30758 | 1735 | 4807.85
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Fire Watch Services October 01-31, 2024 | DAS2025041153 | 1154.98 | 5962.83
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning October 01-31, 2024 | DAS2025041153 | 855 | 6817.83
IET DAS202505115300001 | 2024-12-06 | 2507 |  | Locksmith & Key Services November 01-30, 2024 | DAS2025051153 | 475.73 | 7293.56
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Service December 01-31, 2024 | DAS2025061153 | 427.5 | 7721.06
IET 33525031903 | 2025-01-31 | 9210 |  | ICN Bill | Inv. 713342 | 476.86 | 8197.92
IET DAS202508115300001 | 2025-03-10 | 2507 |  | Space Planning Service February 01-28, 2025 | DAS2025081153 | 47.5 | 8245.42
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Service March 1-31, 2025 | DAS2025091153 | 973.75 | 9219.17
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Electric Services April 1-30, 2025 | DAS2025101153 | 168.62 | 9387.79
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Space Planning Services April 01-30, 2025 | DAS2025101153 | 1900 | 11287.79
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Space Plannig May 01-31, 2025 | DAS2025111153 | 47.5 | 11335.29
11335.29
11335.29
11335.29
|  |  |  | Totals: |  | 11335.29

## #9412.00 MA Architecture
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
MA Architecture |  |  | Vendor: 00003166868
Acct. Codes-0506-335-DA24-9260 |  |  | TSB
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524120905 | 2024-04-29 | PO Procore | 24370 | 24370 |  |  | 24370
PRC 3352412PA0905 | 2024-07-05 | Inv. 2401 |  | 24370 | 17725 | 17725 | 6645 | FY24
PO 33525120905 | 2024-08-16 | Roll to FY25 | 0 | 24370 |  | 17725 | 6645
PRC 3352512PB0905 | 2024-09-23 | Inv. 2402 |  | 24370 | 2125 | 19850 | 4520
PO 33525120905 | 2024-10-22 | CO #1 | 620 | 24990 |  | 19850 | 5140
PRC 3352512PC0905 | 2024-11-08 | Inv. 2403 |  | 24990 | 4688 | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  |  |  | 24990 |  | 24538 | 452
|  | Totals: | 24990 |  | 24538 |  | 452

## #9412.00 Bergstrom Construction
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00 | [6 empty] | 1
Program code 941200 |  |  | Major Program 4E12
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0506-335-DA24-9255 |  |  | MA 23199
Project Manager - James T. |  |  | Activity code: Brum
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525184900 | 2024-07-02 | PO Procore | 62475 | 62475 |  |  | 62475
PRC 3352518PA4900 | 2024-09-06 | Inv. 8712-1 |  | 62475 | 10093.76 | 10093.76 | 52381.24 | 531.25
PRC 3352518PB4900 | 2025-02-11 | Inv. 8712-2 |  | 62475 | 31155.15 | 41248.91 | 21226.09 | 2171
PRC 3352518PC4900 | 2025-04-09 | Inv. 8712-retainage | -19055.09 | 43419.91 | 2171 | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  |  |  | 43419.91 |  | 43419.91 | 0
|  | Totals: | 43419.91 |  | 43419.91 |  | 0 | FINAL

## #9412.00 DCI Group (2)
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525256903 | 2024-09-12 | PO Procore | 24455.46 | 24455.46 |  |  | 24455.46
PRC 3352525PA6903 | 2024-09-23 | Inv. 24-016 CA 01 |  | 24455.46 | 5820.61 | 5820.61 | 18634.85
PRC 3352525PB6903 | 2024-10-17 | Inv. 24-016 CA 02 |  | 24455.46 | 6160.02 | 11980.63 | 12474.83
PRC 3352525PC6903 | 2024-11-22 | Inv. 24-016 CA 03 |  | 24455.46 | 6002.85 | 17983.48 | 6471.98
PRC 3352525PD6903 | 2025-01-03 | Inv. 24-016 CA 04 |  | 24455.46 | 2464.56 | 20448.04 | 4007.42
PRC 3352525PE6903 | 2025-01-27 | Inv. 24-016 CA 05 |  | 24455.46 | 1183.42 | 21631.46 | 2824
PRC 3352525PF6903 | 2025-02-11 | Inv. 24-016 CA 06 |  | 24455.46 | 824 | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  |  |  | 24455.46 |  | 22455.46 | 2000
|  | Totals: | 24455.46 |  | 22455.46 |  | 2000
|  | CM Staff Hours | 22455.46 |  | 22455.46 |  | 0
|  | Reimbursables | 2000 |  |  |  | 2000
|  | Total: | 24455.46 |  | 22455.46 |  | 2000

## #9412.00 Siemens Industry
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Siemens Industry |  |  | Vendor: 00002089900
Acct. Codes-0506-335-DA24-9255 |  |  | MA20358A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525256906 | 2024-09-12 | PO Procore | 2520 | 2520 |  |  | 2520
DO 33525256906 | 2025-02-24 | Closing DO Per PM | -2520 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9412.00 Proctor Mechanical
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0506-335-DA24-9255 |  |  | MA21010A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525256908 | 2024-09-12 | PO Procore | 52378 | 52378 |  |  | 52378
PRC 3352525PA6908 | 2025-03-06 | Inv. 901844 |  | 52378 | 36215.83 | 36215.83 | 16162.17 | 1906.1
PRC 3352525PB6908 | 2025-04-16 | Inv. 901844 Retainage | -14256.07 | 38121.93 | 1906.1 | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  |  |  | 38121.93 |  | 38121.93 | 0
|  | Totals: | 38121.93 |  | 38121.93 |  | 0 | FINAL

## #9412.00 Johnson Controls
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Johnson Controls |  |  | Vendor: 00002139022
Acct. Codes-0506-335-DA24-9255 |  |  | MA 24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525257904 | 2024-09-12 | DO Procore | 9888 | 9888 |  |  | 9888
PRC 3352525PA7904 | 2025-02-10 | Inv. 52404072 - Final |  | 9888 | 9888 | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  |  |  | 9888 |  | 9888 | 0
|  | Totals: | 9888 |  | 9888 |  | 0 | FINAL

## #9412.00 Walsh Doors
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Walsh Doors |  |  | Vendor: 00002113318
Acct. Codes-0506-335-DA24-9255 |  |  | MA21018C
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525257905 | 2024-09-12 | DO Procore | 17044.27 | 17044.27 |  |  | 17044.27
PRC 3352525PA7905 | 2024-10-15 | Inv. 816083 |  | 17044.27 | 17044.27 | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  |  |  | 17044.27 |  | 17044.27 | 0
|  | Totals: | 17044.27 |  | 17044.27 |  | 0 | FINAL

## #9412.00 Commonwealth Electric
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Commonwealth Electric |  |  | Vendor: 00002135378
Acct. Codes-0506-335-DA24-9255 |  |  | MA20450A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525257907 | 2024-09-13 | PO Procore | 73440 | 73440 |  |  | 73440
PRC 3352525PA7907 | 2025-02-10 | Inv. 78851 |  | 73440 | 47057.71 | 47057.71 | 26382.29 | 2476.72
PRC 3352525PB7907 | 2025-04-03 | Inv. 11085 |  | 73440 | 728.38 | 47786.09 | 25653.91 | 2515.06
PRC 3352525PC7907 | 2025-04-16 | Inv. 25628 Retainage | -23138.85 | 50301.15 | 2515.06 | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  |  |  | 50301.15 |  | 50301.15 | 0
|  | Totals: | 50301.15 |  | 50301.15 |  | 0 | FINAL

## #9412.00 Johnson Controls (2)
DPS CC Oran Pape Levels 2-5 Renovation (SLFRF)
Project # 9412.00
Program code 941200 |  |  | Major Program 4E12
Johnson Controls (2) |  |  | Vendor: 00002139022
Acct. Codes-0506-335-DA24-9255 |  |  | MA24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525031908 | 2025-01-31 | DO Procore | 14984.61 | 14984.61 |  |  | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  |  |  | 14984.61 |  | 0 | 14984.61
|  | Totals: | 14984.61 |  | 0 |  | 14984.61
|  | CM Staff Hours | 5710.55 |  |  |  | 5710.55
|  | Reimbursables | 9274.06 |  |  |  | 9274.06
|  | Total: | 14984.61 |  | 0 |  | 14984.61

## RECAP #9414.00
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
| Program code 941400 |  |  | Major Program 4E12
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursement
| Funds received per MOU | 768346.9
C | DCI Group #24-018 PC (P) (Unencumbered) |  | 16848.36 | 16848.36 | 0 |  | 0
| PM TIME |  | 29000 | 23948.19 | 5051.81
| Misc. |  | 11637.25 | 11637.25 | 0
| SVPA Architects (Unencumbered) |  | 160901 | 160901 | 0 |  | 22135
| DCI Group #24-018 CA (Unencumbered) |  | 76048.35 | 76048.35 | 0 |  | 164595.41
| PAR Industries (Unencumbered) |  | 0 | 0 | 0 |  | 513887.25
| Pleva Plumbing & Heating (unencumbered) |  | 95474.05 | 95474.05 | 0 |  | 984754.95
| Eick & Day Construction |  | 213059.64 | 213059.64 | 0 |  | 444192.56
| Elite Fire Sprinkler System |  | 13837.89 | 13837.89 | 0 |  | 33752.11
| Total Project Cost | 768346.9 | 616806.54 | 611754.73 | 5051.81 | 151540.36 | 2163317.28

## #9414.00 Funds Rec'd
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 062624TLG13DAS | 2024-06-27 | 10000 | 10000
|  |  | MOU | IET 33505AU2401HBO25 | 2024-08-06 | 3000 | 3000
|  |  | Returning FY24 Funds to Agency | IET 33524241901 | 2024-08-27 | -1435.1 | -1435.1
|  |  | MOU | IET 33530AU24TLG0725 | 2024-08-30 | 50000 | 50000 | `
|  |  | MOU Amendment #1 | IET 33526NO24TLG0525 | 2024-11-26 | 75000 | 75000
|  |  | MOU Amendment #1 | IET 33513DE24TLG1725 | 2024-12-13 | 20000 | 20000
|  |  | MOU Amendment #1 | IET 33514JA25KLC0125 | 2025-01-14 | 20000 | 20000
|  |  | MOU Amendment #1 | IET 33519FE25TLG0125 | 2025-02-20 | 25000 | 25000
|  |  | MOU Amendment #1 | IET 33524MR25TLG0825 | 2025-03-25 | 50000 | 50000
|  |  | MOU Amendment #1 | IET 33501MY25TLG0725 | 2025-05-02 | 100000 | 100000
|  |  | MOU Amendment #1 | IET 33514MY25TLG0625 | 2025-05-15 | 228782 | 228782
|  |  | MOU Amendment #1 | IET 33526JN25TLG0125 | 2025-06-26 | 188000 | 188000
| Total Requested | 0 | Total Transferred |  |  | 768346.9 | 768346.9
MOU Amendment #1 is for a total of $1,000,000.00

## #9414.00 DCI Group #22-018 PC
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
DCI Group #24-018 PC |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Event Type PR07
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524134803 | 2024-05-13 | PO IA Advantage (Unencumbered) | 16848.36 | 16848.36 |  |  | 16848.36
PRC 3352413PA4803 | 2024-06-24 | Inv. 24-018 PC 01 |  | 16848.36 | 2258.73 | 2258.73 | 14589.63
PRC 3352413PB4803 | 2024-07-18 | Inv. 24-018 PC 02 |  | 16848.36 | 1999.53 | 4258.26 | 12590.1 | FY24
PO 33525134803 | 2024-08-16 | Roll to FY25 |  | 16848.36 |  | 4258.26 | 12590.1
PRC 3352513PC4803 | 2024-09-04 | Inv. 24-018 PC 03 |  | 16848.36 | 1787.94 | 6046.2 | 10802.16
PRC 3352513PD4803 | 2024-09-17 | Inv. 24-018 PC 04 |  | 16848.36 | 2790.52 | 8836.72 | 8011.64
PRC 3352513PE4803 | 2024-10-15 | Inv. 24-018 PC 05 |  | 16848.36 | 2436.23 | 11272.95 | 5575.41
PRC 3352513PF4803 | 2024-11-18 | Inv. 24-018 PC 06 |  | 16848.36 | 2033.62 | 13306.57 | 3541.79
PRC 3352513PG4803 | 2024-12-23 | Inv. 24-018 PC 07 |  | 16848.36 | 2436.23 | 15742.8 | 1105.56
PRC 3352513PH4803 | 2025-01-24 | Inv. 24-018 PC 08 - Final |  | 16848.36 | 1105.56 | 16848.36 | 0
|  |  |  | 16848.36 |  | 16848.36 | 0
|  |  |  | 16848.36 |  | 16848.36 | 0
|  |  |  | 16848.36 |  | 16848.36 | 0
|  | Totals: | 16848.36 |  | 16848.36 |  | 0 | FINAL
|  | Contract | 16848.36 |  | 16848.36 |  | 0
|  | Total: | 16848.36 |  | 16848.36 |  | 0

## #9414.00 PM TIME
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A |  |  |  | eDAS: E2D3
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 29000 | 29000 |  |  | 29000
CDE 00524169802 | 2024-06-17 | 2507 | Move funds from 9415.00 to 9414.00 |  | 29000 | 313.63 | 313.63 | 28686.37
CDE 00524169802 | 2024-06-17 | 9500 | Move funds from 9415.00 to 9414.00 |  | 29000 | 2625.5 | 2939.13 | 26060.87
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 29000 | 134.61 | 3073.74 | 25926.26
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 29000 | 1232.9 | 4306.64 | 24693.36
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 29000 | 69.56 | 4376.2 | 24623.8
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 29000 | 755.8 | 5132 | 23868
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 29000 | 348.45 | 5480.45 | 23519.55
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 29000 | 1772 | 7252.45 | 21747.55
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 29000 | 152.84 | 7405.29 | 21594.71
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 29000 | 1358.5 | 8763.79 | 20236.21
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 29000 | 328.12 | 9091.91 | 19908.09
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 29000 | 2186.6 | 11278.51 | 17721.49
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 29000 | 252.84 | 11531.35 | 17468.65
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 29000 | 1680 | 13211.35 | 15788.65
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 29000 | 150.89 | 13362.24 | 15637.76
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 29000 | 1508.5 | 14870.74 | 14129.26
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 29000 | 175.36 | 15046.1 | 13953.9
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 29000 | 1869.5 | 16915.6 | 12084.4
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 29000 | 352.04 | 17267.64 | 11732.36
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 29000 | 1521.7 | 18789.34 | 10210.66
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 29000 | 148.88 | 18938.22 | 10061.78
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 29000 | 1068 | 20006.22 | 8993.78
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 29000 | 248.17 | 20254.39 | 8745.61
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 29000 | 1702.7 | 21957.09 | 7042.91
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 29000 | 225.7 | 22182.79 | 6817.21
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 29000 | 1765.4 | 23948.19 | 5051.81
[5 empty] | 29000 |  | 23948.19 | 5051.81
[5 empty] | 29000 |  | 23948.19 | 5051.81
[5 empty] | 29000 |  | 23948.19 | 5051.81
|  |  | Totals: | 29000 |  | 23948.19 |  | 5051.81
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Adams, Brandon 12:11 PM (0 minutes ago) to me Please increase PM Time budget $2,000 for 9414.00 in DA24. Adams, Brandon 9:28 AM (17 minutes ago) to me Finance, Please increase my PM Time for the following projects: DA24 9414.00 $3,000 DA24 9423.00 $3,000 From: Adams, Brandon <brandon.adams@iowa.gov> Date: Tue, Nov 12, 2024 at 11:19 AM Subject: Re: October PM Time Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Please increase my PM Time on the following projects: DA24 9414.00 $5,000 DA24 9423.00 $5,000 MM22 9429.00 $2,000 MM22 9387.00 $4,000 MM23 9317.00 $4,000 Adams, Brandon 1:12 PM (41 minutes ago) to me Joni, Please increase the following PM Time: DA24 9414.00 - $3,500 MM23 9465.00 - $1,500 MM24 9392.00 - $5,000 Re: PM Time for February has posted $Joni Adams, Brandon 10:57 AM (3 minutes ago) to me Please increase DA24 9414.00 by $5,000. Regards, Brandon Adams Owner's Representative, State Design & Cons Adams, Brandon Jun 16, 2025, 3:19 PM (15 hours ago) to me Finance, Please increase the following projects PM Time: 9414.00 DA24 increase by $8,000 9370.00 MM23 increase by $2,000 9361.00 MM24 increase by $3,000 9396.00 MM24 increase by $3,500 Regards, Brandon Adams Adams, Brandon 8:56 AM (6 minutes ago) to me Joni, Please increase by $7,000. Regards, Brandon Adams

## #9414.00 Misc
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  |  | Major Program 4E12
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 035
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525036907 | 2025-02-05 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV046218 | 4249 | 4249
GAX 33525062902 | 2025-03-04 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. TN42982 | 3212.5 | 7461.5
PRC 33525085900 | 2025-03-26 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 823610 | 2575 | 10036.5
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Service March 1-31, 2025 | DAS2025091153 | 261.25 | 10297.75
GAX 33525105905 | 2025-04-15 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. TN64175 | 1339.5 | 11637.25
11637.25
11637.25
11637.25
11637.25
11637.25
11637.25
11637.25
|  |  |  | Totals: |  | 11637.25

## #9414.00 SVPA Architects
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
SVPA Architects |  |  | Vendor: 00002109254
Acct. Codes-0506-335-DA24-9260 |  |  | RFP 941400-01
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525200903 | 2024-08-07 | PO IA Advantage (Unencumbered) | 160901 | 160901 |  |  | 160901
PRC 3352520PA0903 | 2024-09-16 | Inv. 9414.00-01 |  | 0 | 13550 | 13550 | 147351
PRC 3352520PB0903 | 2024-10-30 | Inv. 0039945 |  | 0 | 14250 | 27800 | 133101
PRC 3352520PC0903 | 2024-12-03 | Inv. 0040058 |  | 0 | 56750 | 84550 | 76351
PRC 3352520PD0903 | 2024-12-17 | Inv. 0040134 |  | 0 | 30825 | 115375 | 45526
PRC 3352520PE0903 | 2025-01-15 | Inv. 0040203 |  | 0 | 20410 | 135785 | 25116
PRC 3352520PF0903 | 2025-02-18 | Inv. 0040279 |  | 0 | 6615 | 142400 | 18501
PRC 3352520PG0903 | 2025-03-17 | Inv. 0040359 |  | 0 | 8231 | 150631 | 10270
PRC 3352520PH0903 | 2025-04-16 | Inv. 0040438 |  | 0 | 1620 | 152251 | 8650
PRC 3352520PI0903 | 2025-05-15 | Inv. 0040517 |  | 0 | 5372 | 157623 | 3278
PRC 3352520PJ0903 | 2025-06-30 | Inv. 0040539 |  | 0 | 3278 | 160901 | 0
|  |  |  | 0 |  | 160901 | 0
|  |  |  | 0 |  | 160901 | 0
|  | Totals: | 160901 |  | 160901 |  | 0
|  | Contract | 27800 |  | 27800 |  | 0
|  | CO #1 10/25/24 | 147000 |  | 131350 |  | 15650
|  | CO #2 02/21/25 | 1751 |  | 1751 |  | 0
|  | CO #3 06/25/25 | 6485 |  |  |  | 6485
|  | Total: | 183036 |  | 160901 |  | 22135 | CO #3 not included in Inv.0040539

## #9414.00 DCI Group #24-018 (2)
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
DCI Group #24-018 PC |  |  | Vendor:00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525043906 | 2025-02-11 | PO Procore (Unencumbered) | 76048.35 | 76048.35 |  |  | 76048.35
PRC 3352504PA3906 | 2025-03-26 | Inv. 24-018 CA 01 |  | 76048.35 | 5530.22 | 5530.22 | 70518.13
PRC 3352504PB3906 | 2025-04-16 | Inv. 24-018 CA 02 |  | 76048.35 | 6849.25 | 12379.47 | 63668.88
PRC 3352504PC3906 | 2025-05-14 | Inv. 24-018 CA 03 |  | 76048.35 | 29499.95 | 41879.42 | 34168.93
PRC 3352504PD3906 | 2025-06-30 | Inv. 24-018 CA 04 |  | 76048.35 | 34168.93 | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  |  |  | 76048.35 |  | 76048.35 | 0
|  | Totals: | 76048.35 |  | 76048.35 |  | 0
|  | CM Staff Hours | 142107.48 |  | 46062.54 |  | 96044.94
|  | Fee | 90536.28 |  | 29876.97 |  | 60659.31
|  | Reimbursables | 8000 |  | 108.84 |  | 7891.16
|  | Total: | 240643.76 |  | 76048.35 |  | 164595.41
|  | Total Contract: | 240643.76 |  | 76048.35 |  | 164595.41

## #9414.00 PAR Industries
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
PAR Industries |  |  | Vendor: 00003068805
Acct. Codes-0506-335-DA24-9255 |  |  | RFB941400-01
Project Manager - Brandon A |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525049900 | 2025-02-18 | PO Procore (Unencumbered) |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | Contract | 501231 |  |  |  | 501231
|  | CO #1 05/22/25 | 12656.25 |  |  |  | 12656.25
|  | Total Contract: | 513887.25 |  | 0 |  | 513887.25

## #9414.00 Pleva Plumbing
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
Pleva Plumbing & Heating |  |  | Vendor: 00003054699
Acct. Codes-0506-335-DA24-9255 |  |  | RFB941400-01
Project Manager - Brandon A |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525060904 | 2025-02-18 | PO Procore (Unencumbered) | 95474.05 | 95474.05 |  |  | 95474.05
PRC 3352506PA0904 | 2025-05-05 | Inv. 9414.00-01 |  | 95474.05 | 95474.05 | 95474.05 | 0 | 5024.95
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  |  |  | 95474.05 |  | 95474.05 | 0
|  | Totals: | 95474.05 |  | 95474.05 |  | 0
|  | Contract | 1077186 |  | 95474.05 |  | 981711.95
|  | CO #1 05/22/25 | 3043 |  |  |  | 3043
|  | Total Contract: | 1080229 |  | 95474.05 |  | 984754.95

## #9414.00 Eick & Day
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
Eick & Day Construction |  |  | Vendor: VS000005512
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 941400-01
Project Manager - Brandon A |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525063901 | 2025-03-05 | PO Procore (Unencumbered) | 213059.64 | 213059.64 |  |  | 213059.64
PRC 3352506PA3901 | 2025-04-16 | Inv. 24829.01 |  | 213059.64 | 32445.35 | 32445.35 | 180614.29 | 1707.65
PRC 3352506PB3901 | 2025-05-29 | Inv. 24829.02 |  | 213059.64 | 180614.29 | 213059.64 | 0 | 11213.68
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  |  |  | 213059.64 |  | 213059.64 | 0
|  | Totals: | 213059.64 |  | 213059.64 |  | 0
|  | Contract | 637400 |  | 213059.64 |  | 424340.36
|  | CO # 1 05/22/25 | 18785.57 |  |  |  | 18785.57
|  | CO #2 06/25/25 | 1066.63 |  |  |  | 1066.63
|  | Total Contract: | 657252.2 |  | 213059.64 |  | 444192.56

## #9414.00 Elite Fire Sprinkler
DPS DSM New Fleet Building Renovations (SLFRF)
Project # 9414.00
Program code 941400 |  |  | Major Program 4E12
Elite Fire Sprinkler Systems |  |  | Vendor: 00003212887
Acct. Codes-0506-335-DA24-9255 |  |  | RFB941400-01
Project Manager - Brandon A |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525063902 | 2025-03-05 | PO Procore (Unencumbered) | 13837.89 | 13837.89 |  |  | 13837.89
PRC 3352506PA3902 | 2025-05-13 | Inv. 9414.00-01 |  | 13837.89 | 6650 | 6650 | 7187.89 | 350
PRC 3352506PB3902 | 2025-05-29 | Inv. 9414.00 Pay App 2 |  | 13837.89 | 7187.89 | 13837.89 | 0 | 728.31
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  |  |  | 13837.89 |  | 13837.89 | 0
|  | Totals: | 13837.89 |  | 13837.89 |  | 0
|  | Total Contract: | 47590 |  | 13837.89 |  | 33752.11
Vendor has used Inv. Pay App X for another project please use 9414.00 Pay App X

## RECAP #9423.00
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
| Program code 942300 |  |  | Major Program 4E12
Recap
Acct. Codes-0506-335-DA24
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Reimbursement
| Funds received per MOU | 617968.19
C | DCI Group (Unencumbered) |  | 16262.29 | 16262.29 | 0
| PM TIME |  | 20000 | 15272.77 | 4727.23
| Misc. |  | 2928.05 | 2928.05 | 0
| OPN Architects (Unencumbered) |  | 196994.56 | 196994.56 | 0 |  | 35530.44
| Keystone Construction Services(Unencumbered) |  | 209649.11 | 209649.11 | 0 |  | 49357.11
| TriCity Electric(Unencumbered) |  | 10157.18 | 10157.18 | 0 |  | 115832.27
| Air Con Mechanical(Unencumbered) |  | 11742.95 | 11742.95 | 0 |  | 218664.48
| Eick & Day Construction(Unencumbered) |  | 46766.4 | 46766.4 | 0 |  | 660593.6
| DCI Group 2(Unencumbered) |  | 46090.37 | 46090.37 | 0 |  | 132056.89
| Total Project Cost | 617968.19 | 560590.91 | 555863.68 | 4727.23 | 57377.28 | 1212034.79

## #9423.00 Funds Rec'd
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Transferred into incorrect unit FY24 | CDR 33525220906 | 2024-08-07 | 2500 | 2500
|  |  | Funds Transferred into incorrect unit FY25 | CDR 33525220901 | 2024-08-07 | 4000 | 4000
|  |  | Returning FY24 Funds to Agency | IET 33524241902 | 2024-08-27 | -481.43 | -481.43
|  |  | Funds Transferred into incorrect unit | CDR 33525247900 | 2024-09-02 | 50000 | 50000
|  |  | MOU | IET 33526NO24TLG0325 | 2024-11-26 | 89000 | 89000
|  |  | MOU | IET 33505DE24TLG0325 | 2024-12-09 | 50000 | 50000
|  |  | MOU | IET 33528FE25TLG0125 | 2025-02-28 | 20000 | 20000
|  |  | MOU | IET 33524MR25TLG0725 | 2024-03-25 | 50000 | 50000
|  |  | MOU | IET 33501MY25TLG0825 | 2025-05-01 | 50000 | 50000
|  |  | MOU | IET 33514MY25TLG0125 | 2025-05-15 | 102949.62 | 102949.62
|  |  | MOU | IET 33509JN25TLG0325 | 2025-06-11 | 200000 | 200000
| Total Requested | 0 | Total Transferred |  |  | 617968.19 | 617968.19

## #9423.00 DCI Group
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524197900 | 2024-07-15 | PO Procore(Unencumbered) | 16262.29 | 16262.29 |  |  | 16262.29
PRC 3352419PA7900 | 2024-07-19 | Inv. 24-030 PC 01 |  | 16262.29 | 992 | 992 | 15270.29 | FY24
PO 33525197900 | 2024-08-16 | Roll to FY25 |  | 16262.29 |  | 992 | 15270.29
PRC 3352519PB7900 | 2024-09-04 | Inv. 24-030 PC 02 |  | 16262.29 | 2504.41 | 3496.41 | 12765.88
PRC 3352519PC7900 | 2024-09-17 | Inv. 24-030 PC 03 |  | 16262.29 | 2838.84 | 6335.25 | 9927.04
PRC 3352519PD7900 | 2024-10-15 | Inv. 24-030 PC 04 |  | 16262.29 | 1910.78 | 8246.03 | 8016.26
PRC 3352519PE7900 | 2024-11-18 | Inv. 24-030 PC 05 |  | 16262.29 | 2877.55 | 11123.58 | 5138.71
PRC 3352519PF7900 | 2024-12-23 | Inv. 24-030 PC 06 |  | 16262.29 | 3541.79 | 14665.37 | 1596.92
PRC 3352519PG7900 | 2025-01-24 | Inv. 24-030 PC 07 FINAL |  | 16262.29 | 1596.92 | 16262.29 | 0
|  |  |  | 16262.29 |  | 16262.29 | 0
|  |  |  | 16262.29 |  | 16262.29 | 0
|  |  |  | 16262.29 |  | 16262.29 | 0
|  |  |  | 16262.29 |  | 16262.29 | 0
|  | Totals: | 16262.29 |  | 16262.29 |  | 0 | FINAL
|  | Total Contract | 16262.29 |  | 16262.29 |  | 0
|  | Total: | 16262.29 |  | 16262.29 |  | 0

## #9423.00 PM TIME
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Brandon A. |  |  |  | eDAS: E2DK
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 20000 | 101.07 | 101.07 | 19898.93
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 20000 | 925.5 | 1026.57 | 18973.43
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 20000 | 118.98 | 1145.55 | 18854.45
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 20000 | 1296 | 2441.55 | 17558.45
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 20000 | 145.91 | 2587.46 | 17412.54
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 20000 | 743.2 | 3330.66 | 16669.34
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 102.27 | 3432.93 | 16567.07
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 905.5 | 4338.43 | 15661.57
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 178.75 | 4517.18 | 15482.82
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 1194.2 | 5711.38 | 14288.62
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 159.1 | 5870.48 | 14129.52
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 1057.2 | 6927.68 | 13072.32
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 156.24 | 7083.92 | 12916.08
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 1559.3 | 8643.22 | 11356.78
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 131.34 | 8774.56 | 11225.44
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 1401.6 | 10176.16 | 9823.84
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 208.95 | 10385.11 | 9614.89
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 903.4 | 11288.51 | 8711.49
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 248 | 11536.51 | 8463.49
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 1775.3 | 13311.81 | 6688.19
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 43.32 | 13355.13 | 6644.87
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 258.7 | 13613.83 | 6386.17
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 188.14 | 13801.97 | 6198.03
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 1470.8 | 15272.77 | 4727.23
[5 empty] | 20000 |  | 15272.77 | 4727.23
[5 empty] | 20000 |  | 15272.77 | 4727.23
[5 empty] | 20000 |  | 15272.77 | 4727.23
[5 empty] | 20000 |  | 15272.77 | 4727.23
[5 empty] | 20000 |  | 15272.77 | 4727.23
|  |  | Totals: | 20000 |  | 15272.77 |  | 4727.23
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Adams, Brandon 1:59 PM (5 minutes ago) to me Please increase PM Time budget $1,000 for 9423.00 in DA24 Regards, Adams, Brandon 9:28 AM (17 minutes ago) to me Finance, Please increase my PM Time for the following projects: DA24 9414.00 $3,000 DA24 9423.00 $3,000 From: Adams, Brandon <brandon.adams@iowa.gov> Date: Tue, Nov 12, 2024 at 11:19 AM Subject: Re: October PM Time Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Please increase my PM Time on the following projects: DA24 9414.00 $5,000 DA24 9423.00 $5,000 MM22 9429.00 $2,000 MM22 9387.00 $4,000 MM23 9317.00 $4,000 Re: PM Time for February has posted $Joni Adams, Brandon 10:50 AM (19 minutes ago) to me Finance, Please increase my PM as follows: DA24 9423.00 $9,500 MM22 9387.00 $1,200 MM23 9370.00 $3,000 MM25 9451.00 $5,000 Regards, Brandon Adams

## #9423.00 Misc
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  |  | Major Program 4E12
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A. |  |  |  | Shipping Code: 1517
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202503115300001 | 2024-10-09 | 2323 |  | Leasing Services September 1-30,2024 | DAS2025031153 | 332.5 | 332.5
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning Services October 1-31 2024 | DAS2025041153 | 308.75 | 641.25
GAX 33525355901 | 2024-12-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV045462 | 2191.8 | 2833.05
IET DAS202506115300001 | 2025-01-09 | 2507 |  | Space Planning Service December 01-31.2024 | DAS2025061153 | 95 | 2928.05
2928.05
2928.05
2928.05
2928.05
2928.05
2928.05
2928.05
2928.05
|  |  |  | Totals: |  | 2928.05

## #9423.00 OPN Architects
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA24-9260 |  |  | RFP 942300-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525222903 | 2024-08-09 | PO Procore(Unencumbered) | 196994.56 | 196994.56 |  |  | 196994.56
PRC 3352522PA2903 | 2024-10-07 | Inv. 24827000-1 |  | 196994.56 | 5319.22 | 5319.22 | 191675.34
PRC 3352522PB2903 | 2024-12-03 | Inv. 24827000-2 |  | 196994.56 | 89300.54 | 94619.76 | 102374.8
PRC 3352522PC2903 | 2024-12-10 | Inv. 24827000-3 |  | 196994.56 | 46425.71 | 141045.47 | 55949.09
PRC 3352522PD2903 | 2025-01-24 | Inv. 24827000-4 |  | 196994.56 | 9182.8 | 150228.27 | 46766.29
PRC 3352522PE2903 | 2025-02-24 | Inv. 24827000-5 |  | 196994.56 | 6796.14 | 157024.41 | 39970.15
PRC 3352522PF2903 | 2025-03-05 | Inv. 24827000-6 |  | 196994.56 | 14674.9 | 171699.31 | 25295.25
PRC 3352522PG2903 | 2025-04-10 | Inv. 24827000-7 |  | 196994.56 | 13557.34 | 185256.65 | 11737.91
PRC 3352522PH2903 | 2025-05-07 | Inv. 24827000-8 |  | 196994.56 | 7597.69 | 192854.34 | 4140.22
PRC 3352522PI2903 | 2025-06-19 | Inv. 24827000-9 |  | 196994.56 | 4140.22 | 196994.56 | 0
|  |  |  | 196994.56 |  | 196994.56 | 0
|  |  |  | 196994.56 |  | 196994.56 | 0
|  |  |  | 196994.56 |  | 196994.56 | 0
|  | Totals: | 196994.56 |  | 196994.56 |  | 0
|  | Design Development Docs | 57849 |  | 57849 |  | 0
|  | Construction Docs | 102141 |  | 102141 |  | 0
|  | Bidding & Negotiations | 6824 |  | 5728.36 |  | 1095.64
|  | Construction Phase | 48861 |  | 20392.2 |  | 28468.8
|  | CO #1 12/23/24 | 16850 |  | 10884 |  | 5966
|  | Total: | 232525 |  | 196994.56 |  | 35530.44

## #9423.00 Keystone Construction
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
Keystone Construction Services |  |  | Vendor: 00003165138
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 942300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525010907 | 2025-01-10 | PO Procore(Unencumbered) | 209649.11 | 209649.11 |  |  | 209649.11
PRC 3352501PA0907 | 2025-05-15 | Inv. 9423.00-01 |  | 209649.11 | 102949.62 | 102949.62 | 106699.49 | 5418.4
PRC 3352501PB0907 | 2025-06-16 | Inv. 9423.00-02 |  | 209649.11 | 106699.49 | 209649.11 | 0 | 11034.16
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  |  |  | 209649.11 |  | 209649.11 | 0
|  | Totals: | 209649.11 |  | 209649.11 |  | 0
|  | Contract | 253000 |  | 203943.2 |  | 49056.8
|  | CO #1 | 1137.96 |  | 1081.06 |  | 56.9
|  | CO #2 | 4868.26 |  | 4624.85 |  | 243.41
|  | Total Contract: | 259006.22 |  | 209649.11 |  | 49357.11

## #9423.00 TriCity Electric
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
TriCity Electric |  |  | Vendor: 00002106567
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 942300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525010913 | 2025-01-10 | PO Procore(Unencumbered) | 10157.18 | 10157.18 |  |  | 10157.18
PRC 3352501PA0913 | 2025-05-20 | Inv. 333150 |  | 10157.18 | 10157.18 | 10157.18 | 0 | 534.59
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  |  |  | 10157.18 |  | 10157.18 | 0
|  | Totals: | 10157.18 |  | 10157.18 |  | 0
|  | Original Contract | 123060 |  | 10157.18 |  | 112902.82
|  | CO#1 06/25/25 | 2929.45 |  |  |  | 2929.45
|  | Total Contract: | 125989.45 |  | 10157.18 |  | 115832.27

## #9423.00 AirCon Mechanical
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
AirCon Mechanical |  |  | Vendor: 00002115651
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 942300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525014900 | 2025-01-14 | PO Procore(Unencumbered) | 11742.95 | 11742.95 |  |  | 11742.95
PRC 3352501PA4900 | 2025-03-04 | Inv. 5108 |  | 11742.95 | 2056.75 | 2056.75 | 9686.2 | 108.25
PRC 3352501PB4900 | 2025-04-24 | Inv. 5143 |  | 11742.95 | 5886.2 | 7942.95 | 3800 | 418.05
PRC 3352501PC4900 | 2025-05-15 | Inv. 5169 |  | 11742.95 | 3800 | 11742.95 | 0 | 618.05
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  |  |  | 11742.95 |  | 11742.95 | 0
|  | Totals: | 11742.95 |  | 11742.95 |  | 0
|  | Original Contract | 216525 |  |  |  | 216525
|  | CO #1 06/30/25 | 2139.48 |  |  |  | 2139.48
|  | Total Contract: | 218664.48 |  | 0 |  | 218664.48

## #9423.00 Eick & Day Construct
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
Eick & Day Construction |  |  | Vendor: VS000005512
Acct. Codes-0506-335-DA24-9255 |  |  | RFB 942300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525023903 | 2025-01-23 | PO Procore(Unencumbered) | 46766.4 | 46766.4 |  |  | 46766.4
PRC 3352502PA3903 | 2025-04-28 | Inv. 24828.01 |  | 46766.4 | 20511.58 | 20511.58 | 26254.82 | 1079.56
PRC 3352502PB3903 | 2025-06-16 | Inv. 24828.02 |  | 46766.4 | 26254.82 | 46766.4 | 0 | 2461.4
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  |  |  | 46766.4 |  | 46766.4 | 0
|  | Totals: | 46766.4 |  | 46766.4 |  | 0
|  | Total Contract: | 707360 |  | 46766.4 |  | 660593.6

## #9423.00 DCI Group (2)
DPS ANK Aircraft Hangar(SLFRF)
Project # 9423.00
Program code 942300 |  |  | Major Program 4E12
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525043905 | 2025-02-12 | PO Procore(Unencumbered) | 46090.37 | 46090.37 |  |  | 46090.37
PRC 3352504PA3905 | 2025-03-26 | Inv. 24-030 CA 01 |  | 46090.37 | 4457.97 | 4457.97 | 41632.4
PRC 3352504PB3905 | 2025-04-16 | Inv. 24-030 CA 02 |  | 46090.37 | 5464.2 | 9922.17 | 36168.2
PRC 3352504PC3905 | 2025-05-15 | Inv. 24-030 CA 03 |  | 46090.37 | 16476.89 | 26399.06 | 19691.31
PRC 3352504PD3905 | 2025-06-17 | Inv. 24-030 CA 04 |  | 46090.37 | 19691.31 | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  |  |  | 46090.37 |  | 46090.37 | 0
|  | Totals: | 46090.37 |  | 46090.37 |  | 0
|  | CM Staff | 103650.01 |  | 31112.13 |  | 72537.88
|  | CM Fee | 64997.25 |  | 12999.45 |  | 51997.8
|  | Reimbursables | 9500 |  | 1978.79 |  | 7521.21
|  | Total: | 178147.26 |  | 46090.37 |  | 132056.89

## RECAP #9424.00
HHS STS Main Electrical Loop Revisions
Project # 9424.00
| Program code 942400 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 10701.46
C | McGough Construction |  | 8441.8 | 8441.8 | 0
C | PM TIME |  | 2095.91 | 2095.91 | 0
C | Misc. |  | 163.75 | 163.75 | 0
| Total Project Cost | 10701.46 | 10701.46 | 10701.46 | 0 | 0
Closed 01/22/25

## #9424.00 Funds Rec'd
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 405EL2424166007 | 2024-06-18 | 20000 | 20000
|  |  | Returning FY24 Funds to Agency | IET 33524227919 | 2024-08-14 | -16054.8 | -16054.8
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263901 | 2024-09-19 | 16054.8 | 16054.8
|  |  | Return remaining funds to agency | IET 33525021202 | 2025-01-22 | -9298.54 | -9298.54
| Total Requested | 0 | Total Transferred |  |  | 10701.46 | 10701.46

## #9424.00 McGough Construction
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA24-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33524173901 | 2024-06-21 | PO Procore | 16976.27 | 16976.27 |  |  | 16976.27
PRC 3352417PA3901 | 2024-07-08 | Inv. 101174.012-PC01 |  | 16976.27 | 1849.29 | 1849.29 | 15126.98 | FY24
PO 33525173901 | 2024-08-28 | Roll to FY25 |  | 16976.27 |  | 1849.29 | 15126.98
PRC 3352517PB3901 | 2024-09-19 | Inv. 101174.012-PC02 |  | 16976.27 | 1102.2 | 2951.49 | 14024.78
PRC 3352517PC3901 | 2024-09-19 | Inv. 101174.012-PC03 |  | 16976.27 | 1613.31 | 4564.8 | 12411.47
PRC 3352517PD3901 | 2024-10-10 | Inv. 101174.012-PC04 |  | 16976.27 | 3379.13 | 7943.93 | 9032.34
PRC 3352517PE3901 | 2024-11-13 | Inv. 101174.012-PC05-FINAL | -8534.47 | 8441.8 | 497.87 | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  |  |  | 8441.8 |  | 8441.8 | 0
|  | Totals: | 8441.8 |  | 8441.8 |  | 0 | FINAL
|  | CM Services | 8201.8 |  | 8201.8 |  | 0
|  | Reimbursables | 240 |  | 240 |  | 0
|  | Total: | 8441.8 |  | 8441.8 |  | 0

## #9424.00 PM TIME
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: E2DL
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2095.91 | 2095.91 |  |  | 2095.91
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 2095.91 | 206.71 | 206.71 | 1889.2
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 2095.91 | 1889.2 | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
[5 empty] | 2095.91 |  | 2095.91 | 0
|  |  | Totals: | 2095.91 |  | 2095.91 |  | 0

## #9424.00 Misc
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525292904 | 2024-10-18 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1130 | 163.75 | 163.75
163.75
163.75
163.75
163.75
163.75
163.75
163.75
163.75
163.75
163.75
163.75
|  |  |  | Totals: |  | 163.75

## RECAP #9425.00
HHS STS North Buildings HazMat Survey
Project # 9425.00
| Program code 942500 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA24
Project Manager - Jennifer K
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 16404.26
C | ATC Group Services |  | 12251.25 | 12251.25 | 0
C | PM TIME |  | 3913.01 | 3913.01 | 0
C | Misc. |  | 240 | 240 | 0
| Total Project Cost | 16404.26 | 16404.26 | 16404.26 | 0 | 0
Closed 11/13/2024

## #9425.00 Funds Rec'd
HHS STS North Buildings HazMat Survey
Project # 9425.00
Program code 942500 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA24-0304
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 405EL24176010 | 2024-06-24 | 20000 | 20000
|  |  | Returning FY24 Funds to Agency | IET 33524227920 | 2024-08-14 | -16670.85 | -16670.85
|  |  | Returning FY24 Funds to Agency Correction | IET 33524227920A | 2024-08-21 | -2254.98 | -2254.98
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263900 | 2024-09-19 | 18925.83 | 18925.83
|  |  | Returning Funds to Agency-Program Closing | IET 33525318906 | 2024-11-13 | -3595.74 | -3595.74
| Total Requested | 0 | Total Transferred |  |  | 16404.26 | 16404.26

## #9425.00 ATC Group Services
HHS STS North Buildings HazMat Survey
Project # 9425.00
Program code 942500 |  |  | Major Program 4E02
ATC Group Services |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA24-9255 |  |  | MA00520262D
Project Manager - Jennifer K |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33524178902 | 2024-06-26 | DO Procore | 14335 | 14335 |  |  | 14335 | FY24
DO 33525178902 | 2024-08-28 | Roll to FY25 |  | 14335 |  | 0 | 14335
PRC 3352517PA8902 | 2024-10-04 | Inv. 2598542 | -2083.75 | 12251.25 | 12251.25 | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  |  |  | 12251.25 |  | 12251.25 | 0
|  | Totals: | 12251.25 |  | 12251.25 |  | 0 | FINAL
|  | Line 2 Asbestos Per Sample Fee 230@ $10per | 2110 |  | 2110 |  | 0
|  | Line 3 Lead Per Sample Fee 90@ $15per | 1050 |  | 1050 |  | 0
|  | Line 5 Administrative Hourly Rate 10Hrs@ $45per | 225 |  | 225 |  | 0
|  | Line 7 Field Technician Hourly Rate 82hrs@ $75per | 4781.25 |  | 4781.25 |  | 0
|  | Line 8 Hygienist Hourly Rate 43hrs@ $95per | 4085 |  | 4085 |  | 0
|  | Total: | 12251.25 |  | 12251.25 |  | 0

## #9425.00 PM TIME
HHS STS North Buildings HazMat Survey
Project # 9425.00
Program code 942500 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - Jennifer K |  |  |  | eDAS: 909O
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 3913.01 | 3913.01 |  |  | 3913.01
IET DAS202412115300001 | 2024-07-10 | 2507 | Finance Support for June 1-30 2024 |  | 3913.01 | 106.07 | 106.07 | 3806.94
IET DAS202412115300001 | 2024-07-10 | 9500 | DAS Services for June 1-30 2024 |  | 3913.01 | 968.1 | 1074.17 | 2838.84
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 3913.01 | 94.49 | 1168.66 | 2744.35
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 3913.01 | 1033 | 2201.66 | 1711.35
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 3913.01 | 123.24 | 2324.9 | 1588.11
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 3913.01 | 629.6 | 2954.5 | 958.51
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 3913.01 | 55.79 | 3010.29 | 902.72
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 3913.01 | 497.8 | 3508.09 | 404.92
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 3913.01 | 52.42 | 3560.51 | 352.5
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 3913.01 | 352.5 | 3913.01 | 0
[5 empty] | 3913.01 |  | 3913.01 | 0
[5 empty] | 3913.01 |  | 3913.01 | 0
|  |  | Totals: | 3913.01 |  | 3913.01 |  | 0

## #9425.00 Misc
HHS STS North Buildings HazMat Survey
Project # 9425.00
Program code 942500 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525277901 | 2024-10-02 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2598705 | 240 | 240
240
240
240
240
240
240
240
240
240
240
240
|  |  |  | Totals: |  | 240

## #XXXX.XX Funds Rec'd Incorrectl
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds Recv'd Incorrect Unit | IET DASPROJECTS 092524 | 2024-09-26 | 164672.99 | 164672.99
|  |  | Transfer Funds to Correct Unit From DA24 to DA23 | CDR 33525271901 | 2024-09-27 | -164672.99 | -164672.99
|  |  | Funds Recv'd Incorrect Unit | IET 23812V25010 | 2025-04-14 | 850000 | 850000
|  |  | Transfer Funds to Correct Unit From DA24 to DA25 | CDR 33525109900 | 2025-04-18 | -850000 | -850000
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Recap
Acct. Codes-0506-335-DA24
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Funds Rec'd
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Funds Rec'd
Acct Code: 0506-335-DA24-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA24-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Staff Hours | 0 |  | 0 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA24-xxxx
Project Manager - |  |  |  | eDAS:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
Misc
Acct. Codes-0506-335-DA24-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager -
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0