## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Additional Funds | 22000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22000000
| . | Less: Total Assigned |  | 20423018
|  | Total Unassigned / Unallocated |  | 1576982
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
C | 9997.25 | Project Management Time | Scott G | 54438.68 |  | 54438.68 | 54438.68 | 54438.68 | 0 | 0
| 9354.00 | DOC ASP LUC Plumbing Repairs Phase 2 & 3 | Oliver S | 1800000 |  | 1800000 | 1748787.01 | 267346.05 | 1481440.96 | 51212.99 | 98453.01
C | 9371.00 | DPS Post 3 Parking Lot Replacement | Jennie E | 378979.56 |  | 378979.56 | 378979.56 | 378979.56 | 0 | 0
| 9422.00 | DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20) | Oliver S | 1217757.86 |  | 1217757.86 | 1064325.2 | 859186.07 | 205139.13 | 153432.66 | 5373.76
C | 9442.00 | DOC MPCF SouthCore & East/West Staircase Tuckpointing | Brandon A. | 431667.61 |  | 431667.61 | 431667.61 | 431667.61 | 0 | 0
| 9443.00 | DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements | Brandon A. | 1275000 |  | 1275000 | 1253237.35 | 1176022.13 | 77215.22 | 21762.65 | 862.41
| 9444.00 | DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing | Brad T. | 1950000 |  | 1950000 | 1899543.04 | 147737.81 | 1751805.23 | 50456.96 | 24658.38
| 9445.00 | DOC IMCC Fire Alarm System Replacement | Jennifer K | 1900000 |  | 1900000 | 1653141.98 | 106470.76 | 1546671.22 | 246858.02 | 4670.69
C | 9447.00 | DAS TH HVAC Repairs | James T. | 44173.65 |  | 44173.65 | 44173.65 | 44173.65 | 0 | 0
| 9448.00 | DAS TH Residence Roof, Porch, & South Garden Wall Repairs | James T. | 700000 |  | 700000 | 302019.26 | 221719.56 | 80299.7 | 397980.74 | 7280.79
| 9449.00 | DAS TH Carriage House Roof Replacement | James T. | 405000 |  | 405000 | 393625.66 | 392903.78 | 721.88 | 11374.34 | 721.88
| 9451.00 | DOC ASP LUA A/C Replacement | Oliver S | 709000 |  | 709000 | 704289.69 | 685752.57 | 18537.12 | 4710.31 | 1869.09
| 9452.00 | HHS CHMHI Generator Controller Replacement | Jennie E | 371000 |  | 371000 | 337781.63 | 38660.39 | 299121.24 | 33218.37 | 6381.67
C | 9453.00 | DOC FDCF IPI Roof Replacement | Jennie E | 286904.3 |  | 286904.3 | 286904.3 | 286904.3 | 0 | 0
C | 9454.00 | DOC ICIW Building 9 Roof Replacement | Brandon A. | 210546.34 |  | 210546.34 | 210546.34 | 210546.34 | 0 | 0
| 9455.00 | IDOE ISD Giangreco Hall Water Infiltration Mitigation | Jennie E | 735500 |  | 735500 | 638101.98 | 501563.68 | 136538.3 | 97398.02 | 31788.3
| 9456.00 | IDOE ISD Elementary School Roof Replacement | Jennie E | 403525 |  | 403525 | 349690.71 | 348181.62 | 1509.09 | 53834.29 | 1509.09
| 9457.00 | IDOE ISD High School Gym Roof Replacement | Jennie E | 405525 |  | 405525 | 401666.28 | 395872.91 | 5793.37 | 3858.72 | 5793.37
| 9458.00 | DOC NCCF Powerhouse Water Heater Replacements | Jennie E | 630000 |  | 630000 | 519459.19 | 471321.35 | 48137.84 | 110540.81 | 8642.72
| 9459.00 | HHS STS A.E. Sheperd AC Replacement | Jennifer K | 280000 |  | 280000 | 250763.55 | 250617.57 | 145.98 | 29236.45 | 145.98
| 9460.00 | DOC NCF LU B, C & D Roof Replacements | Brad T | 1255000 |  | 1255000 | 1130401.54 | 864466.55 | 265934.99 | 124598.46 | 7582.82
| 9462.00 | DOE ISD South Powerhouse Parking Lot Repair | Jennie E | 610000 |  | 610000 | 568384 | 110602.1 | 457781.9 | 41616 | 12885.85
| 9463.00 | HHS WRC Birches Window Replacement | Jennifer K | 1200000 |  | 1200000 | 1060382.2 | 65216.04 | 995166.16 | 139617.8 | 1089.45
| 9474.00 | HHS IMHI Boiler #3 Replacement | Oliver S | 1500000 |  | 1500000 | 1147957.73 | 84153.41 | 1063804.32 | 352042.27 | 6869.74
| 9520.00 | DOC NCCF Perimeter Light Pole & Yard Light Replacement | Jennie E | 629000 |  | 629000 | 29628.95 | 416.9 | 29212.05 | 599371.05 | 12083.1
| 9522.00 | DOC NCF Dietary and Laundry Hot Water Tank Replacement | Brad T | 285000 |  | 285000 | 24482.95 | 610.28 | 23872.67 | 260517.05 | 5889.72
| 9523.00 | DOC NCF Misc Door Replacements | Brad T | 260000 |  | 260000 | 22096.92 | 610.28 | 21486.64 | 237903.08 | 6889.72
| 9526.00 | DPS P02 Parking Lot Replacement | James T | 260000 |  | 260000 | 25402.32 | 0 | 25402.32 | 234597.68 | 8000
| 9528.00 | DOC 5JD Bldg 65/66 Parking Lot Overlay | James T | 235000 |  | 235000 | 21420.72 | 696.64 | 20724.08 | 213579.28 | 7303.36
|  | Major Maintenance Totals |  | 20423018 | 0 | 20423018 | 16953300 | 8396838.59 | 8556461.41 | 3469718 | 266744.9
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 1576982
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 5046700
[6 empty] | Total funds Available |  |  | 22000000
[6 empty] | Total obligated by contract or PO |  |  | -16953300 | 5046700
[6 empty] | Variance |  |  |  | 0
Note on E16: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Sat, Mar 1, 1:05 PM (3 days ago) to me, Jennifer, Scott Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott
Note on E17: Huggins, Joni [DAS]: 9371.00 - DPS Post 3 Parking Lot Rep - MM25 $Joni Elliott, Jennie 8:37 AM (5 minutes ago) to me, Jennifer, Scott Due to good bids, Please return $142,000 in funding from project 9371.00 in MM25 to the Total Unassigned/Unallocated line. This will bring the project budget for 9371.00 in MM25 to $378,000.00 Thank you, Jennie Elliott Re: 9371.00 - DPS P03 Parking Lot Repl - Metro Driveway Replacement - CO #002 - FY 25 Inbox Elliott, Jennie 11:58 AM (11 minutes ago) to Jennifer, me Ugh, it was supposed to go to MM23, not MM25. In the interest of time and fiscal year, please increase the budget in MM25 by $3,196.07. Thank you, Jennie Elliott Owner's Representative, State Design & Const
Note on E18: Huggins, Joni [DAS]: New Major Maintenance Projects $Joni Kleene, Jennifer 9:33 AM (3 hours ago) to me, Scott, Jennie, James, Brad, Brandon Please increase the funding for MM25 Project # 9422.00 by $2,900,000 and set-up the following new projects. Please let me know if you have any questions. 9422 MM25 ASP Tuckpointing Priorities 7,8,9 $Joni Shimp, Oliver 10:43 AM (0 minutes ago) to me, Jennifer, Brandon Good Morning, Please return $1,600,000.00 back to the MM25 funding pool from project 9422.00 MM25 the ASP Tuckpointing project. Thank you, -- Oliver Shimp, PE 9422.00 DOC ASP Tuckpointing Priorities 7,8,9 Inbox Shimp, Oliver 2:10 PM (14 minutes ago) to me, Brandon, Geoff, Jennifer Good Afternoon, Could you please make the following operations for project #9422.00 DOC ASP Tuckpointing Priorities 7,8,9. Transfer $8,000.00 to PM Time Budget, total to $28,000.00 in PM Time Return $182,242.14 from unallocated to the MM25 pool fund. Thank you, let me know if you have any questions -- Oliver Shimp, PE
Note on E19: Huggins, Joni [DAS]: 9442.00 MM25 DOC MPCF South Core & East/West Stair Case Tuckpointing $Joni Adams, Brandon 10:37 AM (11 minutes ago) to me, Jennifer, Charlee Finance, Please decrease the funds from MM25 9442.00 by $300,000 and return to MM25. Please let me know if you have any questions. Regards, Brandon Adams
Note on E20: Huggins, Joni [DAS]: 9443.00 MM25 DOC MPCF Appliance Shop, Powerhouse, Carpentry, and Paint Shop Window Replacement $Joni Adams, Brandon 10:58 AM (14 minutes ago) to me, Jennifer, Charlee Finance, Please deduct funds from MM25 9443.00 by $625,000 and return to MM25. Please let me know if you have any questions. Regards, Brandon Adams MM25 9443.00 DOC MPCF Return Funds Inbox Adams, Brandon 9:30 AM (1 minute ago) to me, Jennifer, Geoff Finance, Please return $100,000 from project 9443.00 DOC MPCF Appliance, Pwr, Carp, Paint Shop Window Replacement project to MM25 funds. Regards, Brandon Adams
Note on E21: Huggins, Joni [DAS]: Budget/PM Time Adjustments Inbox Tonyan, Brad 4:44 PM (1 hour ago) to DAS, me Joni, Can you please make the following (2) adjustments: DA24 - 9223.00 - Increase PM time by $49,467.26 to a total of $89,467.26 MM25 - 9460.00 - Shift $1,100,000 from this project (9460.00) into project 9444.00 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Represe MM25 - 9444.00 Budget Adjustment (HOT Item) $Joni Tonyan, Brad 9:51 AM (8 minutes ago) to me, Geoff, Jennifer, Brad DAS Finance, Please increase the overall project budget on 9444.00 by $600,000 within funding ORG MM25 which shall bring the overall project total funding value to $1,950,000. Please also increase the PM/DAS time budget from $15,000 to $40,000 which will get us through project completion. Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E23: Huggins, Joni [DAS]: Budget Modification Inbox Trower, James 2:14 PM (7 minutes ago) to me, Jennifer Finance - 9447.00 - DAS TH HVAC Repairs (MM25 Funding) Please reduce the project budget by $650,000.00 9393.00 - DOC 5JD FT DM Bldg 71 & 73 Roof Replacement (MM24) Please reduce the project budget by $625,000.00 Thanks, James Trower, Licensed Architect, LEED AP
Note on E24: Huggins, Joni [DAS]: 9448.00 - DAS TH Residence Roof Porch & South Garden Wall Repairs - Budget Modification $Joni Trower, James 1:27 PM (12 minutes ago) to me, Jennifer Finance - Please increase the budget for project 9448.00 by $1,150,00.00 in MM25 funding. Thanks, James Trower, Licensed Architect, LEED AP 9448.00 - DAS TH Residence Roof Porch & South Garden Wall Repairs - Budget $Joni Trower, James 2:17 PM (24 minutes ago) to me, Jennifer Finance - Please increase the MM25 budget for project 9448.00 by $80,000.00. Jennifer - This is for the TH Pool House Lintel and Stone Repairs that is on the FY26 MM List. Thanks, James Trower, Licensed Architect, LEED AP Re: TH Roof/Porch Project Inbox Trower, James 9:26 AM (1 minute ago) to me, Geoff Finance - Project # 9448.00 - DAS TH Residence Roof, Porch, & South Garden Wall Repairs (MM25 funding): Please return $1,500,000.00 (MM25 funds) from project 9448.00 to the MM25 pool fund. Please copy Geoff Wheelock on the email once this is completed. Thank you, James Trower
Note on E25: Huggins, Joni [DAS]: Budget Modifications - James Trower $Joni Trower, James Mon, Feb 10, 4:13 PM (15 hours ago) to me Finance - Please see below budget modifications: 9449.00 - DAS TH Carriage House Roof Replacement Increase MM25 budget by $125,000.00 9375.00 - DOC 5JD DM Bldgs 65-66 Renovation Increase PM Time (DA24) by $28,000.00 Thanks, Re: 9449.00 - Titan Roofing - 802 - BP #01 - Roofing Replacement $Joni Trower, James 1:27 PM (2 minutes ago) to me Joni - Please increase the budget for project 9449.00 by $50,000.00 (MM25). Thanks, James 9449.00 - DAS TH Carriage House Roof Replacement - Budget Increase $Joni Trower, James 8:54 AM (4 hours ago) to me Finance - Please increase project 9449.00 budget (MM25 funding) by $30,000. Thanks, James Trower, Licensed Architec
Note on E26: Huggins, Joni [DAS]: Re: MM25 9451.00 DOC ASP LUA A/C 802 - Foreman Construction, LLC. Inbox Shimp, Oliver 10:06 AM (2 minutes ago) to me, Brandon, Jennifer Please increase the budget of MM25 9451.00 by $109,000. Thank you, Oliver Shimp
Note on E27: Huggins, Joni [DAS]: 9452.00 - HHS CHMI Generator - MM25 $Joni Elliott, Jennie 9:32 AM (2 hours ago) to me, Jennifer Please increase the overall budget for project 9452.00 - HHS CHMHI Generator Controller Replacement in MM25 to $371,000. Thank you Jennie Elliott
Note on E28: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Mar 1, 2025, 1:05 PM (3 days ago) to me, Jennifer, Scott Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott
Note on E29: Huggins, Joni [DAS]: MM25 9454.00 DOC ICIW Building 9 Roof Replacement $Joni Adams, Brandon 12:01 PM (20 minutes ago) to me, Scott, Jennifer Finance, Please return $340,000 to MM25 funding from 9454.00 DOC ICIW Building 9 Roof Replacement. Regards, Brandon Adams
Note on E30: Huggins, Joni [DAS]: 9455.00 - Giangreco Hall Water Infiltration Mitigation - MM25 - Return of Funds FY26 Elliott, Jennie Sat, Jan 24, 1:04 PM (2 days ago) to me, Geoff, Jennifer Please reduce the Overall Budget for 9455.00 in MM25 from $1,000,000.00 down to $735,500.00. The remaining $264,500 can be returned to the Total Unassigned/Unallocated budget in MM25. Thank you, Jennie Elliott
Note on E31: Huggins, Joni [DAS]: Re: Changes to MM25 Inbox Elliott, Jennie 11:01 AM (0 minutes ago) to me, Jennifer, Scott Sorry, no. I meant the following! 9456.00 9467.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Tue, Mar 4, 2025 at 10:55 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Are you wanting to Open Projects 9356.00 (DA24) and 9357.00 (MM24) in MM25? On Sat, Mar 1, 2025 at 1:05 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott 9456.00 - DOE ISD Elementary Roof Replacement - Budget Changes MM25 FY25 Elliott, Jennie Fri, Apr 25, 4:41 PM (3 days ago) to me, Jennifer Bids came in better than anticipated on this project. Please return $26,475.00 in funding from project 9456.00 in MM25 to the "Total Unassigned/Unallocated" line. This will make the new budget for project 9456.00 $403,525.00. Thank you, Jennie Elliott
Note on E32: Huggins, Joni [DAS]: Re: Changes to MM25 Inbox Elliott, Jennie 11:01 AM (0 minutes ago) to me, Jennifer, Scott Sorry, no. I meant the following! 9456.00 9467.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Tue, Mar 4, 2025 at 10:55 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Are you wanting to Open Projects 9356.00 (DA24) and 9357.00 (MM24) in MM25? On Sat, Mar 1, 2025 at 1:05 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott 9457.00 - DOE ISD High School Gym Roof Replacement - Budget Changes MM25 $Joni Elliott, Jennie Fri, Apr 25, 4:47 PM (3 days ago) to me, Jennifer Bids came in better than anticipated on this project. Please return $24,475.00 in funding from project 9457.00 in MM25 to the "Total Unassigned/Unallocated" line. This will make the new budget for project 9457.00 $405,525.00. Thank you, Jennie Elliott
Note on E33: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Mar 1, 2025, 1:05 PM (3 days ago) to me, Jennifer, Scott
Note on E34: Huggins, Joni [DAS]: Budget Reductions Inbox Kleene, Jennifer 3:10 PM (2 minutes ago) to me Please reduce the budget for MM23 9294.01 by $68,000.00. Please reduce the budget for MM24 9279.30 by $24,000.00. Please reduce the budget for MM25 9459.00 by $20,000.00. Regards, Jennifer
Note on E35: Huggins, Joni [DAS]: Budget/PM Time Adjustments Inbox Tonyan, Brad 4:44 PM (1 hour ago) to DAS, me Joni, Can you please make the following (2) adjustments: DA24 - 9223.00 - Increase PM time by $49,467.26 to a total of $89,467.26 MM25 - 9460.00 - Shift $1,100,000 from this project (9460.00) into project 9444.00 Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Represe
Note on E37: Huggins, Joni [DAS]: Budget Changes $Joni Kleene, Jennifer Thu, Aug 7, 4:16 PM (15 hours ago) to me, Geoff MM25 Please decrease the budget for 9463.00 by $300,000.00 MM23 Please decrease the budget for 9268.01 by $3,000.00 Please decrease the budget for 9279.20 by $5,000.00 Regards, Jennifer Jennifer Kleene

## MM25 Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct. Codes-0017-335-MM25
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #9997.25
Project Management Time
Project # 9997.25
| Program code 999725 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - NA
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 54438.68
C | PM TIME |  | 54438.68 | 54438.68 | 0
| Total Project Cost | 54438.68 | 54438.68 | 54438.68 | 0 | 0
Closed 07/22/25

## #9997.25 PM TIME
Project Management Time
Project # 9997.25
Program code 999725 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS E2DU
Project Manager - NA
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 54438.68 | 54438.68 |  |  | 54438.68
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 54438.68 | 584.63 | 584.63 | 53854.05
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 54438.68 | 2805.2 | 3389.83 | 51048.85
CDE 33525229800 | 2024-08-21 | 2507 | Moving PM Expense to CS23 9421.00(Finance Support-July) |  | 54438.68 | -61.68 | 3328.15 | 51110.53
CDE 33525229800 | 2024-08-21 | 9500 | Moving PM Expense to CS23 9421.00(DAS Services-July) |  | 54438.68 | -675 | 2653.15 | 51785.53
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 54438.68 | 1180.54 | 3833.69 | 50604.99
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 54438.68 | 2543.4 | 6377.09 | 48061.59
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 54438.68 | 596.59 | 6973.68 | 47465
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 54438.68 | 2174.4 | 9148.08 | 45290.6
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 54438.68 | 1088.06 | 10236.14 | 44202.54
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 54438.68 | 2628.5 | 12864.64 | 41574.04
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 54438.68 | 1435.53 | 14300.17 | 40138.51
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 54438.68 | 8436.2 | 22736.37 | 31702.31
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 54438.68 | 850.1 | 23586.47 | 30852.21
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 54438.68 | 2403.5 | 25989.97 | 28448.71
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 54438.68 | 1328.73 | 27318.7 | 27119.98
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 54438.68 | 3063.8 | 30382.5 | 24056.18
CDE 33525050904 | 2025-02-19 | 2507 | Move Expenses to Admin time per Project Manager |  | 54438.68 | 92.25 | 30474.75 | 23963.93
CDE 33525050904 | 2025-02-19 | 9500 | Move Expenses to Admin time per Project Manager |  | 54438.68 | 985.6 | 31460.35 | 22978.33
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 54438.68 | 3374.54 | 34834.89 | 19603.79
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 54438.68 | 3786.4 | 38621.29 | 15817.39
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 54438.68 | 1908.2 | 40529.49 | 13909.19
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 54438.68 | 2587.8 | 43117.29 | 11321.39
CDE 33525106901 | 2025-04-15 | 2507 | Move expenses to 999725 due to billable file error |  | 54438.68 | 27.14 | 43144.43 | 11294.25
CDE 33525106901 | 2025-04-15 | 9500 | Move expenses to 999725 due to billable file error |  | 54438.68 | 197 | 43341.43 | 11097.25
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 54438.68 | 1438.39 | 44779.82 | 9658.86
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 54438.68 | 1364.5 | 46144.32 | 8294.36
CDE 33525134911 | 2025-05-13 | 2507 | Move expenses From 999725 due to billable file error |  | 54438.68 | -27.14 | 46117.18 | 8321.5
CDE 33525134911 | 2025-05-13 | 9500 | Move expenses From 999725 due to billable file error |  | 54438.68 | -197 | 45920.18 | 8518.5
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 54438.68 | 1616.78 | 47536.96 | 6901.72
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 54438.68 | 4346.3 | 51883.26 | 2555.42
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 54438.68 | 1320.72 | 53203.98 | 1234.7
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 54438.68 | 1234.7 | 54438.68 | 1.0914e-11
[5 empty] | 54438.68 |  | 54438.68 | 1.0914e-11
|  |  | Totals: | 54438.68 |  | 54438.68 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: FY 25 9997.25 PM Time Inbox Gustafson, Scott Wed, Jun 26, 3:25 PM (17 hours ago) to me John, Please set the budget at $75,000. Respectfully, Scott Re: 9997.25 Inbox Cross, Charlee 8:00 AM (1 minute ago) to me, Geoff Yes! Thank you!! On Mon, Jul 21, 2025 at 10:26 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hello Geoff and Charlee May I have permission to close 9997.25 PM Admin time? I'm showing a remaining balance of $20,561.32 that I can transfer back to the MM25 project pool. I have create 9997.26 in MM26 and updated the billable file. I also have included the below string to you have a point of reference from last year. John

## RECAP #9354.00
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
| Program code 935400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1800000
| Foreman Construction |  | 1501910.63 | 136592.48 | 1365318.15
| PM TIME |  | 100000 | 1546.99 | 98453.01
| Misc. |  | 7957 | 7957 | 0
C | McGough Construction |  | 107797.38 | 107797.38 | 0
| Shive Hattery |  | 31122 | 13452.2 | 17669.8
| Total Project Cost | 1800000 | 1748787.01 | 267346.05 | 1481440.96 | 51212.99

## #9354.00 Foreman Construction
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Foreman Construction |  |  | Vendor: 00003226071
Acct. Codes-0017-335-MM25-9255 |  |  | RFB935400-01
Project Manager - Oliver S |  |  | Activity code: BRUM
Split w/ MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525027908 | 2025-01-27 | PO Procore | 540000 | 540000 |  |  | 540000
PO 33525027908 | 2025-05-05 | CO #1(Procore adjustment only) | 0 | 540000 |  | 0 | 540000
PRC 3352502PA7908 | 2025-05-15 | Inv. 9354.00 Pay App #1(100% to DA24) |  | 540000 | 0 | 0 | 540000
PO 33525027908 | 2025-05-09 | CO #2(100% to MM25) | 396644 | 936644 |  | 0 | 936644
PO 33525027908 | 2025-07-16 | CO #3(100% to MM25) | 38714 | 975358 |  | 0 | 975358 |  | FY25
PO 33526027908 | 2025-07-24 | Roll to FY26 | 0 | 975358 |  | 0 | 975358
PO 33526027908 | 2025-07-30 | CO #4(100% to MM25) | 8713.95 | 984071.95 |  | 0 | 984071.95
PRC 3352602PB7908 | 2025-09-12 | Inv. 9354.00 Pay App #2(Split with MM24) |  | 984071.95 | 3657.5 | 3657.5 | 980414.45 | 192.5
PRC 3352602PC7908 | 2025-09-19 | Inv. 9354.00 Pay App #3(Split with MM24) |  | 984071.95 | 1330 | 4987.5 | 979084.45 | 262.5
PO 33526027908 | 2025-09-23 | CO #5(100% to MM25) | 129549.68 | 1113621.63 |  | 4987.5 | 1108634.13
PRC 3352602PD7908 | 2025-10-13 | Inv. 9354.00 Pay App #4(Split with MM24) |  | 1113621.63 | 9997.8 | 14985.3 | 1098636.33 | 788.7
PRC 3352602PE7908 | 2025-11-18 | Inv. 9354.00 Pay App #5(Split with MM24) |  | 1113621.63 | 31501.22 | 46486.52 | 1067135.11 | 2446.66
PO 33526027908 | 2025-12-03 | CO #6(100% to MM25) | 376083 | 1489704.63 |  | 46486.52 | 1443218.11
PRC 3352602PF7908 | 2025-12-11 | Inv. 9354.00 App #6(Split with MM24) |  | 1489704.63 | 10249.55 | 56736.07 | 1432968.56 | 2986.11
PRC 3352602PG7908 | 2025-12-29 | Inv. 9354.00 App#7(100% to MM25) |  | 1489704.63 | 40689.45 | 97425.52 | 1392279.11 | 5127.66
PO 33526027908 | 2026-01-13 | CO #7 (100% to MM25) | 12206 | 1501910.63 |  | 97425.52 | 1404485.11
PO 33526027908 | 2026-01-15 | CO #8 (100% to MM24) | 0 | 1501910.63 |  | 97425.52 | 1404485.11
PRC 3352602PH7908 | 2026-01-22 | Inv. 9354.00 App#8(Split w/ MM24) |  | 1501910.63 | 347.7 | 97773.22 | 1404137.41 | 5145.96
PRC 3352602PI7908 | 2026-02-05 | Inv. 9354.00 App#9(Split w/ MM24) |  | 1501910.63 | 22638.2 | 120411.42 | 1381499.21 | 6337.44
PRC 3352602PJ7908 | 2026-02-25 | Inv. 9354.00 App#10 - Phase 1 Retainage (Split w/ MM24) |  | 1501910.63 | 2965.93 | 123377.35 | 1378533.28 | 3371.51
PO 33526027908 | 2026-02-27 | CO #9(100% to MM24) | 0 | 1501910.63 |  | 123377.35 | 1378533.28
PRC 3352602PK7908 | 2026-03-19 | Inv. 9354.00 App#11(Split w/ MM24) |  | 1501910.63 | 13215.13 | 136592.48 | 1365318.15 | 4067.04
PO 33526027908 | 2026-03-30 | CO #10(100% to MM24) | 0 | 1501910.63 |  | 136592.48 | 1365318.15
|  |  |  | 1501910.63 |  | 136592.48 | 1365318.15
|  | Totals: | 1501910.63 |  | 136592.48 |  | 1365318.15
|  | MM24 | 1517634.83 |  | 1046666.42 |  | 470968.41
|  | Total: | 3019545.46 |  | 1183258.9 |  | 1836286.56
Inv. 9354.00 App#10 - Phase 1 Retainage is paying out partial retainage

## #9354.00 PM TIME
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909T
Project Manager - Oliver S
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 100000 | 100000 |  |  | 100000
CDE 33525109901 | 2025-04-18 | 2507 | Moving Expense From MM22 |  | 100000 | 54.27 | 54.27 | 99945.73
CDE 33525109901 | 2025-04-18 | 9500 | Moving Expense From MM22 |  | 100000 | 388 | 442.27 | 99557.73
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 100000 | 100.13 | 542.4 | 99457.6
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 100000 | 774.7 | 1317.1 | 98682.9
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 100000 | 19.49 | 1336.59 | 98663.41
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 100000 | 210.4 | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
[5 empty] | 100000 |  | 1546.99 | 98453.01
|  |  | Totals: | 100000 |  | 1546.99 |  | 98453.01
Note on E9: Huggins, Joni [DAS]: 9354.00 - PM Time MM25 $Joni Elliott, Jennie 12:48 PM (32 minutes ago) to me Can you please establish a PM Time budget in MM25 for project 9354.00 of $100,000. Thank you, Jennie Elliott

## #9354.00 Misc
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 163
Project Manager - Oliver S
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525199400 | 2025-07-18 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 843633 | 7957 | 7957
7957
7957
7957
7957
7957
7957
7957
7957
7957
7957
7957
|  |  |  | Totals: |  | 7957

## #9354.00 McGough Construction
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S |  |  | Activity code: CMGR
Split w/MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525038900 | 2025-02-07 | PO Procore | 107797.38 | 107797.38 |  |  | 107797.38
PRC 3352503PA8900 | 2025-04-24 | Inv. 101031.005CA#01(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352503PB8900 | 2025-05-05 | Inv. 101031.005CA#02(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352503PC8900 | 2025-07-07 | Inv. 101031.005CA#03(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352503PD8900 | 2025-07-14 | Inv. 101031.005CA#04(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352503PE8900 | 2025-07-14 | Inv. 101031.005CA#05(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38 | FY25
PO 33526038900 | 2025-07-24 | Roll to FY26 | 0 | 107797.38 |  | 0 | 107797.38
PRC 3352603PF8900 | 2025-08-28 | Inv. 101031.005CA#06(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352603PG8900 | 2025-09-19 | Inv. 101031.005CA#07(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352603PH8900 | 2025-10-27 | Inv. 101031.005CA#08(100% to MM25) |  | 107797.38 | 42150.65 | 42150.65 | 65646.73
PRC 3352603PI8900 | 2025-11-20 | Inv. 101031.005CA#09(100% to MM25) |  | 107797.38 | 20726.58 | 62877.23 | 44920.15
PRC 3352603PJ8900 | 2025-12-11 | Inv. 101031.005CA#10(100% to MM24) |  | 107797.38 | 0 | 62877.23 | 44920.15
PRC 3352603PK8900 | 2026-01-15 | Inv. 101031.005CA#11(100% to MM25) |  | 107797.38 | 21466.52 | 84343.75 | 23453.63
PRC 3352603PL8900 | 2026-02-20 | Inv. 101031.005CA#12(100% to MM25) |  | 107797.38 | 21358.61 | 105702.36 | 2095.02
PRC 3352603PM8900 | 2026-03-19 | Inv. 101031.005CA#013(Split w/ MM24) |  | 107797.38 | 2095.02 | 107797.38 | 7.7307e-12
|  |  |  | 107797.38 |  | 107797.38 | 7.7307e-12
|  |  |  | 107797.38 |  | 107797.38 | 7.7307e-12
|  | Totals: | 107797.38 |  | 107797.38 |  | 0
|  | MM24 | 221700 |  | 109053.79 |  | 112646.21
|  | Total: | 329497.38 |  | 216851.17 |  | 112646.21

## #9354.00 Shive Hattery
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM25-9260 |  |  | 935400-01
Project Manager - Oliver S |  |  | Activity code: DSGN
Split w/MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525317902 | 2025-05-07 | CO #3 Moving from MM22 | 17522 | 17522 |  |  | 17522
PO 33525317902 | 2025-06-05 | CO #4 | 13600 | 31122 |  | 0 | 31122
PRC 3352531PL7902 | 2025-07-18 | Inv. 2112309650-12 |  | 31122 | 900 | 900 | 30222 | FY25
PO 33526317902 | 2025-07-25 | Roll to FY26 | 0 | 31122 |  | 900 | 30222
PRC 3352631PM7902 | 2025-09-12 | Inv. 2112309650-13 |  | 31122 | 1800 | 2700 | 28422
PRC 3352631PN7902 | 2025-10-10 | Inv. 9354.00-14 |  | 31122 | 3600 | 6300 | 24822
PRC 3352631PO7902 | 2025-11-20 | Inv. 9354.00-15 |  | 31122 | 3600 | 9900 | 21222
PRC 3352631PP7902 | 2025-12-29 | Inv. 2112309650-16 |  | 31122 | 1800 | 11700 | 19422
PRC 3352631PQ7902 | 2026-01-20 | Inv. 2112309650-17 |  | 31122 | 1752.2 | 13452.2 | 17669.8
|  |  |  | 31122 |  | 13452.2 | 17669.8
|  |  |  | 31122 |  | 13452.2 | 17669.8
|  |  |  | 31122 |  | 13452.2 | 17669.8
|  |  |  | 31122 |  | 13452.2 | 17669.8
|  | Totals: | 31122 |  | 13452.2 |  | 17669.8
|  | MM22 Closed 06/05/25 | 78022 |  | 78022 |  | 0
|  | Total: | 109144 |  | 91474.2 |  | 17669.8

## RECAP #9371.00
DPS Post 3 Parking Lot Replacement
Project # 9371.00
| Program code 937100 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 378979.56
C | Samuels Group |  | 58379.56 | 58379.56 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 0 | 0 | 0
C | Metro Driveway Replacement |  | 320600 | 320600 | 0
| Total Project Cost | 378979.56 | 378979.56 | 378979.56 | 0 | 0
Closed 11/17/25

## #9371.00 Samuels Group
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327905 | 2024-11-22 | PO Procore | 51805.08 | 51805.08 |  |  | 51805.08
PRC 3352532PA7905 | 2024-12-06 | Inv. 7739.51937100 |  | 51805.08 | 973.74 | 973.74 | 50831.34
PRC 3352532PB7905 | 2025-01-13 | Inv. 7739.52937100 |  | 51805.08 | 1459.75 | 2433.49 | 49371.59
PRC 3352532PC7905 | 2025-02-05 | Inv. 7739.53937100 |  | 51805.08 | 3168.67 | 5602.16 | 46202.92
PRC 3352532PD7905 | 2025-03-10 | Inv. 7739.54937100 |  | 51805.08 | 807.59 | 6409.75 | 45395.33
PO 33525327905 | 2025-04-07 | CO #1 | 8198.85 | 60003.93 |  | 6409.75 | 53594.18
PRC 3352532PE7905 | 2025-04-08 | Inv. 7739.55937100 |  | 60003.93 | 3058.5 | 9468.25 | 50535.68
PRC 3352532PF7905 | 2025-05-09 | Inv. 7739.56937100 |  | 60003.93 | 7534.68 | 17002.93 | 43001
PRC 3352532PG7905 | 2025-06-10 | Inv. 7739.57937100 |  | 60003.93 | 14472.91 | 31475.84 | 28528.09
PRC 3352532PH7905 | 2025-07-14 | Inv. 7739.58937100 |  | 60003.93 | 15576.66 | 47052.5 | 12951.43 | FY25
PO 33526327905 | 2025-07-25 | Roll to FY26 | 0 | 60003.93 |  | 47052.5 | 12951.43
PRC 3352632PI7905 | 2025-08-14 | Inv. 7739.59937100 |  | 60003.93 | 3885.01 | 50937.51 | 9066.42
PRC 3352632PJ7905 | 2025-09-15 | Inv. 7739.60937100 |  | 60003.93 | 2783.99 | 53721.5 | 6282.43
PRC 3352632PK7905 | 2025-09-23 | Inv. 7739.61937100-FINAL | -1624.37 | 58379.56 | 4658.06 | 58379.56 | 7.276e-12
|  |  |  | 58379.56 |  | 58379.56 | 7.276e-12
|  |  |  | 58379.56 |  | 58379.56 | 7.276e-12
|  | Totals: | 58379.56 |  | 58379.56 |  | 0 | FINAL
|  | CM Services: | 48799.02 |  | 48799.02 |  | 0
|  | Reimbursables: | 2098.38 |  | 2098.38 |  | 0
|  | CO #1 | 7482.16 |  | 7482.16 |  | 0
|  | Total: | 58379.56 |  | 58379.56 |  | 0

## #9371.00 PM TIME
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731L
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9371.00 Misc
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9371.00 MetroDriveway
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Metro Driveway Replacement |  |  | Vendor: 00003224688
Acct. Codes-0017-335-MM25-9255 |  |  | RFB937100-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525339906 | 2024-12-04 | PO Procore | 314800 | 314800 |  |  | 314800
PO 33525339906 | 2025-04-16 | CO #1(100% to MM23) | 0 | 314800 |  | 0 | 314800
PRC 3352533PA9906 | 2025-05-29 | Inv. 9371.00-01(Split w/MM23) |  | 314800 | 152750.5 | 152750.5 | 162049.5 | 8039.5
PRC 3352533PB9906 | 2025-06-10 | Inv. 9371.00-02(100% to MM25) |  | 314800 | 113792.52 | 266543.02 | 48256.98 | 14028.58
PO 33525339906 | 2025-06-24 | CO #2(100% to MM25) | 5800 | 320600 |  | 266543.02 | 54056.98
PRC 3352533PC9906 | 2025-07-07 | Inv. 9371.00-03(Split w/MM23) |  | 320600 | 35036.38 | 301579.4 | 19020.6 | 15872.6 | FY25
PO 33526339906 | 2025-07-23 | Roll to FY26 | 0 | 320600 |  | 301579.4 | 19020.6
PO 33526339906 | 2025-07-30 | CO #3(100% to MM23) | 0 | 320600 |  | 301579.4 | 19020.6
PRC 3352633PD9906 | 2025-09-22 | Inv. 9371.00-04(Split w/MM23) |  | 320600 | 2990.6 | 304570 | 16030 | 16030
PRC 3352633PE9906 | 2025-09-23 | Inv. 9371.00-05 - Retainage (Split w/MM23) |  | 320600 | 16030 | 320600 | -1.819e-12
|  |  |  | 320600 |  | 320600 | -1.819e-12
|  |  |  | 320600 |  | 320600 | -1.819e-12
|  |  |  | 320600 |  | 320600 | -1.819e-12
|  | Totals: | 320600 |  | 320600 |  | 0
|  | MM23 | 23500 |  | 23500 |  | 0
|  | Total: | 344100 |  | 344100 |  | 0

## RECAP #9422.00
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
| Program code 942200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1217757.86
| Additional Funds | 0
C | McGough Construction |  | 7994.89 | 7994.89 | 0
| PM TIME |  | 28000 | 22626.24 | 5373.76
| Misc. |  | 0 | 0 | 0
| Horizon Architecture |  | 23565 | 20945.5 | 2619.5
| Bi-State Masonry |  | 907350 | 726267.73 | 181082.27
| McGough Construction(2) |  | 97415.31 | 81351.71 | 16063.6
| Total Project Cost | 1217757.86 | 1064325.2 | 859186.07 | 205139.13 | 153432.66

## #9422.00 Funds Rec'd
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
Funds Rec'd
Acct. Codes-0017-335-MM25
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9422.00 McGough Construction
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320903 | 2024-11-15 | PO Procore | 17289.86 | 17289.86 |  |  | 17289.86
PRC 3352532PA0903 | 2025-02-12 | Inv. 101368.007PC-001 |  | 17289.86 | 2219.12 | 2219.12 | 15070.74
PRC 3352532PB0903 | 2025-03-19 | Inv. 101368.007PC-02 |  | 17289.86 | 899.31 | 3118.43 | 14171.43
PRC 3352532PC0903 | 2025-04-15 | Inv. 101368.007PC-03 |  | 17289.86 | 1479.05 | 4597.48 | 12692.38
PRC 3352532PD0903 | 2025-05-08 | Inv. 101368.007PC-04 |  | 17289.86 | 1936.77 | 6534.25 | 10755.61
PRC 3352532PE0903 | 2025-06-10 | Inv. 101368.007PC-05 |  | 17289.86 | 1054.94 | 7589.19 | 9700.67
PRC 3352532PF0903 | 2025-07-10 | Inv. 101368.007PC-06 FINAL | -9294.97 | 7994.89 | 405.7 | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  |  |  | 7994.89 |  | 7994.89 | 0
|  | Totals: | 7994.89 |  | 7994.89 |  | 0 | FINAL
|  | CM Services: | 7819.39 |  | 7819.39 |  | 0
|  | Reimbursables: | 175.5 |  | 175.5 |  | 0
|  | Total: | 7994.89 |  | 7994.89 |  | 0

## #9422.00 PM TIME
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS E2FF
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 28000 | 28000 |  |  | 28000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 28000 | 134.79 | 134.79 | 27865.21
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 28000 | 686.4 | 821.19 | 27178.81
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 28000 | 56.21 | 877.4 | 27122.6
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 28000 | 503.3 | 1380.7 | 26619.3
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 28000 | 2 | 1382.7 | 26617.3
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 28000 | 46.66 | 1429.36 | 26570.64
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 28000 | 311.4 | 1740.76 | 26259.24
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 28000 | 187.04 | 1927.8 | 26072.2
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 28000 | 1871.6 | 3799.4 | 24200.6
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 28000 | 113.91 | 3913.31 | 24086.69
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 28000 | 1215.2 | 5128.51 | 22871.49
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 28000 | 186.76 | 5315.27 | 22684.73
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 28000 | 808.4 | 6123.67 | 21876.33
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 28000 | 187.68 | 6311.35 | 21688.65
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 28000 | 1346.3 | 7657.65 | 20342.35
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 28000 | 693.31 | 8350.96 | 19649.04
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 28000 | 4833.6 | 13184.56 | 14815.44
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 28000 | 71.63 | 13256.19 | 14743.81
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 28000 | 557 | 13813.19 | 14186.81
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 28000 | 229.23 | 14042.42 | 13957.58
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 28000 | 1780 | 15822.42 | 12177.58
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 28000 | 62.55 | 15884.97 | 12115.03
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 28000 | 689.2 | 16574.17 | 11425.83
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 28000 | 111.65 | 16685.82 | 11314.18
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 28000 | 858.3 | 17544.12 | 10455.88
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 28000 | 194.12 | 17738.24 | 10261.76
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 28000 | 1000.6 | 18738.84 | 9261.16
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 28000 | 314.22 | 19053.06 | 8946.94
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 28000 | 1370.1 | 20423.16 | 7576.84
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 28000 | 12.74 | 20435.9 | 7564.1
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 28000 | 1053.6 | 21489.5 | 6510.5
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 28000 | 42.8 | 21532.3 | 6467.7
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 28000 | 488.8 | 22021.1 | 5978.9
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 28000 | 16.43 | 22037.53 | 5962.47
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 28000 | 201.2 | 22238.73 | 5761.27
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 28000 | 31.01 | 22269.74 | 5730.26
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 28000 | 356.5 | 22626.24 | 5373.76
[5 empty] | 28000 |  | 22626.24 | 5373.76
[5 empty] | 28000 |  | 22626.24 | 5373.76
[5 empty] | 28000 |  | 22626.24 | 5373.76
|  |  | Totals: | 28000 |  | 22626.24 |  | 5373.76
Note on E9: Huggins, Joni [DAS]: MM24 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 $Joni Adams, Brandon Aug 6, 2024, 11:08 AM (2 days ago) to me, Jennifer, Scott Finance, Please close PM Time for MM24 9422.00 once July PM time posts. Please return all remaining funds back to MM24. Please transfer $100,000 from MM25 and create 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 in MM25 Please set the PM budget in MM25 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 at $5,000. Please update the August billing sheet. Regards, Brandon Adams Re: PM Time Inbox Adams, Brandon 10:25 AM (4 minutes ago) to me Please increase my PM Time by $5000.00 Regards, Brandon Adams Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-201-2197 mobile brandon.adams@iowa.gov https://das.iowa.gov On Wed, Feb 19, 2025 at 9:23 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Brandon We are negative for PM time on 9422.00 in MM25. Can we increase the budget? Currently -128.51 Re: April PM Time $Joni Shimp, Oliver 2:41 PM (9 minutes ago) to me Good Afternoon Joni, Could you please; 1) Add $10,000 to the PM time budget from the uncontracted budget for project MM25 9422.00. 2) Add $7,000 to the PM time budget from the uncontracted budget for project MM25 9422.00 3) Can you please assign $10,000 of the $50,000 to PM time for project 5800 9473.00 Thank you very much! Oliver Shimp 9422.00 DOC ASP Tuckpointing Priorities 7,8,9 Inbox Shimp, Oliver 2:10 PM (16 minutes ago) to me, Brandon, Geoff, Jennifer Good Afternoon, Could you please make the following operations for project #9422.00 DOC ASP Tuckpointing Priorities 7,8,9. Transfer $8,000.00 to PM Time Budget, total to $28,000.00 in PM Time Return $182,242.14 from unallocated to the MM25 pool fund. Thank you, let me know if you have any questions -- Oliver Shimp, PE

## #9422.00 Misc
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 163
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9422.00 Horizon Architecture
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP#942200-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525014902 | 2025-01-14 | PO Procore | 23565 | 23565 |  |  | 23565
PRC 3352501PA4902 | 2025-03-14 | Inv. 9422.00-01 |  | 23565 | 11347.5 | 11347.5 | 12217.5
PRC 3352501PB4902 | 2025-04-24 | Inv. 9422.00-02 |  | 23565 | 4526.5 | 15874 | 7691
PRC 3352501PC4902 | 2025-06-10 | Inv. 9422.00-03 |  | 23565 | 580 | 16454 | 7111 | FY25
PO 33526014902 | 2025-07-30 | Roll to FY26 | 0 | 23565 |  | 16454 | 7111
PRC 3352601PD4902 | 2025-09-12 | Inv. 9422.00-04 |  | 23565 | 1382 | 17836 | 5729
PRC 3352601PE4902 | 2025-10-10 | Inv. 9422.00-05 |  | 23565 | 2073 | 19909 | 3656
PRC 3352601PF4902 | 2025-11-14 | Inv. 9422.00-06 |  | 23565 | 1036.5 | 20945.5 | 2619.5
|  |  |  | 23565 |  | 20945.5 | 2619.5
|  |  |  | 23565 |  | 20945.5 | 2619.5
|  |  |  | 23565 |  | 20945.5 | 2619.5
|  |  |  | 23565 |  | 20945.5 | 2619.5
|  |  |  | 23565 |  | 20945.5 | 2619.5
|  | Totals: | 23565 |  | 20945.5 |  | 2619.5
|  | Design Development | 7370 |  | 7370 |  | 0
|  | Construction Documents | 7955 |  | 7955 |  | 0
|  | Bidding Assistance | 580 |  | 580 |  | 0
|  | Construction Phase | 6910 |  | 4491.5 |  | 2418.5
|  | Reimbursables | 750 |  | 549 |  | 201
|  | Total: | 23565 |  | 20945.5 |  | 2619.5

## #9422.00 Bi-State Masonry
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM25-9255 |  |  | RFB942200-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525161905 | 2025-06-10 | PO Procore | 899903 | 899903 |  |  | 899903 |  | FY25
PO 33526161905 | 2025-07-25 | Roll to FY26 | 0 | 899903 |  | 0 | 899903
PO 33526161905 | 2025-09-16 | CO #1 | 2127 | 902030 |  | 0 | 902030
PRC 3352616PA1905 | 2025-09-29 | Inv. 6463R |  | 902030 | 101632.89 | 101632.89 | 800397.11 | 5349.11
PRC 3352616PB1905 | 2025-10-28 | Inv. 6480R1 |  | 902030 | 142205.77 | 243838.66 | 658191.34 | 12833.64
PRC 3352616PC1905 | 2025-11-04 | Inv. 6549 |  | 902030 | 331850.14 | 575688.8 | 326341.2 | 30299.45
PRC 3352616PD1905 | 2025-12-18 | Inv. 6613 |  | 902030 | 150578.93 | 726267.73 | 175762.27 | 38224.67
PO 33526161905 | 2026-02-10 | CO #2 | 5320 | 907350 |  | 726267.73 | 181082.27
|  |  |  | 907350 |  | 726267.73 | 181082.27
|  |  |  | 907350 |  | 726267.73 | 181082.27
|  |  |  | 907350 |  | 726267.73 | 181082.27
|  |  |  | 907350 |  | 726267.73 | 181082.27
|  |  |  | 907350 |  | 726267.73 | 181082.27
|  | Totals: | 907350 |  | 726267.73 |  | 181082.27

## #9422.00 McGough Constructi (2)
DOC ASP Tuckpointing Priorities 7, 8, & 9 (29C20)
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525169901 | 2025-06-16 | PO Procore | 97415.31 | 97415.31 |  |  | 97415.31
PRC 3352516PA9901 | 2025-07-10 | Inv. 101368.007CA-01 |  | 97415.31 | 3431.87 | 3431.87 | 93983.44 | FY25
PO 33526169901 | 2025-07-30 | Roll to FY26 | 0 | 97415.31 |  | 3431.87 | 93983.44
PRC 3352616PB9901 | 2025-08-18 | Inv. 101368.007CA-02 |  | 97415.31 | 5887.04 | 9318.91 | 88096.4
PRC 3352616PC9901 | 2025-09-16 | Inv. 101368.007CA-03 |  | 97415.31 | 14906.25 | 24225.16 | 73190.15
PRC 3352616PD9901 | 2025-10-17 | Inv. 101368.007CA-04 |  | 97415.31 | 17042.48 | 41267.64 | 56147.67
PRC 3352616PE9901 | 2025-11-10 | Inv. 101368.007CA-05 |  | 97415.31 | 23541.21 | 64808.85 | 32606.46
PRC 3352616PF9901 | 2025-12-11 | Inv. 101368.007CA-06 |  | 97415.31 | 14934.9 | 79743.75 | 17671.56
PRC 3352616PG9901 | 2026-01-15 | Inv. 101368.007CA-07 |  | 97415.31 | 1073.36 | 80817.11 | 16598.2
PRC 3352616PH9901 | 2026-03-10 | Inv. 101368.007CA-08 |  | 97415.31 | 534.6 | 81351.71 | 16063.6
|  |  |  | 97415.31 |  | 81351.71 | 16063.6
|  |  |  | 97415.31 |  | 81351.71 | 16063.6
|  |  |  | 97415.31 |  | 81351.71 | 16063.6
|  | Totals: | 97415.31 |  | 81351.71 |  | 16063.6
|  | CM Services | 46081.16 |  | 40208.99 |  | 5872.17
|  | Reimbursables | 6339 |  | 2918.1 |  | 3420.9
|  | Fees | 44995.15 |  | 38224.62 |  | 6770.53
|  | Total: | 97415.31 |  | 81351.71 |  | 16063.6

## RECAP #9442.00
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
| Program code 944200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 431667.61
C | McGough Construction |  | 11257.63 | 11257.63 | 0
C | PM TIME |  | 21371.75 | 21371.75 | 0
C | Misc. |  | 1386.65 | 1386.65 | 0
C | Horizon Architecture |  | 16855 | 16855 | 0
C | Bi-State Masonry |  | 351337.1 | 351337.1 | 0
C | McGough Construction (2) |  | 29459.48 | 29459.48 | 0
| Total Project Cost | 431667.61 | 431667.61 | 431667.61 | 0 | 0
Closed 01/21/26

## #9442.00 McGough Construction
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
McGoughConstruction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525347907 | 2024-12-12 | PO Procore | 17451.65 | 17451.65 |  |  | 17451.65
PCR 3352534PA7907 | 2025-01-14 | Inv. 101368.005-PC01 |  | 17451.65 | 1745.3 | 1745.3 | 15706.35
PCR 3352534PB7907 | 2025-02-12 | Inv. 101368.005-PC02 |  | 17451.65 | 1053.05 | 2798.35 | 14653.3
PCR 3352534PC7907 | 2025-03-19 | Inv. 101368.005-PC03 |  | 17451.65 | 664.68 | 3463.03 | 13988.62
PCR 3352534PD7907 | 2025-04-15 | Inv. 101368.005-PC04 |  | 17451.65 | 1945.22 | 5408.25 | 12043.4
PCR 3352534PE7907 | 2025-05-07 | Inv. 101368.005-PC05 |  | 17451.65 | 5085.51 | 10493.76 | 6957.89
PCR 3352534PF7907 | 2025-06-13 | Inv. 101368.005-PC06 Final | -6194.02 | 11257.63 | 763.87 | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  |  |  | 11257.63 |  | 11257.63 | 0
|  | Totals: | 11257.63 |  | 11257.63 |  | 0 | FINAL
|  | CM Services: | 10883.63 |  | 10883.63 |  | 0
|  | Reimbursables: | 374 |  | 374 |  | 0
|  | Total: | 11257.63 |  | 11257.63 |  | 0

## #9442.00 PM TIME
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731P
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 21371.75 | 21371.75 |  |  | 21371.75
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 21371.75 | 103.44 | 103.44 | 21268.31
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 21371.75 | 684 | 787.44 | 20584.31
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 21371.75 | 109.13 | 896.57 | 20475.18
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 21371.75 | 1092.5 | 1989.07 | 19382.68
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 21371.75 | 74.39 | 2063.46 | 19308.29
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 21371.75 | 794.8 | 2858.26 | 18513.49
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 21371.75 | 175.81 | 3034.07 | 18337.68
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 21371.75 | 761.4 | 3795.47 | 17576.28
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 21371.75 | 194.86 | 3990.33 | 17381.42
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 21371.75 | 1391.6 | 5381.93 | 15989.82
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 21371.75 | 253.51 | 5635.44 | 15736.31
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 21371.75 | 1743.1 | 7378.54 | 13993.21
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 21371.75 | 225.7 | 7604.24 | 13767.51
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 21371.75 | 1765.4 | 9369.64 | 12002.11
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 21371.75 | 110.4 | 9480.04 | 11891.71
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 21371.75 | 857 | 10337.04 | 11034.71
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 21371.75 | 115.28 | 10452.32 | 10919.43
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 21371.75 | 1267.4 | 11719.72 | 9652.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 21371.75 | 309.73 | 12029.45 | 9342.3
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 21371.75 | 2385.2 | 14414.65 | 6957.1
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 21371.75 | 312.94 | 14727.59 | 6644.16
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 21371.75 | 1606.7 | 16334.29 | 5037.46
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 21371.75 | 169.34 | 16503.63 | 4868.12
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 21371.75 | 2336.3 | 18839.93 | 2531.82
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 21371.75 | 233.67 | 19073.6 | 2298.15
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 21371.75 | 1125 | 20198.6 | 1173.15
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 21371.75 | 94.95 | 20293.55 | 1078.2
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 21371.75 | 1078.2 | 21371.75 | -2.2737e-12
[5 empty] | 21371.75 |  | 21371.75 | -2.2737e-12
[5 empty] | 21371.75 |  | 21371.75 | -2.2737e-12
[5 empty] | 21371.75 |  | 21371.75 | -2.2737e-12
|  |  | Totals: | 21371.75 |  | 21371.75 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: November PM Time $Joni Adams, Brandon 9:01 AM (45 minutes ago) to me Finance, Please increase the DAS Cost for MM25 9442.00 $10,000 Please set the DAS Cost for MM25 9443.00 to $25,000 Regards, Brandon Adams Adams, Brandon 2:41 PM (32 minutes ago) to me Please increase the PM Time for the following projects: MM24 9372.00 - $10,000 MM24 9477.00 - $1,475.14 - Please close PM Time and this project can close. MM25 9442.00 - $5,000 Regards, Adams, Brandon 1:51 PM (1 hour ago) to me DA24 9414.00 (3,176.95) increase by $6,000 DA26 9481.00 (1302.54) set pm budget at $10,000 MM23 9450.00 (491.54) increase by $491.54 and close MM25 9442.00 (1,198.60) increase by $2,000 Regards, Brandon Adams

## #9442.00 Misc
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525097905 | 2025-04-07 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2640102 | 1155 | 1155
PRC 33525139901 | 2025-05-19 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1740 | 231.65 | 1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
|  |  |  | Totals: |  | 1386.65

## #9442.00 Horizon Architecture
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944200-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525015901 | 2025-01-15 | PO Procore | 16855 | 16855 |  |  | 16855
PRC 3352501PA5901 | 2025-03-04 | Inv. 9442.00-01 |  | 16855 | 3007.5 | 3007.5 | 13847.5
PRC 3352501PB5901 | 2025-05-06 | Inv. 9442.00-02 |  | 16855 | 9322.5 | 12330 | 4525
PRC 3352501PC5901 | 2025-06-13 | Inv. 9442.00-03 |  | 16855 | 1181.5 | 13511.5 | 3343.5 | FY25
PO 33526015901 | 2025-07-25 | Roll to FY26 | 0 | 16855 |  | 13511.5 | 3343.5
PRC 3352601PD5901 | 2025-09-15 | Inv. 9442.00-04 |  | 16855 | 557.25 | 14068.75 | 2786.25
PRC 3352601PE5901 | 2025-10-06 | Inv. 9442.00-05 |  | 16855 | 928.75 | 14997.5 | 1857.5
PRC 3352601PF5901 | 2025-11-04 | Inv. 9442.00-06 |  | 16855 | 743 | 15740.5 | 1114.5
PRC 3352601PG5901 | 2026-01-06 | Inv. 9442.00-07 - FINAL |  | 16855 | 1114.5 | 16855 | 0
|  |  |  | 16855 |  | 16855 | 0
|  |  |  | 16855 |  | 16855 | 0
|  |  |  | 16855 |  | 16855 | 0
|  |  |  | 16855 |  | 16855 | 0
|  | Totals: | 16855 |  | 16855 |  | 0 | FINAL
|  | Desgin Development | 6015 |  | 6015 |  | 0
|  | Construction Documents | 6315 |  | 6315 |  | 0
|  | Bidding/Negotiation | 810 |  | 810 |  | 0
|  | Construction Phase | 3715 |  | 3715 |  | 0
|  | Total: | 16855 |  | 16855 |  | 0

## #9442.00 Bi-State Masonry
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944200-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525127905 | 2025-05-07 | PO Procore | 344711 | 344711 |  |  | 344711 |  | FY25
PO 33526127905 | 2025-07-25 | Roll to FY26 | 0 | 344711 |  | 0 | 344711
PO 33526127905 | 2025-09-12 | CO #1 | 7725 | 352436 |  | 0 | 352436
PRC 3352612PA7905 | 2025-09-15 | Inv. 6461 |  | 352436 | 93241.52 | 93241.52 | 259194.48 | 4907.48
PRC 3352612PB7905 | 2025-10-08 | Inv. 6478 |  | 352436 | 107608 | 200849.52 | 151586.48 | 10571.08
PRC 3352612PC7905 | 2025-11-04 | Inv. 6548 |  | 352436 | 111448.47 | 312297.99 | 40138.01 | 16436.81
PO 33526127905 | 2025-11-24 | CO #2 | -1098.9 | 351337.1 |  | 312297.99 | 39039.11
PRC 3352612PD7905 | 2025-12-05 | Inv. 6585 |  | 351337.1 | 18194.67 | 330492.66 | 20844.44 | 17394.44
PRC 3352612PE7905 | 2025-12-22 | Inv. 6612 |  | 351337.1 | 3277.5 | 333770.16 | 17566.94 | 17566.94
PRC 3352612PF7905 | 2026-01-02 | Inv. 6627 - Retainage |  | 351337.1 | 17566.94 | 351337.1 | -1.819e-11
|  |  |  | 351337.1 |  | 351337.1 | -1.819e-11
|  |  |  | 351337.1 |  | 351337.1 | -1.819e-11
|  |  |  | 351337.1 |  | 351337.1 | -1.819e-11
|  | Totals: | 351337.1 |  | 351337.1 |  | 0 | FINAL

## #9442.00 McGough Constructi (2)
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
McGoughConstruction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525129900 | 2025-05-09 | PO Procore | 63248.18 | 63248.18 |  |  | 63248.18
PRC 3352512PA9900 | 2025-06-13 | Inv. 101368.005-CA01 |  | 63248.18 | 1635.15 | 1635.15 | 61613.03
PRC 3352512PB9900 | 2025-07-15 | Inv. 101368.005-CA02 |  | 63248.18 | 1421.41 | 3056.56 | 60191.62 | FY25
PO 33526129900 | 2025-07-25 | Roll to FY26 | 0 | 63248.18 |  | 3056.56 | 60191.62
PRC 3352612PC9900 | 2025-04-15 | Inv. 101368.005-CA03 |  | 63248.18 | 2422.31 | 5478.87 | 57769.31
PRC 3352612PD9900 | 2025-09-15 | Inv. 101368.005-CA04 |  | 63248.18 | 10082.46 | 15561.33 | 47686.85
PRC 3352612PE9900 | 2025-10-14 | Inv. 101368.005-CA05 |  | 63248.18 | 5289.78 | 20851.11 | 42397.07
PRC 3352612PF9900 | 2025-11-06 | Inv. 101368.005-CA06 |  | 63248.18 | 5429.95 | 26281.06 | 36967.12
PRC 3352612PG9900 | 2025-12-10 | Inv. 101368.005-CA07 |  | 63248.18 | 2404.46 | 28685.52 | 34562.66
PRC 3352612PH9900 | 2026-01-12 | Inv. 101368.005-CA08 FINAL | -33788.7 | 29459.48 | 773.96 | 29459.48 | 0
|  |  |  | 29459.48 |  | 29459.48 | 0
|  |  |  | 29459.48 |  | 29459.48 | 0
|  |  |  | 29459.48 |  | 29459.48 | 0
|  | Totals: | 29459.48 |  | 29459.48 |  | 0 | FINAL
|  | CM Services: | 28339.48 |  | 28339.48 |  | 0
|  | Reimbursables: | 1120 |  | 1120 |  | 0
|  | Total: | 29459.48 |  | 29459.48 |  | 0

## RECAP #9443.00
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
| Program code 944300 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1275000
C | McGough Construction |  | 9398.35 | 9398.35 | 0
| PM TIME |  | 26200 | 25337.59 | 862.41
| Misc. |  | 2125.2 | 2125.2 | 0
| Horizon Architecture |  | 16855 | 16112 | 743
| McGough Construction (2) |  | 116642.99 | 95134 | 21508.99
| Bi-State Contracting |  | 1082015.81 | 1027914.99 | 54100.82
| Total Project Cost | 1275000 | 1253237.35 | 1176022.13 | 77215.22 | 21762.65

## #9443.00 McGough Construction
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525347908 | 2024-12-12 | PO Procore | 16341.2 | 16341.2 |  |  | 16341.2
PRC 3352534PA7908 | 2025-01-14 | Inv. 101368.006-PC01 |  | 16341.2 | 1231.51 | 1231.51 | 15109.69
PRC 3352534PB7908 | 2025-02-12 | Inv. 101368.006-PC02 |  | 16341.2 | 842.2 | 2073.71 | 14267.49
PRC 3352534PC7908 | 2025-03-19 | Inv. 101368.006-PC03 |  | 16341.2 | 746.96 | 2820.67 | 13520.53
PRC 3352534PD7908 | 2025-04-15 | Inv. 101368.006-PC04 |  | 16341.2 | 1537.18 | 4357.85 | 11983.35
PRC 3352534PE7908 | 2025-05-07 | Inv. 101368.006-PC05 |  | 16341.2 | 4199.99 | 8557.84 | 7783.36
PRC 3352534PF7908 | 2025-06-13 | Inv. 101368.006-PC05 Final | -6942.85 | 9398.35 | 840.51 | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  |  |  | 9398.35 |  | 9398.35 | 0
|  | Totals: | 9398.35 |  | 9398.35 |  | 0 | FINAL
|  | CM Services | 9024.35 |  | 9024.35 |  | 0
|  | Reimbursables | 374 |  | 374 |  | 0
|  | Total: | 9398.35 |  | 9398.35 |  | 0

## #9443.00 PM TIME
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731Q
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 26200 | 26200 |  |  | 26200
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 26200 | 65.35 | 65.35 | 26134.65
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 26200 | 436 | 501.35 | 25698.65
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 26200 | 135.01 | 636.36 | 25563.64
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 26200 | 1124.1 | 1760.46 | 24439.54
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 26200 | 118.82 | 1879.28 | 24320.72
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 26200 | 1261.1 | 3140.38 | 23059.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 26200 | 197.72 | 3338.1 | 22861.9
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 26200 | 855.9 | 4194 | 22006
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 26200 | 220.44 | 4414.44 | 21785.56
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 26200 | 1577.7 | 5992.14 | 20207.86
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 26200 | 253.51 | 6245.65 | 19954.35
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 26200 | 1743.1 | 7988.75 | 18211.25
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 26200 | 230.77 | 8219.52 | 17980.48
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 26200 | 1807.4 | 10026.92 | 16173.08
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 26200 | 104.36 | 10131.28 | 16068.72
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 26200 | 811.2 | 10942.48 | 15257.52
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 26200 | 125.85 | 11068.33 | 15131.67
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 26200 | 1381.6 | 12449.93 | 13750.07
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 26200 | 169.68 | 12619.61 | 13580.39
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 26200 | 1306.6 | 13926.21 | 12273.79
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 26200 | 279.75 | 14205.96 | 11994.04
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 26200 | 1435.5 | 15641.46 | 10558.54
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 26200 | 169.34 | 15810.8 | 10389.2
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 26200 | 1679.6 | 17490.4 | 8709.6
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 26200 | 218.45 | 17708.85 | 8491.15
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 26200 | 1393.3 | 19102.15 | 7097.85
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 26200 | 185.04 | 19287.19 | 6912.81
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 26200 | 2102.8 | 21389.99 | 4810.01
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 26200 | 173.46 | 21563.45 | 4636.55
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 26200 | 2155.9 | 23719.35 | 2480.65
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 26200 | 129.44 | 23848.79 | 2351.21
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 26200 | 1488.8 | 25337.59 | 862.41
[5 empty] | 26200 |  | 25337.59 | 862.41
[5 empty] | 26200 |  | 25337.59 | 862.41
[5 empty] | 26200 |  | 25337.59 | 862.41
|  |  | Totals: | 26200 |  | 25337.59 |  | 862.41
Note on E9: Huggins, Joni [DAS]: Re: November PM Time $Joni Adams, Brandon 9:01 AM (45 minutes ago) to me Finance, Please increase the DAS Cost for MM25 9442.00 $10,000 Please set the DAS Cost for MM25 9443.00 to $25,000 Regards, Brandon Adams Re: February PM Time Posted $Joni Adams, Brandon 2:26 PM (15 minutes ago) to me DA24 9414.00 $(1,363.77) Please increase by $3000 DA24 9423.00 $(205.06) Please increase by $205.06 - DPS has been asked to transfer funds MM23 9465.00 $(537.67) Please increase by $2500 MM24 9372.00 $(3520.54) Please increase by $6000 MM25 9443.00 $(337.59) Please increase by $1200 Regards, Brandon Adams

## #9443.00 Misc
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525097903 | 2025-04-07 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2640099 | 1802.5 | 1802.5
PRC 33525136902 | 2025-05-16 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1741 | 322.7 | 2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
|  |  |  | Totals: |  | 2125.2

## #9443.00 Horizon Architecture
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944300-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525015902 | 2025-01-15 | PO Procore | 16855 | 16855 |  |  | 16855
PRC 3352501PA5902 | 2025-03-04 | Inv. 9443.00-01 |  | 16855 | 3007.5 | 3007.5 | 13847.5
PRC 3352501PB5902 | 2025-05-06 | Inv. 9443.00-02 |  | 16855 | 9322.5 | 12330 | 4525
PRC 3352501PC5902 | 2025-06-13 | Inv. 9443.00-03 |  | 16855 | 1181.5 | 13511.5 | 3343.5 | FY25
PO 33526015902 | 2025-07-25 | Roll to FY26 | 0 | 16855 |  | 13511.5 | 3343.5
PRC 3352601PD5902 | 2025-11-04 | Inv. 9443.00-04 |  | 16855 | 743 | 14254.5 | 2600.5
PRC 3352601PE5902 | 2026-02-09 | Inv. 9443.00-05 |  | 16855 | 743 | 14997.5 | 1857.5
PRC 3352601PF5902 | 2026-03-23 | Inv. 9443.00-06 |  | 16855 | 1114.5 | 16112 | 743
|  |  |  | 16855 |  | 16112 | 743
|  |  |  | 16855 |  | 16112 | 743
|  |  |  | 16855 |  | 16112 | 743
|  |  |  | 16855 |  | 16112 | 743
|  |  |  | 16855 |  | 16112 | 743
|  | Totals: | 16855 |  | 16112 |  | 743
|  | Design Development | 6015 |  | 6015 |  | 0
|  | Construction Documents | 6315 |  | 6315 |  | 0
|  | Bidding/Negotiation | 810 |  | 810 |  | 0
|  | Construction Phase | 3715 |  | 2972 |  | 743
|  | Total: | 16855 |  | 16112 |  | 743

## #9443.00 McGough Constructi (2)
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525128903 | 2025-05-08 | PO Procore | 116642.99 | 116642.99 |  |  | 116642.99
PRC 3352512PA8903 | 2025-06-16 | Inv. 101368.006-CA01 |  | 116642.99 | 1195.63 | 1195.63 | 115447.36
PRC 3352512PB8903 | 2025-07-15 | Inv. 101368.006-CA02 |  | 116642.99 | 3345.02 | 4540.65 | 112102.34 | FY25
PO 33526128903 | 2025-07-25 | Roll to FY26 | 0 | 116642.99 |  | 4540.65 | 112102.34
PRC 3352612PC8903 | 2025-08-14 | Inv. 101368.006-CA03 |  | 116642.99 | 481.14 | 5021.79 | 111621.2
PRC 3352612PD8903 | 2025-09-15 | Inv. 101368.006-CA04 |  | 116642.99 | 1620.18 | 6641.97 | 110001.02
PRC 3352612PE8903 | 2025-10-17 | Inv. 101368.006-CA05 |  | 116642.99 | 2184.89 | 8826.86 | 107816.13
PRC 3352612PF8903 | 2025-11-06 | Inv. 101368.006-CA06 |  | 116642.99 | 8542.95 | 17369.81 | 99273.18
PRC 3352612PG8903 | 2025-12-10 | Inv. 101368.006-CA07 |  | 116642.99 | 22363.56 | 39733.37 | 76909.62
PRC 3352612PH8903 | 2026-01-12 | Inv. 101368.006-CA08 |  | 116642.99 | 24221.37 | 63954.74 | 52688.25
PRC 3352612PI8903 | 2026-02-16 | Inv. 101368.006-CA09 |  | 116642.99 | 14280.93 | 78235.67 | 38407.32
PRC 3352612PJ8903 | 2026-03-19 | Inv. 101368.006-CA10 |  | 116642.99 | 16898.33 | 95134 | 21508.99
|  |  |  | 116642.99 |  | 95134 | 21508.99
|  | Totals: | 116642.99 |  | 95134 |  | 21508.99
|  | CM Services | 58574.34 |  | 40016.3 |  | 18558.04
|  | Reimbursables | 4760 |  | 3290 |  | 1470
|  | Fees | 53308.65 |  | 51827.7 |  | 1480.95
|  | Total: | 116642.99 |  | 95134 |  | 21508.99

## #9443.00 Bi-State Contracting
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
Bi-State Contracting |  |  | Vendor: 00002101614
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525133909 | 2025-05-12 | PO Procore | 1066173 | 1066173 |  |  | 1066173
PRC 3352513PA3909 | 2025-07-03 | Inv. 9443.00-01 |  | 1066173 | 35932.8 | 35932.8 | 1030240.2 | 1891.2 | FY25
PO 33526133909 | 2025-07-25 | Roll to FY26 | 0 | 1066173 |  | 35932.8 | 1030240.2
PRC 3352613PB3909 | 2025-08-18 | Inv. 9443.00-02 |  | 1066173 | 8550 | 44482.8 | 1021690.2 | 2341.2
PRC 3352613PC3909 | 2025-09-15 | Inv. 9443.00-03 |  | 1066173 | 8550 | 53032.8 | 1013140.2 | 2791.2
PRC 3352613PD3909 | 2025-10-08 | Inv. 9443.00-04 |  | 1066173 | 87248.47 | 140281.27 | 925891.73 | 7383.23
PRC 3352613PE3909 | 2025-10-31 | Inv. 9443.00-005 |  | 1066173 | 364794.18 | 505075.45 | 561097.55 | 26582.93
PO 33526133909 | 2025-11-07 | CO #1 | 16063.62 | 1082236.62 |  | 505075.45 | 577161.17
PO 33526133909 | 2025-12-03 | CO #2 | 246.33 | 1082482.95 |  | 505075.45 | 577407.5
PRC 3352613PF3909 | 2025-12-22 | Inv. 9443.00-06 |  | 1082482.95 | 353473.47 | 858548.92 | 223934.03 | 45186.8
PRC 3352613PG3909 | 2026-01-02 | Inv. 9443.00-07 |  | 1082482.95 | 64652.09 | 923201.01 | 159281.94 | 48589.54
PRC 3352613PH3909 | 2026-01-30 | Inv. 9443.00-08-REV |  | 1082482.95 | 61525.31 | 984726.32 | 97756.63 | 51827.72
PO 33526133909 | 2026-02-18 | CO #3 | 1711.82 | 1084194.77 |  | 984726.32 | 99468.45
PO 33526133909 | 2026-02-27 | CO #4 | -2178.96 | 1082015.81 |  | 984726.32 | 97289.49
PRC 3352613PI3909 | 2026-03-03 | Inv. 9443.00-09 |  | 1082015.81 | 33059.77 | 1017786.09 | 64229.72 | 53567.72
PRC 3352613PJ3909 | 2026-03-30 | Inv. 9443.00-10 |  | 1082015.81 | 10128.9 | 1027914.99 | 54100.82 | 54100.82
|  |  |  | 1082015.81 |  | 1027914.99 | 54100.82
|  |  |  | 1082015.81 |  | 1027914.99 | 54100.82
|  | Totals: | 1082015.81 |  | 1027914.99 |  | 54100.82

## RECAP #9444.00
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
| Program code 944400 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1950000
C | Samuels Group |  | 31628.48 | 31628.48 | 0
| PM TIME |  | 40000 | 15341.62 | 24658.38
| Misc. |  | 2549.03 | 2549.03 | 0
| Snyder & Associates |  | 99710 | 73470 | 26240
C | Controlled Asbestos |  | 18243.7 | 18243.7 | 0
| Samuels Group (2) |  | 148972.83 | 6504.98 | 142467.85
| A&W Enterprise |  | 775000 | 0 | 775000
| Rasmussen Mechanical |  | 739439 | 0 | 739439
| O'Neal Electric |  | 44000 | 0 | 44000
| Total Project Cost | 1950000 | 1899543.04 | 147737.81 | 1751805.23 | 50456.96

## #9444.00 Samuels Group
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525338903 | 2024-12-03 | PO Procore | 32642.58 | 32642.58 |  |  | 32642.58
PRC 3352533PA8903 | 2025-01-08 | Inv. 7741.01 PC |  | 32642.58 | 3145.78 | 3145.78 | 29496.8
PRC 3352533PB8903 | 2025-02-12 | Inv. 7741.02PC |  | 32642.58 | 4134.53 | 7280.31 | 25362.27
PRC 3352533PC8903 | 2025-03-11 | Inv. 7741.03 PC |  | 32642.58 | 2694.58 | 9974.89 | 22667.69
PRC 3352533PD8903 | 2025-05-07 | Inv. 7741.04PC |  | 32642.58 | 2545.08 | 12519.97 | 20122.61
PRC 3352533PE8903 | 2025-06-10 | Inv. 7741.05 PC |  | 32642.58 | 1081.07 | 13601.04 | 19041.54
PRC 3352533PF8903 | 2025-07-10 | Inv. 7741.06 PC |  | 32642.58 | 2090.39 | 15691.43 | 16951.15 | FY25
PO 33526338903 | 2025-07-25 | Roll to FY26 | 0 | 32642.58 |  | 15691.43 | 16951.15
PO 3352633PG8903 | 2025-08-19 | Inv. 7741.07 PC |  | 32642.58 | 2734.28 | 18425.71 | 14216.87
PO 3352633PH8903 | 2025-09-12 | Inv. 7741.08 PC |  | 32642.58 | 2089.95 | 20515.66 | 12126.92
PO 3352633PI8903 | 2025-11-05 | Inv. 7741.09 PC |  | 32642.58 | 4648.94 | 25164.6 | 7477.98
PO 3352633PJ8903 | 2025-12-04 | Inv. 7741.10 PC |  | 32642.58 | 2008.73 | 27173.33 | 5469.25
PO 3352633PK8903 | 2026-03-04 | Inv. 7741.11PC Final | -1014.1 | 31628.48 | 4455.15 | 31628.48 | 2.16e-12
|  |  |  | 31628.48 |  | 31628.48 | 2.16e-12
|  |  |  | 31628.48 |  | 31628.48 | 2.16e-12
|  | Totals: | 31628.48 |  | 31628.48 |  | 0 | FINAL
|  | CM Services | 31388.48 |  | 31388.48 |  | 0
|  | Reimbursables | 240 |  | 240 |  | 0
|  | Total: | 31628.48 |  | 31628.48 |  | 0

## #9444.00 PM TIME
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731R
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 40000 | 40000 |  |  | 40000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 40000 | 108.64 | 108.64 | 39891.36
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 40000 | 721.2 | 829.84 | 39170.16
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 40000 | 102.66 | 932.5 | 39067.5
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 40000 | 1029.6 | 1962.1 | 38037.9
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 40000 | 130.21 | 2092.31 | 37907.69
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 40000 | 1387.9 | 3480.21 | 36519.79
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 40000 | 200.25 | 3680.46 | 36319.54
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 40000 | 866.8 | 4547.26 | 35452.74
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 40000 | 159.42 | 4706.68 | 35293.32
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 40000 | 1142.2 | 5848.88 | 34151.12
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 40000 | 106.29 | 5955.17 | 34044.83
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 40000 | 729.1 | 6684.27 | 33315.73
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 40000 | 82.45 | 6766.72 | 33233.28
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 40000 | 646.5 | 7413.22 | 32586.78
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 40000 | 215.18 | 7628.4 | 32371.6
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 40000 | 1670.4 | 9298.8 | 30701.2
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 40000 | 141.27 | 9440.07 | 30559.93
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 40000 | 1554.5 | 10994.57 | 29005.43
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 40000 | 99.87 | 11094.44 | 28905.56
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 40000 | 776.9 | 11871.34 | 28128.66
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 40000 | 63.65 | 11934.99 | 28065.01
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 40000 | 332.5 | 12267.49 | 27732.51
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 40000 | 42.41 | 12309.9 | 27690.1
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 40000 | 417.3 | 12727.2 | 27272.8
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 40000 | 46.05 | 12773.25 | 27226.75
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 40000 | 294.2 | 13067.45 | 26932.55
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 40000 | 84.69 | 13152.14 | 26847.86
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 40000 | 961.7 | 14113.84 | 25886.16
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 40000 | 39.04 | 14152.88 | 25847.12
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 40000 | 486.1 | 14638.98 | 25361.02
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 40000 | 55.84 | 14694.82 | 25305.18
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 40000 | 646.8 | 15341.62 | 24658.38
[5 empty] | 40000 |  | 15341.62 | 24658.38
[5 empty] | 40000 |  | 15341.62 | 24658.38
[5 empty] | 40000 |  | 15341.62 | 24658.38
|  |  | Totals: | 40000 |  | 15341.62 |  | 24658.38
Note on E9: Huggins, Joni [DAS]: MM25 - 9444.00 Budget Adjustment (HOT Item) $Joni Tonyan, Brad 9:51 AM (9 minutes ago) to me, Geoff, Jennifer, Brad DAS Finance, Please increase the overall project budget on 9444.00 by $600,000 within funding ORG MM25 which shall bring the overall project total funding value to $1,950,000. Please also increase the PM/DAS time budget from $15,000 to $40,000 which will get us through project completion. Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9444.00 Misc
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 165
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525048911 | 2025-02-17 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2627700 | 1623.75 | 1623.75
PRC 33526337907 | 2025-12-03 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2324 | 434.35 | 2058.1
PRC 33526029912 | 2026-01-26 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2449 | 238.58 | 2296.68
PRC 33526063906 | 2026-03-04 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2588 | 252.35 | 2549.03
2549.03
2549.03
2549.03
2549.03
2549.03
2549.03
2549.03
2549.03
|  |  |  | Totals: |  | 2549.03

## #9444.00 Synder & Associates
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Synder & Associates |  |  | Vendor: 00002119810
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525049903 | 2025-02-18 | PO Procore | 99710 | 99710 |  |  | 99710
PRC 3352504PA9903 | 2025-05-07 | Inv. 9444.00-01 |  | 99710 | 20132 | 20132 | 79578
PRC 3352504PB9903 | 2025-05-29 | Inv. 9444.00-02 |  | 99710 | 13447.8 | 33579.8 | 66130.2
PRC 3352504PC9903 | 2025-07-10 | Inv. 9444.00-03 |  | 99710 | 9085.2 | 42665 | 57045 | FY25
PO 33526049903 | 2025-07-25 | Roll to FY26 | 0 | 99710 |  | 42665 | 57045
PRC 3352604PD9903 | 2025-10-28 | Inv. 9444.00-04 |  | 99710 | 23257 | 65922 | 33788
PRC 3352604PE9903 | 2026-03-04 | Inv. 9444.00-05 |  | 99710 | 7548 | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  |  |  | 99710 |  | 73470 | 26240
|  | Totals: | 99710 |  | 73470 |  | 26240
|  | Design 50% | 29884 |  | 29884 |  | 0
|  | Design 95% | 15182 |  | 15182 |  | 0
|  | Design 100% | 15666 |  | 15666 |  | 0
|  | Bidding | 3248 |  | 3248 |  | 0
|  | Construction Admin | 26240 |  |  |  | 26240
|  | Geotechnical Work | 4300 |  | 4300 |  | 0
|  | Survey Crew | 5190 |  | 5190 |  | 0
|  | Total: | 99710 |  | 73470 |  | 26240

## #9444.00 Controlled Asbestos
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM25-9255 |  |  | MA21060B
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525090915 | 2025-03-31 | DO Procore | 23122.5 | 23122.5 |  |  | 23122.5
PRC 33525090PA915 | 2025-06-16 | Inv. 0010929-IN - Final | -4878.8 | 18243.7 | 18243.7 | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  |  |  | 18243.7 |  | 18243.7 | 0
|  | Totals: | 18243.7 |  | 18243.7 |  | 0 | FINAL
|  | Line 1 Labor 317Hrs | 16510 |  | 16510 |  | 0
|  | Line 7 | 0 |  | 0 |  | 0
|  | Line 10 Friable 2 ton | 173.7 |  | 173.7 |  | 0
|  | Line 12 Mileage 3,515 miles | 1560 |  | 1560 |  | 0
|  | Total: | 18243.7 |  | 18243.7 |  | 0

## #9444.00 Samuels Group (2)
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Samuels Group(2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526356902 | 2025-12-22 | PO Procore | 109800.88 | 109800.88 |  |  | 109800.88
PRC 3352635PA6902 | 2026-02-03 | Inv. 7843.50 CA |  | 109800.88 | 3181.52 | 3181.52 | 106619.36
PRC 3352635PB6902 | 2026-03-04 | Inv. 7843.51 CA |  | 109800.88 | 3323.46 | 6504.98 | 103295.9
PO 33526356902 | 2026-03-09 | CO #1 | 39171.95 | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  |  |  | 148972.83 |  | 6504.98 | 142467.85
|  | Totals: | 148972.83 |  | 6504.98 |  | 142467.85
|  | CM Services | 68550.88 |  | 5004.98 |  | 63545.9
|  | Reimbursables | 2500 |  |  |  | 2500
|  | 5% Fees | 38750 |  | 1500 |  | 37250
|  | CO #1 | 39171.95 |  |  |  | 39171.95
|  | Total: | 148972.83 |  | 6504.98 |  | 142467.85

## #9444.00 A&W Enterprise
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
A&W Enterprise |  |  | Vendor: 00003055532
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944400-01
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526363903 | 2025-12-29 | PO Procore | 775000 | 775000 |  |  | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  | Totals: | 775000 |  | 0 |  | 775000

## #9444.00 Rasmussen Mechanical
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Rasmussen Mechanical |  |  | Vendor: 00002109813
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944400-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526070918 | 2026-03-11 | PO Procore | 739439 | 739439 |  |  | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  |  |  | 739439 |  | 0 | 739439
|  | Totals: | 739439 |  | 0 |  | 739439

## #9444.00 ONeal Electric
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
O'Neal Electric |  |  | Vendor: 00002115025
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944400-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526075905 | 2026-03-16 | PO Procore | 44000 | 44000 |  |  | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  |  |  | 44000 |  | 0 | 44000
|  | Totals: | 44000 |  | 0 |  | 44000

## RECAP #9445.00
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
| Program code 944500 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1900000
C | Samuels Group |  | 28873.02 | 28873.02 | 0
| PM TIME |  | 22255 | 17584.31 | 4670.69
| Misc. |  | 470.45 | 470.45 | 0
| KCL Engineering |  | 53685 | 42529 | 11156
C | Terracon |  | 3215.5 | 3215.5 | 0
| Samuels Group (2) |  | 172002.01 | 4100.42 | 167901.59
| Gerad Electric Inc |  | 1372641 | 9698.06 | 1362942.94
| Total Project Cost | 1900000 | 1653141.98 | 106470.76 | 1546671.22 | 246858.02

## #9445.00 Samuels Group
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525324900 | 2024-11-19 | PO Procore | 28873.02 | 28873.02 |  |  | 28873.02
PRC 3352532PA4900 | 2024-12-06 | Inv. 9445.01 PC |  | 28873.02 | 846.53 | 846.53 | 28026.49
PRC 3352532PB4900 | 2025-01-08 | Inv. 9445.02 PC |  | 28873.02 | 846.53 | 1693.06 | 27179.96
PRC 3352532PC4900 | 2025-02-17 | Inv. 9445.03PC |  | 28873.02 | 2725.57 | 4418.63 | 24454.39
PRC 3352532PD4900 | 2025-03-10 | Inv. 9445.04 PC |  | 28873.02 | 1576.77 | 5995.4 | 22877.62
PRC 3352532PE4900 | 2025-04-04 | Inv. 9445.05 PC |  | 28873.02 | 747.65 | 6743.05 | 22129.97
PRC 3352532PF4900 | 2025-05-09 | Inv. 9445.06 PC |  | 28873.02 | 3052.14 | 9795.19 | 19077.83
PRC 3352532PG4900 | 2025-06-05 | Inv. 9445.07 PC |  | 28873.02 | 5044.03 | 14839.22 | 14033.8
PRC 3352532PH4900 | 2025-07-17 | Inv. 9445.08 PC |  | 28873.02 | 791.13 | 15630.35 | 13242.67 | FY25
PO 33526324900 | 2025-07-25 | Roll to FY26 | 0 | 28873.02 |  | 15630.35 | 13242.67
PRC 3352632PI4900 | 2025-08-08 | Inv. 9445.09 PC |  | 28873.02 | 3468.84 | 19099.19 | 9773.83
PRC 3352632PJ4900 | 2025-09-12 | Inv. 9445.10 PC |  | 28873.02 | 4397.76 | 23496.95 | 5376.07
PRC 3352632PK4900 | 2025-10-10 | Inv. 9445.11 PC |  | 28873.02 | 1575.4 | 25072.35 | 3800.67
PRC 3352632PL4900 | 2025-12-05 | Inv. 9445.12 PC FINAL |  | 28873.02 | 3800.67 | 28873.02 | 3.1832e-12
|  |  |  | 28873.02 |  | 28873.02 | 3.1832e-12
|  |  |  | 28873.02 |  | 28873.02 | 3.1832e-12
|  | Totals: | 28873.02 |  | 28873.02 |  | 0 | FINAL
|  | CM Services | 28153.02 |  | 28153.02 |  | 0
|  | Reimbursables | 720 |  | 720 |  | 0
|  | Total: | 28873.02 |  | 28873.02 |  | 0

## #9445.00 PM TIME
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731S
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22255 | 22255 |  |  | 22255
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 22255 | 103.44 | 103.44 | 22151.56
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 22255 | 687.3 | 790.74 | 21464.26
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 22255 | 27.01 | 817.75 | 21437.25
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 22255 | 272.5 | 1090.25 | 21164.75
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 22255 | 183.79 | 1274.04 | 20980.96
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 22255 | 1960.8 | 3234.84 | 19020.16
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 22255 | 323.67 | 3558.51 | 18696.49
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 22255 | 1399.9 | 4958.41 | 17296.59
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 22255 | 87.45 | 5045.86 | 17209.14
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 22255 | 627.6 | 5673.46 | 16581.54
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 22255 | 332.54 | 6006 | 16249
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 22255 | 2283.4 | 8289.4 | 13965.6
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 22255 | 29.41 | 8318.81 | 13936.19
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 22255 | 232.4 | 8551.21 | 13703.79
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 22255 | 67.78 | 8618.99 | 13636.01
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 22255 | 529.9 | 9148.89 | 13106.11
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 22255 | 80.38 | 9229.27 | 13025.73
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 22255 | 877.7 | 10106.97 | 12148.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 22255 | 269.54 | 10376.51 | 11878.49
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 22255 | 2075.8 | 12452.31 | 9802.69
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 22255 | 150.48 | 12602.79 | 9652.21
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 22255 | 775.2 | 13377.99 | 8877.01
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 22255 | 103.68 | 13481.67 | 8773.33
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 22255 | 1631.6 | 15113.27 | 7141.73
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 22255 | 58.27 | 15171.54 | 7083.46
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 22255 | 370.2 | 15541.74 | 6713.26
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 22255 | 111.81 | 15653.55 | 6601.45
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 22255 | 1264.6 | 16918.15 | 5336.85
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 22255 | 32.85 | 16951 | 5304
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 22255 | 405.7 | 17356.7 | 4898.3
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 22255 | 18.21 | 17374.91 | 4880.09
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 22255 | 209.4 | 17584.31 | 4670.69
[5 empty] | 22255 |  | 17584.31 | 4670.69
[5 empty] | 22255 |  | 17584.31 | 4670.69
[5 empty] | 22255 |  | 17584.31 | 4670.69
|  |  | Totals: | 22255 |  | 17584.31 |  | 4670.69

## #9445.00 Misc
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 175
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526262900 | 2025-09-19 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2104 | 200 | 200
PRC 33526336902 | 2025-12-02 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2328 | 270.45 | 470.45
470.45
470.45
470.45
470.45
470.45
470.45
470.45
470.45
470.45
470.45
|  |  |  | Totals: |  | 470.45

## #9445.00 KCL Engineering
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944500-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525038902 | 2025-02-07 | PO Procore | 53685 | 53685 |  |  | 53685
PRC 3352503PA8902 | 2025-03-31 | Inv. 11542 |  | 53685 | 14460 | 14460 | 39225
PRC 3352503PB8902 | 2025-07-03 | Inv. 11895 |  | 53685 | 16772.25 | 31232.25 | 22452.75 | FY25
PO 33526038902 | 2025-07-25 | Roll to FY26 | 0 | 53685 |  | 31232.25 | 22452.75
PRC 3352603PC8902 | 2025-09-24 | Inv. 12660 |  | 53685 | 4518.7 | 35750.95 | 17934.05
PRC 3352603PD8902 | 2026-01-05 | Inv. 13319 |  | 53685 | 5383.55 | 41134.5 | 12550.5
PRC 3352603PE8902 | 2026-02-09 | Inv. 13408 |  | 53685 | 1394.5 | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  |  |  | 53685 |  | 42529 | 11156
|  | Totals: | 53685 |  | 42529 |  | 11156
|  | Design Development Docs | 14460 |  | 14460 |  | 0
|  | Construction Docs | 17655 |  | 17655 |  | 0
|  | Bidding/Negotiation | 7625 |  | 7625 |  | 0
|  | Construction Phase | 13945 |  | 2789 |  | 11156
|  | Total: | 53685 |  | 42529 |  | 11156

## #9445.00 Terracon
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM25-9255 |  |  | MA00525049
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525132902 | 2025-05-09 | DO Procore | 3905 | 3905 |  |  | 3905
PRC 3352513PA2902 | 2025-06-30 | Inv. TP04978 | -689.5 | 3215.5 | 3215.5 | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  |  |  | 3215.5 |  | 3215.5 | 0
|  | Totals: | 3215.5 |  | 3215.5 |  | 0 | FINAL
|  | Construction Services Line 4 | 3052.5 |  | 3052.5 |  | 0
|  | Labor 2hrs@130 Line 5 | 130 |  | 130 |  | 0
|  | Travel 120miles@.5 Line 7 | 33 |  | 33 |  | 0
|  | Total: | 3215.5 |  | 3215.5 |  | 0

## #9445.00 Samuels Group (2)
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526339901 | 2025-12-05 | PO Procore | 172002.01 | 172002.01 |  |  | 172002.01
PRC 3352633PA9901 | 2026-01-13 | Inv. 7839.944500.00 CA |  | 172002.01 | 2696.15 | 2696.15 | 169305.86
PRC 3352633PB9901 | 2026-02-10 | Inv. 7839.944500.01 CA |  | 172002.01 | 1404.27 | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  |  |  | 172002.01 |  | 4100.42 | 167901.59
|  | Totals: | 172002.01 |  | 4100.42 |  | 167901.59
|  | CM Services | 100869.96 |  | 4100.42 |  | 96769.54
|  | Reimbursables | 2500 |  |  |  | 2500
|  | 5% Fees | 68632.05 |  |  |  | 68632.05
|  | Total: | 172002.01 |  | 4100.42 |  | 167901.59

## #9445.00 Gerard Electric
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Gerard Electric |  |  | Vendor: 00002110928
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944500-02
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526349900 | 2025-12-15 | PO Procore | 1372641 | 1372641 |  |  | 1372641
PRC 3352634PA9900 | 2026-02-18 | Inv. 25M006-1 |  | 1372641 | 9698.06 | 9698.06 | 1362942.94 | 299.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  |  |  | 1372641 |  | 9698.06 | 1362942.94
|  | Totals: | 1372641 |  | 9698.06 |  | 1362942.94
3% Retainage

## RECAP #9447.00
DAS TH HVAC Repairs
Project # 9447.00
| Program code 944700 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager -James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 44173.65
C | DCI Group |  | 7705.71 | 7705.71 | 0
C | PM TIME |  | 10594.34 | 10594.34 | 0
C | Misc. |  | 0 | 0 | 0
C | OPN Architects |  | 15060 | 15060 | 0
C | DCI Group(2) |  | 2938.6 | 2938.6 | 0
C | OPN Architects(2) |  | 7875 | 7875 | 0
| Total Project Cost | 44173.65 | 44173.65 | 44173.65 | 0 | 0
Closed 02/09/26

## #9447.00 DCI Group
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager -James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525345900 | 2024-12-10 | PO Procore | 7709.12 | 7709.12 |  |  | 7709.12
PRC 3352534PA5900 | 2025-01-14 | Inv. 24-047 PC 01 |  | 7709.12 | 2649.66 | 2649.66 | 5059.46
PRC 3352534PB5900 | 2025-02-18 | Inv. 24-047 PC 02 |  | 7709.12 | 2768.94 | 5418.6 | 2290.52
PRC 3352534PC5900 | 2025-03-14 | Inv. 24-047 PC 03 |  | 7709.12 | 1143.56 | 6562.16 | 1146.96
PRC 3352534PD5900 | 2025-04-15 | Inv. 24-047 PC 04 |  | 7709.12 | 875.05 | 7437.21 | 271.91
PRC 3352534PE5900 | 2025-06-19 | Inv. 24-047 PC 05 FINAL | -3.41 | 7705.71 | 268.5 | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  |  |  | 7705.71 |  | 7705.71 | 8.1712e-14
|  | Totals: | 7705.71 |  | 7705.71 |  | 0 | FINAL

## #9447.00 PM TIME
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731V
Project Manager -James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10594.34 | 10594.34 |  |  | 10594.34
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10594.34 | 90.37 | 90.37 | 10503.97
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10594.34 | 597.7 | 688.07 | 9906.27
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10594.34 | 120.52 | 808.59 | 9785.75
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10594.34 | 1199.2 | 2007.79 | 8586.55
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10594.34 | 106.31 | 2114.1 | 8480.24
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10594.34 | 1135.9 | 3250 | 7344.34
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10594.34 | 253.75 | 3503.75 | 7090.59
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10594.34 | 1099.5 | 4603.25 | 5991.09
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10594.34 | 157.88 | 4761.13 | 5833.21
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10594.34 | 1129.1 | 5890.23 | 4704.11
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10594.34 | 162.68 | 6052.91 | 4541.43
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10594.34 | 1119.3 | 7172.21 | 3422.13
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 10594.34 | 36.03 | 7208.24 | 3386.1
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 10594.34 | 281.5 | 7489.74 | 3104.6
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 10594.34 | 72.71 | 7562.45 | 3031.89
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 10594.34 | 563.7 | 8126.15 | 2468.19
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 10594.34 | 69.05 | 8195.2 | 2399.14
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 10594.34 | 757.5 | 8952.7 | 1641.64
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 10594.34 | 101.08 | 9053.78 | 1540.56
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 10594.34 | 779.6 | 9833.38 | 760.96
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10594.34 | 123.66 | 9957.04 | 637.3
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10594.34 | 637.3 | 10594.34 | -2.2737e-12
[5 empty] | 10594.34 |  | 10594.34 | -2.2737e-12
[5 empty] | 10594.34 |  | 10594.34 | -2.2737e-12
[5 empty] | 10594.34 |  | 10594.34 | -2.2737e-12
[5 empty] | 10594.34 |  | 10594.34 | -2.2737e-12
[5 empty] | 10594.34 |  | 10594.34 | -2.2737e-12
|  |  | Totals: | 10594.34 |  | 10594.34 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time: 9447.00 - DAS TH HVAC Repairs Funding: MM25 PM Time: $15,000

## #9447.00 Misc
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager -James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9447.00 OPN Architects
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager -James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 3352536290 | 2024-12-27 | PO Procore | 12060 | 12060 |  |  | 12060
PRC 335253PA6290 | 2025-03-05 | Inv. 24852000-1 |  | 12060 | 780.89 | 780.89 | 11279.11
PRC 335253PB6290 | 2025-03-14 | Inv. 24852000-2 |  | 12060 | 7178.71 | 7959.6 | 4100.4
PRC 335253PC6290 | 2025-04-22 | Inv. 24852000-3 |  | 12060 | 3497.4 | 11457 | 603
PRC 335253PD6290 | 2025-05-08 | Inv. 24852000-4 |  | 12060 | 361.8 | 11818.8 | 241.2
PO 3352536290 | 2025-07-23 | CO #1 | 3000 | 15060 |  | 11818.8 | 3241.2
PRC 335253PE6290 | 2025-07-23 | Inv. 24852000-5 |  | 15060 | 3241.2 | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  |  |  | 15060 |  | 15060 | 4.5475e-13
|  | Totals: | 15060 |  | 15060 |  | 0 | FINAL

## #9447.00 DCI Group (2)
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
DCI Group(2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager -James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526262906 | 2025-09-19 | PO Procore | 2938.6 | 2938.6 |  |  | 2938.6
PRC 3352626PA2906 | 2025-10-23 | Inv. 24-047 Eval 01 FINAL |  | 2938.6 | 2938.6 | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  |  |  | 2938.6 |  | 2938.6 | 0
|  | Totals: | 2938.6 |  | 2938.6 |  | 0 | Final

## #9447.00 OPN Architects (2)
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
OPN Architects (2) |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager -James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526269905 | 2025-09-26 | PO Procore | 11350 | 11350 |  |  | 11350
PRC 3352626PA9905 | 2025-10-27 | Inv. 24852000-1 FINAL | -3475 | 7875 | 7875 | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  |  |  | 7875 |  | 7875 | 0
|  | Totals: | 7875 |  | 7875 |  | 0 | FINAL

## RECAP #9448.00
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
| Program code 944800 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 700000
C | DCI Group |  | 11937.21 | 11937.21 | 0
| PM TIME |  | 30000 | 22719.21 | 7280.79
| Misc. |  | 2306.5 | 2306.5 | 0
C | OPN Architects |  | 32845 | 32845 | 0
| DCI Group (2) |  | 31227.3 | 26275.14 | 4952.16
| OPN Architects (2) |  | 185777 | 118935 | 66842
| Terracon Consultants |  | 7926.25 | 6701.5 | 1224.75
| Total Project Cost | 700000 | 302019.26 | 221719.56 | 80299.7 | 397980.74

## #9448.00 DCI Group
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525351904 | 2024-12-16 | PO Procore | 10665.48 | 10665.48 |  |  | 10665.48
PRC 3352535PA1904 | 2025-01-21 | Inv. 24-046 PC 01 |  | 10665.48 | 3162.15 | 3162.15 | 7503.33
PRC 3352535PB1904 | 2025-02-25 | Inv. 24-046 PC 02 |  | 10665.48 | 934.34 | 4096.49 | 6568.99
PRC 3352535PC1904 | 2025-03-14 | Inv. 24-046 PC 03 |  | 10665.48 | 1325.52 | 5422.01 | 5243.47
PRC 3352535PD1904 | 2025-04-15 | Inv. 24-046 PC 04 |  | 10665.48 | 2645.58 | 8067.59 | 2597.89
PRC 3352535PE1904 | 2025-05-08 | Inv. 24-046 PC 05 |  | 10665.48 | 1837.65 | 9905.24 | 760.24
PRC 3352535PF1904 | 2025-06-19 | Inv. 24-046 PC 06 | -7.87 | 10657.61 | 752.37 | 10657.61 | -6.7768e-13
PO 33525351904A | 2025-06-20 | Reopening PO Per PM | 7.87 | 10665.48 |  | 10657.61 | 7.87
PO 33525351904A | 2025-06-20 | CO #1 | 1279.6 | 11945.08 |  | 10657.61 | 1287.47
PRC 3352535PG1904A | 2025-07-11 | Inv. 24-046 PC 07 FINAL | -7.87 | 11937.21 | 1279.6 | 11937.21 | -5.6399e-13
|  |  |  | 11937.21 |  | 11937.21 | -5.6399e-13
|  |  |  | 11937.21 |  | 11937.21 | -5.6399e-13
|  |  |  | 11937.21 |  | 11937.21 | -5.6399e-13
|  | Totals: | 11937.21 |  | 11937.21 |  | 0 | FINAL
Note on C16: Huggins, Joni [DAS]: Re: DAS TH Residence Roof, Porch, & South Garden Wall Repairs: Action Required for Subcontractor Invoice #6: DCI Group $Joni Trower, James Thu, Jun 19, 3:36 PM (15 hours ago) to me Finance - Is it possible to open the PO? If not, I will write a new contract and you will need to reject their change order. Thanks, James On Thu, Jun 19, 2025 at 10:09 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Is this supposed to be a FINAL invoice? The remainder is $7.87 ~Joni

## #9448.00 PM TIME
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731W
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 30000 | 30000 |  |  | 30000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 30000 | 90.37 | 90.37 | 29909.63
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 30000 | 597.7 | 688.07 | 29311.93
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 30000 | 124.32 | 812.39 | 29187.61
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 30000 | 1240.7 | 2053.09 | 27946.91
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 30000 | 29.25 | 2082.34 | 27917.66
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 30000 | 313.2 | 2395.54 | 27604.46
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 30000 | 117.96 | 2513.5 | 27486.5
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 30000 | 510.7 | 3024.2 | 26975.8
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 30000 | 89.69 | 3113.89 | 26886.11
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 30000 | 644.5 | 3758.39 | 26241.61
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 30000 | 76.77 | 3835.16 | 26164.84
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 30000 | 526.1 | 4361.26 | 25638.74
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 30000 | 90.2 | 4451.46 | 25548.54
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 30000 | 705.4 | 5156.86 | 24843.14
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 30000 | 100.13 | 5256.99 | 24743.01
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 30000 | 774.7 | 6031.69 | 23968.31
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 30000 | 131.15 | 6162.84 | 23837.16
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 30000 | 1439 | 7601.84 | 22398.16
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 30000 | 207.44 | 7809.28 | 22190.72
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 30000 | 1599.6 | 9408.88 | 20591.12
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 30000 | 372.2 | 9781.08 | 20218.92
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 30000 | 1913.6 | 11694.68 | 18305.32
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 30000 | 191.82 | 11886.5 | 18113.5
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 30000 | 1900 | 13786.5 | 16213.5
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 30000 | 354.17 | 14140.67 | 15859.33
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 30000 | 2256.7 | 16397.37 | 13602.63
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 30000 | 269.74 | 16667.11 | 13332.89
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 30000 | 3064.5 | 19731.61 | 10268.39
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 30000 | 154.16 | 19885.77 | 10114.23
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 30000 | 1919.7 | 21805.47 | 8194.53
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 30000 | 72.84 | 21878.31 | 8121.69
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 30000 | 840.9 | 22719.21 | 7280.79
[5 empty] | 30000 |  | 22719.21 | 7280.79
[5 empty] | 30000 |  | 22719.21 | 7280.79
[5 empty] | 30000 |  | 22719.21 | 7280.79
|  |  | Totals: | 30000 |  | 22719.21 |  | 7280.79
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time: 9448.00 - DAS TH Residence Roof, Porch, & South Garden Wall Repairs MM25 Funding: PM Time: $30,000

## #9448.00 Misc
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526316904 | 2025-11-12 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2681196 | 2306.5 | 2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
2306.5
|  |  |  | Totals: |  | 2306.5

## #9448.00 OPN Architects
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362903 | 2024-12-27 | PO Procore | 23255 | 23255 |  |  | 23255
PRC 3352536PA2903 | 2025-02-25 | Inv. 24853000-1 |  | 23255 | 436.03 | 436.03 | 22818.97
PRC 3352536PB2903 | 2025-03-14 | Inv. 24853000-2 |  | 23255 | 854.62 | 1290.65 | 21964.35
PRC 3352536PC2903 | 2025-04-23 | Inv. 24853000-3 |  | 23255 | 11499.6 | 12790.25 | 10464.75
PRC 3352536PD2903 | 2025-05-08 | Inv. 24853000-4 |  | 23255 | 9999.65 | 22789.9 | 465.1
PO 33525362903 | 2025-06-25 | CO #1 | 9590 | 32845 |  | 22789.9 | 10055.1
PRC 3352536PE2903 | 2025-07-09 | Inv. 24853000-5 |  | 32845 | 9490 | 32279.9 | 565.1 | FY25
PO 33526362903 | 2025-07-25 | Roll to FY26 | 0 | 32845 |  | 32279.9 | 565.1
PRC 3352636PF2903 | 2025-08-19 | Inv. 24853000-6 |  | 32845 | 565.1 | 32845 | 2.16e-12
|  |  |  | 32845 |  | 32845 | 2.16e-12
|  |  |  | 32845 |  | 32845 | 2.16e-12
|  |  |  | 32845 |  | 32845 | 2.16e-12
|  |  |  | 32845 |  | 32845 | 2.16e-12
|  | Totals: | 32845 |  | 32845 |  | 0 | FINAL

## #9448.00 DCI Group (2)
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526217916 | 2025-08-05 | PO Procore | 31227.3 | 31227.3 |  |  | 31227.3
PRC 3352621PA7916 | 2025-09-22 | Inv. 24-046 PC-2 01 |  | 31227.3 | 3046.78 | 3046.78 | 28180.52
PRC 3352621PB7916 | 2025-10-24 | Inv. 24-046 PC-2 02 |  | 31227.3 | 6306.43 | 9353.21 | 21874.09
PRC 3352621PC7916 | 2025-11-21 | Inv. 24-046 PC 003 |  | 31227.3 | 5878.36 | 15231.57 | 15995.73
PRC 3352621PD7916 | 2025-12-29 | Inv. 24-046 PC 004 |  | 31227.3 | 3796.92 | 19028.49 | 12198.81
PRC 3352621PE7916 | 2026-01-26 | Inv. 24-046 PC 005 |  | 31227.3 | 2343.35 | 21371.84 | 9855.46
PRC 3352621PF7916 | 2026-02-20 | Inv. 24-046 PC 006 |  | 31227.3 | 3634.5 | 25006.34 | 6220.96
PRC 3352621PG7916 | 2026-03-24 | Inv. 24-046 PC 007 |  | 31227.3 | 1268.8 | 26275.14 | 4952.16
|  |  |  | 31227.3 |  | 26275.14 | 4952.16
|  |  |  | 31227.3 |  | 26275.14 | 4952.16
|  |  |  | 31227.3 |  | 26275.14 | 4952.16
|  |  |  | 31227.3 |  | 26275.14 | 4952.16
|  |  |  | 31227.3 |  | 26275.14 | 4952.16
|  | Totals: | 31227.3 |  | 26275.14 |  | 4952.16
|  | CM Staff Hours | 26227.3 |  | 23808.28 |  | 2419.02
|  | Reimbursables | 5000 |  | 2466.86 |  | 2533.14
|  | Total: | 31227.3 |  | 26275.14 |  | 4952.16
Invoice format Inv. 24-046 PC 0X has been previously used
Please use Inv. 24-046 PC 00X

## #9448.00 OPN Architects (2)
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526232900 | 2025-08-20 | PO Procore | 183777 | 183777 |  |  | 183777
PO 33526232900 | 2025-09-19 | CO #1 | 2000 | 185777 |  | 0 | 185777
PRC 3352623PA2900 | 2025-10-24 | Inv. 24853003-1 |  | 185777 | 84846.8 | 84846.8 | 100930.2
PRC 3352623PB2900 | 2025-11-07 | Inv. 24853003-2 |  | 185777 | 27901.56 | 112748.36 | 73028.64
PRC 3352623PC2900 | 2026-02-20 | Inv. 24853003-3 |  | 185777 | 6186.64 | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  |  |  | 185777 |  | 118935 | 66842
|  | Totals: | 185777 |  | 118935 |  | 66842
|  | Design Development | 53010 |  | 53010 |  | 0
|  | Construction Development | 63925 |  | 63925 |  | 0
|  | Bidding | 8610 |  |  |  | 8610
|  | Construction Admin Services | 48030 |  |  |  | 48030
|  | Structural Engineering | 9000 |  |  |  | 9000
|  | Reimbursables | 1202 |  |  |  | 1202
|  | CO #1 | 2000 |  | 2000 |  | 0
|  | Total: | 185777 |  | 118935 |  | 66842

## #9448.00 Terracon Consultants
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM25-9255 |  |  | MA25049
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526267900 | 2025-09-24 | PO Procore | 5976.25 | 5976.25 |  |  | 5976.25
DO 33526267900 | 2026-01-07 | CO #1 | 1950 | 7926.25 |  | 0 | 7926.25
PRC 3352626PA7900 | 2026-01-29 | Inv. TP73966 |  | 7926.25 | 4629 | 4629 | 3297.25
PRC 3352626PB7900 | 2026-01-29 | Inv. TP90042 |  | 7926.25 | 1630 | 6259 | 1667.25
PRC 3352626PC7900 | 2026-02-03 | Inv. TQ24289 |  | 7926.25 | 442.5 | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  |  |  | 7926.25 |  | 6701.5 | 1224.75
|  | Totals: | 7926.25 |  | 6701.5 |  | 1224.75

## RECAP #9449.00
DAS TH Carriage House Roof Replacement
Project # 9449.00
| Program code 944900 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 405000
C | DCI Group |  | 17006.09 | 17006.09 | 0
| PM TIME |  | 18000 | 17278.12 | 721.88
| Misc. |  | 12747.59 | 12747.59 | 0
C | OPN Architects |  | 58900 | 58900 | 0
C | DCI Group (2) |  | 68776.33 | 68776.33 | 0
C | Titan Roofing |  | 218195.65 | 218195.65 | 0
| Total Project Cost | 405000 | 393625.66 | 392903.78 | 721.88 | 11374.34

## #9449.00 DCI Group
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525351903 | 2024-12-16 | PO Procore | 22170.45 | 22170.45 |  |  | 22170.45
PRC 3352535PA1903 | 2025-03-10 | Inv. 24-045 PC 01 |  | 22170.45 | 2349.8 | 2349.8 | 19820.65
PRC 3352535PB1903 | 2025-04-09 | Inv. 24-045 PC 02 |  | 22170.45 | 1802.55 | 4152.35 | 18018.1
PRC 3352535PC1903 | 2025-05-09 | Inv. 24-045 PC 03 FINAL | -5164.36 | 17006.09 | 12853.74 | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  | Totals: | 17006.09 |  | 17006.09 |  | 0 | FINAL
|  | CM Services | 14888.59 |  | 14888.59 |  | 0
|  | Reimbursables | 2117.5 |  | 2117.5 |  | 0
|  | Total: | 17006.09 |  | 17006.09 |  | 0

## #9449.00 PM TIME
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731X
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18000 | 18000 |  |  | 18000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 18000 | 96 | 96 | 17904
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 18000 | 636.5 | 732.5 | 17267.5
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 18000 | 120.52 | 853.02 | 17146.98
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 18000 | 1199.2 | 2052.22 | 15947.78
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 18000 | 21.66 | 2073.88 | 15926.12
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 18000 | 234.5 | 2308.38 | 15691.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 18000 | 317.5 | 2625.88 | 15374.12
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 18000 | 1373.7 | 3999.58 | 14000.42
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 18000 | 129.62 | 4129.2 | 13870.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 18000 | 927.2 | 5056.4 | 12943.6
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 18000 | 100.68 | 5157.08 | 12842.92
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 18000 | 692 | 5849.08 | 12150.92
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 18000 | 72.05 | 5921.13 | 12078.87
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 18000 | 564.1 | 6485.23 | 11514.77
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 18000 | 72.71 | 6557.94 | 11442.06
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 18000 | 563.7 | 7121.64 | 10878.36
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 18000 | 162.42 | 7284.06 | 10715.94
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 18000 | 1778.9 | 9062.96 | 8937.04
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 18000 | 202.6 | 9265.56 | 8734.44
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 18000 | 1560.8 | 10826.36 | 7173.64
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 18000 | 248.53 | 11074.89 | 6925.11
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 18000 | 1275.2 | 12350.09 | 5649.91
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 18000 | 124.06 | 12474.15 | 5525.85
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 18000 | 1227.3 | 13701.45 | 4298.55
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 18000 | 142.22 | 13843.67 | 4156.33
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 18000 | 902.8 | 14746.47 | 3253.53
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 18000 | 80.17 | 14826.64 | 3173.36
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 18000 | 906.5 | 15733.14 | 2266.86
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 18000 | 57.12 | 15790.26 | 2209.74
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 18000 | 704.8 | 16495.06 | 1504.94
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 18000 | 62.46 | 16557.52 | 1442.48
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 18000 | 720.6 | 17278.12 | 721.88
[5 empty] | 18000 |  | 17278.12 | 721.88
[5 empty] | 18000 |  | 17278.12 | 721.88
[5 empty] | 18000 |  | 17278.12 | 721.88
|  |  | Totals: | 18000 |  | 17278.12 |  | 721.88
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time 9449.00 - DAS TH Carriage House Roof Replacement MM25 Funding: PM Time: $15,000 Trower, James 9:26 AM (4 minutes ago) to me Finance - James MM25 9449.00 (733.14) Please add $3,000 to PM Time (MM25) Thanks, James

## #9449.00 Misc
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 00525114905 | 2025-04-23 | 9500 |  | Moving Beeline Inv INV047465 from 9411.00 to 9449.00 |  | 340.18 | 340.18
PRC 33526280901 | 2025-10-07 | 9500 | CNST | Terracon Consultants V#(00002116513) | Inv. TP48551 | 6781.25 | 7121.43
PRC 33526280902 | 2025-10-07 | 9500 | BRUM | Controlled Asbestos V#(00002118118) | Inv. 0010979-IN | 5203.66 | 12325.09
PRC 33526302903 | 2025-10-29 | 9500 | CNST | Terracon Consultants V#(00002116513) | Inv. TP74057 | 422.5 | 12747.59
12747.59
12747.59
12747.59
12747.59
12747.59
12747.59
12747.59
12747.59
|  |  |  | Totals: |  | 12747.59

## #9449.00 OPN Architects
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362905 | 2024-12-27 | PO Procore | 54750 | 54750 |  |  | 54750
PRC 3352536PA2905 | 2025-02-20 | Inv. 24854000-1 |  | 54750 | 15705.83 | 15705.83 | 39044.17
PRC 3352536PB2905 | 2025-03-14 | Inv. 24854000-2 |  | 54750 | 10081.92 | 25787.75 | 28962.25
PRC 3352536PC2905 | 2025-04-16 | Inv. 24854000-3 |  | 54750 | 7762.25 | 33550 | 21200
PRC 3352536PD2905 | 2025-05-08 | Inv. 24854000-4 |  | 54750 | 4160 | 37710 | 17040
PRC 3352536PE2905 | 2025-06-10 | Inv. 24854000-5 |  | 54750 | 4160 | 41870 | 12880
PRC 3352536PF2905 | 2025-07-09 | Inv. 24854000-6 |  | 54750 | 4004 | 45874 | 8876 | FY25
PO 33526362905 | 2025-07-25 | Roll to FY26 | 0 | 54750 |  | 45874 | 8876
PRC 3352636PG2905 | 2025-08-07 | Inv. 24854000-7 |  | 54750 | 2860 | 48734 | 6016
PO 33526362905 | 2025-08-20 | CO #1 | 4150 | 58900 |  | 48734 | 10166
PRC 3352636PH2905 | 2025-09-16 | Inv. 24854000-8 |  | 58900 | 8726 | 57460 | 1440
PRC 3352636PI2905 | 2025-10-24 | Inv. 24854000-9 |  | 58900 | 780 | 58240 | 660
PRC 3352636PJ2905 | 2026-01-23 | Inv. 24854000-10FINAL |  | 58900 | 660 | 58900 | 0
|  | Totals: | 58900 |  | 58900 |  | 0 | FINAL
|  | Construction Docs | 29550 |  | 29550 |  | 0
|  | Bidding/Negotiation | 4000 |  | 4000 |  | 0
|  | Construction Phase | 20800 |  | 20800 |  | 0
|  | Reimbursables | 400 |  | 400 |  | 0
|  | CO #1 | 4150 |  | 4150 |  | 0
|  | Total: | 58900 |  | 58900 |  | 0

## #9449.00 DCI Group (2)
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525111900 | 2025-04-21 | PO Procore | 64168.83 | 64168.83 |  |  | 64168.83
PRC 3352511PA1900 | 2025-06-19 | Inv. 24-045 CA 01 |  | 64168.83 | 8613.71 | 8613.71 | 55555.12
PRC 3352511PB1900 | 2025-07-17 | Inv. 24-045 02 |  | 64168.83 | 4917.58 | 13531.29 | 50637.54 | FY25
PO 33526111900 | 2025-07-25 | Roll to FY26 | 0 | 64168.83 |  | 13531.29 | 50637.54
PRC 3352611PC1900 | 2025-08-19 | Inv. 24-045 CA 03 |  | 64168.83 | 25368.7 | 38899.99 | 25268.84
PRC 3352611PD1900 | 2025-09-22 | Inv. 24-045 CA 04 |  | 64168.83 | 18259.26 | 57159.25 | 7009.58
PO 33526111900 | 2025-11-20 | CO #1 | 4607.5 | 68776.33 |  | 57159.25 | 11617.08
PRC 3352611PE1900 | 2026-01-23 | Inv. 24-045 CA 05 Final |  | 68776.33 | 11617.08 | 68776.33 | 1.819e-12
|  |  |  | 68776.33 |  | 68776.33 | 1.819e-12
|  |  |  | 68776.33 |  | 68776.33 | 1.819e-12
|  |  |  | 68776.33 |  | 68776.33 | 1.819e-12
|  |  |  | 68776.33 |  | 68776.33 | 1.819e-12
|  |  |  | 68776.33 |  | 68776.33 | 1.819e-12
|  | Totals: | 68776.33 |  | 68776.33 |  | 0 | FINAL
|  | CM Services | 56668.83 |  | 56668.83 |  | 0
|  | Reimbursables | 7500 |  | 7500 |  | 0
|  | CO #1 | 4607.5 |  | 4607.5 |  | 0
|  | Total: | 68776.33 |  | 68776.33 |  | 0

## #9449.00 Titan Roofing
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
Titan Roofing |  |  | Vendor: 00003108323
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944900-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525112906 | 2025-04-22 | PO Procore | 199866.92 | 199866.92 |  |  | 199866.92
PRC 3352511PA2906 | 2025-07-15 | Inv. TH01 |  | 199866.92 | 3325 | 3325 | 196541.92 | 175 | FY25
PO 33526112906 | 2025-07-25 | Roll to FY26 | 0 | 199866.92 |  | 3325 | 196541.92
PO 33526112906 | 2025-08-19 | CO #1 | 18328.73 | 218195.65 |  | 3325 | 214870.65
PRC 3352611PB2906 | 2025-08-21 | Inv. TH02 |  | 218195.65 | 157462.06 | 160787.06 | 57408.59 | 8462.49
PRC 3352611PC2906 | 2025-10-22 | Inv. TH03 |  | 218195.65 | 44600.05 | 205387.11 | 12808.54 | 10809.88
PRC 3352611PD2906 | 2025-12-10 | Inv. TH04 |  | 218195.65 | 1898.73 | 207285.84 | 10909.81 | 10909.81
PRC 3352611PE2906 | 2025-12-17 | Inv. TH05 - RETAINAGE |  | 218195.65 | 10909.81 | 218195.65 | 2.3647e-11
|  |  |  | 218195.65 |  | 218195.65 | 2.3647e-11
|  |  |  | 218195.65 |  | 218195.65 | 2.3647e-11
|  |  |  | 218195.65 |  | 218195.65 | 2.3647e-11
|  |  |  | 218195.65 |  | 218195.65 | 2.3647e-11
|  |  |  | 218195.65 |  | 218195.65 | 2.3647e-11
|  | Totals: | 218195.65 |  | 218195.65 |  | 0 | FINAL

## RECAP #9451.00
DOC ASP LUA A/C Replacement
Project # 9451.00
| Program code 945100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 709000
C | McGough Construction |  | 16761.78 | 16761.78 | 0
| PM TIME |  | 24000 | 22130.91 | 1869.09
| Misc. |  | 12360.81 | 12360.81 | 0
| IMEG Corporation |  | 34348 | 30934 | 3414
| System Works |  | 11760 | 9520 | 2240
C | Mechanical Sales |  | 140500 | 140500 | 0
| Foreman Construction |  | 388546.5 | 384546.5 | 4000
| McGough Construction (2) |  | 76012.6 | 68998.57 | 7014.03
| Total Project Cost | 709000 | 704289.69 | 685752.57 | 18537.12 | 4710.31

## #9451.00 McGough Construction
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525267902 | 2024-09-23 | PO Procore | 18799.75 | 18799.75 |  |  | 18799.75
PRC 3352526PA7902 | 2024-10-14 | Inv. 101174.016-PC01 |  | 18799.75 | 1519.54 | 1519.54 | 17280.21
PRC 3352526PB7902 | 2024-11-12 | Inv. 101174.016-PC02 |  | 18799.75 | 2286.17 | 3805.71 | 14994.04
PRC 3352526PC7902 | 2024-12-16 | Inv. 101174.016-PC03 |  | 18799.75 | 3045.93 | 6851.64 | 11948.11
PRC 3352526PD7902 | 2025-01-17 | Inv. 101174-016-PC04 |  | 18799.75 | 1795.81 | 8647.45 | 10152.3
PRC 3352526PE7902 | 2025-02-12 | Inv. 101174-016-PC05 |  | 18799.75 | 716.59 | 9364.04 | 9435.71
PRC 3352526PF7902 | 2025-03-19 | Inv. 101174.016-PC06 |  | 18799.75 | 1015.11 | 10379.15 | 8420.6
PRC 3352526PG7902 | 2025-04-03 | Inv. 101174.016-PC07 |  | 18799.75 | 90 | 10469.15 | 8330.6
PRC 3352526PH7902 | 2025-04-15 | Inv. 101174.016-PC08 |  | 18799.75 | 3535.03 | 14004.18 | 4795.57
PRC 3352526PI7902 | 2025-05-07 | Inv. 101174.016-PC09 - FINAL | -2037.97 | 16761.78 | 2757.6 | 16761.78 | -2.0464e-12
|  |  |  | 16761.78 |  | 16761.78 | -2.0464e-12
|  |  |  | 16761.78 |  | 16761.78 | -2.0464e-12
|  |  |  | 16761.78 |  | 16761.78 | -2.0464e-12
|  | Totals: | 16761.78 |  | 16761.78 |  | 0 | FINAL
|  | CM Services | 16424.78 |  | 16424.78 |  | 0
|  | Reimbursables | 337 |  | 337 |  | 0
|  | Total: | 16761.78 |  | 16761.78 |  | 0

## #9451.00 PM Time
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909Y
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 24000 | 24000 |  |  | 24000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 24000 | 102.27 | 102.27 | 23897.73
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 24000 | 905.5 | 1007.77 | 22992.23
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 24000 | 290.6 | 1298.37 | 22701.63
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 24000 | 1938.3 | 3236.67 | 20763.33
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 24000 | 234.15 | 3470.82 | 20529.18
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 24000 | 1554.9 | 5025.72 | 18974.28
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 24000 | 114.05 | 5139.77 | 18860.23
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 24000 | 1144.9 | 6284.67 | 17715.33
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 24000 | 118.82 | 6403.49 | 17596.51
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 24000 | 1261.1 | 7664.59 | 16335.41
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 24000 | 186.76 | 7851.35 | 16148.65
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 24000 | 808.4 | 8659.75 | 15340.25
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 24000 | 200.9 | 8860.65 | 15139.35
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 24000 | 1439.1 | 10299.75 | 13700.25
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 24000 | 339.97 | 10639.72 | 13360.28
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 24000 | 2374.5 | 13014.22 | 10985.78
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 24000 | 171.95 | 13186.17 | 10813.83
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 24000 | 1348.6 | 14534.77 | 9465.23
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 24000 | 5.34 | 14540.11 | 9459.89
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 24000 | 44.7 | 14584.81 | 9415.19
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 24000 | 9.37 | 14594.18 | 9405.82
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 24000 | 104.4 | 14698.58 | 9301.42
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 24000 | 73.89 | 14772.47 | 9227.53
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 24000 | 565.3 | 15337.77 | 8662.23
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 24000 | 120.47 | 15458.24 | 8541.76
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 24000 | 618.2 | 16076.44 | 7923.56
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 24000 | 115.91 | 16192.35 | 7807.65
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 24000 | 1149.1 | 17341.45 | 6658.55
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 24000 | 59.49 | 17400.94 | 6599.06
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 24000 | 378.4 | 17779.34 | 6220.66
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 24000 | 107.3 | 17886.64 | 6113.36
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 24000 | 1217.6 | 19104.24 | 4895.76
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 24000 | 110.16 | 19214.4 | 4785.6
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 24000 | 1368 | 20582.4 | 3417.6
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 24000 | 123.71 | 20706.11 | 3293.89
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 24000 | 1424.8 | 22130.91 | 1869.09
[5 empty] | 24000 |  | 22130.91 | 1869.09
[5 empty] | 24000 |  | 22130.91 | 1869.09
[5 empty] | 24000 |  | 22130.91 | 1869.09
|  |  | Totals: | 24000 |  | 22130.91 |  | 1869.09
Note on E9: Huggins, Joni [DAS]: Re: PM Time for February has posted $Joni Adams, Brandon 10:50 AM (22 minutes ago) to me Finance, Please increase my PM as follows: DA24 9423.00 $9,500 MM22 9387.00 $1,200 MM23 9370.00 $3,000 MM25 9451.00 $5,000 Regards, Brandon Adams Re: April PM Time $Joni Shimp, Oliver 3:10 PM (0 minutes ago) to me Sorry! 1) Add $10,000 to the PM time budget from the uncontracted budget for project MM25 9422.00. 2) Add $7,000 to the PM time budget from the uncontracted budget for project MM25 9451.00 3) Can you please assign $10,000 of the $50,000 to PM time for project 5800 9473.00 That's what I meant. Thank you, Oliver Shimp Re: February PM Time Posted $Joni Shimp, Oliver Mar 13, 2026, 8:26 AM (3 days ago) to me Good Morning, Thank for you the list, could you please make the following adjustments? DA25 9358.01 $(361.98) Please move $5,000.00 from unallocated to PM Time DA26 9534.00 $(298.97) Please move $5,000.00 from unallocated to PM Time MM24 9226.00 $(290.03) Please move $5,000.00 from unallocated to PM Time. MM24 9392.00 $(264.99) Please move $3,000 from unallocated to PM Time MM25 9451.00 $(130.91) Please move $2,000.00 from unallocated to PM Time

## #9451.00 Misc
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 163
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525105905 | 2025-04-15 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1635 | 305.81 | 305.81
PRC 33525148910 | 2025-05-28 | 9500 | CNST | Terracon Consultants V#(00002116513) | Inv. TN68035 | 2875 | 3180.81
GAX 33526318901 | 2025-11-14 | 9500 | CNST | Iowa-Illinois Taylor Insulation V#(00002108903) | Inv. 25022271 | 9180 | 12360.81
12360.81
12360.81
12360.81
12360.81
12360.81
12360.81
12360.81
12360.81
12360.81
|  |  |  | Totals: |  | 12360.81

## #9451.00 IMEG Corporation
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
IMEG Corporation |  |  | Vendor: 00003224175
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945100-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320904 | 2024-11-15 | PO Procore | 34348 | 34348 |  |  | 34348
PRC 3352532PA0904 | 2024-12-19 | Inv. 24006748.00-1 |  | 34348 | 10656 | 10656 | 23692
PRC 3352532PB0904 | 2025-01-17 | Inv. 24006748.00-2 |  | 34348 | 9590.4 | 20246.4 | 14101.6
PRC 3352532PC0904 | 2025-03-05 | Inv. 24006748.00-3 |  | 34348 | 1065.6 | 21312 | 13036
PRC 3352532PD0904 | 2025-03-26 | Inv. 24006748.00-4 |  | 34348 | 828 | 22140 | 12208
PRC 3352532PE0904 | 2025-04-22 | Inv. 24006748.00-5 |  | 34348 | 828 | 22968 | 11380
PRC 3352532PF0904 | 2025-05-30 | Inv. 24006748.00-6 |  | 34348 | 800 | 23768 | 10580
PRC 3352532PG0904 | 2025-06-24 | Inv. 24006748.00-7 |  | 34348 | 565.6 | 24333.6 | 10014.4 | FY25
PO 33526320904 | 2025-07-30 | Roll to FY26 | 0 | 34348 |  | 24333.6 | 10014.4
PRC 3352632PH0904 | 2025-07-31 | Inv. 24006748.00-8 |  | 34348 | 682.8 | 25016.4 | 9331.6
PRC 3352632PI0904 | 2025-08-27 | Inv. 24006748.00-9 |  | 34348 | 796.6 | 25813 | 8535
PRC 3352632PJ0904 | 2025-12-03 | Inv. 24006748.00-10 |  | 34348 | 1138 | 26951 | 7397
PRC 3352632PK0904 | 2025-12-29 | Inv. 24006748.00-11 |  | 34348 | 2276 | 29227 | 5121
PRC 3352632PL0904 | 2026-01-12 | Inv. 24006748.00-12 |  | 34348 | 1707 | 30934 | 3414
|  |  |  | 34348 |  | 30934 | 3414
|  |  |  | 34348 |  | 30934 | 3414
|  | Totals: | 34348 |  | 30934 |  | 3414
|  | Construction Documents | 21312 |  | 21312 |  | 0
|  | Bidding/Negtiation | 1656 |  | 1656 |  | 0
|  | Construction Phase | 11380 |  | 7966 |  | 3414
|  | Total: | 34348 |  | 30934 |  | 3414

## #9451.00 System Works
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
System Works |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM25-9255 |  |  | SRVV5
Project Manager - Oliver S. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525041909 | 2025-02-10 | PO Procore | 11760 | 11760 |  |  | 11760
PRC 3352504PA1909 | 2025-05-30 | Inv. 12358 |  | 11760 | 2100 | 2100 | 9660 | FY25
PO 33526041909 | 2025-07-30 | Roll to FY26 | 0 | 11760 |  | 2100 | 9660
PRC 3352604PB1909 | 2026-01-16 | Inv. 12690 |  | 11760 | 4340 | 6440 | 5320
PRC 3352604PC1909 | 2026-03-24 | Inv. 12811 |  | 11760 | 3080 | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  |  |  | 11760 |  | 9520 | 2240
|  | Totals: | 11760 |  | 9520 |  | 2240
|  | Design Phase | 1400 |  | 1400 |  | 0
|  | Construction Phase | 8120 |  | 8120 |  | 0
|  | Closeout Phase | 2240 |  |  |  | 2240
|  | Total: | 11760 |  | 9520 |  | 2240

## #9451.00 Mechanical Sales
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
Mechanical Sales |  |  | Vendor: 00003004950
Acct. Codes-0017-335-MM25-9255 |  |  | MA 21194B
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525083908 | 2025-03-21 | PO Procore | 140500 | 140500 |  |  | 140500 | FY25
PO 33526083908 | 2025-07-30 | Roll to FY26 | 0 | 140500 |  | 0 | 140500
PRC 3352608PA3908 | 2025-08-26 | Inv. 34792 |  | 140500 | 25000 | 25000 | 115500
PO 33526083908A | 2025-09-16 | Updating VC | 0 | 140500 |  | 25000 | 115500
PRC 3352608PB3908A | 2025-09-16 | Inv. 34922 |  | 140500 | 31000 | 56000 | 84500
PRC 3352608PC3908A | 2025-10-13 | Inv. 35245 |  | 140500 | 12500 | 68500 | 72000
PRC 3352608PD3908A | 2025-12-03 | Inv. 34997 |  | 140500 | 72000 | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  |  |  | 140500 |  | 140500 | 0
|  | Totals: | 140500 |  | 140500 |  | 0 | FINAL

## #9451.00 Foreman Construction
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
Foreman Construction |  |  | Vendor: 00003226071
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945100-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525109905 | 2025-04-18 | PO Procore | 387500 | 387500 |  |  | 387500
PRC 3352510PA9905 | 2025-05-08 | Inv. Pay App #1 |  | 387500 | 19000 | 19000 | 368500 | 1000
PRC 3352510PB9905 | 2025-07-21 | Inv. Pay App #2 |  | 387500 | 14250 | 33250 | 354250 | 1750 | FY25
PO 33526109905 | 2025-07-30 | Roll to FY26 | 0 | 387500 |  | 33250 | 354250
PRC 3352610PA9905 | 2025-08-26 | Inv. Pay App #3 |  | 387500 | 11305 | 44555 | 342945 | 2345
PRC 3352610PD9905 | 2025-09-15 | Inv. Pay App #4 |  | 387500 | 25840 | 70395 | 317105 | 3705
PRC 3352610PE9905 | 2025-10-06 | Inv. Pay App #5 |  | 387500 | 46930 | 117325 | 270175 | 6175
PO 33526109905 | 2025-11-04 | CO #1 | 1046.5 | 388546.5 |  | 117325 | 271221.5
PRC 3352610PF9905 | 2025-11-10 | Inv. Pay App #6 |  | 388546.5 | 106305 | 223630 | 164916.5 | 11770
PO 33526109905 | 2025-12-08 | CO #2(No cost CO) | 0 | 388546.5 |  | 223630 | 164916.5
PRC 3352610PG9905 | 2026-01-14 | Inv. App #7 |  | 388546.5 | 130289.17 | 353919.17 | 34627.33 | 18627.33
PRC 3352610PH9905 | 2026-02-05 | Inv. App#8 |  | 388546.5 | 11400 | 365319.17 | 23227.33 | 19227.33
PRC 3352610PI9905 | 2026-03-11 | Inv. App#9 - Retainage |  | 388546.5 | 19227.33 | 384546.5 | 4000 | 0
|  | Totals: | 388546.5 |  | 384546.5 |  | 4000

## #9451.00 McGough Constructi (2)
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525114908 | 2025-04-23 | PO Procore | 57327.76 | 57327.76 |  |  | 57327.76
PRC 3352511PA4908 | 2025-06-16 | Inv. 101174.016CA-01 |  | 57327.76 | 2791.74 | 2791.74 | 54536.02
PRC 3352511PB4908 | 2025-07-10 | Inv. 101174.016CA-02 |  | 57327.76 | 4897.9 | 7689.64 | 49638.12 | FY25
PO 33526114908 | 2025-07-30 | Roll to FY26 | 0 | 57327.76 |  | 7689.64 | 49638.12
PRC 3352611PC4908 | 2025-08-13 | Inv. 101174.016-CA03 |  | 57327.76 | 3765.77 | 11455.41 | 45872.35
PRC 3352611PD4908 | 2025-09-16 | Inv. 101174.016CA-03 |  | 57327.76 | 10487.28 | 21942.69 | 35385.07
PRC 3352611PE4908 | 2025-10-17 | Inv. 101174.016CA-04 |  | 57327.76 | 10075.56 | 32018.25 | 25309.51
PRC 3352611PF4908 | 2025-11-10 | Inv. 101174.016-CA06 |  | 57327.76 | 9156.76 | 41175.01 | 16152.75
PO 33526114908 | 2025-12-29 | CO #1 | 18684.84 | 76012.6 |  | 41175.01 | 34837.59
PRC 3352611PG4908 | 2026-01-12 | Inv. 101174.016-CA07 |  | 76012.6 | 18478.69 | 59653.7 | 16358.9
PRC 3352611PH4908 | 2026-01-15 | Inv. 101174.016CA-08 |  | 76012.6 | 3971.53 | 63625.23 | 12387.37
PRC 3352611PI4908 | 2026-02-13 | Inv. 101174.016-CA09 |  | 76012.6 | 2792.41 | 66417.64 | 9594.96
PRC 3352611PJ4908 | 2026-03-10 | Inv. 101174.016-CA11 |  | 76012.6 | 2580.93 | 68998.57 | 7014.03
|  |  |  | 76012.6 |  | 68998.57 | 7014.03
|  |  |  | 76012.6 |  | 68998.57 | 7014.03
|  |  |  | 76012.6 |  | 68998.57 | 7014.03
|  | Totals: | 76012.6 |  | 68998.57 |  | 7014.03
|  | CM Services | 28447.76 |  | 28447.76 |  | 0
|  | Reimbursables | 2480 |  | 303 |  | 2177
|  | Fee | 26400 |  | 25080 |  | 1320
|  | CO #1 | 18684.84 |  | 15167.81 |  | 3517.03
|  | Total: | 76012.6 |  | 68998.57 |  | 7014.03

## RECAP #9452.00
HHS CHMHI Generator Controller Replacement
Project # 9452.00
| Program code 945200 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 371000
| Innovative Engineers |  | 24875 | 18660 | 6215
| PM TIME |  | 12000 | 5618.33 | 6381.67
| Misc. |  | 976.25 | 976.25 | 0
C | DCI Group |  | 11748.34 | 11748.34 | 0
| Cummins |  | 248280.63 | 0 | 248280.63
| DCI Group |  | 39901.41 | 1657.47 | 38243.94
| Total Project Cost | 371000 | 337781.63 | 38660.39 | 299121.24 | 33218.37

## #9452.00 Innovative Engineers
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
Innovative Engineers |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945200-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362906 | 2024-12-27 | PO Procore | 24875 | 24875 |  |  | 24875
PRC 3352536PA2906 | 2025-05-05 | Inv. 9452.00-01 |  | 24875 | 14875 | 14875 | 10000
PRC 3352536PB2906 | 2025-07-07 | Inv. 9452.00-02 |  | 24875 | 3785 | 18660 | 6215 | FY25
PO 33526362906 | 2025-07-25 | Roll to FY26 | 0 | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  |  |  | 24875 |  | 18660 | 6215
|  | Totals: | 24875 |  | 18660 |  | 6215
|  | Design Development Docs | 6825 |  | 6825 |  | 0
|  | Construction Docs | 8050 |  | 8050 |  | 0
|  | Bidding/Negotiation | 3785 |  | 3785 |  | 0
|  | Construction Phase | 4670 |  |  |  | 4670
|  | Close Out | 1545 |  |  |  | 1545
|  | Total: | 24875 |  | 18660 |  | 6215

## #9452.00 PM TIME
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909Z
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12000 | 12000 |  |  | 12000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12000 | 86.56 | 86.56 | 11913.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12000 | 575.4 | 661.96 | 11338.04
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12000 | 112.43 | 774.39 | 11225.61
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12000 | 747.4 | 1521.79 | 10478.21
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12000 | 29.68 | 1551.47 | 10448.53
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12000 | 299.8 | 1851.27 | 10148.73
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12000 | 33.05 | 1884.32 | 10115.68
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12000 | 354.2 | 2238.52 | 9761.48
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12000 | 73.16 | 2311.68 | 9688.32
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12000 | 317.9 | 2629.58 | 9370.42
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 12000 | 75.78 | 2705.36 | 9294.64
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 12000 | 543 | 3248.36 | 8751.64
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 12000 | 75.64 | 3324 | 8676
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 12000 | 517.9 | 3841.9 | 8158.1
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 12000 | 13.93 | 3855.83 | 8144.17
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 12000 | 110.2 | 3966.03 | 8033.97
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 12000 | 36.56 | 4002.59 | 7997.41
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 12000 | 282.4 | 4284.99 | 7715.01
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 12000 | 14.21 | 4299.2 | 7700.8
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 12000 | 154.1 | 4453.3 | 7546.7
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 12000 | 5.29 | 4458.59 | 7541.41
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 12000 | 44.3 | 4502.89 | 7497.11
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 12000 | 33.2 | 4536.09 | 7463.91
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 12000 | 169.6 | 4705.69 | 7294.31
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 12000 | 8.15 | 4713.84 | 7286.16
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 12000 | 80.4 | 4794.24 | 7205.76
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 12000 | 7.84 | 4802.08 | 7197.92
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 12000 | 92.4 | 4894.48 | 7105.52
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 12000 | 42.35 | 4936.83 | 7063.17
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 12000 | 524.9 | 5461.73 | 6538.27
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 12000 | 12.8 | 5474.53 | 6525.47
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 12000 | 143.8 | 5618.33 | 6381.67
[5 empty] | 12000 |  | 5618.33 | 6381.67
[5 empty] | 12000 |  | 5618.33 | 6381.67
[5 empty] | 12000 |  | 5618.33 | 6381.67
|  |  | Totals: | 12000 |  | 5618.33 |  | 6381.67
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (2 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9452.00 Misc
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 548
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525090903 | 2025-03-31 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2635179 | 976.25 | 976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
|  |  |  | Totals: |  | 976.25

## #9452.00 DCI Group
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525058903 | 2025-02-27 | PO Procore | 12823.33 | 12823.33 |  |  | 12823.33
PRC 3352505PA8903 | 2025-03-17 | Inv. 25-003 PC 01 |  | 12823.33 | 786.49 | 786.49 | 12036.84
PRC 3352505PB8903 | 2025-04-14 | Inv. 25-003 PC 02 |  | 12823.33 | 6027.91 | 6814.4 | 6008.93
PRC 3352505PC8903 | 2025-05-09 | Inv. 25-003 PC 03 |  | 12823.33 | 3208.22 | 10022.62 | 2800.71
PRC 3352505PD8903 | 2025-06-10 | Inv. 25-003 PC 04 FINAL | -1074.99 | 11748.34 | 1725.72 | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  |  |  | 11748.34 |  | 11748.34 | 0
|  | Totals: | 11748.34 |  | 11748.34 |  | 0 | FINAL

## #9452.00 Cummins
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
Cummins |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM25-9255 |  |  | RFQ945200-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525134904 | 2025-05-13 | PO Procore | 248280.63 | 248280.63 |  |  | 248280.63 | FY25
PO 33526134904 | 2025-07-25 | Roll to FY26 | 0 | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  | Totals: | 248280.63 |  | 0 |  | 248280.63

## #9452.00 DCI Group (2)
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255903 | 2025-09-12 | PO Procore | 39901.41 | 39901.41 |  |  | 39901.41
PRC 3352625PA5903 | 2025-10-10 | Inv. 25-003 CA 01 |  | 39901.41 | 1308.53 | 1308.53 | 38592.88
PRC 3352625PB5903 | 2025-12-22 | Inv. 25-003 CA 02 |  | 39901.41 | 174.47 | 1483 | 38418.41
PRC 3352625PC5903 | 2026-03-24 | Inv. 25-003 CA 03 |  | 39901.41 | 174.47 | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  |  |  | 39901.41 |  | 1657.47 | 38243.94
|  | Totals: | 39901.41 |  | 1657.47 |  | 38243.94
|  | CM Services | 34901.41 |  | 1657.47 |  | 33243.94
|  | Reimbursable | 5000 |  |  |  | 5000
|  | Total: | 39901.41 |  | 1657.47 |  | 38243.94

## RECAP #9453.00
DOC FDCF IPI Roof Replacement
Project # 9453.00
| Program code 945300 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 286904.3
C | McGough Construction |  | 8893.05 | 8893.05 | 0
C | PM TIME |  | 9964.17 | 9964.17 | 0
C | Misc. |  | 756.64 | 756.64 | 0
C | Genesis Architectural |  | 15300 | 15300 | 0
C | Academy Roofing & Sheet Metal |  | 227300 | 227300 | 0
C | McGough Construction (2) |  | 24690.44 | 24690.44 | 0
| Total Project Cost | 286904.3 | 286904.3 | 286904.3 | 0 | 0
Closed 01/22/26

## #9453.00 McGough Construction
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525276905 | 2024-10-02 | PO Procore | 14911.74 | 14911.74 |  |  | 14911.74
PRC 3352527PA6905 | 2024-11-19 | Inv. 101174.019PC-01 |  | 14911.74 | 1826.29 | 1826.29 | 13085.45
PRC 3352527PB6905 | 2024-12-18 | Inv. 101174.019PC-02 |  | 14911.74 | 930.4 | 2756.69 | 12155.05
PRC 3352527PC6905 | 2025-01-22 | Inv. 101174-019PC-03 |  | 14911.74 | 688.66 | 3445.35 | 11466.39
PRC 3352527PD6905 | 2025-02-12 | Inv. 101174-019PC-04 |  | 14911.74 | 941.07 | 4386.42 | 10525.32
PRC 3352527PE6905 | 2025-03-24 | Inv. 101174.019PC-05 |  | 14911.74 | 2753.99 | 7140.41 | 7771.33
PRC 3352527PF6905 | 2025-04-25 | Inv. 101174.019PC-06 |  | 14911.74 | 820.2 | 7960.61 | 6951.13
PRC 3352527PG6905 | 2025-05-09 | Inv. 101174.019PC-07 FINAL | -6018.69 | 8893.05 | 932.44 | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  | Totals: | 8893.05 |  | 8893.05 |  | 0 | FINAL
|  | CM Services | 8716.55 |  | 8716.55 |  | 0
|  | Reimbursables | 176.5 |  | 176.5 |  | 0
|  | Total: | 8893.05 |  | 8893.05 |  | 0

## #9453.00 PM TIME
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910A
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 9964.17 | 9964.17 |  |  | 9964.17
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 9964.17 | 68.6 | 68.6 | 9895.57
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 9964.17 | 609.3 | 677.9 | 9286.27
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 9964.17 | 137.85 | 815.75 | 9148.42
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 9964.17 | 921.9 | 1737.65 | 8226.52
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 9964.17 | 113.13 | 1850.78 | 8113.39
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 9964.17 | 748.5 | 2599.28 | 7364.89
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 9964.17 | 109.13 | 2708.41 | 7255.76
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 9964.17 | 1091.1 | 3799.51 | 6164.66
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 9964.17 | 78.18 | 3877.69 | 6086.48
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 9964.17 | 834.7 | 4712.39 | 5251.78
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 9964.17 | 247.57 | 4959.96 | 5004.21
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 9964.17 | 1072.2 | 6032.16 | 3932.01
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 9964.17 | 43.72 | 6075.88 | 3888.29
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 9964.17 | 310.5 | 6386.38 | 3577.79
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 9964.17 | 105.59 | 6491.97 | 3472.2
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 9964.17 | 725.3 | 7217.27 | 2746.9
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 9964.17 | 23.22 | 7240.49 | 2723.68
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 9964.17 | 183.3 | 7423.79 | 2540.38
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 9964.17 | 45.7 | 7469.49 | 2494.68
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 9964.17 | 352.2 | 7821.69 | 2142.48
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 9964.17 | 20.7 | 7842.39 | 2121.78
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 9964.17 | 231.7 | 8074.09 | 1890.08
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 9964.17 | 119.36 | 8193.45 | 1770.72
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 9964.17 | 920.1 | 9113.55 | 850.62
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 9964.17 | 35.92 | 9149.47 | 814.7
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 9964.17 | 358.8 | 9508.27 | 455.9
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 9964.17 | 6.95 | 9515.22 | 448.95
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 9964.17 | 44.3 | 9559.52 | 404.65
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 9964.17 | 32.85 | 9592.37 | 371.8
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 9964.17 | 371.8 | 9964.17 | 1.1369e-12
[5 empty] | 9964.17 |  | 9964.17 | 1.1369e-12
|  |  | Totals: | 9964.17 |  | 9964.17 |  | 0
Note on E9: Huggins, Joni [DAS]: New DAS Costs Budget for MM25 9453.00 $Joni Kleene, Jennifer 10:40 AM (23 minutes ago) to me Please create a new DAS Costs budget for $6,300.00 for MM25 Project 9453.00. Regards, Jennifer Re: March PM Time Posted $Joni Elliott, Jennie 1:13 PM (2 minutes ago) to me, Jennifer Please increase the PM Time in the Contracted line to a total of $13,000.00 Thank you, Jennie Elliott

## #9453.00 Misc
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525029903 | 2025-01-29 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2623363 | 547.5 | 547.5
PRC 33525090905 | 2025-03-31 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1573 | 209.14 | 756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
|  |  |  | Totals: |  | 756.64

## #9453.00 GenesisArchitectural
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
Genesis Architecural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP954300-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327904 | 2024-11-22 | PO Procore | 15300 | 15300 |  |  | 15300
PRC 3352532PA7904 | 2025-02-26 | Inv. 2412.01-01 |  | 15300 | 8100 | 8100 | 7200
PRC 3352532PB7904 | 2025-05-05 | Inv. 2412.01-02 |  | 15300 | 800 | 8900 | 6400
PRC 3352532PC7904 | 2025-06-16 | Inv. 2412.01-03 |  | 15300 | 640 | 9540 | 5760 | FY25
PO 33526327904 | 2025-07-29 | Roll to FY26 | 0 | 15300 |  | 9540 | 5760
PRC 3352632PD7904 | 2025-12-04 | Inv. 2412.01-04 FINAL |  | 15300 | 5760 | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  |  |  | 15300 |  | 15300 | 0
|  | Totals: | 15300 |  | 15300 |  | 0 | FINAL
|  | Construction Docs | 8100 |  | 8100 |  | 0
|  | Bidding Phase | 800 |  | 800 |  | 0
|  | Construction Phase | 6400 |  | 6400 |  | 0
|  | Total: | 15300 |  | 15300 |  | 0

## #9453.00 Academy Roofing
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
Academy Roofing & Sheet Metal |  |  | Vendor: 00003010234
Acct. Codes-0017-335-MM25-9255 |  |  | RFB954300-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525086901 | 2025-03-27 | PO Procore | 227300 | 227300 |  |  | 227300 |  | FY25
PO 33526086901 | 2025-07-29 | Roll to FY26 | 0 | 227300 |  | 0 | 227300
PRC 3352608PA6901 | 2025-09-15 | Inv. 9453.00-01 |  | 227300 | 213560 | 213560 | 13740 | 11240
PRC 3352608PB6901 | 2025-10-27 | Inv. 9453.00-02 |  | 227300 | 2375 | 215935 | 11365 | 11365
PRC 3352608PC6901 | 2025-11-12 | Inv. 9453.00-Retainage |  | 227300 | 11365 | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  |  |  | 227300 |  | 227300 | 0
|  | Totals: | 227300 |  | 227300 |  | 0 | FINAL

## #9453.00 McGough Constructi (2)
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525098902 | 2025-04-08 | PO Procore | 33443.04 | 33443.04 |  |  | 33443.04
PRC 3352509PA8902 | 2025-06-16 | Inv. 101174.019CA-01 |  | 33443.04 | 2455.58 | 2455.58 | 30987.46
PRC 3352509PB8902 | 2025-07-15 | Inv. 101174.019CA-02 |  | 33443.04 | 1852.66 | 4308.24 | 29134.8 | FY25
PO 33526098902 | 2025-07-29 | Roll to FY26 | 0 | 33443.04 |  | 4308.24 | 29134.8
PRC 3352609PC8902 | 2025-08-14 | Inv. 101174.019CA-03 |  | 33443.04 | 7573.36 | 11881.6 | 21561.44
PRC 3352609PD8902 | 2025-09-22 | Inv. 101174.019CA-04 |  | 33443.04 | 11048.82 | 22930.42 | 10512.62
PRC 3352609PE8902 | 2025-10-15 | Inv. 101174.019CA-05 |  | 33443.04 | 762.1 | 23692.52 | 9750.52
PRC 3352609PF8902 | 2025-12-04 | Inv. 101174.019CA-06 - FINAL | -8752.6 | 24690.44 | 997.92 | 24690.44 | 0
|  |  |  | 24690.44 |  | 24690.44 | 0
|  |  |  | 24690.44 |  | 24690.44 | 0
|  |  |  | 24690.44 |  | 24690.44 | 0
|  |  |  | 24690.44 |  | 24690.44 | 0
|  |  |  | 24690.44 |  | 24690.44 | 0
|  | Totals: | 24690.44 |  | 24690.44 |  | 0 | FINAL
|  | CM Services | 23519.94 |  | 23519.94 |  | 0
|  | Reimbursables | 1170.5 |  | 1170.5 |  | 0
|  | Total: | 24690.44 |  | 24690.44 |  | 0

## RECAP #9454.00
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
| Program code 9454.00 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 210546.34
C | Samuels Group |  | 17817.7 | 17817.7 | 0
C | PM TIME |  | 16514.24 | 16514.24 | 0
C | Misc. |  | 2087.9 | 2087.9 | 0
C | Horizon Architecture |  | 17650 | 17650 | 0
C | Brockway Mechanical |  | 132778 | 132778 | 0
C | Samuels Group (2) |  | 23698.5 | 23698.5 | 0
| Total Project Cost | 210546.34 | 210546.34 | 210546.34 | 0 | 0
Closed 07/15/25

## #9454.00 Samuels Group
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525256902 | 2024-09-12 | PO Procore | 17987.44 | 17987.44 |  |  | 17987.44
PRC 3352525PA6902 | 2024-10-07 | Inv. 7718.019454 PC |  | 17987.44 | 3002.64 | 3002.64 | 14984.8
PRC 3352525PB6902 | 2024-11-06 | Inv. 7718.029454 PC |  | 17987.44 | 3679.52 | 6682.16 | 11305.28
PRC 3352525PC6902 | 2024-12-06 | Inv. 7718.039454 PC |  | 17987.44 | 3321.48 | 10003.64 | 7983.8
PRC 3352525PD6902 | 2025-01-14 | Inv. 7718.049454 PC |  | 17987.44 | 2675.04 | 12678.68 | 5308.76
PRC 3352525PE6902 | 2025-02-06 | Inv. 7718.05PC |  | 17987.44 | 3682.04 | 16360.72 | 1626.72
PRC 3352525PF6902 | 2025-03-07 | Inv. 7718.06 PC |  | 17987.44 | 1456.98 | 17817.7 | 169.74
PO 33525256902 | 2025-04-30 | Closing PO per PM | -169.74 | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  | Totals: | 17817.7 |  | 17817.7 |  | 0
|  | CM Services | 17717.7 |  | 17717.7 |  | 0
|  | Reimbursables | 100 |  | 100 |  | 0
|  | Total: | 17817.7 |  | 17817.7 |  | 0

## #9454.00 PM TIME
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910B
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 16514.24 | 16514.24 |  |  | 16514.24
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 16514.24 | 78.17 | 78.17 | 16436.07
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 16514.24 | 400.8 | 478.97 | 16035.27
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 16514.24 | 186.94 | 665.91 | 15848.33
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 16514.24 | 1660.7 | 2326.61 | 14187.63
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 16514.24 | 328.12 | 2654.73 | 13859.51
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 16514.24 | 2187.6 | 4842.33 | 11671.91
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 16514.24 | 150.11 | 4992.44 | 11521.8
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 16514.24 | 994.9 | 5987.34 | 10526.9
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 16514.24 | 93.52 | 6080.86 | 10433.38
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 16514.24 | 936.9 | 7017.76 | 9496.48
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 16514.24 | 96.04 | 7113.8 | 9400.44
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 16514.24 | 1027.7 | 8141.5 | 8372.74
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 16514.24 | 352.04 | 8493.54 | 8020.7
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 16514.24 | 1521.7 | 10015.24 | 6499
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 16514.24 | 129.62 | 10144.86 | 6369.38
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 16514.24 | 927.2 | 11072.06 | 5442.18
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 16514.24 | 193.33 | 11265.39 | 5248.85
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 16514.24 | 1327.8 | 12593.19 | 3921.05
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 16514.24 | 230.77 | 12823.96 | 3690.28
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 16514.24 | 1807.4 | 14631.36 | 1882.88
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 16514.24 | 215.18 | 14846.54 | 1667.7
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 16514.24 | 1667.7 | 16514.24 | 0
[5 empty] | 16514.24 |  | 16514.24 | 0
[5 empty] | 16514.24 |  | 16514.24 | 0
[5 empty] | 16514.24 |  | 16514.24 | 0
|  |  | Totals: | 16514.24 |  | 16514.24 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: PM Time Posted Inbox Adams, Brandon 1:48 PM (14 minutes ago) to me Joni, Please set my PM Time for MM25 9454.00 at $18,000. Regards, Brandon Adams Owner's Representative, State Design & Construction Resou MM25 9454.00 DOC ICIW Building 9 Roof Replacement $Joni Adams, Brandon Wed, Jul 2, 1:23 PM (8 days ago) to me Finance, Please close PM Time for MM25 9454.00 once June PM Time posts. Regards, Brandon Adams

## #9454.00 Misc
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 169
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525292902 | 2024-10-18 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1136 | 425.88 | 425.88
PRC 33525355900 | 2024-12-20 | 9500 | CNST | Brockway Mechanical V#(00002116146) | Inv. R8510 | 500 | 925.88
PRC 33525010910 | 2025-01-10 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2621892 | 827.5 | 1753.38
PRC 33525027902 | 2025-01-27 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1280 | 569.48 | 2322.86
PRC 33525076905 | 2025-03-17 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV047464 | 334.52 | 2657.38
CDE 33525114901 | 2025-04-24 | 9500 | CNST | Moving RapidsReproduction INVCL1280 From MM25 9454.00 to MM22 9354.00 | Inv. INVCL1280 | -569.48 | 2087.9
2087.9
2087.9
2087.9
2087.9
2087.9
2087.9
|  |  |  | Totals: |  | 2087.9

## #9454.00 Horizon Architecture
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945400-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525284903 | 2024-10-10 | PO Procore | 18400 | 18400 |  |  | 18400
PRC 3352528PA4903 | 2024-11-06 | Inv. 9454.00-01 |  | 18400 | 3196.88 | 3196.88 | 15203.12
PRC 3352528PB4903 | 2024-12-03 | Inv. 9454.00-02 |  | 18400 | 2580 | 5776.88 | 12623.12
PRC 3352528PC4903 | 2025-01-14 | Inv. 9454.00-03 |  | 18400 | 4240.25 | 10017.13 | 8382.87
PRC 3352528PD4903 | 2025-04-07 | Inv. 9454.00-04 |  | 18400 | 1720.37 | 11737.5 | 6662.5
PRC 3352528PE4903 | 2025-06-03 | Inv. 9454.00-05 |  | 18400 | 2956.25 | 14693.75 | 3706.25
PRC 3352528PF4903 | 2025-07-03 | Inv. 9454.00-06 - Final | -750 | 17650 | 2956.25 | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  |  |  | 17650 |  | 17650 | -9.0949e-13
|  | Totals: | 17650 |  | 17650 |  | 0 | FINAL
|  | Design Docs | 4262.5 |  | 4262.5 |  | 0
|  | Construction Docs | 6057.5 |  | 6057.5 |  | 0
|  | Bidding/Negoiation | 1417.5 |  | 1417.5 |  | 0
|  | Construction Phase | 5912.5 |  | 5912.5 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 17650 |  | 17650 |  | 0

## #9454.00 Brockway Mechanical
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Brockway Mechanical & Roofing |  |  | Vendor: 00002116146
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945400-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525088902 | 2025-03-28 | PO Procore | 132778 | 132778 |  |  | 132778
PRC 3352508PA8902 | 2025-07-08 | Inv. 3165R-1 |  | 132778 | 126139.1 | 126139.1 | 6638.9 | 6638.9
PRC 3352508PB8902 | 2025-07-11 | Inv. 3165-2 retention |  | 132778 | 6638.9 | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  |  |  | 132778 |  | 132778 | -5.457e-12
|  | Totals: | 132778 |  | 132778 |  | 0 | FINAL

## #9454.00 Samuels Group (2)
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525097906 | 2025-04-07 | PO Procore | 25593.76 | 25593.76 |  |  | 25593.76
PRC 3352509PA7906 | 2025-05-08 | Inv. 7764.01 CA |  | 25593.76 | 3747.36 | 3747.36 | 21846.4
PRC 3352509PB7906 | 2025-06-10 | Inv. 7764.02 CA |  | 25593.76 | 9279.68 | 13027.04 | 12566.72
PRC 3352509PC7906 | 2025-07-03 | Inv. 7764.03 CA FINAL | -1895.26 | 23698.5 | 10671.46 | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  |  |  | 23698.5 |  | 23698.5 | 0
|  | Totals: | 23698.5 |  | 23698.5 |  | 0 | FINAL
|  | CM Services | 23517.5 |  | 23517.5 |  | 0
|  | Reimbursables | 181 |  | 181 |  | 0
|  | Total: | 23698.5 |  | 23698.5 |  | 0

## RECAP #9455.00
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
| Program code 945500 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 735500
C | Samuels Group |  | 27943.26 | 27943.26 | 0
| PM TIME |  | 50000 | 18211.7 | 31788.3
| Misc. |  | 300 | 300 | 0
C | OPN Architects |  | 44140 | 44140 | 0
| OPN Architects (2) |  | 343780 | 239030 | 104750
C | Samuels Group (2) |  | 131521.27 | 131521.27 | 0
C | MTS Contracting |  | 40417.45 | 40417.45 | 0
| Total Project Cost | 735500 | 638101.98 | 501563.68 | 136538.3 | 97398.02

## #9455.00 Samuels Group
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525283902 | 2024-10-09 | PO Procore | 45969.22 | 45969.22 |  |  | 45969.22
PRC 3352528PA3902 | 2024-11-07 | Inv. 7729.01945500 |  | 45969.22 | 2068.79 | 2068.79 | 43900.43
PRC 3352528PB3902 | 2024-12-06 | Inv. 7729.02945500 |  | 45969.22 | 7340.12 | 9408.91 | 36560.31
PRC 3352528PC3902 | 2025-01-14 | Inv. 7729.03945500 |  | 45969.22 | 3632.7 | 13041.61 | 32927.61
PRC 3352528PD3902 | 2025-02-05 | Inv. 7729.04945500 |  | 45969.22 | 4268.45 | 17310.06 | 28659.16
PRC 3352528PE3902 | 2025-03-06 | Inv. 7729.05945500 |  | 45969.22 | 2478.12 | 19788.18 | 26181.04
PRC 3352528PF3902 | 2025-04-08 | Inv. 7729.06945500 |  | 45969.22 | 1232.95 | 21021.13 | 24948.09
PRC 3352528PG3902 | 2025-05-09 | Inv. 7729.07945500 |  | 45969.22 | 3631.85 | 24652.98 | 21316.24
PRC 3352528PH3902 | 2025-05-29 | Inv. 7729.08945500-FINAL | -18025.96 | 27943.26 | 3290.28 | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  | Totals: | 27943.26 |  | 27943.26 |  | 0 | FINAL
|  | CM Services: | 24902.16 |  | 24902.16 |  | 0
|  | Reimbursables: | 3041.1 |  | 3041.1 |  | 0
|  | Total: | 27943.26 |  | 27943.26 |  | 0

## #9455.00 PM TIME
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910C
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 50000 | 50000 |  |  | 50000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 50000 | 270.93 | 270.93 | 49729.07
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 50000 | 1802.7 | 2073.63 | 47926.37
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 50000 | 160.93 | 2234.56 | 47765.44
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 50000 | 1068.1 | 3302.66 | 46697.34
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 50000 | 60.05 | 3362.71 | 46637.29
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 50000 | 601.8 | 3964.51 | 46035.49
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 50000 | 18.56 | 3983.07 | 46016.93
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 50000 | 197.9 | 4180.97 | 45819.03
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 50000 | 238.44 | 4419.41 | 45580.59
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 50000 | 1032.3 | 5451.71 | 44548.29
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 50000 | 135.67 | 5587.38 | 44412.62
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 50000 | 969.2 | 6556.58 | 43443.42
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 50000 | 145.67 | 6702.25 | 43297.75
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 50000 | 1000.9 | 7703.15 | 42296.85
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 50000 | 46.86 | 7750.01 | 42249.99
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 50000 | 365.5 | 8115.51 | 41884.49
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 50000 | 108.57 | 8224.08 | 41775.92
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 50000 | 846.1 | 9070.18 | 40929.82
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 50000 | 95.03 | 9165.21 | 40834.79
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 50000 | 1042.2 | 10207.41 | 39792.59
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 50000 | 23.12 | 10230.53 | 39769.47
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 50000 | 174.4 | 10404.93 | 39595.07
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 50000 | 220.5 | 10625.43 | 39374.57
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 50000 | 1135.7 | 11761.13 | 38238.87
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 50000 | 116.36 | 11877.49 | 38122.51
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 50000 | 1156.2 | 13033.69 | 36966.31
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 50000 | 181.32 | 13215.01 | 36784.99
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 50000 | 1153.8 | 14368.81 | 35631.19
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 50000 | 69.47 | 14438.28 | 35561.72
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 50000 | 790.6 | 15228.88 | 34771.12
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 50000 | 144.68 | 15373.56 | 34626.44
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 50000 | 1794.5 | 17168.06 | 32831.94
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 50000 | 83.54 | 17251.6 | 32748.4
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 50000 | 960.1 | 18211.7 | 31788.3
[5 empty] | 50000 |  | 18211.7 | 31788.3
[5 empty] | 50000 |  | 18211.7 | 31788.3
[5 empty] | 50000 |  | 18211.7 | 31788.3
|  |  | Totals: | 50000 |  | 18211.7 |  | 31788.3
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (3 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9455.00 Misc
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Jennie E |  |  |  | Shipping Code 231A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526350900 | 2025-12-16 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV054455 | 300 | 300
300
300
300
300
300
300
300
300
300
300
300
|  |  |  | Totals: |  | 300

## #9455.00 OPN Architects
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945500-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320905 | 2024-11-15 | PO Procore | 44140 | 44140 |  |  | 44140
PRC 3352532PA0905 | 2025-01-27 | Inv. 24843000-1 |  | 44140 | 29132.4 | 29132.4 | 15007.6
PRC 3352532PB0905 | 2025-04-14 | Inv. 24843000-2 |  | 44140 | 15007.6 | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  |  |  | 44140 |  | 44140 | -1.819e-12
|  | Totals: | 44140 |  | 44140 |  | 0 | FINAL

## #9455.00 OPN Architects (2)
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
OPN Architects (2) |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945500-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525114900 | 2025-04-23 | PO Procore | 343780 | 343780 |  |  | 343780
PRC 3352511PA4900 | 2025-06-10 | Inv. 24843001-1 |  | 343780 | 32228 | 32228 | 311552
PRC 3352511PB4900 | 2025-07-07 | Inv. 24843001-2 |  | 343780 | 77442 | 109670 | 234110 | FY25
PO 33526114900 | 2025-07-29 | Roll to FY26 | 0 | 343780 |  | 109670 | 234110
PRC 3352611PC4900 | 2025-08-27 | Inv. 24843001-3 |  | 343780 | 71988.68 | 181658.68 | 162121.32
PRC 3352611PD4900 | 2025-11-05 | Inv. 24843001-4 |  | 343780 | 35921.32 | 217580 | 126200
PRC 3352611PE4900 | 2025-12-16 | Inv. 24843001-5 |  | 343780 | 15220 | 232800 | 110980
PRC 3352611PF4900 | 2026-02-24 | Inv. 24843001-6 |  | 343780 | 6230 | 239030 | 104750
|  |  |  | 343780 |  | 239030 | 104750
|  |  |  | 343780 |  | 239030 | 104750
|  |  |  | 343780 |  | 239030 | 104750
|  |  |  | 343780 |  | 239030 | 104750
|  |  |  | 343780 |  | 239030 | 104750
|  | Totals: | 343780 |  | 239030 |  | 104750
|  | Design Development | 80570 |  | 80570 |  | 0
|  | Construction Documents | 119900 |  | 119900 |  | 0
|  | Bidding/Negotiation | 6460 |  | 6460 |  | 0
|  | Construction Admin | 102090 |  | 3000 |  | 99090
|  | Rake Rhodes Engineers | 3000 |  |  |  | 3000
|  | Reimbursables | 31760 |  | 29100 |  | 2660
|  | Total: | 343780 |  | 239030 |  | 104750

## #9455.00 Samuels Group (2)
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525154909 | 2025-06-03 | PO Procore | 267056.12 | 267056.12 |  |  | 267056.12
PRC 3352515PA4909 | 2025-07-08 | Inv. 7787.01945500 |  | 267056.12 | 54494.67 | 54494.67 | 212561.45 | FY25
PO 33526154909 | 2025-07-29 | Roll to FY26 | 0 | 267056.12 |  | 54494.67 | 212561.45
PRC 3352615PB4909 | 2025-08-14 | Inv. 7787.02945500 |  | 267056.12 | 17812.06 | 72306.73 | 194749.39
PRC 3352615PC4909 | 2025-09-15 | Inv. 7787.03945500 |  | 267056.12 | 14285.74 | 86592.47 | 180463.65
PRC 3352615PD4909 | 2025-10-08 | Inv. 7787.04945500 |  | 267056.12 | 28060.17 | 114652.64 | 152403.48
PRC 3352615PE4909 | 2025-12-04 | Inv. 7787.05945500 |  | 267056.12 | 3752.31 | 118404.95 | 148651.17
PRC 3352615PF4909 | 2025-12-04 | Inv. 7787.06945500 |  | 267056.12 | 5083.68 | 123488.63 | 143567.49
PRC 3352615PG4909 | 2026-01-12 | Inv. 7787.07945500-FINAL | -135534.85 | 131521.27 | 8032.64 | 131521.27 | 0
|  |  |  | 131521.27 |  | 131521.27 | 0
|  |  |  | 131521.27 |  | 131521.27 | 0
|  |  |  | 131521.27 |  | 131521.27 | 0
|  |  |  | 131521.27 |  | 131521.27 | 0
|  | Totals: | 131521.27 |  | 131521.27 |  | 0
|  | CM Services | 28462.86 |  | 28462.86 |  | 0
|  | Reimbursables (Travel) | 298 |  | 298 |  | 0
|  | Reimbursables (Overhead Protection) | 92470.27 |  | 92470.27 |  | 0
|  | Reimbursables (Temp Fencing/Signage) | 10290.14 |  | 10290.14 |  | 0
|  | Total: | 131521.27 |  | 131521.27 |  | 0 | FINAL

## #9455.00 MTS Contracting
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-MM25-9255 |  |  | MA005 20243C
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526219902 | 2025-08-07 | PO Procore | 62907 | 62907 |  |  | 62907
PRC 3352621PA9902 | 2025-12-16 | Inv. 25-6095A |  | 62907 | 38396.58 | 38396.58 | 24510.42 | 2020.87
PO 33526219902 | 2026-02-03 | CO #1 | -22489.55 | 40417.45 |  | 38396.58 | 2020.87
PRC 3352621PB9902 | 2026-02-16 | Inv. 9455.00 Retainage |  | 40417.45 | 2020.87 | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  |  |  | 40417.45 |  | 40417.45 | -9.0949e-13
|  | Totals: | 40417.45 |  | 40417.45 |  | 0 | FINAL

## RECAP #9456.00
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
| Program code 945600 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 403525
C | Samuels Group |  | 22669.34 | 22669.34 | 0
| PM TIME |  | 13000 | 11490.91 | 1509.09
| Misc. |  | 1460.99 | 1460.99 | 0
C | CMBA Architects |  | 28525 | 28525 | 0
C | McKinnis Roofing |  | 247308.85 | 247308.85 | 0
C | Samuels Group (2) |  | 36726.53 | 36726.53 | 0
| Total Project Cost | 403525 | 349690.71 | 348181.62 | 1509.09 | 53834.29

## #9456.00 Samuels Group
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298909 | 2024-10-24 | PO Procore | 24471.92 | 24471.92 |  |  | 24471.92
PRC 3352529PA8909 | 2024-11-06 | Inv. 7734.01945600 |  | 24471.92 | 1048.51 | 1048.51 | 23423.41
PRC 3352529PB8909 | 2025-01-13 | Inv. 7734.02945600 |  | 24471.92 | 2713.5 | 3762.01 | 20709.91
PRC 3352529PC8909 | 2025-02-05 | Inv. 7734.03945600 |  | 24471.92 | 5115.51 | 8877.52 | 15594.4
PRC 3352529PD8909 | 2025-03-06 | Inv. 7734.04945600 |  | 24471.92 | 5168.25 | 14045.77 | 10426.15
PRC 3352529PE8909 | 2025-04-08 | Inv. 7734.05945600 |  | 24471.92 | 1330.34 | 15376.11 | 9095.81
PRC 3352529PF8909 | 2025-05-09 | Inv. 7734.06945600 |  | 24471.92 | 5275.2 | 20651.31 | 3820.61
PRC 3352529PG8909 | 2025-05-29 | Inv. 7734.07945600-FINAL | -1802.58 | 22669.34 | 2018.03 | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  | Totals: | 22669.34 |  | 22669.34 |  | 0 | FINAL
|  | CM Services | 21631.92 |  | 21631.92 |  | 0
|  | Reimbursables | 1037.42 |  | 1037.42 |  | 0
|  | Total: | 22669.34 |  | 22669.34 |  | 0

## #9456.00 PM TIME
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910D
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13000 | 13000 |  |  | 13000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 28.94 | 28.94 | 12971.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 191.6 | 220.54 | 12779.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 16.45 | 236.99 | 12763.01
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 107.1 | 344.09 | 12655.91
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 34.59 | 378.68 | 12621.32
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 343.5 | 722.18 | 12277.82
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13000 | 81.28 | 803.46 | 12196.54
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13000 | 867.5 | 1670.96 | 11329.04
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13000 | 64.46 | 1735.42 | 11264.58
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13000 | 278 | 2013.42 | 10986.58
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13000 | 75.78 | 2089.2 | 10910.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13000 | 543 | 2632.2 | 10367.8
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13000 | 40.5 | 2672.7 | 10327.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13000 | 275.6 | 2948.3 | 10051.7
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 13000 | 79.36 | 3027.66 | 9972.34
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 13000 | 621.4 | 3649.06 | 9350.94
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 13000 | 31.65 | 3680.71 | 9319.29
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 13000 | 246.4 | 3927.11 | 9072.89
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 13000 | 84.46 | 4011.57 | 8988.43
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 13000 | 926.9 | 4938.47 | 8061.53
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 13000 | 392.99 | 5331.46 | 7668.54
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 13000 | 3024.3 | 8355.76 | 4644.24
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 13000 | 33.2 | 8388.96 | 4611.04
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 13000 | 169.6 | 8558.56 | 4441.44
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 13000 | 168.57 | 8727.13 | 4272.87
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 13000 | 1674.7 | 10401.83 | 2598.17
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 13000 | 35.03 | 10436.86 | 2563.14
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 13000 | 222 | 10658.86 | 2341.14
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 13000 | 36.61 | 10695.47 | 2304.53
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 13000 | 417.7 | 11113.17 | 1886.83
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 13000 | 28.34 | 11141.51 | 1858.49
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 13000 | 349.4 | 11490.91 | 1509.09
[5 empty] | 13000 |  | 11490.91 | 1509.09
[5 empty] | 13000 |  | 11490.91 | 1509.09
[5 empty] | 13000 |  | 11490.91 | 1509.09
[5 empty] | 13000 |  | 11490.91 | 1509.09
[5 empty] | 13000 |  | 11490.91 | 1509.09
|  |  | Totals: | 13000 |  | 11490.91 |  | 1509.09
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (4 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9456.00 Misc
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 231A
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525055900 | 2025-02-25 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2629554 | 1021.25 | 1021.25
PRC 33525140903 | 2025-05-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048431 | 439.74 | 1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
|  |  |  | Totals: |  | 1460.99

## #9456.00 CMBA Architects
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
CMBA Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945600-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023906 | 2025-01-23 | PO Procore | 28645 | 28645 |  |  | 28645
PRC 3352502PA3906 | 2025-02-24 | Inv. 65173 |  | 28645 | 3250 | 3250 | 25395
PRC 3352502PB3906 | 2025-03-17 | Inv. 65253 |  | 28645 | 4430 | 7680 | 20965
PRC 3352502PC3906 | 2025-04-24 | Inv. 65418 |  | 28645 | 7440 | 15120 | 13525
PRC 3352502PD3906 | 2025-05-14 | Inv. 65545 |  | 28645 | 3406 | 18526 | 10119
PRC 3352502PE3906 | 2025-06-10 | Inv. 65634 |  | 28645 | 1519 | 20045 | 8600
PRC 3352502PF3906 | 2025-07-03 | Inv. 65704 |  | 28645 | 1292.5 | 21337.5 | 7307.5 | FY25
PO 33526023906 | 2025-07-29 | Roll to FY26 | 0 | 28645 |  | 21337.5 | 7307.5
PRC 3352602PG3906 | 2025-09-15 | Inv. 66009 |  | 28645 | 3137.5 | 24475 | 4170
PRC 3352602PH3906 | 2025-09-15 | Inv. 66046 |  | 28645 | 2025 | 26500 | 2145
PRC 3352602PI3906 | 2025-10-14 | Inv. 66292 |  | 28645 | 1518.75 | 28018.75 | 626.25
PRC 3352602PJ3906 | 2025-11-12 | Inv. 66480 |  | 28645 | 303.75 | 28322.5 | 322.5
PRC 3352602PK3906 | 2025-12-29 | Inv. 66559 |  | 28645 | 202.5 | 28525 | 120
PO 33526023906 | 2026-01-23 | Closing PO Per Email | -120 | 28525 |  | 28525 | 0
|  |  |  | 28525 |  | 28525 | 0
|  | Totals: | 28525 |  | 28525 |  | 0
|  | Design Development | 6160 |  | 6160 |  | 0
|  | Construction Documents | 8460 |  | 8460 |  | 0
|  | Bidding/Negotiation | 2900 |  | 2900 |  | 0
|  | Construction Phase | 10125 |  | 10125 |  | 0
|  | Reimbursables | 880 |  | 880 |  | 0
|  | Total: | 28525 |  | 28525 |  | 0
Note on C22: Huggins, Joni [DAS]: Fwd: 9456.00 - DOE ISD Elementary School Roof Replacement - Final Invoice $Joni Elliott, Jennie 8:11 AM (30 minutes ago) to me Finance, Per the email below please close CMBA's Contract in 9456.00 - DOE ISD Elementary School Roof Replacement. Thank you, Jennie Elliott

## #9456.00 McKinnis Roofing
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
McKinnis Roofing |  |  | Vendor: 00003217305
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945600-01
Project Manager - Jennie E |  |  | Activity code: Brum
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525129901 | 2025-05-09 | PO Procore | 243401 | 243401 |  |  | 243401
PRC 3352512PA9901 | 2025-07-15 | Inv. 9456.00-01 |  | 243401 | 134155.1 | 134155.1 | 109245.9 | 7060.79
PO 33525129901 | 2025-07-18 | CO #1 | 1963 | 245364 |  | 134155.1 | 111208.9 |  | FY25
PO 33526129901 | 2025-07-29 | Roll to FY26 | 0 | 245364 |  | 134155.1 | 111208.9
PRC 3352612PB9901 | 2025-08-14 | Inv. 9456.00-02 |  | 245364 | 32112.32 | 166267.42 | 79096.58 | 8750.91
PO 33526129901 | 2025-08-22 | CO #2 | 1944.85 | 247308.85 |  | 166267.42 | 81041.43
PRC 3352612PC9901 | 2025-08-29 | Inv. 9456.00-03 |  | 247308.85 | 36261.99 | 202529.41 | 44779.44 | 10659.43
PO 33526129901 | 2025-10-23 | CO #3(No Cost CO) | 0 | 247308.85 |  | 202529.41 | 44779.44
PRC 3352612PD9901 | 2025-12-16 | Inv. 48799 |  | 247308.85 | 30101.7 | 232631.11 | 14677.74 | 12243.73
PRC 3352612PE9901 | 2025-12-29 | Inv. 49053 |  | 247308.85 | 2312.31 | 234943.42 | 12365.43 | 12365.43
PRC 3352612PF9901 | 2026-01-09 | Inv. 49053R - Retainage |  | 247308.85 | 12365.43 | 247308.85 | -5.457e-12
|  |  |  | 247308.85 |  | 247308.85 | -5.457e-12
|  |  |  | 247308.85 |  | 247308.85 | -5.457e-12
|  | Totals: | 247308.85 |  | 247308.85 |  | 0 | FINAL

## #9456.00 Samuels Group (2)
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525154910 | 2025-06-03 | PO Procore | 38625.16 | 38625.16 |  |  | 38625.16
PRC 3352515PA4910 | 2025-07-08 | Inv. 7785.51945600 |  | 38625.16 | 3014.28 | 3014.28 | 35610.88 | FY25
PO 33526154910 | 2025-07-29 | Roll to FY26 | 0 | 38625.16 |  | 3014.28 | 35610.88
PRC 3352615PB4910 | 2025-08-14 | Inv. 7785.52945600 |  | 38625.16 | 9904.26 | 12918.54 | 25706.62
PRC 3352615PC4910 | 2025-09-15 | Inv. 7785.53945600 |  | 38625.16 | 7174.65 | 20093.19 | 18531.97
PRC 3352615PD4910 | 2025-10-08 | Inv. 7785.54945600 |  | 38625.16 | 2351.59 | 22444.78 | 16180.38
PRC 3352615PE4910 | 2025-11-18 | Inv. 7785.55945600 |  | 38625.16 | 5500.22 | 27945 | 10680.16
PRC 3352615PF4910 | 2025-12-04 | Inv. 7785.56945600 |  | 38625.16 | 2811.08 | 30756.08 | 7869.08
PRC 3352615PG4910 | 2025-12-29 | Inv. 7785.57945600-FINAL | -1898.63 | 36726.53 | 5970.45 | 36726.53 | 0
|  |  |  | 36726.53 |  | 36726.53 | 0
|  |  |  | 36726.53 |  | 36726.53 | 0
|  |  |  | 36726.53 |  | 36726.53 | 0
|  |  |  | 36726.53 |  | 36726.53 | 0
|  | Totals: | 36726.53 |  | 36726.53 |  | 0 | FINAL
|  | CM Services | 35193.49 |  | 35193.49 |  | 0
|  | Reimbursables | 1533.04 |  | 1533.04 |  | 0
|  | Total: | 36726.53 |  | 36726.53 |  | 0

## RECAP #9457.00
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
| Program code 945700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 405525
C | Samuels Group |  | 22739.45 | 22739.45 | 0
| PM TIME |  | 13000 | 7206.63 | 5793.37
| Misc. |  | 19534.76 | 19534.76 | 0
C | CMBA Architects |  | 28425 | 28425 | 0
C | Martino Commercial Roofing |  | 276990.89 | 276990.89 | 0
C | Samuels Group (2) |  | 40976.18 | 40976.18 | 0
| Total Project Cost | 405525 | 401666.28 | 395872.91 | 5793.37 | 3858.72

## #9457.00 Samuels Group
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298908 | 2024-10-24 | PO Procore | 24471.92 | 24471.92 |  |  | 24471.92
PRC 3352529PA8908 | 2025-01-13 | Inv. 7735.01945700 |  | 24471.92 | 5145.5 | 5145.5 | 19326.42
PRC 3352529PB8908 | 2024-02-05 | Inv. 7735.02945700 |  | 24471.92 | 4330.81 | 9476.31 | 14995.61
PRC 3352529PC8908 | 2025-03-06 | Inv. 7735.03945700 |  | 24471.92 | 4118.39 | 13594.7 | 10877.22
PRC 3352529PD8908 | 2025-04-08 | Inv. 7735.04945700 |  | 24471.92 | 1429.23 | 15023.93 | 9447.99
PRC 3352529PE8908 | 2025-05-08 | Inv. 7735.05945700 |  | 24471.92 | 5364.57 | 20388.5 | 4083.42
PRC 3352529PF8908 | 2025-05-29 | Inv. 7735.06945700-FINAL | -1732.47 | 22739.45 | 2350.95 | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  | Totals: | 22739.45 |  | 22739.45 |  | 0 | FINAL
|  | CM Services | 21631.92 |  | 21631.92 |  | 0
|  | Reimbursables | 1107.53 |  | 1107.53 |  | 0
|  | Total: | 22739.45 |  | 22739.45 |  | 0

## #9457.00 PM TIME
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910E
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13000 | 13000 |  |  | 13000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 28.94 | 28.94 | 12971.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 191.6 | 220.54 | 12779.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 16.45 | 236.99 | 12763.01
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 107.1 | 344.09 | 12655.91
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 34.59 | 378.68 | 12621.32
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 343.5 | 722.18 | 12277.82
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13000 | 81.28 | 803.46 | 12196.54
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13000 | 867.5 | 1670.96 | 11329.04
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13000 | 64.46 | 1735.42 | 11264.58
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13000 | 278 | 2013.42 | 10986.58
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13000 | 75.78 | 2089.2 | 10910.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13000 | 543 | 2632.2 | 10367.8
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13000 | 40.5 | 2672.7 | 10327.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13000 | 275.6 | 2948.3 | 10051.7
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 13000 | 79.36 | 3027.66 | 9972.34
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 13000 | 621.4 | 3649.06 | 9350.94
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 13000 | 31.65 | 3680.71 | 9319.29
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 13000 | 246.4 | 3927.11 | 9072.89
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 13000 | 42.61 | 3969.72 | 9030.28
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 13000 | 464 | 4433.72 | 8566.28
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 13000 | 45.47 | 4479.19 | 8520.81
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 13000 | 351 | 4830.19 | 8169.81
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 13000 | 88.05 | 4918.24 | 8081.76
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 13000 | 453.5 | 5371.74 | 7628.26
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 13000 | 39.99 | 5411.73 | 7588.27
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 13000 | 398.7 | 5810.43 | 7189.57
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 13000 | 62.35 | 5872.78 | 7127.22
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 13000 | 399.7 | 6272.48 | 6727.52
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 13000 | 45.21 | 6317.69 | 6682.31
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 13000 | 511.2 | 6828.89 | 6171.11
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 13000 | 28.34 | 6857.23 | 6142.77
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 13000 | 349.4 | 7206.63 | 5793.37
[5 empty] | 13000 |  | 7206.63 | 5793.37
[5 empty] | 13000 |  | 7206.63 | 5793.37
[5 empty] | 13000 |  | 7206.63 | 5793.37
[5 empty] | 13000 |  | 7206.63 | 5793.37
[5 empty] | 13000 |  | 7206.63 | 5793.37
|  |  | Totals: | 13000 |  | 7206.63 |  | 5793.37
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (4 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9457.00 Misc
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 231A
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525090906 | 2025-03-31 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2636754 | 2152.5 | 2152.5
PRC 33525140902 | 2025-05-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048460 | 442.26 | 2594.76
PRC 33526054902 | 2026-02-23 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010975-IN | 16940 | 19534.76
19534.76
19534.76
19534.76
19534.76
19534.76
19534.76
19534.76
19534.76
19534.76
|  |  |  | Totals: |  | 19534.76

## #9457.00 CMBA Architects
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
CMBA Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945700-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023907 | 2025-01-23 | PO Procore | 28645 | 28645 |  |  | 28645
PRC 3352502PA3907 | 2025-02-24 | Inv. 65172 |  | 28645 | 3250 | 3250 | 25395
PRC 3352502PB3907 | 2025-03-17 | Inv. 65252 |  | 28645 | 4430 | 7680 | 20965
PRC 3352502PC3907 | 2025-04-25 | Inv. 65417 |  | 28645 | 7440 | 15120 | 13525
PRC 3352502PD3907 | 2025-05-14 | Inv. 65544 |  | 28645 | 3406 | 18526 | 10119
PRC 3352502PE3907 | 2025-06-12 | Inv. 65684 |  | 28645 | 1519 | 20045 | 8600
PRC 3352502PF3907 | 2025-07-03 | Inv. 65703 |  | 28645 | 1292.5 | 21337.5 | 7307.5 | FY25
PO 33526023907 | 2025-07-29 | Roll to FY26 | 0 | 28645 |  | 21337.5 | 7307.5
PRC 3352602PG3907 | 2025-09-15 | Inv. 66008-R |  | 28645 | 5062.5 | 26400 | 2245
PRC 3352602PH3907 | 2025-10-14 | Inv. 66291 |  | 28645 | 1518.75 | 27918.75 | 726.25
PRC 3352602PI3907 | 2025-11-12 | Inv. 66479 |  | 28645 | 303.75 | 28222.5 | 422.5
PRC 3352602PJ3907 | 2025-12-29 | Inv. 66558 |  | 28645 | 202.5 | 28425 | 220
PO 33526023907 | 2026-01-23 | Closing PO Per Email | -220 | 28425 |  | 28425 | 0
|  |  |  | 28425 |  | 28425 | 0
|  |  |  | 28425 |  | 28425 | 0
|  | Totals: | 28425 |  | 28425 |  | 0
|  | Design Development | 6160 |  | 6160 |  | 0
|  | Construction Documents | 8460 |  | 8460 |  | 0
|  | Bidding/Negotiation | 2900 |  | 2900 |  | 0
|  | Construction Phase | 10125 |  | 10125 |  | 0
|  | Reimbursables: | 780 |  | 780 |  | 0
|  | Total: | 28425 |  | 28425 |  | 0
Note on C21: Fwd: 9457.00 - DOE ISD High School Gym Roof Replacement - Final Invoice $Joni Elliott, Jennie 8:12 AM (33 minutes ago) to me Finance, Per the email below please close CMBA's Contract in 9457.00 - DOE ISD High School Gym Roof Replacement. Thank you, Jennie Elliott

## #9457.00 Martino Commercial
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
Martino Commercial Roofing |  |  | Vendor: 00003228049
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945700-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525132901 | 2025-05-09 | PO Procore | 245404 | 245404 |  |  | 245404
PRC 3352513PA2901 | 2025-07-14 | Inv. 9457.00-01 |  | 245404 | 163666 | 163666 | 81738 | 8614 | FY25
PO 33526132901 | 2025-07-29 | Roll to FY26 | 0 | 245404 |  | 163666 | 81738
PO 33526132901 | 2025-08-14 | CO #1 | 3948.81 | 249352.81 |  | 163666 | 85686.81
PRC 3352613PB2901 | 2025-08-19 | Inv. 9457.00-02 |  | 249352.81 | 26980 | 190646 | 58706.81 | 10034
PRC 3352613PC2901 | 2025-09-17 | Inv. 9457.00-03 |  | 249352.81 | 15218.96 | 205864.96 | 43487.85 | 10835
PO 33526132901 | 2025-11-05 | CO #2 | 24693.38 | 274046.19 |  | 205864.96 | 68181.23
PO 33526132901 | 2025-11-12 | CO #3 | 4308.55 | 278354.74 |  | 205864.96 | 72489.78
PRC 3352613PD2901 | 2025-12-16 | Inv. 9457.00-04 |  | 278354.74 | 54945.04 | 260810 | 17544.74 | 13726.85
PRC 3352613PE2901 | 2026-01-09 | Inv. 9457.00-05 |  | 278354.74 | 2331.34 | 263141.34 | 15213.4 | 13849.55
PRC 3352613PF2901 | 2026-01-13 | Inv. 9457.00-06-Retainage | -1363.85 | 276990.89 | 13849.55 | 276990.89 | 0
|  |  |  | 276990.89 |  | 276990.89 | 0
|  |  |  | 276990.89 |  | 276990.89 | 0
|  | Totals: | 276990.89 |  | 276990.89 |  | 0 | FINAL

## #9457.00 Samuels Group (2)
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525154908 | 2025-06-03 | PO Procore | 42625.16 | 42625.16 |  |  | 42625.16
PRC 3352515PA4908 | 2025-07-08 | Inv. 7784.51945700 |  | 42625.16 | 2887.02 | 2887.02 | 39738.14 | FY25
PO 33526154908 | 2025-07-29 | Roll to FY26 | 0 | 42625.16 |  | 2887.02 | 39738.14
PRC 3352615PB4908 | 2025-08-14 | Inv. 7784.52945700 |  | 42625.16 | 6494.06 | 9381.08 | 33244.08
PRC 3352615PC4908 | 2025-09-15 | Inv. 7784.53945700 |  | 42625.16 | 7304.77 | 16685.85 | 25939.31
PRC 3352615PD4908 | 2025-10-08 | Inv. 7784.54945700 |  | 42625.16 | 10382.66 | 27068.51 | 15556.65
PO 33526154908 | 2025-10-28 | CO #1 | -1648.98 | 40976.18 |  | 27068.51 | 13907.67
PRC 3352615PE4908 | 2025-11-18 | Inv. 7784.55945700 |  | 40976.18 | 261.7 | 27330.21 | 13645.97
PRC 3352615PF4908 | 2025-12-04 | Inv. 7784.56945700 |  | 40976.18 | 6383 | 33713.21 | 7262.97
PRC 3352615PG4908 | 2026-01-09 | Inv. 7784.57945700-FINAL |  | 40976.18 |  | 33713.21 | 7262.97
|  |  |  | 40976.18 | 7262.97 | 40976.18 | 8.1855e-12
|  |  |  | 40976.18 |  | 40976.18 | 8.1855e-12
|  |  |  | 40976.18 |  | 40976.18 | 8.1855e-12
|  | Totals: | 40976.18 |  | 40976.18 |  | 0 | FINAL
|  | CM Services | 36625.16 |  | 36625.16 |  | 0
|  | Reimbursables(Mileage, Meals, Hotels) | 2000 |  | 2000 |  | 0
|  | Reimbursables(Temp Electric Disconnect) | 4000 |  | 4000 |  | 0
|  | CO #1 | -1648.98 |  | -1648.98 |  | 0
|  | Total: | 40976.18 |  | 40976.18 |  | 0

## RECAP #9458.00
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
| Program code 945800 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 630000
C | McGough Construction |  | 8788.77 | 8788.77 | 0
| PM TIME |  | 20000 | 11357.28 | 8642.72
| Misc. |  | 2500 | 2500 | 0
| Resource Consulting Engineers |  | 36000 | 34848 | 1152
C | Proctor Mechanical |  | 116420.66 | 116420.66 | 0
| McGough Construction (2) |  | 34904.76 | 16376.96 | 18527.8
| Riley Armstrong Plumbing & Heating |  | 300845 | 281029.68 | 19815.32
| Total Project Cost | 630000 | 519459.19 | 471321.35 | 48137.84 | 110540.81

## #9458.00 McGough
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525312906 | 2025-11-07 | PO Procore | 15563.96 | 15563.96 |  |  | 15563.96
PRC 3352531PA2906 | 2025-01-27 | Inv. 101368.003PC-01 |  | 15563.96 | 2151.48 | 2151.48 | 13412.48
PRC 3352531PB2906 | 2025-02-15 | Inv. 101368.003PC-02 |  | 15563.96 | 739.53 | 2891.01 | 12672.95
PRC 3352531PC2906 | 2025-03-17 | Inv. 101368.003PC-03A* |  | 15563.96 | 989.01 | 3880.02 | 11683.94
PRC 3352531PD2906 | 2025-04-25 | Inv. 101368.003PC-04A |  | 15563.96 | 2671.17 | 6551.19 | 9012.77
PRC 3352531PE2906 | 2025-05-09 | Inv. 101368.003PC-05A FINAL | -6775.19 | 8788.77 | 2237.58 | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  | Totals: | 8788.77 |  | 8788.77 |  | 0 | FINAL
|  | CM Services | 8551.77 |  | 8551.77 |  | 0
|  | Reimbursables | 237 |  | 237 |  | 0
|  | Total: | 8788.77 |  | 8788.77 |  | 0
Inv. 101368.003PC-XX* was used by this vendor in another tab. Adding an A to this tab

## #9458.00 PM TIME
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910F
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 109.61 | 109.61 | 19890.39
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 728.3 | 837.91 | 19162.09
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 144.9 | 982.81 | 19017.19
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 961 | 1943.81 | 18056.19
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 155.12 | 2098.93 | 17901.07
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 1546.5 | 3645.43 | 16354.57
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 73.69 | 3719.12 | 16280.88
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 787.7 | 4506.82 | 15493.18
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 229.74 | 4736.56 | 15263.44
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 991.9 | 5728.46 | 14271.54
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 64.81 | 5793.27 | 14206.73
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 465.5 | 6258.77 | 13741.23
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 130.91 | 6389.68 | 13610.32
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 898.3 | 7287.98 | 12712.02
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 65.43 | 7353.41 | 12646.59
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 511.2 | 7864.61 | 12135.39
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 20000 | 36.56 | 7901.17 | 12098.83
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 20000 | 282.4 | 8183.57 | 11816.43
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 42.61 | 8226.18 | 11773.82
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 464 | 8690.18 | 11309.82
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 11.34 | 8701.52 | 11298.48
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 88 | 8789.52 | 11210.48
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 110.47 | 8899.99 | 11100.01
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 568.4 | 9468.39 | 10531.61
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 27.76 | 9496.15 | 10503.85
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 278.4 | 9774.55 | 10225.45
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 6.95 | 9781.5 | 10218.5
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 44.3 | 9825.8 | 10174.2
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 20.95 | 9846.75 | 10153.25
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 231.8 | 10078.55 | 9921.45
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 56.35 | 10134.9 | 9865.1
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 701.5 | 10836.4 | 9163.6
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 41.38 | 10877.78 | 9122.22
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 479.5 | 11357.28 | 8642.72
[5 empty] | 20000 |  | 11357.28 | 8642.72
[5 empty] | 20000 |  | 11357.28 | 8642.72
[5 empty] | 20000 |  | 11357.28 | 8642.72
|  |  | Totals: | 20000 |  | 11357.28 |  | 8642.72
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (5 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9458.00 Misc
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 177
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526350901 | 2025-12-16 | 9500 | CNST | CH McGuiness V#(00002109782) | Inv. 251522 | 2500 | 2500
2500
2500
2500
2500
2500
2500
2500
2500
2500
2500
2500
|  |  |  | Totals: |  | 2500

## #9458.00 Resource Consulting
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Resource Consulting Engineers |  |  | Vendor: 00003224689
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945800-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525010905 | 2025-01-10 | PO Procore | 36000 | 36000 |  |  | 36000
PRC 3352501PA0905 | 2025-03-04 | Inv. 2024.029.00-01 |  | 36000 | 3000 | 3000 | 33000
PRC 3352501PB0905 | 2025-03-06 | Inv. 2024.029.00-02 |  | 36000 | 3000 | 6000 | 30000
PRC 3352501PC0905 | 2025-03-10 | Inv. 2024.029.00-03 |  | 36000 | 7500 | 13500 | 22500
PRC 3352501PD0905 | 2025-03-24 | Inv. 2024.029.00-04 |  | 36000 | 13500 | 27000 | 9000
PRC 3352501PE0905 | 2025-05-19 | Inv. 2024.029.00-05 |  | 36000 | 1800 | 28800 | 7200 | FY25
PO 33526010905 | 2025-07-29 | Roll to FY26 | 0 | 36000 |  | 28800 | 7200
PRC 3352601PF0905 | 2025-10-15 | Inv. 2024.029.00-06 |  | 36000 | 1440 | 30240 | 5760
PRC 3352601PG0905 | 2025-12-04 | Inv. 2024.029.00-07 |  | 36000 | 2000 | 32240 | 3760
PRC 3352601PH0905 | 2026-01-20 | Inv. 2024.029.00-08 |  | 36000 | 1440 | 33680 | 2320
PRC 3352601PI0905 | 2026-03-18 | Inv. 2024.029.00-09 |  | 36000 | 1168 | 34848 | 1152
|  |  |  | 36000 |  | 34848 | 1152
|  |  |  | 36000 |  | 34848 | 1152
|  | Totals: | 36000 |  | 34848 |  | 1152
|  | Design Development | 12600 |  | 12600 |  | 0
|  | Construction Documents | 14400 |  | 14400 |  | 0
|  | Bidding/Negotiation | 1800 |  | 1800 |  | 0
|  | Construction Phase | 7200 |  | 6048 |  | 1152
|  | Total: | 36000 |  | 34848 |  | 1152

## #9458.00 Proctor Mechanical
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM25-9255 |  |  | MA#21010A
Project Manager - Jennie E |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525043904 | 2025-02-11 | PO Procore | 140100 | 140100 |  |  | 140100
PRC 3352504PA3904 | 2025-05-29 | Inv. 7615.0/1 |  | 140100 | 110599.63 | 110599.63 | 29500.37 | 5821.03
PO 33525043904 | 2025-07-03 | CO #1 | -23679.34 | 116420.66 |  | 110599.63 | 5821.03
PRC 3352504PB3904 | 2025-07-21 | Inv. 7615.0/2-Retainage |  | 116420.66 | 5821.03 | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  |  |  | 116420.66 |  | 116420.66 | -4.5475e-12
|  | Totals: | 116420.66 |  | 116420.66 |  | 0 | FINAL

## #9458.00 McGough Construction 2
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525127906 | 2025-05-07 | PO Procore | 34904.76 | 34904.76 |  |  | 34904.76
PRC 33525127PA906 | 2025-06-16 | Inv. 101368.004CA-01 |  | 34904.76 | 2430.62 | 2430.62 | 32474.14
PRC 33525127PB906 | 2025-07-15 | Inv. 101368.003CA-02 |  | 34904.76 | 1606.16 | 4036.78 | 30867.98 | FY25
PO 33526127906 | 2025-07-29 | Roll to FY26 | 0 | 34904.76 |  | 4036.78 | 30867.98
PRC 3352612PC7906 | 2025-08-14 | Inv. 101368.003CA-03 |  | 34904.76 | 1167.8 | 5204.58 | 29700.18
PRC 3352612PD7906 | 2025-09-22 | Inv. 101368.003CA-04 |  | 34904.76 | 1524.2 | 6728.78 | 28175.98
PRC 3352612PE7906 | 2025-10-15 | Inv. 101368.003CA-05 |  | 34904.76 | 1822.98 | 8551.76 | 26353
PRC 3352612PF7906 | 2025-11-12 | Inv. 101368.003CA-06 |  | 34904.76 | 910 | 9461.76 | 25443
PRC 3352612PG7906 | 2025-12-10 | Inv. 101368.003CA-07 |  | 34904.76 | 2216.78 | 11678.54 | 23226.22
PRC 3352612PH7906 | 2026-01-13 | Inv. 101368.003CA-08 |  | 34904.76 | 1288.38 | 12966.92 | 21937.84
PRC 3352612PI7906 | 2026-02-16 | Inv. 101368.003CA-09 |  | 34904.76 | 1518.76 | 14485.68 | 20419.08
PRC 3352612PJ7906 | 2026-03-18 | Inv. 101368.003CA-10 |  | 34904.76 | 1891.28 | 16376.96 | 18527.8
|  |  |  | 34904.76 |  | 16376.96 | 18527.8
|  | Totals: | 34904.76 |  | 16376.96 |  | 18527.8
|  | CM Services | 32384.76 |  | 16082.46 |  | 16302.3
|  | Reimbursables | 2520 |  | 294.5 |  | 2225.5
|  | Total: | 34904.76 |  | 16376.96 |  | 18527.8

## #9458.00 Riley Armstrong
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Rily Armstrong Heating & Plumbing |  |  | Vendor: 00002118365
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945800-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525133910 | 05/12/25 | PO Procore | 299175 | 299175 |  |  | 299175
PRC 3352513PA3910 | 2025-06-30 | Inv. 235495 |  | 299175 | 9500 | 9500 | 289675 | 500 | FY25
PO 33526133910 | 2025-07-29 | Roll to FY26 | 0 | 299175 |  | 9500 | 289675
PRC 3352613PB3910 | 2025-10-28 | Inv. 236993 |  | 299175 | 19000 | 28500 | 270675 | 1500
PRC 3352613PC3910 | 2025-11-12 | Inv. 237552 |  | 299175 | 68162.5 | 96662.5 | 202512.5 | 5087.5
PRC 3352613PD3910 | 2026-01-26 | Inv. 238296 |  | 299175 | 150776.87 | 247439.37 | 51735.63 | 13023.13
PO 33526133910 | 2026-01-28 | CO #1 | 1207.47 | 300382.47 |  | 247439.37 | 52943.1
PRC 3352613PE3910 | 2026-02-04 | Inv. 238691 |  | 300382.47 | 4750 | 252189.37 | 48193.1 | 13273.13
PRC 3352613PF3910 | 2026-03-03 | Inv. 239099 |  | 300382.47 | 28840.31 | 281029.68 | 19352.79 | 14791.04
PO 33526133910 | 2026-03-10 | CO #2 | 462.53 | 300845 |  | 281029.68 | 19815.32
|  |  |  | 300845 |  | 281029.68 | 19815.32
|  |  |  | 300845 |  | 281029.68 | 19815.32
|  |  |  | 300845 |  | 281029.68 | 19815.32
|  | Totals: | 300845 |  | 281029.68 |  | 19815.32

## RECAP #9459.00
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
| Program code 945900 |  |  | Major Program 4F03
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 280000
C | McGough Construction |  | 12555.91 | 12555.91 | 0
| PM TIME |  | 14400 | 14254.02 | 145.98
| Misc. |  | 1556.25 | 1556.25 | 0
C | IMEG Corporation |  | 18964 | 18964 | 0
C | McGough Construction (2) |  | 14787.87 | 14787.87 | 0
C | Reliable 1 |  | 188499.52 | 188499.52 | 0
| Total Project Cost | 280000 | 250763.55 | 250617.57 | 145.98 | 29236.45

## #9459.00 McGough Constructi
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525257901 | 2024-09-13 | PO Procore | 16497.41 | 16497.41 |  |  | 16497.41
PRC 3352525PA7901 | 2024-10-14 | Inv. 101174.015-PC01 |  | 16497.41 | 451.24 | 451.24 | 16046.17
PRC 3352525PB7901 | 2024-11-14 | Inv. 101174.015-PC02 |  | 16497.41 | 2489.89 | 2941.13 | 13556.28
PRC 3352525PC7901 | 2024-12-18 | Inv. 101174.015-PC03 |  | 16497.41 | 2689.03 | 5630.16 | 10867.25
PRC 3352525PD7901 | 2025-01-14 | Inv. 101174.015-PC04 |  | 16497.41 | 1908.57 | 7538.73 | 8958.68
PRC 3352525PE7901 | 2025-02-12 | Inv. 101174.015-PC05 |  | 16497.41 | 2297.07 | 9835.8 | 6661.61
PRC 3352525PF7901 | 2025-03-21 | Inv. 101174.015-PC06 |  | 16497.41 | 1571.86 | 11407.66 | 5089.75
PRC 3352525PG7901 | 2025-04-14 | Inv. 101174.015-PC07 Final | -3941.5 | 12555.91 | 1148.25 | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  | Totals: | 12555.91 |  | 12555.91 |  | 0 | FINAL
|  | CM Services: | 12155.91 |  | 12155.91 |  | 0
|  | Reimbursables: | 400 |  | 400 |  | 0
|  | Total: | 12555.91 |  | 12555.91 |  | 0

## #9459.00 PM TIME
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910G
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14400 | 14400 |  |  | 14400
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 14400 | 37.89 | 37.89 | 14362.11
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 14400 | 194.4 | 232.29 | 14167.71
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 14400 | 118.33 | 350.62 | 14049.38
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 14400 | 1051.4 | 1402.02 | 12997.98
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 14400 | 210.36 | 1612.38 | 12787.62
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 14400 | 1404.9 | 3017.28 | 11382.72
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 14400 | 225.58 | 3242.86 | 11157.14
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 14400 | 1498.1 | 4740.96 | 9659.04
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 14400 | 41.07 | 4782.03 | 9617.97
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 14400 | 410.1 | 5192.13 | 9207.87
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 14400 | 183.79 | 5375.92 | 9024.08
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 14400 | 1960.8 | 7336.72 | 7063.28
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 14400 | 208.95 | 7545.67 | 6854.33
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 14400 | 903.4 | 8449.07 | 5950.93
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 14400 | 95.32 | 8544.39 | 5855.61
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 14400 | 680.5 | 9224.89 | 5175.11
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 14400 | 111.22 | 9336.11 | 5063.89
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 14400 | 761.3 | 10097.41 | 4302.59
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 14400 | 11.96 | 10109.37 | 4290.63
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 14400 | 312.2 | 10421.57 | 3978.43
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 14400 | 15.61 | 10437.18 | 3962.82
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 14400 | 122.1 | 10559.28 | 3840.72
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 14400 | 28.4 | 10587.68 | 3812.32
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 14400 | 313.7 | 10901.38 | 3498.62
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 14400 | 43.82 | 10945.2 | 3454.8
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 14400 | 337.3 | 11282.5 | 3117.5
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 14400 | 108.05 | 11390.55 | 3009.45
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 14400 | 553.6 | 11944.15 | 2455.85
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 14400 | 31.84 | 11975.99 | 2424.01
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 14400 | 367.3 | 12343.29 | 2056.71
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 14400 | 135.72 | 12479.01 | 1920.99
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 14400 | 864.5 | 13343.51 | 1056.49
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 14400 | 42.79 | 13386.3 | 1013.7
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 14400 | 486.6 | 13872.9 | 527.1
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 14400 | 7.39 | 13880.29 | 519.71
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 14400 | 90.2 | 13970.49 | 429.51
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 14400 | 22.73 | 13993.22 | 406.78
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 14400 | 260.8 | 14254.02 | 145.98
[5 empty] | 14400 |  | 14254.02 | 145.98
[5 empty] | 14400 |  | 14254.02 | 145.98
[5 empty] | 14400 |  | 14254.02 | 145.98
|  |  | Totals: | 14400 |  | 14254.02 |  | 145.98
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Kleene, Jennifer Wed, Feb 19, 3:56 PM (14 hours ago) to me Please increase the PM Time by $5,000.00 Regards, Jennifer Jennifer Kleene Owner’s Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-822-8197 mobile Jennifer.Kleene@iowa.gov https://das.iowa.gov On Wed, Feb 19, 2025 at 10:21 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Jennifer We are negative on PM Time for 9459.00 for MM25 after posting the January billing file Can we increase the budget? Currently -136.72 Kleene, Jennifer 9:34 AM (6 minutes ago) to Geoff, me Please increase the DAS Cost budgets as follows: DA23 9277.00 Increase budget by $1,000.00 MM23 9268.01 Increase budget by $429.61 MM25 9459.00 Increase budget by $2,200.00 Regards, JenniferKleene, Jennifer 9:34 AM (6 minutes ago) to Geoff, me Please increase the DAS Cost budgets as follows: DA23 9277.00 Increase budget by $1,000.00 MM23 9268.01 Increase budget by $429.61 MM25 9459.00 Increase budget by $2,200.00 Regards, Jennifer

## #9459.00 Misc
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  |  | Major Program 4F03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 200
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525024908 | 2025-01-24 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2624735 | 1356.25 | 1356.25
PRC 33525088900 | 2025-03-28 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1548 | 200 | 1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
|  |  |  | Totals: |  | 1556.25

## #9459.00 IMEG Corporation
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
IMEG Corporation |  |  | Vendor: 00003224175
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525310907 | 2024-11-05 | PO Procore | 20564 | 20564 |  |  | 20564
PRC 3352531PA0907 | 2025-01-03 | Inv. 9459.00-01 |  | 20564 | 6518 | 6518 | 14046
PRC 3352531PB0907 | 2025-03-05 | Inv. 24006792.00-2 |  | 20564 | 7606 | 14124 | 6440
PRC 3352531PC0907 | 2025-04-23 | Inv. 24006792.00-3 |  | 20564 | 644 | 14768 | 5796
PRC 3352531PD0907 | 2025-04-17 | Inv. 24006792.00-4 |  | 20564 | 966 | 15734 | 4830 | FY25
PO 33526310907 | 2025-07-29 | Roll to FY26 | 0 | 20564 |  | 15734 | 4830
PRC 3352631PE0907 | 2025-11-20 | Inv. 24006792.00-5 |  | 20564 | 966 | 16700 | 3864
PRC 3352631PF0907 | 2026-02-17 | Inv. 9459.00-06 - Final | -1600 | 18964 | 2264 | 18964 | 0
|  |  |  | 18964 |  | 18964 | 0
|  |  |  | 18964 |  | 18964 | 0
|  |  |  | 18964 |  | 18964 | 0
|  |  |  | 18964 |  | 18964 | 0
|  |  |  | 18964 |  | 18964 | 0
|  | Totals: | 18964 |  | 18964 |  | 0 | FINAL
|  | Construction Docs | 13036 |  | 13036 |  | 0
|  | Bidding/Negotiation Assistance | 1088 |  | 1088 |  | 0
|  | Construction Phase | 4840 |  | 4840 |  | 0
|  | Total: | 18964 |  | 18964 |  | 0

## #9459.00 McGough Construction 2
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525076901 | 2025-03-17 | PO Procore | 19869.58 | 19869.58 |  |  | 19869.58
PRC 3352507PA6901 | 2025-04-14 | Inv. 101174.015CA01 |  | 19869.58 | 205.52 | 205.52 | 19664.06
PRC 3352507PB6901 | 2025-05-09 | Inv. 101174.015CA02 |  | 19869.58 | 2513.39 | 2718.91 | 17150.67
PRC 3352507PC6901 | 2025-06-11 | Inv. 101174.015CA03 |  | 19869.58 | 383.72 | 3102.63 | 16766.95
PRC 3352507PD6901 | 2025-07-14 | Inv. 101174.015-CA04 |  | 19869.58 | 895.74 | 3998.37 | 15871.21 | FY25
PO 33526076901 | 2025-07-29 | Roll to FY26 | 0 | 19869.58 |  | 3998.37 | 15871.21
PRC 3352607PE6901 | 2025-08-14 | Inv. 101174.015-CA05 |  | 19869.58 | 672.99 | 4671.36 | 15198.22
PRC 3352607PF6901 | 2025-09-15 | Inv. 101174.015-CA06 |  | 19869.58 | 1008.59 | 5679.95 | 14189.63
PRC 3352607PG6901 | 2025-10-15 | Inv. 101174.015-CA07 |  | 19869.58 | 3744.2 | 9424.15 | 10445.43
PRC 3352607PH6901 | 2025-11-13 | Inv. 101174.015-CA08 |  | 19869.58 | 1991.46 | 11415.61 | 8453.97
PRC 3352607PI6901 | 2025-12-10 | Inv. 101174.015-CA09 |  | 19869.58 | 1591.5 | 13007.11 | 6862.47
PRC 3352607PJ6901 | 2026-01-09 | Inv. 101174.015-CA10 |  | 19869.58 | 876.72 | 13883.83 | 5985.75
PRC 3352607PK6901 | 2026-02-16 | Inv. 101174.015-CA11 |  | 19869.58 | 671.2 | 14555.03 | 5314.55
PRC 3352607PL6901 | 2026-03-03 | Inv. 101174.015-CA12 - CA FINAL | -5081.71 | 14787.87 | 232.84 | 14787.87 | 0
|  |  |  | 14787.87 |  | 14787.87 | 0
|  |  |  | 14787.87 |  | 14787.87 | 0
|  | Totals: | 14787.87 |  | 14787.87 |  | 0 | FINAL
|  | CM Services | 13987.87 |  | 13987.87 |  | 0
|  | Reimbursables | 800 |  | 800 |  | 0
|  | Total: | 14787.87 |  | 14787.87 |  | 0

## #9459.00 Reliable 1
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
Reliable 1 |  |  | Vendor: 00002120637
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945900-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525076902 | 2025-03-17 | PO Procore | 188499.52 | 188499.52 |  |  | 188499.52
PRC 3352507PA6902 | 2025-06-23 | Inv. 9459.00-01 |  | 188499.52 | 4543.85 | 4543.85 | 183955.67 | 239.15
PRC 3352507PB6902 | 2025-07-03 | Inv. 9459.00-02 |  | 188499.52 | 55693.75 | 60237.6 | 128261.92 | 3170.4
PRC 3352507PC6902 | 2025-08-04 | Inv. 9459.00-03 |  | 188499.52 | 15075 | 75312.6 | 113186.92 | 3963.82 | FY25
PO 33526076906 | 2025-08-07 | Roll to FY26 | 0 | 188499.52 |  | 75312.6 | 113186.92
PO 33526076906 | 2025-08-25 | CO #1(No Cost CO) | 0 | 188499.52 |  | 75312.6 | 113186.92
PRC 3352607PD6906 | 2025-09-12 | Inv. 9459.00-04 |  | 188499.52 | 5391.25 | 80703.85 | 107795.67 | 4247.57
PRC 3352607PE6906 | 2025-10-06 | Inv. 9459.00-05 |  | 188499.52 | 57729.32 | 138433.17 | 50066.35 | 7285.96
PO 33526076906 | 2025-10-30 | CO #2(No Cost CO) | 0 | 188499.52 |  | 138433.17 | 50066.35
PRC 3352607PF6906 | 2025-11-04 | Inv. 9459.00-06 |  | 188499.52 | 34369.34 | 172802.51 | 15697.01 | 9094.87
PRC 3352607PG6906 | 2026-02-06 | Inv. 9459.00-07 |  | 188499.52 | 6272.02 | 179074.53 | 9424.99 | 9424.99
PRC 3352607PH6906 | 2026-02-12 | Inv. 9459.00-Retainage |  | 188499.52 | 9424.99 | 188499.52 | -1.2733e-11
|  |  |  | 188499.52 |  | 188499.52 | -1.2733e-11
|  | Totals: | 188499.52 |  | 188499.52 |  | 0 | FINAL

## RECAP #9460.00
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
| Program code 946000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1255000
C | Boyd Jones |  | 18622.46 | 18622.46 | 0
| PM TIME |  | 35000 | 27417.18 | 7582.82
| Misc. |  | 16669.63 | 16669.63 | 0
| Genesis Architectural |  | 19400 | 14460 | 4940
| R3 Commercial Roofing |  | 927636.88 | 717706.74 | 209930.14
| Boyd Jones (2) |  | 113072.57 | 69590.54 | 43482.03
| Total Project Cost | 1255000 | 1130401.54 | 864466.55 | 265934.99 | 124598.46

## #9460.00 Boyd Jones
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525310906 | 2024-11-05 | PO Procore | 21740.56 | 21740.56 |  |  | 21740.56
PRC 3352531PA0906 | 2024-11-06 | Inv. 9460.00-01 |  | 21740.56 | 4662.66 | 4662.66 | 17077.9
PRC 3352531PB0906 | 2024-12-13 | Inv. 9460.00-02 |  | 21740.56 | 2938.78 | 7601.44 | 14139.12
PRC 3352531PC0906 | 2025-01-10 | Inv. 9460.00-03 |  | 21740.56 | 4246 | 11847.44 | 9893.12
PRC 3352531PD0906 | 2025-02-06 | Inv. 9460.00-04 |  | 21740.56 | 5061.83 | 16909.27 | 4831.29
PRC 3352531PE0906 | 2025-03-11 | Inv. 9460.00-05 - FINAL | -3118.1 | 18622.46 | 1713.19 | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  | Totals: | 18622.46 |  | 18622.46 |  | 0 | FINAL
|  | CM Services | 18450.46 |  | 18450.46 |  | 0
|  | Reimbursables | 172 |  | 172 |  | 0
|  | Total: | 18622.46 |  | 18622.46 |  | 0

## #9460.00 PM TIME
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910H
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 35000 | 35000 |  |  | 35000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 35000 | 42.67 | 42.67 | 34957.33
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 35000 | 216.8 | 259.47 | 34740.53
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 35000 | 84.24 | 343.71 | 34656.29
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 35000 | 747 | 1090.71 | 33909.29
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 35000 | 175.37 | 1266.08 | 33733.92
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 35000 | 1169.7 | 2435.78 | 32564.22
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 35000 | 275.61 | 2711.39 | 32288.61
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 35000 | 1828.1 | 4539.49 | 30460.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 35000 | 116.72 | 4656.21 | 30343.79
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 35000 | 1168.8 | 5825.01 | 29174.99
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 35000 | 165.51 | 5990.52 | 29009.48
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 35000 | 1766.2 | 7756.72 | 27243.28
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 35000 | 351.34 | 8108.06 | 26891.94
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 35000 | 1517.9 | 9625.96 | 25374.04
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 35000 | 159.42 | 9785.38 | 25214.62
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 35000 | 1142.2 | 10927.58 | 24072.42
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 35000 | 143 | 11070.58 | 23929.42
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 35000 | 983.4 | 12053.98 | 22946.02
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 35000 | 88.65 | 12142.63 | 22857.37
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 35000 | 692.3 | 12834.93 | 22165.07
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 35000 | 112.37 | 12947.3 | 22052.7
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 35000 | 873.9 | 13821.2 | 21178.8
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 35000 | 118.15 | 13939.35 | 21060.65
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 35000 | 1308.6 | 15247.95 | 19752.05
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 35000 | 172.54 | 15420.49 | 19579.51
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 35000 | 1337.3 | 16757.79 | 18242.21
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 35000 | 373.4 | 17131.19 | 17868.81
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 35000 | 1949.6 | 19080.79 | 15919.21
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 35000 | 328.56 | 19409.35 | 15590.65
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 35000 | 3263.5 | 22672.85 | 12327.15
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 35000 | 210.3 | 22883.15 | 12116.85
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 35000 | 1341.9 | 24225.05 | 10774.95
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 35000 | 173.9 | 24398.95 | 10601.05
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 35000 | 1969.4 | 26368.35 | 8631.65
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 35000 | 32.85 | 26401.2 | 8598.8
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 35000 | 405.7 | 26806.9 | 8193.1
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 35000 | 48.78 | 26855.68 | 8144.32
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 35000 | 561.5 | 27417.18 | 7582.82
[5 empty] | 35000 |  | 27417.18 | 7582.82
[5 empty] | 35000 |  | 27417.18 | 7582.82
[5 empty] | 35000 |  | 27417.18 | 7582.82
|  |  | Totals: | 35000 |  | 27417.18 |  | 7582.82

## #9460.00 Misc
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 174
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525070905 | 2025-03-11 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1522 | 219.86 | 219.86
CDE 33526034912 | 2026-02-04 | 9500 | CNST | Newton Correctional Facility V#(00000024500) | Inv. 9460.00-01 | 16449.77 | 16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
16669.63
|  |  |  | Totals: |  | 16669.63

## #9460.00 Genesis Architectural
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946000-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525339903 | 2024-12-03 | PO Procore | 19400 | 19400 |  |  | 19400
PRC 3352533PA9903 | 2025-01-08 | Inv. 2414-01 |  | 19400 | 7750 | 7750 | 11650
PRC 3352533PB9903 | 2025-05-05 | Inv. 2414-02 |  | 19400 | 4050 | 11800 | 7600
PRC 3352533PC9903 | 2025-07-09 | Inv. 2414-03 |  | 19400 | 912 | 12712 | 6688 | FY25
PO 33526339903 | 2025-07-29 | Roll to FY26 | 0 | 19400 |  | 12712 | 6688
PRC 3352633PD9903 | 2025-12-03 | Inv. 2414-04 |  | 19400 | 1748 | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  |  |  | 19400 |  | 14460 | 4940
|  | Totals: | 19400 |  | 14460 |  | 4940
|  | Schematic Design Docs | 2000 |  | 2000 |  | 0
|  | Design Development Docs | 2950 |  | 2950 |  | 0
|  | Construction Docs | 5600 |  | 5600 |  | 0
|  | Bidding Assistance | 1250 |  | 1250 |  | 0
|  | Construction Phase | 7600 |  | 2660 |  | 4940
|  | Total: | 19400 |  | 14460 |  | 4940

## #9460.00 R3 Commercial Roofing
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
R3 Commerical Roofing |  |  | Vendor: 00003226335
Acct. Codes-0017-335-MM25-9255 |  |  | 946000-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525080907 | 2025-03-21 | PO Procore | 922000 | 922000 |  |  | 922000 |  | FY25
PO 33526080907 | 2025-07-29 | Roll to FY26 | 0 | 922000 |  | 0 | 922000
PRC 3352608PA0907 | 2025-08-06 | Inv. 9460.00-001 |  | 922000 | 551745.75 | 551745.75 | 370254.25 | 29039.25
PO 33526080907 | 2025-09-12 | CO #1 | 4520.78 | 926520.78 |  | 551745.75 | 374775.03
PRC 3352608PB0907 | 2025-11-10 | Inv. 9460.00-002 |  | 926520.78 | 165960.99 | 717706.74 | 208814.04 | 37774.04
PO 33526080907 | 2025-11-12 | CO #2 | 6878.68 | 933399.46 |  | 717706.74 | 215692.72
PO 33526080907 | 2025-11-25 | CO #3 | 3047.5 | 936446.96 |  | 717706.74 | 218740.22
PO 33526080907 | 2025-12-16 | CO #4 | -8810.08 | 927636.88 |  | 717706.74 | 209930.14
|  |  |  | 927636.88 |  | 717706.74 | 209930.14
|  |  |  | 927636.88 |  | 717706.74 | 209930.14
|  |  |  | 927636.88 |  | 717706.74 | 209930.14
|  |  |  | 927636.88 |  | 717706.74 | 209930.14
|  |  |  | 927636.88 |  | 717706.74 | 209930.14
|  | Totals: | 927636.88 |  | 717706.74 |  | 209930.14

## #9460.00 Boyd Jones (2)
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | CA MA #RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525100902 | 2025-04-10 | PO Procore | 91055.44 | 91055.44 |  |  | 91055.44
PRC 3352510PA0902 | 2025-05-08 | Inv. 9460.00-001 |  | 91055.44 | 1478.4 | 1478.4 | 89577.04
PRC 3352510PB0902 | 2025-06-24 | Inv. 9460.00-002 |  | 91055.44 | 381.33 | 1859.73 | 89195.71
PRC 3352510PC0902 | 2025-07-10 | Inv. 9460.00-003 |  | 91055.44 | 1685.59 | 3545.32 | 87510.12 | FY25
PO 33526100902 | 2025-07-29 | Roll to FY26 | 0 | 91055.44 |  | 3545.32 | 87510.12
PRC 3352610PD0902 | 2025-08-13 | Inv. 9460.00-004 |  | 91055.44 | 10706.82 | 14252.14 | 76803.3
PRC 3352610PE0902 | 2025-09-12 | Inv. 9460.00-005 |  | 91055.44 | 6389.81 | 20641.95 | 70413.49
PRC 3352610PF0902 | 2025-10-07 | Inv. 9460.00-006 |  | 91055.44 | 12329.91 | 32971.86 | 58083.58
PRC 3352610PG0902 | 2025-11-06 | Inv. 9460.00-007 |  | 91055.44 | 24486.68 | 57458.54 | 33596.9
PRC 3352610PH0902 | 2025-12-11 | Inv. 9460.00-008 |  | 91055.44 | 2305 | 59763.54 | 31291.9
PO 33526100902 | 2025-12-29 | CO #1 | 22017.13 | 113072.57 |  | 59763.54 | 53309.03
PRC 3352610PI0902 | 2026-01-12 | Inv. 9460.00-009 |  | 113072.57 | 7560.68 | 67324.22 | 45748.35
PRC 3352610PJ0902 | 2026-02-06 | Inv. 9460.00-010 |  | 113072.57 | 971.67 | 68295.89 | 44776.68
PRC 3352610PK0902 | 2026-03-16 | Inv. 9460.00-011 |  | 113072.57 | 1294.65 | 69590.54 | 43482.03
|  |  |  | 113072.57 |  | 69590.54 | 43482.03
|  |  |  | 113072.57 |  | 69590.54 | 43482.03
|  | Totals: | 113072.57 |  | 69590.54 |  | 43482.03
|  | CM Services | 44009.44 |  | 44009.44 |  | 0
|  | Reimbursables | 946 |  | 913.82 |  | 32.18
|  | Fee | 46100 |  | 14982.5 |  | 31117.5
|  | CO #1 | 22017.13 |  | 9684.78 |  | 12332.35
|  | Total: | 113072.57 |  | 69590.54 |  | 43482.03
Vendor used Inv. 9460.00-0X in previous tab, please use 9460.00-00X

## RECAP #9462.00
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
| Program code 946200 |  |  | Major Program 3G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 610000
C | Samuels Group |  | 32155.43 | 32155.43 | 0
| PM TIME |  | 20000 | 7114.15 | 12885.85
| Misc. |  | 300 | 300 | 0
| Snyder & Associates |  | 82901 | 68197 | 14704
| Samuels Group(2) |  | 73006.57 | 2835.52 | 70171.05
| Big River Maintenance |  | 360021 | 0 | 360021
| Total Project Cost | 610000 | 568384 | 110602.1 | 457781.9 | 41616

## #9462.00 Samuels Group
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525063900 | 2025-03-05 | PO Procore | 29270.96 | 29270.96 |  |  | 29270.96
PRC 3352506PA3900 | 2025-04-08 | Inv. 7761.01946200 |  | 29270.96 | 990.18 | 990.18 | 28280.78
PRC 3352506PB3900 | 2025-05-12 | Inv. 7761.02946200 |  | 29270.96 | 1998.43 | 2988.61 | 26282.35
PO 33525063900 | 2025-06-10 | CO #1 | 3000 | 32270.96 |  | 2988.61 | 29282.35
PRC 3352506PC3900 | 2025-06-10 | Inv. 7761.03946200 |  | 32270.96 | 4620.64 | 7609.25 | 24661.71
PRC 3352506PD3900 | 2025-07-14 | Inv. 7761.04946200 |  | 32270.96 | 2343.16 | 9952.41 | 22318.55 | FY25
PO 33526063900 | 2025-07-29 | Roll to FY26 | 0 | 32270.96 |  | 9952.41 | 22318.55
PRC 3352606PE3900 | 2025-08-14 | Inv. 7761.05946200 |  | 32270.96 | 1586.31 | 11538.72 | 20732.24
PRC 3352606PF3900 | 2025-09-15 | Inv. 7761.06946200 |  | 32270.96 | 7666.28 | 19205 | 13065.96
PRC 3352606PG3900 | 2025-10-08 | Inv. 7761.07946200 |  | 32270.96 | 4217.7 | 23422.7 | 8848.26
PRC 3352606PH3900 | 2025-11-18 | Inv. 7761.08946200 |  | 32270.96 | 421.68 | 23844.38 | 8426.58
PRC 3352606PI3900 | 2025-12-04 | Inv. 7761.09946200 |  | 32270.96 | 1179.78 | 25024.16 | 7246.8
PRC 3352606PJ3900 | 2026-01-09 | Inv. 7761.10946200 |  | 32270.96 | 4928.61 | 29952.77 | 2318.19
PRC 3352606PK3900 | 2026-02-03 | Inv. 7761.11946200-FINAL | -115.53 | 32155.43 | 2202.66 | 32155.43 | -1.1653e-12
|  |  |  | 32155.43 |  | 32155.43 | -1.1653e-12
|  |  |  | 32155.43 |  | 32155.43 | -1.1653e-12
|  | Totals: | 32155.43 |  | 32155.43 |  | 0 | FINAL
|  | CM Services | 24263.43 |  | 24263.43 |  | 0
|  | Reimbursables | 5000 |  | 5000 |  | 0
|  | CO #1 | 2892 |  | 2892 |  | 0
|  | Total: | 32155.43 |  | 32155.43 |  | 0

## #9462.00 PM TIME
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  |  | Major Program 3G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910Q
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 8.72 | 8.72 | 19991.28
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 85.2 | 93.92 | 19906.08
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 18.56 | 112.48 | 19887.52
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 197.9 | 310.38 | 19689.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 18.54 | 328.92 | 19671.08
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 79.2 | 408.12 | 19591.88
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 146.21 | 554.33 | 19445.67
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 1046.7 | 1601.03 | 18398.97
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 70.72 | 1671.75 | 18328.25
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 483 | 2154.75 | 17845.25
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 116.93 | 2271.68 | 17728.32
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 913.8 | 3185.48 | 16814.52
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 20000 | 31.65 | 3217.13 | 16782.87
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 20000 | 246.4 | 3463.53 | 16536.47
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 14.21 | 3477.74 | 16522.26
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 154.1 | 3631.84 | 16368.16
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 73.89 | 3705.73 | 16294.27
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 569.1 | 4274.83 | 15725.17
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 66.07 | 4340.9 | 15659.1
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 340.8 | 4681.7 | 15318.3
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 60.38 | 4742.08 | 15257.92
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 598.9 | 5340.98 | 14659.02
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 6.95 | 5347.93 | 14652.07
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 44.3 | 5392.23 | 14607.77
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 16.43 | 5408.66 | 14591.34
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 185.9 | 5594.56 | 14405.44
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 70.68 | 5665.24 | 14334.76
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 875.4 | 6540.64 | 13459.36
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 45.91 | 6586.55 | 13413.45
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 527.6 | 7114.15 | 12885.85
[5 empty] | 20000 |  | 7114.15 | 12885.85
[5 empty] | 20000 |  | 7114.15 | 12885.85
[5 empty] | 20000 |  | 7114.15 | 12885.85
|  |  | Totals: | 20000 |  | 7114.15 |  | 12885.85

## #9462.00 Misc
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  |  | Major Program 3G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 231A
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526021904 | 2026-01-21 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV055171 | 300 | 300
300
300
300
300
300
300
300
300
300
300
300
|  |  |  | Totals: |  | 300

## #9462.00 Synder & Associates
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Synder & Associates |  |  | Vendor: 00002119810
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946200-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525115907 | 2025-04-25 | PO Procore | 82901 | 82901 |  |  | 82901
PRC 3352511PA5907 | 2025-06-10 | Inv. 9462.00-01 |  | 82901 | 4214.6 | 4214.6 | 78686.4
PRC 3352511PB5907 | 2025-07-14 | Inv. 9462.00-02 |  | 82901 | 21092.4 | 25307 | 57594 | FY25
PO 33526115907 | 2025-07-29 | Roll to FY26 | 0 | 82901 |  | 25307 | 57594
PRC 3352611PC5907 | 2025-09-29 | Inv. 9462.00-03 |  | 82901 | 9574.8 | 34881.8 | 48019.2
PRC 3352611PD5907 | 2025-10-27 | Inv. 9462.00-04 |  | 82901 | 12267.2 | 47149 | 35752
PRC 3352611PE5907 | 2025-12-29 | Inv. 9462.00-05 |  | 82901 | 11390 | 58539 | 24362
PRC 3352611PF5907 | 2026-03-03 | Inv. 9462.00-06 |  | 82901 | 9658 | 68197 | 14704
|  |  |  | 82901 |  | 68197 | 14704
|  |  |  | 82901 |  | 68197 | 14704
|  |  |  | 82901 |  | 68197 | 14704
|  |  |  | 82901 |  | 68197 | 14704
|  |  |  | 82901 |  | 68197 | 14704
|  | Totals: | 82901 |  | 68197 |  | 14704
|  | Design 50% | 24700 |  | 24700 |  | 0
|  | Design 95% | 14432 |  | 14432 |  | 0
|  | Design 100% | 11390 |  | 11390 |  | 0
|  | Bidding | 9658 |  | 9658 |  | 0
|  | Construction Admin | 14704 |  |  |  | 14704
|  | Survey | 5017 |  | 5017 |  | 0
|  | Boundry Survey of Parking Lot | 3000 |  | 3000 |  | 0
|  | Total: | 82901 |  | 68197 |  | 14704

## #9462.00 Samuels Group (2)
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Samuels Group(2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030911 | 2026-01-30 | PO Procore | 73006.57 | 73006.57 |  |  | 73006.57
PRC 3352603PA0911 | 2026-02-03 | Inv. 7855.51946200 |  | 73006.57 | 1225.62 | 1225.62 | 71780.95
PRC 3352603PB0911 | 2026-03-03 | Inv. 7855.52946200 |  | 73006.57 | 1609.9 | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  |  |  | 73006.57 |  | 2835.52 | 70171.05
|  | Totals: | 73006.57 |  | 2835.52 |  | 70171.05
|  | CM Services | 69006.57 |  | 2835.52 |  | 66171.05
|  | Reimbursables | 4000 |  |  |  | 4000
|  | Total: | 73006.57 |  | 2835.52 |  | 70171.05

## #9462.00 Big River Maintenance
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Big River Maintenance |  |  | Vendor: 00003235051
Acct. Codes-0017-335-MM25-9255 |  |  | RFB946200-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526033915 | 2026-02-03 | PO Procore | 360021 | 360021 |  |  | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  |  |  | 360021 |  | 0 | 360021
|  | Totals: | 360021 |  | 0 |  | 360021

## RECAP #9463.00
HHS WRC Birches Window Replacement
Project # 9463.00
| Program code 946300 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1200000
C | Story Construction |  | 11467.23 | 11467.23 | 0
| PM TIME |  | 10000 | 8910.55 | 1089.45
| Misc. |  | 311.79 | 311.79 | 0
| Genesis Architectural Design |  | 27700 | 20900 | 6800
| Story Construction (2) |  | 92825.18 | 2049.79 | 90775.39
| Voss Services |  | 744278 | 0 | 744278
| Controlled Asbestos |  | 173800 | 21576.68 | 152223.32
| Total Project Cost | 1200000 | 1060382.2 | 65216.04 | 995166.16 | 139617.8

## #9463.00 Story Construction
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525016903 | 2025-01-16 | PO Procore | 18402.96 | 18402.96 |  |  | 18402.96
PRC 3352501PA6903 | 2025-03-21 | Inv. 34771 |  | 18402.96 | 3232.63 | 3232.63 | 15170.33
PRC 3352501PB6903 | 2025-04-15 | Inv. 34804 |  | 18402.96 | 919.13 | 4151.76 | 14251.2
PRC 3352501PC6903 | 2025-05-15 | Inv. 34840 |  | 18402.96 | 701.11 | 4852.87 | 13550.09
PRC 3352501PD6903 | 2025-06-13 | Inv. 34867 |  | 18402.96 | 1078.7 | 5931.57 | 12471.39
PRC 3352501PE6903 | 2025-07-17 | Inv. 34907 |  | 18402.96 | 3401.9 | 9333.47 | 9069.49 | FY25
PO 33526016903 | 2025-07-29 | Roll to FY26 | 0 | 18402.96 |  | 9333.47 | 9069.49
PRC 3352601PF6903 | 2025-08-15 | Inv. 34947 FINAL | -6935.73 | 11467.23 | 2133.76 | 11467.23 | 0
|  |  |  | 11467.23 |  | 11467.23 | 0
|  |  |  | 11467.23 |  | 11467.23 | 0
|  |  |  | 11467.23 |  | 11467.23 | 0
|  |  |  | 11467.23 |  | 11467.23 | 0
|  |  |  | 11467.23 |  | 11467.23 | 0
|  | Totals: | 11467.23 |  | 11467.23 |  | 0 | FINAL
|  | CM Services | 11437.73 |  | 11437.73 |  | 0
|  | Reimbursables | 29.5 |  | 29.5 |  | 0
|  | Total: | 11467.23 |  | 11467.23 |  | 0

## #9463.00 PM TIME
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910R
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 9.14 | 9.14 | 9990.86
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 91.2 | 100.34 | 9899.66
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 105.89 | 206.23 | 9793.77
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 1126.6 | 1332.83 | 8667.17
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 167.1 | 1499.93 | 8500.07
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 722.6 | 2222.53 | 7777.47
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 95.32 | 2317.85 | 7682.15
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 680.5 | 2998.35 | 7001.65
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10000 | 122.61 | 3120.96 | 6879.04
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10000 | 842.1 | 3963.06 | 6036.94
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 10000 | 106.1 | 4069.16 | 5930.84
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 10000 | 834.7 | 4903.86 | 5096.14
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 10000 | 109.7 | 5013.56 | 4986.44
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 10000 | 855.4 | 5868.96 | 4131.04
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 10000 | 80.38 | 5949.34 | 4050.66
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 10000 | 877.7 | 6827.04 | 3172.96
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 10000 | 119.36 | 6946.4 | 3053.6
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 10000 | 916.8 | 7863.2 | 2136.8
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10000 | 64.41 | 7927.61 | 2072.39
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10000 | 332.6 | 8260.21 | 1739.79
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 27.32 | 8287.53 | 1712.47
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 323 | 8610.53 | 1389.47
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | 19.17 | 8629.7 | 1370.3
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 122.5 | 8752.2 | 1247.8
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10000 | 12.35 | 8764.55 | 1235.45
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10000 | 146 | 8910.55 | 1089.45
[5 empty] | 10000 |  | 8910.55 | 1089.45
[5 empty] | 10000 |  | 8910.55 | 1089.45
[5 empty] | 10000 |  | 8910.55 | 1089.45
|  |  | Totals: | 10000 |  | 8910.55 |  | 1089.45

## #9463.00 Misc
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 564
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526225908 | 2025-08-14 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL2011 | 311.79 | 311.79
311.79
311.79
311.79
311.79
311.79
311.79
311.79
311.79
311.79
311.79
311.79
|  |  |  | Totals: |  | 311.79

## #9463.00 Genesis Architectural
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525060902 | 2025-02-28 | PO Procore | 27700 | 27700 |  |  | 27700
PRC 3352506PA0902 | 2025-06-12 | Inv. 2501-01 |  | 27700 | 17200 | 17200 | 10500
PRC 3352506PB0902 | 2025-07-03 | Inv. 2501-02 |  | 27700 | 1000 | 18200 | 9500 | FY25
PO 33526060902 | 2025-07-29 | Roll to FY26 | 0 | 27700 |  | 18200 | 9500
PRC 3352606PC0902 | 2025-12-03 | Inv. 2501-03 |  | 27700 | 2700 | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  |  |  | 27700 |  | 20900 | 6800
|  | Totals: | 27700 |  | 20900 |  | 6800
|  | Design Development Docs | 8200 |  | 8200 |  | 0
|  | Construction Docs | 10000 |  | 10000 |  | 0
|  | Bid Assistance | 1500 |  | 1500 |  | 0
|  | Construction Phase | 8000 |  | 1200 |  | 6800
|  | Total: | 27700 |  | 20900 |  | 6800

## #9463.00 Story Construction (2)
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Story Construction(2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526216902 | 2025-08-04 | PO Procore | 92825.18 | 92825.18 |  |  | 92825.18
PRC 3352621PA6902 | 2025-09-15 | Inv. 34978 |  | 92825.18 | 754.47 | 754.47 | 92070.71
PRC 3352621PB6902 | 2025-10-16 | Inv. 35014 |  | 92825.18 | 646.63 | 1401.1 | 91424.08
PRC 3352621PC6902 | 2025-11-14 | Inv. 35046 |  | 92825.18 | 648.69 | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  |  |  | 92825.18 |  | 2049.79 | 90775.39
|  | Totals: | 92825.18 |  | 2049.79 |  | 90775.39
|  | CM Services | 46478.78 |  | 2049.79 |  | 44428.99
|  | Reimbursables | 442.5 |  |  |  | 442.5
|  | Voss Fee | 37213.9 |  |  |  | 37213.9
|  | CA Fee | 8690 |  |  |  | 8690
|  | Total: | 92825.18 |  | 2049.79 |  | 90775.39

## #9463.00 Voss Services
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Voss Services |  |  | Vendor: 00003179688
Acct. Codes-0017-335-MM25-9255 |  |  | RFB946300-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526231900 | 2025-08-19 | PO Procore | 744278 | 744278 |  |  | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  |  |  | 744278 |  | 0 | 744278
|  | Totals: | 744278 |  | 0 |  | 744278

## #9463.00 Controlled Asbestos
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM25-9255 |  |  | RFB946300-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526231901 | 2025-08-19 | PO Procore | 173800 | 173800 |  |  | 173800
PRC 3352623PA1901 | 2025-09-25 | Inv. 0010978 |  | 173800 | 4538.63 | 4538.63 | 169261.37 | 140.37
PRC 3352623PB1901 | 2025-11-13 | Inv. 0010996 |  | 173800 | 8220.75 | 12759.38 | 161040.62 | 394.62
PRC 3352623PC1901 | 2025-12-15 | Inv. 0011010 |  | 173800 | 8817.3 | 21576.68 | 152223.32 | 667.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  |  |  | 173800 |  | 21576.68 | 152223.32
|  | Totals: | 173800 |  | 21576.68 |  | 152223.32
FY26 Retainage- 3%

## RECAP #9474.00
HHS IMHI Boiler #3 Replacement
Project # 9474.00
| Program code 947400 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1500000
C | Samuels Group |  | 13409.57 | 13409.57 | 0
| PM TIME |  | 20000 | 13130.26 | 6869.74
| Misc. |  | 3600 | 3600 | 0
| KCL Engineering |  | 45100 | 35220 | 9880
C | Story Construction |  | 16074.04 | 16074.04 | 0
| Story Construction(2) |  | 107462.12 | 2719.54 | 104742.58
| S&S Plumbing |  | 942312 | 0 | 942312
| Total Project Cost | 1500000 | 1147957.73 | 84153.41 | 1063804.32 | 352042.27

## #9474.00 Samuels Group
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Oliver S |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525120900 | 2025-04-30 | PO Procore | 39296.56 | 39296.56 |  |  | 39296.56
PRC 3352512PA0900 | 2025-06-16 | Inv. 7774.01 PC |  | 39296.56 | 2253.05 | 2253.05 | 37043.51
PRC 3352512PB0900 | 2025-07-07 | Inv. 7774.02 PC |  | 39296.56 | 4801.7 | 7054.75 | 32241.81 | FY25
PO 33526120900 | 2025-07-29 | Roll to FY26 | 0 | 39296.56 |  | 7054.75 | 32241.81
PRC 3352612PC0900 | 2025-09-15 | Inv. 7774.03 PC |  | 39296.56 | 3378.96 | 10433.71 | 28862.85
PRC 3352612PD0900 | 2025-10-17 | Inv. 7774.04 PC Final | -25886.99 | 13409.57 | 2975.86 | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  |  |  | 13409.57 |  | 13409.57 | 0
|  | Totals: | 13409.57 |  | 13409.57 |  | 0 | FINAL
|  | CM Services | 13254.57 |  | 13254.57 |  | 0
|  | Reimbursables | 155 |  | 155 |  | 0
|  | Total: | 13409.57 |  | 13409.57 |  | 0

## #9474.00 PM TIME
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 732Y
Project Manager - Oliver S
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 55.25 | 55.25 | 19944.75
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 380.4 | 435.65 | 19564.35
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 46.86 | 482.51 | 19517.49
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 365.5 | 848.01 | 19151.99
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 20000 | 31.65 | 879.66 | 19120.34
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 20000 | 246.4 | 1126.06 | 18873.94
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 63.31 | 1189.37 | 18810.63
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 695.7 | 1885.07 | 18114.93
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 40.19 | 1925.26 | 18074.74
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 306.7 | 2231.96 | 17768.04
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 222.92 | 2454.88 | 17545.12
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 1146.6 | 3601.48 | 16398.52
CDE 33526281901 | 2025-10-07 | 2507 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 20000 | 274.14 | 3875.62 | 16124.38
CDE 33526281901 | 2025-10-07 | 9500 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 20000 | 1410.3 | 5285.92 | 14714.08
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 234.68 | 5520.6 | 14479.4
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 2328.8 | 7849.4 | 12150.6
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 93.75 | 7943.15 | 12056.85
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 594.4 | 8537.55 | 11462.45
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 127.04 | 8664.59 | 11335.41
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 1439 | 10103.59 | 9896.41
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 110.16 | 10213.75 | 9786.25
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 1368 | 11581.75 | 8418.25
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 123.71 | 11705.46 | 8294.54
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 1424.8 | 13130.26 | 6869.74
[5 empty] | 20000 |  | 13130.26 | 6869.74
[5 empty] | 20000 |  | 13130.26 | 6869.74
[5 empty] | 20000 |  | 13130.26 | 6869.74
|  |  | Totals: | 20000 |  | 13130.26 |  | 6869.74
Note on E9: Huggins, Joni [DAS]: Changes for PM Time $Joni Elliott, Jennie May 4, 2025, 3:12 PM (15 hours ago) to me Can you please make the following change for PM time, thank you! 9388.00 - Please increase PM Time in the "Contracted" line to $15,000.00 9401.00 - Please increase PM Time in the "Contracted" line to $9,000.00 9475.00 - Please Establish a PM Time budget of $7,500.00 9474.00 - Please Establish a PM Time budget of $10,000.00 Re: December PM Time has been posted Inbox Shimp, Oliver 2:26 PM (0 minutes ago) to me Good Afternoon Joni, Sorry this one took awhile, I have taken over MM25 project 9474.00 from Jennie. Could you please add $10,000.00 from the unallocated funds to the PM time budget? Thank you, Oliver Shimp

## #9474.00 Misc
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 556
Project Manager - Oliver S
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526014911 | 2026-01-14 | 9500 | CNST | Advanced Environmental V#(00002125877) | Inv. INVOICE 12421 | 3600 | 3600
3600
3600
3600
3600
3600
3600
3600
3600
3600
3600
3600
|  |  |  | Totals: |  | 3600

## #9474.00 KCL Engineering
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM25-9260 |  |  | RFP947400-01
Project Manager - Oliver S |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526218907 | 2025-08-06 | PO Procore | 45100 | 45100 |  |  | 45100
PRC 3352621PA8907 | 2025-09-15 | Inv. 12644 |  | 45100 | 9800 | 9800 | 35300
PRC 3352621PB8907 | 2025-12-03 | Inv. 13026 |  | 45100 | 20600 | 30400 | 14700
PRC 3352621PC8907 | 2026-03-04 | Inv. 13468 |  | 45100 | 4300 | 34700 | 10400
PRC 3352621PD8907 | 2026-03-11 | Inv. 13582 |  | 45100 | 520 | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  |  |  | 45100 |  | 35220 | 9880
|  | Totals: | 45100 |  | 35220 |  | 9880
|  | Design Development Docs | 9800 |  | 9800 |  | 0
|  | Construction Documents | 20600 |  | 20600 |  | 0
|  | Bidding/Negotiation Assistance | 4300 |  | 4300 |  | 0
|  | Construction Phase | 10400 |  | 520 |  | 9880
|  | Total: | 45100 |  | 35220 |  | 9880

## #9474.00 Story Construction
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Oliver S |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526279902 | 2025-10-06 | PO Procore | 16491.8 | 16491.8 |  |  | 16491.8
PRC 3352627PA9902 | 2025-11-25 | Inv. 35049 |  | 16491.8 | 2434.46 | 2434.46 | 14057.34
PRC 3352627PB9902 | 2025-12-18 | Inv. 35079 |  | 16491.8 | 4059.54 | 6494 | 9997.8
PRC 3352627PC9902 | 2026-01-20 | Inv. 35118 |  | 16491.8 | 4599.71 | 11093.71 | 5398.09
PRC 3352627PD9902 | 2026-02-20 | Inv. 35152 FINAL | -417.76 | 16074.04 | 4980.33 | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  |  |  | 16074.04 |  | 16074.04 | -6.8212e-13
|  | Totals: | 16074.04 |  | 16074.04 |  | 0 | FINAL
|  | Preconstruction Services | 15836.04 |  | 15836.04 |  | 0
|  | Reimbursables | 238 |  | 238 |  | 0
|  | Total: | 16074.04 |  | 16074.04 |  | 0

## #9474.00 Story Construction (2)
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM25-9255 |  |  | RFP947400-01
Project Manager - Oliver S |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030912 | 2026-01-30 | PO Procore | 107462.12 | 107462.12 |  |  | 107462.12
PRC 3352603PA0912 | 2026-03-19 | Inv. 35195 |  | 107462.12 | 2719.54 | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  |  |  | 107462.12 |  | 2719.54 | 104742.58
|  | Totals: | 107462.12 |  | 2719.54 |  | 104742.58
|  | Preconstruction Services | 57133.52 |  | 2719.54 |  | 54413.98
|  | Reimbursables | 3213 |  |  |  | 3213
|  | Fees | 47115.6 |  |  |  | 47115.6
|  | Total: | 107462.12 |  | 2719.54 |  | 104742.58

## #9474.00 S&S Plumbing
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
S&S Plumbing |  |  | Vendor: 00003036947
Acct. Codes-0017-335-MM25-9255 |  |  | RFP947400-01
Project Manager - Oliver S |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526033912 | 2026-02-03 | PO Procore | 942312 | 942312 |  |  | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  |  |  | 942312 |  | 0 | 942312
|  | Totals: | 942312 |  | 0 |  | 942312

## RECAP #9520.00
DOC NCCF Perimeter Light Pole & Yard Light Replacement
Project # 9520.00
Program code 952000 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 629000
McGough Construction |  | 17128.95 | 0 | 17128.95
PM TIME |  | 12500 | 416.9 | 12083.1
Misc. |  | 0 | 0 | 0
Total Project Cost | 629000 | 29628.95 | 416.9 | 29212.05 | 599371.05

## #9520.00 McGough Construction
DOC NCCF Perimeter Light Pole & Yard Light Replacement
Project # 9520.00
Program code 952000 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526078910 | 2026-03-19 | PO Procore | 17128.95 | 17128.95 |  |  | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  |  |  | 17128.95 |  | 0 | 17128.95
|  | Totals: | 17128.95 |  | 0 |  | 17128.95
|  | CM Services | 16528.95 |  | 0 |  | 16528.95
|  | Reimbursables | 600 |  |  |  | 600
|  | Total: | 17128.95 |  | 0 |  | 17128.95

## #9520.00 PM TIME
DOC NCCF Perimeter Light Pole & Yard Light Replacement
Project # 9520.00
Program code 952000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 911K
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12500 | 12500 |  |  | 12500
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 12500 | 33.1 | 33.1 | 12466.9
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 12500 | 383.8 | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
[5 empty] | 12500 |  | 416.9 | 12083.1
|  |  | Totals: | 12500 |  | 416.9 |  | 12083.1

## #9520.00 Misc
DOC NCCF Perimeter Light Pole & Yard Light Replacement
Project # 9520.00
Program code 952000 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Jennie E |  |  |  | Shipping Code: 177
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9522.00
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 285000
Boyd Jones |  | 17982.95 | 0 | 17982.95
PM TIME |  | 6500 | 610.28 | 5889.72
Misc. |  | 0 | 0 | 0
Total Project Cost | 285000 | 24482.95 | 610.28 | 23872.67 | 260517.05

## #9522.00 Boyd Jones
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526068910 | 2026-03-09 | PO Procore | 17982.95 | 17982.95 |  |  | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  |  |  | 17982.95 |  | 0 | 17982.95
|  | Totals: | 17982.95 |  | 0 |  | 17982.95
|  | CM Services | 17907.95 |  | 0 |  | 17907.95
|  | Reimbursables | 75 |  |  |  | 75
|  | Total: | 17982.95 |  | 0 |  | 17982.95

## #9522.00 PM TIME
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 911M
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 6500 | 6500 |  |  | 6500
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 6500 | 48.78 | 48.78 | 6451.22
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 6500 | 561.5 | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
[5 empty] | 6500 |  | 610.28 | 5889.72
|  |  | Totals: | 6500 |  | 610.28 |  | 5889.72

## #9522.00 Misc
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Brad T |  |  |  | Shipping Code: 174
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9523.00
DOC NCF Misc Door Replacements
Project # 9523.00
Program code 952300 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 260000
Boyd Jones |  | 14596.92 | 0 | 14596.92
PM TIME |  | 7500 | 610.28 | 6889.72
Misc. |  | 0 | 0 | 0
Total Project Cost | 260000 | 22096.92 | 610.28 | 21486.64 | 237903.08

## #9523.00 Boyd Jones
DOC NCF Misc Door Replacements
Project # 9523.00
Program code 952300 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526068911 | 2026-03-09 | PO Procore | 14596.92 | 14596.92 |  |  | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  |  |  | 14596.92 |  | 0 | 14596.92
|  | Totals: | 14596.92 |  | 0 |  | 14596.92
|  | CM Services | 14464.92 |  | 0 |  | 14464.92
|  | Reimbursables | 132 |  |  |  | 132
|  | Total: | 14596.92 |  | 0 |  | 14596.92

## #9523.00 PM TIME
DOC NCF Misc Door Replacements
Project # 9523.00
Program code 952300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 911N
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7500 | 7500 |  |  | 7500
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 7500 | 48.78 | 48.78 | 7451.22
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 7500 | 561.5 | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
[5 empty] | 7500 |  | 610.28 | 6889.72
|  |  | Totals: | 7500 |  | 610.28 |  | 6889.72

## #9523.00 Misc
DOC NCF Misc Door Replacements
Project # 9523.00
Program code 952300 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Brad T |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9526.00
DPS P02 Parking Lot Replacement
Project # 9526.00
Program code 952600 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 260000
McGough Construction |  | 17402.32 | 0 | 17402.32
PM TIME |  | 8000 | 0 | 8000
Misc. |  | 0 | 0 | 0
Total Project Cost | 260000 | 25402.32 | 0 | 25402.32 | 234597.68

## #9526.00 McGough Construction
DPS P02 Parking Lot Replacement
Project # 9526.00
Program code 952600 |  |  | Major Program 4G01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047908 | 2026-02-16 | PO Procore | 17402.32 | 17402.32 |  |  | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  |  |  | 17402.32 |  | 0 | 17402.32
|  | Totals: | 17402.32 |  | 0 |  | 17402.32
|  | CM Services | 17264.32 |  | 0 |  | 17264.32
|  | Reimbursables | 138 |  |  |  | 138
|  | Total: | 17402.32 |  | 0 |  | 17402.32

## #9526.00 PM TIME
DPS P02 Parking Lot Replacement
Project # 9526.00
Program code 952600 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 911Q
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
|  |  | Totals: | 8000 |  | 0 |  | 8000

## #9526.00 Misc
DPS P02 Parking Lot Replacement
Project # 9526.00
Program code 952600 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - James T |  |  |  | Shipping Code: 934
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9528.00
DOC 5JD Bldg 65/66 Parking Lot Overlay
Project # 9528.00
Program code 952800 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 235000
McGough Construction |  | 13420.72 | 0 | 13420.72
PM TIME |  | 8000 | 696.64 | 7303.36
Misc. |  | 0 | 0 | 0
Total Project Cost | 235000 | 21420.72 | 696.64 | 20724.08 | 213579.28

## #9528.00 McGough Construction
DOC 5JD Bldg 65/66 Parking Lot Overlay
Project # 9528.00
Program code 952800 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047907 | 2026-02-16 | PO Procore | 13420.72 | 13420.72 |  |  | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  |  |  | 13420.72 |  | 0 | 13420.72
|  | Totals: | 13420.72 |  | 0 |  | 13420.72
|  | CM Services | 13382.22 |  | 0 |  | 13382.22
|  | Reimbursables | 38.5 |  |  |  | 38.5
|  | Total: | 13420.72 |  | 0 |  | 13420.72

## #9528.00 PM TIME
DOC 5JD Bldg 65/66 Parking Lot Overlay
Project # 9528.00
Program code 952800 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 911S
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 8000 | 55.84 | 55.84 | 7944.16
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 8000 | 640.8 | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
[5 empty] | 8000 |  | 696.64 | 7303.36
|  |  | Totals: | 8000 |  | 696.64 |  | 7303.36

## #9528.00 Misc
DOC 5JD Bldg 65/66 Parking Lot Overlay
Project # 9528.00
Program code 952800 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - James T |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #XXXX.XX
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM25
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM25-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  | 0 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0