## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Additional Funds | 22000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22000000
| . | Less: Total Assigned |  | 20146050
|  | Total Unassigned / Unallocated |  | 1853950
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9997.25 | Project Management Time | Scott G | 75000 | 0 | 75000 | 75000 | 45920.18 | 29079.82 | 0
| 9354.00 | DOC ASP LUC Plumbing Repairs Phase 2 & 3 | Jennie E | 1800000 |  | 1800000 | 1161963.38 | 442.27 | 1161521.11 | 638036.62 | 99557.73
| 9371.00 | DPS Post 3 Parking Lot Replacement | Jennie E | 378000 |  | 378000 | 374803.93 | 169753.43 | 205050.5 | 3196.07 | 0
| 9422.00 | DOC ASP Tuckpointing Priorities 7, 8, & 9 | Brandon A. | 3000000 |  | 3000000 | 60854.86 | 35592.81 | 25262.05 | 2939145.14 | 6815.44
| 9442.00 | DOC MPCF SouthCore & East/West Staircase Tuckpointing | Brandon A. | 500000 |  | 500000 | 453652.48 | 31588.95 | 422063.53 | 46347.52 | 2621.46
| 9443.00 | DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements | Brandon A. | 1375000 |  | 1375000 | 1243137.39 | 31001.79 | 1212135.6 | 131862.61 | 17011.25
| 9444.00 | DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing | Brad T. | 250000 |  | 250000 | 172098.83 | 54407.79 | 117691.04 | 77901.17 | 8315.73
| 9445.00 | DOC IMCC Fire Alarm System Replacement | Jennifer K | 1800000 |  | 1800000 | 108718.02 | 32544.59 | 76173.43 | 1691281.98 | 13965.6
| 9447.00 | DAS TH HVAC Repairs | James T. | 720000 |  | 720000 | 34769.12 | 26428.22 | 8340.9 | 685230.88 | 7827.79
| 9448.00 | DAS TH Residence Roof, Porch, & South Garden Wall Repairs | James T. | 970000 |  | 970000 | 63920.48 | 37056.4 | 26864.08 | 906079.52 | 25638.74
| 9449.00 | DAS TH Carriage House Roof Replacement | James T. | 375000 |  | 375000 | 351132.02 | 60905.35 | 290226.67 | 23867.98 | 9150.92
| 9451.00 | DOC ASP LUA A/C Replacement | Brandon A. | 709000 |  | 709000 | 671378.35 | 77824.81 | 593553.54 | 37621.65 | 6985.78
| 9452.00 | HHS CHMHI Generator Controller Replacement | Jennie E | 300000 |  | 300000 | 298955.21 | 29715.77 | 269239.44 | 1044.79 | 8158.1
| 9453.00 | DOC FDCF IPI Roof Replacement | Jennifer K | 330000 |  | 330000 | 298692.73 | 25766.96 | 272925.77 | 31307.27 | 5782.73
| 9454.00 | DOC ICIW Building 9 Roof Replacement | Brandon A. | 260000 |  | 260000 | 214677.36 | 47983.65 | 166693.71 | 45322.64 | 5406.81
| 9455.00 | IDOE ISD Giangreco Hall Water Infiltration Mitigation | Jennie E | 1000000 |  | 1000000 | 465863.26 | 79786.41 | 386076.85 | 534136.74 | 42296.85
| 9456.00 | IDOE ISD Elementary School Roof Replacement | Jennie E | 403525 |  | 403525 | 309176.33 | 45604.63 | 263571.7 | 94348.67 | 10051.7
| 9457.00 | IDOE ISD High School Gym Roof Replacement | Jennie E | 405525 |  | 405525 | 312383.21 | 46808.51 | 265574.7 | 93141.79 | 10051.7
| 9458.00 | DOC NCCF Powerhouse Water Heater Replacements | Jennie E | 630000 |  | 630000 | 528968.53 | 155476.38 | 373492.15 | 101031.47 | 2712.02
| 9459.00 | HHS STS A.E. Sheperd AC Replacement | Jennifer K | 300000 |  | 300000 | 255245.26 | 41696.48 | 213548.78 | 44754.74 | 2102.59
| 9460.00 | DOC NCF LU B, C & D Roof Replacements | Brad T | 2355000 |  | 2355000 | 1086297.76 | 44174.7 | 1042123.06 | 1268702.24 | 22946.02
| 9462.00 | DOE ISD South Powerhouse Parking Lot Repair | Jennie E | 610000 |  | 610000 | 137171.96 | 5143.36 | 132028.6 | 472828.04 | 22845.25
| 9463.00 | HHS WRC Birches Window Replacement | Jennifer K | 1500000 |  | 1500000 | 56102.96 | 8815.93 | 47287.03 | 1443897.04 | 6036.94
| 9474.00 | HHS IMHI Boiler #3 Replacement | Jennie E | 100000 |  | 100000 | 49296.56 | 435.65 | 48860.91 | 50703.44 | 9564.35
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 20146050 | 0 | 20146050 | 8784259.99 | 1134875.02 | 7649384.97 | 11361790.01 | 345845.5
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 1853950
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 13215740.01
[6 empty] | Total funds Available |  |  | 22000000
[6 empty] | Total obligated by contract or PO |  |  | -8784259.99 | 13215740.01
[6 empty] | Variance |  |  |  | 0
Note on E16: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Sat, Mar 1, 1:05 PM (3 days ago) to me, Jennifer, Scott Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott
Note on E17: Huggins, Joni [DAS]: 9371.00 - DPS Post 3 Parking Lot Rep - MM25 $Joni Elliott, Jennie 8:37 AM (5 minutes ago) to me, Jennifer, Scott Due to good bids, Please return $142,000 in funding from project 9371.00 in MM25 to the Total Unassigned/Unallocated line. This will bring the project budget for 9371.00 in MM25 to $378,000.00 Thank you, Jennie Elliott
Note on E18: Huggins, Joni [DAS]: New Major Maintenance Projects $Joni Kleene, Jennifer 9:33 AM (3 hours ago) to me, Scott, Jennie, James, Brad, Brandon Please increase the funding for MM25 Project # 9422.00 by $2,900,000 and set-up the following new projects. Please let me know if you have any questions.
Note on E19: Huggins, Joni [DAS]: 9442.00 MM25 DOC MPCF South Core & East/West Stair Case Tuckpointing $Joni Adams, Brandon 10:37 AM (11 minutes ago) to me, Jennifer, Charlee Finance, Please decrease the funds from MM25 9442.00 by $300,000 and return to MM25. Please let me know if you have any questions. Regards, Brandon Adams
Note on E20: Huggins, Joni [DAS]: 9443.00 MM25 DOC MPCF Appliance Shop, Powerhouse, Carpentry, and Paint Shop Window Replacement $Joni Adams, Brandon 10:58 AM (14 minutes ago) to me, Jennifer, Charlee Finance, Please deduct funds from MM25 9443.00 by $625,000 and return to MM25. Please let me know if you have any questions. Regards, Brandon Adams
Note on E25: Huggins, Joni [DAS]: Budget Modifications - James Trower $Joni Trower, James Mon, Feb 10, 4:13 PM (15 hours ago) to me Finance - Please see below budget modifications: 9449.00 - DAS TH Carriage House Roof Replacement Increase MM25 budget by $125,000.00 9375.00 - DOC 5JD DM Bldgs 65-66 Renovation Increase PM Time (DA24) by $28,000.00 Thanks, Re: 9449.00 - Titan Roofing - 802 - BP #01 - Roofing Replacement $Joni Trower, James 1:27 PM (2 minutes ago) to me Joni - Please increase the budget for project 9449.00 by $50,000.00 (MM25). Thanks, James
Note on E26: Huggins, Joni [DAS]: Re: MM25 9451.00 DOC ASP LUA A/C 802 - Foreman Construction, LLC. Inbox Shimp, Oliver 10:06 AM (2 minutes ago) to me, Brandon, Jennifer Please increase the budget of MM25 9451.00 by $109,000. Thank you, Oliver Shimp
Note on E28: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Mar 1, 2025, 1:05 PM (3 days ago) to me, Jennifer, Scott Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott
Note on E29: Huggins, Joni [DAS]: MM25 9454.00 DOC ICIW Building 9 Roof Replacement $Joni Adams, Brandon 12:01 PM (20 minutes ago) to me, Scott, Jennifer Finance, Please return $340,000 to MM25 funding from 9454.00 DOC ICIW Building 9 Roof Replacement. Regards, Brandon Adams
Note on E31: Huggins, Joni [DAS]: Re: Changes to MM25 Inbox Elliott, Jennie 11:01 AM (0 minutes ago) to me, Jennifer, Scott Sorry, no. I meant the following! 9456.00 9467.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Tue, Mar 4, 2025 at 10:55 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Are you wanting to Open Projects 9356.00 (DA24) and 9357.00 (MM24) in MM25? On Sat, Mar 1, 2025 at 1:05 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott 9456.00 - DOE ISD Elementary Roof Replacement - Budget Changes MM25 FY25 Elliott, Jennie Fri, Apr 25, 4:41 PM (3 days ago) to me, Jennifer Bids came in better than anticipated on this project. Please return $26,475.00 in funding from project 9456.00 in MM25 to the "Total Unassigned/Unallocated" line. This will make the new budget for project 9456.00 $403,525.00. Thank you, Jennie Elliott
Note on E32: Huggins, Joni [DAS]: Re: Changes to MM25 Inbox Elliott, Jennie 11:01 AM (0 minutes ago) to me, Jennifer, Scott Sorry, no. I meant the following! 9456.00 9467.00 Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-745-3244 mobile jennie.elliott@iowa.gov https://das.iowa.gov On Tue, Mar 4, 2025 at 10:55 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Are you wanting to Open Projects 9356.00 (DA24) and 9357.00 (MM24) in MM25? On Sat, Mar 1, 2025 at 1:05 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Finance, Please make the following changes below to MM25. 9354.00 - ASP Plumbing - Return $1,200,000.00 from this project to the unallocated line in MM25 9356.00 - ISD Elem Roof - Add $130,000 to this project budget in MM25 9357.00 - ISD HS Gym Roof - Add $130,000 to this project budget in MM25 9458.00 - NCCF Water Heater - Add $330,000 to this project budget in MM25 9453.00 - FDCF IPI Roof - Add $20,000 to this project budget in MM25 Thank you, Jennie Elliott 9457.00 - DOE ISD High School Gym Roof Replacement - Budget Changes MM25 $Joni Elliott, Jennie Fri, Apr 25, 4:47 PM (3 days ago) to me, Jennifer Bids came in better than anticipated on this project. Please return $24,475.00 in funding from project 9457.00 in MM25 to the "Total Unassigned/Unallocated" line. This will make the new budget for project 9457.00 $405,525.00. Thank you, Jennie Elliott
Note on E33: Huggins, Joni [DAS]: Changes to MM25 $Joni Elliott, Jennie Mar 1, 2025, 1:05 PM (3 days ago) to me, Jennifer, Scott

## MM25 Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct. Codes-0017-335-MM25
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #9997.25
Project Management Time
Project # 9997.25
Program code 999725 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - NA
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 75000
PM TIME |  | 75000 | 45920.18 | 29079.82
Total Project Cost | 75000 | 75000 | 45920.18 | 29079.82 | 0

## #9997.25 PM TIME
Project Management Time
Project # 9997.25
Program code 999725 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS E2DU
Project Manager - NA
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 75000 | 584.63 | 584.63 | 74415.37
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 75000 | 2805.2 | 3389.83 | 71610.17
CDE 33525229800 | 2024-08-21 | 2507 | Moving PM Expense to CS23 9421.00(Finance Support-July) |  | 75000 | -61.68 | 3328.15 | 71671.85
CDE 33525229800 | 2024-08-21 | 9500 | Moving PM Expense to CS23 9421.00(DAS Services-July) |  | 75000 | -675 | 2653.15 | 72346.85
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 75000 | 1180.54 | 3833.69 | 71166.31
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 75000 | 2543.4 | 6377.09 | 68622.91
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 75000 | 596.59 | 6973.68 | 68026.32
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 75000 | 2174.4 | 9148.08 | 65851.92
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 75000 | 1088.06 | 10236.14 | 64763.86
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 75000 | 2628.5 | 12864.64 | 62135.36
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 75000 | 1435.53 | 14300.17 | 60699.83
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 75000 | 8436.2 | 22736.37 | 52263.63
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 75000 | 850.1 | 23586.47 | 51413.53
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 75000 | 2403.5 | 25989.97 | 49010.03
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 75000 | 1328.73 | 27318.7 | 47681.3
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 75000 | 3063.8 | 30382.5 | 44617.5
CDE 33525050904 | 2025-02-19 | 2507 | Move Expenses to Admin time per Project Manager |  | 75000 | 92.25 | 30474.75 | 44525.25
CDE 33525050904 | 2025-02-19 | 9500 | Move Expenses to Admin time per Project Manager |  | 75000 | 985.6 | 31460.35 | 43539.65
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 75000 | 3374.54 | 34834.89 | 40165.11
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 75000 | 3786.4 | 38621.29 | 36378.71
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 75000 | 1908.2 | 40529.49 | 34470.51
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 75000 | 2587.8 | 43117.29 | 31882.71
CDE 33525106901 | 2025-04-15 | 2507 | Move expenses to 999725 due to billable file error |  | 75000 | 27.14 | 43144.43 | 31855.57
CDE 33525106901 | 2025-04-15 | 9500 | Move expenses to 999725 due to billable file error |  | 75000 | 197 | 43341.43 | 31658.57
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 75000 | 1438.39 | 44779.82 | 30220.18
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 75000 | 1364.5 | 46144.32 | 28855.68
CDE 33525134911 | 2025-05-13 | 2507 | Move expenses From 999725 due to billable file error |  | 75000 | -27.14 | 46117.18 | 28882.82
CDE 33525134911 | 2025-05-13 | 9500 | Move expenses From 999725 due to billable file error |  | 75000 | -197 | 45920.18 | 29079.82
[5 empty] | 75000 |  | 45920.18 | 29079.82
|  |  | Totals: | 75000 |  | 45920.18 |  | 29079.82
Note on E9: Jurgenson, John [DAS]: Re: FY 25 9997.25 PM Time Inbox Gustafson, Scott Wed, Jun 26, 3:25 PM (17 hours ago) to me John, Please set the budget at $75,000. Respectfully, Scott

## RECAP #9354.00
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1800000
Foreman Construction |  | 936644 | 0 | 936644
PM TIME |  | 100000 | 442.27 | 99557.73
Misc. |  | 0 | 0 | 0
McGough Construction |  | 107797.38 | 0 | 107797.38
Shive Hattery |  | 17522 | 0 | 17522
Total Project Cost | 1800000 | 1161963.38 | 442.27 | 1161521.11 | 638036.62

## #9354.00 Foreman Construction
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Foreman Construction |  |  | Vendor: 00003226071
Acct. Codes-0017-335-MM25-9255 |  |  | RFB935400-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Split w/ MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525027908 | 2025-01-27 | PO Procore | 540000 | 540000 |  |  | 540000
PO 33525027908 | 2025-05-05 | CO #1(Procore adjustment only) | 0 | 540000 |  | 0 | 540000
PRC 3352502PA7908 | 2025-05-15 | Inv. 9354.00 Pay App #1(100% to DA24) |  | 540000 | 0 | 0 | 540000
PO 33525027908 | 2025-05-09 | CO #2(100% to MM25) | 396644 | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  |  |  | 936644 |  | 0 | 936644
|  | Totals: | 936644 |  | 0 |  | 936644
|  | MM24 | 1548300 |  | 91977.1 |  | 1456322.9
|  | Total: | 2484944 |  | 91977.1 |  | 2392966.9

## #9354.00 PM TIME
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909T
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 100000 | 100000 |  |  | 100000
CDE 33525109901 | 2025-04-18 | 2507 | Moving Expense From MM22 |  | 100000 | 54.27 | 54.27 | 99945.73
CDE 33525109901 | 2025-04-18 | 9500 | Moving Expense From MM22 |  | 100000 | 388 | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
[5 empty] | 100000 |  | 442.27 | 99557.73
|  |  | Totals: | 100000 |  | 442.27 |  | 99557.73
Note on E9: Huggins, Joni [DAS]: 9354.00 - PM Time MM25 $Joni Elliott, Jennie 12:48 PM (32 minutes ago) to me Can you please establish a PM Time budget in MM25 for project 9354.00 of $100,000. Thank you, Jennie Elliott

## #9354.00 Misc
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 163
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9354.00 McGough Construction
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Split w/MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525038900 | 2025-02-07 | PO Procore | 107797.38 | 107797.38 |  |  | 107797.38
PRC 3352503PA8900 | 2025-04-24 | Inv. 101031.005CA#01(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
PRC 3352503PB8900 | 2025-05-05 | Inv. 101031.005CA#02(100% to MM24) |  | 107797.38 | 0 | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  |  |  | 107797.38 |  | 0 | 107797.38
|  | Totals: | 107797.38 |  | 0 |  | 107797.38
|  | MM24 | 221700 |  | 4735.5 |  | 216964.5
|  | Total: | 329497.38 |  | 4735.5 |  | 324761.88

## #9354.00 Shive Hattery
DOC ASP LUC Plumbing Repairs Phase 2 & 3
Project # 9354.00
Program code 935400 |  |  | Major Program 4B01
Shive Hattery |  |  | Vendor:00002108803
Acct. Codes-0017-335-MM25-9260 |  |  | 935400-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Split w/MM22
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525317902 | 2025-05-07 | CO #3 Splitting w/MM22 | 17522 | 17522 |  |  | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  |  |  | 17522 |  | 0 | 17522
|  | Totals: | 17522 |  | 0 |  | 17522
|  | MM22 | 91622 |  | 78022 |  | 13600
|  | Total: | 109144 |  | 78022 |  | 31122

## RECAP #9371.00
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 378000
Samuels Group |  | 60003.93 | 17002.93 | 43001
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Metro Driveway Replacement |  | 314800 | 152750.5 | 162049.5
Total Project Cost | 378000 | 374803.93 | 169753.43 | 205050.5 | 3196.07

## #9371.00 Samuels Group
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327905 | 2024-11-22 | PO Procore | 51805.08 | 51805.08 |  |  | 51805.08
PRC 3352532PA7905 | 2024-12-06 | Inv. 7739.51937100 |  | 51805.08 | 973.74 | 973.74 | 50831.34
PRC 3352532PB7905 | 2025-01-13 | Inv. 7739.52937100 |  | 51805.08 | 1459.75 | 2433.49 | 49371.59
PRC 3352532PC7905 | 2025-02-05 | Inv. 7739.53937100 |  | 51805.08 | 3168.67 | 5602.16 | 46202.92
PRC 3352532PD7905 | 2025-03-10 | Inv. 7739.54937100 |  | 51805.08 | 807.59 | 6409.75 | 45395.33
PO 33525327905 | 2025-04-07 | CO #1 | 8198.85 | 60003.93 |  | 6409.75 | 53594.18
PRC 3352532PE7905 | 2025-04-08 | Inv. 7739.55937100 |  | 60003.93 | 3058.5 | 9468.25 | 50535.68
PRC 3352532PF7905 | 2025-05-09 | Inv. 7739.56937100 |  | 60003.93 | 7534.68 | 17002.93 | 43001
|  |  |  | 60003.93 |  | 17002.93 | 43001
|  |  |  | 60003.93 |  | 17002.93 | 43001
|  |  |  | 60003.93 |  | 17002.93 | 43001
|  |  |  | 60003.93 |  | 17002.93 | 43001
|  |  |  | 60003.93 |  | 17002.93 | 43001
|  | Totals: | 60003.93 |  | 17002.93 |  | 43001
|  | CM Services: | 48805.08 |  | 15824.89 |  | 32980.19
|  | Reimbursables: | 3000 |  | 618.98 |  | 2381.02
|  | CO #1 | 8198.85 |  | 559.06 |  | 7639.79
|  | Total: | 60003.93 |  | 17002.93 |  | 43001

## #9371.00 PM TIME
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731L
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9371.00 Misc
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9371.00 MetroDriveway
DPS Post 3 Parking Lot Replacement
Project # 9371.00
Program code 937100 |  |  | Major Program 4G01
Metro Driveway Replacement |  |  | Vendor: 00003224688
Acct. Codes-0017-335-MM25-9255 |  |  | RFB937100-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525339906 | 2024-12-04 | PO Procore | 314800 | 314800 |  |  | 314800
PO 33525339906 | 2025-04-16 | CO #1(100% to MM23) | 0 | 314800 |  | 0 | 314800
PRC 3352533PA9906 | 2025-05-29 | Inv. 9371.00-01 |  | 314800 | 152750.5 | 152750.5 | 162049.5 | 8039.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  |  |  | 314800 |  | 152750.5 | 162049.5
|  | Totals: | 314800 |  | 152750.5 |  | 162049.5
|  | MM23 | 22000 |  | 13080.82 |  | 8919.18
|  | Total: | 336800 |  | 165831.32 |  | 170968.68

## RECAP #9422.00
DOC ASP Tuckpointing Priorities 7, 8, & 9
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 3000000
McGough Construction |  | 17289.86 | 6534.25 | 10755.61
PM TIME |  | 20000 | 13184.56 | 6815.44
Misc. |  | 0 | 0 | 0
Horizon Architecture |  | 23565 | 15874 | 7691
Total Project Cost | 3000000 | 60854.86 | 35592.81 | 25262.05 | 2939145.14

## #9422.00 McGough Construction
DOC ASP Tuckpointing Priorities 7, 8, & 9
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320903 | 2024-11-15 | PO Procore | 17289.86 | 17289.86 |  |  | 17289.86
PRC 3352532PA0903 | 2025-02-12 | Inv. 101368.007PC-001 |  | 17289.86 | 2219.12 | 2219.12 | 15070.74
PRC 3352532PB0903 | 2025-03-19 | Inv. 101368.007PC-02 |  | 17289.86 | 899.31 | 3118.43 | 14171.43
PRC 3352532PC0903 | 2025-04-15 | Inv. 101368.007PC-03 |  | 17289.86 | 1479.05 | 4597.48 | 12692.38
PRC 3352532PD0903 | 2025-05-08 | Inv. 101368.007PC-04 |  | 17289.86 | 1936.77 | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  |  |  | 17289.86 |  | 6534.25 | 10755.61
|  | Totals: | 17289.86 |  | 6534.25 |  | 10755.61
|  | CM Services: | 16359.86 |  | 6358.75 |  | 10001.11
|  | Reimbursables: | 930 |  | 175.5 |  | 754.5
|  | Total: | 17289.86 |  | 6534.25 |  | 10755.61

## #9422.00 PM TIME
DOC ASP Tuckpointing Priorities 7, 8, & 9
Project # 9422.00
Program code 942200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS E2FF
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 20000 | 134.79 | 134.79 | 19865.21
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 20000 | 686.4 | 821.19 | 19178.81
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 56.21 | 877.4 | 19122.6
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 503.3 | 1380.7 | 18619.3
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 2 | 1382.7 | 18617.3
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 46.66 | 1429.36 | 18570.64
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 311.4 | 1740.76 | 18259.24
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 187.04 | 1927.8 | 18072.2
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 1871.6 | 3799.4 | 16200.6
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 113.91 | 3913.31 | 16086.69
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 1215.2 | 5128.51 | 14871.49
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 186.76 | 5315.27 | 14684.73
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 808.4 | 6123.67 | 13876.33
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 187.68 | 6311.35 | 13688.65
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 1346.3 | 7657.65 | 12342.35
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 693.31 | 8350.96 | 11649.04
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 4833.6 | 13184.56 | 6815.44
[5 empty] | 20000 |  | 13184.56 | 6815.44
|  |  | Totals: | 20000 |  | 13184.56 |  | 6815.44
Note on E9: Huggins, Joni [DAS]: MM24 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 $Joni Adams, Brandon Aug 6, 2024, 11:08 AM (2 days ago) to me, Jennifer, Scott Finance, Please close PM Time for MM24 9422.00 once July PM time posts. Please return all remaining funds back to MM24. Please transfer $100,000 from MM25 and create 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 in MM25 Please set the PM budget in MM25 9422.00 DOC ASP Tuckpointing Priorities 7, 8, & 9 at $5,000. Please update the August billing sheet. Regards, Brandon Adams Re: PM Time Inbox Adams, Brandon 10:25 AM (4 minutes ago) to me Please increase my PM Time by $5000.00 Regards, Brandon Adams Owner's Representative, State Design & Construction Resources Bureau General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-201-2197 mobile brandon.adams@iowa.gov https://das.iowa.gov On Wed, Feb 19, 2025 at 9:23 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Brandon We are negative for PM time on 9422.00 in MM25. Can we increase the budget? Currently -128.51 Re: April PM Time $Joni Shimp, Oliver 2:41 PM (9 minutes ago) to me Good Afternoon Joni, Could you please; 1) Add $10,000 to the PM time budget from the uncontracted budget for project MM25 9422.00. 2) Add $7,000 to the PM time budget from the uncontracted budget for project MM25 9422.00 3) Can you please assign $10,000 of the $50,000 to PM time for project 5800 9473.00 Thank you very much! Oliver Shimp

## #9422.00 Misc
DOC ASP Tuckpointing Priorities 7, 8, & 9
Project # 9422.00
Program code 942200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 163
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9422.00 Horizon Architecture
DOC ASP Tuckpointing Priorities 7, 8, & 9
Project # 9422.00
Program code 942200 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP#942200-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525014902 | 2025-01-14 | PO Procore | 23565 | 23565 |  |  | 23565
PRC 3352501PA4902 | 2025-03-14 | Inv. 9422.00-01 |  | 23565 | 11347.5 | 11347.5 | 12217.5
PRC 3352501PB4902 | 2025-04-24 | Inv. 9422.00-02 |  | 23565 | 4526.5 | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  |  |  | 23565 |  | 15874 | 7691
|  | Totals: | 23565 |  | 15874 |  | 7691
|  | Design Development | 7370 |  | 7370 |  | 0
|  | Construction Documents | 7955 |  | 7955 |  | 0
|  | Bidding Assistance | 580 |  |  |  | 580
|  | Construction Phase | 6910 |  |  |  | 6910
|  | Reimbursables | 750 |  | 549 |  | 201
|  | Total: | 23565 |  | 15874 |  | 7691

## RECAP #9442.00
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 500000
McGough Construction |  | 17451.65 | 10493.76 | 6957.89
PM TIME |  | 10000 | 7378.54 | 2621.46
Misc. |  | 1386.65 | 1386.65 | 0
Horizon Architecture |  | 16855 | 12330 | 4525
Bi-State Masonry |  | 344711 | 0 | 344711
McGough Construction (2) |  | 63248.18 | 0 | 63248.18
Total Project Cost | 500000 | 453652.48 | 31588.95 | 422063.53 | 46347.52

## #9442.00 McGough Construction
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
McGoughConstruction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525347907 | 2024-12-12 | PO Procore | 17451.65 | 17451.65 |  |  | 17451.65
PCR 3352534PA7907 | 2025-01-14 | Inv. 101368.005-PC01 |  | 17451.65 | 1745.3 | 1745.3 | 15706.35
PCR 3352534PB7907 | 2025-02-12 | Inv. 101368.005-PC02 |  | 17451.65 | 1053.05 | 2798.35 | 14653.3
PCR 3352534PC7907 | 2025-03-19 | Inv. 101368.005-PC03 |  | 17451.65 | 664.68 | 3463.03 | 13988.62
PCR 3352534PD7907 | 2025-04-15 | Inv. 101368.005-PC04 |  | 17451.65 | 1945.22 | 5408.25 | 12043.4
PCR 3352534PE7907 | 2025-05-07 | Inv. 101368.005-PC05 |  | 17451.65 | 5085.51 | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  |  |  | 17451.65 |  | 10493.76 | 6957.89
|  | Totals: | 17451.65 |  | 10493.76 |  | 6957.89
|  | CM Services: | 16751.65 |  | 10119.76 |  | 6631.89
|  | Reimbursables: | 700 |  | 374 |  | 326
|  | Total: | 17451.65 |  | 10493.76 |  | 6957.89

## #9442.00 PM TIME
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731P
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10000 | 103.44 | 103.44 | 9896.56
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10000 | 684 | 787.44 | 9212.56
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 109.13 | 896.57 | 9103.43
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 1092.5 | 1989.07 | 8010.93
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 74.39 | 2063.46 | 7936.54
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 794.8 | 2858.26 | 7141.74
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 175.81 | 3034.07 | 6965.93
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 761.4 | 3795.47 | 6204.53
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 194.86 | 3990.33 | 6009.67
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 1391.6 | 5381.93 | 4618.07
[5 empty] | 10000 | 253.51 | 5635.44 | 4364.56
[5 empty] | 10000 | 1743.1 | 7378.54 | 2621.46
[5 empty] | 10000 |  | 7378.54 | 2621.46
[5 empty] | 10000 |  | 7378.54 | 2621.46
|  |  | Totals: | 10000 |  | 7378.54 |  | 2621.46
Note on E9: Huggins, Joni [DAS]: Re: November PM Time $Joni Adams, Brandon 9:01 AM (45 minutes ago) to me Finance, Please increase the DAS Cost for MM25 9442.00 $10,000 Please set the DAS Cost for MM25 9443.00 to $25,000 Regards, Brandon Adams

## #9442.00 Misc
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525097905 | 2025-04-07 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2640102 | 1155 | 1155
PRC 33525139901 | 2025-05-19 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1740 | 231.65 | 1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
1386.65
|  |  |  | Totals: |  | 1386.65

## #9442.00 Horizon Architecture
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944200-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525015901 | 2025-01-15 | PO Procore | 16855 | 16855 |  |  | 16855
PRC 3352501PA5901 | 2025-03-04 | Inv. 9442.00-01 |  | 16855 | 3007.5 | 3007.5 | 13847.5
PRC 3352501PB5901 | 2025-05-06 | Inv. 9442.00-02 |  | 16855 | 9322.5 | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  | Totals: | 16855 |  | 12330 |  | 4525
|  | Desgin Development | 6015 |  | 6015 |  | 0
|  | Construction Documents | 6315 |  | 6315 |  | 0
|  | Bidding/Negotiation | 810 |  |  |  | 810
|  | Construction Phase | 3715 |  |  |  | 3715
|  | Total: | 16855 |  | 12330 |  | 4525

## #9442.00 Bi-State Masonry
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944200-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525127905 | 2025-05-07 | PO Procore | 344711 | 344711 |  |  | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  |  |  | 344711 |  | 0 | 344711
|  | Totals: | 344711 |  | 0 |  | 344711

## #9442.00 McGough Constructi (2)
DOC MPCF SouthCore & East/West Staircase Tuckpointing
Project # 9442.00
Program code 944200 |  |  | Major Program 4E01
McGoughConstruction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525129900 | 2025-05-09 | PO Procore | 63248.18 | 63248.18 |  |  | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  |  |  | 63248.18 |  | 0 | 63248.18
|  | Totals: | 63248.18 |  | 0 |  | 63248.18
|  | CM Services: | 59188.18 |  |  |  | 59188.18
|  | Reimbursables: | 4060 |  |  |  | 4060
|  | Total: | 63248.18 |  | 0 |  | 63248.18

## RECAP #9443.00
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1375000
McGough Construction |  | 16341.2 | 8557.84 | 7783.36
PM TIME |  | 25000 | 7988.75 | 17011.25
Misc. |  | 2125.2 | 2125.2 | 0
Horizon Architecture |  | 16855 | 12330 | 4525
McGough Construction (2) |  | 116642.99 | 0 | 116642.99
Bi-State Contracting |  | 1066173 | 0 | 1066173
Total Project Cost | 1375000 | 1243137.39 | 31001.79 | 1212135.6 | 131862.61

## #9443.00 McGough Construction
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525347908 | 2024-12-12 | PO Procore | 16341.2 | 16341.2 |  |  | 16341.2
PRC 3352534PA7908 | 2025-01-14 | Inv. 101368.006-PC01 |  | 16341.2 | 1231.51 | 1231.51 | 15109.69
PRC 3352534PB7908 | 2025-02-12 | Inv. 101368.006-PC02 |  | 16341.2 | 842.2 | 2073.71 | 14267.49
PRC 3352534PC7908 | 2025-03-19 | Inv. 101368.006-PC03 |  | 16341.2 | 746.96 | 2820.67 | 13520.53
PRC 3352534PD7908 | 2025-04-15 | Inv. 101368.006-PC04 |  | 16341.2 | 1537.18 | 4357.85 | 11983.35
PRC 3352534PE7908 | 2025-05-07 | Inv. 101368.006-PC05 |  | 16341.2 | 4199.99 | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  |  |  | 16341.2 |  | 8557.84 | 7783.36
|  | Totals: | 16341.2 |  | 8557.84 |  | 7783.36
|  | CM Services | 15641.2 |  | 8183.84 |  | 7457.36
|  | Reimbursables | 700 |  | 374 |  | 326
|  | Total: | 16341.2 |  | 8557.84 |  | 7783.36

## #9443.00 PM TIME
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731Q
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 25000 | 25000 |  |  | 25000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 25000 | 65.35 | 65.35 | 24934.65
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 25000 | 436 | 501.35 | 24498.65
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 25000 | 135.01 | 636.36 | 24363.64
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 25000 | 1124.1 | 1760.46 | 23239.54
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 25000 | 118.82 | 1879.28 | 23120.72
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 25000 | 1261.1 | 3140.38 | 21859.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 25000 | 197.72 | 3338.1 | 21661.9
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 25000 | 855.9 | 4194 | 20806
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 25000 | 220.44 | 4414.44 | 20585.56
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 25000 | 1577.7 | 5992.14 | 19007.86
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 25000 | 253.51 | 6245.65 | 18754.35
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 25000 | 1743.1 | 7988.75 | 17011.25
[5 empty] | 25000 |  | 7988.75 | 17011.25
[5 empty] | 25000 |  | 7988.75 | 17011.25
|  |  | Totals: | 25000 |  | 7988.75 |  | 17011.25
Note on E9: Huggins, Joni [DAS]: Re: November PM Time $Joni Adams, Brandon 9:01 AM (45 minutes ago) to me Finance, Please increase the DAS Cost for MM25 9442.00 $10,000 Please set the DAS Cost for MM25 9443.00 to $25,000 Regards, Brandon Adams

## #9443.00 Misc
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525097903 | 2025-04-07 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2640099 | 1802.5 | 1802.5
PRC 33525136902 | 2025-05-16 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1741 | 322.7 | 2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
2125.2
|  |  |  | Totals: |  | 2125.2

## #9443.00 Horizon Architecture
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944300-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525015902 | 2025-01-15 | PO Procore | 16855 | 16855 |  |  | 16855
PRC 3352501PA5902 | 2025-03-04 | Inv. 9443.00-01 |  | 16855 | 3007.5 | 3007.5 | 13847.5
PRC 3352501PB5902 | 2025-05-06 | Inv. 9443.00-02 |  | 16855 | 9322.5 | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  |  |  | 16855 |  | 12330 | 4525
|  | Totals: | 16855 |  | 12330 |  | 4525
|  | Design Development | 6015 |  | 6015 |  | 0
|  | Construction Documents | 6315 |  | 6315 |  | 0
|  | Bidding/Negotiation | 810 |  |  |  | 810
|  | Construction Phase | 3715 |  |  |  | 3715
|  | Total: | 16855 |  | 12330 |  | 4525

## #9443.00 McGough Constructi (2)
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525128903 | 2025-05-08 | PO Procore | 116642.99 | 116642.99 |  |  | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  |  |  | 116642.99 |  | 0 | 116642.99
|  | Totals: | 116642.99 |  | 0 |  | 116642.99
|  | CM Services | 58574.34 |  |  |  | 58574.34
|  | Reimbursables | 4760 |  |  |  | 4760
|  | Fees | 53308.65 |  |  |  | 53308.65
|  | Total: | 116642.99 |  | 0 |  | 116642.99

## #9443.00 Bi-State Contracting
DOC MPCF Appliance, Carpentry, Paint, & Powerhouse Window Replacements
Project # 9443.00
Program code 944300 |  |  | Major Program 4E01
Bi-State Contracting |  |  | Vendor: 00002101614
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944300-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525133909 | 2025-05-12 | PO Procore | 1066173 | 1066173 |  |  | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  |  |  | 1066173 |  | 0 | 1066173
|  | Totals: | 1066173 |  | 0 |  | 1066173

## RECAP #9444.00
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
Samuels Group |  | 32642.58 | 12519.97 | 20122.61
PM TIME |  | 15000 | 6684.27 | 8315.73
Misc. |  | 1623.75 | 1623.75 | 0
Snyder & Associates |  | 99710 | 33579.8 | 66130.2
Controlled Asbestos |  | 23122.5 | 0 | 23122.5
Total Project Cost | 250000 | 172098.83 | 54407.79 | 117691.04 | 77901.17

## #9444.00 Samuels Group
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525338903 | 2024-12-03 | PO Procore | 32642.58 | 32642.58 |  |  | 32642.58
PRC 3352533PA8903 | 2025-01-08 | Inv. 7741.01 PC |  | 32642.58 | 3145.78 | 3145.78 | 29496.8
PRC 3352533PB8903 | 2025-02-12 | Inv. 7741.02PC |  | 32642.58 | 4134.53 | 7280.31 | 25362.27
PRC 3352533PC8903 | 2025-03-11 | Inv. 7741.03 PC |  | 32642.58 | 2694.58 | 9974.89 | 22667.69
PRC 3352533PD8903 | 2025-05-07 | Inv. 7741.04PC |  | 32642.58 | 2545.08 | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  |  |  | 32642.58 |  | 12519.97 | 20122.61
|  | Totals: | 32642.58 |  | 12519.97 |  | 20122.61
|  | CM Services | 31389.58 |  | 12279.97 |  | 19109.61
|  | Reimbursables | 1253 |  | 240 |  | 1013
|  | Total: | 32642.58 |  | 12519.97 |  | 20122.61

## #9444.00 PM TIME
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731R
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15000 | 108.64 | 108.64 | 14891.36
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15000 | 721.2 | 829.84 | 14170.16
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15000 | 102.66 | 932.5 | 14067.5
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15000 | 1029.6 | 1962.1 | 13037.9
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 15000 | 130.21 | 2092.31 | 12907.69
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 15000 | 1387.9 | 3480.21 | 11519.79
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 15000 | 200.25 | 3680.46 | 11319.54
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 15000 | 866.8 | 4547.26 | 10452.74
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 15000 | 159.42 | 4706.68 | 10293.32
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 15000 | 1142.2 | 5848.88 | 9151.12
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 15000 | 106.29 | 5955.17 | 9044.83
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 15000 | 729.1 | 6684.27 | 8315.73
[5 empty] | 15000 |  | 6684.27 | 8315.73
[5 empty] | 15000 |  | 6684.27 | 8315.73
|  |  | Totals: | 15000 |  | 6684.27 |  | 8315.73

## #9444.00 Misc
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 165
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525048911 | 2025-02-17 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2627700 | 1623.75 | 1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
1623.75
|  |  |  | Totals: |  | 1623.75

## #9444.00 Synder & Associates
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Synder & Associates |  |  | Vendor: 00002119810
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525049903 | 2025-02-18 | PO Procore | 99710 | 99710 |  |  | 99710
PRC 3352504PA9903 | 2025-05-07 | Inv. 9444.00-01 |  | 99710 | 20132 | 20132 | 79578
PRC 3352504PB9903 | 2025-05-29 | Inv. 9444.00-02 |  | 99710 | 13447.8 | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  |  |  | 99710 |  | 33579.8 | 66130.2
|  | Totals: | 99710 |  | 33579.8 |  | 66130.2
|  | Design 50% | 29884 |  | 28389.8 |  | 1494.2
|  | Design 95% | 15182 |  |  |  | 15182
|  | Design 100% | 15666 |  |  |  | 15666
|  | Bidding | 3248 |  |  |  | 3248
|  | Construction Admin | 26240 |  |  |  | 26240
|  | Geotechnical Work | 4300 |  |  |  | 4300
|  | Survey Crew | 5190 |  | 5190 |  | 0
|  | Total: | 99710 |  | 33579.8 |  | 66130.2

## #9444.00 Controlled Asbestos
DOC CCF Tunnel Repair/Replace Main Bldg to SW Wing
Project # 9444.00
Program code 944400 |  |  | Major Program 4E01
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0017-335-MM25-9255 |  |  | MA21060B
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525090915 | 2025-03-31 | DO Procore | 23122.5 | 23122.5 |  |  | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  |  |  | 23122.5 |  | 0 | 23122.5
|  | Totals: | 23122.5 |  | 0 |  | 23122.5
|  | Line 1 Labor 317Hrs | 20605 |  |  |  | 20605
|  | Line 7 | 580 |  |  |  | 580
|  | Line 10 Friable 2 ton | 180 |  |  |  | 180
|  | Line 12 Mileage 3,515 miles | 1757.5 |  |  |  | 1757.5
|  | Total: | 23122.5 |  | 0 |  | 23122.5

## RECAP #9445.00
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1800000
Samuels Group |  | 28873.02 | 9795.19 | 19077.83
PM TIME |  | 22255 | 8289.4 | 13965.6
Misc. |  | 0 | 0 | 0
KCL Engineering |  | 53685 | 14460 | 39225
Terracon |  | 3905 | 0 | 3905
Total Project Cost | 1800000 | 108718.02 | 32544.59 | 76173.43 | 1691281.98

## #9445.00 Samuels Group
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525324900 | 2024-11-19 | PO Procore | 28873.02 | 28873.02 |  |  | 28873.02
PRC 3352532PA4900 | 2024-12-06 | Inv. 9445.01 PC |  | 28873.02 | 846.53 | 846.53 | 28026.49
PRC 3352532PB4900 | 2025-01-08 | Inv. 9445.02 PC |  | 28873.02 | 846.53 | 1693.06 | 27179.96
PRC 3352532PC4900 | 2025-02-17 | Inv. 9445.03PC |  | 28873.02 | 2725.57 | 4418.63 | 24454.39
PRC 3352532PD4900 | 2025-03-10 | Inv. 9445.04 PC |  | 28873.02 | 1576.77 | 5995.4 | 22877.62
PRC 3352532PE4900 | 2025-04-04 | Inv. 9445.05 PC |  | 28873.02 | 747.65 | 6743.05 | 22129.97
PRC 3352532PF4900 | 2025-05-09 | Inv. 9445.06 PC |  | 28873.02 | 3052.14 | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  |  |  | 28873.02 |  | 9795.19 | 19077.83
|  | Totals: | 28873.02 |  | 9795.19 |  | 19077.83
|  | CM Services: | 28153.02 |  | 9385.69 |  | 18767.33
|  | Reimbursables: | 720 |  | 409.5 |  | 310.5
|  | Total: | 28873.02 |  | 9795.19 |  | 19077.83

## #9445.00 PM TIME
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731S
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22255 | 22255 |  |  | 22255
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 22255 | 103.44 | 103.44 | 22151.56
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 22255 | 687.3 | 790.74 | 21464.26
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 22255 | 27.01 | 817.75 | 21437.25
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 22255 | 272.5 | 1090.25 | 21164.75
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 22255 | 183.79 | 1274.04 | 20980.96
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 22255 | 1960.8 | 3234.84 | 19020.16
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 22255 | 323.67 | 3558.51 | 18696.49
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 22255 | 1399.9 | 4958.41 | 17296.59
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 22255 | 87.45 | 5045.86 | 17209.14
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 22255 | 627.6 | 5673.46 | 16581.54
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 22255 | 332.54 | 6006 | 16249
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 22255 | 2283.4 | 8289.4 | 13965.6
[5 empty] | 22255 |  | 8289.4 | 13965.6
[5 empty] | 22255 |  | 8289.4 | 13965.6
[5 empty] | 22255 |  | 8289.4 | 13965.6
|  |  | Totals: | 22255 |  | 8289.4 |  | 13965.6

## #9445.00 Misc
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 175
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9445.00 KCL Engineering
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944500-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525038902 | 2025-02-07 | PO Procore | 53685 | 53685 |  |  | 53685
PRC 3352503PA8902 | 2025-03-31 | Inv. 11542 |  | 53685 | 14460 | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  |  |  | 53685 |  | 14460 | 39225
|  | Totals: | 53685 |  | 14460 |  | 39225
|  | Design Development Docs | 14460 |  | 14460 |  | 0
|  | Construction Docs | 17655 |  |  |  | 17655
|  | Bidding/Negotiation | 7625 |  |  |  | 7625
|  | Construction Phase | 13945 |  |  |  | 13945
|  | Total: | 53685 |  | 14460 |  | 39225

## #9445.00 Terracon
DOC IMCC Fire Alarm System Replacement
Project # 9445.00
Program code 944500 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM25-9255 |  |  | MA00525049
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525132902 | 2025-05-09 | DO Procore | 3905 | 3905 |  |  | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  |  |  | 3905 |  | 0 | 3905
|  | Totals: | 3905 |  | 0 |  | 3905
|  | Construction Services Line 4 | 3585 |  |  |  | 3585
|  | Labor 2hrs@130 Line 5 | 260 |  |  |  | 260
|  | Travel 120miles@.5 Line 7 | 60 |  |  |  | 60
|  | Total: | 3905 |  | 0 |  | 3905

## RECAP #9447.00
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager -James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 720000
DCI Group |  | 7709.12 | 7437.21 | 271.91
PM TIME |  | 15000 | 7172.21 | 7827.79
Misc. |  | 0 | 0 | 0
OPN Architects |  | 12060 | 11818.8 | 241.2
Total Project Cost | 720000 | 34769.12 | 26428.22 | 8340.9 | 685230.88

## #9447.00 DCI Group
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager -James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525345900 | 2024-12-10 | PO Procore | 7709.12 | 7709.12 |  |  | 7709.12
PRC 3352534PA5900 | 2025-01-14 | Inv. 24-047 PC 01 |  | 7709.12 | 2649.66 | 2649.66 | 5059.46
PRC 3352534PB5900 | 2025-02-18 | Inv. 24-047 PC 02 |  | 7709.12 | 2768.94 | 5418.6 | 2290.52
PRC 3352534PC5900 | 2025-03-14 | Inv. 24-047 PC 03 |  | 7709.12 | 1143.56 | 6562.16 | 1146.96
PRC 3352534PD5900 | 2025-04-15 | Inv. 24-047 PC 04 |  | 7709.12 | 875.05 | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  |  |  | 7709.12 |  | 7437.21 | 271.91
|  | Totals: | 7709.12 |  | 7437.21 |  | 271.91

## #9447.00 PM TIME
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731V
Project Manager -James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15000 | 90.37 | 90.37 | 14909.63
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15000 | 597.7 | 688.07 | 14311.93
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15000 | 120.52 | 808.59 | 14191.41
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15000 | 1199.2 | 2007.79 | 12992.21
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 15000 | 106.31 | 2114.1 | 12885.9
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 15000 | 1135.9 | 3250 | 11750
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 15000 | 253.75 | 3503.75 | 11496.25
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 15000 | 1099.5 | 4603.25 | 10396.75
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 15000 | 157.88 | 4761.13 | 10238.87
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 15000 | 1129.1 | 5890.23 | 9109.77
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 15000 | 162.68 | 6052.91 | 8947.09
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 15000 | 1119.3 | 7172.21 | 7827.79
[5 empty] | 15000 |  | 7172.21 | 7827.79
[5 empty] | 15000 |  | 7172.21 | 7827.79
|  |  | Totals: | 15000 |  | 7172.21 |  | 7827.79
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time: 9447.00 - DAS TH HVAC Repairs Funding: MM25 PM Time: $15,000

## #9447.00 Misc
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager -James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9447.00 OPN Architects
DAS TH HVAC Repairs
Project # 9447.00
Program code 944700 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager -James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 3352536290 | 2024-12-27 | PO Procore | 12060 | 12060 |  |  | 12060
PRC 335253PA6290 | 2025-03-05 | Inv. 24852000-1 |  | 12060 | 780.89 | 780.89 | 11279.11
PRC 335253PB6290 | 2025-03-14 | Inv. 24852000-2 |  | 12060 | 7178.71 | 7959.6 | 4100.4
PRC 335253PC6290 | 2025-04-22 | Inv. 24852000-3 |  | 12060 | 3497.4 | 11457 | 603
PRC 335253PD6290 | 2025-05-08 | Inv. 24852000-4 |  | 12060 | 361.8 | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  |  |  | 12060 |  | 11818.8 | 241.2
|  | Totals: | 12060 |  | 11818.8 |  | 241.2
*Fix PO # when rolling to FY26
33526326900

## RECAP #9448.00
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 970000
DCI Group |  | 10665.48 | 9905.24 | 760.24
PM TIME |  | 30000 | 4361.26 | 25638.74
Misc. |  | 0 | 0 | 0
OPN Architects |  | 23255 | 22789.9 | 465.1
Total Project Cost | 970000 | 63920.48 | 37056.4 | 26864.08 | 906079.52

## #9448.00 DCI Group
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525351904 | 2024-12-16 | PO Procore | 10665.48 | 10665.48 |  |  | 10665.48
PRC 3352535PA1904 | 2025-01-21 | Inv. 24-046 PC 01 |  | 10665.48 | 3162.15 | 3162.15 | 7503.33
PRC 3352535PB1904 | 2025-02-25 | Inv. 24-046 PC 02 |  | 10665.48 | 934.34 | 4096.49 | 6568.99
PRC 3352535PC1904 | 2025-03-14 | Inv. 24-046 PC 03 |  | 10665.48 | 1325.52 | 5422.01 | 5243.47
PRC 3352535PD1904 | 2025-04-15 | Inv. 24-046 PC 04 |  | 10665.48 | 2645.58 | 8067.59 | 2597.89
PRC 3352535PE1904 | 2025-05-08 | Inv. 24-046 PC 05 |  | 10665.48 | 1837.65 | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  |  |  | 10665.48 |  | 9905.24 | 760.24
|  | Totals: | 10665.48 |  | 9905.24 |  | 760.24

## #9448.00 PM TIME
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731W
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 30000 | 30000 |  |  | 30000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 30000 | 90.37 | 90.37 | 29909.63
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 30000 | 597.7 | 688.07 | 29311.93
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 30000 | 124.32 | 812.39 | 29187.61
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 30000 | 1240.7 | 2053.09 | 27946.91
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 30000 | 29.25 | 2082.34 | 27917.66
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 30000 | 313.2 | 2395.54 | 27604.46
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 30000 | 117.96 | 2513.5 | 27486.5
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 30000 | 510.7 | 3024.2 | 26975.8
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 30000 | 89.69 | 3113.89 | 26886.11
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 30000 | 644.5 | 3758.39 | 26241.61
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 30000 | 76.77 | 3835.16 | 26164.84
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 30000 | 526.1 | 4361.26 | 25638.74
[5 empty] | 30000 |  | 4361.26 | 25638.74
[5 empty] | 30000 |  | 4361.26 | 25638.74
|  |  | Totals: | 30000 |  | 4361.26 |  | 25638.74
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time: 9448.00 - DAS TH Residence Roof, Porch, & South Garden Wall Repairs MM25 Funding: PM Time: $30,000

## #9448.00 Misc
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9448.00 OPN Architects
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362903 | 2024-12-27 | PO Procore | 23255 | 23255 |  |  | 23255
PRC 3352536PA2903 | 2025-02-25 | Inv. 24853000-1 |  | 23255 | 436.03 | 436.03 | 22818.97
PRC 3352536PB2903 | 2025-03-14 | Inv. 24853000-2 |  | 23255 | 854.62 | 1290.65 | 21964.35
PRC 3352536PC2903 | 2025-04-23 | Inv. 24853000-3 |  | 23255 | 11499.6 | 12790.25 | 10464.75
PRC 3352536PD2903 | 2025-05-08 | Inv. 24853000-4 |  | 23255 | 9999.65 | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  |  |  | 23255 |  | 22789.9 | 465.1
|  | Totals: | 23255 |  | 22789.9 |  | 465.1

## RECAP #9449.00
DAS TH Carriage House Roof Replacement
Project # 9449.00
| Program code 944900 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM25
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 375000
C | DCI Group |  | 17006.09 | 17006.09 | 0
| PM TIME |  | 15000 | 5849.08 | 9150.92
| Misc. |  | 340.18 | 340.18 | 0
| OPN Architects |  | 54750 | 37710 | 17040
| DCI Group (2) |  | 64168.83 | 0 | 64168.83
| Titan Roofing |  | 199866.92 | 0 | 199866.92
| Total Project Cost | 375000 | 351132.02 | 60905.35 | 290226.67 | 23867.98

## #9449.00 DCI Group
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525351903 | 2024-12-16 | PO Procore | 22170.45 | 22170.45 |  |  | 22170.45
PRC 3352535PA1903 | 2025-03-10 | Inv. 24-045 PC 01 |  | 22170.45 | 2349.8 | 2349.8 | 19820.65
PRC 3352535PB1903 | 2025-04-09 | Inv. 24-045 PC 02 |  | 22170.45 | 1802.55 | 4152.35 | 18018.1
PRC 3352535PC1903 | 2025-05-09 | Inv. 24-045 PC 03 FINAL | -5164.36 | 17006.09 | 12853.74 | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  |  |  | 17006.09 |  | 17006.09 | 0
|  | Totals: | 17006.09 |  | 17006.09 |  | 0 | FINAL
|  | CM Services | 14888.59 |  | 14888.59 |  | 0
|  | Reimbursables | 2117.5 |  | 2117.5 |  | 0
|  | Total: | 17006.09 |  | 17006.09 |  | 0

## #9449.00 PM TIME
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 731X
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 15000 | 96 | 96 | 14904
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 15000 | 636.5 | 732.5 | 14267.5
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 15000 | 120.52 | 853.02 | 14146.98
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 15000 | 1199.2 | 2052.22 | 12947.78
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 15000 | 21.66 | 2073.88 | 12926.12
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 15000 | 234.5 | 2308.38 | 12691.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 15000 | 317.5 | 2625.88 | 12374.12
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 15000 | 1373.7 | 3999.58 | 11000.42
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 15000 | 129.62 | 4129.2 | 10870.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 15000 | 927.2 | 5056.4 | 9943.6
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 15000 | 100.68 | 5157.08 | 9842.92
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 15000 | 692 | 5849.08 | 9150.92
[5 empty] | 15000 |  | 5849.08 | 9150.92
[5 empty] | 15000 |  | 5849.08 | 9150.92
|  |  | Totals: | 15000 |  | 5849.08 |  | 9150.92
Note on E9: Huggins, Joni [DAS]: PM Time - James Trower $Joni Trower, James 9:00 AM (1 hour ago) to me Finance - Please set up PM Time 9449.00 - DAS TH Carriage House Roof Replacement MM25 Funding: PM Time: $15,000

## #9449.00 Misc
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
CDE 00525114905 | 2025-04-23 | 9500 |  | Moving Beeline Inv INV047465 from 9411.00 to 9449.00 |  | 340.18 | 340.18
340.18
340.18
340.18
340.18
340.18
340.18
340.18
340.18
340.18
340.18
340.18
|  |  |  | Totals: |  | 340.18

## #9449.00 OPN Architects
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP944800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362905 | 2024-12-27 | PO Procore | 54750 | 54750 |  |  | 54750
PRC 3352536PA2905 | 2025-02-20 | Inv. 24854000-1 |  | 54750 | 15705.83 | 15705.83 | 39044.17
PRC 3352536PB2905 | 2025-03-14 | Inv. 24854000-2 |  | 54750 | 10081.92 | 25787.75 | 28962.25
PRC 3352536PC2905 | 2025-04-16 | Inv. 24854000-3 |  | 54750 | 7762.25 | 33550 | 21200
PRC 3352536PD2905 | 2025-05-08 | Inv. 24854000-4 |  | 54750 | 4160 | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  |  |  | 54750 |  | 37710 | 17040
|  | Totals: | 54750 |  | 37710 |  | 17040
|  | Construction Docs | 29550 |  | 29550 |  | 0
|  | Bidding/Negotiation | 4000 |  | 4000 |  | 0
|  | Construction Phase | 20800 |  | 4160 |  | 16640
|  | Reimbursables | 400 |  |  |  | 400
|  | Total: | 54750 |  | 37710 |  | 17040

## #9449.00 DCI Group (2)
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525111900 | 2025-04-21 | PO Procore | 64168.83 | 64168.83 |  |  | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  |  |  | 64168.83 |  | 0 | 64168.83
|  | Totals: | 64168.83 |  | 0 |  | 64168.83
|  | CM Services | 56668.83 |  |  |  | 56668.83
|  | Reimbursables | 7500 |  |  |  | 7500
|  | Total: | 64168.83 |  | 0 |  | 64168.83

## #9449.00 Titan Roofing
DAS TH Carriage House Roof Replacement
Project # 9449.00
Program code 944900 |  |  | Major Program 4D04
Titan Roofing |  |  | Vendor: 00003108323
Acct. Codes-0017-335-MM25-9255 |  |  | RFB944900-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525112906 | 2025-04-22 | PO Procore | 199866.92 | 199866.92 |  |  | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  |  |  | 199866.92 |  | 0 | 199866.92
|  | Totals: | 199866.92 |  | 0 |  | 199866.92

## RECAP #9451.00
DOC ASP LUA A/C Replacement
Project # 9451.00
| Program code 945100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Oliver S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 709000
C | McGough Construction |  | 16761.78 | 16761.78 | 0
| PM TIME |  | 20000 | 13014.22 | 6985.78
| Misc. |  | 3180.81 | 3180.81 | 0
| IMEG Corporation |  | 34348 | 23768 | 10580
| System Works |  | 11760 | 2100 | 9660
| Mechanical Sales |  | 140500 | 0 | 140500
| Foreman Construction |  | 387500 | 19000 | 368500
| McGough Construction (2) |  | 57327.76 | 0 | 57327.76
| Total Project Cost | 709000 | 671378.35 | 77824.81 | 593553.54 | 37621.65

## #9451.00 McGough Construction
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525267902 | 2024-09-23 | PO Procore | 18799.75 | 18799.75 |  |  | 18799.75
PRC 3352526PA7902 | 2024-10-14 | Inv. 101174.016-PC01 |  | 18799.75 | 1519.54 | 1519.54 | 17280.21
PRC 3352526PB7902 | 2024-11-12 | Inv. 101174.016-PC02 |  | 18799.75 | 2286.17 | 3805.71 | 14994.04
PRC 3352526PC7902 | 2024-12-16 | Inv. 101174.016-PC03 |  | 18799.75 | 3045.93 | 6851.64 | 11948.11
PRC 3352526PD7902 | 2025-01-17 | Inv. 101174-016-PC04 |  | 18799.75 | 1795.81 | 8647.45 | 10152.3
PRC 3352526PE7902 | 2025-02-12 | Inv. 101174-016-PC05 |  | 18799.75 | 716.59 | 9364.04 | 9435.71
PRC 3352526PF7902 | 2025-03-19 | Inv. 101174.016-PC06 |  | 18799.75 | 1015.11 | 10379.15 | 8420.6
PRC 3352526PG7902 | 2025-04-03 | Inv. 101174.016-PC07 |  | 18799.75 | 90 | 10469.15 | 8330.6
PRC 3352526PH7902 | 2025-04-15 | Inv. 101174.016-PC08 |  | 18799.75 | 3535.03 | 14004.18 | 4795.57
PRC 3352526PI7902 | 2025-05-07 | Inv. 101174.016-PC09 - FINAL | -2037.97 | 16761.78 | 2757.6 | 16761.78 | 0
|  |  |  | 16761.78 |  | 16761.78 | 0
|  |  |  | 16761.78 |  | 16761.78 | 0
|  |  |  | 16761.78 |  | 16761.78 | 0
|  | Totals: | 16761.78 |  | 16761.78 |  | 0 | FINAL
|  | CM Services | 16424.78 |  | 16424.78 |  | 0
|  | Reimbursables | 337 |  | 337 |  | 0
|  | Total: | 16761.78 |  | 16761.78 |  | 0

## #9451.00 PM Time
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909Y
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 20000 | 102.27 | 102.27 | 19897.73
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 20000 | 905.5 | 1007.77 | 18992.23
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 20000 | 290.6 | 1298.37 | 18701.63
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 20000 | 1938.3 | 3236.67 | 16763.33
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 20000 | 234.15 | 3470.82 | 16529.18
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 20000 | 1554.9 | 5025.72 | 14974.28
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 20000 | 114.05 | 5139.77 | 14860.23
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 20000 | 1144.9 | 6284.67 | 13715.33
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 20000 | 118.82 | 6403.49 | 13596.51
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 20000 | 1261.1 | 7664.59 | 12335.41
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 20000 | 186.76 | 7851.35 | 12148.65
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 20000 | 808.4 | 8659.75 | 11340.25
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 20000 | 200.9 | 8860.65 | 11139.35
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 20000 | 1439.1 | 10299.75 | 9700.25
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 339.97 | 10639.72 | 9360.28
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 2374.5 | 13014.22 | 6985.78
[5 empty] | 20000 |  | 13014.22 | 6985.78
[5 empty] | 20000 |  | 13014.22 | 6985.78
|  |  | Totals: | 20000 |  | 13014.22 |  | 6985.78
Note on E9: Huggins, Joni [DAS]: Re: PM Time for February has posted $Joni Adams, Brandon 10:50 AM (22 minutes ago) to me Finance, Please increase my PM as follows: DA24 9423.00 $9,500 MM22 9387.00 $1,200 MM23 9370.00 $3,000 MM25 9451.00 $5,000 Regards, Brandon Adams Re: April PM Time $Joni Shimp, Oliver 3:10 PM (0 minutes ago) to me Sorry! 1) Add $10,000 to the PM time budget from the uncontracted budget for project MM25 9422.00. 2) Add $7,000 to the PM time budget from the uncontracted budget for project MM25 9451.00 3) Can you please assign $10,000 of the $50,000 to PM time for project 5800 9473.00 That's what I meant. Thank you, Oliver Shimp

## #9451.00 Misc
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 163
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525105905 | 2025-04-15 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1635 | 305.81 | 305.81
PRC 33525148910 | 2025-05-28 | 9500 | CNST | Terracon Consultants V#(00002116513) | Inv. TN68035 | 2875 | 3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
3180.81
|  |  |  | Totals: |  | 3180.81

## #9451.00 IMEG Corporation
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
IMEG Corporation |  |  | Vendor: 00003224175
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945100-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320904 | 2024-11-15 | PO Procore | 34348 | 34348 |  |  | 34348
PRC 3352532PA0904 | 2024-12-19 | Inv. 24006748.00-1 |  | 34348 | 10656 | 10656 | 23692
PRC 3352532PB0904 | 2025-01-17 | Inv. 24006748.00-2 |  | 34348 | 9590.4 | 20246.4 | 14101.6
PRC 3352532PC0904 | 2025-03-05 | Inv. 24006748.00-3 |  | 34348 | 1065.6 | 21312 | 13036
PRC 3352532PD0904 | 2025-03-26 | Inv. 24006748.00-4 |  | 34348 | 828 | 22140 | 12208
PRC 3352532PE0904 | 2025-04-22 | Inv. 24006748.00-5 |  | 34348 | 828 | 22968 | 11380
PRC 3352532PF0904 | 2025-05-30 | Inv. 24006748.00-6 |  | 34348 | 800 | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  |  |  | 34348 |  | 23768 | 10580
|  | Totals: | 34348 |  | 23768 |  | 10580
|  | Construction Documents | 21312 |  | 21312 |  | 0
|  | Bidding/Negtiation | 1656 |  | 1656 |  | 0
|  | Construction Phase | 11380 |  | 800 |  | 10580
|  | Total: | 34348 |  | 23768 |  | 10580

## #9451.00 System Works
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
System Works |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM25-9255 |  |  | SRVV5
Project Manager - Oliver S. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525041909 | 2025-02-10 | PO Procore | 11760 | 11760 |  |  | 11760
PRC 3352504PA1909 | 2025-05-30 | Inv. 12358 |  | 11760 | 2100 | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  |  |  | 11760 |  | 2100 | 9660
|  | Totals: | 11760 |  | 2100 |  | 9660
|  | Design Phase | 1400 |  | 1400 |  | 0
|  | Construction Phase | 8120 |  | 700 |  | 7420
|  | Closeout Phase | 2240 |  |  |  | 2240
|  | Total: | 11760 |  | 2100 |  | 9660

## #9451.00 Mechanical Sales
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
Mechanical Sales |  |  | Vendor: 00002134854
Acct. Codes-0017-335-MM25-9255 |  |  | MA 21194B
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525083908 | 2025-03-21 | PO Procore | 140500 | 140500 |  |  | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  |  |  | 140500 |  | 0 | 140500
|  | Totals: | 140500 |  | 0 |  | 140500

## #9451.00 Foreman Construction
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
Foreman Construction |  |  | Vendor: 00003226071
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945100-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525109905 | 2025-04-18 | PO Procore | 387500 | 387500 |  |  | 387500
PRC 3352510PA9905 | 2025-05-08 | Inv. Pay App #1 |  | 387500 | 19000 | 19000 | 368500 | 1000
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  |  |  | 387500 |  | 19000 | 368500
|  | Totals: | 387500 |  | 19000 |  | 368500

## #9451.00 McGough Constructi (2)
DOC ASP LUA A/C Replacement
Project # 9451.00
Program code 945100 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525114908 | 2025-04-23 | PO Procore | 57327.76 | 57327.76 |  |  | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  |  |  | 57327.76 |  | 0 | 57327.76
|  | Totals: | 57327.76 |  | 0 |  | 57327.76
|  | CM Services: | 28447.76 |  |  |  | 28447.76
|  | Reimbursables: | 2480 |  |  |  | 2480
|  | Fee | 26400 |  |  |  | 26400
|  | Total: | 57327.76 |  | 0 |  | 57327.76

## RECAP #9452.00
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 300000
Innovative Engineers |  | 24875 | 14875 | 10000
PM TIME |  | 12000 | 3841.9 | 8158.1
Misc. |  | 976.25 | 976.25 | 0
DCI Group |  | 12823.33 | 10022.62 | 2800.71
Cummins |  | 248280.63 | 0 | 248280.63
Total Project Cost | 300000 | 298955.21 | 29715.77 | 269239.44 | 1044.79

## #9452.00 Innovative Engineers
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
Innovative Engineers |  |  | Vendor: 00003080298
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945200-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525362906 | 2024-12-27 | PO Procore | 24875 | 24875 |  |  | 24875
PRC 3352536PA2906 | 2025-05-05 | Inv. 9452.00-01 |  | 24875 | 14875 | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  |  |  | 24875 |  | 14875 | 10000
|  | Totals: | 24875 |  | 14875 |  | 10000
|  | Design Development Docs | 6825 |  | 6825 |  | 0
|  | Construction Docs | 8050 |  | 8050 |  | 0
|  | Bidding/Negotiation | 3785 |  |  |  | 3785
|  | Construction Phase | 4670 |  |  |  | 4670
|  | Close Out | 1545 |  |  |  | 1545
|  | Total: | 24875 |  | 14875 |  | 10000

## #9452.00 PM TIME
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 909Z
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12000 | 12000 |  |  | 12000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12000 | 86.56 | 86.56 | 11913.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12000 | 575.4 | 661.96 | 11338.04
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12000 | 112.43 | 774.39 | 11225.61
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12000 | 747.4 | 1521.79 | 10478.21
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12000 | 29.68 | 1551.47 | 10448.53
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12000 | 299.8 | 1851.27 | 10148.73
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12000 | 33.05 | 1884.32 | 10115.68
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12000 | 354.2 | 2238.52 | 9761.48
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12000 | 73.16 | 2311.68 | 9688.32
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12000 | 317.9 | 2629.58 | 9370.42
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 12000 | 75.78 | 2705.36 | 9294.64
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 12000 | 543 | 3248.36 | 8751.64
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 12000 | 75.64 | 3324 | 8676
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 12000 | 517.9 | 3841.9 | 8158.1
[5 empty] | 12000 |  | 3841.9 | 8158.1
|  |  | Totals: | 12000 |  | 3841.9 |  | 8158.1
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (2 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9452.00 Misc
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 548
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525090903 | 2025-03-31 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2635179 | 976.25 | 976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
976.25
|  |  |  | Totals: |  | 976.25

## #9452.00 DCI Group
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525058903 | 2025-02-27 | PO Procore | 12823.33 | 12823.33 |  |  | 12823.33
PRC 3352505PA8903 | 2025-03-17 | Inv. 25-003 PC 01 |  | 12823.33 | 786.49 | 786.49 | 12036.84
PRC 3352505PB8903 | 2025-04-14 | Inv. 25-003 PC 02 |  | 12823.33 | 6027.91 | 6814.4 | 6008.93
PRC 3352505PC8903 | 2025-05-09 | Inv. 25-003 PC 03 |  | 12823.33 | 3208.22 | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  |  |  | 12823.33 |  | 10022.62 | 2800.71
|  | Totals: | 12823.33 |  | 10022.62 |  | 2800.71

## #9452.00 Cummins
HHS CHMHI Generator Controller Replacement
Project # 9452.00
Program code 945200 |  |  | Major Program 4B02
Cummins |  |  | Vendor: 00003104792
Acct. Codes-0017-335-MM25-9255 |  |  | RFQ945200-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525134904 | 2025-05-13 | PO Procore | 248280.63 | 248280.63 |  |  | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  |  |  | 248280.63 |  | 0 | 248280.63
|  | Totals: | 248280.63 |  | 0 |  | 248280.63

## RECAP #9453.00
DOC FDCF IPI Roof Replacement
Project # 9453.00
| Program code 945300 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 330000
C | McGough Construction |  | 8893.05 | 8893.05 | 0
| PM TIME |  | 13000 | 7217.27 | 5782.73
| Misc. |  | 756.64 | 756.64 | 0
| Genesis Architectural |  | 15300 | 8900 | 6400
| Academy Roofing & Sheet Metal |  | 227300 | 0 | 227300
| McGough Construction (2) |  | 33443.04 | 0 | 33443.04
| Total Project Cost | 330000 | 298692.73 | 25766.96 | 272925.77 | 31307.27

## #9453.00 McGough Construction
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525276905 | 2024-10-02 | PO Procore | 14911.74 | 14911.74 |  |  | 14911.74
PRC 3352527PA6905 | 2024-11-19 | Inv. 101174.019PC-01 |  | 14911.74 | 1826.29 | 1826.29 | 13085.45
PRC 3352527PB6905 | 2024-12-18 | Inv. 101174.019PC-02 |  | 14911.74 | 930.4 | 2756.69 | 12155.05
PRC 3352527PC6905 | 2025-01-22 | Inv. 101174-019PC-03 |  | 14911.74 | 688.66 | 3445.35 | 11466.39
PRC 3352527PD6905 | 2025-02-12 | Inv. 101174-019PC-04 |  | 14911.74 | 941.07 | 4386.42 | 10525.32
PRC 3352527PE6905 | 2025-03-24 | Inv. 101174.019PC-05 |  | 14911.74 | 2753.99 | 7140.41 | 7771.33
PRC 3352527PF6905 | 2025-04-25 | Inv. 101174.019PC-06 |  | 14911.74 | 820.2 | 7960.61 | 6951.13
PRC 3352527PG6905 | 2025-05-09 | Inv. 101174.019PC-07 FINAL | -6018.69 | 8893.05 | 932.44 | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  |  |  | 8893.05 |  | 8893.05 | 0
|  | Totals: | 8893.05 |  | 8893.05 |  | 0 | FINAL
|  | CM Services | 8716.55 |  | 8716.55 |  | 0
|  | Reimbursables | 176.5 |  | 176.5 |  | 0
|  | Total: | 8893.05 |  | 8893.05 |  | 0

## #9453.00 PM TIME
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910A
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13000 | 13000 |  |  | 13000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 13000 | 68.6 | 68.6 | 12931.4
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 13000 | 609.3 | 677.9 | 12322.1
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 137.85 | 815.75 | 12184.25
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 921.9 | 1737.65 | 11262.35
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 113.13 | 1850.78 | 11149.22
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 748.5 | 2599.28 | 10400.72
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 109.13 | 2708.41 | 10291.59
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 1091.1 | 3799.51 | 9200.49
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13000 | 78.18 | 3877.69 | 9122.31
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13000 | 834.7 | 4712.39 | 8287.61
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13000 | 247.57 | 4959.96 | 8040.04
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13000 | 1072.2 | 6032.16 | 6967.84
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13000 | 43.72 | 6075.88 | 6924.12
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13000 | 310.5 | 6386.38 | 6613.62
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13000 | 105.59 | 6491.97 | 6508.03
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13000 | 725.3 | 7217.27 | 5782.73
[5 empty] | 13000 |  | 7217.27 | 5782.73
[5 empty] | 13000 |  | 7217.27 | 5782.73
|  |  | Totals: | 13000 |  | 7217.27 |  | 5782.73
Note on E9: Huggins, Joni [DAS]: New DAS Costs Budget for MM25 9453.00 $Joni Kleene, Jennifer 10:40 AM (23 minutes ago) to me Please create a new DAS Costs budget for $6,300.00 for MM25 Project 9453.00. Regards, Jennifer Re: March PM Time Posted $Joni Elliott, Jennie 1:13 PM (2 minutes ago) to me, Jennifer Please increase the PM Time in the Contracted line to a total of $13,000.00 Thank you, Jennie Elliott

## #9453.00 Misc
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525029903 | 2025-01-29 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2623363 | 547.5 | 547.5
PRC 33525090905 | 2025-03-31 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1573 | 209.14 | 756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
756.64
|  |  |  | Totals: |  | 756.64

## #9453.00 GenesisArchitectural
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
Genesis Architecural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP954300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525327904 | 2024-11-22 | PO Procore | 15300 | 15300 |  |  | 15300
PRC 3352532PA7904 | 2025-02-26 | Inv. 2412.01-01 |  | 15300 | 8100 | 8100 | 7200
PRC 3352532PB7904 | 2025-05-05 | Inv. 2412.01-02 |  | 15300 | 800 | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  |  |  | 15300 |  | 8900 | 6400
|  | Totals: | 15300 |  | 8900 |  | 6400
|  | Construction Docs | 8100 |  | 8100 |  | 0
|  | Bidding Phase | 800 |  | 800 |  | 0
|  | Construction Phase | 6400 |  |  |  | 6400
|  | Total: | 15300 |  | 8900 |  | 6400

## #9453.00 Academy Roofing
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
Academy Roofing & Sheet Metal |  |  | Vendor: 00003010234
Acct. Codes-0017-335-MM25-9255 |  |  | RFB954300-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525086901 | 2025-03-27 | PO Procore | 227300 | 227300 |  |  | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  |  |  | 227300 |  | 0 | 227300
|  | Totals: | 227300 |  | 0 |  | 227300

## #9453.00 McGough Constructi (2)
DOC FDCF IPI Roof Replacement
Project # 9453.00
Program code 945300 |  |  | Major Program 4B01
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525098902 | 2025-04-08 | PO Procore | 33443.04 | 33443.04 |  |  | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  |  |  | 33443.04 |  | 0 | 33443.04
|  | Totals: | 33443.04 |  | 0 |  | 33443.04
|  | CM Services | 31843.04 |  |  |  | 31843.04
|  | Reimbursables | 1600 |  |  |  | 1600
|  | Total: | 33443.04 |  | 0 |  | 33443.04

## RECAP #9454.00
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
| Program code 9454.00 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 260000
C | Samuels Group |  | 17817.7 | 17817.7 | 0
| PM TIME |  | 18000 | 12593.19 | 5406.81
| Misc. |  | 2087.9 | 2087.9 | 0
| Horizon Architecture |  | 18400 | 11737.5 | 6662.5
| Brockway Mechanical |  | 132778 | 0 | 132778
| Samuels Group (2) |  | 25593.76 | 3747.36 | 21846.4
| Total Project Cost | 260000 | 214677.36 | 47983.65 | 166693.71 | 45322.64

## #9454.00 Samuels Group
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525256902 | 2024-09-12 | PO Procore | 17987.44 | 17987.44 |  |  | 17987.44
PRC 3352525PA6902 | 2024-10-07 | Inv. 7718.019454 PC |  | 17987.44 | 3002.64 | 3002.64 | 14984.8
PRC 3352525PB6902 | 2024-11-06 | Inv. 7718.029454 PC |  | 17987.44 | 3679.52 | 6682.16 | 11305.28
PRC 3352525PC6902 | 2024-12-06 | Inv. 7718.039454 PC |  | 17987.44 | 3321.48 | 10003.64 | 7983.8
PRC 3352525PD6902 | 2025-01-14 | Inv. 7718.049454 PC |  | 17987.44 | 2675.04 | 12678.68 | 5308.76
PRC 3352525PE6902 | 2025-02-06 | Inv. 7718.05PC |  | 17987.44 | 3682.04 | 16360.72 | 1626.72
PRC 3352525PF6902 | 2025-03-07 | Inv. 7718.06 PC |  | 17987.44 | 1456.98 | 17817.7 | 169.74
PO 33525256902 | 2025-04-30 | Closing PO per PM | -169.74 | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  |  |  | 17817.7 |  | 17817.7 | -6.8212e-13
|  | Totals: | 17817.7 |  | 17817.7 |  | 0
|  | CM Services | 17717.7 |  | 17717.7 |  | 0
|  | Reimbursables | 100 |  | 100 |  | 0
|  | Total: | 17817.7 |  | 17817.7 |  | 0

## #9454.00 PM TIME
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910B
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18000 | 18000 |  |  | 18000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 18000 | 78.17 | 78.17 | 17921.83
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 18000 | 400.8 | 478.97 | 17521.03
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 18000 | 186.94 | 665.91 | 17334.09
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 18000 | 1660.7 | 2326.61 | 15673.39
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 18000 | 328.12 | 2654.73 | 15345.27
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 18000 | 2187.6 | 4842.33 | 13157.67
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 18000 | 150.11 | 4992.44 | 13007.56
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 18000 | 994.9 | 5987.34 | 12012.66
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 18000 | 93.52 | 6080.86 | 11919.14
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 18000 | 936.9 | 7017.76 | 10982.24
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 18000 | 96.04 | 7113.8 | 10886.2
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 18000 | 1027.7 | 8141.5 | 9858.5
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 18000 | 352.04 | 8493.54 | 9506.46
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 18000 | 1521.7 | 10015.24 | 7984.76
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 18000 | 129.62 | 10144.86 | 7855.14
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 18000 | 927.2 | 11072.06 | 6927.94
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 18000 | 193.33 | 11265.39 | 6734.61
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 18000 | 1327.8 | 12593.19 | 5406.81
[5 empty] | 18000 |  | 12593.19 | 5406.81
[5 empty] | 18000 |  | 12593.19 | 5406.81
[5 empty] | 18000 |  | 12593.19 | 5406.81
|  |  | Totals: | 18000 |  | 12593.19 |  | 5406.81
Note on E9: Huggins, Joni [DAS]: Re: PM Time Posted Inbox Adams, Brandon 1:48 PM (14 minutes ago) to me Joni, Please set my PM Time for MM25 9454.00 at $18,000. Regards, Brandon Adams Owner's Representative, State Design & Construction Resou

## #9454.00 Misc
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 169
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525292902 | 2024-10-18 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1136 | 425.88 | 425.88
PRC 33525355900 | 2024-12-20 | 9500 | CNST | Brockway Mechanical V#(00002116146) | Inv. R8510 | 500 | 925.88
PRC 33525010910 | 2025-01-10 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2621892 | 827.5 | 1753.38
PRC 33525027902 | 2025-01-27 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1280 | 569.48 | 2322.86
PRC 33525076905 | 2025-03-17 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV047464 | 334.52 | 2657.38
CDE 33525114901 | 2025-04-24 | 9500 | CNST | Moving RapidsReproduction INVCL1280 From MM25 9454.00 to MM22 9354.00 | Inv. INVCL1280 | -569.48 | 2087.9
2087.9
2087.9
2087.9
2087.9
2087.9
2087.9
|  |  |  | Totals: |  | 2087.9

## #9454.00 Horizon Architecture
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945400-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525284903 | 2024-10-10 | PO Procore | 18400 | 18400 |  |  | 18400
PRC 3352528PA4903 | 2024-11-06 | Inv. 9454.00-01 |  | 18400 | 3196.88 | 3196.88 | 15203.12
PRC 3352528PB4903 | 2024-12-03 | Inv. 9454.00-02 |  | 18400 | 2580 | 5776.88 | 12623.12
PRC 3352528PC4903 | 2025-01-14 | Inv. 9454.00-03 |  | 18400 | 4240.25 | 10017.13 | 8382.87
PRC 3352528PD4903 | 2025-04-07 | Inv. 9454.00-04 |  | 18400 | 1720.37 | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  |  |  | 18400 |  | 11737.5 | 6662.5
|  | Totals: | 18400 |  | 11737.5 |  | 6662.5
|  | Design Docs | 4262.5 |  | 4262.5 |  | 0
|  | Construction Docs | 6057.5 |  | 6057.5 |  | 0
|  | Bidding/Negoiation | 1417.5 |  | 1417.5 |  | 0
|  | Construction Phase | 5912.5 |  |  |  | 5912.5
|  | Reimbursables | 750 |  |  |  | 750
|  | Total: | 18400 |  | 11737.5 |  | 6662.5

## #9454.00 Brockway Mechanical
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Brockway Mechanical & Roofing |  |  | Vendor: 00002116146
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945400-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525088902 | 2025-03-28 | PO Procore | 132778 | 132778 |  |  | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  |  |  | 132778 |  | 0 | 132778
|  | Totals: | 132778 |  | 0 |  | 132778

## #9454.00 Samuels Group (2)
DOC ICIW Building 9 Roof Replacement
Project # 9454.00
Program code 9454.00 |  |  | Major Program 4B01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525097906 | 2025-04-07 | PO Procore | 25593.76 | 25593.76 |  |  | 25593.76
PRC 3352509PA7906 | 2025-05-08 | Inv. 7764.01 CA |  | 25593.76 | 3747.36 | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  |  |  | 25593.76 |  | 3747.36 | 21846.4
|  | Totals: | 25593.76 |  | 3747.36 |  | 21846.4
|  | CM Services | 25093.76 |  | 3722.36 |  | 21371.4
|  | Reimbursables | 500 |  | 25 |  | 475
|  | Total: | 25593.76 |  | 3747.36 |  | 21846.4

## RECAP #9455.00
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
| Program code 945500 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1000000
C | Samuels Group |  | 27943.26 | 27943.26 | 0
| PM TIME |  | 50000 | 7703.15 | 42296.85
| Misc. |  | 0 | 0 | 0
C | OPN Architects |  | 44140 | 44140 | 0
| OPN Architects (2) |  | 343780 | 0 | 343780
| Total Project Cost | 1000000 | 465863.26 | 79786.41 | 386076.85 | 534136.74

## #9455.00 Samuels Group
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525283902 | 2024-10-09 | PO Procore | 45969.22 | 45969.22 |  |  | 45969.22
PRC 3352528PA3902 | 2024-11-07 | Inv. 7729.01945500 |  | 45969.22 | 2068.79 | 2068.79 | 43900.43
PRC 3352528PB3902 | 2024-12-06 | Inv. 7729.02945500 |  | 45969.22 | 7340.12 | 9408.91 | 36560.31
PRC 3352528PC3902 | 2025-01-14 | Inv. 7729.03945500 |  | 45969.22 | 3632.7 | 13041.61 | 32927.61
PRC 3352528PD3902 | 2025-02-05 | Inv. 7729.04945500 |  | 45969.22 | 4268.45 | 17310.06 | 28659.16
PRC 3352528PE3902 | 2025-03-06 | Inv. 7729.05945500 |  | 45969.22 | 2478.12 | 19788.18 | 26181.04
PRC 3352528PF3902 | 2025-04-08 | Inv. 7729.06945500 |  | 45969.22 | 1232.95 | 21021.13 | 24948.09
PRC 3352528PG3902 | 2025-05-09 | Inv. 7729.07945500 |  | 45969.22 | 3631.85 | 24652.98 | 21316.24
PRC 3352528PH3902 | 2025-05-29 | Inv. 7729.08945500-FINAL | -18025.96 | 27943.26 | 3290.28 | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  |  |  | 27943.26 |  | 27943.26 | 0
|  | Totals: | 27943.26 |  | 27943.26 |  | 0 | FINAL
|  | CM Services: | 24902.16 |  | 24902.16 |  | 0
|  | Reimbursables: | 3041.1 |  | 3041.1 |  | 0
|  | Total: | 27943.26 |  | 27943.26 |  | 0

## #9455.00 PM TIME
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910C
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 50000 | 50000 |  |  | 50000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 50000 | 270.93 | 270.93 | 49729.07
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 50000 | 1802.7 | 2073.63 | 47926.37
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 50000 | 160.93 | 2234.56 | 47765.44
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 50000 | 1068.1 | 3302.66 | 46697.34
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 50000 | 60.05 | 3362.71 | 46637.29
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 50000 | 601.8 | 3964.51 | 46035.49
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 50000 | 18.56 | 3983.07 | 46016.93
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 50000 | 197.9 | 4180.97 | 45819.03
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 50000 | 238.44 | 4419.41 | 45580.59
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 50000 | 1032.3 | 5451.71 | 44548.29
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 50000 | 135.67 | 5587.38 | 44412.62
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 50000 | 969.2 | 6556.58 | 43443.42
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 50000 | 145.67 | 6702.25 | 43297.75
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 50000 | 1000.9 | 7703.15 | 42296.85
[5 empty] | 50000 |  | 7703.15 | 42296.85
[5 empty] | 50000 |  | 7703.15 | 42296.85
|  |  | Totals: | 50000 |  | 7703.15 |  | 42296.85
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (3 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9455.00 Misc
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - Jennie E |  |  |  | Shipping Code 231A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9455.00 OPN Architects
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945500-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320905 | 2024-11-15 | PO Procore | 44140 | 44140 |  |  | 44140
PRC 3352532PA0905 | 2025-01-27 | Inv. 24843000-1 |  | 44140 | 29132.4 | 29132.4 | 15007.6
PRC 3352532PB0905 | 2025-04-14 | Inv. 24843000-2 |  | 44140 | 15007.6 | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  |  |  | 44140 |  | 44140 | 0
|  | Totals: | 44140 |  | 44140 |  | 0 | FINAL

## #9455.00 OPN Architects (2)
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
OPN Architects (2) |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945500-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525114900 | 2025-04-23 | PO Procore | 343780 | 343780 |  |  | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  |  |  | 343780 |  | 0 | 343780
|  | Totals: | 343780 |  | 0 |  | 343780
|  | Design Development | 80570 |  |  |  | 80570
|  | Construction Documents | 119900 |  |  |  | 119900
|  | Bidding/Negotiation | 6460 |  |  |  | 6460
|  | Construction Admin | 102090 |  |  |  | 102090
|  | Rake Rhodes Engineers | 3000 |  |  |  | 3000
|  | Reimbursables | 31760 |  |  |  | 31760
|  | Total: | 343780 |  | 0 |  | 343780

## RECAP #9456.00
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
| Program code 945600 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 403525
C | Samuels Group |  | 22669.34 | 22669.34 | 0
| PM TIME |  | 13000 | 2948.3 | 10051.7
| Misc. |  | 1460.99 | 1460.99 | 0
| CMBA Architects |  | 28645 | 18526 | 10119
| McKinnis Roofing |  | 243401 | 0 | 243401
| Total Project Cost | 403525 | 309176.33 | 45604.63 | 263571.7 | 94348.67

## #9456.00 Samuels Group
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298909 | 2024-10-24 | PO Procore | 24471.92 | 24471.92 |  |  | 24471.92
PRC 3352529PA8909 | 2024-11-06 | Inv. 7734.01945600 |  | 24471.92 | 1048.51 | 1048.51 | 23423.41
PRC 3352529PB8909 | 2025-01-13 | Inv. 7734.02945600 |  | 24471.92 | 2713.5 | 3762.01 | 20709.91
PRC 3352529PC8909 | 2025-02-05 | Inv. 7734.03945600 |  | 24471.92 | 5115.51 | 8877.52 | 15594.4
PRC 3352529PD8909 | 2025-03-06 | Inv. 7734.04945600 |  | 24471.92 | 5168.25 | 14045.77 | 10426.15
PRC 3352529PE8909 | 2025-04-08 | Inv. 7734.05945600 |  | 24471.92 | 1330.34 | 15376.11 | 9095.81
PRC 3352529PF8909 | 2025-05-09 | Inv. 7734.06945600 |  | 24471.92 | 5275.2 | 20651.31 | 3820.61
PRC 3352529PG8909 | 2025-05-29 | Inv. 7734.07945600-FINAL | -1802.58 | 22669.34 | 2018.03 | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  |  |  | 22669.34 |  | 22669.34 | 0
|  | Totals: | 22669.34 |  | 22669.34 |  | 0 | FINAL
|  | CM Services | 21631.92 |  | 21631.92 |  | 0
|  | Reimbursables | 1037.42 |  | 1037.42 |  | 0
|  | Total: | 22669.34 |  | 22669.34 |  | 0

## #9456.00 PM TIME
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910D
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13000 | 13000 |  |  | 13000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 28.94 | 28.94 | 12971.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 191.6 | 220.54 | 12779.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 16.45 | 236.99 | 12763.01
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 107.1 | 344.09 | 12655.91
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 34.59 | 378.68 | 12621.32
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 343.5 | 722.18 | 12277.82
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13000 | 81.28 | 803.46 | 12196.54
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13000 | 867.5 | 1670.96 | 11329.04
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13000 | 64.46 | 1735.42 | 11264.58
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13000 | 278 | 2013.42 | 10986.58
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13000 | 75.78 | 2089.2 | 10910.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13000 | 543 | 2632.2 | 10367.8
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13000 | 40.5 | 2672.7 | 10327.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13000 | 275.6 | 2948.3 | 10051.7
[5 empty] | 13000 |  | 2948.3 | 10051.7
[5 empty] | 13000 |  | 2948.3 | 10051.7
|  |  | Totals: | 13000 |  | 2948.3 |  | 10051.7
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (4 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9456.00 Misc
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 231A
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525055900 | 2025-02-25 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2629554 | 1021.25 | 1021.25
PRC 33525140903 | 2025-05-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048431 | 439.74 | 1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
1460.99
|  |  |  | Totals: |  | 1460.99

## #9456.00 CMBA Architects
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
CMBA Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945600-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023906 | 2025-01-23 | PO Procore | 28645 | 28645 |  |  | 28645
PRC 3352502PA3906 | 2025-02-24 | Inv. 65173 |  | 28645 | 3250 | 3250 | 25395
PRC 3352502PB3906 | 2025-03-17 | Inv. 65253 |  | 28645 | 4430 | 7680 | 20965
PRC 3352502PC3906 | 2025-04-24 | Inv. 65418 |  | 28645 | 7440 | 15120 | 13525
PRC 3352502PD3906 | 2025-05-14 | Inv. 65545 |  | 28645 | 3406 | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  | Totals: | 28645 |  | 18526 |  | 10119
|  | Design Development | 6160 |  | 6160 |  | 0
|  | Construction Documents | 8460 |  | 8460 |  | 0
|  | Bidding/Negotiation | 2900 |  | 2900 |  | 0
|  | Construction Phase | 10125 |  | 506 |  | 9619
|  | Reimbursables | 1000 |  | 500 |  | 500
|  | Total: | 28645 |  | 18526 |  | 10119

## #9456.00 McKinnis Roofing
IDOE ISD Elementary School Roof Replacement
Project # 9456.00
Program code 945600 |  |  | Major Program 4E02
McKinnis Roofing |  |  | Vendor: 00003217305
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945600-01
Project Manager - Jennie E |  |  | Activity code: Brum
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525129901 | 2025-05-09 | PO Procore | 24341 | 24341 |  |  | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  |  |  | 24341 |  | 0 | 24341
|  | Totals: | 243401 |  | 0 |  | 243401

## RECAP #9457.00
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
| Program code 945700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 405525
C | Samuels Group |  | 22739.45 | 22739.45 | 0
| PM TIME |  | 13000 | 2948.3 | 10051.7
| Misc. |  | 2594.76 | 2594.76 | 0
| CMBA Architects |  | 28645 | 18526 | 10119
| Martino Commercial Roofing |  | 245404 | 0 | 245404
| Total Project Cost | 405525 | 312383.21 | 46808.51 | 265574.7 | 93141.79

## #9457.00 Samuels Group
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525298908 | 2024-10-24 | PO Procore | 24471.92 | 24471.92 |  |  | 24471.92
PRC 3352529PA8908 | 2025-01-13 | Inv. 7735.01945700 |  | 24471.92 | 5145.5 | 5145.5 | 19326.42
PRC 3352529PB8908 | 2024-02-05 | Inv. 7735.02945700 |  | 24471.92 | 4330.81 | 9476.31 | 14995.61
PRC 3352529PC8908 | 2025-03-06 | Inv. 7735.03945700 |  | 24471.92 | 4118.39 | 13594.7 | 10877.22
PRC 3352529PD8908 | 2025-04-08 | Inv. 7735.04945700 |  | 24471.92 | 1429.23 | 15023.93 | 9447.99
PRC 3352529PE8908 | 2025-05-08 | Inv. 7735.05945700 |  | 24471.92 | 5364.57 | 20388.5 | 4083.42
PRC 3352529PF8908 | 2025-05-29 | Inv. 7735.06945700-FINAL | -1732.47 | 22739.45 | 2350.95 | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  |  |  | 22739.45 |  | 22739.45 | 0
|  | Totals: | 22739.45 |  | 22739.45 |  | 0 | FINAL
|  | CM Services | 21631.92 |  | 21631.92 |  | 0
|  | Reimbursables | 1107.53 |  | 1107.53 |  | 0
|  | Total: | 22739.45 |  | 22739.45 |  | 0

## #9457.00 PM TIME
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910E
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 13000 | 13000 |  |  | 13000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 13000 | 28.94 | 28.94 | 12971.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 13000 | 191.6 | 220.54 | 12779.46
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 13000 | 16.45 | 236.99 | 12763.01
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 13000 | 107.1 | 344.09 | 12655.91
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 13000 | 34.59 | 378.68 | 12621.32
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 13000 | 343.5 | 722.18 | 12277.82
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13000 | 81.28 | 803.46 | 12196.54
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13000 | 867.5 | 1670.96 | 11329.04
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13000 | 64.46 | 1735.42 | 11264.58
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13000 | 278 | 2013.42 | 10986.58
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13000 | 75.78 | 2089.2 | 10910.8
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13000 | 543 | 2632.2 | 10367.8
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13000 | 40.5 | 2672.7 | 10327.3
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13000 | 275.6 | 2948.3 | 10051.7
[5 empty] | 13000 |  | 2948.3 | 10051.7
[5 empty] | 13000 |  | 2948.3 | 10051.7
|  |  | Totals: | 13000 |  | 2948.3 |  | 10051.7
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (4 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9457.00 Misc
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 231A
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525090906 | 2025-03-31 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2636754 | 2152.5 | 2152.5
PRC 33525140902 | 2025-05-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048460 | 442.26 | 2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
2594.76
|  |  |  | Totals: |  | 2594.76

## #9457.00 CMBA Architects
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
CMBA Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945700-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525023907 | 2025-01-23 | PO Procore | 28645 | 28645 |  |  | 28645
PRC 3352502PA3907 | 2025-02-24 | Inv. 65172 |  | 28645 | 3250 | 3250 | 25395
PRC 3352502PB3907 | 2025-03-17 | Inv. 65252 |  | 28645 | 4430 | 7680 | 20965
PRC 3352502PC3907 | 2025-04-25 | Inv. 65417 |  | 28645 | 7440 | 15120 | 13525
PRC 3352502PD3907 | 2025-05-14 | Inv. 65544 |  | 28645 | 3406 | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  |  |  | 28645 |  | 18526 | 10119
|  | Totals: | 28645 |  | 18526 |  | 10119
|  | Design Development | 6160 |  | 6160 |  | 0
|  | Construction Documents | 8460 |  | 8460 |  | 0
|  | Bidding/Negotiation | 2900 |  | 2900 |  | 0
|  | Construction Phase | 10125 |  | 506 |  | 9619
|  | Reimbursables: | 1000 |  | 500 |  | 500
|  | Total: | 28645 |  | 18526 |  | 10119

## #9457.00 Martino Commercial
IDOE ISD High School Gym Roof Replacement
Project # 9457.00
Program code 945700 |  |  | Major Program 4E02
Martino Commercial Roofing |  |  | Vendor: 00003228049
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945700-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525132901 | 2025-05-09 | PO Procore | 245404 | 245404 |  |  | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  |  |  | 245404 |  | 0 | 245404
|  | Totals: | 245404 |  | 0 |  | 245404

## RECAP #9458.00
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
| Program code 945800 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 630000
C | McGough Construction |  | 8788.77 | 8788.77 | 0
| PM TIME |  | 10000 | 7287.98 | 2712.02
| Misc. |  | 0 | 0 | 0
| Resource Consulting Engineers |  | 36000 | 28800 | 7200
| Proctor Mechanical |  | 140100 | 110599.63 | 29500.37
| McGough Construction (2) |  | 34904.76 | 0 | 34904.76
| Riley Armstrong Plumbing & Heating |  | 299175 | 0 | 299175
| Total Project Cost | 630000 | 528968.53 | 155476.38 | 373492.15 | 101031.47

## #9458.00 McGough
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525312906 | 2025-11-07 | PO Procore | 15563.96 | 15563.96 |  |  | 15563.96
PRC 3352531PA2906 | 2025-01-27 | Inv. 101368.003PC-01 |  | 15563.96 | 2151.48 | 2151.48 | 13412.48
PRC 3352531PB2906 | 2025-02-15 | Inv. 101368.003PC-02 |  | 15563.96 | 739.53 | 2891.01 | 12672.95
PRC 3352531PC2906 | 2025-03-17 | Inv. 101368.003PC-03A* |  | 15563.96 | 989.01 | 3880.02 | 11683.94
PRC 3352531PD2906 | 2025-04-25 | Inv. 101368.003PC-04A |  | 15563.96 | 2671.17 | 6551.19 | 9012.77
PRC 3352531PE2906 | 2025-05-09 | Inv. 101368.003PC-05A FINAL | -6775.19 | 8788.77 | 2237.58 | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  |  |  | 8788.77 |  | 8788.77 | 0
|  | Totals: | 8788.77 |  | 8788.77 |  | 0 | FINAL
|  | CM Services | 8551.77 |  | 8551.77 |  | 0
|  | Reimbursables | 237 |  | 237 |  | 0
|  | Total: | 8788.77 |  | 8788.77 |  | 0
Inv. 101368.003PC-XX* was used by this vendor in another tab. Adding an A to this tab

## #9458.00 PM TIME
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910F
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 10000 | 109.61 | 109.61 | 9890.39
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 10000 | 728.3 | 837.91 | 9162.09
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 10000 | 144.9 | 982.81 | 9017.19
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 10000 | 961 | 1943.81 | 8056.19
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 155.12 | 2098.93 | 7901.07
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 1546.5 | 3645.43 | 6354.57
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 73.69 | 3719.12 | 6280.88
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 787.7 | 4506.82 | 5493.18
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 229.74 | 4736.56 | 5263.44
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 991.9 | 5728.46 | 4271.54
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 64.81 | 5793.27 | 4206.73
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 465.5 | 6258.77 | 3741.23
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10000 | 130.91 | 6389.68 | 3610.32
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10000 | 898.3 | 7287.98 | 2712.02
[5 empty] | 10000 |  | 7287.98 | 2712.02
[5 empty] | 10000 |  | 7287.98 | 2712.02
|  |  | Totals: | 10000 |  | 7287.98 |  | 2712.02
Note on E9: Huggins, Joni [DAS]: PM TIME Budgets $Joni Elliott, Jennie 2:56 PM (5 minutes ago) to me Please establish the following for PM Time budgets in the corresponding projects. 9452.00 - $12,000.00 9455.00 - $50,000.00 9456.00 - $13,000.00 9457.00 - $13,000.00 9458.00 - $10,000.00

## #9458.00 Misc
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 177
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9458.00 Resource Consulting
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Resource Consulting Engineers |  |  | Vendor: 00003224689
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945800-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525010905 | 2025-01-10 | PO Procore | 36000 | 36000 |  |  | 36000
PRC 3352501PA0905 | 2025-03-04 | Inv. 2024.029.00-01 |  | 36000 | 3000 | 3000 | 33000
PRC 3352501PB0905 | 2025-03-06 | Inv. 2024.029.00-02 |  | 36000 | 3000 | 6000 | 30000
PRC 3352501PC0905 | 2025-03-10 | Inv. 2024.029.00-03 |  | 36000 | 7500 | 13500 | 22500
PRC 3352501PD0905 | 2025-03-24 | Inv. 2024.029.00-04 |  | 36000 | 13500 | 27000 | 9000
PRC 3352501PE0905 | 2025-05-19 | Inv. 2024.029.00-05 |  | 36000 | 1800 | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  |  |  | 36000 |  | 28800 | 7200
|  | Totals: | 36000 |  | 28800 |  | 7200
|  | Design Development | 12600 |  | 12600 |  | 0
|  | Construction Documents | 14400 |  | 14400 |  | 0
|  | Bidding/Negotiation | 1800 |  | 1800 |  | 0
|  | Construction Phase | 7200 |  |  |  | 7200
|  | Total: | 36000 |  | 28800 |  | 7200

## #9458.00 Proctor Mechanical
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-MM25-9255 |  |  | MA#21010A
Project Manager - Jennie E |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525043904 | 2025-02-11 | PO Procore | 140100 | 140100 |  |  | 140100
PRC 3352504PA3904 | 2025-05-29 | Inv. 7615.0/1 |  | 140100 | 110599.63 | 110599.63 | 29500.37 | 5821.03
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  |  |  | 140100 |  | 110599.63 | 29500.37
|  | Totals: | 140100 |  | 110599.63 |  | 29500.37

## #9458.00 McGough Construction 2
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525127906 | 2025-05-07 | PO Procore | 34904.76 | 34904.76 |  |  | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  |  |  | 34904.76 |  | 0 | 34904.76
|  | Totals: | 34904.76 |  | 0 |  | 34904.76
|  | CM Services | 32384.76 |  |  |  | 32384.76
|  | Reimbursables | 2520 |  |  |  | 2520
|  | Total: | 34904.76 |  | 0 |  | 34904.76

## #9458.00 Riley Armstrong
DOC NCCF Powerhouse Water Heater Replacements
Project # 9458.00
Program code 945800 |  |  | Major Program 4F04
Rily Armstrong Heating & Plumbing |  |  | Vendor: 00002118365
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945800-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525133910 | 05/12/25 | PO Procore | 299175 | 299175 |  |  | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  |  |  | 299175 |  | 0 | 299175
|  | Totals: | 299175 |  | 0 |  | 299175

## RECAP #9459.00
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
| Program code 945900 |  |  | Major Program 4F03
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 300000
C | McGough Construction |  | 12555.91 | 12555.91 | 0
| PM TIME |  | 12200 | 10097.41 | 2102.59
| Misc. |  | 1556.25 | 1556.25 | 0
| IMEG Corporation |  | 20564 | 14768 | 5796
| McGough Construction (2) |  | 19869.58 | 2718.91 | 17150.67
| Reliable 1 |  | 188499.52 | 0 | 188499.52
| Total Project Cost | 300000 | 255245.26 | 41696.48 | 213548.78 | 44754.74

## #9459.00 McGough Constructi
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525257901 | 2024-09-13 | PO Procore | 16497.41 | 16497.41 |  |  | 16497.41
PRC 3352525PA7901 | 2024-10-14 | Inv. 101174.015-PC01 |  | 16497.41 | 451.24 | 451.24 | 16046.17
PRC 3352525PB7901 | 2024-11-14 | Inv. 101174.015-PC02 |  | 16497.41 | 2489.89 | 2941.13 | 13556.28
PRC 3352525PC7901 | 2024-12-18 | Inv. 101174.015-PC03 |  | 16497.41 | 2689.03 | 5630.16 | 10867.25
PRC 3352525PD7901 | 2025-01-14 | Inv. 101174.015-PC04 |  | 16497.41 | 1908.57 | 7538.73 | 8958.68
PRC 3352525PE7901 | 2025-02-12 | Inv. 101174.015-PC05 |  | 16497.41 | 2297.07 | 9835.8 | 6661.61
PRC 3352525PF7901 | 2025-03-21 | Inv. 101174.015-PC06 |  | 16497.41 | 1571.86 | 11407.66 | 5089.75
PRC 3352525PG7901 | 2025-04-14 | Inv. 101174.015-PC07 Final | -3941.5 | 12555.91 | 1148.25 | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  |  |  | 12555.91 |  | 12555.91 | 0
|  | Totals: | 12555.91 |  | 12555.91 |  | 0 | FINAL
|  | CM Services: | 12155.91 |  | 12155.91 |  | 0
|  | Reimbursables: | 400 |  | 400 |  | 0
|  | Total: | 12555.91 |  | 12555.91 |  | 0

## #9459.00 PM TIME
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910G
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12200 | 12200 |  |  | 12200
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 12200 | 37.89 | 37.89 | 12162.11
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 12200 | 194.4 | 232.29 | 11967.71
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 12200 | 118.33 | 350.62 | 11849.38
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 12200 | 1051.4 | 1402.02 | 10797.98
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 12200 | 210.36 | 1612.38 | 10587.62
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 12200 | 1404.9 | 3017.28 | 9182.72
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 12200 | 225.58 | 3242.86 | 8957.14
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 12200 | 1498.1 | 4740.96 | 7459.04
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 12200 | 41.07 | 4782.03 | 7417.97
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 12200 | 410.1 | 5192.13 | 7007.87
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 12200 | 183.79 | 5375.92 | 6824.08
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 12200 | 1960.8 | 7336.72 | 4863.28
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 12200 | 208.95 | 7545.67 | 4654.33
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 12200 | 903.4 | 8449.07 | 3750.93
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 12200 | 95.32 | 8544.39 | 3655.61
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 12200 | 680.5 | 9224.89 | 2975.11
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 12200 | 111.22 | 9336.11 | 2863.89
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 12200 | 761.3 | 10097.41 | 2102.59
[5 empty] | 12200 |  | 10097.41 | 2102.59
[5 empty] | 12200 |  | 10097.41 | 2102.59
[5 empty] | 12200 |  | 10097.41 | 2102.59
|  |  | Totals: | 12200 |  | 10097.41 |  | 2102.59
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Kleene, Jennifer Wed, Feb 19, 3:56 PM (14 hours ago) to me Please increase the PM Time by $5,000.00 Regards, Jennifer Jennifer Kleene Owner’s Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, IA 50319 515-822-8197 mobile Jennifer.Kleene@iowa.gov https://das.iowa.gov On Wed, Feb 19, 2025 at 10:21 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Jennifer We are negative on PM Time for 9459.00 for MM25 after posting the January billing file Can we increase the budget? Currently -136.72

## #9459.00 Misc
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  |  | Major Program 4F03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 200
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525024908 | 2025-01-24 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2624735 | 1356.25 | 1356.25
PRC 33525088900 | 2025-03-28 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1548 | 200 | 1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
1556.25
|  |  |  | Totals: |  | 1556.25

## #9459.00 IMEG Corporation
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
IMEG Corporation |  |  | Vendor: 00003224175
Acct. Codes-0017-335-MM25-9260 |  |  | RFP945900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525310907 | 2024-11-05 | PO Procore | 20564 | 20564 |  |  | 20564
PRC 3352531PA0907 | 2025-01-03 | Inv. 9459.00-01 |  | 20564 | 6518 | 6518 | 14046
PRC 3352531PB0907 | 2025-03-05 | Inv. 24006792.00-2 |  | 20564 | 7606 | 14124 | 6440
PRC 3352531PC0907 | 2025-04-23 | Inv. 24006792.00-3 |  | 20564 | 644 | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  |  |  | 20564 |  | 14768 | 5796
|  | Totals: | 20564 |  | 14768 |  | 5796
|  | Construction Docs | 13036 |  | 13036 |  | 0
|  | Bidding/Negotiation Assistance | 1088 |  | 1088 |  | 0
|  | Construction Phase | 6440 |  | 644 |  | 5796
|  | Total: | 20564 |  | 14768 |  | 5796

## #9459.00 McGough Construction 2
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525076901 | 2025-03-17 | PO Procore | 19869.58 | 19869.58 |  |  | 19869.58
PRC 3352507PA6901 | 2025-04-14 | Inv. 101174.015CA01 |  | 19869.58 | 205.52 | 205.52 | 19664.06
PRC 3352507PB6901 | 2025-05-09 | Inv. 101174.015CA02 |  | 19869.58 | 2513.39 | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  |  |  | 19869.58 |  | 2718.91 | 17150.67
|  | Totals: | 19869.58 |  | 2718.91 |  | 17150.67
|  | CM Services | 19069.58 |  | 2558.91 |  | 16510.67
|  | Reimbursables | 800 |  | 160 |  | 640
|  | Total: | 19869.58 |  | 2718.91 |  | 17150.67

## #9459.00 Reliable 1
HHS STS A.E. Sheperd AC Replacement
Project # 9459.00
Program code 945900 |  |  | Major Program 4F03
Reliable 1 |  |  | Vendor: 00002120637
Acct. Codes-0017-335-MM25-9255 |  |  | RFB945900-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525076902 | 2025-03-17 | PO Procore | 188499.52 | 188499.52 |  |  | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  |  |  | 188499.52 |  | 0 | 188499.52
|  | Totals: | 188499.52 |  | 0 |  | 188499.52

## RECAP #9460.00
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
| Program code 946000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 2355000
C | Boyd Jones |  | 18622.46 | 18622.46 | 0
| PM TIME |  | 35000 | 12053.98 | 22946.02
| Misc. |  | 219.86 | 219.86 | 0
| Genesis Architectural |  | 19400 | 11800 | 7600
| R3 Commercial Roofing |  | 922000 | 0 | 922000
| Boyd Jones (2) |  | 91055.44 | 1478.4 | 89577.04
| Total Project Cost | 2355000 | 1086297.76 | 44174.7 | 1042123.06 | 1268702.24

## #9460.00 Boyd Jones
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525310906 | 2024-11-05 | PO Procore | 21740.56 | 21740.56 |  |  | 21740.56
PRC 3352531PA0906 | 2024-11-06 | Inv. 9460.00-01 |  | 21740.56 | 4662.66 | 4662.66 | 17077.9
PRC 3352531PB0906 | 2024-12-13 | Inv. 9460.00-02 |  | 21740.56 | 2938.78 | 7601.44 | 14139.12
PRC 3352531PC0906 | 2025-01-10 | Inv. 9460.00-03 |  | 21740.56 | 4246 | 11847.44 | 9893.12
PRC 3352531PD0906 | 2025-02-06 | Inv. 9460.00-04 |  | 21740.56 | 5061.83 | 16909.27 | 4831.29
PRC 3352531PE0906 | 2025-03-11 | Inv. 9460.00-05 - FINAL | -3118.1 | 18622.46 | 1713.19 | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  |  |  | 18622.46 |  | 18622.46 | 0
|  | Totals: | 18622.46 |  | 18622.46 |  | 0 | FINAL
|  | CM Services: | 18450.46 |  | 18450.46 |  | 0
|  | Reimbursables: | 172 |  | 172 |  | 0
|  | Total: | 18622.46 |  | 18622.46 |  | 0

## #9460.00 PM TIME
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910H
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 35000 | 35000 |  |  | 35000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 35000 | 42.67 | 42.67 | 34957.33
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 35000 | 216.8 | 259.47 | 34740.53
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 35000 | 84.24 | 343.71 | 34656.29
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 35000 | 747 | 1090.71 | 33909.29
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 35000 | 175.37 | 1266.08 | 33733.92
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 35000 | 1169.7 | 2435.78 | 32564.22
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 35000 | 275.61 | 2711.39 | 32288.61
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 35000 | 1828.1 | 4539.49 | 30460.51
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 35000 | 116.72 | 4656.21 | 30343.79
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 35000 | 1168.8 | 5825.01 | 29174.99
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 35000 | 165.51 | 5990.52 | 29009.48
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 35000 | 1766.2 | 7756.72 | 27243.28
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 35000 | 351.34 | 8108.06 | 26891.94
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 35000 | 1517.9 | 9625.96 | 25374.04
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 35000 | 159.42 | 9785.38 | 25214.62
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 35000 | 1142.2 | 10927.58 | 24072.42
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 35000 | 143 | 11070.58 | 23929.42
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 35000 | 983.4 | 12053.98 | 22946.02
[5 empty] | 35000 |  | 12053.98 | 22946.02
[5 empty] | 35000 |  | 12053.98 | 22946.02
[5 empty] | 35000 |  | 12053.98 | 22946.02
|  |  | Totals: | 35000 |  | 12053.98 |  | 22946.02

## #9460.00 Misc
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code 174
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525070905 | 2025-03-11 | 9500 | CNST | Rapids ReproductionsV#(00002111375) | Inv. INVCL1522 | 219.86 | 219.86
219.86
219.86
219.86
219.86
219.86
219.86
219.86
219.86
219.86
219.86
219.86
|  |  |  | Totals: |  | 219.86

## #9460.00 Genesis Architectural
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946000-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525339903 | 2024-12-03 | PO Procore | 19400 | 19400 |  |  | 19400
PRC 3352533PA9903 | 2025-01-08 | Inv. 2414-01 |  | 19400 | 7750 | 7750 | 11650
PRC 3352533PB9903 | 2025-05-05 | Inv. 2414-02 |  | 19400 | 4050 | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  |  |  | 19400 |  | 11800 | 7600
|  | Totals: | 19400 |  | 11800 |  | 7600
|  | Schematic Design Docs | 2000 |  | 2000 |  | 0
|  | Design Development Docs | 2950 |  | 2950 |  | 0
|  | Construction Docs | 5600 |  | 5600 |  | 0
|  | Bidding Assistance | 1250 |  | 1250 |  | 0
|  | Construction Phase | 7600 |  |  |  | 7600
|  | Total: | 19400 |  | 11800 |  | 7600

## #9460.00 R3 Commercial Roofing
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
R3 Commerical Roofing |  |  | Vendor: 00003226335
Acct. Codes-0017-335-MM25-9255 |  |  | 946000-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525080907 | 2025-03-21 | PO Procore | 922000 | 922000 |  |  | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  |  |  | 922000 |  | 0 | 922000
|  | Totals: | 922000 |  | 0 |  | 922000

## #9460.00 Boyd Jones (2)
DOC NCF LU B, C & D Roof Replacements
Project # 9460.00
Program code 946000 |  |  | Major Program 4E02
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM25-9255 |  |  | CA MA #RFP1821335228-BoydJones11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525100902 | 2025-04-10 | PO Procore | 91055.44 | 91055.44 |  |  | 91055.44
PRC 3352510PA0902 | 2025-05-08 | Inv. 9460.00-001 |  | 91055.44 | 1478.4 | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  |  |  | 91055.44 |  | 1478.4 | 89577.04
|  | Totals: | 91055.44 |  | 1478.4 |  | 89577.04
|  | CM Services | 44009.44 |  | 1478.4 |  | 42531.04
|  | Reimbursables | 946 |  |  |  | 946
|  | Fee | 46100 |  |  |  | 46100
|  | Total: | 91055.44 |  | 1478.4 |  | 89577.04
Vendor used Inv. 9460.00-0X in previous tab, please use 9460.00-00X

## RECAP #9462.00
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 610000
Samuels Group |  | 29270.96 | 2988.61 | 26282.35
PM TIME |  | 25000 | 2154.75 | 22845.25
Misc. |  | 0 | 0 | 0
Snyder & Associates |  | 82901 | 0 | 82901
Total Project Cost | 610000 | 137171.96 | 5143.36 | 132028.6 | 472828.04

## #9462.00 Samuels Group
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525063900 | 2025-03-05 | PO Procore | 29270.96 | 29270.96 |  |  | 29270.96
PRC 3352506PA3900 | 2025-04-08 | Inv. 7761.01946200 |  | 29270.96 | 990.18 | 990.18 | 28280.78
PRC 3352506PB3900 | 2025-05-12 | Inv. 7761.02946200 |  | 29270.96 | 1998.43 | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  |  |  | 29270.96 |  | 2988.61 | 26282.35
|  | Totals: | 29270.96 |  | 2988.61 |  | 26282.35
|  | CM Services | 24270.96 |  | 2988.61 |  | 21282.35
|  | Reimbursables | 5000 |  |  |  | 5000
|  | Total: | 29270.96 |  | 2988.61 |  | 26282.35

## #9462.00 PM TIME
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  |  | Major Program 3G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910Q
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 25000 | 25000 |  |  | 25000
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 25000 | 8.72 | 8.72 | 24991.28
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 25000 | 85.2 | 93.92 | 24906.08
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 25000 | 18.56 | 112.48 | 24887.52
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 25000 | 197.9 | 310.38 | 24689.62
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 25000 | 18.54 | 328.92 | 24671.08
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 25000 | 79.2 | 408.12 | 24591.88
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 25000 | 146.21 | 554.33 | 24445.67
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 25000 | 1046.7 | 1601.03 | 23398.97
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 25000 | 70.72 | 1671.75 | 23328.25
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 25000 | 483 | 2154.75 | 22845.25
[5 empty] | 25000 |  | 2154.75 | 22845.25
[5 empty] | 25000 |  | 2154.75 | 22845.25
|  |  | Totals: | 25000 |  | 2154.75 |  | 22845.25

## #9462.00 Misc
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  |  | Major Program 3G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 231A
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9462.00 Synder & Associates
DOE ISD South Powerhouse Parking Lot Repair
Project # 9462.00
Program code 946200 |  |  | Major Program 3G01
Synder & Associates |  |  | Vendor: 00002119810
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946200-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525115907 | 2025-04-25 | PO Procore | 82901 | 82901 |  |  | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  |  |  | 82901 |  | 0 | 82901
|  | Totals: | 82901 |  | 0 |  | 82901
|  | Design 50% | 24700 |  |  |  | 24700
|  | Design 95% | 14432 |  |  |  | 14432
|  | Design 100% | 11390 |  |  |  | 11390
|  | Bidding | 9658 |  |  |  | 9658
|  | Construction Admin | 14704 |  |  |  | 14704
|  | Survey | 5017 |  |  |  | 5017
|  | Boundry Survey of Parking Lot | 3000 |  |  |  | 3000
|  | Total: | 82901 |  | 0 |  | 82901

## RECAP #9463.00
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1500000
StoryConstruction |  | 18402.96 | 4852.87 | 13550.09
PM TIME |  | 10000 | 3963.06 | 6036.94
Misc. |  | 0 | 0 | 0
Genesis Architectural Design |  | 27700 | 0 | 27700
Total Project Cost | 1500000 | 56102.96 | 8815.93 | 47287.03 | 1443897.04

## #9463.00 Story Construction
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525016903 | 2025-01-16 | PO Procore | 18402.96 | 18402.96 |  |  | 18402.96
PRC 3352501PA6903 | 2025-03-21 | Inv. 34771 |  | 18402.96 | 3232.63 | 3232.63 | 15170.33
PRC 3352501PB6903 | 2025-04-15 | Inv. 34804 |  | 18402.96 | 919.13 | 4151.76 | 14251.2
PRC 3352501PC6903 | 2025-05-15 | Inv. 34840 |  | 18402.96 | 701.11 | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  |  |  | 18402.96 |  | 4852.87 | 13550.09
|  | Totals: | 18402.96 |  | 4852.87 |  | 13550.09
|  | CM Services | 18314.46 |  | 4823.37 |  | 13491.09
|  | Reimbursables | 88.5 |  | 29.5 |  | 59
|  | Total: | 18402.96 |  | 4852.87 |  | 13550.09

## #9463.00 PM TIME
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 910R
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 10000 | 9.14 | 9.14 | 9990.86
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 10000 | 91.2 | 100.34 | 9899.66
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10000 | 105.89 | 206.23 | 9793.77
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10000 | 1126.6 | 1332.83 | 8667.17
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10000 | 167.1 | 1499.93 | 8500.07
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10000 | 722.6 | 2222.53 | 7777.47
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10000 | 95.32 | 2317.85 | 7682.15
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10000 | 680.5 | 2998.35 | 7001.65
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10000 | 122.61 | 3120.96 | 6879.04
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10000 | 842.1 | 3963.06 | 6036.94
[5 empty] | 10000 |  | 3963.06 | 6036.94
[5 empty] | 10000 |  | 3963.06 | 6036.94
|  |  | Totals: | 10000 |  | 3963.06 |  | 6036.94

## #9463.00 Misc
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code: 564
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9463.00 Genesis Architectural
HHS WRC Birches Window Replacement
Project # 9463.00
Program code 946300 |  |  | Major Program 4G01
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM25-9260 |  |  | RFP946300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525060902 | 2025-02-28 | PO Procore | 27700 | 27700 |  |  | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  |  |  | 27700 |  | 0 | 27700
|  | Totals: | 27700 |  | 0 |  | 27700
|  | Design Development Docs | 8200 |  |  |  | 8200
|  | Construction Docs | 10000 |  |  |  | 10000
|  | Bid Assistance | 1500 |  |  |  | 1500
|  | Construction Phase | 8000 |  |  |  | 8000
|  | Total: | 27700 |  | 0 |  | 27700

## RECAP #9474.00
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
Recap
Acct. Codes-0017-335-MM25
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 100000
Samuels Group |  | 39296.56 | 0 | 39296.56
PM TIME |  | 10000 | 435.65 | 9564.35
Misc. |  | 0 | 0 | 0
Total Project Cost | 100000 | 49296.56 | 435.65 | 48860.91 | 50703.44

## #9474.00 Samuels Group
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  | Major Program 4B02
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM25-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525120900 | 2025-04-30 | PO Procore | 39296.56 | 39296.56 |  |  | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  |  |  | 39296.56 |  | 0 | 39296.56
|  | Totals: | 39296.56 |  | 0 |  | 39296.56
|  | CM Services | 38446.56 |  | 0 |  | 38446.56
|  | Reimbursables | 850 |  |  |  | 850
|  | Total: | 39296.56 |  | 0 |  | 39296.56

## #9474.00 PM TIME
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS 732Y
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10000 | 55.25 | 55.25 | 9944.75
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10000 | 380.4 | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
[5 empty] | 10000 |  | 435.65 | 9564.35
|  |  | Totals: | 10000 |  | 435.65 |  | 9564.35
Note on E9: Huggins, Joni [DAS]: Changes for PM Time $Joni Elliott, Jennie May 4, 2025, 3:12 PM (15 hours ago) to me Can you please make the following change for PM time, thank you! 9388.00 - Please increase PM Time in the "Contracted" line to $15,000.00 9401.00 - Please increase PM Time in the "Contracted" line to $9,000.00 9475.00 - Please Establish a PM Time budget of $7,500.00 9474.00 - Please Establish a PM Time budget of $10,000.00

## #9474.00 Misc
HHS IMHI Boiler #3 Replacement
Project # 9474.00
Program code 947400 |  |  |  | Major Program 4B02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #XXXX.XX
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM25
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM25-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  | 0 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM25-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM25-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0