## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation R60 | 2000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 2000000
| . | Less: Total Assigned |  | 2000000
|  | Total Unassigned / Unallocated |  | 0
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9420.00 | DAS CC Capitol West Stairs & Surrounding Landings Repairs | James T. | 2000000 |  | 2000000 | 1533817.12 | 1087085.48 | 446731.64 | 466182.88
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 2000000 | 0 | 2000000 | 1533817.12 | 1087085.48 | 446731.64 | 466182.88
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 466182.88
[6 empty] | Total funds Available |  |  | 2000000
[6 empty] | Total obligated by contract or PO |  |  | -1533817.12 | 466182.88
[6 empty] | Variance |  |  |  | 0
Note on E15: Huggins, Joni [DAS]: 9420.00 - DAS CC Capitol West Stairs & Surrounding Landings Repair - Increase Budget $Joni Trower, James Aug 6, 2024, 7:46 PM (15 hours ago) to me Finance - Please increase the MM FY25 0017-0001 Capitol Stairs budget for project 9420.00 by $700,000. Thanks, James Trower, Licensed Architect, LEED AP 9420.00 - DAS CC Capitol West Stairs & Surrounding Landings Repairs $Joni Trower, James Tue, Apr 8, 2:41 PM (16 hours ago) to me Finance - Increase project budget for 9420.00 Capitol Stairs funding by $500,000. There should be a total of $2,000,000.00 in Capitol Stairs funding. Thanks, James Trower, Licensed Architect, LEED AP

## RECAP #9420.00
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
| Program code 942000 |  |  | Major Program 4D01
Recap
Acct. Codes-0017-335-0001
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 2000000
C | Neumann Brothers |  | 158157.09 | 158157.09 | 0
| PM TIME |  | 40000 | 31775.18 | 8224.82
| Misc. |  | 4065.61 | 4065.61 | 0
C | Samuels Group |  | 124029.1 | 124029.1 | 0
C | Neumann Brothers (2) |  | 557662.78 | 557662.78 | 0
C | MTS Contracting |  | 17766.85 | 17766.85 | 0
C | MTS Contracting (2) |  | 34653.74 | 34653.74 | 0
| Samuels Group (2) |  | 65217.8 | 58332.9 | 6884.9
| OPN Architects |  | 79936 | 67054.88 | 12881.12
C | MTS Contracting (3) |  | 30328.15 | 30328.15 | 0
| Neumann Brothers (3) |  | 422000 | 3259.2 | 418740.8
| Total Project Cost | 2000000 | 1533817.12 | 1087085.48 | 446731.64 | 466182.88

## #9420.00 Neumann Brothers
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Neumann Brothers |  |  | Vendor: 00002106354
Acct. Codes-0017-335-0001-9255 |  |  | MA20436D
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525187925 | 2024-07-05 | PO Procore | 262788 | 262788 |  |  | 262788
PRC 3352518PA7925 | 2024-10-14 | Inv. 56410 |  | 262788 | 52678.36 | 52678.36 | 210109.64 | 2772.54
PRC 3352518PB7925 | 2024-10-31 | Inv. 56508 |  | 262788 | 21145.29 | 73823.65 | 188964.35 | 3885.45
PRC 3352518PC7925 | 2024-11-12 | Inv. 56509 |  | 262788 | 23248.89 | 97072.54 | 165715.46 | 5109.08
PRC 3352518PD7925 | 2024-12-03 | Inv. 56510 |  | 262788 | 33279.39 | 130351.93 | 132436.07 | 6860.63
PRC 3352518PE7925 | 2024-12-23 | Inv. 56650 |  | 262788 | 19897.3 | 150249.23 | 112538.77 | 7907.86
PRC 3352518PF7925 | 2025-01-31 | Inv. 56665-Retainage | -104630.91 | 158157.09 | 7907.86 | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  |  |  | 158157.09 |  | 158157.09 | 0
|  | Totals: | 158157.09 |  | 158157.09 |  | 0 | FINAL
|  | Labor 1268hrs @93.30 | 71141.25 |  | 71141.25 |  | 0
|  | Materials | 75173.76 |  | 75173.76 |  | 0
|  | Labor OT 240hrs @114.77 | 4533.42 |  | 4533.42 |  | 0
|  | Project Manager 60Hrs @115 | 6900 |  | 6900 |  | 0
|  | Labor Double Time 240hrs @136.22 | 408.66 |  | 408.66 |  | 0
|  |  | 158157.09 |  | 158157.09 |  | 0

## #9420.00 PM TIME
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  |  | Major Program 4D01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-0001-xxxx |  |  |  | eDAS E2DW
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 40000 | 40000 |  |  | 40000
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 40000 | 243.87 | 243.87 | 39756.13
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 40000 | 2660.8 | 2904.67 | 37095.33
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 40000 | 403.52 | 3308.19 | 36691.81
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 40000 | 2055.4 | 5363.59 | 34636.41
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 40000 | 271.59 | 5635.18 | 34364.82
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 40000 | 2414.8 | 8049.98 | 31950.02
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 40000 | 439.27 | 8489.25 | 31510.75
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 40000 | 2923.5 | 11412.75 | 28587.25
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 40000 | 191.56 | 11604.31 | 28395.69
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 40000 | 1274.1 | 12878.41 | 27121.59
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 40000 | 144.85 | 13023.26 | 26976.74
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 40000 | 1447.7 | 14470.96 | 25529.04
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 40000 | 146.95 | 14617.91 | 25382.09
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 40000 | 1567.2 | 16185.11 | 23814.89
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 40000 | 390.66 | 16575.77 | 23424.23
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 40000 | 1688.3 | 18264.07 | 21735.93
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 40000 | 371.57 | 18635.64 | 21364.36
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 40000 | 2658.8 | 21294.44 | 18705.56
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 40000 | 244.8 | 21539.24 | 18460.76
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 40000 | 1679.8 | 23219.04 | 16780.96
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 40000 | 175.75 | 23394.79 | 16605.21
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 40000 | 1374.8 | 24769.59 | 15230.41
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 40000 | 131.78 | 24901.37 | 15098.63
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 40000 | 1022.2 | 25923.57 | 14076.43
CDE 33526246821 | 2025-09-11 | 2507 | Move expense from 9997.26 |  | 40000 | 169.68 | 26093.25 | 13906.75
CDE 33526246821 | 2025-09-11 | 9500 | Move expense from 9997.26 |  | 40000 | 1854.9 | 27948.15 | 12051.85
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 40000 | 207.44 | 28155.59 | 11844.41
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 40000 | 1599.6 | 29755.19 | 10244.81
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 40000 | 193.67 | 29948.86 | 10051.14
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 40000 | 997.3 | 30946.16 | 9053.84
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 40000 | 75.92 | 31022.08 | 8977.92
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 40000 | 753.1 | 31775.18 | 8224.82
[5 empty] | 40000 |  | 31775.18 | 8224.82
|  |  | Totals: | 40000 |  | 31775.18 |  | 8224.82
Note on E9: Huggins, Joni [DAS]: Re: PM Time Posted $Joni Trower, James 9:22 AM (5 minutes ago) to me Finance - Please see below modifications in red: On Wed, Oct 8, 2025 at 3:04 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: 0001 9420.00 (946.16) INCREASE PMTIME BY $10,000 MM23 9373.00 (149.58) INCREASE PM TIME BY $149.58 AND CLOSE MM26 9498.00 (238.59) SET UP PM TIME FOR $7,000

## #9420.00 Misc
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  |  | Major Program 4D01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-0001-xxxx |  |  |  | Shipping Code 035
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525003904 | 2025-01-03 | 9500 | BRUM | Waldinger Corp V#(00002116105) | Inv. 82244E-001 | 1191.16 | 1191.16
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Heating/Ventilation/Air Condidioning/Plumbing | Inv. DAS2025091153 | 2354.35 | 3545.51
PRC 33526275906 | 2025-10-03 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV051574 | 520.1 | 4065.61
4065.61
4065.61
4065.61
4065.61
4065.61
4065.61
4065.61
4065.61
4065.61
|  |  |  | Totals: |  | 4065.61

## #9420.00 Samuels Group
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-0001-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525187926 | 2024-07-05 | PO Procore | 75929.32 | 75929.32 |  |  | 75929.32
PRC 3352518PA7926 | 2024-08-08 | Inv. 7705.01940200 |  | 75929.32 | 13456.74 | 13456.74 | 62472.58
PO 33525187926 | 2024-09-06 | CO #1 | 7712.4 | 83641.72 |  | 13456.74 | 70184.98
PRC 3352518PB7926 | 2024-09-13 | Inv. 7705.02940200 |  | 83641.72 | 13861.42 | 27318.16 | 56323.56
PRC 3352518PC7926 | 2024-10-02 | Inv. 7705.03940200 |  | 83641.72 | 14921.06 | 42239.22 | 41402.5
PRC 3352518PD7926 | 2024-11-12 | Inv. 7705.04940200 |  | 83641.72 | 17913.06 | 60152.28 | 23489.44
PO 33525187926 | 2024-11-15 | CO #2 | 52939.82 | 136581.54 |  | 60152.28 | 76429.26
PRC 3352518PE7926 | 2024-12-05 | Inv. 7705.0594200-FINAL | -12552.44 | 124029.1 | 63876.82 | 124029.1 | 0
|  |  |  | 124029.1 |  | 124029.1 | 0
|  |  |  | 124029.1 |  | 124029.1 | 0
|  |  |  | 124029.1 |  | 124029.1 | 0
|  |  |  | 124029.1 |  | 124029.1 | 0
|  |  |  | 124029.1 |  | 124029.1 | 0
|  | Totals: | 124029.1 |  | 124029.1 |  | 0 | FINAL
|  | CM Services | 60789.92 |  | 60789.92 |  | 0
|  | Reimbursables | 99.51 |  | 99.51 |  | 0
|  | Fee | 13139.4 |  | 13139.4 |  | 0
|  | CO #1 | 6840.98 |  | 6840.98 |  | 0
|  | CO #2 | 43159.29 |  | 43159.29 |  | 0
|  | Total | 124029.1 |  | 124029.1 |  | 0

## #9420.00 Neumann Brothers (2)
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Neumann Brothers |  |  | Vendor: 00002106354
Acct. Codes-0017-335-0001-9255 |  |  | MA20436D
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525222900 | 2024-08-09 | PO Procore | 488893 | 488893 |  |  | 488893
PO 33525222900 | 2024-09-06 | CO #1 | 12149 | 501042 |  | 0 | 501042
PO 33525222900 | 2024-10-14 | CO #2 | 171854.06 | 672896.06 |  | 0 | 672896.06
PO 33525222900 | 2024-10-25 | CO #3 | 28577.08 | 701473.14 |  | 0 | 701473.14
PRC 3352522PA2900 | 2024-11-22 | Inv. 56511 |  | 701473.14 | 266030.42 | 266030.42 | 435442.72 | 14001.6
PO 33525222900 | 2024-11-22 | CO #4 | 21482.96 | 722956.1 |  | 266030.42 | 456925.68
PRC 3352522PB2900 | 2024-12-11 | Inv. 56608 |  | 722956.1 | 162253.95 | 428284.37 | 294671.73 | 22541.28
PO 33525222900 | 2024-12-11 | CO #5 No Cost CO | 0 | 722956.1 |  | 428284.37 | 294671.73
PRC 3352522PC2900 | 2025-01-07 | Inv. 56651 |  | 722956.1 | 72396.16 | 500680.53 | 222275.57 | 26351.61
PO 33525222900 | 2025-02-05 | CO #6 | -156553.23 | 566402.87 |  | 500680.53 | 65722.34
PRC 3352522PD2900 | 2025-02-17 | Inv. 56708 |  | 566402.87 | 10933.87 | 511614.4 | 54788.47 | 26927.08
PRC 3352522PE2900 | 2025-07-16 | Inv. 57014-FINAL* |  | 566402.87 | 17555.62 | 529170.02 | 37232.85 | 27851.06
PRC 3352522PF2900 | 2025-07-24 | Inv. 57052 |  | 566402.87 | 609.61 | 529779.63 | 36623.24 | 27883.15
PRC 3352522PG2900 | 2025-08-18 | Inv. 57094 Retainage | -8740.09 | 557662.78 | 27883.15 | 557662.78 | 1.819e-11
|  |  |  | 557662.78 |  | 557662.78 | 1.819e-11
|  | Totals: | 557662.78 |  | 557662.78 |  | 0 | FINAL
|  | Labor 1585hrs @93.30 | 147881 |  | 147881 |  | 0
|  | Materials | 233942.62 |  | 233942.62 |  | 0
|  | Labor OT 240hrs @114.77 | 37300.25 |  | 37300.25 |  | 0
|  | Project Manager 60Hrs @115 | 9200 |  | 9200 |  | 0
|  | Labor Double Time 240hrs @136.22 | 3950.38 |  | 3950.38 |  | 0
|  | CO #1 | 0 |  |  |  | 0
|  | CO #2 | 113879.19 |  | 113879.19 |  | 0
|  | CO #3 | 0 |  |  |  | 0
|  | CO #4 | 11509.34 |  | 11509.34 |  | 0
|  | CO #5 | 0 |  |  |  | 0
|  | CO #6 | 0 |  |  |  | 0
|  | Total: | 557662.78 |  | 557662.78 |  | 0

## #9420.00 MTS Contracting
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0017-335-0001-9255 |  |  | MA005 20243C
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525262900 | 2024-08-09 | PO Procore | 20358.4 | 20358.4 |  |  | 20358.4
PRC 3352526PA2900 | 2024-12-05 | Inv. 24-5620A |  | 20358.4 | 16878.51 | 16878.51 | 3479.89 | 888.34
PRC 3352526PB2900 | 2025-01-03 | Inv. 24-5620ARetainage | -2591.55 | 17766.85 | 888.34 | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  |  |  | 17766.85 |  | 17766.85 | 0
|  | Totals: | 17766.85 |  | 17766.85 |  | 0 | FINAL

## #9420.00 MTS Contracting (2)
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
MTS Contracting (2) |  |  | Vendor: 00003067019
Acct. Codes-0017-335-0001-9255 |  |  | MA005 20243C
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525267903 | 2024-09-23 | PO Procore | 38889.93 | 38889.93 |  |  | 38889.93
PRC 3352526PA7903 | 2024-12-05 | Inv. 24-5620B |  | 38889.93 | 30133.76 | 30133.76 | 8756.17 | 1585.98
PO 33525267903 | 2024-12-11 | CO #1 No Cost CO | 0 | 38889.93 |  | 30133.76 | 8756.17
PRC 3352526PB7903 | 2024-12-27 | Inv. 24-5620B2 |  | 38889.93 | 2787.3 | 32921.06 | 5968.87 | 1732.68
PRC 3352526PC7903 | 2025-01-09 | Inv. 24-5620B2 Retainage | -4236.19 | 34653.74 | 1732.68 | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  |  |  | 34653.74 |  | 34653.74 | 0
|  | Totals: | 34653.74 |  | 34653.74 |  | 0 | FINAL

## #9420.00 Samuels Group (2)
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0017-335-0001-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525003910 | 2025-01-03 | PO Procore | 65217.8 | 65217.8 |  |  | 65217.8
PRC 3352500PA3910 | 2025-02-06 | Inv. 7747.01942000 |  | 65217.8 | 6934.69 | 6934.69 | 58283.11
PRC 3352500PB3910 | 2025-03-06 | Inv. 7747.02942000 |  | 65217.8 | 3608.08 | 10542.77 | 54675.03
PRC 3352500PC3910 | 2025-04-08 | Inv. 7747.03942000 |  | 65217.8 | 9413.08 | 19955.85 | 45261.95
PRC 3352500PD3910 | 2025-05-08 | Inv. 7747.04942000 |  | 65217.8 | 3953.73 | 23909.58 | 41308.22
PRC 3352500PE3910 | 2025-06-12 | Inv. 7747.05942000 |  | 65217.8 | 7513.53 | 31423.11 | 33794.69
PRC 3352500PF3910 | 2025-07-08 | Inv. 7747.06942000 |  | 65217.8 | 8117.84 | 39540.95 | 25676.85 | FY25
PO 33526003910 | 2025-08-21 | Roll to FY26 | 0 | 65217.8 |  | 39540.95 | 25676.85
PRC 3352600PG3910 | 2025-09-08 | Inv. 7747.07942000 |  | 65217.8 | 5508.23 | 45049.18 | 20168.62
PRC 3352600PH3910 | 2025-09-10 | Inv. 7747.08942000 |  | 65217.8 | 12216.81 | 57265.99 | 7951.81
PRC 3352600PI3910 | 2026-10-07 | Inv. 7747.09942000 |  | 65217.8 | 1066.91 | 58332.9 | 6884.9
|  |  |  | 65217.8 |  | 58332.9 | 6884.9
|  |  |  | 65217.8 |  | 58332.9 | 6884.9
|  | Totals: | 65217.8 |  | 58332.9 |  | 6884.9
|  | CM Close Out Services | 24972.43 |  | 24433.44 |  | 538.99
|  | Reimbursables | 2500 |  | 483.84 |  | 2016.16
|  | Bid Issuance 1 & 2 | 9777.55 |  | 9777.55 |  | 0
|  | Total: | 37249.98 |  | 34694.83 |  | 2555.15
|  | CM Services for Bid Issuance 3 | 27767.82 |  | 23638.07 |  | 4129.75
|  | Bid Issuance 3 Reimbursables | 200 |  |  |  | 200
|  | Total: | 27967.82 |  | 23638.07 |  | 4329.75
|  | Grand Total: | 65217.8 |  | 58332.9 |  | 6884.9

## #9420.00 OPN Architects
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-0001-9260 |  |  | -
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525016902 | 2025-01-16 | PO Procore | 73864 | 73864 |  |  | 73864
PRC 3352501PA6902 | 2025-03-11 | Inv. 19802019-1 |  | 73864 | 35224.8 | 35224.8 | 38639.2
PRC 3352501PB6902 | 2025-06-10 | Inv. 19802019-2 |  | 73864 | 3906.34 | 39131.14 | 34732.86 | FY25
PO 33526016902 | 2025-08-21 | Roll to FY26 | 0 | 73864 |  | 39131.14 | 34732.86
PRC 3352601PC6902 | 2025-09-08 | Inv. 19802019-3 |  | 73864 | 2200 | 41331.14 | 32532.86
PRC 3352601PD6902 | 2025-09-10 | Inv. 19802019-4 |  | 73864 | 2200 | 43531.14 | 30332.86
PRC 3352601PE6902 | 2025-10-13 | Inv. 19802019-5 |  | 73864 | 5589.92 | 49121.06 | 24742.94
PO 33526016902 | 2025-10-15 | CO #1 | 6072 | 79936 |  | 49121.06 | 30814.94
PRC 3352601PF6902 | 2025-11-10 | Inv. 19802019-6 |  | 79936 | 17933.82 | 67054.88 | 12881.12
|  |  |  | 79936 |  | 67054.88 | 12881.12
|  |  |  | 79936 |  | 67054.88 | 12881.12
|  |  |  | 79936 |  | 67054.88 | 12881.12
|  |  |  | 79936 |  | 67054.88 | 12881.12
|  | Totals: | 79936 |  | 67054.88 |  | 12881.12
|  | Remaining in Bid Issuance | 11204 |  | 11204 |  | 0
|  | Construction Field Observations | 2800 |  |  |  | 2800
|  | Construction Documents | 34020 |  | 34020 |  | 0
|  | Bidding/Negotiation | 4400 |  | 4400 |  | 0
|  | Cost Estimates | 5000 |  | 5000 |  | 0
|  | Construction Admin | 16440 |  | 6358.88 |  | 10081.12
|  | CO #1 | 6072 |  | 6072 |  | 0
|  | Total: | 79936 |  | 67054.88 |  | 12881.12

## #9420.00 MTS Contracting (3)
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
MTS Contracting (3) |  |  | Vendor: 00003067019
Acct. Codes-0017-335-0001-9255 |  |  | MA005 20243C
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525128900 | 2025-05-08 | PO Procore | 35155.04 | 35155.04 |  |  | 35155.04
PRC 3352512PA8900 | 2025-07-15 | Inv. 25-5962F-FINAL |  | 35155.04 | 28811.74 | 28811.74 | 6343.3 | 1516.4074
PRC 3352512PB8900 | 2025-08-18 | Inv. 25-5962-Retainage | -4826.89 | 30328.15 | 1516.41 | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  |  |  | 30328.15 |  | 30328.15 | 0
|  | Totals: | 30328.15 |  | 30328.15 |  | 0 | FINAL
|  | Materials | 5815.04 |  | 5815.04 |  | 0
|  | Mason | 24513.11 |  | 24513.11 |  | 0
|  | Total: | 30328.15 |  | 30328.15 |  | 0

## #9420.00 Neumann Brothers (3)
DAS CC Capitol West Stairs & Surrounding Landings Repairs
Project # 9420.00
Program code 942000 |  |  | Major Program 4D01
Neumann Brothers (3) |  |  | Vendor: 00002106354
Acct. Codes-0017-335-0001-9255 |  |  | RFB942000-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526254902 | 2025-09-11 | PO Procore | 422000 | 422000 |  |  | 422000
PRC 3352625PA4902 | 2025-10-10 | Inv. 57253 |  | 422000 | 3259.2 | 3259.2 | 418740.8 | 100.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  |  |  | 422000 |  | 3259.2 | 418740.8
|  | Totals: | 422000 |  | 3259.2 |  | 418740.8

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-0001
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-0001-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-0001-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-0001-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0