## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation R51 | 5364500
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 5364500
| . | Less: Total Assigned |  | 5364500
|  | Total Unassigned / Unallocated |  | 0
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9436.00 | DAS TH Residence Elevator Replacement | James T. | 799500 | 0 | 799500 | 775879.22 | 774772.06 | 1107.16 | 23620.78 | 1107.16
| 9440.00 | DAS CC Elevator Replacements | Brad T. | 4565000 |  | 4565000 | 4421607.19 | 2963848.45 | 1457758.74 | 143392.81 | 38123.63
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 5364500 | 0 | 5364500 | 5197486.41 | 3738620.51 | 1458865.9 | 167013.59 | 39230.79
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 167013.59
[6 empty] | Total funds Available |  |  | 5364500
[6 empty] | Total obligated by contract or PO |  |  | -5197486.41 | 167013.59
[6 empty] | Variance |  |  |  | -2.3283e-10
Note on E15: Jurgenson, John [DAS]: 9436.00 - DAS TH Residence Elevator Replacement Inbox Trower, James 12:05 PM (33 minutes ago) to me Finance - Please increase project 9436.00 R51 by $80,000. Thanks, James Trower, Licensed Architect, LEED AP 9436.00 - DAS TH Residence Elevator Replacement - R51 $Joni Trower, James 9:47 AM (34 minutes ago) to me Finance - Please increase funding for project 9436.00 (R51 Funding) by $135,000. Thanks, James Trower, Licensed Architect, LEED 9436.00 - DAS TH Residence Elevator Replacement - Funding Increase $Joni Trower, James 10:29 AM (5 minutes ago) to me Finance - Please increase the budget for project 9436.00 by $49,500.00. Thanks, James Trower, Licensed Architect, LEED AP Tonyan, Brad 12:48 PM (20 minutes ago) to me, Joni, Brent, Brad, Matthew, Charlee, James, Brad Finance, Just wanted to bring you up to speed on project 9440.00 as this will be dual funding between R51 and X674. Note that the R51 funding is already set up in Procore and the DAS Billables but we need to set up the X674 funding for project 9440.00. X674 - Please set up the overall budget of $400,000 - Please set up PM time as $5,000 R51 Fund Adjustments - Please reduce the budget on 9440.00 by $35,000 and shift those funds to James Trower project 9436.00. Please reach out to me directly if you have any questions and let me know once this is completed. Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E16: Huggins, Joni [DAS]: Tonyan, Brad 12:48 PM (20 minutes ago) to me, Joni, Brent, Brad, Matthew, Charlee, James, Brad Finance, Just wanted to bring you up to speed on project 9440.00 as this will be dual funding between R51 and X674. Note that the R51 funding is already set up in Procore and the DAS Billables but we need to set up the X674 funding for project 9440.00. X674 - Please set up the overall budget of $400,000 - Please set up PM time as $5,000 R51 Fund Adjustments - Please reduce the budget on 9440.00 by $35,000 and shift those funds to James Trower project 9436.00. Please reach out to me directly if you have any questions and let me know once this is completed. Thank you, Brad Tonyan, CPM, LEED Green Associate

## RECAP #9436.00
DAS TH Residence Elevator Replacement
Project # 9436.00
| Program code 943600 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-2000
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 799500
C | DCI Group |  | 23472.83 | 23472.83 | 0
| PM TIME |  | 24000 | 22892.84 | 1107.16
| Misc. |  | 1230.32 | 1230.32 | 0
C | OPN Architects |  | 74850 | 74850 | 0
C | Bergstrom Construction |  | 24800 | 24800 | 0
C | Schumacher Elevator |  | 291074 | 291074 | 0
C | All Iowa Mechanical |  | 24600 | 24600 | 0
C | Air Con Electric |  | 49692 | 49692 | 0
C | DCI Group (2) |  | 119895.79 | 119895.79 | 0
C | Johnson Controls |  | 5360 | 5360 | 0
C | Johnson Controls (2) |  | 116731.47 | 116731.47 | 0
C | Johnson Controls (3) |  | 0 | 0 | 0
C | Basepoint-Access Controls |  | 14244.11 | 14244.11 | 0
C | Johnson Controls (4) |  | 5928.7 | 5928.7 | 0
| Total Project Cost | 799500 | 775879.22 | 774772.06 | 1107.16 | 23620.78

## #9436.00 DCI Group
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-2000-9255 |  |  | RFP1821335228-DC11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525257906 | 2024-09-13 | PO Procore | 19937.17 | 19937.17 |  |  | 19937.17
PRC 3352525PA7906 | 2024-10-25 | Inv. 24-039 PC-01 |  | 19937.17 | 2847.46 | 2847.46 | 17089.71
PRC 3352525PB7906 | 2024-11-22 | Inv. 24-039 PC 02 |  | 19937.17 | 3897.56 | 6745.02 | 13192.15
PO 33525257906 | 2024-12-27 | CO #1 | 4500 | 24437.17 |  | 6745.02 | 17692.15
PRC 3352525PC7906 | 2025-01-03 | Inv. 24-039 PC 03 |  | 24437.17 | 4445.81 | 11190.83 | 13246.34
PRC 3352525PD7906 | 2025-01-14 | Inv. 24-039 PC 04 |  | 24437.17 | 3251.78 | 14442.61 | 9994.56
PRC 3352525PE7906 | 2025-02-17 | Inv. 24-039 PC 05 |  | 24437.17 | 6353.38 | 20795.99 | 3641.18
PRC 3352525PF7906 | 2025-04-22 | Inv. 24-039 PC 06 FINAL INV | -964.34 | 23472.83 | 2676.84 | 23472.83 | 0
|  |  |  | 23472.83 |  | 23472.83 | 0
|  |  |  | 23472.83 |  | 23472.83 | 0
|  |  |  | 23472.83 |  | 23472.83 | 0
|  |  |  | 23472.83 |  | 23472.83 | 0
|  |  |  | 23472.83 |  | 23472.83 | 0
|  | Totals: | 23472.83 |  | 23472.83 |  | 0 | FINAL

## #9436.00 PM TIME
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-2000-xxxx |  |  |  | eDAS E2FZ
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 24000 | 24000 |  |  | 24000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 24000 | 128.76 | 128.76 | 23871.24
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 24000 | 1145.4 | 1274.16 | 22725.84
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 24000 | 79.53 | 1353.69 | 22646.31
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 24000 | 535.2 | 1888.89 | 22111.11
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 24000 | 119.88 | 2008.77 | 21991.23
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 24000 | 796.6 | 2805.37 | 21194.63
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 24000 | 91.27 | 2896.64 | 21103.36
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 24000 | 909.8 | 3806.44 | 20193.56
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 24000 | 84.65 | 3891.09 | 20108.91
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 24000 | 900.3 | 4791.39 | 19208.61
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 24000 | 226.78 | 5018.17 | 18981.83
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 24000 | 981.5 | 5999.67 | 18000.33
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 24000 | 197.1 | 6196.77 | 17803.23
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 24000 | 1410.7 | 7607.47 | 16392.53
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 24000 | 72.27 | 7679.74 | 16320.26
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 24000 | 495 | 8174.74 | 15825.26
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 24000 | 36.03 | 8210.77 | 15789.23
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 24000 | 281.5 | 8492.27 | 15507.73
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 24000 | 108.57 | 8600.84 | 15399.16
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 24000 | 846.1 | 9446.94 | 14553.06
CDE 33526246821 | 2025-09-11 | 2507 | Move expense from 9997.26 |  | 24000 | 110.44 | 9557.38 | 14442.62
CDE 33526246821 | 2025-09-11 | 9500 | Move expense from 9997.26 |  | 24000 | 1211.1 | 10768.48 | 13231.52
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 24000 | 141.72 | 10910.2 | 13089.8
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 24000 | 1092.3 | 12002.5 | 11997.5
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 24000 | 209.29 | 12211.79 | 11788.21
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 24000 | 1076.6 | 13288.39 | 10711.61
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 24000 | 211.44 | 13499.83 | 10500.17
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 24000 | 2098 | 15597.83 | 8402.17
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 24000 | 156.1 | 15753.93 | 8246.07
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 24000 | 994.1 | 16748.03 | 7251.97
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 24000 | 163.65 | 16911.68 | 7088.32
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 24000 | 1856.2 | 18767.88 | 5232.12
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 24000 | 78.51 | 18846.39 | 5153.61
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 24000 | 979.8 | 19826.19 | 4173.81
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 24000 | 177.45 | 20003.64 | 3996.36
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 24000 | 2042.1 | 22045.74 | 1954.26
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 24000 | 92.7 | 22138.44 | 1861.56
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 24000 | 754.4 | 22892.84 | 1107.16
[5 empty] | 24000 |  | 22892.84 | 1107.16
|  |  | Totals: | 24000 |  | 22892.84 |  | 1107.16
Note on E9: Huggins, Joni [DAS]: Fwd: 9436.00 - DAS TH Residence Elevator Replacement $Joni Trower, James 11:27 AM (19 minutes ago) to me Finance - 9436.00 - DAS TH Residence Elevator Replacement Please set up $16,000.00 in PM Time Thanks, James Trower, Licensed Architect, LEED AP 9436.00 - DAS TH Residence Elevator Replacement - PM Time $Joni Trower, James 9:34 AM (1 hour ago) to me Finance - Please increase PM Time by $3,000.00 for project 9436.00 (R51 funding). Thanks, James Re: February PM Time Posted $Joni Trower, James 10:46 AM (3 minutes ago) to me Finance - See below in red: 2000 9436.00 $1,045.74 Increase PM Time by $3,000 MM24 9407.00 $1,028.00 Increase PM Time by $2,000 Thanks, James

## #9436.00 Misc
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-2000-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525114400 | 2025-04-23 | 9500 | CNST | Beeline BlueV#( 00002108204) | Inv. INV046722 | 694 | 694
IET 33526316906 | 2025-11-12 | 9255 | BRUM | ICN - October 2025 | Inv. 732691-943600 | 536.32 | 1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
1230.32
|  |  |  | Totals: |  | 1230.32

## #9436.00 OPN Architects
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-2000-9260 |  |  | RFP943600-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525291901 | 2024-10-17 | PO Procore | 74850 | 74850 |  |  | 74850
PRC 3352529PA1901 | 2024-12-18 | Inv. 24835000-1 |  | 74850 | 28409.32 | 28409.32 | 46440.68
PRC 3352529PB1901 | 2025-01-14 | Inv. 24835000-2 |  | 74850 | 16103.98 | 44513.3 | 30336.7
PRC 3352529PC1901 | 2025-03-05 | Inv. 24835000-3 |  | 74850 | 5475.65 | 49988.95 | 24861.05
PRC 3352529PD1901 | 2025-03-14 | Inv. 24835000-4 |  | 74850 | 6156.05 | 56145 | 18705
PRC 3352529PE1901 | 2025-04-15 | Inv. 24835000-5 |  | 74850 | 1877.78 | 58022.78 | 16827.22
PRC 3352529PF1901 | 2025-05-08 | Inv. 24835000-6 |  | 74850 | 2231.47 | 60254.25 | 14595.75
PRC 3352529PG1901 | 2025-06-19 | Inv. 24835000-7 |  | 74850 | 2151.94 | 62406.19 | 12443.81
PRC 3352529PH1901 | 2025-07-11 | Inv. 24835000-8 |  | 74850 | 2151.94 | 64558.13 | 10291.87 | FY25
PO 33526291901 | 2025-08-22 | Roll to FY26 | 0 | 74850 |  | 64558.13 | 10291.87
PRC 3352629PI1901 | 2025-09-10 | Inv. 24835000-9 |  | 74850 | 2432.62 | 66990.75 | 7859.25
PRC 3352629PJ1901 | 2025-09-16 | Inv. 24835000-10 |  | 74850 | 2245.5 | 69236.25 | 5613.75
PRC 3352629PK1901 | 2025-10-08 | Inv. 24835000-11 |  | 74850 | 2245.5 | 71481.75 | 3368.25
PRC 3352629PL1901 | 2025-11-07 | Inv. 24835000-12 |  | 74850 | 1075.97 | 72557.72 | 2292.28
PRC 3352629PM1901 | 2026-03-25 | Inv. 24835000-13 |  | 74850 | 2292.28 | 74850 | 4.0927e-12
|  |  |  | 74850 |  | 74850 | 4.0927e-12
|  |  |  | 74850 |  | 74850 | 4.0927e-12
|  | Totals: | 74850 |  | 74850 |  | 0 | FINAL

## #9436.00 Bergstrom Construction
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0017-335-2000-9255 |  |  | RFB943600-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525052907 | 2025-02-21 | PO Procore | 29800 | 29800 |  |  | 29800
PRC 3352505PA2907 | 2025-06-05 | Inv. 8780-1 |  | 29800 | 7805.44 | 7805.44 | 21994.56 | 410.81 | FY25
PO 33526052907 | 2025-08-22 | Roll to FY26 | 0 | 29800 |  | 7805.44 | 21994.56
PRC 3352605PB2907 | 2025-09-22 | Inv. 8780-2 |  | 29800 | 6728.37 | 14533.81 | 15266.19 | 764.94
PRC 3352605PC2907 | 2025-11-10 | Inv. 8780-3 |  | 29800 | 7021.68 | 21555.49 | 8244.51 | 1134.51
PO 33526052907 | 2025-12-16 | CO #1 | -5000 | 24800 |  | 21555.49 | 3244.51
PRC 3352605PD2907 | 2026-01-22 | Inv. 8780-4 |  | 24800 | 2004.5 | 23559.99 | 1240.01 | 1240.01
PRC 3352605PE2907 | 2026-01-26 | Inv. 8780-retainage |  | 24800 | 1240.01 | 24800 | 2.0464e-12
|  |  |  | 24800 |  | 24800 | 2.0464e-12
|  |  |  | 24800 |  | 24800 | 2.0464e-12
|  |  |  | 24800 |  | 24800 | 2.0464e-12
|  |  |  | 24800 |  | 24800 | 2.0464e-12
|  |  |  | 24800 |  | 24800 | 2.0464e-12
|  | Totals: | 24800 |  | 24800 |  | 0 | FINAL

## #9436.00 Schumacher Elevator
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Schumacher Elevator |  |  | Vendor: 00002108471
Acct. Codes-0017-335-2000-9255 |  |  | RFB943600-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525062903 | 2025-02-21 | PO Procore | 287674 | 287674 |  |  | 287674
PRC 3352506PA2903 | 2025-07-23 | Inv. 90654107 |  | 287674 | 11162.5 | 11162.5 | 276511.5 | 587.5 | FY25
PO 33526062903 | 2025-08-22 | Roll to FY26 | 0 | 287674 |  | 11162.5 | 276511.5 |  |  | `
PRC 3352606PB2903 | 2025-09-18 | Inv. 90657357 |  | 287674 | 35150 | 46312.5 | 241361.5 | 2437.5
PRC 3352606PC2903 | 2025-10-03 | Inv. 90660736 |  | 287674 | 120553.1 | 166865.6 | 120808.4 | 8782.4
PO 33526062903 | 2025-12-16 | CO #1 | 3400 | 291074 |  | 166865.6 | 124208.4
PRC 3352606PD2903 | 2026-01-05 | Inv. 90663108 |  | 291074 | 103690.6 | 270556.2 | 20517.8 | 14239.8
PRC 3352606PE2903 | 2026-02-04 | Inv. 90671130 |  | 291074 | 5964.1 | 276520.3 | 14553.7 | 14553.7
PRC 3352606PF2903 | 2026-02-10 | Inv. 9346.00-Retainage |  | 291074 | 14553.7 | 291074 | -1.2733e-11
|  |  |  | 291074 |  | 291074 | -1.2733e-11
|  |  |  | 291074 |  | 291074 | -1.2733e-11
|  |  |  | 291074 |  | 291074 | -1.2733e-11
|  |  |  | 291074 |  | 291074 | -1.2733e-11
|  | Totals: | 291074 |  | 291074 |  | 0

## #9436.00 All Iowa Mechanical
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
All Iowa Mechanical |  |  | Vendor: VS000009118
Acct. Codes-0017-335-2000-9255 |  |  | RFB943600-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525063904 | 2025-03-05 | PO Procore | 24600 | 24600 |  |  | 24600
PRC 3352506PA3904 | 2025-07-17 | Inv. 9436.00 - 01 |  | 24600 | 8569 | 8569 | 16031 | 451 | FY25
PO 33526063904 | 2025-08-22 | Roll to FY26 | 0 | 24600 |  | 8569 | 16031
PRC 3352606PB3904 | 2025-10-29 | Inv. 9436.00-02 |  | 24600 | 6920.75 | 15489.75 | 9110.25 | 815.25
PRC 3352606PC3904 | 2026-02-03 | Inv. 9436.00-03 |  | 24600 | 5524.25 | 21014 | 3586 | 1106
PRC 3352606PD3904 | 2026-02-16 | Inv. 9436.00-04 |  | 24600 | 1406 | 22420 | 2180 | 1180
PRC 3352606PE3904 | 2026-06-13 | Inv. 9436.00-05 |  | 24600 | 950 | 23370 | 1230 | 1230
PRC 3352606PF3904 | 2026-03-26 | Inv. 9436.00-06 - Retainage |  | 24600 | 1230 | 24600 | 0
|  |  |  | 24600 |  | 24600 | 0
|  |  |  | 24600 |  | 24600 | 0
|  |  |  | 24600 |  | 24600 | 0
|  |  |  | 24600 |  | 24600 | 0
|  |  |  | 24600 |  | 24600 | 0
|  | Totals: | 24600 |  | 24600 |  | 0 | FINAL

## #9436.00 Air Con Electric
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Air Con Electric |  |  | Vendor: 00003095844
Acct. Codes-0017-335-2000-9255 |  |  | RFB #943600-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525063905 | 2025-03-05 | PO Procore | 39998 | 39998 |  |  | 39998
PRC 3352506PA3905 | 2025-06-05 | Inv. 1874 |  | 39998 | 2137.5 | 2137.5 | 37860.5 | 112.5
PRC 3352506PB3905 | 2025-07-17 | Inv. 1893 |  | 39998 | 3291.75 | 5429.25 | 34568.75 | 285.75 | FY25
PO 33526063905 | 2025-08-22 | Roll to FY26 | 0 | 39998 |  | 5429.25 | 34568.75
PRC 3352606PC3905 | 2025-10-10 | Inv. 1904 |  | 39998 | 9213.1 | 14642.35 | 25355.65 | 770.65
PRC 3352606PD3905 | 2025-10-23 | Inv. 1923 |  | 39998 | 9659.98 | 24302.33 | 15695.67 | 1279.07
PRC 3352606PE3905 | 2025-11-10 | Inv. 1934 |  | 39998 | 12745.77 | 37048.1 | 2949.9 | 1949.9
PO 33526063905 | 2026-01-07 | CO #1 | 9694 | 49692 |  | 37048.1 | 12643.9
PRC 3352606PF3905 | 2026-02-06 | Inv. 1955 |  | 49692 | 10159.3 | 47207.4 | 2484.6 | 2484.6
PRC 3352606PG3905 | 2026-02-10 | Inv. 9436.00-Retainage |  | 49692 | 2484.6 | 49692 | 2.2737e-12
|  |  |  | 49692 |  | 49692 | 2.2737e-12
|  |  |  | 49692 |  | 49692 | 2.2737e-12
|  |  |  | 49692 |  | 49692 | 2.2737e-12
|  | Totals: | 49692 |  | 49692 |  | 0

## #9436.00 DCI Group (2)
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-2000-9255 |  |  | RFP1821335228-DC11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525105907 | 2025-04-15 | PO Procore | 128545.99 | 128545.99 |  |  | 128545.99
PRC 3352510PA5907 | 2025-05-08 | Inv. 24-032 CA 01 |  | 128545.99 | 4770.75 | 4770.75 | 123775.24
PRC 3352510PB5907 | 2025-06-19 | Inv. 24-032 CA 02 |  | 128545.99 | 10491.3 | 15262.05 | 113283.94
PRC 3352510PC5907 | 2025-07-17 | Inv. 24-032 CA 03 |  | 128545.99 | 8199.99 | 23462.04 | 105083.95 | FY25
PO 33526105907 | 2025-08-22 | Roll to FY26 | 0 | 128545.99 |  | 23462.04 | 105083.95
PRC 3352610PD5907 | 2025-09-10 | Inv. 24-032 CA 04 |  | 128545.99 | 6583.9 | 30045.94 | 98500.05
PRC 3352610PE5907 | 2025-09-22 | Inv. 24-032 CA 05 |  | 128545.99 | 18724.83 | 48770.77 | 79775.22
PRC 3352610PF5907 | 2025-10-09 | Inv. 24-032 CA 06 |  | 128545.99 | 32038.03 | 80808.8 | 47737.19
PRC 3352610PG5907 | 2025-11-21 | Inv. 24-032 CA 07 |  | 128545.99 | 30217.75 | 111026.55 | 17519.44 |  | `
PRC 3352610PH5907 | 2025-12-29 | Inv. 24-032 CA 08 |  | 128545.99 | 3140.27 | 114166.82 | 14379.17
PRC 3352610PI5907 | 2026-01-23 | Inv. 24-032 CA 09 |  | 128545.99 | 2750.93 | 116917.75 | 11628.24
PRC 3352610PJ5907 | 2026-02-23 | Inv. 24-032 CA FINAL | -8650.2 | 119895.79 | 2978.04 | 119895.79 | 0
|  |  |  | 119895.79 |  | 119895.79 | 0
|  | Totals: | 119895.79 |  | 119895.79 |  | 0 | FINAL
|  | CM Staff Hours | 96005.15 |  | 96005.15 |  | 0
|  | Reimbursables Expense | 1874.96 |  | 1874.96 |  | 0
|  | Project Fee | 22015.68 |  | 22015.68 |  | 0
|  | Totals: | 119895.79 |  | 119895.79 |  | 0

## #9436.00 Johnson Controls
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Johnson Controls-Sprinkler |  |  | Vendor: 00002102328
Acct. Codes-0017-335-2000-9255 |  |  | MA24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525127901 | 2025-05-07 | DO Procore |  | 0 |  |  | 0 | FY25
PO 33526127901 | 2025-08-29 | Roll to FY26 | 0 | 0 |  | 0 | 0
PO 33526127901A | 2025-12-10 | Opening as Encumbered | 5360 | 5360 |  | 0 | 5360
PRC 3352612PA7901A | 2026-02-23 | Inv. 53778746 |  | 5360 | 5360 | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  |  |  | 5360 |  | 5360 | 0
|  | Totals: | 5360 |  | 5360 |  | 0 | FINAL

## #9436.00 Johnson Controls (2)
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Johnson Controls -Fire Alarm (2) |  |  | Vendor: 00002139022
Acct. Codes-0017-335-2000-9255 |  |  | MA 24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
DO 33525141901 | 2025-05-21 | DO Procore | 116731.47 | 116731.47 |  |  | 116731.47 |  | FY25
PO 33526141901 | 2025-08-22 | Roll to FY26 | 0 | 116731.47 |  | 0 | 116731.47
PRC 3352614PA1901 | 2025-10-27 | Inv. 41846815 |  | 116731.47 | 5956.44 | 5956.44 | 110775.03 | 313.5
PRC 3352614PB1901 | 2026-01-05 | Inv. 41852406 |  | 116731.47 | 93445.4 | 99401.84 | 17329.63 | 5231.67
PRC 3352614PC1901 | 2026-01-15 | Inv. 41864153 |  | 116731.47 | 11493.06 | 110894.9 | 5836.57 | 5836.57
PRC 3352614PD1901 | 2026-01-20 | Inv. 41865188 - Retainage |  | 116731.47 | 5836.57 | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  |  |  | 116731.47 |  | 116731.47 | 5.457e-12
|  | Totals: | 116731.47 |  | 116731.47 |  | 0
Refer to the Remit address on vendor's invoice

## #9436.00 Johnson Controls ( (3)
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Johnson Controls-Fire Protection(3) |  |  | Vendor: 00002139022
Acct. Codes-0017-335-2000-9255 |  |  | MA24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526040921 | 2026-02-09 | DO Procore | 568.7 | 568.7 |  |  | 568.7
DO 33526040921 | 2026-02-10 | Cancelling DO per PM Email | -568.7 | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
Note on C10: Huggins, Joni [DAS]: 9436.00 - DAS TH Residence Elevator Replacement - D.O.s 335 Trower, James Attachments 8:15 AM (10 minutes ago) to me, Mike Joni - It's been a poor experience with Johnson Controls, Inc. (JCI) sprinkler again. I issued Contract #DO-9436.00-009 ($5,360.00) to JCI at the start of the project. To my record, JCI did not submit an invoice for the base scope of work. There was change issued by the design professional and JCI proceeded with work prior to a change order. After the work had been completed for months, JCI sent the attached document, which created a lot of confusion. I issued Contract #DO-9436.00-014 ($568.70) to reconcile their $5,928.70 amount. Now JCI is setting that they need $5,928.70 in addition to the $5,360.00 D.O. that was initially submitted. At this point, the State and our CM have spent thousands of dollars, as usual, on JCI and their invoices & contract changes. Is it possible to cancel Contract #DO-9436.00-014 ($568.70) on your end and I will do an internal deductive change order. I will issue them a new D.O. for $5,928.70 and never use them on a master agreement again. Thanks, James Trower, Licensed Architect, LEED AP

## #9436.00 Basepoint-Access Contr
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Basepoint- Access Controls |  |  | Vendor: 00002115535
Acct. Codes-0017-335-2000-9255 |  |  | MA20360A
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526040922 | 2026-02-09 | DO Procore | 14244.11 | 14244.11 |  |  | 14244.11
PRC 3352604PA0922 | 2026-03-26 | Inv. 178369 |  | 14244.11 | 14244.11 | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  |  |  | 14244.11 |  | 14244.11 | 0
|  | Totals: | 14244.11 |  | 14244.11 |  | 0 | FINAL
|  | Labor | 9697.79 |  | 9697.79 |  | 0
|  | Materials | 4546.32 |  | 4546.32 |  | 0
|  | Totals: | 14244.11 |  | 14244.11 |  | 0

## #9436.00 Johnson Controls (4)
DAS TH Residence Elevator Replacement
Project # 9436.00
Program code 943600 |  |  | Major Program 4D03
Johnson Controls-Sprinkler |  |  | Vendor: 00002139022
Acct. Codes-0017-335-2000-9255 |  |  | MA24023
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526047918 | 2026-02-16 | DO Procore | 5928.7 | 5928.7 |  |  | 5928.7
PRC 3352604PA7918 | 2026-02-23 | Inv. 53816396 |  | 5928.7 | 5928.7 | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  |  |  | 5928.7 |  | 5928.7 | 0
|  | Totals: | 5928.7 |  | 5928.7 |  | 0 | FINAL

## RECAP #9440.00
DAS CC Elevator Replacements
Project # 9440.00
| Program code 944000 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-2000
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 4565000
| OPN Architects |  | 416854 | 371916.5 | 44937.5
| PM TIME |  | 75000 | 36876.37 | 38123.63
| Misc. |  | 17453.46 | 17453.46 | 0
C | DCI Group |  | 28943.39 | 28943.39 | 0
| DCI Group (2) |  | 424038.2 | 225999.98 | 198038.22
| Van Maanen Electrical |  | 392915.14 | 244056.18 | 148858.96
| Proctor Mechanical |  | 131885 | 93102.82 | 38782.18
| Bergstrom Construction |  | 222272 | 195724.69 | 26547.31
| Metro Elevator Great Plains |  | 2712246 | 1749775.06 | 962470.94
| Total Project Cost | 4565000 | 4421607.19 | 2963848.45 | 1457758.74 | 143392.81

## #9440.00 OPN Architects
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-2000-9260 |  |  | RPF94400-01
Project Manager - Brad T. |  |  | Activity Code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525353900 | 2024-12-18 | PO Procore | 378005 | 378005 |  |  | 378005
PO 33525353900 | 2024-12-27 | CO #1 | 38849 | 416854 |  | 0 | 416854
PRC 3352535PA3900 | 2025-01-24 | Inv. 24850000-1 |  | 416854 | 75881.4 | 75881.4 | 340972.6
PRC 3352535PB3900 | 2025-03-07 | Inv. 24850000-2 |  | 416854 | 75884.6 | 151766 | 265088
PRC 3352535PC3900 | 2025-04-16 | Inv. 24850000-3 |  | 416854 | 138186 | 289952 | 126902
PRC 3352535PD3900 | 2025-05-09 | Inv. 24850000-4 |  | 416854 | 14510 | 304462 | 112392
PRC 3352535PE3900 | 2025-06-24 | Inv. 24850000-5 |  | 416854 | 5619.23 | 310081.23 | 106772.77
PRC 3352535PF3900 | 2025-07-15 | Inv. 24850000-6 |  | 416854 | 5621.97 | 315703.2 | 101150.8 | FY25
PO 33526353900 | 2025-08-22 | Roll to FY26 | 0 | 416854 |  | 315703.2 | 101150.8
PRC 3352635PG3900 | 2025-09-10 | Inv. 24850000-7 |  | 416854 | 5619.45 | 321322.65 | 95531.35
PRC 3352635PH3900 | 2025-09-15 | Inv. 24850000-8 |  | 416854 | 5625.46 | 326948.11 | 89905.89
PRC 3352635PI3900 | 2026-10-07 | Inv. 24850000-9 |  | 416854 | 5621.27 | 332569.38 | 84284.62
PRC 3352635PJ3900 | 2025-11-12 | Inv. 24850000-10 |  | 416854 | 5621.7 | 338191.08 | 78662.92
PRC 3352635PK3900 | 2025-12-09 | Inv. 24850000-11 |  | 416854 | 5620.03 | 343811.11 | 73042.89
PRC 3352635PL3900 | 2026-01-12 | Inv. 24850000-12 |  | 416854 | 5621 | 349432.11 | 67421.89
PRC 3352635PM3900 | 2026-02-12 | Inv. 24850000-13 |  | 416854 | 5619.84 | 355051.95 | 61802.05
PRC 3352635PN3900 | 2026-03-11 | Inv. 24850000-14 |  | 416854 | 5621.19 | 360673.14 | 56180.86
PRC 3352635PO3900 | 2026-04-07 | Inv. 24850000-15 |  | 416854 | 5623.91 | 366297.05 | 50556.95
PRC 3352635PP3900 | 2026-05-12 | Inv. 24850000-16 |  | 416854 | 5619.45 | 371916.5 | 44937.5
|  |  |  | 416854 |  | 371916.5 | 44937.5
|  | Totals: | 416854 |  | 371916.5 |  | 44937.5
`
Grimes Building Freight Elevator #113
|  | 50% CDs | 17810 |  | 17810 |  | 0
|  | Final CDs | 15570 |  | 15570 |  | 0
|  | Bid | 1745 |  | 1745 |  | 0
|  | Construction Admin | 11640 |  | 6984 |  | 4656
|  | Totals: | 46765 |  | 42109 |  | 4656
Hoover bldg. Freight Elevator #1494
|  | 50% CDs | 17810 |  | 17810 |  | 0
|  | Final CDs | 15570 |  | 15570 |  | 0
|  | Bid | 1745 |  | 1745 |  | 0
|  | Construction Admin | 11955 |  | 7173 |  | 4782
|  | Totals: | 47080 |  | 42298 |  | 4782
IA Workforce Development Elevator #115
|  | 50% CDs | 14088 |  | 14088 |  | 0
|  | Final CDs | 12948 |  | 12948 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 11008 |  | 6604.8 |  | 4403.2
|  | Totals: | 39369 |  | 34965.8 |  | 4403.2
IA Workforce Development #117
|  | 50% CDs | 14088 |  | 14088 |  | 0
|  | Final CDs | 12948 |  | 12948 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 10908 |  | 6544.8 |  | 4363.2
|  | Totals: | 39269 |  | 34905.8 |  | 4363.2
Lucas Building Freight Traction Elevator #110
|  | 50% CDs | 14928 |  | 14928 |  | 0
|  | Final CDs | 13998 |  | 13998 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 11008 |  | 6604.8 |  | 4403.2
|  | Totals: | 41259 |  | 36855.8 |  | 4403.2
Lucas Bldg Passenger Hydraulic Elevator #4174
|  | 50% CDs | 13668 |  | 13668 |  | 0
|  | Final CDs | 12738 |  | 12738 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 10908 |  | 6544.8 |  | 4363.2
|  | Totals: | 38639 |  | 34275.8 |  | 4363.2
Jesse Parker Bldg Passenger Hydraulic Elevator #120
|  | 50% CDs | 13668 |  | 13668 |  | 0
|  | Final CDs | 12948 |  | 12948 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 10908 |  | 6544.8 |  | 4363.2
|  | Totals: | 38849 |  | 34485.8 |  | 4363.2
Jesse Parker Bldg Passenger Hydraulic Elevator #2502
|  | 50% CDs | 13668 |  | 13668 |  | 0
|  | Final CDs | 12948 |  | 12948 |  | 0
|  | Bid | 1325 |  | 1325 |  | 0
|  | Construction Admin | 10908 |  | 6544.8 |  | 4363.2
|  | Totals: | 38849 |  | 34485.8 |  | 4363.2
Oran Pape Bldg Freight Traction Elevator #11589
|  | 50% CDs | 18370 |  | 18370 |  | 0
|  | Final CDs | 15570 |  | 15570 |  | 0
|  | Bid | 1745 |  | 1745 |  | 0
|  | Construction Admin | 12241 |  | 7344.6 |  | 4896.4
|  | Totals: | 47926 |  | 43029.6 |  | 4896.4
|  | CO #1 | 38849 |  | 34505.1 |  | 4343.9
|  | Total: | 416854 |  | 371916.5 |  | 44937.5

## #9440.00 PM TIME
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-2000-xxxx |  |  |  | eDAS 730O
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 75000 | 44.51 | 44.51 | 74955.49
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 75000 | 395.1 | 439.61 | 74560.39
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 75000 | 42.72 | 482.33 | 74517.67
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 75000 | 283.2 | 765.53 | 74234.47
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 75000 | 144.9 | 910.43 | 74089.57
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 75000 | 962.1 | 1872.53 | 73127.47
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 75000 | 144.85 | 2017.38 | 72982.62
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 75000 | 1448.9 | 3466.28 | 71533.72
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 75000 | 122.63 | 3588.91 | 71411.09
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 75000 | 1304.3 | 4893.21 | 70106.79
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 75000 | 200.25 | 5093.46 | 69906.54
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 75000 | 866.8 | 5960.26 | 69039.74
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 75000 | 136.79 | 6097.05 | 68902.95
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 75000 | 978.5 | 7075.55 | 67924.45
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 75000 | 196 | 7271.55 | 67728.45
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 75000 | 1348 | 8619.55 | 66380.45
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 75000 | 312.8 | 8932.35 | 66067.65
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 75000 | 2446.8 | 11379.15 | 63620.85
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 75000 | 200.68 | 11579.83 | 63420.17
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 75000 | 1556.5 | 13136.33 | 61863.67
CDE 33526246821 | 2025-09-11 | 2507 | Move expense from 9997.26 |  | 75000 | 144.14 | 13280.47 | 61719.53
CDE 33526246821 | 2025-09-11 | 9500 | Move expense from 9997.26 |  | 75000 | 1595.5 | 14875.97 | 60124.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 75000 | 111.21 | 14987.18 | 60012.82
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 75000 | 862.2 | 15849.38 | 59150.62
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 75000 | 209.29 | 16058.67 | 58941.33
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 75000 | 1093.2 | 17151.87 | 57848.13
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 75000 | 135.08 | 17286.95 | 57713.05
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 75000 | 1338.9 | 18625.85 | 56374.15
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 75000 | 223.74 | 18849.59 | 56150.41
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 75000 | 1425 | 20274.59 | 54725.41
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 75000 | 225.73 | 20500.32 | 54499.68
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 75000 | 2564.8 | 23065.12 | 51934.88
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 75000 | 241.27 | 23306.39 | 51693.61
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 75000 | 2997.4 | 26303.79 | 48696.21
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 75000 | 254.81 | 26558.6 | 48441.4
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 75000 | 2933.3 | 29491.9 | 45508.1
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 75000 | 429.76 | 29921.66 | 45078.34
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 75000 | 3484.9 | 33406.56 | 41593.44
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 75000 | 303.81 | 33710.37 | 41289.63
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 75000 | 3166 | 36876.37 | 38123.63
[5 empty] | 75000 |  | 36876.37 | 38123.63
|  |  | Totals: | 75000 |  | 36876.37 |  | 38123.63

## #9440.00 Misc
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-2000-xxxx |  |  |  | Shipping Code: 035
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525115903 | 2025-04-25 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048364 | 1121.8 | 1121.8
PRC 33526350904 | 2025-12-16 | 9500 | BRUM | Johnson Controls V#(00002139022) | Inv. 53616607 / 53604396 | 4476.26 | 5598.06
GAX 33526029903 | 2026-01-29 | 9500 | CNST | Schumacher Elevator V#(00002108471) | Inv. 90671168 | 4765.4 | 10363.46
GAX 33526132906 | 2026-05-12 | 9500 | CNST | PyeBarkerFire&Safety V#(00003216510) | Inv. IV01111200 | 3140 | 13503.46
GAX 33526139901 | 2026-05-19 | 9500 | CNST | PyeBarkerFire&Safety V#(00003216510) | Inv. IV01119522 | 3950 | 17453.46
17453.46
17453.46
17453.46
17453.46
17453.46
17453.46
17453.46
|  |  |  | Totals: |  | 17453.46

## #9440.00 DCI Group
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-2000-9255 |  |  | RFP1821335228-DC11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525313901 | 2024-11-08 | PO Procore | 45016.58 | 45016.58 |  |  | 45016.58
PRC 3352531PA3901 | 2024-12-30 | Inv. 24-044 PC 01 |  | 45016.58 | 2276.64 | 2276.64 | 42739.94
PRC 3352531PB3901 | 2025-01-14 | Inv. 24-044 PC 02 |  | 45016.58 | 2860.88 | 5137.52 | 39879.06
PRC 3352531PC3901 | 2025-02-12 | Inv. 24-044 PC 03 |  | 45016.58 | 1369.6 | 6507.12 | 38509.46
PRC 3352531PD3901 | 2025-03-14 | Inv. 24-044 PC 04 |  | 45016.58 | 4160.96 | 10668.08 | 34348.5
PRC 3352531PE3901 | 2025-04-16 | Inv. 24-044 PC 05 |  | 45016.58 | 13358.41 | 24026.49 | 20990.09
PRC 3352531PF3901 | 2025-05-07 | Inv. 24-044 PC 06 FINAL | -16073.19 | 28943.39 | 4916.9 | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  |  |  | 28943.39 |  | 28943.39 | 0
|  | Totals: | 28943.39 |  | 28943.39 |  | 0 | FINAL
|  | CM Staff Hours | 22764.64 |  | 22764.64 |  | 0
|  | Reimbursables Expense | 6178.75 |  | 6178.75 |  | 0
|  | Totals: | 28943.39 |  | 28943.39 |  | 0

## #9440.00 DCI Group (2)
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-2000-9255 |  |  | RFP1821335228-DC11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525134912 | 2025-05-14 | PO Procore | 424038.2 | 424038.2 |  |  | 424038.2
PRC 3352513PA4912 | 2025-06-20 | Inv. 23-050 CA 01A(100% to 2000) |  | 424038.2 | 10883.84 | 10883.84 | 413154.36
PRC 3352513PB4912 | 2025-07-15 | Inv. 24-044 CA 02A(100% to 2000) |  | 424038.2 | 9403.56 | 20287.4 | 403750.8 | FY25
PO 33526134912 | 2025-08-22 | Roll to FY26 | 0 | 424038.2 |  | 20287.4 | 403750.8
PRC 3352613PC4912 | 2025-09-08 | Inv. 24-044 CA 03(Split w X674) |  | 424038.2 | 5263.48 | 25550.88 | 398487.32
PRC 3352613PD4912 | 2025-09-24 | Inv. 24-044 CA 04(Split w X674) |  | 424038.2 | 11197.93 | 36748.81 | 387289.39
PRC 3352613PE4912 | 2025-10-15 | Inv. 24-044 CA 05(Split w X674) |  | 424038.2 | 13998.41 | 50747.22 | 373290.98
PRC 3352613PF4912 | 2025-12-03 | Inv. 24-044 CA 06(Split w X674 |  | 424038.2 | 20790.96 | 71538.18 | 352500.02
PRC 3352613PG4912 | 2025-12-18 | Inv. 24-044 CA 07(Split w X674) |  | 424038.2 | 25512.73 | 97050.91 | 326987.29
PRC 3352613PH4912 | 2026-01-29 | Inv. 24-044 CA 08(Split w X674) |  | 424038.2 | 29940.82 | 126991.73 | 297046.47
PRC 3352613PI4912 | 2026-02-13 | Inv. 24-044 CA 09(Split w X674) |  | 424038.2 | 14359.27 | 141351 | 282687.2
PRC 3352613PJ4912 | 2026-03-24 | Inv. 24-044 CA 10(Split w X674) |  | 424038.2 | 28388.98 | 169739.98 | 254298.22
PRC 3352613PK4912 | 2026-04-15 | Inv. 24-044 CA 11(100% to 2000) |  | 424038.2 | 32314.12 | 202054.1 | 221984.1
PRC 3352613PL4912 | 2026-05-12 | Inv. 24-044 CA #12(100% to 2000) |  | 424038.2 | 23945.88 | 225999.98 | 198038.22
|  |  |  | 424038.2 |  | 225999.98 | 198038.22
|  |  |  | 424038.2 |  | 225999.98 | 198038.22
|  | Totals: | 424038.2 |  | 225999.98 |  | 198038.22
|  | CM Services | 270785.24 |  | 149143.58 |  | 121641.66
|  | Reimbursables Expense | 18000 |  | 1500 |  | 16500
|  | Fee | 135252.96 |  | 75356.4 |  | 59896.56
|  | Total: | 424038.2 |  | 225999.98 |  | 198038.22
|  | X674 | 43273.28 |  | 36842.41 |  | 6430.87
|  | Total: | 467311.48 |  | 262842.39 |  | 204469.09
Vendor used 23-050 CA 0X in previous tab, add A to the end

## #9440.00 Van Maanen Electrical
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
Van Maanen Electrical |  |  | Vendor: 00002091370
Acct. Codes-0017-335-2000-9255 |  |  | RFB944000-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525136905 | 2025-05-16 | PO Procore | 381025 | 381025 |  |  | 381025 |  | FY25
PO 33526136905 | 2025-08-22 | Roll to FY26 | 0 | 381025 |  | 0 | 381025
PRC 3352613PA6905 | 2025-12-29 | Inv. 2615-01(Split w/X674) |  | 381025 | 119547.65 | 119547.65 | 261477.35 | 6292.1
PRC 3352613PB6905 | 2026-01-29 | Inv. 2615-02(Split w/X674) |  | 381025 | 46350.23 | 165897.88 | 215127.12 | 8731.65
PO 33526136905 | 2026-03-03 | CO #1(100% to 2000) | 9542.46 | 390567.46 |  | 165897.88 | 224669.58
PO 33526136905 | 2026-04-14 | CO #2(100% to 2000) | 2497.68 | 393065.14 |  | 165897.88 | 227167.26
PRC 3352613PC6905 | 2026-04-14 | Inv. 2615-03(Split w/X674) |  | 393065.14 | 78158.3 | 244056.18 | 149008.96 | 12845.36
PO 33526136905 | 2026-05-06 | CO #3(100% to 2000) | -150 | 392915.14 |  | 244056.18 | 148858.96
|  |  |  | 392915.14 |  | 244056.18 | 148858.96
|  |  |  | 392915.14 |  | 244056.18 | 148858.96
|  |  |  | 392915.14 |  | 244056.18 | 148858.96
|  |  |  | 392915.14 |  | 244056.18 | 148858.96
|  | Totals: | 392915.14 |  | 244056.18 |  | 148858.96
|  | X674 | 28000 |  | 25425.55 |  | 2574.45
|  | Total: | 420915.14 |  | 269481.73 |  | 151433.41
Payment A Retainage is off due to the number of lines this invoice is broken down to in Procore

## #9440.00 Proctor Mechanical
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0017-335-2000-9255 |  |  | RFB944000-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525136906 | 2025-05-16 | PO Procore | 117850 | 117850 |  |  | 117850
PRC 3352513PA6906 | 2025-07-11 | Inv. 7629.0 |  | 117850 | 2927.8 | 2927.8 | 114922.2 | 154.1 | FY25
PO 33526136906 | 2025-08-22 | Roll to FY26 | 0 | 117850 |  | 2927.8 | 114922.2
PRC 3352613PB6906 | 2025-11-12 | Inv. 7629.0/2(Split w/x674) |  | 117850 | 30032.1 | 32959.9 | 84890.1 | 1734.75
PO 33526136906 | 2025-11-18 | CO #1(100% to 2000) | 4313 | 122163 |  | 32959.9 | 89203.1
PRC 3352613PC6906 | 2025-12-03 | Inv. 7629.0/3(Split w/x674) |  | 122163 | 3609.85 | 36569.75 | 85593.25 | 1924.75
PRC 3352613PD6906 | 2026-01-06 | Inv. 7629.0/4(Split w/x674) |  | 122163 | 1508.13 | 38077.88 | 84085.12 | 2004.13
PRC 3352613PE6906 | 2026-02-03 | Inv. 7629.0/5(100% to 2000) |  | 122163 | 8952.13 | 47030.01 | 75132.99 | 2475.29
PO 33526136906 | 2026-03-03 | CO #2(100% to 2000) | 9722 | 131885 |  | 47030.01 | 84854.99
PRC 3352613PF6906 | 2026-03-06 | Inv. 7629.0/6(100% to 2000) |  | 131885 | 10535.02 | 57565.03 | 74319.97 | 3029.77
PRC 3352613PG6906 | 2026-05-13 | Inv. 7629.0/7(100% to 2000) |  | 131885 | 35537.79 | 93102.82 | 38782.18 | 4900.18
|  |  |  | 131885 |  | 93102.82 | 38782.18
|  |  |  | 131885 |  | 93102.82 | 38782.18
|  | Totals: | 131885 |  | 93102.82 |  | 38782.18
|  | X674 | 14650 |  | 13917.49 |  | 732.51
|  | Total: | 146535 |  | 107020.31 |  | 39514.69

## #9440.00 Bergstrom Construction
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0017-335-2000-9255 |  |  | RFB944000-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525136907 | 2025-05-16 | PO Procore | 206604 | 206604 |  |  | 206604
PRC 3352513PA6907 | 2025-07-03 | Inv. 8805-1 |  | 206604 | 8866.82 | 8866.82 | 197737.18 | 466.68 | FY25
PO 33526136907 | 2025-08-22 | Roll to FY26 | 0 | 206604 |  | 8866.82 | 197737.18
PRC 3352613PB6907 | 2025-11-12 | Inv. 9440.00-02 |  | 206604 | 13183.15 | 22049.97 | 184554.03 | 1160.53
PRC 3352613PC6907 | 2025-12-03 | Inv. 8805-3 |  | 206604 | 22816.91 | 44866.88 | 161737.12 | 2361.42
PO 33526136907 | 2025-12-16 | CO #1(100% to 2000) | 845 | 207449 |  | 44866.88 | 162582.12
PRC 3352613PD6907 | 2026-01-06 | Inv. 8805-4 |  | 207449 | 6211.95 | 51078.83 | 156370.17 | 2688.37
PRC 3352613PE6907 | 2026-02-06 | Inv. 8805-5 |  | 207449 | 23059.35 | 74138.18 | 133310.82 | 3902.02
PRC 3352613PF6907 | 2026-03-03 | Inv. 8805-6 |  | 207449 | 26445.91 | 100584.09 | 106864.91 | 5293.91
PO 33526136907 | 2026-03-30 | CO #2(100% to 2000) | 12712 | 220161 |  | 100584.09 | 119576.91
PRC 3352613PG6907 | 2026-04-13 | Inv. 8805-7(100% to 2000) |  | 220161 | 25517 | 126101.09 | 94059.91 | 6636.91
PO 33526136907 | 2026-04-21 | CO #3(100% to 2000) | 2111 | 222272 |  | 126101.09 | 96170.91
PRC 3352613PH6907 | 2026-05-04 | Inv. 8805-8(100% to 2000) |  | 222272 | 69623.6 | 195724.69 | 26547.31 | 10301.31
|  | Totals: | 222272 |  | 195724.69 |  | 26547.31
|  | X674 | 42753 |  | 0 |  | 35904.46
|  | Total: | 265025 |  | 195724.69 |  | 62451.77
Per SAE two documents must be processed because this PO has two departments

## #9440.00 Metro Elevator
DAS CC Elevator Replacements
Project # 9440.00
Program code 944000 |  |  | Major Program 4D03
Metro Elevator Great Plains |  |  | Vendor: 00003228062
Acct. Codes-0017-335-2000-9255 |  |  | RFB944000-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Split w/ X674
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525148402 | 2025-05-23 | PO Procore | 2693845 | 2693845 |  |  | 2693845
PRC 3352514PA8402 | 2025-07-15 | Inv. 9440.00-01(Split w/X674) |  | 2693845 | 123027.85 | 123027.85 | 2570817.15 | 6475.15 | FY25
PO 33526148402 | 2025-08-22 | Roll to FY26 | 0 | 2693845 |  | 123027.85 | 2570817.15
PRC 3352614PB8402 | 2025-10-20 | Inv. 9440.00-02(Split w/X674) |  | 2693845 | 195318.57 | 318346.42 | 2375498.58 | 16755.09
PRC 3352614PC8402 | 2025-11-13 | Inv. 9440.00-03(Split w/X674) |  | 2693845 | 294167.02 | 612513.44 | 2081331.56 | 32237.57
PO 33526148402 | 2025-11-18 | CO #1(100% to 2000) | 20000 | 2713845 |  | 612513.44 | 2101331.56
PRC 3352614PD8402 | 2025-12-16 | Inv. 9440.00-04(Split w/X674) |  | 2713845 | 202919.76 | 815433.2 | 1898411.8 | 42917.56
PRC 3352614PE8402 | 2026-01-14 | Inv. 9440.00-05(100%to 2000) |  | 2713845 | 144618.5 | 960051.7 | 1753793.3 | 50529.06
PRC 3352614PF8402 | 2026-02-06 | Inv. 9440.00-06(Split w/X674) |  | 2713845 | 200663.75 | 1160715.45 | 1553129.55 | 61090.31
PO 33526148402 | 2026-03-03 | CO #2(100% to 2000) | -1599 | 2712246 |  | 1160715.45 | 1551530.55
PRC 3352614PG8402 | 2026-03-06 | Inv. 9440.00-07(Split w/X674) |  | 2712246 | 274466.16 | 1435181.61 | 1277064.39 | 75535.9
PRC 3352614PH8402 | 2026-04-03 | Inv. 9440.00-08(100% to 2000) |  | 2712246 | 101080.95 | 1536262.56 | 1175983.44 | 80855.95
PRC 3352614PI8402 | 2026-05-04 | Inv. 9440.00-09(100% to 2000) |  | 2712246 | 213512.5 | 1749775.06 | 962470.94 | 92093.45
|  |  |  | 2712246 |  | 1749775.06 | 962470.94
|  |  |  | 2712246 |  | 1749775.06 | 962470.94
|  |  |  | 2712246 |  | 1749775.06 | 962470.94
|  | Totals: | 2712246 |  | 1749775.06 |  | 962470.94
|  | X674 | 177650 |  | 162098.5 |  | 15551.5
|  | Total: | 2889896 |  | 1911873.56 |  | 978022.44
Must be submitted in 2 documents per SAE

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-2000
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-2000-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables Expense |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-2000-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-2000-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0