## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 53923752.16
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 53923752.16
|  | Less: Total Assigned |  | 45044423.09
|  | Total Unassigned / Unallocated |  | 8879329.07
DA25 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9239.02 | DOC-NCF-IPI Homes or Iowa Facility Project Phase II (SLFRF)(Warehouse) | Brad T. | 0 | 3700000 | 3700000 | 3661855.67 | 2146119.44 | 1515736.23 | 38144.33
| 9239.03 | DOC-NCF-IPI Homes or Iowa Facility Project Fencing Phase II | Brad T. | 0 | 650000 | 650000 | 522512.26 | 404792.9 | 117719.36 | 127487.74
| 9279.40 | HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3 | Jennifer K. | 0 | 14500067.36 | 14500067.36 | 8218736.7 | 5407206.17 | 2811530.53 | 6281330.66
| 9279.41 | HHS WRC Linden Court Fire Suppression | Jennifer K. | 0 | 130000 | 130000 | 129938.24 | 124069.55 | 5868.69 | 61.76
C | 9294.00 | DHS WRC Fire Alarm System Replacement Phase 1 | Jennifer K. | 0 | 12790.78 | 12790.78 | 12790.78 | 12790.78 | -1.819e-12 | 0
| 9358.01 | ICN CC Lucas CRAC Replacement | Jennifer K. | 0 | 595000 | 595000 | 567637.84 | 563804.71 | 3833.13 | 27362.16
C | 9360.01 | IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement | Brandon A. | 0 | 142460.45 | 142460.45 | 142460.45 | 142460.45 | 0 | 0
C | 9366.00 | DOC NCCF IPI Sally Port Vehicle Gate | Jennie E. | 0 | 41634.05 | 41634.05 | 41634.05 | 41634.05 | 0 | 0
C | 9424.00 | HHS STS Main Electrical Loop Revisions | Jennifer K. | 0 | 112934.75 | 112934.75 | 112934.75 | 112934.75 | 0 | 0
C | 9425.01 | HHS STS North Buildings HazMat Remediation | Jennifer K. | 0 | 120684.88 | 120684.88 | 120684.88 | 120684.88 | -1.4552e-11 | 0
| 9429.00 | ANK HHS IMEO Expansion and Renovation | James T. | 0 | 33018000 | 33018000 | 30696455.11 | 2490940.79 | 28205514.32 | 2321544.89
C | 9433.00 | HHS WRC Cottage Siding Replacement | Jennifer K. | 0 | 192927.83 | 192927.83 | 192927.83 | 192927.83 | 0 | 0
| 9466.00 | DOC 3JD CBC New Backup Generator | Jennie E. | 0 | 405000 | 405000 | 330365.21 | 75126.39 | 255238.82 | 74634.79
C | 9467.00 | HHS IMHI Soil Remediation | Jennie E. | 0 | 15645.69 | 15645.69 | 15645.69 | 15645.69 | 1.819e-12 | 0
C | 9468.00 | IUC CC IUC Building Window Shade System Replacement | Oliver S | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 9470.00 | DOC 6JD IC Hope-Stratton Retaining Wall Repairs | Jennifer K. | 0 | 8629.61 | 8629.61 | 8629.61 | 8629.61 | 0 | 0
C | 9472.00 | DAS CC Hoover Level B Sprinkler Modifications | Oliver S | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 9473.00 | DAS CC Hoover Print Shop Expansion | Oliver S | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9475.00 | HHS CHMHI Fleet Garage Repairs | Jennie E. | 0 | 211000 | 211000 | 202237.26 | 50755.95 | 151481.31 | 8762.74
C | 9476.00 | HHS STS New Garage Building | Jennifer K. | 0 | 41976.76 | 41976.76 | 41976.76 | 41976.76 | -7.276e-12 | 0
| 9480.00 | HHS STS Canteen Roof Repair Design (29C20) | Jennifer K. | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0
|  | DA25 (MOU) Totals |  | 0 | 53923752.16 | 53923752.16 | 45044423.09 | 11977500.7 | 33066922.39 | 8879329.07
41946251.46

## RECAP #9239.02
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
| Program code 923902 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 3700000
C | Samuels Group |  | 9925.15 | 9925.15 | 0
| PM TIME |  | 45000 | 18431.16 | 26568.84
| Misc. |  | 10088.62 | 10088.62 | 0
C | Farnsworth Group |  | 15540 | 15540 | 0
| Farnsworth Group (2) |  | 236411 | 219848.9 | 16562.1
C | Samuels Group (2) |  | 39312.93 | 39312.93 | 0
| Accurate Commercial |  | 1599112.14 | 1045903.31 | 553208.83
| Proctor Mechanical |  | 868592.29 | 269410.65 | 599181.64
| Con-Struct Inc |  | 524703.69 | 410253.79 | 114449.9
| Samuels Group (3) |  | 280801.1 | 96527.93 | 184273.17
| Terracon Consultants |  | 15170 | 10877 | 4293
| Interstate Power & Lights |  | 17198.75 | 0 | 17198.75
| Total Project Cost | 3700000 | 3661855.67 | 2146119.44 | 1515736.23 | 38144.33

## #9239.02 Funds Recv'd
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 0A7444011625 | 2025-01-16 | 3500000 | 3500000
|  |  | Funds Received in without program code | CDR 33525021200 | 2025-01-21 | 0 | 0
|  |  | Returning FY25 Funds to Agency | IET 33525224913 | 2025-08-12 | -3299991.35 | -3299991.35
|  |  | Received FY26 Funds received from Agency | IET 0A7935082925 | 2025-09-03 | 3299991.35 | 3299991.35
|  |  | Funds Received in without program code | CDR 33526254800 | 2025-09-04 | 0 | 0
|  |  | Move funds from 923903 to 923902 DA25 | CDR 33526282903 | 2025-10-09 | 200000 | 200000
| Total Requested | 0 | Total Transferred |  |  | 3700000 | 3700000

## #9239.02 Samuels Group
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525031906 | 2025-01-31 | PO Procore | 10000 | 10000 |  |  | 10000
PRC 3352503PA1906 | 2025-03-07 | Inv. 7757.01923902 |  | 10000 | 3486.59 | 3486.59 | 6513.41
PRC 3352503PB1906 | 2025-04-08 | Inv. 7757.02923902 |  | 10000 | 3255 | 6741.59 | 3258.41
PRC 3352503PC1906 | 2025-05-07 | Inv. 7757.03923902 |  | 10000 | 968.24 | 7709.83 | 2290.17
PRC 3352503PD1906 | 2025-05-23 | Inv, 7757.04923902-FINAL | -74.85 | 9925.15 | 2215.32 | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  |  |  | 9925.15 |  | 9925.15 | 0
|  | Totals: | 9925.15 |  | 9925.15 |  | 0 | FINAL
|  | CM Services | 9835.15 |  | 9835.15 |  | 0
|  | Reimbursable Expenses | 90 |  | 90 |  | 0
|  | Total: | 9925.15 |  | 9925.15 |  | 0

## #9239.02 PM TIME
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Brad T. |  |  |  | eDAS 910U
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 45000 | 45000 |  |  | 45000
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 45000 | 102.52 | 102.52 | 44897.48
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 45000 | 1093.3 | 1195.82 | 43804.18
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 45000 | 130.32 | 1326.14 | 43673.86
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 45000 | 562.6 | 1888.74 | 43111.26
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 45000 | 153.81 | 2042.55 | 42957.45
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 45000 | 1101.3 | 3143.85 | 41856.15
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 45000 | 122.19 | 3266.04 | 41733.96
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 45000 | 838.8 | 4104.84 | 40895.16
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 45000 | 135.5 | 4240.34 | 40759.66
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 45000 | 1061.1 | 5301.44 | 39698.56
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 45000 | 97.88 | 5399.32 | 39600.68
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 45000 | 758.9 | 6158.22 | 38841.78
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 45000 | 70.25 | 6228.47 | 38771.53
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 45000 | 777.5 | 7005.97 | 37994.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 45000 | 94.58 | 7100.55 | 37899.45
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 45000 | 732.6 | 7833.15 | 37166.85
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 45000 | 200.5 | 8033.65 | 36966.35
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 45000 | 1045.6 | 9079.25 | 35920.75
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 45000 | 131 | 9210.25 | 35789.75
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 45000 | 1297.3 | 10507.55 | 34492.45
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 45000 | 151.57 | 10659.12 | 34340.88
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 45000 | 963.5 | 11622.62 | 33377.38
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 45000 | 125.38 | 11748 | 33252
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 45000 | 1418.8 | 13166.8 | 31833.2
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 45000 | 97.81 | 13264.61 | 31735.39
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 45000 | 1214.9 | 14479.51 | 30520.49
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 45000 | 127.02 | 14606.53 | 30393.47
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 45000 | 1466.9 | 16073.43 | 28926.57
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 45000 | 259.13 | 16332.56 | 28667.44
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 45000 | 2098.6 | 18431.16 | 26568.84
[5 empty] | 45000 |  | 18431.16 | 26568.84
[5 empty] | 45000 |  | 18431.16 | 26568.84
[5 empty] | 45000 |  | 18431.16 | 26568.84
|  |  | Totals: | 45000 |  | 18431.16 |  | 26568.84
Note on E9: Huggins, Joni [DAS]: onyan, Brad 1:59 PM (8 minutes ago) to Jerry, me Joni, The contracts look correct now and thank you. Please update the following PM Time budgets on project 9239.02-.03 under DA25: 9239.02 - Make overall PM Time budget total value $45K 9239.03 - Make overall PM Time budget total value $20K Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9239.02 Misc
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 174
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526281902 | 2025-10-08 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV052848 | 1708.31 | 1708.31
PRC 33526318900 | 2025-11-14 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV052002 | 2317.31 | 4025.62
PRC 33526318902 | 2025-11-14 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 862990 | 6063 | 10088.62
10088.62
10088.62
10088.62
10088.62
10088.62
10088.62
10088.62
10088.62
10088.62
|  |  |  | Totals: |  | 10088.62

## #9239.02 FarnsworthGroup
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA25-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525049904 | 2025-01-31 | PO Procore | 15540 | 15540 |  |  | 15540
PRC 3352504PA9904 | 2025-03-21 | Inv. 259212 |  | 15540 | 7250 | 7250 | 8290
PRC 3352504PB9904 | 2025-05-13 | Inv. 9239.02-02 - Final |  | 15540 | 8290 | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  |  |  | 15540 |  | 15540 | 0
|  | Totals: | 15540 |  | 15540 |  | 0 | FINAL

## #9239.02 FarnsworthGroup (2)
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Farnsworth Group (2) |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA25-9260 |  |  | RFP913300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525094901 | 2025-04-04 | PO Procore | 236411 | 236411 |  |  | 236411
PRC 3352509PA4901 | 2025-07-09 | Inv. 9239.02-01 |  | 236411 | 157796.8 | 157796.8 | 78614.2 | FY25
PO 33526094901 | 2025-08-20 | Roll to FY26 | 0 | 236411 |  | 157796.8 | 78614.2
PRC 3352609PB4901 | 2025-09-15 | Inv. 9239.02-02 |  | 236411 | 11402.2 | 169199 | 67212
PRC 3352609PC4901 | 2025-09-16 | Inv. 9239.02-03 |  | 236411 | 10804.5 | 180003.5 | 56407.5
PRC 3352609PD4901 | 2025-10-15 | Inv. 9239.02-04 |  | 236411 | 1200.5 | 181204 | 55207
PRC 3352609PE4901 | 2025-11-12 | Inv. 9239.02-05 |  | 236411 | 4416.56 | 185620.56 | 50790.44
PRC 3352609PF4901 | 2025-12-16 | Inv. 9239.02-06 |  | 236411 | 11041.4 | 196661.96 | 39749.04
PRC 3352609PG4901 | 2026-01-20 | Inv. 9239.02-07 |  | 236411 | 11041.4 | 207703.36 | 28707.64
PRC 3352609PH4901 | 2026-02-17 | Inv. 9239.02-08 |  | 236411 | 4416.56 | 212119.92 | 24291.08
PRC 3352609PI4901 | 2026-03-20 | Inv. 9239.02-09 |  | 236411 | 2208.28 | 214328.2 | 22082.8
PRC 3352609PJ4901 | 2026-04-20 | Inv. 9239.02-10 |  | 236411 | 5520.7 | 219848.9 | 16562.1
|  |  |  | 236411 |  | 219848.9 | 16562.1
|  | Totals: | 236411 |  | 219848.9 |  | 16562.1
Farnsworth Group Architecutral Fee
|  | Design Development | 17315 |  | 17315 |  | 0
|  | Construction Docs | 48975 |  | 48975 |  | 0
|  | Bidding/Negotiation | 7020 |  | 7020 |  | 0
|  | Construction Admin | 29120 |  | 20384 |  | 8736
|  | Total: | 102430 |  | 93694 |  | 8736
Bishop Engineering Civil Fee
|  | Design Development | 5885 |  | 5885 |  | 0
|  | Construction Docs | 16650 |  | 16650 |  | 0
|  | Bidding/Negotiation | 1480 |  | 1480 |  | 0
|  | Construction Admin | 3975 |  | 2782.5 |  | 1192.5
|  | Total: | 27990 |  | 26797.5 |  | 1192.5
KPFF Structural Fee
|  | Design Development | 3627 |  | 3627 |  | 0
|  | Construction Docs | 5707 |  | 5707 |  | 0
|  | Bidding/Negotiation | 665 |  | 665 |  | 0
|  | Construction Admin | 3512 |  | 2458.4 |  | 1053.6
|  | Total: | 13511 |  | 12457.4 |  | 1053.6
Twin Rivers MEP Fee
|  | Design Development | 28350 |  | 28350 |  | 0
|  | Construction Docs | 42690 |  | 42690 |  | 0
|  | Bidding/Negotiation | 2840 |  | 2840 |  | 0
|  | Construction Admin | 18600 |  | 13020 |  | 5580
|  | Total: | 92480 |  | 86900 |  | 5580
|  | Grand Total: | 236411 |  | 219848.9 |  | 16562.1

## #9239.02 Samuels Group (2)
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525148902 | 2025-05-28 | PO Procore | 39889.48 | 39889.48 |  |  | 39889.48
PRC 3352514PA8902 | 2025-07-16 | Inv. 7783.01923902 |  | 39889.48 | 10588.48 | 10588.48 | 29301 | FY25
PO 33526148902 | 2025-08-20 | Roll to FY26 | 0 | 39889.48 |  | 10588.48 | 29301
PRC 3352614PB8902 | 2025-09-08 | Inv. 7783.02923902 |  | 39889.48 | 10492.27 | 21080.75 | 18808.73
PRC 3352614PC8902 | 2025-09-15 | Inv. 7783.03923902 |  | 39889.48 | 7239.5 | 28320.25 | 11569.23
PRC 3352614PD8902 | 2025-10-07 | Inv. 7783.04923902 |  | 39889.48 | 4797.3 | 33117.55 | 6771.93
PRC 3352614PE8902 | 2025-11-13 | Inv. 7783.05923902 FINAL | -576.55 | 39312.93 | 6195.38 | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  |  |  | 39312.93 |  | 39312.93 | 2.9559e-12
|  | Totals: | 39312.93 |  | 39312.93 |  | 0 | FINAL
|  | CM Services | 35473.93 |  | 35473.93 |  | 0
|  | Reimbursables-Geotech/Testing | 3794 |  | 3794 |  | 0
|  | Reimbursables-Mileage, hotels, meals | 45 |  | 45 |  | 0
|  | Total: | 39312.93 |  | 39312.93 |  | 0

## #9239.02 Accurate Commercial
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Accurate Commercial |  |  | Vendor: 00003177484
Acct. Codes-0506-335-DA25-9255 |  |  | RFB923902-01
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526266900 | 2025-09-23 | PO Procore | 1547000 | 1547000 |  |  | 1547000
PRC 3352626PA6900 | 2026-01-16 | Inv. 2500561-1 |  | 1547000 | 30894.5 | 30894.5 | 1516105.5 | 955.5
PO 33526266900 | 2026-01-23 | CO #1 | 9076.56 | 1556076.56 |  | 30894.5 | 1525182.06
PRC 3352626PB6900 | 2026-02-12 | Inv. 2500561-2 |  | 1556076.56 | 273274.97 | 304169.47 | 1251907.09 | 9407.29
PRC 3352626PC6900 | 2026-03-16 | Inv. 2500561-3 |  | 1556076.56 | 373060.68 | 677230.15 | 878846.41 | 20945.26
PO 33526266900 | 2026-04-14 | CO #2 | 43035.58 | 1599112.14 |  | 677230.15 | 921881.99
PRC 3352626PD6900 | 2026-04-22 | Inv. 2500561-4 |  | 1599112.14 | 368673.16 | 1045903.31 | 553208.83 | 32347.54
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  |  |  | 1599112.14 |  | 1045903.31 | 553208.83
|  | Totals: | 1599112.14 |  | 1045903.31 |  | 553208.83
Retainage 3%

## #9239.02 Proctor Mechanical
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0506-335-DA25-9255 |  |  | RFB923902-01
Project Manager - Brad T. |  |  | Activity code: BRIN
Split w/9239.03
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526266901 | 2025-09-23 | PO Procore | 910000 | 910000 |  |  | 910000
PO 33526266901 | 2025-10-24 | Correcting PO to be split w/9239.03 | -52000 | 858000 |  | 0 | 858000
PO 33526266901 | 2025-11-06 | CO #1 | 2146 | 860146 |  | 0 | 860146
PRC 3352626PA6901 | 2025-12-16 | Inv. 7641.0/1(Split with 9239.03) |  | 860146 | 77412.79 | 77412.79 | 782733.21 | 2394.21
PO 33526266901 | 2026-01-21 | CO #2(Split with 9239.03) | 2441.29 | 862587.29 |  | 77412.79 | 785174.5
PRC 3352626PB6901 | 2026-01-29 | Inv. 7641.0/2(100% to 9239.02) |  | 862587.29 | 22579.66 | 99992.45 | 762594.84 | 3092.55
PRC 3352626PC6901 | 2026-02-12 | Inv. 7641.0/3(100% to 9239.02) |  | 862587.29 | 86504.6 | 186497.05 | 676090.24 | 5767.95
PRC 3352626PD6901 | 2026-03-06 | Inv. 7641.0/4(100% to 9239.02) |  | 862587.29 | 38458.91 | 224955.96 | 637631.33 | 6957.4
PRC 3352626PE6901 | 2026-04-08 | Inv. 7641.0/5(Split with 9239.03) |  | 862587.29 | 44454.69 | 269410.65 | 593176.64 | 8332.3
PO 33526266901 | 2026-04-17 | CO #3(100% to 9239.02) | 6005 | 868592.29 |  | 269410.65 | 599181.64
|  |  |  | 868592.29 |  | 269410.65 | 599181.64
|  |  |  | 868592.29 |  | 269410.65 | 599181.64
|  |  |  | 868592.29 |  | 269410.65 | 599181.64
|  | Totals: | 868592.29 |  | 269410.65 |  | 599181.64
|  | DA25 9239.03 | 54303 |  | 47918 |  | 6385
|  | Total: | 922895.29 |  | 317328.65 |  | 605566.64
Retainage 3%

## #9239.02 Con-Struct Inc
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Con-Struct Inc |  |  | Vendor: 00002110440
Acct. Codes-0506-335-DA25-9255 |  |  | RFB923902-02
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526286905 | 2025-10-13 | PO Procore | 741490 | 741490 |  |  | 741490
PO 33526286905 | 2025-10-24 | Correcting PO to split w/9239.03 | -238195 | 503295 |  | 0 | 503295
PO 33526286905 | 2025-11-14 | CO #1 (100% to 9239.02) | 13324.19 | 516619.19 |  | 0 | 516619.19
PRC 3352628PA6905 | 2025-12-29 | Inv. 9239.02-#1(Split w/9239.03) |  | 516619.19 | 385281.14 | 385281.14 | 131338.05 | 11915.91
PO 33526286905 | 2026-01-09 | CO #2 (100% to 9239.02) | 8084.5 | 524703.69 |  | 385281.14 | 139422.55
PO 33526286905 | 2026-04-13 | CO #3 (No Cost CO) | 0 | 524703.69 |  | 385281.14 | 139422.55
PRC 3352628PB6905 | 2026-04-22 | Inv. 9239.02-#2(Split w/9239.03) |  | 524703.69 | 24972.65 | 410253.79 | 114449.9 | 12688.26
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  |  |  | 524703.69 |  | 410253.79 | 114449.9
|  | Totals: | 524703.69 |  | 410253.79 |  | 114449.9
|  | DA25 9239.03 | 238195 |  | 189109.31 |  | 49085.69
|  | Total: | 762898.69 |  | 599363.1 |  | 163535.59
Retainage 3%

## #9239.02 Samuels Group (3)
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Samuels Group (3) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526296905 | 2025-10-23 | PO Procore | 280801.1 | 280801.1 |  |  | 280801.1
PRC 3352629PA6905 | 2025-12-04 | Inv. 7824.01923902 |  | 280801.1 | 9597.04 | 9597.04 | 271204.06
PRC 3352629PB6905 | 2026-01-12 | Inv. 7824.02923902 |  | 280801.1 | 10195.63 | 19792.67 | 261008.43
PRC 3352629PC6905 | 2026-02-03 | Inv. 7824.03923902 |  | 280801.1 | 15942.33 | 35735 | 245066.1
PRC 3352629PD6905 | 2026-03-03 | Inv. 7824.04923902 |  | 280801.1 | 32592.25 | 68327.25 | 212473.85
PRC 3352629PE6905 | 2026-04-07 | Inv. 7824.05923902 |  | 280801.1 | 28200.68 | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  |  |  | 280801.1 |  | 96527.93 | 184273.17
|  | Totals: | 280801.1 |  | 96527.93 |  | 184273.17
|  | CM Services | 134749.3 |  | 45549.61 |  | 89199.69
|  | Reimbursables-Mileage, hotels, meals | 13500 |  | 2674.96 |  | 10825.04
|  | Reimbursables-Dumpsters, roll-off, toilets | 5600 |  | 288 |  | 5312
|  | Reimbursables-Temp toilets | 3120 |  | 1426.44 |  | 1693.56
|  | Reimbursables-Temp Protections, Heat | 7500 |  | 1689.38 |  | 5810.62
|  | 4% SG Fees | 116331.8 |  | 44899.54 |  | 71432.26
|  | Total: | 280801.1 |  | 96527.93 |  | 184273.17

## #9239.02 Terracon Consultants
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0506-335-DA25-9255 |  |  | MA00525049
Project Manager - Brad T. |  |  | Activity code: CNST
Split w/ 9239.03
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310906 | 2025-11-07 | Moving from 9239.03 | 15170 | 15170 |  |  | 15170
PRC 3352631PA0906 | 2025-12-11 | Inv. TP98180 (Split w/9239.03) |  | 15170 | 691.5 | 691.5 | 14478.5
PRC 3352631PB0906 | 2025-12-29 | Inv. TQ05378(Split w/9239.03) |  | 15170 | 947.5 | 1639 | 13531
PRC 3352631PC0906 | 2026-02-24 | Inv. TQ32544(100% to 9239.02) |  | 15170 | 1645.5 | 3284.5 | 11885.5
PRC 3352631PD0906 | 2026-03-04 | Inv. TQ35671(100% to 9239.02) |  | 15170 | 2203 | 5487.5 | 9682.5
PRC 3352631PE0906 | 2026-04-07 | Inv. TQ50954 (100% to 9239.02) |  | 15170 | 447.5 | 5935 | 9235
PRC 3352631PF0906 | 2026-04-29 | Inv. TQ68316 (100% to 9239.02) |  | 15170 | 4942 | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  |  |  | 15170 |  | 10877 | 4293
|  | Totals: | 15170 |  | 10877 |  | 4293
|  | DA25 9239.03 | 4330 |  | 2890 |  | 1440
|  | Total: | 19500 |  | 13767 |  | 5733

## #9239.02 Interstate Power
DOC-NCF-IPI Homes or Iowa Facility Project Phase II(Warehouse)
Project # 9239.02
Program code 923902 |  |  | Major Program 4B01
Interstate Power & Light (dba Alliant Energy) |  |  | Vendor: 00002106184
Acct. Codes-0506-335-DA25-9255 |  |  | CNST
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526092912 | 2026-04-02 | PO Procore | 17198.75 | 17198.75 |  |  | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  |  |  | 17198.75 |  | 0 | 17198.75
|  | Totals: | 17198.75 |  | 0 |  | 17198.75

## RECAP #9239.03
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
| Program code 923903 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Brad T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 650000
| Farnsworth Group |  | 138405 | 101715 | 36690
| PM TIME |  | 20000 | 8154.46 | 11845.54
| Misc. |  | 0 | 0 | 0
C | Samuels Group |  | 25509.33 | 25509.33 | 0
| Proctor Mechanical |  | 54303 | 47918 | 6385
| Con-Struct Inc |  | 238195 | 189109.31 | 49085.69
| Samuels Group(2) |  | 41769.93 | 29496.8 | 12273.13
| Terracon Consultants |  | 4330 | 2890 | 1440
| Total Project Cost | 650000 | 522512.26 | 404792.9 | 117719.36 | 127487.74

## #9239.03 Funds Rec'd
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Transfer Funds to Correct Unit From DA24 to DA25 | CDR 33525109900 | 2025-04-18 | 850000 | 850000
|  |  | Returning FY25 Funds to Agency | IET 33525224914 | 2025-08-12 | -747002.85 | -747002.85
|  |  | Transfer Funds to Correct Unit From DA24 to DA25 | CDR 33526238900 | 2025-08-27 | 747002.85 | 747002.85
|  |  | Move funds from 923903 to 923902 DA25 | CDR 33526282903 | 2025-10-09 | -200000 | -200000
| Total Requested | 0 | Total Transferred |  |  | 650000 | 650000

## #9239.03 Farnsworth Group
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA25-9260 |  |  | RFP913300-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525132900 | 2025-05-09 | PO Procore | 138405 | 138405 |  |  | 138405
PO 3352513PA2900 | 2025-07-16 | Inv. 9239.03-001 |  | 138405 | 94959.5 | 94959.5 | 43445.5 | FY25
PO 3352613290 | 2025-08-20 | Roll to FY26 | 0 | 138405 |  | 94959.5 | 43445.5
PRC 3352613PB290 | 2025-09-15 | Inv. 9239.03-002 |  | 138405 | 6755.5 | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  |  |  | 138405 |  | 101715 | 36690
|  | Totals: | 138405 |  | 101715 |  | 36690
Design Grand Totals
|  | Design Development | 34160 |  | 34160 |  | 0
|  | Construction Docs | 67555 |  | 67555 |  | 0
|  | Bidding/Negotiation | 8780 |  |  |  | 8780
|  | Construction Admin | 27910 |  |  |  | 27910
|  | Total: | 138405 |  | 101715 |  | 36690
Please use 9239.03-00X as 9239.03-0X has previously been used for this vendor

## #9239.03 PM TIME
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Brad T |  |  |  | eDAS: 732W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 20000 | 20000 |  |  | 20000
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 20000 | 74.52 | 74.52 | 19925.48
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 20000 | 510.8 | 585.32 | 19414.68
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 20000 | 88.65 | 673.97 | 19326.03
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 20000 | 692.3 | 1366.27 | 18633.73
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 20000 | 73.13 | 1439.4 | 18560.6
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 20000 | 569.7 | 2009.1 | 17990.9
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 40.63 | 2049.73 | 17950.27
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 449.7 | 2499.43 | 17500.57
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 55.6 | 2555.03 | 17444.97
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 431.9 | 2986.93 | 17013.07
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 109.26 | 3096.19 | 16903.81
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 570.4 | 3666.59 | 16333.41
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 92.66 | 3759.25 | 16240.75
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 919.4 | 4678.65 | 15321.35
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 72.16 | 4750.81 | 15249.19
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 460.4 | 5211.21 | 14788.79
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 48.53 | 5259.74 | 14740.26
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 548.4 | 5808.14 | 14191.86
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 52.6 | 5860.74 | 14139.26
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 647.9 | 6508.64 | 13491.36
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 59.6 | 6568.24 | 13431.76
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 690 | 7258.24 | 12741.76
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 98.12 | 7356.36 | 12643.64
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 798.1 | 8154.46 | 11845.54
[5 empty] | 20000 |  | 8154.46 | 11845.54
[5 empty] | 20000 |  | 8154.46 | 11845.54
[5 empty] | 20000 |  | 8154.46 | 11845.54
|  |  | Totals: | 20000 |  | 8154.46 |  | 11845.54
Note on E9: Jurgenson, John [DAS]: Re: April PM Time Inbox Tonyan, Brad 1:47 PM (0 minutes ago) to me Joni and Finance, For now please set up the PM time budget for $10,000. Thank you, Brad Tonyan, CPM, LEED Green Associate Owner Representative General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street, Des Moines, IA 50319 515-360-7718 mobile brad.tonyan@iowa.gov https://das.iowa.gov On Tue, May 20, 2025 at 1:10 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi Brad I missed DA25 9239.03 is short -585.32 There isn't budget set ~Joni onyan, Brad 1:59 PM (8 minutes ago) to Jerry, me Joni, The contracts look correct now and thank you. Please update the following PM Time budgets on project 9239.02-.03 under DA25: 9239.02 - Make overall PM Time budget total value $45K 9239.03 - Make overall PM Time budget total value $20K Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9239.03 Misc
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T |  |  |  | Shipping Code: 174
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9239.03 Samuels Group
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525148901 | 2025-05-28 | PO Procore | 26776.8 | 26776.8 |  |  | 26776.8
PRC 3352514PA8901 | 2025-07-10 | Inv. 7782.01923903 |  | 26776.8 | 6028.55 | 6028.55 | 20748.25 | FY25
PO 33526148901 | 2025-08-20 | Roll to FY26 | 0 | 26776.8 |  | 6028.55 | 20748.25
PRC 3352614PB8901 | 2025-09-08 | Inv. 7782.02923903 |  | 26776.8 | 8356.73 | 14385.28 | 12391.52
PRC 3352614PC8901 | 2025-09-15 | Inv. 7782.03923903 |  | 26776.8 | 3452.75 | 17838.03 | 8938.77
PRC 3352614PD8901 | 2025-10-07 | Inv. 7782.04923903 |  | 26776.8 | 2323.84 | 20161.87 | 6614.93
PRC 3352614PE8901 | 2025-11-13 | Inv. 7782.05923903 FINAL | -1267.47 | 25509.33 | 5347.46 | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  |  |  | 25509.33 |  | 25509.33 | 0
|  | Totals: | 25509.33 |  | 25509.33 |  | 0 | FINAL
|  | CM Services | 22609.33 |  | 22609.33 |  | 0
|  | Reimbursables-Geotech/Testing | 2900 |  | 2900 |  | 0
|  | Reimbursables-Mileage,hotels,meals | 0 |  |  |  | 0
|  | Total: | 25509.33 |  | 25509.33 |  | 0

## #9239.03 Proctor Mechanical
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0506-335-DA25-9255 |  |  | RFB923902-01
Project Manager - Brad T |  |  | Activity code: BRIN
Split w/9239.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526266901 | 2025-10-24 | PO Procore | 52000 | 52000 |  |  | 52000
PRC 3352626PA6901 | 2025-12-16 | Inv. 7641.0/1(Split w/9239.02) |  | 52000 | 16499.7 | 16499.7 | 35500.3 | 510.3
PO 33526266901 | 2026-01-21 | CO #2(Split with 9239.02) | 2303 | 54303 |  | 16499.7 | 37803.3
PRC 3352626PB6901 | 2026-01-29 | Inv. 7641.0/2(100% to 9239.02) |  | 54303 | 0 | 16499.7 | 37803.3 | 510.3
PRC 3352626PC6901 | 2026-02-12 | Inv. 7641.0/3(100% to 9239.02) |  | 54303 | 0 | 16499.7 | 37803.3 | 510.3
PRC 3352626PD6901 | 2026-03-06 | Inv. 7641.0/4(100% to 9239.02) |  | 54303 | 0 | 16499.7 | 37803.3 | 510.3
PRC 3352626PE6901 | 2026-04-08 | Inv. 7641.0/5(Split with 9239.02) |  | 54303 | 31418.3 | 47918 | 6385 | 1482
|  |  |  | 54303 |  | 47918 | 6385
|  |  |  | 54303 |  | 47918 | 6385
|  |  |  | 54303 |  | 47918 | 6385
|  |  |  | 54303 |  | 47918 | 6385
|  |  |  | 54303 |  | 47918 | 6385
|  |  |  | 54303 |  | 47918 | 6385
|  | Totals: | 54303 |  | 47918 |  | 6385
|  | DA25 9239.02 | 868592.29 |  | 269410.65 |  | 599181.64
|  | Total: | 922895.29 |  | 317328.65 |  | 605566.64
Retainage 3%

## #9239.03 Con-Struct Inc
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Con-Struct Inc |  |  | Vendor: 00002110440
Acct. Codes-0506-335-DA25-9255 |  |  | RFB923902-02
Project Manager - Brad T |  |  | Activity code: BRIN
Split w/9239.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526286905 | 2025-10-24 | PO Procore | 238195 | 238195 |  |  | 238195
PO 33526286905 | 2025-11-14 | CO #1(100% to 9239.02) | 0 | 238195 |  | 0 | 238195
PRC 3352628PA6905 | 2025-12-29 | Inv. 9239.02-#1(Split w/9239.02) |  | 238195 | 172813.31 | 172813.31 | 65381.69 | 5344.74
PO 33526286905 | 2026-01-09 | CO #2(100% to 9239.02) | 0 | 238195 |  | 172813.31 | 65381.69
PO 33526286905 | 2026-04-13 | CO #3 (No Cost CO) | 0 | 238195 |  | 172813.31 | 65381.69
PRC 3352628PB6905 | 2026-04-22 | Inv. 9239.02-#2(Split w/9239.02) |  | 238195 | 16296 | 189109.31 | 49085.69 | 5848.74
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  |  |  | 238195 |  | 189109.31 | 49085.69
|  | Totals: | 238195 |  | 189109.31 |  | 49085.69
|  | DA25 9239.02 | 524703.69 |  | 410253.79 |  | 114449.9
|  | Total: | 762898.69 |  | 599363.1 |  | 163535.59
Retainage 3%

## #9239.03 Samuels Group (2)
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Samuels110122021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526297900 | 2025-10-24 | PO Procore | 41769.93 | 41769.93 |  |  | 41769.93
PRC 3352629PA7900 | 2025-12-04 | Inv. 7825.01923903 |  | 41769.93 | 5668.48 | 5668.48 | 36101.45
PRC 3352629PB7900 | 2026-01-09 | Inv. 7825.02923903 |  | 41769.93 | 3563.26 | 9231.74 | 32538.19
PRC 3352629PC7900 | 2026-02-03 | Inv. 7825.03923903 |  | 41769.93 | 4515.16 | 13746.9 | 28023.03
PRC 3352629PD7900 | 2026-03-03 | Inv. 7825.04923903 |  | 41769.93 | 3116.54 | 16863.44 | 24906.49
PRC 3352629PE7900 | 2026-04-07 | Inv. 7825.05923903 |  | 41769.93 | 12633.36 | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  |  |  | 41769.93 |  | 29496.8 | 12273.13
|  | Totals: | 41769.93 |  | 29496.8 |  | 12273.13
|  | CM Services | 40269.93 |  | 29186.8 |  | 11083.13
|  | Reimbursables | 1500 |  | 310 |  | 1190
|  | Total: | 41769.93 |  | 29496.8 |  | 12273.13

## #9239.03 Terracon Consultants
DOC-NCF-IPI Homes or Iowa Facility Project Fencing - Phase II
Project # 9239.03
Program code 923903 |  |  | Major Program 4B01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0506-335-DA25-9255 |  |  | MA00525049
Project Manager - Brad T |  |  | Activity code: CNST
Split w/ 9239.02
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310906 | 2025-11-06 | DO Procore | 19500 | 19500 |  |  | 19500
PO 33526310906 | 2025-11-07 | Moving to 9239.02 | -15170 | 4330 |  | 0 | 4330
PRC 3352631PA0906 | 2025-12-11 | Inv. TP98180 (Split w/9239.02) |  | 4330 | 2485.5 | 2485.5 | 1844.5
PRC 3352631PB0906 | 2025-12-29 | Inv. TQ05378(Split w/9239.02) |  | 4330 | 404.5 | 2890 | 1440
PRC 3352631PC0906 | 2026-02-24 | Inv. TQ32544(100% to 9239.02) |  | 4330 | 0 | 2890 | 1440
PRC 3352631PD0906 | 2026-03-04 | Inv. TQ35671(100% to 9239.02) |  | 4330 | 0 | 2890 | 1440
PRC 3352631PE0906 | 2026-04-07 | Inv. TQ50954 (100% to 9239.02) |  | 4330 | 0 | 2890 | 1440
PRC 3352631PF0906 | 2026-04-29 | Inv. TQ68316 (100% to 9239.02) |  | 4330 | 0 | 2890 | 1440
|  |  |  | 4330 |  | 2890 | 1440
|  |  |  | 4330 |  | 2890 | 1440
|  |  |  | 4330 |  | 2890 | 1440
|  |  |  | 4330 |  | 2890 | 1440
|  |  |  | 4330 |  | 2890 | 1440
|  | Totals: | 4330 |  | 2890 |  | 1440
|  | DA25 9239.02 | 15170 |  | 10877 |  | 4293
|  | Total: | 19500 |  | 13767 |  | 5733

## RECAP #9279.40
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
| Program code 927940 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 14500067.36
C | Shive Hattery |  | 142970 | 142970 | 0
| PM TIME |  | 127079 | 93135.41 | 33943.59
| Misc. |  | 5548.21 | 5548.21 | 0
| Story Construction |  | 127565.66 | 115023.91 | 12541.75
C | ATC Group |  | 25335 | 25335 | 0
| Shive Hattery (2) |  | 628358 | 518579 | 109779
| SystemWorks |  | 51355 | 3430 | 47925
| ATC Group (2) |  | 36160 | 4683.75 | 31476.25
| Shive Hattery(3) |  | 157782 | 147541.94 | 10240.06
| Shive Hattery (4) |  | 120612 | 75208.9 | 45403.1
C | ATC Group (3) |  | 7434 | 7434 | 0
| Story Construction (2) |  | 806021.18 | 543579.25 | 262441.93
C | Advanced Environmental |  | 13500.04 | 13500.04 | 0
| VanMaanen Electric |  | 905961.74 | 753544.75 | 152416.99
| Pleva Plumbing |  | 3714582.5 | 2813171.27 | 901411.23
| SystemWorks |  | 14865 | 7880 | 6985
| Kline Electrical |  | 4468.91 | 0 | 4468.91
| Shive Hattery(5) |  | 131130 | 100870 | 30260
C | Story Construction(3) |  | 20033.18 | 20033.18 | 0
C | ATC Group (4) |  | 9362 | 9362 | 0
| ATC Group (5) |  | 5958 | 0 | 5958
C | Controlled Asbestos |  | 2483.4 | 2483.4 | 0
| Story Construction(4) |  | 147749.88 | 3892.16 | 143857.72
| VanMaanen Electric (2) |  | 998762 | 0 | 998762
| Controlled Asbestos (2) |  | 13660 | 0 | 13660
| Total Project Cost | 14500067.36 | 8218736.7 | 5407206.17 | 2811530.53 | 6281330.66

## #9279.40 Funds Rec'd
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUDECENT4FIREALARM3 | 2024-07-12 | 14500000 | 14500000
|  |  | Rapids Reproduction refund | CR 00525212101A | 2025-07-31 | 67.36 | 67.36
|  |  | Returning FY25 Funds to Agency | IET 33525224915 | 2025-08-12 | -13566468.88 | -13566468.88
|  |  | Received FY26 Funds received from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 13566468.88 | 13566468.88
| Total Requested | 0 | Total Transferred |  |  | 14500067.36 | 14500067.36

## #9279.40 Shive Hattery
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RPF927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525236905 | 2024-08-23 | PO Procore | 142970 | 142970 |  |  | 142970
PRC 3352523PA6905 | 2024-11-05 | Inv. 2240007040-101 |  | 142970 | 60320 | 60320 | 82650
PRC 3352523PB6905 | 2024-12-12 | Inv. 2240007040-102 |  | 142970 | 53915 | 114235 | 28735
PRC 3352523PC6905 | 2025-01-27 | Inv. 2240007040-103 |  | 142970 | 25861.5 | 140096.5 | 2873.5
PRC 3352523PD6905 | 2025-05-09 | Inv. 2240007040-104 |  | 142970 | 2873.5 | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  |  |  | 142970 |  | 142970 | 0
|  | Totals: | 142970 |  | 142970 |  | 0 | FINAL
Birches Building Heating Decentralization
|  | Schematic Design Docs | 26100 |  | 26100 |  | 0
|  | Design Development Docs | 32300 |  | 32300 |  | 0
|  | Construction Docs | 34090 |  | 34090 |  | 0
|  | Total | 92490 |  | 92490 |  | 0
Powerhouse Building Heating Decentralization
|  | Schematic Design Docs | 6200 |  | 6200 |  | 0
|  | Design Development Docs | 6800 |  | 6800 |  | 0
|  | Construction Docs | 7970 |  | 7970 |  | 0
|  | Total | 20970 |  | 20970 |  | 0
Fire Alarm Phase 3 - Birch & Powerhouse
|  | Schematic Design Docs | 3500 |  | 3500 |  | 0
|  | Design Development Docs | 10600 |  | 10600 |  | 0
|  | Construction Docs | 15410 |  | 15410 |  | 0
|  | Total | 29510 |  | 29510 |  | 0
|  | Contract Total | 142970 |  | 142970 |  | 0

## #9279.40 PM TIME
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E2DX
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 127079 | 127079 |  |  | 127079
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 127079 | 59.27 | 59.27 | 127019.73
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 127079 | 645 | 704.27 | 126374.73
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 127079 | 237.6 | 941.87 | 126137.13
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 127079 | 1209 | 2150.87 | 124928.13
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 127079 | 292.44 | 2443.31 | 124635.69
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 127079 | 2599.5 | 5042.81 | 122036.19
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 127079 | 671.13 | 5713.94 | 121365.06
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 127079 | 4475.3 | 10189.24 | 116889.76
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 127079 | 281.93 | 10471.17 | 116607.83
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 127079 | 1873.4 | 12344.57 | 114734.43
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 127079 | 556.18 | 12900.75 | 114178.25
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 127079 | 5549.9 | 18450.65 | 108628.35
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 127079 | 485.57 | 18936.22 | 108142.78
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 127079 | 5174.5 | 24110.72 | 102968.28
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 127079 | 751.83 | 24862.55 | 102216.45
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 127079 | 3253.7 | 28116.25 | 98962.75
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 127079 | 212.57 | 28328.82 | 98750.18
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 127079 | 1518.2 | 29847.02 | 97231.98
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 127079 | 425.62 | 30272.64 | 96806.36
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 127079 | 2924.6 | 33197.24 | 93881.76
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 127079 | 355.01 | 33552.25 | 93526.75
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 127079 | 2782.3 | 36334.55 | 90744.45
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 127079 | 241.47 | 36576.02 | 90502.98
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 127079 | 1874.3 | 38450.32 | 88628.68
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 127079 | 343.43 | 38793.75 | 88285.25
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 127079 | 3764.4 | 42558.15 | 84520.85
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 127079 | 420.17 | 42978.32 | 84100.68
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 127079 | 3234.2 | 46212.52 | 80866.48
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 127079 | 1032.93 | 47245.45 | 79833.55
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 127079 | 5311.4 | 52556.85 | 74522.15
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 127079 | 604.45 | 53161.3 | 73917.7
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 127079 | 6493.1 | 59654.4 | 67424.6
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 127079 | 368.81 | 60023.21 | 67055.79
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 127079 | 2346.4 | 62369.61 | 64709.39
CDE 33526352902 | 2025-12-18 | 2507 | Moving expense from 9279.50 to 9279.40 |  | 127079 | 116.55 | 62486.16 | 64592.84
CDE 33526352902 | 2025-12-18 | 9500 | Moving expense from 9279.50 to 9279.40 |  | 127079 | 741.5 | 63227.66 | 63851.34
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 127079 | 569.47 | 63797.13 | 63281.87
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 127079 | 6469.1 | 70266.23 | 56812.77
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 127079 | 748.97 | 71015.2 | 56063.8
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 127079 | 9304.9 | 80320.1 | 46758.9
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 127079 | 444.73 | 80764.83 | 46314.17
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 127079 | 5125.2 | 85890.03 | 41188.97
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 127079 | 791.98 | 86682.01 | 40396.99
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 127079 | 6453.4 | 93135.41 | 33943.59
[5 empty] | 127079 |  | 93135.41 | 33943.59
[5 empty] | 127079 |  | 93135.41 | 33943.59
[5 empty] | 127079 |  | 93135.41 | 33943.59
|  |  | Totals: | 127079 |  | 93135.41 |  | 33943.59
Note on E9: Jurgenson, John [DAS]: Kleene, Jennifer Aug 8, 2024, 4:37 PM (14 hours ago) to me, DAS Please set up the DAS Costs budget for DA25 9279.40 for $127,079.00. Regards, Jennifer

## #9279.40 Misc
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525181900 | 2025-06-30 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1815 | 67.36 | 67.36
PRC 33525184908 | 2025-07-03 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1897 | 740.05 | 807.41
PRC 33525195400 | 2025-07-03 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 840697 | 3422 | 4229.41
PRC 33525196903 | 2025-07-15 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1896 | 294.11 | 4523.52
PRC 33526275903 | 2025-10-03 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2186 | 14.25 | 4537.77
PRC 33526300902 | 2025-10-27 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2677988 | 544.5 | 5082.27
PRC 33526337904 | 2025-12-03 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2318 | 15.6 | 5097.87
PRC 33526058905 | 2026-02-27 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2575 | 200 | 5297.87
PRC 33526069906 | 2026-03-10 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2612 | 223.72 | 5521.59
PRC 33526075912 | 2026-03-16 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2624 | 26.62 | 5548.21
5548.21
5548.21
|  |  |  | Totals: |  | 5548.21

## #9279.40 Story Construction
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525253900 | 2024-09-09 | PO Procore | 25245.04 | 25245.04 |  |  | 25245.04
PRC 3352525PA3900 | 2024-10-16 | Inv. 34569 |  | 25245.04 | 1098.79 | 1098.79 | 24146.25
PRC 3352525PB3900 | 2024-11-19 | Inv. 34613 |  | 25245.04 | 1407.52 | 2506.31 | 22738.73
PRC 3352525PC3900 | 2024-12-17 | Inv. 34662 |  | 25245.04 | 3636.03 | 6142.34 | 19102.7
PRC 3352525PD3900 | 2025-01-16 | Inv. 34701 |  | 25245.04 | 6032.82 | 12175.16 | 13069.88
PRC 3352525PE3900 | 2025-02-17 | Inv. 34733 |  | 25245.04 | 5054.86 | 17230.02 | 8015.02
PO 33525253900 | 2025-03-05 | CO #1 | 28543.22 | 53788.26 |  | 17230.02 | 36558.24
PRC 3352525PF3900 | 2025-03-21 | Inv. 34769 |  | 53788.26 | 7223.67 | 24453.69 | 29334.57
PRC 3352525PG3900 | 2025-04-18 | Inv. 34802 |  | 53788.26 | 29282.26 | 53735.95 | 52.31
PO 33525253900 | 2025-04-21 | CO #2 | 20620.59 | 74408.85 |  | 53735.95 | 20672.9
PRC 3352525PH3900 | 2025-05-19 | Inv. 34838 |  | 74408.85 | 2673.46 | 56409.41 | 17999.44
PRC 3352525PI3900 | 2025-06-13 | Inv. 34866 |  | 74408.85 | 6226.46 | 62635.87 | 11772.98
PRC 3352525PJ3900 | 2025-07-21 | Inv. 34904 |  | 74408.85 | 5899.89 | 68535.76 | 5873.09 | FY25
PO 33526253900 | 2025-08-20 | Roll to FY26 | 0 | 74408.85 |  | 68535.76 | 5873.09
PRC 3352625PK3900 | 2025-09-11 | Inv. 34944 |  | 74408.85 | 1651.42 | 70187.18 | 4221.67
PO 33526253900 | 2025-09-16 | CO #3 | 21038.6 | 95447.45 |  | 70187.18 | 25260.27
PRC 3352625PL3900 | 2025-10-17 | Inv. 35011 |  | 95447.45 | 6615.07 | 76802.25 | 18645.2
PRC 3352625PM3900 | 2025-11-19 | Inv. 35043 |  | 95447.45 | 6854.84 | 83657.09 | 11790.36
PO 33526253900 | 2025-12-15 | CO #4 | 7414.33 | 102861.78 |  | 83657.09 | 19204.69
PRC 3352625PN3900 | 2025-12-16 | Inv. 35075 |  | 102861.78 | 10894.67 | 94551.76 | 8310.02
PRC 3352625PO3900 | 2026-01-20 | Inv. 35113 |  | 102861.78 | 4739.4 | 99291.16 | 3570.62
PO 33526253900 | 2026-02-06 | CO #5 | 24703.88 | 127565.66 |  | 99291.16 | 28274.5
PRC 3352625PP3900 | 2026-03-18 | Inv. 35192 |  | 127565.66 | 11309.63 | 110600.79 | 16964.87
PRC 3352625PQ3900 | 2026-04-21 | Inv. 35224 |  | 127565.66 | 4423.12 | 115023.91 | 12541.75
|  |  |  | 127565.66 |  | 115023.91 | 12541.75
|  |  |  | 127565.66 |  | 115023.91 | 12541.75
|  | Totals: | 127565.66 |  | 115023.91 |  | 12541.75
|  | CM Services | 25156.54 |  | 25156.54 |  | 0
|  | Reimbursable Expenses | 88.5 |  | 88.5 |  | 0
|  | CO #1 | 28543.22 |  | 28543.22 |  | 0
|  | CO #2 | 20620.59 |  | 20620.59 |  | 0
|  | CO #3 | 21038.6 |  | 21038.6 |  | 0
|  | CO #4 | 7414.33 |  | 7414.33 |  | 0
|  | CO #5 | 24703.88 |  | 12162.13 |  | 12541.75
|  | Total: | 127565.66 |  | 115023.91 |  | 12541.75

## #9279.40 ATC Group Services
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
ATC Group Services |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9255 |  |  | MA00520262D
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525262901 | 2024-09-17 | PO Procore | 34907.5 | 34907.5 |  |  | 34907.5
PO 33525262901 | 2025-01-13 | CO #1 | 1000 | 35907.5 |  | 0 | 35907.5
PRC 3352526PA2901 | 2025-03-28 | Inv. 9279.40-01-FINAL | -10572.5 | 25335 | 25335 | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  |  |  | 25335 |  | 25335 | 0
|  | Totals: | 25335 |  | 25335 |  | 0 | FINAL
Tunnels
|  | Asbestos $10ea x 80 | 500 |  | 500 |  | 0
|  | Lead $15 x 25 | 0 |  |  |  | 0
|  | Admin Hours $45 x 2 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 34 | 2550 |  | 2550 |  | 0
|  | Hygienist Hours $95 x 4 | 380 |  | 380 |  | 0
|  | Total | 3475 |  | 3475 |  | 0
Birches
|  | Asbestos $10ea x 110 | 520 |  | 520 |  | 0
|  | Lead $15 x 60 | 210 |  | 210 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 30 | 2250 |  | 2250 |  | 0
|  | Hygienist Hours $95 x 18.5 | 1140 |  | 1140 |  | 0
|  | Total | 4165 |  | 4165 |  | 0
Powerhouse
|  | Asbestos $10ea x 110 | 90 |  | 90 |  | 0
|  | Lead $15 x 60 | 75 |  | 75 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 30 | 2250 |  | 2250 |  | 0
|  | Hygienist Hours $95 x 18.5 | 1140 |  | 1140 |  | 0
|  | Total | 3600 |  | 3600 |  | 0
Linden A/B
|  | Asbestos $10ea x 110 | 1100 |  | 1100 |  | 0
|  | Lead $15 x 60 | 165 |  | 165 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 30 | 2250 |  | 2250 |  | 0
|  | Hygienist Hours $95 x 18.5 | 1235 |  | 1235 |  | 0
|  | CO #1 Asbestos $10ea x 38 | 380 |  | 380 |  | 0
|  | Total | 5175 |  | 5175 |  | 0
Linden C/D
|  | Asbestos $10ea x 110 | 1100 |  | 1100 |  | 0
|  | Lead $15 x 60 | 300 |  | 300 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 30 | 2250 |  | 2250 |  | 0
|  | Hygienist Hours $95 x 18.5 | 1235 |  | 1235 |  | 0
|  | CO #1 Asbestos $10ea x 62 | 620 |  | 620 |  | 0
|  | Total | 5550 |  | 5550 |  | 0
Chiller Plant
|  | Asbestos $10ea x 110 | 80 |  | 80 |  | 0
|  | Lead $15 x 60 | 45 |  | 45 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $75 x 30 | 2250 |  | 2250 |  | 0
|  | Hygienist Hours $95 x 18.5 | 950 |  | 950 |  | 0
|  | Total | 3370 |  | 3370 |  | 0
|  | Contract Total | 25335 |  | 25335 |  | 0

## #9279.40 Shive Hattery (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Shive Hattery (2) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RPF927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525282904 | 2024-10-08 | PO Procore | 491700 | 491700 |  |  | 491700
PRC 3352528PA2904 | 2024-11-05 | Inv. 2240007040-201 |  | 491700 | 18180 | 18180 | 473520
PRC 3352528PB2904 | 2024-12-12 | Inv. 2240007040-202 |  | 491700 | 211250 | 229430 | 262270
PO 33525282904 | 2024-12-16 | CO #1 | 22560 | 514260 |  | 229430 | 284830
PO 33525282904 | 2025-01-07 | CO #2 | 6705 | 520965 |  | 229430 | 291535
PRC 3352528PC2904 | 2025-01-27 | Inv. 2240007040-203 |  | 520965 | 153082.4 | 382512.4 | 138452.6
PRC 3352528PD2904 | 2025-02-24 | Inv. 2240007040-204 |  | 520965 | 90688.92 | 473201.32 | 47763.68
PRC 3352528PE2904 | 2025-04-15 | Inv. 2240007040-205 |  | 520965 | 29329.14 | 502530.46 | 18434.54
PRC 3352528PF2904 | 2025-07-07 | Inv. 2240007040-206 |  | 520965 | 670.5 | 503200.96 | 17764.04 | FY25
PO 33526282904 | 2025-08-20 | Roll to FY26 | 0 | 520965 |  | 503200.96 | 17764.04
PO 33526282904 | 2026-01-29 | CO #3 | 107393 | 628358 |  | 503200.96 | 125157.04
PRC 3352628PG2904 | 2026-02-05 | Inv. 2240007040-207 |  | 628358 | 15226.32 | 518427.28 | 109930.72
PRC 3352628PH2904 | 2026-04-09 | Inv. 2240007040-208 |  | 628358 | 151.72 | 518579 | 109779
|  |  |  | 628358 |  | 518579 | 109779
|  |  |  | 628358 |  | 518579 | 109779
|  | Totals: | 628358 |  | 518579 |  | 109779
Linden Court Heating Decentralization
|  | Schematic Design Docs | 86500 |  | 86500 |  | 0
|  | Design Development Docs | 139000 |  | 139000 |  | 0
|  | Construction Docs | 216600 |  | 214434 |  | 2166
|  | Total: | 442100 |  | 439934 |  | 2166
Linden Court Living Units Fire Alarm
|  | Schematic Design Docs | 8800 |  | 8800 |  | 0
|  | Design Development Docs | 18800 |  | 18800 |  | 0
|  | Construction Docs | 22000 |  | 21780 |  | 220
|  | Total: | 49600 |  | 49380 |  | 220
|  | CO #1 | 22560 |  | 22560 |  | 0
|  | CO #2 | 6705 |  | 6705 |  | 0
|  | CO #3 | 107393 |  |  |  | 107393
|  | Contract Total: | 628358 |  | 518579 |  | 109779

## #9279.40 SystemWorks
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0506-335-DA25-9255 |  |  | RFP927900-02
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525003911 | 2025-01-03 | PO Procore | 41580 | 41580 |  |  | 41580
PRC 3352500PA3911 | 2025-03-21 | Inv. 12280 |  | 41580 | 2744 | 2744 | 38836
PRC 3352500PB3911 | 2025-07-03 | Inv. 12426 |  | 41580 | 686 | 3430 | 38150 | FY25
PO 33526003911 | 2025-08-20 | Roll to FY26 | 0 | 41580 |  | 3430 | 38150
PO 33526003911 | 2025-12-22 | CO #1 | 9775 | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  |  |  | 51355 |  | 3430 | 47925
|  | Totals: | 51355 |  | 3430 |  | 47925
|  | Design Phase Services | 3430 |  | 3430 |  | 0
|  | Birches Const & Testing | 6090 |  |  |  | 6090
|  | Powerhouse Const & Testing | 4130 |  |  |  | 4130
|  | Linden Court Academy Const & Testing | 22820 |  |  |  | 22820
|  | Final | 5110 |  |  |  | 5110
|  | CO #1 | 9775 |  |  |  | 9775
|  | Total: | 51355 |  | 3430 |  | 47925

## #9279.40 ATC Group Services (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
ATC Group Services (2) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9255 |  |  | MA00520262D
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525010900 | 2025-01-10 | PO Procore | 36160 | 36160 |  |  | 36160
PRC 3352501PA0900 | 2025-04-30 | Inv. 2618262 |  | 36160 | 2843.75 | 2843.75 | 33316.25 | FY25
PO 33526010900 | 2025-08-20 | Roll to FY26 | 0 | 36160 |  | 2843.75 | 33316.25
PRC 3352601PB0900 | 2025-12-10 | Inv. 2684330 |  | 36160 | 1555 | 4398.75 | 31761.25
PRC 3352601PC0900 | 2026-02-16 | Inv. 2693089 |  | 36160 | 285 | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  |  |  | 36160 |  | 4683.75 | 31476.25
|  | Totals: | 36160 |  | 4683.75 |  | 31476.25
Design Phase
|  | Asbestos $10ea x 60 | 600 |  | 20 |  | 580
|  | Lead $15 x 10 | 150 |  |  |  | 150
|  | Admin Hours $45 x 4 | 180 |  | 90 |  | 90
|  | Field Tech Hours $75 x 45 | 3375 |  | 750 |  | 2625
|  | Hygienist Hours $95 x 50 | 4750 |  | 3823.75 |  | 926.25
|  | Total: | 9055 |  | 4683.75 |  | 4371.25
Bidding Phase
|  | Admin Hours $45 x 3 | 135 |  |  |  | 135
|  | Field Tech Hours $75 x 12 | 900 |  |  |  | 900
|  | Hygienist Hours $95 x 45 | 4275 |  |  |  | 4275
|  | Total: | 5310 |  | 0 |  | 5310
Birches
|  | Admin Hours $45 x 3 | 135 |  |  |  | 135
|  | Field Tech Hours $75 x 24 | 1800 |  |  |  | 1800
|  | Hygienist Hours $95 x 6 | 570 |  |  |  | 570
|  | Total: | 2505 |  | 0 |  | 2505
Powerhouse
|  | Admin Hours $45 x 1 | 45 |  |  |  | 45
|  | Field Tech Hours $75 x 8 | 600 |  |  |  | 600
|  | Hygienist Hours $95 x 3 | 285 |  |  |  | 285
|  | Total: | 930 |  | 0 |  | 930
Linden A/B
|  | Admin Hours $45 x 4 | 180 |  |  |  | 180
|  | Field Tech Hours $75 x 48 | 3600 |  |  |  | 3600
|  | Hygienist Hours $95 x 15 | 1425 |  |  |  | 1425
|  | Total: | 5205 |  | 0 |  | 5205
Linden C/D
|  | Admin Hours $45 x 4 | 180 |  |  |  | 180
|  | Field Tech Hours $75 x 48 | 3600 |  |  |  | 3600
|  | Hygienist Hours $95 x 115 | 1425 |  |  |  | 1425
|  | Total: | 5205 |  | 0 |  | 5205
Elmcrest
|  | Admin Hours $45 x 3 | 135 |  |  |  | 135
|  | Field Tech Hours $75 x 36 | 2700 |  |  |  | 2700
|  | Hygienist Hours $95 x 12 | 1140 |  |  |  | 1140
|  | Total: | 3975 |  | 0 |  | 3975
Med Center
|  | Admin Hours $45 x 3 | 135 |  |  |  | 135
|  | Field Tech Hours $75 x 36 | 2700 |  |  |  | 2700
|  | Hygienist Hours $95 x 12 | 1140 |  |  |  | 1140
|  | Total: | 3975 |  | 0 |  | 3975
TOTAL LINES
|  | Asbestos | 600 |  | 20 |  | 580
|  | Lead | 150 |  |  |  | 150
|  | Admin Hours $45 x | 1125 |  | 45 |  | 1080
|  | Field Tech Hours $75 x | 19275 |  |  |  | 19275
|  | Hygienist Hours $95 x | 15010 |  | 2778.75 |  | 12231.25
|  | Contract Total: | 36160 |  | 2843.75 |  | 31476.25

## #9279.40 Shive Hattery (3)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Shive Hattery (3) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RPF927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525010908 | 2025-01-10 | PO Procore | 108800 | 108800 |  |  | 108800
PRC 3352501PA0908 | 2025-02-20 | Inv. 2240007040-301 |  | 108800 | 36700 | 36700 | 72100
PRC 3352501PB0908 | 2025-04-07 | Inv. 2240007040-302 |  | 108800 | 54780 | 91480 | 17320
PRC 3352501PC0908 | 2025-05-15 | Inv. 2240007040-3 |  | 108800 | 16454 | 107934 | 866
PO 33525010908 | 2025-06-04 | CO #1 | 48982 | 157782 |  | 107934 | 49848
PRC 3352501PD0908 | 2025-07-07 | Inv. 2240007040-304 |  | 157782 | 5326 | 113260 | 44522 | FY25
PO 33526010908 | 2025-08-20 | Roll to FY26 | 0 | 157782 |  | 113260 | 44522
PRC 3352601PE0908 | 2025-01-06 | Inv. 2240007040-305 |  | 157782 | 11130.5 | 124390.5 | 33391.5
PRC 3352601PF0908 | 2026-04-09 | Inv. 2240007040-306 |  | 157782 | 23151.44 | 147541.94 | 10240.06
|  |  |  | 157782 |  | 147541.94 | 10240.06
|  |  |  | 157782 |  | 147541.94 | 10240.06
|  |  |  | 157782 |  | 147541.94 | 10240.06
|  |  |  | 157782 |  | 147541.94 | 10240.06
|  | Totals: | 157782 |  | 147541.94 |  | 10240.06
|  | Schematic Design Docs | 36700 |  | 36700 |  | 0
|  | Design Development Docs | 28800 |  | 28800 |  | 0
|  | Construction Docs | 43300 |  | 43300 |  | 0
|  | CO #1 | 48982 |  | 38741.94 |  | 10240.06
|  | Total: | 157782 |  | 147541.94 |  | 10240.06

## #9279.40 Shive Hattery (4)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Shive Hattery (4) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RPF927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525141900 | 2025-05-21 | PO Procore | 120612 | 120612 |  |  | 120612
PRC 3352514PA1900 | 2025-07-07 | Inv. 2240007040-501 |  | 120612 | 8150 | 8150 | 112462 | FY25
PO 33526141900 | 2025-08-20 | Roll to FY26 | 0 | 120612 |  | 8150 | 112462
PRC 3352614PB1900 | 2025-12-23 | Inv. 2240007040-502 |  | 120612 | 49088.1 | 57238.1 | 63373.9
PRC 3352614PC1900 | 2026-04-09 | Inv. 2240007040-503 |  | 120612 | 17970.8 | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  |  |  | 120612 |  | 75208.9 | 45403.1
|  | Totals: | 120612 |  | 75208.9 |  | 45403.1
|  | Bid Issuance #1 | 8150 |  | 8150 |  | 0
|  | Birches Construction Admin | 35982 |  | 26986.5 |  | 8995.5
|  | Med Center Construction Admin | 28120 |  | 14060 |  | 14060
|  | Elmcrest Construction Admin | 28120 |  | 12654 |  | 15466
|  | Powerhouse Construction Admin | 10120 |  | 5060 |  | 5060
|  | Dispatch Garage Construction | 10120 |  | 8298.4 |  | 1821.6
|  | Total: | 120612 |  | 75208.9 |  | 45403.1

## #9279.40 ATC Group Services (3)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
ATC Group Services (3) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9255 |  |  | MA00520262E
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525148909 | 2025-05-28 | PO Procore | 13110 | 13110 |  |  | 13110
PRC 3352514PA8909 | 2025-07-15 | Inv. 2657542 |  | 13110 | 7434 | 7434 | 5676
DO 33525148909 | 2025-07-17 | Closing per pm | -5676 | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  |  |  | 7434 |  | 7434 | 0
|  | Totals: | 7434 |  | 7434 |  | 0
|  | Asbestos $12 x 200 | 1128 |  | 1128 |  | 0
|  | Lead $17 x 100 | 731 |  | 731 |  | 0
|  | Admin Hours $45 x 3 | 45 |  | 45 |  | 0
|  | Field Tech Hours $80 x 65 | 3280 |  | 3280 |  | 0
|  | Hygienist Hours $100 x 35 | 2075 |  | 2075 |  | 0
|  | Travel .50 x 350 miles | 175 |  | 175 |  | 0
|  | Total: | 7434 |  | 7434 |  | 0

## #9279.40 Story Construction (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525150901 | 2025-05-30 | PO Procore | 648615.69 | 648615.69 |  |  | 648615.69
PO 33525150901 | 2025-06-13 | CO #1 | 157405.49 | 806021.18 |  | 0 | 806021.18
PRC 3352515PA0901 | 2025-07-23 | Inv. 34905 |  | 806021.18 | 7585.17 | 7585.17 | 798436.01 | FY25
PO 33526150901 | 2025-08-20 | Roll to FY26 | 0 | 806021.18 |  | 7585.17 | 798436.01
PRC 3352615PB0901 | 2025-09-11 | Inv. 34945 |  | 806021.18 | 33771.22 | 41356.39 | 764664.79
PRC 3352615PC0901 | 2025-09-15 | Inv. 34796 |  | 806021.18 | 51984.88 | 93341.27 | 712679.91
PRC 3352615PD0901 | 2025-10-17 | Inv. 35012 |  | 806021.18 | 74726.46 | 168067.73 | 637953.45
PRC 3352615PE0901 | 2025-11-20 | Inv. 35044 |  | 806021.18 | 78706.92 | 246774.65 | 559246.53
PRC 3352615PF0901 | 2025-12-17 | Inv. 35076 |  | 806021.18 | 76698.4 | 323473.05 | 482548.13
PRC 3352615PG0901 | 2026-01-20 | Inv. 35114 |  | 806021.18 | 57069.54 | 380542.59 | 425478.59
PRC 3352615PH0901 | 2026-02-20 | Inv. 35150 |  | 806021.18 | 46850.99 | 427393.58 | 378627.6
PRC 3352615PI0901 | 2026-03-18 | Inv. 35191 |  | 806021.18 | 44739.84 | 472133.42 | 333887.76
PRC 3352615PJ0901 | 2026-04-21 | Inv. 35225 |  | 806021.18 | 71445.83 | 543579.25 | 262441.93
|  |  |  | 806021.18 |  | 543579.25 | 262441.93
|  |  |  | 806021.18 |  | 543579.25 | 262441.93
|  | Totals: | 806021.18 |  | 543579.25 |  | 262441.93
|  | CM Services | 377103.98 |  | 269485.38 |  | 107618.6
|  | Reimbursable Expenses | 7581.5 |  | 4513.5 |  | 3068
|  | Fee | 129870.21 |  | 89000 |  | 40870.21
|  | General Conditions | 134060 |  | 33051.34 |  | 101008.66
|  | CO #1 | 157405.49 |  | 147529.03 |  | 9876.46
|  | Total: | 806021.18 |  | 543579.25 |  | 262441.93

## #9279.40 Advanced Environmental
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Advanced Environmental |  |  | Vendor: 00002125877
Acct. Codes-0506-335-DA25-9255 |  |  | MA 005 21063B
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525155902 | 2025-06-04 | DO Procore | 10772.32 | 10772.32 |  |  | 10772.32 | FY25
PO 33526155902 | 2025-08-20 | Roll to FY26 | 0 | 10772.32 |  | 0 | 10772.32
PO 33526155902 | 2025-08-20 | CO #1 | 5550.92 | 16323.24 |  | 0 | 16323.24
PRC 3352615PA5902 | 2025-11-04 | Inv. 29978-FINAL | -2823.2 | 13500.04 | 13500.04 | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  |  |  | 13500.04 |  | 13500.04 | 0
|  | Totals: | 13500.04 |  | 13500.04 |  | 0 | FINAL
|  | Asbestos Line 1 | 8026.2 |  | 8026.2 |  | 0
|  | Abatement & Remediation Line 7 | 1566.89 |  | 1566.89 |  | 0
|  | Non-Friable Disposal Fee Line 11 | 200 |  | 200 |  | 0
|  | Travel Expense Line 12 | 646.12 |  | 646.12 |  | 0
|  | CO #1 | 3060.83 |  | 3060.83 |  | 0
|  | Total: | 13500.04 |  | 13500.04 |  | 0

## #9279.40 VanMaanen Electric
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Van Maanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA25-9255 |  |  | 927940-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525155903 | 2025-06-04 | PO Procore | 886906 | 886906 |  |  | 886906 |  | FY25
PO 33526155903 | 2025-08-20 | Roll to FY26 | 0 | 886906 |  | 0 | 886906
PO 33526155903 | 2025-09-04 | CO #1 | 11519.76 | 898425.76 |  | 0 | 898425.76
PRC 3352615PA5903 | 2025-12-10 | Inv. 2636-01 |  | 898425.76 | 190012.8 | 190012.8 | 708412.96 | 10000.7
PO 33526155903 | 2025-12-29 | CO #2 | 7535.98 | 905961.74 |  | 190012.8 | 715948.94
PRC 3352615PB5903 | 2026-03-18 | Inv. 2636-02 |  | 905961.74 | 362346.34 | 552359.14 | 353602.6 | 29071.6
PRC 3352615PC5903 | 2026-04-13 | Inv. 2636-03 |  | 905961.74 | 201185.61 | 753544.75 | 152416.99 | 39660.35
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  |  |  | 905961.74 |  | 753544.75 | 152416.99
|  | Totals: | 905961.74 |  | 753544.75 |  | 152416.99

## #9279.40 Pleva Plumbing
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Pleva Plumbing |  |  | Vendor: 00003054699
Acct. Codes-0506-335-DA25-9255 |  |  | 927940-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525163905 | 2025-06-12 | PO Procore | 3701587 | 3701587 |  |  | 3701587 |  | FY25
PO 33526163905 | 2025-08-20 | Roll to FY26 | 0 | 3701587 |  | 0 | 3701587
PRC 3352616PA3905 | 2025-09-11 | Inv. 9279.40-01 |  | 3701587 | 224200 | 224200 | 3477387 | 11800
PRC 3352616PB3905 | 2025-09-30 | Inv. 9279.40-02 |  | 3701587 | 173755 | 397955 | 3303632 | 20945
PO 33526163905 | 2025-10-13 | CO #1 | 2088.5 | 3703675.5 |  | 397955 | 3305720.5
PRC 3352616PC3905 | 2025-10-24 | Inv. 9279.40-03 |  | 3703675.5 | 414165.16 | 812120.16 | 2891555.34 | 42743.17
PRC 3352616PD3905 | 2025-11-20 | Inv. 9279.40-04 |  | 3703675.5 | 701870.45 | 1513990.61 | 2189684.89 | 79683.72
PRC 3352616PE3905 | 2026-01-16 | Inv. 9279.40-05 |  | 3703675.5 | 542089.95 | 2056080.56 | 1647594.94 | 108214.77
PRC 3352616PF3905 | 2026-02-25 | Inv. 9279.40-06 |  | 3703675.5 | 472106.62 | 2528187.18 | 1175488.32 | 133062.49
PRC 3352616PG3905 | 2026-03-27 | Inv. 9279.40-07 |  | 3703675.5 | 284984.09 | 2813171.27 | 890504.23 | 148061.65
PO 33526163905 | 2026-03-30 | CO #2 | 10907 | 3714582.5 |  | 2813171.27 | 901411.23
|  |  |  | 3714582.5 |  | 2813171.27 | 901411.23
|  |  |  | 3714582.5 |  | 2813171.27 | 901411.23
|  | Totals: | 3714582.5 |  | 2813171.27 |  | 901411.23

## #9279.40 SystemWorks (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
SystemWorks (2) |  |  | Vendor: 00002144353
Acct. Codes-0506-335-DA25-9255 |  |  | MA00521396B
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525169906 | 2025-06-18 | DO Procore | 14865 | 14865 |  |  | 14865
PRC 3352516PA9906 | 2025-07-03 | Inv. 12433 |  | 14865 | 7880 | 7880 | 6985 | FY25
PO 33526169906 | 2025-08-20 | Roll to FY26 | 0 | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  |  |  | 14865 |  | 7880 | 6985
|  | Totals: | 14865 |  | 7880 |  | 6985

## #9279.40 Kline Electrical
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Kline Electrical |  |  | Vendor:00003038115
Acct. Codes-0506-335-DA25-9255 |  |  | 927940-02
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Split w/ DA24 9279.30
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525169910 | 2025-06-18 | PO Procore | 146831 | 146831 |  |  | 146831 |  | FY25
PO 33526169910 | 2025-08-18 | Roll to FY26 | 0 | 146831 |  | 0 | 146831
PRC 3352616PA9910 | 2025-09-11 | Inv. 9279.40-01(100% to DA24) |  | 146831 | 0 | 0 | 146831
PRC 3352616PB9910 | 2025-09-19 | Inv. 9279.40-02(100% to DA24) |  | 146831 | 0 | 0 | 146831
PRC 3352616PC9910 | 2025-12-03 | Inv. 9279.40-03(100% to DA24) |  | 146831 | 0 | 0 | 146831
PO 33526169910 | 2025-12-17 | CO #1 (100% to DA25) | 6118.83 | 152949.83 |  | 0 | 152949.83
PRC 3352616PD9910 | 2026-01-15 | Inv. 9279.40-04(100% to DA24) |  | 152949.83 | 0 | 0 | 152949.83
PRC 3352616PE9910 | 2026-02-23 | Inv. 9279.40-05(100% to DA24) |  | 152949.83 | 0 | 0 | 152949.83
PO 33526169910 | 2026-04-22 | CO #2(Split w/DA24) | -148480.92 | 4468.91 |  | 0 | 4468.91
|  |  |  | 4468.91 |  | 0 | 4468.91
|  |  |  | 4468.91 |  | 0 | 4468.91
|  |  |  | 4468.91 |  | 0 | 4468.91
|  | Totals: | 4468.91 |  | 0 |  | 4468.91
|  | DA24 9279.30 | 1144000 |  | 992268.58 |  | 151731.42
|  | Total Contract: | 1148468.91 |  | 992268.58 |  | 156200.33

## #9279.40 Shive Hattery (5)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Shive Hattery (5) |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RPF927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259908 | 2025-09-16 | PO Procore | 96210 | 96210 |  |  | 96210
PO 33526259908 | 2026-02-10 | CO #1 | 4660 | 100870 |  | 0 | 100870
PO 33526259908 | 2026-04-14 | CO #2 | 30260 | 131130 |  | 0 | 131130
PRC 3352625PA9908 | 2029-04-27 | Inv. 2240007040-701 |  | 131130 | 100870 | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  |  |  | 131130 |  | 100870 | 30260
|  | Totals: | 131130 |  | 100870 |  | 30260
|  | Schematic Design | 18370 |  | 18370 |  | 0
|  | Design Development | 27920 |  | 27920 |  | 0
|  | Construction Docs | 47280 |  | 47280 |  | 0
|  | Bidding | 2640 |  | 2640 |  | 0
|  | CO #1 | 4660 |  | 4660 |  | 0
|  | CO #2 | 30260 |  |  |  | 30260
|  | Total: | 131130 |  | 100870 |  | 30260

## #9279.40 Story Construction (3)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Story Construction (3) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259910 | 2025-09-16 | PO Procore | 21849.03 | 21849.03 |  |  | 21849.03
PRC 3352625PA9910 | 2025-11-18 | Inv. 35048 |  | 21849.03 | 1113.67 | 1113.67 | 20735.36
PRC 3352625PB9910 | 2025-12-16 | Inv. 35078 |  | 21849.03 | 1456.02 | 2569.69 | 19279.34
PRC 3352625PC9910 | 2026-01-16 | Inv. 35117 |  | 21849.03 | 2766.79 | 5336.48 | 16512.55
PRC 3352625PD9910 | 2026-02-19 | Inv. 35151 |  | 21849.03 | 3683.88 | 9020.36 | 12828.67
PRC 3352625PE9910 | 2026-03-18 | Inv. 35194 Final | -1815.85 | 20033.18 | 11012.82 | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  |  |  | 20033.18 |  | 20033.18 | 0
|  | Totals: | 20033.18 |  | 20033.18 |  | 0 | FINAL
|  | CM Services | 20033.18 |  | 20033.18 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Total: | 20033.18 |  | 20033.18 |  | 0

## #9279.40 ATC Group Services (4)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
ATC Group Services (4) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9255 |  |  | MA00520262E
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526339904 | 2028-12-05 | DO Procore | 19270 | 19270 |  |  | 19270
DO 33526339904 | 2026-01-20 | CO #1 | -1928 | 17342 |  | 0 | 17342
PRC 3352633PA9904 | 2026-01-22 | Inv. 2693196 | -7980 | 9362 | 9362 | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  |  |  | 9362 |  | 9362 | 0
|  | Totals: | 9362 |  | 9362 |  | 0 | FINAL
|  | Asbestos $12 ea x 350 | 1932 |  | 1932 |  | 0
|  | Lead $17 x 60 | 1360 |  | 1360 |  | 0
|  | Admin Hours $45 x 4 | 45 |  | 45 |  | 0
|  | Field Tech Hours $80 x 120 | 5160 |  | 5160 |  | 0
|  | Hygienist Hours $100 x 40 | 625 |  | 625 |  | 0
|  | Mileage .50 x 540 | 240 |  | 240 |  | 0
|  | CO #1 Changed line 1 & 2 | 0 |  | 0 |  | 0
|  | Total: | 9362 |  | 9362 |  | 0

## #9279.40 ATC Group Services (5)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
ATC Group Services (5) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9255 |  |  | MA00520262E
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526026913 | 2026-01-26 | DO Procore | 5958 | 5958 |  |  | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  |  |  | 5958 |  | 0 | 5958
|  | Totals: | 5958 |  | 0 |  | 5958
|  | Asbestos $12 ea x 10 | 120 |  |  |  | 120
|  | Lead $17 x 4 | 68 |  |  |  | 68
|  | Admin Hours $45 x 3 | 135 |  |  |  | 135
|  | Field Tech Hours $80 x 39 | 3120 |  |  |  | 3120
|  | Hygienist Hours $100 x 24 | 2400 |  |  |  | 2400
|  | Mileage .50 x 230 | 115 |  |  |  | 115
|  | Total: | 5958 |  | 0 |  | 5958

## #9279.40 Controlled Asbestos
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0506-335-DA25-9255 |  |  | MA00521060C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526050900 | 2026-02-19 | DO Procore | 18497.2 | 18497.2 |  |  | 18497.2
PRC 3352605PA0900 | 2026-03-16 | Inv. 0011040-IN |  | 18497.2 | 1088 | 1088 | 17409.2
PRC 3352605PB0900 | 2026-04-09 | Inv. 0011054-IN-FINAL | -16013.8 | 2483.4 | 1395.4 | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  |  |  | 2483.4 |  | 2483.4 | 0
|  | Totals: | 2483.4 |  | 2483.4 |  | 0 | FINAL
| Line 1 | Asbestos Abatement 244@68 | 2380 |  | 2380 |  | 0
| Line 7 | Abatement & Remediation | 41.4 |  | 41.4 |  | 0
| Line 11 | Non-Friable Disposal | 0 |  |  |  | 0
| Line 12 | Travel 2150.4@.5 | 62 |  | 62 |  | 0
|  | Total: | 2483.4 |  | 2483.4 |  | 0

## #9279.40 Story Construction (4)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Story Construction (4) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526062920 | 2026-03-03 | PO Procore | 147749.88 | 147749.88 |  |  | 147749.88
PRC 3352606PA2920 | 2026-04-21 | Inv. 35227 |  | 147749.88 | 3892.16 | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  |  |  | 147749.88 |  | 3892.16 | 143857.72
|  | Totals: | 147749.88 |  | 3892.16 |  | 143857.72
|  | CM Services | 119339.92 |  | 3892.16 |  | 115447.76
|  | Reimbursable | 944 |  |  |  | 944
|  | Fee | 27465.96 |  |  |  | 27465.96
|  | Total: | 147749.88 |  | 3892.16 |  | 143857.72

## #9279.40 VanMaanen Electric (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Van Maanen Electric(2) |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA25-9255 |  |  | 927940-03
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526077900 | 2026-03-18 | PO Procore | 998762 | 998762 |  |  | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  |  |  | 998762 |  | 0 | 998762
|  | Totals: | 998762 |  | 0 |  | 998762

## #9279.40 Controlled Asbesto (2)
HHS WRC Campus Utility Decentralization Phase 4 & Fire Alarm Phase 3
Project # 9279.40
Program code 927940 |  |  | Major Program 4B02
Controlled Asbestos |  |  | Vendor: 00002118118
Acct. Codes-0506-335-DA25-9255 |  |  | MA00521060C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526118911 | 2026-04-28 | DO Procore | 13660 | 13660 |  |  | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  |  |  | 13660 |  | 0 | 13660
|  | Totals: | 13660 |  | 0 |  | 13660
| Line 3 | Remediation Services 190hrs@68 | 12920 |  |  |  | 12920
| Line 11 | Non-Friable Disposal 1ton @100 | 100 |  |  |  | 100
| Line 12 | Travel 1280@.50 | 640 |  |  |  | 640
|  | Total: | 13660 |  | 0 |  | 13660

## RECAP #9279.41
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 130000
Shive Hattery |  | 98744 | 95714 | 3030
PM TIME |  | 10500 | 9474.02 | 1025.98
Misc. |  | 0 | 0 | 0
Story Construction |  | 20694.24 | 18881.53 | 1812.71
Total Project Cost | 130000 | 129938.24 | 124069.55 | 5868.69 | 61.76

## #9279.41 Funds Rec'd
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOULINDENCTFIRESUPPR | 2025-01-23 | 130000 | 130000
|  |  | Returning FY25 Funds to Agency | IET 33525224916 | 2025-08-12 | -83235.16 | -83235.16
|  |  | FY26 Funds Received from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 83235.16 | 83235.16
| Total Requested | 0 | Total Transferred |  |  | 130000 | 130000

## #9279.41 Shive Hattery
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA25-9260 |  |  | RFP927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525028905 | 2025-01-28 | PO Procore | 12436 | 12436 |  |  | 12436
PRC 3352502PA8905 | 2025-02-20 | Inv. 2240007040-401 |  | 12436 | 6218 | 6218 | 6218
PO 33525028905 | 2025-04-21 | CO #1 | 33409 | 45845 |  | 6218 | 39627
PRC 3352502PB8905 | 2025-04-24 | Inv. 2240007040-402 |  | 45845 | 6218 | 12436 | 33409
PRC 3352502PC8905 | 2025-07-07 | Inv. 2240007040-403 |  | 45845 | 28999.01 | 41435.01 | 4409.99 | FY25
PO 33526028905 | 2025-08-21 | Roll to FY26 | 0 | 45845 |  | 41435.01 | 4409.99
PO 33526028905 | 2025-09-12 | CO #2 | 52899 | 98744 |  | 41435.01 | 57308.99
PRC 3352602PD8905 | 2026-01-06 | Inv. 2240007040-404R |  | 98744 | 54278.99 | 95714 | 3030
|  |  |  | 98744 |  | 95714 | 3030
|  |  |  | 98744 |  | 95714 | 3030
|  |  |  | 98744 |  | 95714 | 3030
|  |  |  | 98744 |  | 95714 | 3030
|  |  |  | 98744 |  | 95714 | 3030
|  | Totals: | 98744 |  | 95714 |  | 3030

## #9279.41 PM TIME
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 732E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10500 | 10500 |  |  | 10500
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 10500 | 39.1 | 39.1 | 10460.9
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 10500 | 417.1 | 456.2 | 10043.8
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 10500 | 302.9 | 759.1 | 9740.9
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 10500 | 1309.8 | 2068.9 | 8431.1
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 10500 | 22.21 | 2091.11 | 8408.89
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 10500 | 156.6 | 2247.71 | 8252.29
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 10500 | 40.5 | 2288.21 | 8211.79
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 10500 | 281.6 | 2569.81 | 7930.19
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 10500 | 6.19 | 2576 | 7924
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 10500 | 46.9 | 2622.9 | 7877.1
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 10500 | 10.27 | 2633.17 | 7866.83
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 10500 | 81.8 | 2714.97 | 7785.03
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 10500 | 45.47 | 2760.44 | 7739.56
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 10500 | 501.7 | 3262.14 | 7237.86
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 10500 | 94.58 | 3356.72 | 7143.28
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 10500 | 723.8 | 4080.52 | 6419.48
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10500 | 355.38 | 4435.9 | 6064.1
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10500 | 1826.1 | 6262 | 4238
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10500 | 71.84 | 6333.84 | 4166.16
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10500 | 714.3 | 7048.14 | 3451.86
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10500 | 32.6 | 7080.74 | 3419.26
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10500 | 205.6 | 7286.34 | 3213.66
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10500 | 29.99 | 7316.33 | 3183.67
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10500 | 340.6 | 7656.93 | 2843.07
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 10500 | 93.73 | 7750.66 | 2749.34
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 10500 | 1167.9 | 8918.56 | 1581.44
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10500 | 36.41 | 8954.97 | 1545.03
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10500 | 418.8 | 9373.77 | 1126.23
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10500 | 11.15 | 9384.92 | 1115.08
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10500 | 89.1 | 9474.02 | 1025.98
[5 empty] | 10500 |  | 9474.02 | 1025.98
[5 empty] | 10500 |  | 9474.02 | 1025.98
[5 empty] | 10500 |  | 9474.02 | 1025.98
|  |  | Totals: | 10500 |  | 9474.02 |  | 1025.98
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Kleene, Jennifer 2:28 PM (1 minute ago) to me My apologies, please create a PM Time budget for $8,000.00 for 9279.41. Regards, Jennifer DAS Cost Budget Increases $Joni Kleene, Jennifer 9:49 AM (4 minutes ago) to me Please increase the DAS Cost budget for MM24 9277.00 by $3,000.00 Please increase the DAS Cost budget for DA26 9480.01 by $2,000.00 Please increase the DAS Cost budget for DA25 9433.00 by $1,000.00 Please increase the DAS Cost budget for DA25 9476.00 by $500.00 Please increase the DAS Cost budget for DA25 9279.41 by $1,000.00 Regards, Jennifer DA25 9279.41 DAS Cost Budget Adjustments $Joni Kleene, Jennifer Fri, Mar 6, 1:03 PM (3 days ago) to me Please increase the PM Time budget for DA25 9279.41 I by $1,500.00. Regards, Jennifer Jennifer Kleene

## #9279.41 Misc
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9279.41 Story Construction
HHS WRC Linden Court Fire Suppression
Project # 9279.41
Program code 927941 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525038904 | 2025-01-28 | PO Procore | 15796.16 | 15796.16 |  |  | 15796.16
PRC 3352503PA8904 | 2025-03-21 | Inv. 34772 |  | 15796.16 | 477.56 | 477.56 | 15318.6
PRC 3352503PB8904 | 2025-05-19 | Inv. 34841 |  | 15796.16 | 1912.94 | 2390.5 | 13405.66
PRC 3352503PC8904 | 2025-07-17 | Inv. 34908 |  | 15796.16 | 224.36 | 2614.86 | 13181.3 | FY25
PO 33526038904 | 2025-08-21 | Roll to FY26 | 0 | 15796.16 |  | 2614.86 | 13181.3
PRC 3352603PD8904 | 2025-10-17 | Inv. 35015 |  | 15796.16 | 2379.71 | 4994.57 | 10801.59
PRC 3352603PE8904 | 2025-11-18 | Inv. 35047 |  | 15796.16 | 1939.67 | 6934.24 | 8861.92
PRC 3352603PF8904 | 2025-12-16 | Inv. 35077 |  | 15796.16 | 3267.31 | 10201.55 | 5594.61
PRC 3352603PG8904 | 2026-01-20 | Inv. 35116 |  | 15796.16 | 4009.67 | 14211.22 | 1584.94
PO 33526038904 | 2026-02-05 | CO #1 | 4898.08 | 20694.24 |  | 14211.22 | 6483.02
PRC 3352603PH8904 | 2026-03-18 | Inv. 35193 |  | 20694.24 | 4670.31 | 18881.53 | 1812.71
|  |  |  | 20694.24 |  | 18881.53 | 1812.71
|  |  |  | 20694.24 |  | 18881.53 | 1812.71
|  | Totals: | 20694.24 |  | 18881.53 |  | 1812.71
|  | CM Services | 15707.66 |  | 15707.66 |  | 0
|  | Reimbursable Expenses | 88.5 |  |  |  | 88.5
|  | CO #1 | 4898.08 |  | 3173.87 |  | 1724.21
|  | Total: | 20694.24 |  | 18881.53 |  | 1812.71

## RECAP #9294.00
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
| Program code 929400 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager -Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 12790.78
C | Van Maanen |  | 12362.4 | 12362.4 | 0
C | PM TIME |  | 428.38 | 428.38 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 12790.78 | 12790.78 | 12790.78 | -1.819e-12 | 0
Closing 07/21/25

## #9294.00 Funds Recv'd
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager -Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUPROJ929400 | 2024-09-26 | 20000 | 20000
|  |  | Returning Funds to Agency Per PM | IET 33525136913 | 2025-05-16 | -6500 | -6500
|  |  | Returning Funds to Agency | IET 33525202900 | 2025-07-21 | -709.22 | -709.22
| Total Requested | 0 | Total Transferred |  |  | 12790.78 | 12790.78

## #9294.00 Van Maanen
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  | Major Program 4B02
Van Maanen |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA25-9255 |  |  | 927920-01
Project Manager -Jennifer K. |  |  | Activity code: BRUM
Split w/MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525073801 | 2024-10-14 | CO #5 | 12362.4 | 12362.4 |  |  | 12362.4
PO 33525073801 | 2024-12-19 | CO #6(No cost CO) | 0 | 12362.4 |  | 0 | 12362.4
PO 33525073801 | 2025-02-17 | CO #7(100% to MM23) | 0 | 12362.4 |  | 0 | 12362.4
PRC 3352507PF3801 | 2025-02-17 | Inv. 2271-05(Split W/DA25) |  | 12362.4 | 11744.28 | 11744.28 | 618.12 | 618.12
PRC 3352507PG3801 | 2025-06-18 | Inv. 2271-07(100% to MM23) |  | 12362.4 | 0 | 11744.28 | 618.12
PRC 3352507PH3801 | 2025-06-19 | Inv. 2271-08F Retainage (Split w/MM23) |  | 12362.4 | 618.12 | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  |  |  | 12362.4 |  | 12362.4 | -1.0232e-12
|  | Totals: | 12362.4 |  | 12362.4 |  | 0 | FINAL
|  | MM23 | 770378.71 |  | 770378.71 |  | 0
|  | Total Contract: | 782741.11 |  | 782741.11 |  | 0

## #9294.00 PM TIME
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager -Jennifer K. |  |  |  | eDAS 729Y
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 428.38 | 428.38 |  |  | 428.38
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 428.38 | 12.82 | 12.82 | 415.56
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 428.38 | 110.4 | 123.22 | 305.16
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 428.38 | 19.67 | 142.89 | 285.49
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 428.38 | 132.6 | 275.49 | 152.89
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 428.38 | 4.92 | 280.41 | 147.97
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 428.38 | 45.3 | 325.71 | 102.67
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 428.38 | 10.53 | 336.24 | 92.14
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 428.38 | 45.9 | 382.14 | 46.24
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 428.38 | 5.34 | 387.48 | 40.9
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 428.38 | 40.9 | 428.38 | -2.1316e-14
[5 empty] | 428.38 |  | 428.38 | -2.1316e-14
[5 empty] | 428.38 |  | 428.38 | -2.1316e-14
|  |  | Totals: | 428.38 |  | 428.38 |  | 0
Note on E9: Huggins, Joni [DAS]: DA25 Project 9294.00 DHS WRC Fire Alarm System Replacement Phase 1 $Joni Kleene, Jennifer Sun, Jul 20, 4:24 PM (16 hours ago) to me, Lucas All invoices have been paid and all DAS costs have posted, so please close DA25 project 9294.00 and return the remaining $709.22 to HHS. Regards, Jennifer

## #9294.00 Misc
DHS WRC Fire Alarm System Replacement Phase 1
Project # 9294.00
Program code 929400 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager -Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9358.01
ICN CC Lucas CRAC Replacement
Project # 9358.01
| Program code 935801 |  |  | Major Program 4F02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Oliver S.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 595000
C | Commonwealth Electric |  | 54357.1 | 54357.1 | 0
| PM TIME |  | 14557.5 | 10724.37 | 3833.13
| Misc. |  | 4575.12 | 4575.12 | 0
C | Central Iowa Mechanical |  | 418605.37 | 418605.37 | 0
| DCI Group |  | 75542.75 | 75542.75 | 0
| Total Project Cost | 595000 | 567637.84 | 563804.71 | 3833.13 | 27362.16
`

## #9358.01 Funds Recv'd
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  | Major Program 4F02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25EH022261 | 2024-08-02 | 595000 | 595000
|  |  | Returning FY25 Funds to Agency | IET 33525224917 | 2025-08-12 | -195203.53 | -195203.53
|  |  | Received FY26 Funds from Agency | IET 26EH024174 | 2025-08-27 | 195203.53 | 195203.53
| Total Requested | 0 | Total Transferred |  |  | 595000 | 595000

## #9358.01 Commonwealth Electric
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  | Major Program 4F02
Commonwealth Electric |  |  | Vendor: 00002135378
Acct. Codes-0506-335-DA25-9255 |  |  | RFB935800-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525219900 | 2024-08-06 | PO Procore | 35369 | 35369 |  |  | 35369
PRC 3352521PA9900 | 2025-04-02 | Inv. 79875 |  | 35369 | 3265.15 | 3265.15 | 32103.85 | 171.85
PO 33525219900 | 2025-04-22 | CO #1 | -55.56 | 35313.44 |  | 3265.15 | 32048.29
PO 33525219900 | 2025-05-08 | CO #2 | 19043.66 | 54357.1 |  | 3265.15 | 51091.95
PRC 3352521PB9900 | 2025-05-13 | Inv. 50365 |  | 54357.1 | 16929 | 20194.15 | 34162.95 | 1062.85
PO 33525219900 | 2025-06-12 | CO #3(No Cost CO) | 0 | 54357.1 |  | 20194.15 | 34162.95
PRC 3352521PC9900 | 2025-07-02 | Inv. 9358.01-03 |  | 54357.1 | 929.52 | 21123.67 | 33233.43 | 1111.77
PRC 3352521PD9900 | 2025-07-08 | Inv. 73257 |  | 54357.1 | 11875 | 32998.67 | 21358.43 | 1736.77 | FY25
PO 33526219900 | 2025-08-21 | Roll to FY26 | 0 | 54357.1 |  | 32998.67 | 21358.43
PCR 3352621PE9900 | 2025-08-28 | Inv. 80820 |  | 54357.1 | 4750 | 37748.67 | 16608.43 | 1986.77
PCR 3352621PF9900 | 2025-09-15 | Inv. 26195 |  | 54357.1 | 6031.23 | 43779.9 | 10577.2 | 2304.2
PO 33526219900 | 2025-09-16 | CO #4(No Cost CO) | 0 | 54357.1 |  | 43779.9 | 10577.2
PCR 3352621PG9900 | 2026-01-16 | Inv. 81196 |  | 54357.1 | 6909.35 | 50689.25 | 3667.85 | 2667.85
PCR 3352621PH9900 | 2026-02-24 | Inv. 9358.01-08 FINAL |  | 54357.1 | 950 | 51639.25 | 2717.85 | 2717.85
PCR 3352621PI9900 | 2026-03-04 | Inv. 9358.01 Please add retainage |  | 54357.1 | 2717.85 | 54357.1 | 4.5475e-13
|  | Totals: | 54357.1 |  | 54357.1 |  | 0

## #9358.01 PM TIME
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  |  | Major Program 4F02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S. |  |  |  | eDAS 909Q
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 14557.5 | 14557.5 |  |  | 14557.5
CDE 33525132908 | 2025-05-12 | 2507 | Moving PM Time From 9358.00 DA24 |  | 14557.5 | 70.02 | 70.02 | 14487.48
CDE 33525132908 | 2025-05-12 | 9500 | Moving PM Time From 9358.00 DA24 |  | 14557.5 | 480.8 | 550.82 | 14006.68
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 14557.5 | 114.96 | 665.78 | 13891.72
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 14557.5 | 243.5 | 909.28 | 13648.22
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 14557.5 | 10.27 | 919.55 | 13637.95
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 14557.5 | 81.8 | 1001.35 | 13556.15
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 14557.5 | 38.54 | 1039.89 | 13517.61
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 14557.5 | 421.9 | 1461.79 | 13095.71
CDE 33526226902 | 2025-08-14 | 2507 | Moving PM Time From 9358.00 DA24 |  | 14557.5 | 57.26 | 1519.05 | 13038.45
CDE 33526226902 | 2025-08-14 | 9500 | Moving PM Time From 9358.00 DA24 |  | 14557.5 | 631.8 | 2150.85 | 12406.65
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 14557.5 | 95.79 | 2246.64 | 12310.86
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 14557.5 | 738.6 | 2985.24 | 11572.26
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 14557.5 | 186.1 | 3171.34 | 11386.16
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 14557.5 | 956.8 | 4128.14 | 10429.36
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 14557.5 | 99.15 | 4227.29 | 10330.21
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 14557.5 | 985 | 5212.29 | 9345.21
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 14557.5 | 124.7 | 5336.99 | 9220.51
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 14557.5 | 792.9 | 6129.89 | 8427.61
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 14557.5 | 103.22 | 6233.11 | 8324.39
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 14557.5 | 1175.5 | 7408.61 | 7148.89
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 14557.5 | 90.87 | 7499.48 | 7058.02
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 14557.5 | 1126.9 | 8626.38 | 5931.12
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 14557.5 | 103.4 | 8729.78 | 5827.72
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 14557.5 | 1189.7 | 9919.48 | 4638.02
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 14557.5 | 88.19 | 10007.67 | 4549.83
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 14557.5 | 716.7 | 10724.37 | 3833.13
[5 empty] | 14557.5 |  | 10724.37 | 3833.13
[5 empty] | 14557.5 |  | 10724.37 | 3833.13
[5 empty] | 14557.5 |  | 10724.37 | 3833.13
|  |  | Totals: | 14557.5 |  | 10724.37 |  | 3833.13
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer 3:21 PM (8 minutes ago) to me, Oliver Please make the following budget changes and let me know if you have any questions. MM23 9279.20 increase the PM Time budget by $2000.00 MM23 9268.01 increase the PM Time budget by $2000.00 Please also create a DAS Costs budget for $3,057.50 in DA25 9358.01. This is where our billing will need to switch to once the available funds in DA24 9358.00 are exhausted. Regards, Jennifer Jennifer Kleene DA25 9358.01 - Please increase PM Time budget by $2,000.00 Thank you very much, I've contacted Iowa Department of Revenue regarding providing the funds for project 9492.00 as quickly as possible let me know if I can help further. Oliver Shimp Shimp, Oliver Nov 10, 2025, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. Shimp, Oliver 11:40 AM (1 minute ago) to me Could you please move $2,000.00 of this unallocated budget to the PM time code? for 9358.01 DA25 Thank you, Oliver -- Oliver Shimp, PE Shimp, Oliver 11:13 AM (9 minutes ago) to me Good Morning Joni, Thank you for the reminder about these. Could you please make the below changes to these projects. I'll be in touch about the TerraCon invoice for DA 26 9482.00 shortly as well, thank you for your help! Unit DA25 Program 935801 Please move $2,000.00 from Unallocated to PM Time Unit DA26 Program 948200 I will follow up on this project. Additional MOU funds are needed, but IDB now uses DAS finance, it's unclear if MOU is the appropriate process still Unit MM23 Program 940400 Please move $600.00 from the unallocated to PM Time Unit MM25 Program 945100 Please move $2,000.00 from unallocated to PM Time Unit X674 Program 947200 Please Move $2,000.00 from unallocated to PM Time. Thank you, Oliver Shimp Re: February PM Time Posted $Joni Shimp, Oliver Mar 13, 2026, 8:26 AM (3 days ago) to me Good Morning, Thank for you the list, could you please make the following adjustments? DA25 9358.01 $(361.98) Please move $5,000.00 from unallocated to PM Time

## #9358.01 Misc
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  |  | Major Program 4F02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S. |  |  |  | Shipping Code: 035
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525099900 | 2025-04-09 | 9500 | CNST | Controlled Asbestos V#(00002118118) | Inv. 0010914-IN | 558.5 | 558.5
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Fire Watch Services March1-31, 2025 | DAS2025091153 | 182.68 | 741.18
IET 33525182902 | 2025-07-02 | 9500 | CNST | ICN Bill | Inv. 64525063 | 1200 | 1941.18
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Electrical Services August1-31,2025 | DAS2026021153 | 171.43 | 2112.61
GAX 33526275904 | 2025-10-03 | 9500 | CNST | Protex Central V#(00002134903) | Inv. 165085 | 900 | 3012.61
PRC 33526324900 | 2025-11-20 | 9500 | CNST | Waldinger Corp V#(00002116105) | Inv. 7561410-1 | 625.71 | 3638.32
IET 33526078913 | 2026-03-19 | 9500 | CNST | ICN - Cummins Testing | Inv. 64526038 | 936.8 | 4575.12
4575.12
4575.12
4575.12
4575.12
4575.12
|  |  |  | Totals: |  | 4575.12

## #9358.01 Central IA Mechanical
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  | Major Program 4F02
Central Iowa Mechanical |  |  | Vendor: 00002109717
Acct. Codes-0506-335-DA25-9255 |  |  | RFB935800-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525219901 | 2024-08-06 | PO Procore | 402364 | 402364 |  |  | 402364
PRC 3352521PA9901 | 2025-02-20 | Inv. 9358.01-AIA #01 |  | 402364 | 19309.7 | 19309.7 | 383054.3 | 1016.3
PO 33525219901 | 2025-02-21 | CO #1 | 1351 | 403715 |  | 19309.7 | 384405.3
PO 33525219901 | 2025-03-17 | CO #2 | 2752.32 | 406467.32 |  | 19309.7 | 387157.62
PRC 3352521PB9901 | 2025-04-02 | Inv. 9358.01-AIA #02 |  | 406467.32 | 14950.15 | 34259.85 | 372207.47 | 1803.15
PO 33525219901 | 2025-04-03 | CO #3 | 7909 | 414376.32 |  | 34259.85 | 380116.47
PRC 3352521PC9901 | 2025-04-09 | Inv. 9358.01-AIA #03 |  | 414376.32 | 151959.45 | 186219.3 | 228157.02 | 9801.02
PRC 3352521PD9901 | 2025-05-12 | Inv. 9358.01-AIA #04 |  | 414376.32 | 86649.88 | 272869.18 | 141507.14 | 14361.54
PO 33525219901 | 2025-05-21 | CO #4 | 2367.75 | 416744.07 |  | 272869.18 | 143874.89
PRC 3352521PE9901 | 2025-06-10 | Inv. 9358.01-AIA #05 |  | 416744.07 | 14127.22 | 286996.4 | 129747.67 | 15105.07
PRC 3352521PF9901 | 2025-07-02 | Inv. 9358.01-AIA#06 |  | 416744.07 | 27417 | 314413.4 | 102330.67 | 16548.07 | FY25
PO 33526219901 | 2025-08-21 | Roll to FY26 | 0 | 416744.07 |  | 314413.4 | 102330.67
PRC 3352621PG9901 | 2025-08-28 | Inv. 9358.01-AIA #07 |  | 416744.07 | 2955.45 | 317368.85 | 99375.22 | 16703.62
PO 33526219901 | 2025-09-11 | CO #5 | 1861.3 | 418605.37 |  | 317368.85 | 101236.52
PRC 3352621PH9901 | 2025-09-15 | Inv. 9358.01-AIA #08 |  | 418605.37 | 43790.82 | 361159.67 | 57445.7 | 19008.4
PO 33526219901 | 2025-09-23 | CO #6(No Cost CO) | 0 | 418605.37 |  | 361159.67 | 57445.7
PRC 3352621PI9901 | 2025-10-14 | Inv. 9358.01-AIA #09 |  | 418605.37 | 32690.73 | 393850.4 | 24754.97 | 20728.97
PRC 3352621PJ9901 | 2025-11-14 | Inv. 9358.01-AIA #10 |  | 418605.37 | 3824.7 | 397675.1 | 20930.27 | 20930.27
PRC 3352621PK9901 | 2026-01-26 | Inv. 9358.01 Retention |  | 418605.37 | 20930.27 | 418605.37 | -4.0018e-11
|  |  |  | 418605.37 |  | 418605.37 | -4.0018e-11
|  |  |  | 418605.37 |  | 418605.37 | -4.0018e-11
|  | Totals: | 418605.37 |  | 418605.37 |  | 0 | FINAL
Use 9358.0-AIA #X =Vendor has used AIA #X in another tab

## #9358.01 DCI Group
ICN CC Lucas CRAC Replacement
Project # 9358.01
Program code 935801 |  |  | Major Program 4F02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525208908 | 2024-08-06 | PO Procore | 76924.68 | 76924.68 |  |  | 76924.68
PRC 3352520PA8908 | 2024-12-03 | Inv. 23-047 CA 01A |  | 76924.68 | 9179.4 | 9179.4 | 67745.28
PRC 3352520PB8908 | 2024-12-20 | Inv. 23-047 CA 02A |  | 76924.68 | 2652.46 | 11831.86 | 65092.82
PRC 3352520PC8908 | 2025-02-17 | Inv. 23-049 CA 03A |  | 76924.68 | 1279.51 | 13111.37 | 63813.31
PRC 3352520PD8908 | 2025-03-11 | Inv. 23-049 CA 04A |  | 76924.68 | 7279.42 | 20390.79 | 56533.89
PRC 3352520PE8908 | 2025-04-09 | Inv. 23-049 CA 05A |  | 76924.68 | 11680.78 | 32071.57 | 44853.11
PRC 3352520PF8908 | 2025-05-12 | Inv. 23-049 CA 06A |  | 76924.68 | 10255.55 | 42327.12 | 34597.56
PRC 3352520PG8908 | 2025-06-10 | Inv. 23-049 CA 07A |  | 76924.68 | 898.1 | 43225.22 | 33699.46
PRC 3352520PH8908 | 2025-07-08 | Inv. 23-049 CA 08A |  | 76924.68 | 6216.65 | 49441.87 | 27482.81 | FY25
PO 33526208908 | 2025-08-21 | Roll to FY26 | 0 | 76924.68 |  | 49441.87 | 27482.81
PRC 3352620PI8908 | 2025-08-29 | Inv. 23-049 CA 09 |  | 76924.68 | 4470.32 | 53912.19 | 23012.49
PO 33526208908 | 2025-09-16 | CO #1 | 1936.72 | 78861.4 |  | 53912.19 | 24949.21
PRC 3352620PJ8908 | 2025-09-23 | Inv. 23-049 CA 10 |  | 78861.4 | 8674.58 | 62586.77 | 16274.63
PRC 3352620PK8908 | 2025-10-10 | Inv. 23-049 CA 11 |  | 78861.4 | 10199.82 | 72786.59 | 6074.81
PRC 3352620PL8908 | 2025-11-18 | Inv. 23-049 CA 12 |  | 78861.4 | 2915.46 | 75702.05 | 3159.35
PO 33526208908 | 2025-11-21 | CO #2 | -312.85 | 78548.55 |  | 75702.05 | 2846.5
PO 33526208908 | 2026-04-21 | Closing out PO per PM Email | -3005.8 | 75542.75 |  | 75702.05 | -159.3
PO 33526208908 | 2026-04-21 | Check received from DCI group |  | 75542.75 | -159.3 | 75542.75 | -6.2528e-13
|  |  |  | 75542.75 |  | 75542.75 | -6.2528e-13
|  | Totals: | 75542.75 |  | 75542.75 |  | 0
|  | Construction Management | 37408.03 |  | 37408.03 |  | 0
|  | Reimbursable Expenses | 0 |  |  |  | 0
|  | Construction Management Fee | 36198 |  | 36198 |  | 0
|  | CO #1 | 1936.72 |  | 1936.72 |  | 0
|  | CO #2 | 0 |  |  |  | 0
|  | Total: | 75542.75 |  | 75542.75 |  | 0
*Vendor has previously used 23-047 CA 0X in another tab.
Please add a letter at the end
PO closed in Iowa Advantage for $26260.18 Spreadsheet will not match as a refund check for $159.30 was received

## RECAP #9360.01
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
| Program code 936001 |  |  | Major Program 3E01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 142460.45
C | Air-Con Electric |  | 116482 | 116482 | 0
C | PM TIME |  | 3795 | 3795 | 0
C | Misc. |  | 0 | 0 | 0
C | McGough Construction |  | 15602.16 | 15602.16 | 0
C | McGough Construction(2) |  | 696.29 | 696.29 | 0
C | KCL Engineering |  | 5885 | 5885 | 0
| Total Project Cost | 142460.45 | 142460.45 | 142460.45 | 0 | 0
Closed 04/10/25

## #9360.01 Funds Recv'd
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  | Major Program 3E01
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Brandon A.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 07292400008 | 2024-07-29 | 175000 | 175000
|  |  | Closing Project Per PM | IET 33525100900 | 2025-04-10 | -32539.55 | -32539.55
| Total Requested | 0 | Total Transferred |  |  | 142460.45 | 142460.45

## #9360.01 Air-Con Electric
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  | Major Program 3E01
Air-Con Electric |  |  | Vendor: 00003095844
Acct. Codes-0506-335-DA25-9255 |  |  | RFB 936000-02
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525212900 | 2024-07-30 | PO Procore | 114989 | 114989 |  |  | 114989
PRC 3352521PA2900 | 2024-10-02 | Inv. 1794 |  | 114989 | 9397.16 | 9397.16 | 105591.84 | 494.59
PO 33525212900 | 2024-11-04 | CO #1 | 350 | 115339 |  | 9397.16 | 105941.84
PRC 3352521PB2900 | 2024-11-06 | Inv. 1806 |  | 115339 | 63434.08 | 72831.24 | 42507.76 | 3833.23
PRC 3352521PC2900 | 2024-12-16 | Inv. 1816 |  | 115339 | 24219.51 | 97050.75 | 18288.25 | 5107.95
PRC 3352521PD2900 | 2025-01-14 | Inv. 1831 |  | 115339 | 3455.62 | 100506.37 | 14832.63 | 5289.83
PRC 3352521PE2900 | 2025-02-05 | Inv. 1845 |  | 115339 | 7772.71 | 108279.08 | 7059.92 | 5698.93
PO 33525212900 | 2025-02-18 | CO #2 | 1143 | 116482 |  | 108279.08 | 8202.92
PRC 3352521PF2900 | 2025-02-24 | Inv. 1851 |  | 116482 | 1286.39 | 109565.47 | 6916.53 | 5766.64
PRC 3352521PG2900 | 2025-03-26 | Inv. 1859 |  | 116482 | 1092.4 | 110657.87 | 5824.13 | 5824.13
PRC 3352521PH2900 | 2025-04-02 | Inv. 1861 Retainage |  | 116482 | 5824.13 | 116482 | -2.7285e-12
|  |  |  | 116482 |  | 116482 | -2.7285e-12
|  |  |  | 116482 |  | 116482 | -2.7285e-12
|  | Totals: | 116482 |  | 116482 |  | 0 | FINAL

## #9360.01 PM TIME
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Brandon A. |  |  |  | eDAS E2E1
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 3795 | 3795 |  |  | 3795
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 3795 | 440 | 440 | 3355
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 3795 | 275 | 715 | 3080
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 3795 | 385 | 1100 | 2695
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 3795 | 385 | 1485 | 2310
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 3795 | 247.5 | 1732.5 | 2062.5
IET DAS202506115300001 | 2025-01-09 | 9500 | Finance Support for December 1-31, 2024 |  | 3795 | 247.5 | 1980 | 1815
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 3795 | 687.5 | 2667.5 | 1127.5
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 3795 | 522.5 | 3190 | 605
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 3795 | 605 | 3795 | 0
[5 empty] | 3795 |  | 3795 | 0
|  |  | Totals: | 3795 |  | 3795 |  | 0
Note on E9: Huggins, Joni [DAS]: Projects Closing $Joni Adams, Brandon Apr 3, 2025, 10:36 AM (7 days ago) to me Finance, Please close the following project PM Time once March hours post: MM23 - 9250.00 MM22 - 9367.00 DA25 - 9360.01 All above projects will close after PM Time posts. Regards, Brandon Adams

## #9360.01 Misc
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  |  | Major Program 3E01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9360.01 McGough Construction
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  | Major Program 3E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525212902 | 2024-07-30 | PO Procore | 26719.46 | 26719.46 |  |  | 26719.46
PRC 3352521PA2902 | 2024-09-12 | Inv. 101031.006-01CA |  | 26719.46 | 1959.11 | 1959.11 | 24760.35
PRC 3352521PB2902 | 2024-10-09 | Inv. 101031.006-02CA |  | 26719.46 | 3185.03 | 5144.14 | 21575.32
PRC 3352521PC2902 | 2024-11-12 | Inv. 101031.006-03CA |  | 26719.46 | 3278.46 | 8422.6 | 18296.86
PO 33525212902 | 2024-12-16 | CO #1 | 120 | 26839.46 |  | 8422.6 | 18416.86
PRC 3352521PD2902 | 2024-12-23 | Inv. 101031.006-04CA |  | 26839.46 | 4993.27 | 13415.87 | 13423.59
PRC 3352521PE2902 | 2025-01-14 | Inv. 101031.006-05CA |  | 26839.46 | 680.93 | 14096.8 | 12742.66
PRC 3352521PF2902 | 2025-02-12 | Inv. 101031.006-06CA |  | 26839.46 | 592.51 | 14689.31 | 12150.15
PRC 3352521PG2902 | 2025-03-19 | Inv. 101031.006-07CA |  | 26839.46 | 625.86 | 15315.17 | 11524.29
PRC 3352521PH2902 | 2025-04-03 | Inv. 101031.006-08CA FINAL | -11237.3 | 15602.16 | 286.99 | 15602.16 | 0
|  |  |  | 15602.16 |  | 15602.16 | 0
|  |  |  | 15602.16 |  | 15602.16 | 0
|  |  |  | 15602.16 |  | 15602.16 | 0
|  | Totals: | 15602.16 |  | 15602.16 |  | 0 | FINAL
|  | CM Services | 15272.82 |  | 15272.82 |  | 0
|  | Reimbursables | 270 |  | 270 |  | 0
|  | CO #1 | 59.34 |  | 59.34 |  | 0
|  | Total: | 15602.16 |  | 15602.16 |  | 0

## #9360.01 McGough Constr (2)
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  | Major Program 3E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525283800 | 2024-08-15 | Moved PO From DA24 | 906.42 | 906.42 |  |  | 906.42
PRC 3352528PJ3800 | 2024-08-19 | Inv. 101031.006-PC10-FINAL | -210.13 | 696.29 | 696.29 | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  |  |  | 696.29 |  | 696.29 | 0
|  | Totals: | 696.29 |  | 696.29 |  | 0 | FINAL
|  | DA24(Closed 08/15/2024) | 12880.01 |  | 12880.01 |  | 0
|  | Total Contract | 13576.3 |  | 13576.3 |  | 0

## #9360.01 KCL Engineering
IPBS JOH 6450 Corporate Dr. Fire Alarm System Replacement
Project # 9360.01
Program code 936001 |  |  | Major Program 3E01
KCL Engineering |  |  | Vendor:00002103747
Acct. Codes-0506-335-DA25-9260 |  |  | RFP936000-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525334912 | 2025-08-16 | Moved PO From DA24 | 5885 | 5885 |  |  | 5885
PRC 3352533PE4912 | 2024-08-23 | Inv. 10476 |  | 5885 | 1177 | 1177 | 4708
PRC 3352533PF4912 | 2024-10-14 | Inv. 10739 |  | 5885 | 1177 | 2354 | 3531
PRC 3352533PG4912 | 2024-12-03 | Inv. 10928 |  | 5885 | 1466 | 3820 | 2065
PRC 3352533PH4912 | 2025-01-24 | Inv. 11208 |  | 5885 | 774.25 | 4594.25 | 1290.75
PRC 3352533PI4912 | 2025-02-24 | Inv. 11378 |  | 5885 | 1231.9 | 5826.15 | 58.85
PRC 3352533PJ4912 | 2025-04-03 | Inv. 11378FINAL |  | 5885 | 58.85 | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  |  |  | 5885 |  | 5885 | -9.2371e-14
|  | Totals: | 5885 |  | 5885 |  | 0 | FINAL
|  | DA24(Closed 08/15/2024) | 19930 |  | 19930 |  | 0
|  | Total Contract | 25815 |  | 25815 |  | 0

## RECAP #9366.00
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
| Program code 936600 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 41634.05
C | Jensen Builders |  | 40868 | 40868 | 0
C | PM TIME |  | 766.05 | 766.05 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 41634.05 | 41634.05 | 41634.05 | 0 | 0
Closed 11/14/26

## #9366.00 Funds Rec'd
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812Y25042 | 2025-05-29 | 48000 | 48000
|  |  | Returning FY25 Funds to Agency | IET 33525224918 | 2025-08-12 | -48000 | -48000
|  |  | Received FY26 Funds from Agency | IET 23812Y26002 | 2025-08-27 | 48000 | 48000
|  |  | Returning Funds to Agency - Closing Project | IET 33526321901 | 2025-11-17 | -6365.95 | -6365.95
| Total Requested | 0 | Total Transferred |  |  | 41634.05 | 41634.05

## #9366.00 Jensen Builders
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  | Major Program 4B01
Jensen Builders |  |  | Vendor: 00002115639
Acct. Codes-0506-335-DA25-9255 |  |  | RFB936600-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM24
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526351900 | 2025-09-17 | Splitting with MM24 | 40868 | 40868 |  |  | 40868
PRC 3352635PB1900 | 2025-09-22 | Inv. 25028-00003(Split W/MM24) |  | 40868 | 38824.6 | 38824.6 | 2043.4 | 2043.4
PRC 3352635PC1900 | 2025-10-14 | Inv. 9366.00-Retainage(Split w/MM24) |  | 40868 | 2043.4 | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  |  |  | 40868 |  | 40868 | 1.3642e-12
|  | Totals: | 40868 |  | 40868 |  | 0
|  | MM24 | 255172 |  | 255172 |  | 0
|  | Total: | 296040 |  | 296040 |  | 0

## #9366.00 PM TIME
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 911B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 766.05 | 766.05 |  |  | 766.05
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 766.05 | 14.21 | 14.21 | 751.84
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 766.05 | 154.1 | 168.31 | 597.74
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 766.05 | 28.4 | 196.71 | 569.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 766.05 | 219.2 | 415.91 | 350.14
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 766.05 | 31.84 | 447.75 | 318.3
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 766.05 | 318.3 | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
[5 empty] | 766.05 |  | 766.05 | 1.7053e-13
|  |  | Totals: | 766.05 |  | 766.05 |  | 0

## #9366.00 Misc
DOC NCCF IPI Sally Port Vehicle Gate
Project # 9366.00
Program code 936600 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9424.00
HHS STS Main Electrical Loop Revisions
Project # 9424.00
| Program code 942400 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 112934.75
C | IMEG Corporation |  | 13925 | 13925 | 0
C | PM TIME |  | 8519.71 | 8519.71 | 0
C | Misc. |  | 0 | 0 | 0
C | McGough Construction |  | 9868.04 | 9868.04 | 0
C | K&W Electric |  | 80622 | 80622 | 0
| Total Project Cost | 112934.75 | 112934.75 | 112934.75 | 0 | 0
Closed 07/31/25

## #9424.00 Funds Rec'd
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 405EL25184008 | 2024-07-02 | 280000 | 280000
|  |  | MOU | IET 405EL25184007 | 2024-08-02 | 280000 | 280000
|  |  | Funds Reversed for duplicate payment | IET 400EL25220020 | 2024-08-08 | -280000 | -280000
|  |  | FY25 Funds Recv'd incorrect Unit | IET 405EL25262001 | 2024-09-18 | 16054.8 | 16054.8
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263901 | 2024-09-19 | -16054.8 | -16054.8
|  |  | Return funds to agency | IET 33525021201 | 2025-01-22 | -140000 | -140000
|  |  | Return funds to agency | IET 33525148904 | 2025-05-28 | -20000 | -20000
|  |  | Return funds to agency - Closing Project | IET 33525213900 | 2025-07-31 | -7065.25 | -7065.25
| Total Requested | 0 | Total Transferred |  |  | 112934.75 | 112934.75

## #9424.00 IMEG Corporation
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
IMEG Corporation |  |  | Vendor: 00003106665
Acct. Codes-0506-335-DA25-9260 |  |  | RFP942400-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525228900 | 2024-08-15 | PO Procore | 13925 | 13925 |  |  | 13925
PRC 3352522PA8900 | 2024-10-09 | Inv. 24004598.00-1 |  | 13925 | 8925 | 8925 | 5000
PRC 3352522PB8900 | 2025-01-06 | Inv. 9424.00-02 |  | 13925 | 2500 | 11425 | 2500
PRC 3352522PC8900 | 2025-06-23 | Inv. 24004598.00-3 Final |  | 13925 | 2500 | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  |  |  | 13925 |  | 13925 | 0
|  | Totals: | 13925 |  | 13925 |  | 0 | FINAL
|  | 100% Construction Docs | 7425 |  | 7425 |  | 0
|  | Bidding & Negotiation | 1500 |  | 1500 |  | 0
|  | Construction Phase | 5000 |  | 5000 |  | 0
|  | Total: | 13925 |  | 13925 |  | 0

## #9424.00 PM TIME
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E2DY
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8519.71 | 8519.71 |  |  | 8519.71
IET DAS202501115300001 | 2024-08-07 | 2507 | Finance Support for July 1-31,2024 |  | 8519.71 | 141.93 | 141.93 | 8377.78
IET DAS202501115300001 | 2024-08-07 | 9500 | DAS Services for July 1-31, 2024 |  | 8519.71 | 1549.2 | 1691.13 | 6828.58
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 8519.71 | 228.03 | 1919.16 | 6600.55
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 8519.71 | 1160.4 | 3079.56 | 5440.15
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 8519.71 | 155.66 | 3235.22 | 5284.49
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 8519.71 | 1383.1 | 4618.32 | 3901.39
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 8519.71 | 177.62 | 4795.94 | 3723.77
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 8519.71 | 1187.5 | 5983.44 | 2536.27
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 8519.71 | 28.39 | 6011.83 | 2507.88
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 8519.71 | 187.4 | 6199.23 | 2320.48
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 8519.71 | 18.29 | 6217.52 | 2302.19
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 8519.71 | 182.4 | 6399.92 | 2119.79
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 8519.71 | 15.18 | 6415.1 | 2104.61
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 8519.71 | 166.7 | 6581.8 | 1937.91
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 8519.71 | 20.79 | 6602.59 | 1917.12
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 8519.71 | 90.1 | 6692.69 | 1827.02
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 8519.71 | 118.48 | 6811.17 | 1708.54
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 8519.71 | 926.9 | 7738.07 | 781.64
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 8519.71 | 88.74 | 7826.81 | 692.9
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 8519.71 | 692.9 | 8519.71 | 2.2737e-13
[5 empty] | 8519.71 |  | 8519.71 | 2.2737e-13
|  |  | Totals: | 8519.71 |  | 8519.71 |  | 0
Note on E9: Huggins, Joni [DAS]: PM Time Budget Changes $Joni Kleene, Jennifer 10:13 AM (1 hour ago) to me, Scott Please increase the PM Time Budgets as follows: MM23 9294.01 increase by $3,740.00 DA25 9424.00 increase by $2,000.00 MM22 9244.00 increase by $2,000.00 MM22 9274.00 increase by $600.00 X674 9379.00 increase by $8,800.00 MM24 9391.00 increase by $8,800.00 Regards, Jennifer Please Close DA25 Project 9424.00 HHS STS Main Electrical Loop Revisions $Joni Kleene, Jennifer 11:30 AM (27 minutes ago) to me, Geoff, Christopher, Robert All invoices have been paid and all DAS costs have posted, so please close DA25 9424.00 and return the remaining $7,065.25 to HHS. Regards, Jennifer

## #9424.00 Misc
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9424.00 McGough Construction
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525276910 | 2024-10-02 | PO Procore | 16471.94 | 16471.94 |  |  | 16471.94
PRC 3352527PA6910 | 2024-11-19 | Inv. 101174.012-CA01 |  | 16471.94 | 2320.67 | 2320.67 | 14151.27
PRC 3352527PB6910 | 2024-12-18 | Inv. 101174.012-CA02 |  | 16471.94 | 1394.02 | 3714.69 | 12757.25
PRC 3352527PC6910 | 2025-01-17 | Inv. 101174.012-CA03 |  | 16471.94 | 4333.42 | 8048.11 | 8423.83
PRC 3352527PD6910 | 2025-02-12 | Inv. 101174.012-CA04 |  | 16471.94 | 172.67 | 8220.78 | 8251.16
PRC 3352527PE6910 | 2025-06-24 | Inv. 101174.012-CA05 Final | -6603.9 | 9868.04 | 1647.26 | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  |  |  | 9868.04 |  | 9868.04 | 0
|  | Totals: | 9868.04 |  | 9868.04 |  | 0 | FINAL
|  | CM Services | 9388.04 |  | 9388.04 |  | 0
|  | Reimbursables | 480 |  | 480 |  | 0
|  | Total: | 9868.04 |  | 9868.04 |  | 0

## #9424.00 K&W Electric
HHS STS Main Electrical Loop Revisions
Project # 9424.00
Program code 942400 |  |  | Major Program 4E02
K&W Electric |  |  | Vendor: 00002114444
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942400-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525278901 | 2024-10-04 | PO Procore | 75750 | 75750 |  |  | 75750
PO 33525278901 | 2024-12-19 | CO #1 | 4872 | 80622 |  | 0 | 80622
PRC 3352527PA8901 | 2025-01-03 | Inv. 7226ES1 |  | 80622 | 71850.4 | 71850.4 | 8771.6 | 3781.6
PRC 3352527PB8901 | 2025-06-12 | Inv. 7226ES2 |  | 80622 | 4740.5 | 76590.9 | 4031.1 | 4031.1
PRC 3352527PC8901 | 2025-06-18 | Inv. 7226RT1 -Retainage |  | 80622 | 4031.1 | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  |  |  | 80622 |  | 80622 | 5.9117e-12
|  | Totals: | 80622 |  | 80622 |  | 0 | FINAL

## RECAP #9425.01
HHS STS North Buildings HazMat Survey
Project # 9425.01
| Program code 942501 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 120684.88
C | McGough Construction |  | 9134.23 | 9134.23 | 0
C | PM TIME |  | 7487.86 | 7487.86 | 0
C | Misc. |  | 200 | 200 | 0
C | ATC Group |  | 12326.25 | 12326.25 | 0
C | Jamco Abatement Services |  | 73730 | 73730 | 0
C | McGough Construction (2) |  | 17806.54 | 17806.54 | 0
| Total Project Cost | 120684.88 | 120684.88 | 120684.88 | -1.4552e-11 | 0
Closed 08/05/25

## #9425.01 Funds Recv'd
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 405EL25295008 | 2024-10-22 | 650000 | 650000
|  |  | Return funds to agency | IET 33525070904 | 2025-03-11 | -480000 | -480000
|  |  | Return funds to agency | IET 33525148905 | 2025-05-28 | -32000 | -32000
|  |  | Return funds to agency-Project closing | IET 33525217904 | 2025-08-05 | -17315.12 | -17315.12
| Total Requested | 0 | Total Transferred |  |  | 120684.88 | 120684.88

## #9425.01 McGough Construction
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  | Major Program 4E02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525312905 | 2025-11-07 | PO Procore | 13967.81 | 13967.81 |  |  | 13967.81
PRC 3352531PA2905 | 2024-12-18 | Inv. 101368.001-PC01 |  | 13967.81 | 1749.52 | 1749.52 | 12218.29
PRC 3352531PB2905 | 2025-01-15 | Inv. 101368.001-PC02 |  | 13967.81 | 1113.13 | 2862.65 | 11105.16
PRC 3352531PC2905 | 2025-02-12 | Inv. 101368.001-PC03 |  | 13967.81 | 2168.05 | 5030.7 | 8937.11
PRC 3352531PD2905 | 2025-03-21 | Inv. 101368.001-PC04 |  | 13967.81 | 3120.48 | 8151.18 | 5816.63
PRC 3352531PE2905 | 2025-04-15 | Inv. 101368.001-PC05 Final | -4833.58 | 9134.23 | 983.05 | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  |  |  | 9134.23 |  | 9134.23 | 0
|  | Totals: | 9134.23 |  | 9134.23 |  | 0 | FINAL
|  | CM Services | 8814.23 |  | 8814.23 |  | 0
|  | Reimbursables | 320 |  | 320 |  | 0
|  | Total: | 9134.23 |  | 9134.23 |  | 0

## #9425.01 PM TIME
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS 910O
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 7487.86 | 7487.86 |  |  | 7487.86
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 7487.86 | 39.77 | 39.77 | 7448.09
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 7487.86 | 262.6 | 302.37 | 7185.49
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 7487.86 | 253.97 | 556.34 | 6931.52
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 7487.86 | 1685.5 | 2241.84 | 5246.02
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 7487.86 | 45.98 | 2287.82 | 5200.04
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 7487.86 | 454.9 | 2742.72 | 4745.14
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 7487.86 | 101.39 | 2844.11 | 4643.75
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 7487.86 | 1085.1 | 3929.21 | 3558.65
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 7487.86 | 83.41 | 4012.62 | 3475.24
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 7487.86 | 361.6 | 4374.22 | 3113.64
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 7487.86 | 73.1 | 4447.32 | 3040.54
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 7487.86 | 523.9 | 4971.22 | 2516.64
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 7487.86 | 139.63 | 5110.85 | 2377.01
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 7487.86 | 962.7 | 6073.55 | 1414.31
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 7487.86 | 76.69 | 6150.24 | 1337.62
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 7487.86 | 602.3 | 6752.54 | 735.32
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 7487.86 | 83.82 | 6836.36 | 651.5
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 7487.86 | 651.5 | 7487.86 | -6.8212e-13
[5 empty] | 7487.86 |  | 7487.86 | -6.8212e-13
|  |  | Totals: | 7487.86 |  | 7487.86 |  | 0
Note on E9: Huggins, Joni [DAS]: From: Kleene, Jennifer <jennifer.kleene@iowa.gov> Date: Tue, Nov 12, 2024 at 7:48 AM Subject: Re: October PM Time Posting Shortages To: Huggins, Joni <joni.huggins@iowa.gov> Sorry about that! Please increase the DAS Cost budgets as follows: DA24 9377.00 Increase budget by $4,400.00 DA24 9378.00 Increase budget by $298.43 DA25 9245.01 Create a budget for $14,370.00 MM23 9279.20 Increase budget by $2200.00 Please Close DA25 Project 9425.01 HHS STS North Buildings HazMat Survey $Joni Kleene, Jennifer Mon, Aug 4, 3:37 PM (15 hours ago) to me, Geoff, Christopher All invoices have been paid and all DAS costs have posted, so please close DA25 project 9425.01 and return the remaining $17,315.12 to HHS. Regards, Jennifer Jennifer Kleene

## #9425.01 Misc
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525132909 | 2025-05-09 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1550 | 200 | 200
200
200
200
200
200
200
200
200
200
200
200
|  |  |  | Totals: |  | 200

## #9425.01 ATC Group
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  | Major Program 4E02
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA25-9260 |  |  | MA00520262D
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525320906 | 2024-11-15 | PO Procore | 22395 | 22395 |  |  | 22395
PRC 3352532PA0906 | 2025-04-15 | Inv. 2633531 |  | 22395 | 5737.5 | 5737.5 | 16657.5
PRC 3352532PB0906 | 2025-06-30 | Inv. 9425.01-02 - Final | -10068.75 | 12326.25 | 6588.75 | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  |  |  | 12326.25 |  | 12326.25 | 0
|  | Totals: | 12326.25 |  | 12326.25 |  | 0 | FINAL
|  | Line 2 Asbestos Samples 5@$10 ea | 0 |  |  |  | 0
|  | Line 3 Lead Samples 5@$15ea | 0 |  |  |  | 0
|  | Line 5 Admin Hourly 11@$45ea | 315 |  | 315 |  | 0
|  | Line 7 Field Tech $132@75ea | 4743.75 |  | 4743.75 |  | 0
|  | Line 8 Hygienist Hourly 125@$95 | 7267.5 |  | 7267.5 |  | 0
|  | Total: | 12326.25 |  | 12326.25 |  | 0

## #9425.01 JamcoAbatement Service
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  | Major Program 4E02
Jamco Abatement Services |  |  | Vendor: 00003226704
Acct. Codes-0506-335-DA25-9255 |  |  | RFB 942501-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33525058901 | 2025-02-27 | PO Procore | 73730 | 73730 |  |  | 73730
PRC 3352505PA8901 | 2025-06-05 | Inv. 9425.01-01 |  | 73730 | 69093.5 | 69093.5 | 4636.5 | 3636.5
PRC 3352505PB8901 | 2025-06-10 | Inv. 9425.01-02 |  | 73730 | 950 | 70043.5 | 3686.5 | 3686.5
PRC 3352505PC8901 | 2025-06-23 | Inv. 9425.01-03 - Retainage |  | 73730 | 3686.5 | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  |  |  | 73730 |  | 73730 | 0
|  | Totals: | 73730 |  | 73730 |  | 0 | FINAL

## #9425.01 McGough Constructi (2)
HHS STS North Buildings HazMat Survey
Project # 9425.01
Program code 942501 |  |  | Major Program 4E02
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525076903 | 2025-03-17 | PO Procore | 17905.44 | 17905.44 |  |  | 17905.44
PRC 3352507PA6903 | 2025-04-15 | Inv. 101368.001-CA01 |  | 17905.44 | 2882.11 | 2882.11 | 15023.33
PRC 3352507PB6903 | 2005-05-09 | Inv. 101368.001-CA02 |  | 17905.44 | 10359.39 | 13241.5 | 4663.94
PO 33525076903 | 2025-05-12 | CO #1(No Cost CO) | 0 | 17905.44 |  | 13241.5 | 4663.94
PRC 3352507PC6903 | 2025-06-12 | Inv. 101368.001-CA03 |  | 17905.44 | 3719.21 | 16960.71 | 944.73
PRC 3352507PD6903 | 2025-07-14 | Inv. 101368.001-CA04 Final | -98.9 | 17806.54 | 845.83 | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  |  |  | 17806.54 |  | 17806.54 | -1.3927e-12
|  | Totals: | 17806.54 |  | 17806.54 |  | 0 | FINAL
|  | CM Services | 16446.54 |  | 16446.54 |  | 0
|  | Reimbursables | 1360 |  | 1360 |  | 0
|  | CO #1 Moving allowance from CM Services to Reimbursable | 0 |  | 0 |  | 0
|  | Total: | 17806.54 |  | 17806.54 |  | 0

## RECAP #9429.00
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
| Program code 942900 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA25
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 33018000
| OPN Architects |  | 45000 | 18000 | 27000
| PM TIME |  | 400000 | 154793.1 | 245206.9
| Misc. |  | 100809.23 | 100809.23 | 0
| OPN Architects (2) |  | 1680303 | 1679303 | 1000
| Weitz Company |  | 214910 | 208670 | 6240
C | Terracon Consultants |  | 18152.75 | 18152.75 | 0
C | Terracon Consultants (2) |  | 6046.25 | 6046.25 | 0
| Jaeager Corporation |  | 2900 | 0 | 2900
| SystemWorks |  | 88040 | 5670 | 82370
| OPN Architects (3) |  | 774000 | 53406 | 720594
| Core Construction Services |  | 890000 | 7237.17 | 882762.83
| Core Construction Services(2) |  | 1386500 | 10961 | 1375539
| Seedorff Masonry |  | 529700 | 0 | 529700
| US Erectors. Inc |  | 1095100 | 0 | 1095100
| Breiholz Conatruction |  | 6227600 | 58959.51 | 6168640.49
| Bailey Roofing |  | 307100 | 0 | 307100
| Elite Glass and Metal |  | 775000 | 0 | 775000
| Van Maanen Electric |  | 2684856.67 | 0 | 2684856.67
| SGH Concepts |  | 606723 | 64023.88 | 542699.12
| Veit & Company |  | 1280500 | 0 | 1280500
| Grazzini Brothers |  | 403200 | 0 | 403200
| JF Ahern Company |  | 177596 | 6020.79 | 171575.21
| Andersen Construction |  | 7581200 | 0 | 7581200
| Conference Technologies |  | 140893.93 | 0 | 140893.93
| Weitz Company (2) |  | 3029827 | 98888.11 | 2930938.89
| Terracon Consultants (3) |  | 40885 | 0 | 40885
| All Makes - Furniture - Phase 1 |  | 209612.28 | 0 | 209612.28
| Total Project Cost | 33018000 | 30696455.11 | 2490940.79 | 28205514.32 | 2321544.89

## #9429.00 Funds Recv'd
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - James T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 072224KCL01SME | 2024-07-29 | 5000000 | 5000000
|  |  | MOU Amendment #1- Non RIIF Funds | IET 400KDH121324001 | 2024-12-13 | 50000 | 50000
|  |  | Returning FY25 funds to Agency | IET 33525224919 | 2025-08-12 | -3735949.31 | -3735949.31
|  |  | Received FY26 funds from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 3735949.31 | 3735949.31
|  |  | MOU Amendment #2 | IET 400KDH121625001 | 2025-12-16 | 28000000 | 28000000
|  |  | Returning funds to HHS from Amend #1-NON RIIF Funds | IET 33526051900 | 2026-02-20 | -32000 | -32000
| Total Requested | 0 | Total Transferred |  |  | 33018000 | 33018000

## #9429.00 OPN Architects
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA25-9260 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525256900 | 2024-09-12 | PO Procore | 45000 | 45000 |  |  | 45000
PRC 3352525PA6900 | 2024-12-04 | Inv. 23825001-1A |  | 45000 | 4680 | 4680 | 40320
PRC 3352525PB6900 | 2024-12-20 | Inv. 23825001-2A |  | 45000 | 40320 | 45000 | 0 | FY25
PO 33526256900 | 2025-09-18 | Open PO in FY26 with returned funds-CR 00526266101 |  | 45000 | -27000 | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  |  |  | 45000 |  | 18000 | 27000
|  | Totals: | 45000 |  | 18000 |  | 27000

## #9429.00 PM TIME
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - James T. |  |  |  | eDAS E2DZ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 400000 | 400000 |  |  | 400000
IET DAS202502115300001 | 2024-09-09 | 2507 | Finance Support for August 1-31,2024 |  | 400000 | 1261.11 | 1261.11 | 398738.89
IET DAS202502115300001 | 2024-09-09 | 9500 | DAS Services for August 1-31, 2024 |  | 400000 | 6418.5 | 7679.61 | 392320.39
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 400000 | 385.99 | 8065.6 | 391934.4
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 400000 | 3436.7 | 11502.3 | 388497.7
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 400000 | 587.52 | 12089.82 | 387910.18
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 400000 | 3922 | 16011.82 | 383988.18
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 400000 | -2234.62 | 13777.2 | 386222.8
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 400000 | 3820.6 | 17597.8 | 382402.2
IET DAS202506115300001 | 2025-01-09 | 9500 | Finance Support for December 1-31, 2024 |  | 400000 | 2688.4 | 20286.2 | 379713.8
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 400000 | 5992.8 | 26279 | 373721
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 400000 | 6164.4 | 32443.4 | 367556.6
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 400000 | 6286.8 | 38730.2 | 361269.8
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 400000 | 4941.7 | 43671.9 | 356328.1
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 400000 | 5610 | 49281.9 | 350718.1
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 400000 | 5777.8 | 55059.7 | 344940.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 400000 | 6512.3 | 61572 | 338428
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 400000 | 8582.5 | 70154.5 | 329845.5
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 400000 | 13036.4 | 83190.9 | 316809.1
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 400000 | 12270.3 | 95461.2 | 304538.8
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 400000 | 9752.4 | 105213.6 | 294786.4
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 400000 | 12085.8 | 117299.4 | 282700.6
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 400000 | 11517.7 | 128817.1 | 271182.9
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 400000 | 11774.7 | 140591.8 | 259408.2
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 400000 | 14201.3 | 154793.1 | 245206.9
[5 empty] | 400000 |  | 154793.1 | 245206.9
[5 empty] | 400000 |  | 154793.1 | 245206.9
[5 empty] | 400000 |  | 154793.1 | 245206.9
|  |  | Totals: | 400000 |  | 154793.1 |  | 245206.9
Note on E9: Huggins, Joni [DAS]: Trower, James 2:57 PM (0 minutes ago) to me Joni - Please increase PM Time by $300,000 for project 9429.00 (DA25). Thanks, James

## #9429.00 Misc
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T. |  |  |  | Shipping Code: S24
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202504115300001 | 2024-11-07 | 2507 |  | Space Planning Services October 01-31,2024 | Inv. DAS2025041153 | 95 | 95
IET DAS202505115300001 | 2024-12-06 | 2507 |  | Fire Watch November 01-30, 2024 | Inv. DAS2025051153 | 286.32 | 381.32
PRC 33525024902 | 2025-01-24 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV045137 | 286.95 | 668.27
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Fire Watch February 01-28, 2025 | Inv. DAS2025081153 | 711.81 | 1380.08
IET DAS202508115300001 | 2025-03-07 | 2507 |  | Space Planning Services February 01-28, 2025 | Inv. DAS2025081153 | 47.5 | 1427.58
IET DAS202509115300001 | 2025-04-09 | 2507 |  | Space Planning Services March1-31, 2025 | Inv. DAS2025091153 | 403.75 | 1831.33
IET DAS202510115300001 | 2025-05-09 | 2507 |  | Space Planning Services April 01-30, 2025 | Inv. DAS2025101153 | 308.75 | 2140.08
IET DAS202511115300001 | 2025-06-09 | 2507 |  | Space Planning May 01-31, 2025 | Inv. DAS2025111153 | 546.25 | 2686.33
GAX 33525175907 | 2025-06-24 | 9500 | CNST | GPRS V#(00003035582) | Inv. 892180 | 1100 | 3786.33
IET DAS202512115300001 | 2025-07-10 | 2507 |  | Space Planning Services June 1-30,2025 | Inv. DAS2025121153 | 3277.5 | 7063.83
IET DAS202513115300001 | 2025-07-22 | 2507 |  | Electrical Service June 1-30, 2025 | Inv. DAS2025131153 | 829.85 | 7893.68
IET 33525202407 | 2025-07-16 | 2398 | CNST | ICN - General Servs & Equip | Inv. 724944-9429.00 | 585 | 8478.68
IET DAS202601115300001 | 2025-08-07 | 2507 |  | Space Planning Services July 1-31,2025 | Inv. DAS2026011153 | 308.75 | 8787.43
GAX 33526260900 | 2025-09-17 | 9500 | CNST | GPRS V#(00003035582) | Inv. 917181 | 625 | 9412.43
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Space Planning Services August 1-31,2025 | Inv. DAS2026021153 | 332.5 | 9744.93
PRC 33526273906 | 2025-09-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV052644 | 423 | 10167.93
IET DAS202603115300001 | 2025-10-07 | 2507 |  | Space Planning 09/01-09/30/25 | Inv. DAS2026031153 | 498.75 | 10666.68
IET DAS202604115300001 | 2025-11-07 | 2507 |  | Space Planning 10/01-10/31/25 | Inv. DAS2026041153 | 1187.5 | 11854.18
PRC 33526363906 | 2025-12-29 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2378 | 4291.8 | 16145.98
IET DAS202606115300001 | 2026-01-08 | 2507 |  | Space Planning Services December 1-31,2025 | Inv. DAS2026061153 | 878.75 | 17024.73
IET 33526020907 | 2026-01-20 | 9255 | BRUM | ICN - General Servs & Equip | Inv. 738507 - 9429.00 | 2301 | 19325.73
IET DAS202608115300001 | 2026-03-09 | 2507 |  | Space Planning Services February 01-28, 2026 | Inv. DAS2026081153 | 1805 | 21130.73
PRC 33526069905 | 2026-03-10 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 881921 | 78966 | 100096.73
IET DAS202609115300001 | 2026-04-06 | 2507 |  | Space Planning Services: March 01-31, 2026 | Inv. DAS2026091153 | 712.5 | 100809.23
100809.23
100809.23
|  |  |  | Totals: |  | 100809.23

## #9429.00 OPN Architects (2)
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
OPN Architects (2) |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA25-9260 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525309904 | 2024-11-04 | PO Procore | 1624300 | 1624300 |  |  | 1624300
PRC 3352530PA9904 | 2024-12-03 | Inv. 23825001-1 |  | 1624300 | 34869.78 | 34869.78 | 1589430.22
PRC 3352530PB9904 | 2025-01-21 | Inv. 23825001-2 |  | 1624300 | 76873.59 | 111743.37 | 1512556.63
PRC 3352530PC9904 | 2025-03-05 | Inv. 23825001-3A |  | 1624300 | 139549.62 | 251292.99 | 1373007.01
PRC 3352530PD9904 | 2025-04-02 | Inv. 23825001-4 |  | 1624300 | 235581.5 | 486874.49 | 1137425.51
PO 33525309904 | 2025-05-02 | CO #1 | 31620 | 1655920 |  | 486874.49 | 1169045.51
PRC 3352530PE9904 | 2025-06-03 | Inv. 23825001-5 |  | 1655920 | 262465.65 | 749340.14 | 906579.86
PRC 3352530PF9904 | 2025-07-09 | Inv. 23825001-9 |  | 1655920 | 168219.98 | 917560.12 | 738359.88
PRC 3352530PH9904 | 2025-07-09 | Inv. 23825001-7 |  | 1655920 | 174588.94 | 1092149.06 | 563770.94 | FY25
PO 33526309904 | 2025-08-21 | Roll to FY26 | 0 | 1655920 |  | 1092149.06 | 563770.94
PRC 3352630PI9904 | 2025-09-18 | Inv. 23825001-8 |  | 1655920 | 194627.19 | 1286776.25 | 369143.75
PRC 3352630PJ9904 | 2025-09-19 | Inv. 23825001-10 |  | 1655920 | 71457.81 | 1358234.06 | 297685.94
PO 33526309904 | 2025-09-29 | CO #2 | 24383 | 1680303 |  | 1358234.06 | 322068.94
PRC 3352630PK9904 | 2025-10-08 | Inv. 23825001-11 |  | 1680303 | 116406.9 | 1474640.96 | 205662.04
PRC 3352630PL9904 | 2025-11-12 | Inv. 23825001-12 |  | 1680303 | 103439.5 | 1578080.46 | 102222.54
PRC 3352630PM9904 | 2025-12-22 | Inv. 23825001-14 |  | 1680303 | 34308.97 | 1612389.43 | 67913.57
PRC 3352630PN9904 | 2026-01-12 | Inv. 23825001-13 |  | 1680303 | 66913.57 | 1679303 | 1000
|  |  |  | 1680303 |  | 1679303 | 1000
|  |  |  | 1680303 |  | 1679303 | 1000
|  |  |  | 1680303 |  | 1679303 | 1000
|  | Totals: | 1680303 |  | 1679303 |  | 1000
|  | Site Survey | 13800 |  | 13800 |  | 0
|  | Schematic Design | 292500 |  | 292500 |  | 0
|  | Design Development | 561000 |  | 561000 |  | 0
|  | Construction Documents | 707000 |  | 707000 |  | 0
|  | Bidding | 50000 |  | 49000 |  | 1000
|  | CO #1 | 31620 |  | 31620 |  | 0
|  | CO #2 | 24383 |  | 24383 |  | 0
|  | Total: | 1680303 |  | 1679303 |  | 1000
Payment G was skipped

## #9429.00 Weitz Company
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Weitz Company |  |  | Vendor: 00003223486
Acct. Codes-0506-335-DA25-9255 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525313900 | 2024-11-08 | PO Procore | 211990 | 211990 |  |  | 211990
PRC 3352531PA3900 | 2025-03-13 | Inv. PC 01 |  | 211990 | 41180 | 41180 | 170810
PRC 3352531PB3900 | 2025-04-08 | Inv. PC 02 |  | 211990 | 9800 | 50980 | 161010
PRC 3352531PC3900 | 2025-05-12 | Inv. PC 03 |  | 211990 | 6470 | 57450 | 154540
PRC 3352531PD3900 | 2025-06-10 | Inv. PC 04 |  | 211990 | 27840 | 85290 | 126700
PRC 3352531PE3900 | 2025-07-09 | Inv. PC 05 |  | 211990 | 14840 | 100130 | 111860 | FY25
PO 33526313900 | 2025-08-21 | Roll to FY26 | 0 | 211990 |  | 100130 | 111860
PRC 3352631PF3900 | 2025-09-10 | Inv. PC 06 |  | 211990 | 8960 | 109090 | 102900
PRC 3352631PG3900 | 2025-09-15 | Inv. PC 07 |  | 211990 | 12870 | 121960 | 90030
PRC 3352631PH3900 | 2025-09-29 | Inv. PC 08 |  | 211990 | 16620 | 138580 | 73410
PRC 3352631PI3900 | 2025-12-08 | Inv. PC 09 |  | 211990 | 14680 | 153260 | 58730
PRC 3352631PJ3900 | 2025-12-18 | Inv. PC 10 |  | 211990 | 33680 | 186940 | 25050
PRC 3352631PK3900 | 2026-01-20 | Inv. PC 11 |  | 211990 | 18340 | 205280 | 6710
PRC 3352631PL3900 | 2026-03-09 | Inv. PC 12 |  | 211990 | 3390 | 208670 | 3320
PO 33526313900 | 2026-04-28 | CO #1 | 2920 | 214910 |  | 208670 | 6240
|  |  |  | 214910 |  | 208670 | 6240
|  | Totals: | 214910 |  | 208670 |  | 6240
|  | CM Services | 208740 |  | 208670 |  | 70
|  | Reimbursables | 3250 |  |  |  | 3250
|  | CO #1 | 2920 |  |  |  | 2920
|  | Total: | 214910 |  | 208670 |  | 6240

## #9429.00 Terracon Consultants
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0506-335-DA25-9255 |  |  | MA25049
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525119900 | 2025-04-29 | DO Procore | 11089.5 | 11089.5 |  |  | 11089.5
PRC 3352511PA9900 | 2025-07-15 | Inv. TP13219 |  | 11089.5 | 7187 | 7187 | 3902.5 | FY25
PO 33526119900 | 2025-08-21 | Roll to FY26 | 0 | 11089.5 |  | 7187 | 3902.5
PO 33526119900 | 2025-10-03 | CO #1 | 7065 | 18154.5 |  | 7187 | 10967.5
PRC 3352611PB9900 | 2025-10-03 | Inv. TP59050 |  | 18154.5 | 5594.25 | 12781.25 | 5373.25
PRC 3352611PC9900 | 2026-01-02 | Inv. TP28535 |  | 18154.5 | 3432.5 | 16213.75 | 1940.75
PRC 3352611PD9900 | 2026-01-02 | Inv. TP73965 |  | 18154.5 | 291.5 | 16505.25 | 1649.25
PRC 3352611PE9900 | 2026-01-02 | Inv. TP44091 |  | 18154.5 | 1647.5 | 18152.75 | 1.75
PO 33526119900 | 2026-01-05 | Closing PO Per PM | -1.75 | 18152.75 |  | 18152.75 | 0
|  |  |  | 18152.75 |  | 18152.75 | 0
|  |  |  | 18152.75 |  | 18152.75 | 0
|  |  |  | 18152.75 |  | 18152.75 | 0
|  |  |  | 18152.75 |  | 18152.75 | 0
|  | Totals: | 18152.75 |  | 18152.75 |  | 0
Note on C17: Huggins, Joni [DAS]: e: HHS ANK IMEO Expansion and Renovation: Action Required for Subcontractor Invoice #5: Terracon Consultants, Inc. $Joni Trower, James 9:31 AM (18 minutes ago) to me Finance - Please close the contract. James On Fri, Jan 2, 2026 at 2:08 PM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: Hi James Is this invoice closing out PO 33526119900? It leaves a remainder of $1.75 Thank you for your time ~Joni

## #9429.00 Terracon Consultan (2)
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Terracon Consultants (2) |  |  | Vendor: 00002116513
Acct. Codes-0506-335-DA25-9255 |  |  | MA25049
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33525119905 | 2025-04-29 | DO Procore | 8595 | 8595 |  |  | 8595
PRC 3352511PA9905 | 2025-07-15 | Inv. TP16792 |  | 8595 | 6046.25 | 6046.25 | 2548.75 | FY25
PO 33526119905 | 2025-08-21 | Roll to FY26 | 0 | 8595 |  | 6046.25 | 2548.75
PO 33526119905 | 2026-04-02 | Closing Per PM Email | -2548.75 | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  |  |  | 6046.25 |  | 6046.25 | 0
|  | Totals: | 6046.25 |  | 6046.25 |  | 0
Note on C12: Huggins, Joni [DAS]: Re: 9429.00 - HHS ANK IMEO Expansion and Renovation - Close contract $Joni Trower, James 9:01 AM (6 minutes ago) to me Terracon; they are on master agreement. Thanks, James On Thu, Apr 2, 2026 at 7:25 AM Finance Payables Infrastructure, DAS <dasfinanceinfrastructure@iowa.gov> wrote: James, What vendor is this for? ~Joni On Wed, Apr 1, 2026 at 9:51 AM Trower, James <james.trower@iowa.gov> wrote: Finance - Contract #DO-9429.00-006: Invoice #1 is final; please close. Thanks, James Trower, Licensed Architect, LEED AP

## #9429.00 Jaeger Corporation
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Jaeger Corporation |  |  | Vendor: 00003175664
Acct. Codes-0506-335-DA25-9255 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526253400 | 2025-09-10 | PO Procore | 2900 | 2900 |  |  | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  |  |  | 2900 |  | 0 | 2900
|  | Totals: | 2900 |  | 0 |  | 2900

## #9429.00 SystemWorks
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0506-335-DA25-9255 |  |  | MA 21396C
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526272905 | 2025-09-29 | PO Procore | 88040 | 88040 |  |  | 88040
PRC 3352627PA2905 | 2025-12-18 | Inv. 12596 |  | 88040 | 5670 | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  |  |  | 88040 |  | 5670 | 82370
|  | Totals: | 88040 |  | 5670 |  | 82370
|  | Professional Personnel | 82460 |  | 5670 |  | 76790
|  | Administration | 2520 |  |  |  | 2520
|  | Software | 3060 |  |  |  | 3060
|  | Total: | 88040 |  | 5670 |  | 82370

## #9429.00 OPN Architects (3)
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
OPN Architects (3) |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA25-9260 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526040920 | 2026-02-09 | PO Procore | 774000 | 774000 |  |  | 774000
PRC 3352604PA0920 | 2026-03-10 | Inv. 23825001-15 |  | 774000 | 26683.65 | 26683.65 | 747316.35
PRC 3352604PB0920 | 2026-04-13 | Inv. 23825001-2B |  | 774000 | 26722.35 | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  |  |  | 774000 |  | 53406 | 720594
|  | Totals: | 774000 |  | 53406 |  | 720594
|  | Construction Admin Phase 1 | 524343 |  | 53406 |  | 470937
|  | Construction Admin Phase 2 | 204640 |  |  |  | 204640
|  | Construction Admin Phase 3 | 45017 |  |  |  | 45017
|  | Total: | 774000 |  | 53406 |  | 720594
Vendor previously used Inv. 23825001-X in this project, please add B

## #9429.00 Core Construction
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Core Construction |  |  | Vendor: 00003201207
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526047903 | 2026-02-16 | PO Procore | 890000 | 890000 |  |  | 890000
PRC 3352604PA7903 | 2026-03-24 | Inv. 9429.00-01 |  | 890000 | 7237.17 | 7237.17 | 882762.83 | 223.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  |  |  | 890000 |  | 7237.17 | 882762.83
|  | Totals: | 890000 |  | 7237.17 |  | 882762.83

## #9429.00 Core Construction (2)
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Core Construction(2) |  |  | Vendor: 00003201207
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526047904 | 2026-02-16 | PO Procore | 1386500 | 1386500 |  |  | 1386500
PRC 3352604PA7904 | 2026-03-24 | Inv. 9429.00-001 |  | 1386500 | 10961 | 10961 | 1375539 | 339
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  |  |  | 1386500 |  | 10961 | 1375539
|  | Totals: | 1386500 |  | 10961 |  | 1375539
Inv. 92429.00- X was previously used in the project, use 9429.00-00X

## #9429.00 Seedorff Masonry
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Seedorff Masonry |  |  | Vendor: 00002108955
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047905 | 2026-02-16 | PO Procore | 529700 | 529700 |  |  | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  |  |  | 529700 |  | 0 | 529700
|  | Totals: | 529700 |  | 0 |  | 529700

## #9429.00 US Erectors
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
US Erectors, Inc |  |  | Vendor: 00002137555
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047906 | 2026-02-16 | PO Procore | 1095100 | 1095100 |  |  | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  |  |  | 1095100 |  | 0 | 1095100
|  | Totals: | 1095100 |  | 0 |  | 1095100

## #9429.00 Breiholz Construction
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Breiholz Construction |  |  | Vendor: 00002107863
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526047913 | 2026-02-16 | PO Procore | 6227600 | 6227600 |  |  | 6227600
PRC 3352604PA7913 | 2026-03-24 | Inv. 9429.00-01 |  | 6227600 | 58959.51 | 58959.51 | 6168640.49 | 1823.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  |  |  | 6227600 |  | 58959.51 | 6168640.49
|  | Totals: | 6227600 |  | 58959.51 |  | 6168640.49

## #9429.00 Bailey Roofing
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Bailey Roofing |  |  | Vendor: 00002118286
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047914 | 2026-02-16 | PO Procore | 307100 | 307100 |  |  | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  |  |  | 307100 |  | 0 | 307100
|  | Totals: | 307100 |  | 0 |  | 307100

## #9429.00 Elite Glass and Metal
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Elite Glass and Metal |  |  | Vendor: 00003078283
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047915 | 2026-02-16 | PO Procore | 775000 | 775000 |  |  | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  |  |  | 775000 |  | 0 | 775000
|  | Totals: | 775000 |  | 0 |  | 775000

## #9429.00 VanMaanen Electric
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Van Maanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047911 | 2026-02-16 | PO Procore | 2683098 | 2683098 |  |  | 2683098
PO 33526047911 | 2026-04-17 | CO #1 | 1758.67 | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  |  |  | 2684856.67 |  | 0 | 2684856.67
|  | Totals: | 2684856.67 |  | 0 |  | 2684856.67

## #9429.00 SGH Concepts
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
SGH Concepts |  |  | Vendor: 00003114014
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526047902 | 2026-02-16 | PO Procore | 606723 | 606723 |  |  | 606723
PRC 3352604PA7902 | 2026-04-20 | Inv. 011461 |  | 606723 | 64023.88 | 64023.88 | 542699.12 | 1980.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  |  |  | 606723 |  | 64023.88 | 542699.12
|  | Totals: | 606723 |  | 64023.88 |  | 542699.12

## #9429.00 Veit & Company
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Veit Company |  |  | Vendor: 00003007320
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047901 | 2026-02-16 | PO Procore | 1280500 | 1280500 |  |  | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  |  |  | 1280500 |  | 0 | 1280500
|  | Totals: | 1280500 |  | 0 |  | 1280500

## #9429.00 Grazzini Brothers
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Grazzini Brothers |  |  | Vendor: 00003235048
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526048901 | 2026-02-18 | PO Procore | 403200 | 403200 |  |  | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  |  |  | 403200 |  | 0 | 403200
|  | Totals: | 403200 |  | 0 |  | 403200

## #9429.00 JF Ahern
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
JF Ahern Company |  |  | Vendor: 00002102310 |  | 00002102311
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526049902 | 2026-02-18 | PO Procore | 177596 | 177596 |  |  | 177596
PO 33526049902A | 2026-03-30 | Changing Vendor Code |  | 177596 |  | 0 | 177596
PRC 3352604PA9902A | 2026-03-30 | Inv. 9779-001 |  | 177596 | 6020.79 | 6020.79 | 171575.21 | 186.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  |  |  | 177596 |  | 6020.79 | 171575.21
|  | Totals: | 177596 |  | 6020.79 |  | 171575.21
3% Retainage

## #9429.00 Andersen Construction
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Andersen Construction |  |  | Vendor: 00003235049
Acct. Codes-0506-335-DA25-9255 |  |  | RFB942900-01
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526049904 | 2026-02-18 | PO Procore | 7581200 | 7581200 |  |  | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  |  |  | 7581200 |  | 0 | 7581200
|  | Totals: | 7581200 |  | 0 |  | 7581200

## #9429.00 Conference Technologie
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Conference Technologies |  |  | Vendor: 00002133110
Acct. Codes-0506-335-DA25-9255 |  |  | MA22036D
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526063912 | 2026-03-04 | DO Procore | 140893.93 | 140893.93 |  |  | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  |  |  | 140893.93 |  | 0 | 140893.93
|  | Totals: | 140893.93 |  | 0 |  | 140893.93

## #9429.00 Weitz Company (2)
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Weitz Company (2) |  |  | Vendor: 00003223486
Acct. Codes-0506-335-DA25-9255 |  |  | RFP935200-01
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526069907 | 2026-03-10 | PO Procore | 3029827 | 3029827 |  |  | 3029827
PRC 3352606PA9907 | 2026-04-14 | Inv. 9429.00-CA-01 |  | 3029827 | 98888.11 | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  |  |  | 3029827 |  | 98888.11 | 2930938.89
|  | Totals: | 3029827 |  | 98888.11 |  | 2930938.89
|  | Staffing | 1744157 |  | 89945.68 |  | 1654211.32
|  | General Conditions | 163280 |  | 2075.96 |  | 161204.04
|  | General Requirements | 333397 |  | 3951.47 |  | 329445.53
|  | Fee - 3.25% | 788993 |  | 2915 |  | 786078
|  | Total: | 3029827 |  | 98888.11 |  | 2930938.89

## #9429.00 Terracon Consultants 3
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
Terracon Consultants (3) |  |  | Vendor: 00002116513
Acct. Codes-0506-335-DA25-9255 |  |  | MA25049
Project Manager - James T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526090907 | 2026-03-31 | PO Procore | 40885 | 40885 |  |  | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  |  |  | 40885 |  | 0 | 40885
|  | Totals: | 40885 |  | 0 |  | 40885
|  | Line #1 Concrete Testing | 4800 |  |  |  | 4800
|  | Line #2 Soil & Land Management | 2110 |  |  |  | 2110
|  | Line #5 Labor-Project Mngmt | 3250 |  |  |  | 3250
|  | Line #6 Labor-Testing Technician | 9310 |  |  |  | 9310
|  | Lin #7 Travel | 940 |  |  |  | 940
|  | Line #9 Specialized Labor | 20475 |  |  |  | 20475
|  | Total: | 40885 |  | 0 |  | 40885

## #9429.00 All Makes-Furniture
ANK HHS IMEO Expansion and Renovation
Project # 9429.00
Program code 942900 |  |  | Major Program 4E02
All Makes - Furniture Phase 1 |  |  | Vendor: 00002110818
Acct. Codes-0506-335-DA25-9255 |  |  | MA23148
Project Manager - James T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526105913 | 2026-04-14 | PO Procore | 209612.28 | 209612.28 |  |  | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  |  |  | 209612.28 |  | 0 | 209612.28
|  | Totals: | 209612.28 |  | 0 |  | 209612.28

## RECAP #9433.00
HHS WRC Cottage Siding Replacement
Project # 9433.00
| Program code 943300 |  |  | Major Program 4E02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 192927.83
C | Story Construction |  | 14532.1 | 14532.1 | 0
C | PM TIME |  | 9847.35 | 9847.35 | 0
C | Misc. |  | 1473.85 | 1473.85 | 0
C | Genesis Architectural |  | 13800 | 13800 | 0
C | Falke Construction |  | 123787.38 | 123787.38 | 0
C | Story Construction (2) |  | 29487.15 | 29487.15 | 0
| Total Project Cost | 192927.83 | 192927.83 | 192927.83 | 0 | 0
Closed 03/16/26

## #9433.00 Funds Recv'd
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  | Major Program 4E02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET MOUPROJ943300 | 2024-09-25 | 40000 | 40000
|  |  | MOU Amend #1 | IET MOUCOTTAGESIDINGAMD1 | 2025-05-02 | 140000 | 140000
|  |  | Returning FY25 funds to Agency | IET 33525224920 | 2025-08-12 | -143156.43 | -143156.43
|  |  | Received FY26 funds from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 143156.43 | 143156.43
|  |  | MOU Amend #2 | IET DASMOU090925 | 2025-09-15 | 30000 | 30000
|  |  | Returning funds to Agency - Project Closing | IET 33526075900 | 2026-03-16 | -17072.17 | -17072.17
| Total Requested | 0 | Total Transferred |  |  | 192927.83 | 192927.83

## #9433.00 Story Construction
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525270903 | 2024-09-26 | PO Procore | 14541.54 | 14541.54 |  |  | 14541.54
PRC 3352527PA0903 | 2024-11-18 | Inv. 34614 |  | 14541.54 | 1998.8 | 1998.8 | 12542.74
PRC 3352527PB0903 | 2024-12-16 | Inv. 34663 |  | 14541.54 | 1238.21 | 3237.01 | 11304.53
PRC 3352527PC0903 | 2024-01-15 | Inv. 34702 |  | 14541.54 | 1219.22 | 4456.23 | 10085.31
PRC 3352527PD0903 | 2025-02-17 | Inv. 34734 |  | 14541.54 | 1114.87 | 5571.1 | 8970.44
PRC 3352527PE0903 | 2025-03-21 | Inv. 34770 |  | 14541.54 | 6315.56 | 11886.66 | 2654.88
PRC 3352527PF0903 | 2025-04-15 | Inv. 34803 FINAL | -9.44 | 14532.1 | 2645.44 | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  |  |  | 14532.1 |  | 14532.1 | 1.8741e-12
|  | Totals: | 14532.1 |  | 14532.1 |  | 0 | FINAL
|  | CM Services | 14473.1 |  | 14473.1 |  | 0
|  | Reimbursables | 59 |  | 59 |  | 0
|  | Total: | 14532.1 |  | 14532.1 |  | 0

## #9433.00 PM TIME
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS E2FQ
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 9847.35 | 9847.35 |  |  | 9847.35
IET DAS202503115300001 | 2024-10-09 | 2507 | Finance Support for September 1-30,2024 |  | 9847.35 | 118.33 | 118.33 | 9729.02
IET DAS202503115300001 | 2024-10-09 | 9500 | DAS Services for September 1-30,2024 |  | 9847.35 | 1051.4 | 1169.73 | 8677.62
IET DAS202504115300001 | 2024-11-07 | 2507 | Finance Support for October 1-31,2024 |  | 9847.35 | 118.18 | 1287.91 | 8559.44
IET DAS202504115300001 | 2024-11-07 | 9500 | DAS Services for October 1-31,2024 |  | 9847.35 | 791.8 | 2079.71 | 7767.64
IET DAS202505115300001 | 2024-12-09 | 2507 | Finance Support for November 1-30 2024 |  | 9847.35 | 28.39 | 2108.1 | 7739.25
IET DAS202505115300001 | 2024-12-09 | 9500 | DAS Support for November 1-30 2024 |  | 9847.35 | 187.4 | 2295.5 | 7551.85
IET DAS202506115300001 | 2025-01-09 | 2507 | Finance Support for December 1-31, 2024 |  | 9847.35 | 50.21 | 2345.71 | 7501.64
IET DAS202506115300001 | 2025-01-09 | 9500 | DAS Support for December 1-31, 2024 |  | 9847.35 | 500.2 | 2845.91 | 7001.44
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 9847.35 | 19.41 | 2865.32 | 6982.03
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 9847.35 | 208.8 | 3074.12 | 6773.23
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 9847.35 | 125.26 | 3199.38 | 6647.97
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 9847.35 | 541.3 | 3740.68 | 6106.67
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 9847.35 | 80.27 | 3820.95 | 6026.4
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 9847.35 | 575.2 | 4396.15 | 5451.2
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 9847.35 | 70.02 | 4466.17 | 5381.18
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 9847.35 | 480.8 | 4946.97 | 4900.38
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 9847.35 | 94.84 | 5041.81 | 4805.54
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 9847.35 | 741.4 | 5783.21 | 4064.14
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 9847.35 | 10.27 | 5793.48 | 4053.87
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 9847.35 | 81.8 | 5875.28 | 3972.07
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 9847.35 | 17.07 | 5892.35 | 3955
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 9847.35 | 189.1 | 6081.45 | 3765.9
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 9847.35 | 56.82 | 6138.27 | 3709.08
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 9847.35 | 434.6 | 6572.87 | 3274.48
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 9847.35 | 75.62 | 6648.49 | 3198.86
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 9847.35 | 387.3 | 7035.79 | 2811.56
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 9847.35 | 99.15 | 7134.94 | 2712.41
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 9847.35 | 982.3 | 8117.24 | 1730.11
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 9847.35 | 44.83 | 8162.07 | 1685.28
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 9847.35 | 288.7 | 8450.77 | 1396.58
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 9847.35 | 34.51 | 8485.28 | 1362.07
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 9847.35 | 389.3 | 8874.58 | 972.77
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 9847.35 | 21.39 | 8895.97 | 951.38
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 9847.35 | 270.1 | 9166.07 | 681.28
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 9847.35 | 54.18 | 9220.25 | 627.1
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 9847.35 | 627.1 | 9847.35 | -1.3642e-12
[5 empty] | 9847.35 |  | 9847.35 | -1.3642e-12
|  |  | Totals: | 9847.35 |  | 9847.35 |  | 0
Note on E9: Huggins, Joni [DAS]: DAS Cost Budget Increases $Joni Kleene, Jennifer 9:49 AM (2 minutes ago) to me Please increase the DAS Cost budget for MM24 9277.00 by $3,000.00 Please increase the DAS Cost budget for DA26 9480.01 by $2,000.00 Please increase the DAS Cost budget for DA25 9433.00 by $1,000.00 Re: February PM Time Posted Inbox Kleene, Jennifer 3:25 PM (0 minutes ago) to me Please increase the PM Time budgets as follows: Increase 566A 9413.00 by $6,000.00 Increase DA25 9433.00 by $47.35 Increase MM23 9279.20 by $4.62 Regards, Jennifer

## #9433.00 Misc
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33525318912 | 2024-11-13 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2609433 | 1267.5 | 1267.5
PRC 33525118900 | 2025-04-25 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL1634 | 206.35 | 1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
1473.85
|  |  |  | Totals: |  | 1473.85

## #9433.00 Genesis Architectural
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA25-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525270904 | 2024-09-26 | PO Procore | 13800 | 13800 |  |  | 13800
PRC 3352527PA0904 | 2025-01-03 | Inv. 2411-01 |  | 13800 | 7400 | 7400 | 6400
PRC 3352527PB0904 | 2025-02-17 | Inv. 2411-02 |  | 13800 | 630 | 8030 | 5770
PRC 3352527PC0904 | 2025-05-05 | Inv. 2411-03 |  | 13800 | 1270 | 9300 | 4500
PRC 3352527PD0904 | 2025-07-03 | Inv. 2411-04 |  | 13800 | 675 | 9975 | 3825 | FY25
PO 33526270904 | 2025-08-21 | Roll to FY26 | 0 | 13800 |  | 9975 | 3825
PRC 3352627PE0904 | 2025-12-03 | Inv. 2411-05 |  | 13800 | 3150 | 13125 | 675
PRC 3352627PF0904 | 2025-12-16 | Inv. 2411-06 |  | 13800 | 225 | 13350 | 450
PRC 3352627PG0904 | 2026-02-20 | Inv. 2411-07 FINAL |  | 13800 | 450 | 13800 | 0
|  |  |  | 13800 |  | 13800 | 0
|  |  |  | 13800 |  | 13800 | 0
|  |  |  | 13800 |  | 13800 | 0
|  |  |  | 13800 |  | 13800 | 0
|  | Totals: | 13800 |  | 13800 |  | 0 | FINAL
|  | Design Development Docs | 4600 |  | 4600 |  | 0
|  | Construction Docs | 3500 |  | 3500 |  | 0
|  | Bidding Assistance | 1200 |  | 1200 |  | 0
|  | Construction Phase | 4500 |  | 4500 |  | 0
|  | Total: | 13800 |  | 13800 |  | 0

## #9433.00 Falke Construction
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  | Major Program 4E02
Falke Construction |  |  | Vendor: 00003189198
Acct. Codes-0506-335-DA25-9255 |  |  | RFB943300-01
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525125900 | 2025-05-05 | PO Procore | 90781 | 90781 |  |  | 90781 | FY25
PO 33526125900 | 2025-08-21 | Roll to FY26 | 0 | 90781 |  | 0 | 90781
PRC 3352612PA5900 | 2025-09-10 | Inv. 9433.00-001 |  | 90781 | 49039 | 49039 | 41742 | 2581
PRC 3352612PB5900 | 2025-10-17 | Inv. 9433.00-002 |  | 90781 | 17446.98 | 66485.98 | 24295.02 | 3499.27
PRC 3352612PC5900 | 2025-11-12 | Inv. 9433.00-003 |  | 90781 | 17836.96 | 84322.94 | 6458.06 | 4438.06
PO 33526125900 | 2025-12-03 | CO #1 | 33006.38 | 123787.38 |  | 84322.94 | 39464.44
PRC 3352612PD5900 | 2026-01-08 | Inv. 9433.00-004 |  | 123787.38 | 31356.06 | 115679 | 8108.38 | 6088.38
PRC 3352612PE5900 | 2026-02-09 | Inv. 9433.00-005 |  | 123787.38 | 1919 | 117598 | 6189.38 | 6189.38
PRC 3352612PF5900 | 2026-02-17 | Inv. 9433.00-006 Retainage |  | 123787.38 | 6189.38 | 123787.38 | 9.0949e-13
|  |  |  | 123787.38 |  | 123787.38 | 9.0949e-13
|  |  |  | 123787.38 |  | 123787.38 | 9.0949e-13
|  |  |  | 123787.38 |  | 123787.38 | 9.0949e-13
|  |  |  | 123787.38 |  | 123787.38 | 9.0949e-13
|  | Totals: | 123787.38 |  | 123787.38 |  | 0

## #9433.00 Story Construction (2)
HHS WRC Cottage Siding Replacement
Project # 9433.00
Program code 943300 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525126902 | 2025-05-06 | PO Procore | 29837.01 | 29837.01 |  |  | 29837.01
PRC 3352512PA6902 | 2025-07-17 | Inv. 34906 |  | 29837.01 | 2732.08 | 2732.08 | 27104.93
PO 33525126902A | 2025-07-21 | Updating VC From 0003226164 to 00002110695 | 0 | 29837.01 |  | 2732.08 | 27104.93
PRC 3352512PA6902A | 2025-07-23 | Inv. 34906A |  | 29837.01 | 2255.26 | 4987.34 | 24849.67 | FY25
PO 33526126902A | 2025-08-21 | Roll to FY26 | 0 | 29837.01 |  | 4987.34 | 24849.67
PRC 3352612PC6902A | 2025-09-05 | Inv. 34946 |  | 29837.01 | 1081.81 | 6069.15 | 23767.86
PRC 3352612PD6902A | 2025-09-16 | Inv. 34977 |  | 29837.01 | 11405.14 | 17474.29 | 12362.72
PRC 3352612PE6902A | 2025-10-17 | Inv. 35013 |  | 29837.01 | 4763.48 | 22237.77 | 7599.24
PRC 3352612PF6902A | 2025-11-17 | Inv. 35045 |  | 29837.01 | 7211.96 | 29449.73 | 387.28
PRC 3352612PG6902A | 2026-01-16 | Inv. 35115 |  | 29837.01 | 37.42 | 29487.15 | 349.86
PO 33526126902A | 2026-02-23 | Closing PO Per PM Email | -349.86 | 29487.15 |  | 29487.15 | -2.1032e-12
|  |  |  | 29487.15 |  | 29487.15 | -2.1032e-12
|  |  |  | 29487.15 |  | 29487.15 | -2.1032e-12
|  | Totals: | 29487.15 |  | 29487.15 |  | 0
|  | CM Services | 29457.65 |  | 29457.65 |  | 0
|  | Reimbursables | 29.5 |  | 29.5 |  | 0
|  | Total: | 29487.15 |  | 29487.15 |  | 0
Inv. 34906&34906A should have been one payment
Inv. 34946 Should be payment #2
Inv. 34977 Should be payment #3
Inv. 35013 Should be payment #4
Inv. 35045 Should be payment #5
Note on C19: Huggins, Joni [DAS]: Fwd: WRC 9433.00 Cottage Siding Replacements - Billing $Joni Kleene, Jennifer 3:18 PM (4 minutes ago) to me Please see below, DA25 9433.00 PO 33526126902A may be closed because Story has no further invoices. Regards, Jennifer

## RECAP #9466.00
DOC 3JD CBC New Backup Generator
Project # 9466.00
| Program code 946600 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 405000
C | Boyd Jones |  | 16367.57 | 16367.57 | 0
| PM TIME |  | 13500 | 8171.99 | 5328.01
| Misc. |  | 2670 | 2670 | 0
| KCL Engineering |  | 36800 | 31800 | 5000
| Thompson Solutions Group |  | 213000 | 3426.04 | 209573.96
| Boyd Jones (2) |  | 48027.64 | 12690.79 | 35336.85
| Total Project Cost | 405000 | 330365.21 | 75126.39 | 255238.82 | 74634.79

## #9466.00 Funds Rec'd
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812Y25012 | 2025-01-14 | 405000 | 405000
|  |  | Returning FY25 funds to Agency | IET 33525224921 | 2025-08-12 | -363618.9 | -363618.9
|  |  | Received FY26 funds from Agency | IET 23812Y26004 | 2025-08-27 | 363618.9 | 363618.9
| Total Requested | 0 | Total Transferred |  |  | 405000 | 405000

## #9466.00 Boyd Jones
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA25-9255 |  |  | MA #RFP1821335228-BoydJones11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525037906 | 2025-02-06 | PO Procore | 17496.38 | 17496.38 |  |  | 17496.38
PRC 3352503PA7906 | 2025-03-10 | Inv. 9466.00-01 |  | 17496.38 | 3249.13 | 3249.13 | 14247.25
PRC 3352503PB7906 | 2025-04-08 | Inv. 9466.00-02 |  | 17496.38 | 2961.09 | 6210.22 | 11286.16
PRC 3352503PC7906 | 2025-05-09 | Inv. 9466.00-03 |  | 17496.38 | 2678.94 | 8889.16 | 8607.22
PRC 3352503PD7906 | 2025-06-23 | Inv. 9466.00-04 |  | 17496.38 | 2322.54 | 11211.7 | 6284.68
PRC 3352503PE7906 | 2025-07-14 | Inv. 9466.00-05 |  | 17496.38 | 546.48 | 11758.18 | 5738.2 | FY25
PO 33526037906 | 2025-08-21 | Roll to FY26 | 0 | 17496.38 |  | 11758.18 | 5738.2
PRC 3352603PF7906 | 2025-08-28 | Inv. 9466.00-06 |  | 17496.38 | 3073.9 | 14832.08 | 2664.3
PRC 3352603PG7906 | 2025-09-15 | Inv. 9466.00-07 - Final | -1128.81 | 16367.57 | 1535.49 | 16367.57 | 0
|  |  |  | 16367.57 |  | 16367.57 | 0
|  |  |  | 16367.57 |  | 16367.57 | 0
|  |  |  | 16367.57 |  | 16367.57 | 0
|  |  |  | 16367.57 |  | 16367.57 | 0
|  | Totals: | 16367.57 |  | 16367.57 |  | 0 | FINAL
|  | CM Services | 15981.57 |  | 15981.57 |  | 0
|  | Reimbursables | 386 |  | 386 |  | 0
|  | Total: | 16367.57 |  | 16367.57 |  | 0

## #9466.00 PM TIME
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 910V
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 13500 | 13500 |  |  | 13500
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 13500 | 51.61 | 51.61 | 13448.39
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 13500 | 552.1 | 603.71 | 12896.29
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 13500 | 247.57 | 851.28 | 12648.72
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 13500 | 1072.2 | 1923.48 | 11576.52
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 13500 | 140.59 | 2064.07 | 11435.93
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 13500 | 1008.5 | 3072.57 | 10427.43
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 13500 | 40.5 | 3113.07 | 10386.93
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 13500 | 275.6 | 3388.67 | 10111.33
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 13500 | 102.58 | 3491.25 | 10008.75
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 13500 | 804.7 | 4295.95 | 9204.05
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 13500 | 63.57 | 4359.52 | 9140.48
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 13500 | 493.4 | 4852.92 | 8647.08
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 13500 | 70.25 | 4923.17 | 8576.83
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 13500 | 772.8 | 5695.97 | 7804.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 13500 | 33.7 | 5729.67 | 7770.33
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 13500 | 262.4 | 5992.07 | 7507.93
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 13500 | 88.05 | 6080.12 | 7419.88
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 13500 | 453.5 | 6533.62 | 6966.38
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 13500 | 16.3 | 6549.92 | 6950.08
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 13500 | 159.7 | 6709.62 | 6790.38
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 13500 | 6.95 | 6716.57 | 6783.43
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 13500 | 44.3 | 6760.87 | 6739.13
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 13500 | 12.35 | 6773.22 | 6726.78
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 13500 | 139.4 | 6912.62 | 6587.38
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 13500 | 39.04 | 6951.66 | 6548.34
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 13500 | 481.7 | 7433.36 | 6066.64
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 13500 | 24.83 | 7458.19 | 6041.81
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 13500 | 287.6 | 7745.79 | 5754.21
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 13500 | 46.8 | 7792.59 | 5707.41
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 13500 | 379.4 | 8171.99 | 5328.01
[5 empty] | 13500 |  | 8171.99 | 5328.01
[5 empty] | 13500 |  | 8171.99 | 5328.01
[5 empty] | 13500 |  | 8171.99 | 5328.01
|  |  | Totals: | 13500 |  | 8171.99 |  | 5328.01
Note on E9: Huggins, Joni [DAS]: 9466.00 - PM Time Budget $Joni Elliott, Jennie 12:19 PM (1 hour ago) to me Please establish PM Time budget in 9466.00 DA25 as $13,500 Thank you, Jennie Elliott

## #9466.00 Misc
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code: 035
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525174902 | 2025-06-23 | 9500 | CNST | GPRS Inc V#(00003035582) | Inv. 881544 | 2470 | 2470
PRC 33526238906 | 2025-08-28 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2021 | 200 | 2670
2670
2670
2670
2670
2670
2670
2670
2670
2670
2670
|  |  |  | Totals: |  | 2670

## #9466.00 KCL Engineering
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  | Major Program 4E01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA25-9260 |  |  | 946600-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525086900 | 2025-03-27 | PO Procore | 36800 | 36800 |  |  | 36800
PRC 3352508PA6900 | 2025-04-25 | Inv. 11793 |  | 36800 | 12400 | 12400 | 24400
PRC 3352508PB6900 | 2025-06-30 | Inv. 12199 |  | 36800 | 9900 | 22300 | 14500 | FY25
PO 33526086900 | 2025-08-21 | Roll to FY26 | 0 | 36800 |  | 22300 | 14500
PRC 3352608PC6900 | 2025-08-28 | Inv. 12379 |  | 36800 | 3300 | 25600 | 11200
PRC 3352608PD6900 | 2025-08-29 | Inv. 12523 |  | 36800 | 3200 | 28800 | 8000
PRC 3352608PE6900 | 2025-10-08 | Inv. 12798 |  | 36800 | 2000 | 30800 | 6000
PRC 3352608PF6900 | 2026-04-09 | Inv. 9466.00-06 |  | 36800 | 1000 | 31800 | 5000
|  |  |  | 36800 |  | 31800 | 5000
|  |  |  | 36800 |  | 31800 | 5000
|  |  |  | 36800 |  | 31800 | 5000
|  |  |  | 36800 |  | 31800 | 5000
|  |  |  | 36800 |  | 31800 | 5000
|  | Totals: | 36800 |  | 31800 |  | 5000
|  | Design Development Docs | 12400 |  | 12400 |  | 0
|  | Construction Docs | 13200 |  | 13200 |  | 0
|  | Bidding Assistance | 3200 |  | 3200 |  | 0
|  | Construction Phase | 8000 |  | 3000 |  | 5000
|  | Total: | 36800 |  | 31800 |  | 5000

## #9466.00 Thompson Solutions
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  | Major Program 4E01
Thompson Solutions Group |  |  | Vendor: 00002108466
Acct. Codes-0506-335-DA25-9255 |  |  | RFB #946600-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526259902 | 2025-09-16 | PO Procore | 213000 | 213000 |  |  | 213000
PRC 3352625PA9902 | 2026-03-23 | Inv. 9466.00-01 |  | 213000 | 3038.04 | 3038.04 | 209961.96 | 93.96
PRC 3352625PB9902 | 2026-03-26 | Inv. 253S122-02 |  | 213000 | 388 | 3426.04 | 209573.96 | 105.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  |  |  | 213000 |  | 3426.04 | 209573.96
|  | Totals: | 213000 |  | 3426.04 |  | 209573.96
3% retainage

## #9466.00 Boyd Jones (2)
DOC 3JD CBC New Backup Generator
Project # 9466.00
Program code 946600 |  |  | Major Program 4E01
Boyd Jones(2) |  |  | Vendor: 00003193325
Acct. Codes-0506-335-DA25-9255 |  |  | 946600-01
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526289901 | 2025-10-16 | PO Procore | 48027.64 | 48027.64 |  |  | 48027.64
PRC 3352628PA9901 | 2025-11-04 | Inv. 9466.00-001 |  | 48027.64 | 2324.32 | 2324.32 | 45703.32
PRC 3352628PB9901 | 2025-12-09 | Inv. 9466.00-002 |  | 48027.64 | 596.67 | 2920.99 | 45106.65
PRC 3352628PC9901 | 2026-01-09 | Inv. 9466.00-003 |  | 48027.64 | 2403.44 | 5324.43 | 42703.21
PRC 3352628PD9901 | 2026-02-06 | Inv. 9466.00-004 |  | 48027.64 | 1640.12 | 6964.55 | 41063.09
PRC 3352628PE9901 | 2026-03-18 | Inv. 9466.00-005 |  | 48027.64 | 3274.86 | 10239.41 | 37788.23
PRC 3352628PF9901 | 2026-04-20 | Inv. 9466.00-006 |  | 48027.64 | 2451.38 | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  |  |  | 48027.64 |  | 12690.79 | 35336.85
|  | Totals: | 48027.64 |  | 12690.79 |  | 35336.85
|  | CM Services | 43644.64 |  | 12607.08 |  | 31037.56
|  | Reimbursables | 4383 |  | 83.71 |  | 4299.29
|  | Total: | 48027.64 |  | 12690.79 |  | 35336.85
Inv.9466.00-0X was used in tab one of this vendor, please use 9466.00-00X

## RECAP #9467.00
HHS IMHI Soil Remediation
Project # 9467.00
| Program code 946700 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 15645.69
| VendorA |  | 0 | 0 | 0
C | PM TIME |  | 3345.69 | 3345.69 | 0
C | Misc. |  | 12300 | 12300 | 0
| Total Project Cost | 15645.69 | 15645.69 | 15645.69 | 1.819e-12 | 0
Closed 06/12/25
Project not proceeding per agency

## #9467.00 Funds Rec'd
HHS IMHI Soil Remediation
Project # 9467.00
Program code 946700 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 4400CKC250221104 | 2025-02-21 | 275000 | 275000
|  |  | Returning Funds to Agency - Closing Project | IET 33525163904 | 2025-06-12 | -259354.31 | -259354.31
| Total Requested | 0 | Total Transferred |  |  | 15645.69 | 15645.69

## #9467.00 Vendor A
HHS IMHI Soil Remediation
Project # 9467.00
Program code 946700 |  |  | Major Program 4B02
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9467.00 PM TIME
HHS IMHI Soil Remediation
Project # 9467.00
Program code 946700 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 910W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 3345.69 | 3345.69 |  |  | 3345.69
IET DAS202507115300001 | 2025-02-11 | 2507 | Finance Support for January 1-31, 2025 |  | 3345.69 | 92.25 | 92.25 | 3253.44
IET DAS202507115300001 | 2025-02-11 | 9500 | DAS Support for January 1-31, 2025 |  | 3345.69 | 985.6 | 1077.85 | 2267.84
CDE 33525050904 | 2025-02-19 | 2507 | Move Expenses to Admin time per Project Manager |  | 3345.69 | -92.25 | 985.6 | 2360.09
CDE 33525050904 | 2025-02-19 | 9500 | Move Expenses to Admin time per Project Manager |  | 3345.69 | -985.6 | 0 | 3345.69
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 3345.69 | 165.28 | 165.28 | 3180.41
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 3345.69 | 713.9 | 879.18 | 2466.51
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 3345.69 | 151.55 | 1030.73 | 2314.96
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 3345.69 | 1086 | 2116.73 | 1228.96
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 3345.69 | 145.67 | 2262.4 | 1083.29
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 3345.69 | 1000.9 | 3263.3 | 82.39
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 3345.69 | 9.29 | 3272.59 | 73.1
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 3345.69 | 73.1 | 3345.69 | -4.5475e-13
[5 empty] | 3345.69 |  | 3345.69 | -4.5475e-13
[5 empty] | 3345.69 |  | 3345.69 | -4.5475e-13
[5 empty] | 3345.69 |  | 3345.69 | -4.5475e-13
|  |  | Totals: | 3345.69 |  | 3345.69 |  | 0
Note on E9: Jurgenson, John [DAS]: Re: PM Time Inbox Elliott, Jennie 2:21 PM (0 minutes ago) to me Please use $5,000 for PM time budget

## #9467.00 Misc
HHS IMHI Soil Remediation
Project # 9467.00
Program code 946700 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33525118902 | 2025-04-28 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2638653 | 12000 | 12000
PRC 33525140901 | 2025-05-20 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV048365 | 300 | 12300
12300
12300
12300
12300
12300
12300
12300
12300
12300
12300
|  |  |  | Totals: |  | 12300

## RECAP #9468.00
IUC CC IUC Building Window Shade System Replacement
Project # 9468.00
Program code 946800 |  |  | Major Program 4A01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Oliver S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed 02/25/25
Project cancelled by Facility Manager

## #9468.00 Funds Rec'd
IUC CC IUC Building Window Shade System Replacement
Project # 9468.00
Program code 946800 |  |  | Major Program 4A01
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Oliver S
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9468.00 Vendor A
IUC CC IUC Building Window Shade System Replacement
Project # 9468.00
Program code 946800 |  |  | Major Program 4A01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9468.00 PM TIME
IUC CC IUC Building Window Shade System Replacement
Project # 9468.00
Program code 946800 |  |  |  | Major Program 4A01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  |  | eDAS: 910X
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9468.00 Misc
IUC CC IUC Building Window Shade System Replacement
Project # 9468.00
Program code 946800 |  |  |  | Major Program 4A01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9470.00
DOC 6JD IC Hope-Stratton Retaining Wall Repairs
Project # 9470.00
| Program code 947000 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 8629.61
C | Horizon Architecture |  | 6810 | 6810 | 0
C | PM TIME |  | 1819.61 | 1819.61 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 8629.61 | 8629.61 | 8629.61 | 0 | 0
Closed 06/13/25

## #9470.00 Funds Rec'd
DOC 6JD IC Hope-Stratton Retaining Wall Repairs
Project # 9470.00
Program code 947000 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 226A062500818 | 2025-02-07 | 10000 | 10000
|  |  | Returning Funds - Closing Project | IET 33525164912 | 2025-06-13 | -1370.39 | -1370.39
| Total Requested | 0 | Total Transferred |  |  | 8629.61 | 8629.61

## #9470.00 Horizon Architecture
DOC 6JD IC Hope-Stratton Retaining Wall Repairs
Project # 9470.00
Program code 947000 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA25-9260 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525049905 | 2025-02-18 | PO Procore | 6810 | 6810 |  |  | 6810
PRC 3352504PA9905 | 2025-04-11 | Inv. 9470.00-01 |  | 6810 | 2780 | 2780 | 4030
PRC 3352504PB9905 | 2025-05-16 | Inv. 9470.00-02 - FINAL |  | 6810 | 4030 | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  |  |  | 6810 |  | 6810 | 0
|  | Totals: | 6810 |  | 6810 |  | 0 | FINAL
|  | Design Development | 2780 |  | 2780 |  | 0
|  | Construction Documents | 4030 |  | 4030 |  | 0
|  | Total: | 6810 |  | 6810 |  | 0

## #9470.00 PM TIME
DOC 6JD IC Hope-Stratton Retaining Wall Repairs
Project # 9470.00
Program code 947000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 910Y
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 1819.61 | 1819.61 |  |  | 1819.61
IET DAS202508115300001 | 2025-03-07 | 2507 | Finance Support for February 2-28, 2025 |  | 1819.61 | 208.95 | 208.95 | 1610.66
IET DAS202508115300001 | 2025-03-07 | 9500 | DAS Support for February 2-28, 2025 |  | 1819.61 | 903.4 | 1112.35 | 707.26
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 1819.61 | 7.17 | 1119.52 | 700.09
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 1819.61 | 52.4 | 1171.92 | 647.69
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 1819.61 | 29.11 | 1201.03 | 618.58
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 1819.61 | 200.3 | 1401.33 | 418.28
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 1819.61 | 47.28 | 1448.61 | 371
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 1819.61 | 371 | 1819.61 | 1.1369e-13
[5 empty] | 1819.61 |  | 1819.61 | 1.1369e-13
[5 empty] | 1819.61 |  | 1819.61 | 1.1369e-13
[5 empty] | 1819.61 |  | 1819.61 | 1.1369e-13
[5 empty] | 1819.61 |  | 1819.61 | 1.1369e-13
|  |  | Totals: | 1819.61 |  | 1819.61 |  | 0
Note on E9: Huggins, Joni [DAS]: DAS Costs Budget for DA25 9470.00 $Joni Kleene, Jennifer Feb 20, 2025, 4:13 PM (15 hours ago) to me Please create a DAS Costs budget of $2000.00 for DA25 project 9470.00. Regards, Jennifer Jennifer Kleene Owner’s Representative Please Close DA25 Project 9470.00 DOC 6JD IC Hope-Stratton Retaining Wall Repairs $Joni Kleene, Jennifer 11:42 AM (23 minutes ago) to me, Brian, Cory, Rob All invoices have been paid and all DAS costs have posted, so please close project 9470.00 and return the remaining $1,370.39 to DOC. Regards, Jennifer Jennifer Kleene

## #9470.00 Misc
DOC 6JD IC Hope-Stratton Retaining Wall Repairs
Project # 9470.00
Program code 947000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 122A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9472.00
DAS CC Hoover Level B Sprinkler Modifications
Project # 9472.00
Program code 947200 |  |  | Major Program 4D01
Recap
Acct. Codes-0506-335-DA25
Project Manager - Oliver S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed/Moving to X674

## #9472.00 Funds Rec'd
DAS CC Hoover Level B Sprinkler Modifications
Project # 9472.00
Program code 947200 |  |  | Major Program 4D01
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Oliver S
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9472.00 Vendor A
DAS CC Hoover Level B Sprinkler Modifications
Project # 9472.00
Program code 947200 |  |  | Major Program 4D01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9472.00 PM TIME
DAS CC Hoover Level B Sprinkler Modifications
Project # 9472.00
Program code 947200 |  |  |  | Major Program 4D01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  |  | eDAS: 732V
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
IET DAS202509115300001 | 2025-04-09 | 2507 | Finance Support for March 01-31, 2025 |  | 0 | 165.47 | 165.47 | -165.47
IET DAS202509115300001 | 2025-04-09 | 9500 | DAS Support for March 01-31, 2025 |  | 0 | 1183.7 | 1349.17 | -1349.17
CDE 33525106900 | 2025-04-16 | 2507 | Move expense from DA25 to X674 |  | 0 | -165.47 | 1183.7 | -1183.7
CDE 33525106900 | 2025-04-16 | 9500 | Move expense from DA25 to X674 |  | 0 | -1183.7 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9472.00 Misc
DAS CC Hoover Level B Sprinkler Modifications
Project # 9472.00
Program code 947200 |  |  |  | Major Program 4D01
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9473.00
DAS CC Hoover Print Shop Expansion
Project # 9473.00
Program code 947300 |  |  | Major Program 4E06
Recap
Acct. Codes-0506-335-DA25
Project Manager - Oliver S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed/Moving to 5800

## #9473.00 Funds Rec'd
DAS CC Hoover Print Shop Expansion
Project # 9473.00
Program code 947300 |  |  | Major Program 4E06
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager - Oliver S
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #9473.00 Vendor A
DAS CC Hoover Print Shop Expansion
Project # 9473.00
Program code 947300 |  |  | Major Program 4E06
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9473.00 PM TIME
DAS CC Hoover Print Shop Expansion
Project # 9473.00
Program code 947300 |  |  |  | Major Program 4E06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Oliver S |  |  |  | eDAS: 732X
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9473.00 Misc
DAS CC Hoover Print Shop Expansion
Project # 9473.00
Program code 947300 |  |  |  | Major Program 4E06
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9475.00
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
| Program code 947500 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 211000
| Genesis Architectural |  | 36600 | 22700 | 13900
| PM TIME |  | 6000 | 5349.74 | 650.26
| Misc. |  | 1420.86 | 1420.86 | 0
C | DCI Group |  | 12634.15 | 12634.15 | 0
| Christiansen Construction |  | 106760 | 0 | 106760
| CW Suter |  | 16380 | 0 | 16380
| DCI Group(2) |  | 22442.25 | 8651.2 | 13791.05
| Total Project Cost | 211000 | 202237.26 | 50755.95 | 151481.31 | 8762.74

## #9475.00 Funds Rec'd
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 41JP2504292513 | 2025-04-30 | 175000 | 175000
|  |  | Returning FY25 Funds to Agency | IET 33525224922 | 2025-08-12 | -174280.81 | -174280.81
|  |  | Received FY26 funds from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 174280.81 | 174280.81
|  |  | MOU Amendment #1 | IET 41JP2601072601 | 2026-01-09 | 36000 | 36000
| Total Requested | 0 | Total Transferred |  |  | 211000 | 211000

## #9475.00 Genesis Architectural
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA25-9260 |  |  | RFP#947500-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526254900 | 2025-09-11 | PO Procore | 36600 | 36600 |  |  | 36600
PRC 3352625PA4900 | 2025-10-13 | Inv. 2514-01 |  | 36600 | 16650 | 16650 | 19950
PRC 3352625PB4900 | 2025-10-24 | Inv. 9475.00-#02 |  | 36600 | 1850 | 18500 | 18100
PRC 3352625PC4900 | 2025-12-16 | Inv. 2514-03 |  | 36600 | 4200 | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  |  |  | 36600 |  | 22700 | 13900
|  | Totals: | 36600 |  | 22700 |  | 13900
|  | Construction Documents | 18500 |  | 18500 |  | 0
|  | Bid Phase | 4200 |  | 4200 |  | 0
|  | Construction Phase | 13900 |  |  |  | 13900
|  | Total: | 36600 |  | 22700 |  | 13900

## #9475.00 PM TIME
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 732Z
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 6000 | 6000 |  |  | 6000
IET DAS202510115300001 | 2025-05-09 | 2507 | Finance Support for April 01-30, 2025 |  | 6000 | 60.18 | 60.18 | 5939.82
IET DAS202510115300001 | 2025-05-09 | 9500 | DAS Support for April 01-30, 2025 |  | 6000 | 415.3 | 475.48 | 5524.52
IET DAS202511115300001 | 2025-06-09 | 2507 | Finance Support for May 01-31, 2025 |  | 6000 | 18.57 | 494.05 | 5505.95
IET DAS202511115300001 | 2025-06-09 | 9500 | DAS Support for May 01-31, 2025 |  | 6000 | 146.2 | 640.25 | 5359.75
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 6000 | 9.14 | 649.39 | 5350.61
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 6000 | 69.8 | 719.19 | 5280.81
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 6000 | 24.78 | 743.97 | 5256.03
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 6000 | 270 | 1013.97 | 4986.03
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 6000 | 114.08 | 1128.05 | 4871.95
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 6000 | 875.8 | 2003.85 | 3996.15
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 6000 | 209.73 | 2213.58 | 3786.42
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 6000 | 1078.8 | 3292.38 | 2707.62
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 6000 | 60.38 | 3352.76 | 2647.24
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 6000 | 598.9 | 3951.66 | 2048.34
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 6000 | 62.35 | 4014.01 | 1985.99
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 6000 | 399.7 | 4413.71 | 1586.29
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 6000 | 48.97 | 4462.68 | 1537.32
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 6000 | 556.6 | 5019.28 | 980.72
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 6000 | 24.26 | 5043.54 | 956.46
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 6000 | 306.2 | 5349.74 | 650.26
[5 empty] | 6000 |  | 5349.74 | 650.26
[5 empty] | 6000 |  | 5349.74 | 650.26
[5 empty] | 6000 |  | 5349.74 | 650.26
|  |  | Totals: | 6000 |  | 5349.74 |  | 650.26
Note on E9: Huggins, Joni [DAS]: Changes for PM Time $Joni Elliott, Jennie May 4, 2025, 3:12 PM (15 hours ago) to me Can you please make the following change for PM time, thank you! 9388.00 - Please increase PM Time in the "Contracted" line to $15,000.00 9401.00 - Please increase PM Time in the "Contracted" line to $9,000.00 9475.00 - Please Establish a PM Time budget of $7,500.00 9474.00 - Please Establish a PM Time budget of Re: 9475.00 - HHS CHMHI Fleet Garage Repairs - PM Time Budget Adjustment Inbox Elliott, Jennie 8:39 AM (7 minutes ago) to me Jesh, Apparently I should not have done Math yesterday. This is my second math error yesterday. $6,000.00 please! Put the "Contracted" line to $6,000 :) Jennie Elliott

## #9475.00 Misc
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code: 548
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526338907 | 2025-12-04 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2327 | 220.36 | 220.36
PRC 33526346901 | 2025-12-12 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2681858 | 1200.5 | 1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
1420.86
|  |  |  | Totals: |  | 1420.86

## #9475.00 DCI Group
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266905 | 2025-09-23 | PO Procore | 19897.15 | 19897.15 |  |  | 19897.15
PRC 3352626PA6905 | 2025-10-10 | Inv. 25-028 PC 01 |  | 19897.15 | 2106.82 | 2106.82 | 17790.33
PRC 3352626PB6905 | 2025-11-18 | Inv. 25-028 PC 02 |  | 19897.15 | 3844.93 | 5951.75 | 13945.4
PRC 3352626PC6905 | 2025-12-22 | Inv. 25-028 PC 03 |  | 19897.15 | 4394.52 | 10346.27 | 9550.88
PRC 3352626PD6905 | 2026-01-21 | Inv. 25-028 PC 04 FINAL | -7263 | 12634.15 | 2287.88 | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  |  |  | 12634.15 |  | 12634.15 | 0
|  | Totals: | 12634.15 |  | 12634.15 |  | 0 | FINAL
|  | CM Staff Hours | 12514.15 |  | 12514.15 |  | 0
|  | Reimbursables | 120 |  | 120 |  | 0
|  | Total: | 12634.15 |  | 12634.15 |  | 0

## #9475.00 Christiansen Contr
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
Christiansen Construction |  |  | Vendor: 00003234520
Acct. Codes-0506-335-DA25-9255 |  |  | RFB #947500-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526007908 | 2026-01-07 | PO Procore | 106760 | 106760 |  |  | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  |  |  | 106760 |  | 0 | 106760
|  | Totals: | 106760 |  | 0 |  | 106760

## #9475.00 CW Suter
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
CW Suter |  |  | Vendor: 00002134879
Acct. Codes-0506-335-DA25-9255 |  |  | RFB #947500-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526012900 | 2026-01-12 | PO Procore | 16380 | 16380 |  |  | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  |  |  | 16380 |  | 0 | 16380
|  | Totals: | 16380 |  | 0 |  | 16380

## #9475.00 DCI Group (2)
HHS CHMHI Fleet Garage Repairs
Project # 9475.00
Program code 947500 |  |  | Major Program 4B02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526043912 | 2026-02-12 | PO Procore | 22442.25 | 22442.25 |  |  | 22442.25
PRC 3352604PA3912 | 2026-03-24 | Inv. 25-028 CA 01 |  | 22442.25 | 4620.24 | 4620.24 | 17822.01
PRC 3352604PB3912 | 2026-04-16 | Inv. 25-028 CA 02 |  | 22442.25 | 4030.96 | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  |  |  | 22442.25 |  | 8651.2 | 13791.05
|  | Totals: | 22442.25 |  | 8651.2 |  | 13791.05
|  | CM Staff Hours | 18442.25 |  | 6379.2 |  | 12063.05
|  | Reimbursables | 4000 |  | 2272 |  | 1728
|  | Total: | 22442.25 |  | 8651.2 |  | 13791.05

## RECAP #9476.00
HHS STS New Garage Building
Project # 9476.00
| Program code 947600 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 41976.76
C | McGough Construction |  | 14388.45 | 14388.45 | 0
C | PM TIME |  | 8341.81 | 8341.81 | 0
C | Misc. |  | 336.5 | 336.5 | 0
C | HGM Associates Inc. |  | 18910 | 18910 | 0
| Total Project Cost | 41976.76 | 41976.76 | 41976.76 | -7.276e-12 | 0
Closed 02/16/26

## #9476.00 Funds Rec'd
HHS STS New Garage Building
Project # 9476.00
Program code 947600 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL25168001 | 2025-06-17 | 225000 | 225000
|  |  | Returning FY25 Funds to Agency | IET 33525224923 | 2025-08-12 | -224341.04 | -224341.04
|  |  | Received FY26 funds from Agency | IET FY26 MOU TRANFER | 2025-09-02 | 224341.04 | 224341.04
|  |  | Returning Funds/Closing Project | IET 33526047910 | 2026-02-16 | -183023.24 | -183023.24
| Total Requested | 0 | Total Transferred |  |  | 41976.76 | 41976.76

## #9476.00 McGough Construction
HHS STS New Garage Building
Project # 9476.00
Program code 947600 |  |  | Major Program 4B02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525178905 | 2025-06-27 | PO Procore | 14471.98 | 14471.98 |  |  | 14471.98
PO 3352517PA8905 | 2025-07-16 | Inv. 101368.010-PC01 |  | 14471.98 | 291.05 | 291.05 | 14180.93 | FY25
PO 33526178905 | 2025-08-21 | Roll to FY26 | 0 | 14471.98 |  | 291.05 | 14180.93
PRC 3352617PB8905 | 2025-09-05 | Inv. 101368.010-PC02 |  | 14471.98 | 2217.16 | 2508.21 | 11963.77
PRC 3352617PC8905 | 2025-09-15 | Inv. 101368.010-PC03 |  | 14471.98 | 2953.71 | 5461.92 | 9010.06
PRC 3352617PD8905 | 2025-10-15 | Inv. 101368.010-PC04 |  | 14471.98 | 1294.9 | 6756.82 | 7715.16
PRC 3352617PE8905 | 2025-11-13 | Inv. 101368.010-PC05 |  | 14471.98 | 2668.19 | 9425.01 | 5046.97
PRC 3352617PF8905 | 2026-01-29 | Inv. 101368.010-PC06 Final | -83.53 | 14388.45 | 4963.44 | 14388.45 | 1.5632e-12
|  |  |  | 14388.45 |  | 14388.45 | 1.5632e-12
|  |  |  | 14388.45 |  | 14388.45 | 1.5632e-12
|  |  |  | 14388.45 |  | 14388.45 | 1.5632e-12
|  |  |  | 14388.45 |  | 14388.45 | 1.5632e-12
|  |  |  | 14388.45 |  | 14388.45 | 1.5632e-12
|  | Totals: | 14388.45 |  | 14388.45 |  | 0 | FINAL
|  | CM Services | 14228.45 |  | 14228.45 |  | 0
|  | Reimbursables | 160 |  | 160 |  | 0
|  | Total: | 14388.45 |  | 14388.45 |  | 0

## #9476.00 PM TIME
HHS STS New Garage Building
Project # 9476.00
Program code 947600 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 733D
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8341.81 | 8341.81 |  |  | 8341.81
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 8341.81 | 41.91 | 41.91 | 8299.9
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 8341.81 | 326 | 367.91 | 7973.9
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 8341.81 | 142.92 | 510.83 | 7830.98
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 8341.81 | 1567.4 | 2078.23 | 6263.58
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 8341.81 | 238.72 | 2316.95 | 6024.86
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 8341.81 | 1833.6 | 4150.55 | 4191.26
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 8341.81 | 333.39 | 4483.94 | 3857.87
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 8341.81 | 1715.6 | 6199.54 | 2142.27
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8341.81 | 71.84 | 6271.38 | 2070.43
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8341.81 | 769.3 | 7040.68 | 1301.13
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 8341.81 | 110.05 | 7150.73 | 1191.08
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 8341.81 | 699.9 | 7850.63 | 491.18
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 8341.81 | 4.53 | 7855.16 | 486.65
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 8341.81 | 48.1 | 7903.26 | 438.55
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 8341.81 | 32.85 | 7936.11 | 405.7
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 8341.81 | 405.7 | 8341.81 | 3.979e-13
[5 empty] | 8341.81 |  | 8341.81 | 3.979e-13
[5 empty] | 8341.81 |  | 8341.81 | 3.979e-13
[5 empty] | 8341.81 |  | 8341.81 | 3.979e-13
|  |  | Totals: | 8341.81 |  | 8341.81 |  | 0
Note on E9: Huggins, Joni [DAS]: DAS Costs Budget for DA25 9476.00 $Joni Kleene, Jennifer 8:09 AM (56 minutes ago) to me Please create a DAS Costs budget for $8,000.00 for 9476.00. Regards, Jennifer Jennifer Kleene DAS Cost Budget Increases $Joni Kleene, Jennifer 9:49 AM (2 minutes ago) to me Please increase the DAS Cost budget for MM24 9277.00 by $3,000.00 Please increase the DAS Cost budget for DA26 9480.01 by $2,000.00 Please increase the DAS Cost budget for DA25 9433.00 by $1,000.00 Please increase the DAS Cost budget for DA25 9476.00 by $500.00 Please close DA25 Project 9476.00 $Joni Kleene, Jennifer Feb 13, 2026, 3:32 PM (3 days ago) to me, Geoff, Robert All DAS costs have posted and all invoices have been paid, so please close the project, remove it from the billables sheet and return the remaining $183,023.24 to STS. Regards, Jennifer

## #9476.00 Misc
HHS STS New Garage Building
Project # 9476.00
Program code 947600 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526337903 | 2025-12-03 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2330 | 336.5 | 336.5
336.5
336.5
336.5
336.5
336.5
336.5
336.5
336.5
336.5
336.5
336.5
|  |  |  | Totals: |  | 336.5

## #9476.00 HGM Associates Inc
HHS STS New Garage Building
Project # 9476.00
Program code 947600 |  |  | Major Program 4B02
HGM Associates Inc |  |  | Vendor: 00002109941
Acct. Codes-0506-335-DA25-9260 |  |  | RFP947600-01-HGMAssociates
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526248405 | 2025-09-03 | PO Procore | 28275 | 28275 |  |  | 28275
PO 33526248405 | 2025-09-15 | CO #1 | 3000 | 31275 |  | 0 | 31275
PRC 3352624PA8405 | 2025-10-03 | Inv. 106025-1 |  | 31275 | 13401 | 13401 | 17874
PRC 3352624PB8405 | 2025-11-04 | Inv. 106025-2 |  | 31275 | 2219 | 15620 | 15655
PRC 3352624PC8405 | 2026-01-21 | Inv. 106025-3 - FINAL | -12365 | 18910 | 3290 | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  |  |  | 18910 |  | 18910 | 0
|  | Totals: | 18910 |  | 18910 |  | 0 | FINAL
|  | Design Development | 9280 |  | 9280 |  | 0
|  | Construction Documents | 6340 |  | 6340 |  | 0
|  | Bidding or Negotiation Assistance | 290 |  | 290 |  | 0
|  | Construction Phase | 0 |  |  |  | 0
|  | CO #1 | 3000 |  | 3000 |  | 0
|  | Total: | 18910 |  | 18910 |  | 0

## RECAP #9480.00
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
| Program code 948000 |  |  | Major Program 3D02
Recap
Acct. Codes-0506-335-DA25
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 25000
C | McGough Construction |  | 7211.25 | 7211.25 | 0
C | PM TIME |  | 5482.75 | 5482.75 | 0
C | Misc. |  | 1556 | 1556 | 0
C | Genesis Architectural Design |  | 10750 | 10750 | 0
| Total Project Cost | 25000 | 25000 | 25000 | 0 | 0

## #9480.00 Funds Rec'd
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
Program code 948000 |  |  | Major Program 3D02
Funds Rec'd
Acct Code: 0506-335-DA25-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL25175007 | 2025-06-25 | 25000 | 25000
|  |  | Returning FY25 Funds to Agency | IET 33525224924 | 2025-08-12 | -21024.9 | -21024.9
|  |  | Received FY26 Funds received from Agency | IET FY26 MOU TRANSFER | 2025-09-02 | 21024.9 | 21024.9
| Total Requested | 0 | Total Transferred |  |  | 25000 | 25000

## #9480.00 McGough Construction
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
Program code 948000 |  |  | Major Program 3D02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA25-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525178900 | 301478 | PO Procore | 7306.88 | 7306.88 |  |  | 7306.88 | FY25
PO 33526178900 | 2025-08-21 | Roll to FY26 | 0 | 7306.88 |  | 0 | 7306.88
PRC 3352617PA8900 | 2025-09-05 | Inv. 101368.011-PC01 |  | 7306.88 | 3641.15 | 3641.15 | 3665.73
PRC 3352617PB8900 | 2025-09-15 | Inv. 101368.011-PC02 Final | -95.63 | 7211.25 | 3570.1 | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  |  |  | 7211.25 |  | 7211.25 | 1.1369e-13
|  | Totals: | 7211.25 |  | 7211.25 |  | 0 | FINAL
|  | CM Services | 7051.25 |  | 7051.25 |  | 0
|  | Reimbursables | 160 |  | 160 |  | 0
|  | Total: | 7211.25 |  | 7211.25 |  | 0

## #9480.00 PM Time
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
Program code 948000 |  |  |  | Major Program 3D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 733G
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5482.75 | 5482.75 |  |  | 5482.75
IET DAS202512115300001 | 2025-07-10 | 2507 | Finance Support for June 01-30, 2025 |  | 5482.75 | 109.7 | 109.7 | 5373.05
IET DAS202512115300001 | 2025-07-10 | 9500 | DAS Support for June 01-30, 2025 |  | 5482.75 | 855.4 | 965.1 | 4517.65
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 5482.75 | 217.57 | 1182.67 | 4300.08
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 5482.75 | 2383.9 | 3566.57 | 1916.18
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 5482.75 | 376.36 | 3942.93 | 1539.82
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 5482.75 | 2895.8 | 6838.73 | -1355.98
CDE 33526262901 | 2025-09-18 | 9500 | Moving Expense to 9480.01 |  | 5482.75 | -1355.98 | 5482.75 | 4.5475e-13
[5 empty] | 5482.75 |  | 5482.75 | 4.5475e-13
[5 empty] | 5482.75 |  | 5482.75 | 4.5475e-13
[5 empty] | 5482.75 |  | 5482.75 | 4.5475e-13
[5 empty] | 5482.75 |  | 5482.75 | 4.5475e-13
[5 empty] | 5482.75 |  | 5482.75 | 4.5475e-13
|  |  | Totals: | 5482.75 |  | 5482.75 |  | 0
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer Sun, Jul 13, 4:47 PM (13 hours ago) to me Please create a DAS Costs Budget of $4,000.00 for DA25 9480.00. Please increase the budget for MM23 9294.00 by $160.05. Regards, Jennifer

## #9480.00 Misc
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
Program code 948000 |  |  |  | Major Program 3D02
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526253401 | 2025-09-10 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2658324 | 242 | 242
PRC 33526253402 | 2025-09-10 | 9500 | CNST | ATC Group Services V#(00002134218) | Inv. 2663593 | 1314 | 1556
1556
1556
1556
1556
1556
1556
1556
1556
1556
1556
|  |  |  | Totals: |  | 1556

## #9480.00 Genesis Architectural
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.00
Program code 948000 |  |  | Major Program 3D02
Genesis Architectural Design |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA25-9260 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split w/ DA26
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33525181901 | 2025-06-30 | PO Procore | 10750 | 10750 |  |  | 10750
PRC 3352518PA1901 | 2025-07-03 | Inv. 2503-01 |  | 10750 | 3010 | 3010 | 7740 | FY25
PO 33526181901 | 2025-08-21 | Roll to FY26 | 0 | 10750 |  | 3010 | 7740
PO 33526181901 | 2025-08-22 | CO #1 Opening in DA26 | 0 | 10750 |  | 3010 | 7740
PRC 3352618PB1901 | 2025-09-23 | Inv. 2503-02(Split w/DA26) |  | 10750 | 7740 | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  |  |  | 10750 |  | 10750 | 0
|  | Totals: | 10750 |  | 10750 |  | 0
|  | DA26 | 16700 |  | 13950 |  | 2750
|  | Total: | 27450 |  | 24700 |  | 2750

## #XXXX.XX Funds Recv'd Incorrect
#REF!
#REF!
#REF! |  |  | #REF!
Funds Rec'd Incorrect Unit
Acct Code: 0506-335-DA25-xxxx
#REF!
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9425.00 | IET 405EL25262002 | 2024-09-18 | 18925.83 | 18925.83
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263901 | 2024-09-19 | -18925.83 | -18925.83
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9279.21 | IET MOURETFUNDS9279.21 | 2024-09-18 | 115631.44 | 115631.44
|  |  | FY25 Funds Moved from DA25 to DA23 | CDR 33525263902 | 2024-09-19 | -115631.44 | -115631.44
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9279.30 | IET MOURETFUNDS9279.30 | 2024-09-18 | 3807589.71 | 3807589.71
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263903 | 2024-09-19 | -3807589.71 | -3807589.71
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9279.31 | IET MOURETFUNDS9279.31 | 2024-09-18 | 124607.2 | 124607.2
|  |  | FY25 Funds Moved from DA25 to DA23 | CDR 33525263904 | 2024-09-19 | -124607.2 | -124607.2
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9279.32 | IET MOURETFUNDS9279.32 | 2024-09-18 | 97711.73 | 97711.73
|  |  | FY25 Funds Moved from DA25 to DA24 | CDR 33525263905 | 2024-09-19 | -97711.73 | -97711.73
|  |  | FY25 Funds Recv'd In Incorrect Unit - 9345.00 | IET MOURETFUNDS9345.00 | 2024-09-18 | 127711.24 | 127711.24
|  |  | FY25 Funds Moved from DA25 to DA23 | CDR 33525263906 | 2024-09-19 | -127711.24 | -127711.24
|  |  | FY25 Funds Recv'd to a Closed Program - 9399.00 | IET MOURETFUNDS9399.00 | 2024-09-18 | 996.43 | 996.43
|  |  | FY25 Funds Return to Agency | IET 33525263907 | 2024-09-19 | -996.43 | -996.43
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Recap
Acct. Codes-0506-335-DA25
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Funds Rec'd
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Funds Rec'd
Acct Code: 0506-335-DA25-xxxx
Project Manager -
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA25-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA25-xxxx
Project Manager - |  |  |  | eDAS:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
Misc
Acct. Codes-0506-335-DA25-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0