## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 22178934.56
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22178934.56
|  | Less: Total Assigned |  | 3095610.93
|  | Total Unassigned / Unallocated |  | 19083323.63
DA26 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9279.50 | HHS WRC Campus Utility Decentralization Phase 5 | Jennifer K. | 0 | 14275000 | 0 | 776394.59 | 264.69 | 776129.9 | 13498605.41
| 9438.00 | DOC FDCF Warehouse Loading Dock Ramp Repairs | Jennie E. | 0 | 15650 | 0 | 15499.2 | 182.45 | 15316.75 | 150.8
| 9471.00 | DCO FDCF Bldg G Water Heater Replacement (29C20) | Jennie E. | 0 | 27500 | 27500 | 24537 | 13230.65 | 11306.35 | 2963
| 9480.01 | HHS STS Canteen Roof Repair Construction (29C20) | Jennifer K. | 0 | 265000 | 265000 | 244751.3 | 208961.64 | 35789.66 | 20248.7
| 9481.00 | DOC 5JD 150 DSM St Renovation | Brandon A. | 0 | 1400000 | 1400000 | 10783.75 | 3435.24 | 7348.51 | 1389216.25
| 9482.00 | IDB - Chiller Replacement | Oliver S. | 0 | 50000 | 50000 | 48299.4 | 24831.53 | 23467.87 | 1700.6
| 9486.00 | DVA IVH Fox and Ulery Carpet Replacement | Brad T. | 0 | 1000000 | 1000000 | 959441.86 | 535399.2 | 424042.66 | 40558.14
| 9487.00 | DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20) | Brad T. | 0 | 500000 | 500000 | 66780.18 | 28709.25 | 38070.93 | 433219.82
| 9488.00 | DOC 4JD New Central Office Building | Jennie E. | 0 | 4163847 | 4163847 | 633789.88 | 118003.51 | 515786.37 | 3530057.12
| 9489.00 | DOC & ASP TWID Repairs | Oliver S. | 0 | 50000 | 50000 | 21402.42 | 1350.47 | 20051.95 | 28597.58
C | 9490.00 | DOC NCF Forced Main Sewer Pipe Failure (29C20) | Brad T. | 0 | 20787.56 | 20787.56 | 20787.56 | 20787.56 | 0 | 0
| 9492.00 | ATOD Racking Modification | Oliver S. | 0 | 86150 | 86150 | 80175.17 | 15140.57 | 65034.6 | 5974.83
| 9515.00 | DPS District 1 Intel Remodel | Brandon A. | 0 | 25000 | 25000 | 2500 | 762.48 | 1737.52 | 22500
| 9517.00 | DVA IVC Columbarium And Irrigation System Expansion | Brad T. | 0 | 300000 | 300000 | 190468.62 | 0 | 190468.62 | 109531.38
|  | DA26 (MOU) Totals |  | 0 | 22178934.56 | 7888284.56 | 3095610.93 | 971059.24 | 2124551.69 | 19083323.63
21207875.32

## RECAP #9279.50
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 14275000
Shive Hattery |  | 457993 | 0 | 457993
PM TIME |  | 293189 | 264.69 | 292924.31
Misc. |  | 0 | 0 | 0
Story Construction |  | 25212.59 | 0 | 25212.59
Total Project Cost | 14275000 | 776394.59 | 264.69 | 776129.9 | 13498605.41

## #9279.50 Funds Rec'd
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400KDH122325001 | 2025-12-23 | 14275000 | 14275000
| Total Requested | 0 | Total Transferred |  |  | 14275000 | 14275000

## #9279.50 Shive Hattery
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA26-9260 |  |  | RFP927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023916 | 2026-01-23 | PO Procore | 457993 | 457993 |  |  | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  |  |  | 457993 |  | 0 | 457993
|  | Totals: | 457993 |  | 0 |  | 457993
|  | Schematic Design | 172500 |  |  |  | 172500
|  | Design Development | 159000 |  |  |  | 159000
|  | Construction Documents | 112681 |  |  |  | 112681
|  | Bidding Assistance | 13812 |  |  |  | 13812
|  | Total: | 457993 |  | 0 |  | 457993

## #9279.50 PM TIME
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 735I
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 293189 | 293189 |  |  | 293189
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 0 | 116.55 | 116.55 | 293072.45
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 0 | 741.5 | 858.05 | 292330.95
CDE 33526352902 | 2025-12-18 | 2507 | Moving expense from 9279.50 to 9279.40 |  | 0 | -116.55 | 741.5 | 292447.5
CDE 33526352902 | 2025-12-18 | 9500 | Moving expense from 9279.50 to 9279.40 |  | 0 | -741.5 | 0 | 293189
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 21.39 | 21.39 | 293167.61
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 243.3 | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
[5 empty] | 0 |  | 264.69 | 292924.31
|  |  | Totals: | 293189 |  | 264.69 |  | 292924.31
Note on E9: Kleene, Jennifer 9:21 AM (3 minutes ago) to me Please create a DAS Costs budget of $293,189.00 for DA26 9279.50. Regards, Jennifer Jennifer Kleene

## #9279.50 Misc
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9279.50 StoryConstruction
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA26-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030914 | 2026-01-30 | PO Procore | 25212.59 | 25212.59 |  |  | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  |  |  | 25212.59 |  | 0 | 25212.59
|  | Totals: | 25212.59 |  | 0 |  | 25212.59
|  | CM Service | 25124.09 |  |  |  | 25124.09
|  | Reimbursables | 88.5 |  |  |  | 88.5
|  | Total: | 25212.59 |  | 0 |  | 25212.59

## RECAP #9438.00
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 15650
Jasper Construction |  | 15316.75 | 0 | 15316.75
PM TIME |  | 0 | 0 | 0
Misc. |  | 182.45 | 182.45 | 0
Total Project Cost | 15650 | 15499.2 | 182.45 | 15316.75 | 150.8

## #9438.00 Funds Rec'd
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25208202502 | 2025-08-21 | 15650 | 15650
| Total Requested | 0 | Total Transferred |  |  | 15650 | 15650

## #9438.00 Jasper Construction
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Jasper Construction |  |  | Vendor: 00003016436
Acct. Codes-0506-335-DA26-9255 |  |  | RFQ943800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266902 | 2025-09-23 | PO Procore | 14182.75 | 14182.75 |  |  | 14182.75
PO 33526266902 | 2025-11-18 | CO #1(Split w/ DA26) | 1134 | 15316.75 |  | 0 | 15316.75
PO 33526266902 | 2026-01-12 | CO #2(100% to MM23) | 0 | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  |  |  | 15316.75 |  | 0 | 15316.75
|  | Totals: | 15316.75 |  | 0 |  | 15316.75
|  | MM23 | 48451.25 |  | 0 |  | 48451.25
|  | Total: | 63768 |  | 0 |  | 63768

## #9438.00 PM TIME
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 734H
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget |  | 0 |  |  | 0
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 32.85 | 32.85 | -32.85
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 371.8 | 404.65 | -404.65
CDE 33526021906 | 2026-01-21 | 2507 | Moving December Time to MM23 |  | 0 | -32.85 | 371.8 | -371.8
CDE 33526021906 | 2026-01-21 | 9500 | Moving December Time to MM23 |  | 0 | -371.8 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9438.00 Misc
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526349902 | 2025-12-15 | 9500 | CNST | Team Services V#(00002121153) | Inv. 1825258-0 | 182.45 | 182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
|  |  |  | Totals: |  | 182.45

## RECAP #9471.00
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 27500
Midstate Plumbing |  | 24537 | 13230.65 | 11306.35
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 27500 | 24537 | 13230.65 | 11306.35 | 2963

## #9471.00 Funds Rec'd
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25208072504 | 2025-08-12 | 27500 | 27500
| Total Requested | 0 | Total Transferred |  |  | 27500 | 27500

## #9471.00 MidState Plumbing
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Midstate Plumbing |  |  | Vendor: 00002108635
Acct. Codes-0506-335-DA26-9255 |  |  | RFB947100-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526226907 | 2025-08-14 | PO Procore | 24537 | 24537 |  |  | 24537
PRC 3352622PA6907 | 2025-12-22 | Inv. P38754(Split w/MM24) |  | 24537 | 1070.65 | 1070.65 | 23466.35 | 56.35
PRC 3352622PB6907 | 2025-12-29 | Inv. P39138(Split w/MM24) |  | 24537 | 7600 | 8670.65 | 15866.35 | 456.35
PRC 3352622PC6907 | 2026-01-09 | Inv. P39249(100% to MM24) |  | 24537 | 0 | 8670.65 | 15866.35 | 456.35
PRC 3352622PD6907 | 2026-01-30 | Inv. P39322(Split w/MM24) |  | 24537 | 4560 | 13230.65 | 11306.35 | 696.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  |  |  | 24537 |  | 13230.65 | 11306.35
|  | Totals: | 24537 |  | 13230.65 |  | 11306.35
|  | MM23 | 124741 |  | 56031 |  | 68710
|  | Total: | 149278 |  | 69261.65 |  | 80016.35

## #9471.00 PM TIME
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 734B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9471.00 Misc
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9480.01
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
| Program code 948001 |  |  | Major Program 3D02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 265000
| TB Rigid Edge Exteriors |  | 98835.19 | 72339.73 | 26495.46
| PM TIME |  | 10000 | 8105.88 | 1894.12
| Misc. |  | 0 | 0 | 0
| Genesis Architectural |  | 16700 | 13950 | 2750
| McGough Construction |  | 30122 | 26362.92 | 3759.08
| Hilsabeck Schacht |  | 29700 | 28809 | 891
C | MTS Contracting |  | 3518.11 | 3518.11 | 0
C | Kinzler Construction |  | 55876 | 55876 | 0
| Total Project Cost | 265000 | 244751.3 | 208961.64 | 35789.66 | 20248.7

## #9480.01 Funds Rec'd
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL26216003 | 2025-08-06 | 230000 | 230000
|  |  | MOU Amendment #1 | IET 400EL26274001 | 2025-10-02 | 35000 | 35000
| Total Requested | 0 | Total Transferred |  |  | 265000 | 265000

## #9480.01 TB Rigid Edge Exterior
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
TB Rigid Edge Exteriors |  |  | Vendor: 00003193199
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526230902 | 2025-08-18 | PO Procore | 70820.24 | 70820.24 |  |  | 70820.24
PO 33526230902 | 2025-09-16 | CO #1 | 4076.18 | 74896.42 |  | 0 | 74896.42
PO 33526230902 | 2025-10-21 | CO #2 | 23398.77 | 98295.19 |  | 0 | 98295.19
PO 33526230902 | 2025-12-23 | CO #3 | 540 | 98835.19 |  | 0 | 98835.19
PRC 3352623PA0902 | 2026-01-21 | Inv. 9480.01-001 |  | 98835.19 | 72339.73 | 72339.73 | 26495.46 | 2237.32
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  |  |  | 98835.19 |  | 72339.73 | 26495.46
|  | Totals: | 98835.19 |  | 72339.73 |  | 26495.46
Retainage 3%

## #9480.01 PM TIME
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 733M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
CDE 33526262901 | 2025-09-18 | 9500 | Moving Expense from 9480.00 |  | 10000 | 1355.98 | 1355.98 | 8644.02
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10000 | 527.07 | 1883.05 | 8116.95
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10000 | 2712.3 | 4595.35 | 5404.65
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 113.05 | 4708.4 | 5291.6
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 1116.8 | 5825.2 | 4174.8
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | 187.5 | 6012.7 | 3987.3
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 1193.7 | 7206.4 | 2793.6
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10000 | 72.78 | 7279.18 | 2720.82
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10000 | 826.7 | 8105.88 | 1894.12
[5 empty] | 10000 |  | 8105.88 | 1894.12
[5 empty] | 10000 |  | 8105.88 | 1894.12
[5 empty] | 10000 |  | 8105.88 | 1894.12
|  |  | Totals: | 10000 |  | 8105.88 |  | 1894.12
Note on E9: Jurgenson, John [DAS]: DAS Costs Budget for DA26 9480.01 Inbox Kleene, Jennifer 2:58 PM (2 minutes ago) to me Please create a DAS Costs budget for $4,000.00 for DA26 9480.01. Regards, Jennifer DAS Cost Budget Increases $Joni Kleene, Jennifer 9:49 AM (1 minute ago) to me Please increase the DAS Cost budget for MM24 9277.00 by $3,000.00 Please increase the DAS Cost budget for DA26 9480.01 by $2,000.00

## #9480.01 Misc
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9480.01 Genesis Architectural
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split w/DA25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526181901 | 2025-08-22 | CO #1 Opening in DA26 | 16700 | 16700 |  |  | 16700
PRC 3352618PB1901 | 2025-09-23 | Inv. 2503-02(Split w/DA25) |  | 16700 | 7810 | 7810 | 8890
PO 33526181901 | 2025-12-15 | Closed PO to correct accounting lines link |  | 16700 |  | 7810 | 8890
PO 33526181901A | 2025-12-15 | ReOpened PO To correct links in IA |  | 16700 |  | 7810 | 8890
PRC 3352618PC1901A | 2025-12-15 | Inv. 2503-03 |  | 16700 | 6140 | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  |  |  | 16700 |  | 13950 | 2750
|  | Totals: | 16700 |  | 13950 |  | 2750
|  | DA25 Closed 09/23/25 | 10750 |  | 10750 |  | 0
|  | Total: | 27450 |  | 24700 |  | 2750

## #9480.01 McGough Construction
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Mc Gough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGought11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526252403 | 2025-09-09 | PO Procore | 30122 | 30122 |  |  | 30122
PRC 3352625PA2403 | 2025-09-16 | Inv. 101368.011-CA01 |  | 30122 | 2589.8 | 2589.8 | 27532.2
PRC 3352625PB2403 | 2025-10-16 | Inv. 101368.011-CA02 |  | 30122 | 9881.74 | 12471.54 | 17650.46
PRC 3352625PC2403 | 2025-11-17 | Inv. 101368.011-CA03 |  | 30122 | 9467.15 | 21938.69 | 8183.31
PRC 3352625PD2403 | 2025-12-10 | Inv. 101368.011-CA04 |  | 30122 | 3417.43 | 25356.12 | 4765.88
PRC 3352625PE2403 | 2026-01-09 | Inv. 101368.011-CA05 |  | 30122 | 1006.8 | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  |  |  | 30122 |  | 26362.92 | 3759.08
|  | Totals: | 30122 |  | 26362.92 |  | 3759.08
|  | CM Services | 29082 |  | 25482.92 |  | 3599.08
|  | Reimbursables | 1040 |  | 880 |  | 160
|  | Total: | 30122 |  | 26362.92 |  | 3759.08

## #9480.01 Hilsabeck Schacht
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526272906 | 2025-09-29 | PO Procore | 29700 | 29700 |  |  | 29700
PRC 3352627PA2906 | 2025-11-04 | Inv. HS2172 |  | 29700 | 21940.43 | 21940.43 | 7759.57 | 678.57
PRC 3352627PB2906 | 2025-12-03 | Inv. 9480.01-02 |  | 29700 | 5898.57 | 27839 | 1861 | 861
PRC 3352627PC2906 | 2026-01-26 | Inv. 9480.01-03 |  | 29700 | 970 | 28809 | 891 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  |  |  | 29700 |  | 28809 | 891
|  | Totals: | 29700 |  | 28809 |  | 891

## #9480.01 MTS Contracting
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0506-335-DA26-9255 |  |  | MA00520243D
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526272908 | 2025-09-29 | PO Procore | 4907.48 | 4907.48 |  |  | 4907.48
PRC 3352627PA2908 | 2025-12-16 | Inv. 25-6194 - FINAL | -1389.37 | 3518.11 | 3518.11 | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  | Totals: | 3518.11 |  | 3518.11 |  | 0 | FINAL
|  | Tuckpointing | 1874.5 |  | 1874.5 |  | 0
|  | Materials & Supplies | 1643.61 |  | 1643.61 |  | 0
|  | Total: | 3518.11 |  | 3518.11 |  | 0

## #9480.01 Kinzler Construction
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Kinzler Construction |  |  | Vendor: 00003169106
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526273902 | 2025-09-30 | PO Procore | 57958 | 57958 |  |  | 57958
PO 33526273902 | 2025-10-20 | CO #1 | -2082 | 55876 |  | 0 | 55876
PRC 3352627PA3902 | 2025-11-24 | Inv. 2519028 |  | 55876 | 53229.72 | 53229.72 | 2646.28 | 1646.28
PRC 3352627PB3902 | 2025-12-04 | Inv. 2519028.0014 |  | 55876 | 970 | 54199.72 | 1676.28 | 1676.28
PRC 3352627PC3902 | 2026-01-20 | Inv. 9480.01-Retainage |  | 55876 | 1676.28 | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  | Totals: | 55876 |  | 55876 |  | 0 | FINAL

## RECAP #9481.00
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1400000
VendorA |  | 0 | 0 | 0
PM TIME |  | 10000 | 2651.49 | 7348.51
Misc. |  | 783.75 | 783.75 | 0
Total Project Cost | 1400000 | 10783.75 | 3435.24 | 7348.51 | 1389216.25

## #9481.00 Funds Rec'd
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812V26001 | 2025-07-29 | 1400000 | 1400000
| Total Requested | 0 | Total Transferred |  |  | 1400000 | 1400000

## #9481.00 Vendor A
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9481.00 PM TIME
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733O
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 300.34 | 300.34 | 9699.66
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 571.2 | 871.54 | 9128.46
CDE 33526317909 | 2025-11-13 | 2507 | Moving PM Time from 9481.00 DA26 to 9997.26 MM26 |  | 10000 | -300.34 | 571.2 | 9428.8
CDE 33526317909 | 2025-11-13 | 9500 | Moving PM Time from 9481.00 DA26 to 9997.26 MM26 |  | 10000 | -571.2 | 0 | 10000
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | -5.66 | -5.66 | 10005.66
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 1308.2 | 1302.54 | 8697.46
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10000 | 108.95 | 1411.49 | 8588.51
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10000 | 1240 | 2651.49 | 7348.51
[5 empty] | 10000 |  | 2651.49 | 7348.51
[5 empty] | 10000 |  | 2651.49 | 7348.51
[5 empty] | 10000 |  | 2651.49 | 7348.51
[5 empty] | 10000 |  | 2651.49 | 7348.51
|  |  | Totals: | 10000 |  | 2651.49 |  | 7348.51
Note on E9: Huggins, Joni [DAS]: Adams, Brandon 1:51 PM (1 hour ago) to me DA24 9414.00 (3,176.95) increase by $6,000 DA26 9481.00 (1302.54) set pm budget at $10,000 MM23 9450.00 (491.54) increase by $491.54 and close MM25 9442.00 (1,198.60) increase by $2,000 Regards, Brandon Adams

## #9481.00 Misc
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202601115300001 | 2025-08-07 | 2507 |  | Space Planning Services July 1-31,2025 | Inv. DAS2026011153 | 570 | 570
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Space Planning Services August 1-31,2025 | Inv. DAS2026021153 | 166.25 | 736.25
IET DAS202604115300001 | 2025-11-07 | 2507 |  | Space Planning Services October 1-31,2025 | Inv. DAS2026041153 | 47.5 | 783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
|  |  |  | Totals: |  | 783.75

## RECAP #9482.00
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 50000
McGough Construction |  | 8969.4 | 7433.91 | 1535.49
PM TIME |  | 8000 | 7407.62 | 592.38
Misc. |  | 0 | 0 | 0
KCL Engineering |  | 30090 | 9990 | 20100
Systems Management |  | 1240 | 0 | 1240
Total Project Cost | 50000 | 48299.4 | 24831.53 | 23467.87 | 1700.6

## #9482.00 Funds Rec'd
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 13150026212001 | 2025-07-31 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9482.00 McGough Construction
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526223900 | 2025-08-11 | PO Procore | 8969.4 | 8969.4 |  |  | 8969.4
PRC 3352622PA3900 | 2025-09-12 | Inv. 101368.012-PC01 |  | 8969.4 | 1188 | 1188 | 7781.4
PRC 3352622PB3900 | 2025-10-14 | Inv. 101368.012-PC02 |  | 8969.4 | 1360.26 | 2548.26 | 6421.14
PRC 3352622PC3900 | 2025-11-06 | Inv. 101368.012-PC03 |  | 8969.4 | 1226.61 | 3774.87 | 5194.53
PRC 3352622PD3900 | 2025-12-11 | Inv. 101368.012-PC04 |  | 8969.4 | 1630.53 | 5405.4 | 3564
PRC 3352622PE3900 | 2026-01-12 | Inv. 101368.012-PC05 |  | 8969.4 | 2028.51 | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  |  |  | 8969.4 |  | 7433.91 | 1535.49
|  | Totals: | 8969.4 |  | 7433.91 |  | 1535.49

## #9482.00 PM TIME
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S. |  |  |  | eDAS: 733P
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 8000 | 57.26 | 57.26 | 7942.74
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 8000 | 631.8 | 689.06 | 7310.94
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 8000 | 84.01 | 773.07 | 7226.93
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 8000 | 645.1 | 1418.17 | 6581.83
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 8000 | 146.86 | 1565.03 | 6434.97
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 8000 | 755.5 | 2320.53 | 5679.47
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8000 | 239.96 | 2560.49 | 5439.51
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8000 | 2379.7 | 4940.19 | 3059.81
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 8000 | 180.55 | 5120.74 | 2879.26
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 8000 | 1150.5 | 6271.24 | 1728.76
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 8000 | 92.08 | 6363.32 | 1636.68
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 8000 | 1044.3 | 7407.62 | 592.38
[5 empty] | 8000 |  | 7407.62 | 592.38
[5 empty] | 8000 |  | 7407.62 | 592.38
[5 empty] | 8000 |  | 7407.62 | 592.38
[5 empty] | 8000 |  | 7407.62 | 592.38
[5 empty] | 8000 |  | 7407.62 | 592.38
|  |  | Totals: | 8000 |  | 7407.62 |  | 592.38
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 2:04 PM (2 minutes ago) to me Could you please add $3000.00 to the PM time budget from the unallocated funds in project 9482.00? Thank you very much! -- Oliver Shimp, PE

## #9482.00 Misc
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S. |  |  |  | Shipping Code: 403
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9482.00 KCL Engineering
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948200-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266903 | 2025-09-23 | PO Procore | 30090 | 30090 |  |  | 30090
PRC 3352626PA6903 | 2025-11-20 | Inv. 12870 |  | 30090 | 9990 | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  |  |  | 30090 |  | 9990 | 20100
|  | Totals: | 30090 |  | 9990 |  | 20100
|  | Design Development Docs | 9990 |  | 9990 |  | 0
|  | Construction Docs | 20100 |  |  |  | 20100
|  | Total: | 30090 |  | 9990 |  | 20100

## #9482.00 Systems Management
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Systems Management |  |  | Vendor: 00003202455
Acct. Codes-0506-335-DA26-9255 |  |  | SRVV5
Project Manager - Oliver S. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526006903 | 2026-01-06 | PO Procore | 1240 | 1240 |  |  | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  |  |  | 1240 |  | 0 | 1240
|  | Totals: | 1240 |  | 0 |  | 1240

## RECAP #9486.00
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
| Program code 948600 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1000000
C | DCI Group |  | 5949.11 | 5949.11 | 0
| PM TIME |  | 30000 | 3958.38 | 26041.62
| Misc. |  | 0 | 0 | 0
| Ralph N Smith Flooring |  | 795373 | 509733 | 285640
| DCI Group (2) |  | 128119.75 | 15758.71 | 112361.04
| Total Project Cost | 1000000 | 959441.86 | 535399.2 | 424042.66 | 40558.14

## #9486.00 Funds Rec'd
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925401 | 2025-07-29 | 1000000 | 1000000
0
| Total Requested | 0 | Total Transferred |  |  | 1000000 | 1000000

## #9486.00 DCI Group
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255902 | 2025-09-12 | PO Procore | 6725.74 | 6725.74 |  |  | 6725.74
PRC 3352625PA5902 | 2025-10-13 | Inv. 25-023 PC 01 |  | 6725.74 | 2488.21 | 2488.21 | 4237.53
PRC 3352625PB5902 | 2025-12-03 | Inv. 25-023 PC 02 FINAL | -776.63 | 5949.11 | 3460.9 | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  | Totals: | 5949.11 |  | 5949.11 |  | 0 | FINAL

## #9486.00 PM TIME
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 30000 | 30000 |  |  | 30000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 30000 | 33.7 | 33.7 | 29966.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 30000 | 368.8 | 402.5 | 29597.5
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 30000 | 94.58 | 497.08 | 29502.92
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 30000 | 732.6 | 1229.68 | 28770.32
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 30000 | 91.24 | 1320.92 | 28679.08
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 30000 | 474.7 | 1795.62 | 28204.38
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 30000 | 71.84 | 1867.46 | 28132.54
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 30000 | 712.1 | 2579.56 | 27420.44
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 30000 | 72.16 | 2651.72 | 27348.28
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 30000 | 460.4 | 3112.12 | 26887.88
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 30000 | 68.26 | 3180.38 | 26819.62
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 30000 | 778 | 3958.38 | 26041.62
[5 empty] | 30000 |  | 3958.38 | 26041.62
[5 empty] | 30000 |  | 3958.38 | 26041.62
[5 empty] | 30000 |  | 3958.38 | 26041.62
[5 empty] | 30000 |  | 3958.38 | 26041.62
[5 empty] | 30000 |  | 3958.38 | 26041.62
|  |  | Totals: | 30000 |  | 3958.38 |  | 26041.62
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9486.00 Misc
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9486.00 Ralph N Smith Flooring
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Ralph N Smith Flooring |  |  | Vendor: 00002106937
Acct. Codes-0506-335-DA26-9255 |  |  | MA #21175A
Project Manager - Brandon A |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526273904 | 2025-09-30 | DO Procore | 783113 | 783113 |  |  | 783113
PRC 3352627PA3904 | 2025-10-31 | Inv. 9486.00-01 |  | 783113 | 293919 | 293919 | 489194
DO 33526273904 | 2025-12-05 | CO #1 | 12260 | 795373 |  | 293919 | 501454
PRC 3352627PB3904 | 2025-12-29 | Inv. 9486.00-02 |  | 795373 | 116843 | 410762 | 384611
PRC 3352627PC3904 | 2026-01-16 | Inv. 9486.00-03 |  | 795373 | 98971 | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  |  |  | 795373 |  | 509733 | 285640
|  | Totals: | 795373 |  | 509733 |  | 285640

## #9486.00 DCI Group (2)
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
DCI Group(2) |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310903 | 2025-11-06 | PO Procore | 128119.75 | 128119.75 |  |  | 128119.75
PRC 3352631PA0903 | 2025-12-23 | Inv. 25-023 CA 01 |  | 128119.75 | 5787.75 | 5787.75 | 122332
PRC 3352631PB0903 | 2026-01-26 | Inv. 25-023 CA-02 |  | 128119.75 | 9970.96 | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  |  |  | 128119.75 |  | 15758.71 | 112361.04
|  | Totals: | 128119.75 |  | 15758.71 |  | 112361.04
|  | CM Staff Hours | 83964.1 |  | 11585.65 |  | 72378.45
|  | Reimbursables | 5000 |  | 257.5 |  | 4742.5
|  | CM Fee | 39155.65 |  | 3915.56 |  | 35240.09
|  | Total: | 128119.75 |  | 15758.71 |  | 112361.04

## RECAP #9487.00
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 500000
DCI Group |  | 29130.18 | 11297.7 | 17832.48
PM TIME |  | 20000 | 4481.55 | 15518.45
Misc. |  | 0 | 0 | 0
Genesis Architectural |  | 13500 | 12930 | 570
Genesis Architectural (2) |  | 4150 | 0 | 4150
Total Project Cost | 500000 | 66780.18 | 28709.25 | 38070.93 | 433219.82

## #9487.00 Funds Rec'd
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925400 | 2025-07-29 | 500000 | 500000
| Total Requested | 0 | Total Transferred |  |  | 500000 | 500000

## #9487.00 DCI Group
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255904 | 2025-09-12 | PO Procore | 29130.18 | 29130.18 |  |  | 29130.18
PRC 3352625PA5904 | 2025-12-03 | Inv. 25-024PC 01 |  | 29130.18 | 7266.66 | 7266.66 | 21863.52
PRC 3352625PB5904 | 2025-12-23 | Inv. 25-024 PC 02 |  | 29130.18 | 1220.22 | 8486.88 | 20643.3
PRC 3352625PC5904 | 2026-01-26 | Inv. 25-024 PC 03 |  | 29130.18 | 2810.82 | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  |  |  | 29130.18 |  | 11297.7 | 17832.48
|  | Totals: | 29130.18 |  | 11297.7 |  | 17832.48
|  | CM Services | 28130.18 |  | 11091.7 |  | 17038.48
|  | Reimbursables | 1000 |  | 206 |  | 794
|  | Total: | 29130.18 |  | 11297.7 |  | 17832.48

## #9487.00 PM TIME
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 733U
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 33.7 | 33.7 | 19966.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 368.8 | 402.5 | 19597.5
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 99.87 | 502.37 | 19497.63
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 776.9 | 1279.27 | 18720.73
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 127.29 | 1406.56 | 18593.44
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 666.1 | 2072.66 | 17927.34
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 79.99 | 2152.65 | 17847.35
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 794.7 | 2947.35 | 17052.65
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 59.49 | 3006.84 | 16993.16
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 377.3 | 3384.14 | 16615.86
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 89.21 | 3473.35 | 16526.65
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 1008.2 | 4481.55 | 15518.45
[5 empty] | 20000 |  | 4481.55 | 15518.45
[5 empty] | 20000 |  | 4481.55 | 15518.45
[5 empty] | 20000 |  | 4481.55 | 15518.45
[5 empty] | 20000 |  | 4481.55 | 15518.45
[5 empty] | 20000 |  | 4481.55 | 15518.45
|  |  | Totals: | 20000 |  | 4481.55 |  | 15518.45
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9487.00 Misc
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9487.00 Genesis Architectural
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP 948700-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526275905 | 2025-10-03 | PO Procore | 13500 | 13500 |  |  | 13500
PRC 3352627PA5905 | 2025-12-03 | Inv. 2515-01 |  | 13500 | 7020 | 7020 | 6480
PRC 3352627PB5905 | 2025-12-15 | Inv. 2515-02 |  | 13500 | 5910 | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  |  |  | 13500 |  | 12930 | 570
|  | Totals: | 13500 |  | 12930 |  | 570
|  | 50% Schematic Phase | 7800 |  | 7800 |  | 0
|  | 100% Schematic Phase | 5700 |  | 5130 |  | 570
|  | Total: | 13500 |  | 12930 |  | 570

## #9487.00 Genesis Architectu (2)
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Genesis Architectural (2) |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP 948700-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030915 | 2026-01-30 | PO Procore | 4150 | 4150 |  |  | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  |  |  | 4150 |  | 0 | 4150
|  | Totals: | 4150 |  | 0 |  | 4150

## RECAP #9488.00
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 4163847
Samuels Group |  | 71389.88 | 17076.17 | 54313.71
PM TIME |  | 145000 | 8767.34 | 136232.66
Misc. |  | 0 | 0 | 0
SVPA Architects |  | 417400 | 92160 | 325240
Total Project Cost | 4163847 | 633789.88 | 118003.51 | 515786.37 | 3530057.12

## #9488.00 Funds Rec'd
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26001 | 2025-08-15 | 4163847 | 4163847
| Total Requested | 0 | Total Transferred |  |  | 4163847 | 4163847

## #9488.00 Samuels Group
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526273900 | 2025-09-30 | PO Procore | 71389.88 | 71389.88 |  |  | 71389.88
PRC 3352627PA3900 | 2025-12-04 | Inv. 7813.01948800 |  | 71389.88 | 2720.91 | 2720.91 | 68668.97
PRC 3352627PB3900 | 2026-01-09 | Inv. 7813.02948800 |  | 71389.88 | 14355.26 | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  |  |  | 71389.88 |  | 17076.17 | 54313.71
|  | Totals: | 71389.88 |  | 17076.17 |  | 54313.71
|  | CM Services | 63389.88 |  | 16955.17 |  | 46434.71
|  | Reimbursables | 1000 |  | 121 |  | 879
|  | Reimbursables(Geotechnical) | 7000 |  |  |  | 7000
|  | Total: | 71389.88 |  | 17076.17 |  | 54313.71

## #9488.00 PM TIME
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 733W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 145000 | 145000 |  |  | 145000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 85.66 | 85.66 | 144914.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 657.1 | 742.76 | 144257.24
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 0 | 132.45 | 875.21 | 144124.79
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 0 | 681.1 | 1556.31 | 143443.69
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 0 | 212.65 | 1768.96 | 143231.04
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 0 | 2112.8 | 3881.76 | 141118.24
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 0 | 286.09 | 4167.85 | 140832.15
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 0 | 1818.7 | 5986.55 | 139013.45
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 225.29 | 6211.84 | 138788.16
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 2555.5 | 8767.34 | 136232.66
[5 empty] | 0 |  | 8767.34 | 136232.66
[5 empty] | 0 |  | 8767.34 | 136232.66
[5 empty] | 0 |  | 8767.34 | 136232.66
[5 empty] | 0 |  | 8767.34 | 136232.66
|  |  | Totals: | 145000 |  | 8767.34 |  | 136232.66
Note on E9: On Sat, Sep 20, 2025 at 2:15 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Sorry about that, Please establish DAS time for $145,000.00 in 9488.00. Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau

## #9488.00 Misc
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code: B90
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9488.00 SVPA Architects
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
SVPA Architects |  |  | Vendor: 00002109254
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948800-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310900 | 2025-11-06 | PO Procore | 417400 | 417400 |  |  | 417400
PRC 3352631PA0900 | 2025-12-16 | Inv. 0041003 |  | 417400 | 49030 | 49030 | 368370
PRC 3352631PB0900 | 2026-01-26 | Inv. 0041049 |  | 417400 | 43130 | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  |  |  | 417400 |  | 92160 | 325240
|  | Totals: | 417400 |  | 92160 |  | 325240
|  | Scematic Design | 72800 |  | 72800 |  | 0
|  | Desgin Development | 54600 |  | 10920 |  | 43680
|  | Construction Documents | 145600 |  |  |  | 145600
|  | Bidding/ Negotiation | 18200 |  |  |  | 18200
|  | Construction Admin | 72800 |  |  |  | 72800
|  | Furniture | 16000 |  |  |  | 16000
|  | Renovation Schematic Design | 21400 |  | 8440 |  | 12960
|  | Renovation Design Development | 16000 |  |  |  | 16000
|  | Total: | 417400 |  | 92160 |  | 325240

## RECAP #9489.00
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 50000
McGough Construction |  | 16402.42 | 0 | 16402.42
PM TIME |  | 5000 | 1350.47 | 3649.53
Misc. |  | 0 | 0 | 0
Total Project Cost | 50000 | 21402.42 | 1350.47 | 20051.95 | 28597.58

## #9489.00 Funds Rec'd
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Oliver S
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26002 | 2025-08-19 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9489.00 McGough Construction
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526279900 | 2025-10-06 | PO Procore | 16402.42 | 16402.42 |  |  | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  |  |  | 16402.42 |  | 0 | 16402.42
|  | Totals: | 16402.42 |  | 0 |  | 16402.42
|  | CM Services | 15472.42 |  |  |  | 15472.42
|  | Reimbursables | 930 |  |  |  | 930
|  | Total: | 16402.42 |  | 0 |  | 16402.42

## #9489.00 PM TIME
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S |  |  |  | eDAS: 734A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 54.39 | 54.39 | 4945.61
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 415.5 | 469.89 | 4530.11
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 0 | 28.98 | 498.87 | 4501.13
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 0 | 286.6 | 785.47 | 4214.53
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 0 | 12.23 | 797.7 | 4202.3
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 0 | 79.3 | 877 | 4123
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 38.27 | 915.27 | 4084.73
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 435.2 | 1350.47 | 3649.53
[5 empty] | 0 |  | 1350.47 | 3649.53
[5 empty] | 0 |  | 1350.47 | 3649.53
[5 empty] | 0 |  | 1350.47 | 3649.53
[5 empty] | 0 |  | 1350.47 | 3649.53
|  |  | Totals: | 5000 |  | 1350.47 |  | 3649.53
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (23 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon.

## #9489.00 Misc
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S |  |  |  | Shipping Code: 163
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9490.00
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
| Program code 949000 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 20787.56
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 2127.56 | 2127.56 | -4.5475e-13
C | Misc. |  | 18660 | 18660 | 0
| Total Project Cost | 20787.56 | 20787.56 | 20787.56 | 0 | 0
Closed 11/12/25

## #9490.00 Funds Rec'd
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 245269490 | 2025-08-29 | 25000 | 25000
|  |  | Return funds to agency- closing program | IET 33526316900 | 2025-11-12 | -4212.44 | -4212.44
| Total Requested | 0 | Total Transferred |  |  | 20787.56 | 20787.56

## #9490.00 Vendor A
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9490.00 PM TIME
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 734C
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2127.56 | 2127.56 |  |  | 2127.56
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 94.58 | 94.58 | 2032.98
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 732.6 | 827.18 | 1300.38
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 0 | 127.29 | 954.47 | 1173.09
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 0 | 666.1 | 1620.57 | 506.99
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 0 | 46.49 | 1667.06 | 460.5
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 0 | 460.5 | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
[5 empty] | 0 |  | 2127.56 | 1.1369e-13
|  |  | Totals: | 2127.56 |  | 2127.56 |  | -4.5475e-13
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9490.00 Misc
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526259906 | 2025-09-16 | 9500 | DSGN | Shive Hattery V#(00002108803) | Inv. 2250015060-1 | 14700 | 14700
GAX 33526294900 | 2025-10-21 | 9500 | DSGN | Shive Hattery V#(00002108803) | Inv. 2250015060-2 | 3960 | 18660
18660
18660
18660
18660
18660
18660
18660
18660
18660
18660
|  |  |  | Totals: |  | 18660

## RECAP #9492.00
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 86150
Samuels Group |  | 14675.17 | 10047.18 | 4627.99
PM TIME |  | 8000 | 5093.39 | 2906.61
Misc. |  | 0 | 0 | 0
Quick Enterprise LLC |  | 57500 | 0 | 57500
Total Project Cost | 86150 | 80175.17 | 15140.57 | 65034.6 | 5974.83

## #9492.00 Funds Rec'd
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DAS9492RACKING | 2025-09-18 | 86150 | 86150
| Total Requested | 0 | Total Transferred |  |  | 86150 | 86150

## #9492.00 Samuels Group
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526269901 | 2025-09-26 | PO Procore | 14675.17 | 14675.17 |  |  | 14675.17
PRC 3352626PA9901 | 2025-12-11 | Inv. 7815.00 CA |  | 14675.17 | 8361.58 | 8361.58 | 6313.59
PRC 3352626PB9901 | 2026-01-14 | Inv. 7815.01 CA |  | 14675.17 | 1685.6 | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  |  |  | 14675.17 |  | 10047.18 | 4627.99
|  | Totals: | 14675.17 |  | 10047.18 |  | 4627.99

## #9492.00 PM TIME
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S. |  |  |  | eDAS: 911G
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 36.12 | 36.12 | 7963.88
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 276.6 | 312.72 | 7687.28
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 0 | 117.29 | 430.01 | 7569.99
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 0 | 604.5 | 1034.51 | 6965.49
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 0 | 115.91 | 1150.42 | 6849.58
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 0 | 1149.1 | 2299.52 | 5700.48
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 0 | 199.27 | 2498.79 | 5501.21
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 0 | 1269.7 | 3768.49 | 4231.51
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 107.3 | 3875.79 | 4124.21
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 1217.6 | 5093.39 | 2906.61
[5 empty] | 0 |  | 5093.39 | 2906.61
[5 empty] | 0 |  | 5093.39 | 2906.61
[5 empty] | 0 |  | 5093.39 | 2906.61
[5 empty] | 0 |  | 5093.39 | 2906.61
[5 empty] | 0 |  | 5093.39 | 2906.61
|  |  | Totals: | 8000 |  | 5093.39 |  | 2906.61
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (24 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon. Re: December PM Time has been posted $Joni Shimp, Oliver 11:37 AM (1 hour ago) to me For my projects could you please, 5800 9473.00, Add $5,000.00 from unallocated to PM time. DA26 9492.00, Add $3,000.00 from unallocated to PM time. MM24 9386.01, Add $6,000.00 from unallocated to PM time. Thank you! Oliver

## #9492.00 Misc
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S. |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9492.00 Quick Enterprise LLC
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Quick Enterprise LLC |  |  | Vendor: 00003198873
Acct. Codes-0506-335-DA26-9255 |  |  | RFQ949200-01
Project Manager - Oliver S. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526309900 | 2025-11-05 | PO Procore | 27500 | 27500 |  |  | 27500
PO 33526309900 | 2025-12-10 | CO #1 | 30000 | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  |  |  | 57500 |  | 0 | 57500
|  | Totals: | 57500 |  | 0 |  | 57500

## RECAP #9515.00
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 25000
VendorA |  | 0 | 0 | 0
PM TIME |  | 2500 | 762.48 | 1737.52
Misc. |  | 0 | 0 | 0
Total Project Cost | 25000 | 2500 | 762.48 | 1737.52 | 22500

## #9515.00 Funds Rec'd
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 33528JA26KAS0126 | 2026-01-28 | 25000 | 25000
| Total Requested | 0 | Total Transferred |  |  | 25000 | 25000

## #9515.00 Vendor A
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9515.00 PM TIME
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  |  | Major Program 4E08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 735M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2500 | 2500 |  |  | 2500
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 62.08 | 62.08 | 2437.92
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 700.4 | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
[5 empty] | 0 |  | 762.48 | 1737.52
|  |  | Totals: | 2500 |  | 762.48 |  | 1737.52
Note on E9: Adams, Brandon 12:33 PM (37 minutes ago) to me Please set the PM Time to $2,500. Regards,

## #9515.00 Misc
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  |  | Major Program 4E08
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9517.00
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 300000
DCI Group |  | 48848.62 | 0 | 48848.62
PM TIME |  | 15000 | 0 | 15000
Misc. |  | 0 | 0 | 0
Shive Hattery |  | 126620 | 0 | 126620
Total Project Cost | 300000 | 190468.62 | 0 | 190468.62 | 109531.38

## #9517.00 Funds Rec'd
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET010526100 | 2026-01-05 | 300000 | 300000
| Total Requested | 0 | Total Transferred |  |  | 300000 | 300000

## #9517.00 DCI Group
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526009906 | 2026-01-09 | PO Procore | 48848.62 | 48848.62 |  |  | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  |  |  | 48848.62 |  | 0 | 48848.62
|  | Totals: | 48848.62 |  | 0 |  | 48848.62
|  | CM Services | 39484.62 |  |  |  | 39484.62
|  | Reimbursables | 9000 |  |  |  | 9000
|  | Total: | 48484.62 |  | 0 |  | 48484.62

## #9517.00 PM TIME
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  |  | Major Program 4E09
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 735N
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15000 | 15000 |  |  | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
[5 empty] | 0 |  | 0 | 15000
|  |  | Totals: | 15000 |  | 0 |  | 15000

## #9517.00 Misc
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  |  | Major Program 4E09
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 1012
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9517.00 Shive Hattery
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA26-9260 |  |  | SS-0034
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526020902 | 2026-01-20 | PO Procore | 126620 | 126620 |  |  | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  |  |  | 126620 |  | 0 | 126620
|  | Totals: | 126620 |  | 0 |  | 126620
|  | Columbarium Schematic | 33540 |  |  |  | 33540
|  | Columbarium Design | 24300 |  |  |  | 24300
|  | Columbarium Document | 15800 |  |  |  | 15800
|  | Columbarium Bidding | 3180 |  |  |  | 3180
|  | Columbarium Construction | 15400 |  |  |  | 15400
|  | IVC Irrigation Water Supply Documents | 18400 |  |  |  | 18400
|  | IVC Irrigation Controls Documents | 16000 |  |  |  | 16000
|  | Total: | 126620 |  | 0 |  | 126620

## Funds Rec'd incorrectly
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | FY26 Funds recv'd for 9211.01 | IET IET091125100 | 2025-09-11 | 46034.4 | 46034.4
|  |  | Transfer Funds to Correct Unit | CDR 33526255900 | 2025-09-12 | -46034.4 | -46034.4
|  |  | MOU 9476.00 Transfer to DAS | IET 400EL26246001 | 2025-09-03 | 224341.04 | 224341.04
|  |  | Transfer Funds to Correct Unit | IET 400EL26247007 | 2025-09-04 | -224341.04 | -224341.04
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Recap
Acct. Codes-0506-335-DA26
Project Manager - XXXXXX
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Funds Rec'd
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  |  | eDAS:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - XXXXXX |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0