## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 29867344.07
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 29867344.07
|  | Less: Total Assigned |  | 19458272.28
|  | Total Unassigned / Unallocated |  | 10409071.79
DA26 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9239.04 | DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing | Brad T. | 0 | 2550299 | 2550299 | 115581.76 | 21602.46 | 93979.3 | 2434717.24
| 9279.50 | HHS WRC Campus Utility Decentralization Phase 5 | Jennifer K. | 0 | 14275000 | 14275000 | 9670112.69 | 499773.07 | 9170339.62 | 4604887.31
C | 9438.00 | DOC FDCF Warehouse Loading Dock Ramp Repairs | Jennie E. | 0 | 15499.2 | 15499.2 | 15499.2 | 15499.2 | 0 | 0
| 9471.00 | DCO FDCF Bldg G Water Heater Replacement (29C20) | Jennie E. | 0 | 27500 | 27500 | 24537 | 23310.15 | 1226.85 | 2963
| 9476.01 | HHS STS New Garage Building - Phase 2 | Jennifer K. | 0 | 270000 | 270000 | 62996.65 | 2473.97 | 60522.68 | 207003.35
| 9480.01 | HHS STS Canteen Roof Repair Construction (29C20) | Jennifer K. | 0 | 242065.68 | 242065.68 | 242065.68 | 242065.68 | 0 | 0
| 9481.00 | DOC 5JD 150 DSM St Renovation | Brandon A. | 0 | 1400000 | 1400000 | 73343.1 | 9897.54 | 63445.56 | 1326656.9
| 9482.00 | IDB - Chiller Replacement | James T. | 0 | 559000 | 559000 | 537741.36 | 69248.57 | 468492.79 | 21258.64
| 9486.00 | DVA IVH Fox and Ulery Carpet Replacement | Brad T. | 0 | 918852.06 | 918852.06 | 918852.06 | 918852.06 | 0 | 0
| 9486.01 | DVA IVH Fox and Ulery Carpet Replacement - Sound Issues | Brad T. | 0 | 81147.94 | 81147.94 | 32621.92 | 6341.01 | 26280.91 | 48526.02
| 9487.00 | DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20) | Brad T. | 0 | 1600000 | 1600000 | 1459210.76 | 111212.02 | 1347998.74 | 140789.24
| 9488.00 | DOC 4JD New Central Office Building | Jennie E. | 0 | 5663847 | 5663847 | 5528728.73 | 421177.66 | 5107551.07 | 135118.27
| 9489.00 | DOC & ASP TWID Repairs | Brandon A. | 0 | 50000 | 50000 | 9908.62 | 9780.66 | 127.96 | 40091.38
C | 9490.00 | DOC NCF Forced Main Sewer Pipe Failure (29C20) | Brad T. | 0 | 20787.56 | 20787.56 | 20787.56 | 20787.56 | 0 | 0
| 9492.00 | ATOD Racking Modification | Jennie E. | 0 | 79014.54 | 79014.54 | 79014.54 | 79014.54 | 0 | 0
| 9515.00 | DPS District 1 Intel Remodel | Brandon A. | 0 | 100000 | 100000 | 39400 | 28028.4 | 11371.6 | 60600
| 9516.00 | IDR State of Iowa Building Renovation | Jennie E. | 0 | 185000 | 185000 | 163656.75 | 1819.65 | 161837.1 | 21343.25
| 9517.00 | DVA IVC Columbarium And Irrigation System Expansion | Brad T. | 0 | 300000 | 300000 | 204664.54 | 136715.76 | 67948.78 | 95335.46
| 9532.00 | DPS-DCI ANK Room A155, A156 and A157 Renovation | James T. | 0 | 295000 | 295000 | 55662.15 | 14163.5 | 41498.65 | 239337.85
| 9534.00 | IDR ATOD Will call Ramp Replacement | Jennie E. | 0 | 274331.09 | 274331.09 | 36531.56 | 13410.9 | 23120.66 | 237799.53
| 9535.00 | HHS WRC Linden Court Bay Window Replacement | Jennifer K. | 0 | 810000 | 810000 | 65855.65 | 6177.76 | 59677.89 | 744144.35
| 9540.00 | HHS CHMHI CCUSO Strategic Space Plan Study | Jennie E. | 0 | 150000 | 150000 | 101500 | 4879.29 | 96620.71 | 48500
|  | DA26 (MOU) Totals |  | 0 | 29867344.07 | 29867344.07 | 19458272.28 | 2656231.41 | 16802040.87 | 10409071.79
27211112.66

## RECAP #9239.04
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 2550299
Samuels Group |  | 24303.12 | 0 | 24303.12
PM TIME |  | 30000 | 1299.42 | 28700.58
Misc. |  | 358.64 | 358.64 | 0
Farnsworth Group |  | 60920 | 19944.4 | 40975.6
Total Project Cost | 2550299 | 115581.76 | 21602.46 | 93979.3 | 2434717.24

## #9239.04 Funds Rec'd
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 0A8453051326 | 2026-05-14 | 2550299 | 2550299
|  |  | Funds Recvd without Program code | CDR 33526134900 | 2026-05-14 | 0 | 0
| Total Requested | 0 | Total Transferred |  |  | 2550299 | 2550299

## #9239.04 Samuels Group
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526140911 | 2026-05-20 | PO Procore | 24303.12 | 24303.12 |  |  | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  |  |  | 24303.12 |  | 0 | 24303.12
|  | Totals: | 24303.12 |  | 0 |  | 24303.12
|  | CM Services | 24003.12 |  |  |  | 24003.12
|  | Reimbursables | 300 |  |  |  | 300
|  | Total: | 24303.12 |  | 0 |  | 24303.12

## #9239.04 PM TIME
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 736P
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 30000 | 30000 |  |  | 30000
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 30000 | 97.92 | 97.92 | 29902.08
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 30000 | 1201.5 | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
[5 empty] | 30000 |  | 1299.42 | 28700.58
|  |  | Totals: | 30000 |  | 1299.42 |  | 28700.58
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tonyan, Brad ​Joni, Please set up the PM time budget on project 9239.04 as $30,000. Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9239.04 Misc
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 174
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526174921 | 2026-06-23 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV059148 | 358.64 | 358.64
358.64
358.64
358.64
358.64
358.64
358.64
358.64
358.64
358.64
358.64
358.64
|  |  |  | Totals: |  | 358.64

## #9239.04 Farnsworth Group
DOC-NCF-IPI Homes for Iowa Facility Project Phase II Fencing
Project # 9239.04
Program code 923904 |  |  | Major Program 4B01
Farnsworth Group |  |  | Vendor: 00003167963
Acct. Codes-0506-335-DA26-9260 |  |  | RFP913300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526140913 | 2026-05-20 | PO Procore | 60920 | 60920 |  |  | 60920
PRC 3352614PA0913 | 2026-06-18 | Inv. 9239.04-01 |  | 60920 | 19944.4 | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  |  |  | 60920 |  | 19944.4 | 40975.6
|  | Totals: | 60920 |  | 19944.4 |  | 40975.6
|  | Design Development | 1366 |  | 546.4 |  | 819.6
|  | Construction Docs | 48495 |  | 19398 |  | 29097
|  | Bidding & Negotiation | 1515 |  |  |  | 1515
|  | Construction Admin | 2934 |  |  |  | 2934
|  | Site Survey | 6610 |  |  |  | 6610
|  | Total: | 60920 |  | 19944.4 |  | 40975.6

## RECAP #9279.50
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
| Program code 927950 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 14275000
| Shive Hattery |  | 592782 | 454540 | 138242
| PM TIME |  | 293189 | 11046.76 | 282142.24
| Misc. |  | 626.28 | 626.28 | 0
C | Story Construction |  | 25114.78 | 25114.78 | 0
| ATC Group |  | 11861.5 | 8445.25 | 3416.25
| Van Maanen |  | 57562 | 0 | 57562
| Central Iowa Mechanical |  | 645267 | 0 | 645267
| Story Construction(2) |  | 901304.13 | 0 | 901304.13
| Earth Services & Abatement |  | 1725400 | 0 | 1725400
| Earth Services & Abatement(2) |  | 459375 | 0 | 459375
| Breiholz Construction |  | 1286134 | 0 | 1286134
| Van Maanen |  | 1281000 | 0 | 1281000
| ATC Group(2) |  | 15497 | 0 | 15497
| Reily Construction |  | 2375000 | 0 | 2375000
| Total Project Cost | 14275000 | 9670112.69 | 499773.07 | 9170339.62 | 4604887.31

## #9279.50 Funds Rec'd
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400KDH122325001 | 2025-12-23 | 14275000 | 14275000
| Total Requested | 0 | Total Transferred |  |  | 14275000 | 14275000

## #9279.50 Shive Hattery
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA26-9260 |  |  | RFP927900-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023916 | 2026-01-23 | PO Procore | 457993 | 457993 |  |  | 457993
PRC 3352602PA3916 | 2026-04-29 | Inv. 2240007040-801 |  | 457993 | 410376.7 | 410376.7 | 47616.3
PRC 3352602PB3916 | 2026-06-03 | Inv. 2240007040-802 |  | 457993 | 44163.3 | 454540 | 3453
PO 33526023916 | 2026-06-24 | CO #1 | 134789 | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  |  |  | 592782 |  | 454540 | 138242
|  | Totals: | 592782 |  | 454540 |  | 138242
|  | Schematic Design | 172500 |  | 172500 |  | 0
|  | Design Development | 159000 |  | 159000 |  | 0
|  | Construction Documents | 112681 |  | 112681 |  | 0
|  | Bidding Assistance | 13812 |  | 10359 |  | 3453
|  | CO #1 | 134789 |  |  |  | 134789
|  | Total: | 592782 |  | 454540 |  | 138242

## #9279.50 PM TIME
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 735I
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 293189 | 293189 |  |  | 293189
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 293189 | 116.55 | 116.55 | 293072.45
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 293189 | 741.5 | 858.05 | 292330.95
CDE 33526352902 | 2025-12-18 | 2507 | Moving expense from 9279.50 to 9279.40 |  | 293189 | -116.55 | 741.5 | 292447.5
CDE 33526352902 | 2025-12-18 | 9500 | Moving expense from 9279.50 to 9279.40 |  | 293189 | -741.5 | 0 | 293189
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 293189 | 21.39 | 21.39 | 293167.61
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 293189 | 243.3 | 264.69 | 292924.31
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 293189 | 50.95 | 315.64 | 292873.36
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 293189 | 628.8 | 944.44 | 292244.56
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 293189 | 186.17 | 1130.61 | 292058.39
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 293189 | 2143.8 | 3274.41 | 289914.59
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 293189 | 279.88 | 3554.29 | 289634.71
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 293189 | 2285.6 | 5839.89 | 287349.11
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 293189 | 196.51 | 6036.4 | 287152.6
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 293189 | 2050.3 | 8086.7 | 285102.3
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 293189 | 223.66 | 8310.36 | 284878.64
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 293189 | 2736.4 | 11046.76 | 282142.24
|  |  | Totals: | 293189 |  | 11046.76 |  | 282142.24
Note on E9: Kleene, Jennifer 9:21 AM (3 minutes ago) to me Please create a DAS Costs budget of $293,189.00 for DA26 9279.50. Regards, Jennifer Jennifer Kleene

## #9279.50 Misc
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526050912 | 2026-02-19 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2538 | 63.74 | 63.74
PRC 33526168911 | 2026-06-17 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2888 | 74.74 | 138.48
PRC 33526173910 | 2026-06-22 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2904 | 487.8 | 626.28
626.28
626.28
626.28
626.28
626.28
626.28
626.28
626.28
626.28
|  |  |  | Totals: |  | 626.28

## #9279.50 StoryConstruction
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA26-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030914 | 2026-01-30 | PO Procore | 25212.59 | 25212.59 |  |  | 25212.59
PRC 3352603PA0914 | 2026-03-18 | Inv. 35199 |  | 25212.59 | 3021.31 | 3021.31 | 22191.28
PRC 3352603PB0914 | 2026-04-17 | Inv. 35233 |  | 25212.59 | 3646.46 | 6667.77 | 18544.82
PRC 3352603PC0914 | 2026-05-26 | Inv. 35264 |  | 25212.59 | 5124.17 | 11791.94 | 13420.65
PRC 3352603PD0914 | 2026-06-18 | Inv. 35300FINAL | -97.81 | 25114.78 | 13322.84 | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  |  |  | 25114.78 |  | 25114.78 | -5.1159e-13
|  | Totals: | 25114.78 |  | 25114.78 |  | 0 | FINAL
|  | CM Service | 25114.78 |  | 25114.78 |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 25114.78 |  | 25114.78 |  | 0

## #9279.50 ATC Group
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
ATC Group |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA26-9255 |  |  | MA00526283
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526105918 | 2026-04-15 | PO Procore | 11861.5 | 11861.5 |  |  | 11861.5
PRC 3352610PA5918 | 2026-06-03 | Inv. 2712812 |  | 11861.5 | 5219 | 5219 | 6642.5
PRC 3352610PB5918 | 2026-06-08 | Inv. 2715324 |  | 11861.5 | 3226.25 | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  |  |  | 11861.5 |  | 8445.25 | 3416.25
|  | Totals: | 11861.5 |  | 8445.25 |  | 3416.25
Powerhouse Systems Survey
| Line 3 | Asbestos 50@12.5 | 625 |  | 250 |  | 375
| Line 5 | Lead 15@17 | 255 |  | 255 |  | 0
| Line 6 | Admin 2@45 | 90 |  | 45 |  | 45
| Line 8 | Field Tech 10@85 | 850 |  | 680 |  | 170
| Line 9 | Hygienist 20@105 | 2100 |  | 1522.5 |  | 577.5
| Line12 | Reimbursement 75 @.5 | 37.5 |  | 37.5 |  | 0
|  | Total | 3957.5 |  | 2790 |  | 1167.5
Chiller Systems Survey
| Line 3 | Asbestos 14@12.5 | 175 |  | 87.5 |  | 87.5
| Line 5 | Lead 8@17 | 136 |  | 119 |  | 17
| Line 6 | Admin 2@45 | 45 |  |  |  | 45
| Line 8 | Field Tech 5@85 | 425 |  | 340 |  | 85
| Line 9 | Hygienist 9@105 | 945 |  | 945 |  | 0
| Line12 | Reimbursement 75 @.5 | 37.5 |  | 37.5 |  | 0
|  | Total | 1763.5 |  | 1529 |  | 234.5
Tunnel
| Line 3 | Asbestos 8@12.5 | 100 |  |  |  | 100
| Line 5 | Lead 5@17 | 68 |  |  |  | 68
| Line 6 | Admin 1@45 | 45 |  |  |  | 45
| Line 8 | Field Tech 5@85 | 340 |  | 127.5 |  | 212.5
| Line 9 | Hygienist 7@105 | 735 |  | 735 |  | 0
| Line12 | Reimbursement 75 @.5 | 37.5 |  | 37.5 |  | 0
|  | Total | 1325.5 |  | 900 |  | 425.5
Design Services
| Line 6 | Admin 2@45 | 90 |  | 45 |  | 45
| Line 8 | Field Tech 6@85 | 510 |  |  |  | 510
| Line 9 | Hygienist 20@105 | 2100 |  | 1443.75 |  | 656.25
| Line12 | Reimbursement 75 @.5 | 37.5 |  |  |  | 37.5
|  | Total: | 2737.5 |  | 1488.75 |  | 1248.75
Bidding Assistance
| Line 6 | Admin .5@45 | 22.5 |  | 22.5 |  | 0
| Line 8 | Field Tech4@85 | 340 |  |  |  | 340
| Line 9 | Hygienist 15@105 | 1575 |  | 1575 |  | 0
| Line12 | Reimbursement 280 @.5 | 140 |  | 140 |  | 0
|  | Total: | 2077.5 |  | 1737.5 |  | 340
|  | Asbestos @12.5 | 900 |  | 337.5 |  | 562.5
|  | Lead @17 | 459 |  | 374 |  | 85
|  | Admin @45 | 292.5 |  | 112.5 |  | 180
|  | Field Tech @85 | 2465 |  | 1147.5 |  | 1317.5
|  | Hygienist @105 | 7455 |  | 6221.25 |  | 1233.75
|  | Reimbursement @.50 | 290 |  | 252.5 |  | 37.5
|  | Contract Total: | 11861.5 |  | 8445.25 |  | 3416.25

## #9279.50 Van Maanen
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Van Maanen |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA26-9255 |  |  | 927950-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526170911 | 2026-06-19 | PO Procore | 57562 | 57562 |  |  | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  |  |  | 57562 |  | 0 | 57562
|  | Totals: | 57562 |  | 0 |  | 57562

## #9279.50 Central IA Mechanical
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Central Iowa Mechanical |  |  | Vendor: 00002109717
Acct. Codes-0506-335-DA26-9255 |  |  | 927950-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526174910 | 2026-06-23 | PO Procore | 645267 | 645267 |  |  | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  |  |  | 645267 |  | 0 | 645267
|  | Totals: | 645267 |  | 0 |  | 645267

## #9279.50 StoryConstruction (2)
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Story Construction(2) |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA26-9255 |  |  | 927900-01
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526174918 | 2026-06-23 | PO Procore | 901304.13 | 901304.13 |  |  | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  |  |  | 901304.13 |  | 0 | 901304.13
|  | Totals: | 901304.13 |  | 0 |  | 901304.13
|  | Personnel | 602616.25 |  |  |  | 602616.25
|  | Reimbursables | 5988.5 |  |  |  | 5988.5
|  | Bid Packages Fee | 132088.8 |  |  |  | 132088.8
|  | General Conditions Fees | 4298.58 |  |  |  | 4298.58
|  | General Conditions | 156312 |  |  |  | 156312
|  | Total: | 901304.13 |  | 0 |  | 901304.13

## #9279.50 Earth Services
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Earth Services & Abatement |  |  | Vendor: VS000007582
Acct. Codes-0506-335-DA26-9255 |  |  | 927950-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526175915 | 2026-06-24 | PO Procore | 1725400 | 1725400 |  |  | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  |  |  | 1725400 |  | 0 | 1725400
|  | Totals: | 1725400 |  | 0 |  | 1725400

## #9279.50 Earth Services (2)
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Earth Services & Abatement (2) |  |  | Vendor: VS000007582
Acct. Codes-0506-335-DA26-9255 |  |  | 927950-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526175913 | 2026-06-24 | PO Procore | 459375 | 459375 |  |  | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  |  |  | 459375 |  | 0 | 459375
|  | Totals: | 459375 |  | 0 |  | 459375

## #9279.50 Breiholz Construction
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Breiholz Construction |  |  | Vendor: 00002107863
Acct. Codes-0506-335-DA26-9255 |  |  | 927940-04
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Split w/ 9279.41 DA25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176914 | 2026-06-25 | PO Procore | 1286134 | 1286134 |  |  | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  |  |  | 1286134 |  | 0 | 1286134
|  | Totals: | 1286134 |  | 0 |  | 1286134
|  | DA25 9279.41 | 191969 |  | 0 |  | 191969
|  | Total: | 1478103 |  | 0 |  | 1478103

## #9279.50 VanMaanen
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
VanMaanen |  |  | Vendor: 00002091370
Acct. Codes-0506-335-DA26-9255 |  |  | 927940-04
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Split w/ 9279.50 DA26
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176915 | 2026-06-25 | PO Procore | 1281000 | 1281000 |  |  | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  |  |  | 1281000 |  | 0 | 1281000
|  | Totals: | 1281000 |  | 0 |  | 1281000
|  | DA25 9279.41 | 11800 |  | 0 |  | 11800
|  | Total: | 1292800 |  | 0 |  | 1292800

## #9279.50 ATC Group (2)
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
ATC Group (2) |  |  | Vendor: 00002134218
Acct. Codes-0506-335-DA26-9255 |  |  | MA00526283
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526176916 | 2026-06-25 | PO Procore | 15497 | 15497 |  |  | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  |  |  | 15497 |  | 0 | 15497
|  | Totals: | 15497 |  | 0 |  | 15497
| Line 3 | Asbestos 20@12.5 | 250 |  |  |  | 250
| Line 6 | Admin 2@45 | 90 |  |  |  | 90
| Line 8 | Field Tech 135@85 | 11475 |  |  |  | 11475
| Line 9 | Hygienist 32@105 | 3360 |  |  |  | 3360
| Line12 | Reimbursement 644@.5 | 322 |  |  |  | 322
|  | Total: | 15497 |  | 0 |  | 15497

## #9279.50 Reilly Construction
HHS WRC Campus Utility Decentralization Phase 5
Project # 9279.50
Program code 927950 |  |  | Major Program 4B02
Reilly Construction |  |  | Vendor: 00002108239
Acct. Codes-0506-335-DA26-9255 |  |  | 927950-01
Project Manager - Jennifer K. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526177914 | 2026-06-26 | PO Procore | 2375000 | 2375000 |  |  | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  |  |  | 2375000 |  | 0 | 2375000
|  | Totals: | 2375000 |  | 0 |  | 2375000

## RECAP #9438.00
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
| Program code 943800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 15499.2
C | Jasper Construction |  | 15316.75 | 15316.75 | 0
C | PM TIME |  | 0 | 0 | 0
C | Misc. |  | 182.45 | 182.45 | 0
| Total Project Cost | 15499.2 | 15499.2 | 15499.2 | 0 | 0
Closed 04/17/26

## #9438.00 Funds Rec'd
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25208202502 | 2025-08-21 | 15650 | 15650
|  |  | Returning funds to Agency Closing Project | IET 33526110911 | 2026-04-20 | -150.8 | -150.8
| Total Requested | 0 | Total Transferred |  |  | 15499.2 | 15499.2

## #9438.00 Jasper Construction
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Jasper Construction |  |  | Vendor: 00003016436
Acct. Codes-0506-335-DA26-9255 |  |  | RFQ943800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526266902 | 2025-09-23 | PO Procore | 14182.75 | 14182.75 |  |  | 14182.75
PO 33526266902 | 2025-11-18 | CO #1(Split w/ DA26) | 1134 | 15316.75 |  | 0 | 15316.75
PO 33526266902 | 2026-01-12 | CO #2(100% to MM23) | 0 | 15316.75 |  | 0 | 15316.75
PRC 3352626PA6902 | 2026-02-03 | Inv. 9438.00-01(Split w/MM23) |  | 15316.75 | 14857.25 | 14857.25 | 459.5 | 459.5
PRC 3352626PB6902 | 2026-03-09 | Inv. 9438.00-02 - Retainage (Split w/ MM23) |  | 15316.75 | 459.5 | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  |  |  | 15316.75 |  | 15316.75 | 0
|  | Totals: | 15316.75 |  | 15316.75 |  | 0 | FINAL
|  | MM23 | 48451.25 |  | 48451.25 |  | 0
|  | Total: | 63768 |  | 63768 |  | 0

## #9438.00 PM TIME
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 734H
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget |  | 0 |  |  | 0
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 0 | 32.85 | 32.85 | -32.85
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 0 | 371.8 | 404.65 | -404.65
CDE 33526021906 | 2026-01-21 | 2507 | Moving December Time to MM23 |  | 0 | -32.85 | 371.8 | -371.8
CDE 33526021906 | 2026-01-21 | 9500 | Moving December Time to MM23 |  | 0 | -371.8 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9438.00 Misc
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526349902 | 2025-12-15 | 9500 | CNST | Team Services V#(00002121153) | Inv. 1825258-0 | 182.45 | 182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
182.45
|  |  |  | Totals: |  | 182.45

## RECAP #9471.00
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 27500
Midstate Plumbing |  | 24537 | 23310.15 | 1226.85
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 27500 | 24537 | 23310.15 | 1226.85 | 2963

## #9471.00 Funds Rec'd
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25208072504 | 2025-08-12 | 27500 | 27500
| Total Requested | 0 | Total Transferred |  |  | 27500 | 27500

## #9471.00 MidState Plumbing
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Midstate Plumbing |  |  | Vendor: 00002108635
Acct. Codes-0506-335-DA26-9255 |  |  | RFB947100-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526226907 | 2025-08-14 | PO Procore | 24537 | 24537 |  |  | 24537
PRC 3352622PA6907 | 2025-12-22 | Inv. P38754(Split w/MM24) |  | 24537 | 1070.65 | 1070.65 | 23466.35 | 56.35
PRC 3352622PB6907 | 2025-12-29 | Inv. P39138(Split w/MM24) |  | 24537 | 7600 | 8670.65 | 15866.35 | 456.35
PRC 3352622PC6907 | 2026-01-09 | Inv. P39249(100% to MM24) |  | 24537 | 0 | 8670.65 | 15866.35 | 456.35
PRC 3352622PD6907 | 2026-01-30 | Inv. P39322(Split w/MM24) |  | 24537 | 4560 | 13230.65 | 11306.35 | 696.35
PO 33526226907 | 2026-02-03 | CO #1 (No Cost CO) | 0 | 24537 |  | 13230.65 | 11306.35
PRC 3352622PE6907 | 2026-02-26 | Inv. P39484(100% to MM24) | 0 | 24537 |  | 13230.65 | 11306.35
PRC 3352622PF6907 | 2026-03-20 | Inv. P39590(Split w/MM24) |  | 24537 | 2850 | 16080.65 | 8456.35 | 846.35
PRC 3352622PG6907 | 2026-04-22 | Inv. P39682(Split w/MM24) |  | 24537 | 950 | 17030.65 | 7506.35 | 896.35
PRC 3352622PH6907 | 2026-05-26 | Inv. P39915(Split w/MM26) |  | 24537 | 6279.5 | 23310.15 | 1226.85 | 1226.85
PRC 3352622PI6907 | 2026-06-25 | Inv. P41609(100% to MM24) |  | 24537 | 0 | 23310.15 | 1226.85 | 1226.85
|  |  |  | 24537 |  | 23310.15 | 1226.85
|  |  |  | 24537 |  | 23310.15 | 1226.85
|  | Totals: | 24537 |  | 23310.15 |  | 1226.85
|  | MM23 | 124741 |  | 118503.95 |  | 6237.05
|  | Total: | 149278 |  | 141814.1 |  | 7463.9

## #9471.00 PM TIME
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 734B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9471.00 Misc
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9476.01
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 270000
McGough Construction |  | 42023.48 | 1176.12 | 40847.36
PM TIME |  | 8000 | 979.68 | 7020.32
Misc. |  | 318.17 | 318.17 | 0
HGM Associates |  | 12655 | 0 | 12655
Total Project Cost | 270000 | 62996.65 | 2473.97 | 60522.68 | 207003.35

## #9476.01 Funds Rec'd
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL26096007 | 2026-04-13 | 270000 | 270000
| Total Requested | 0 | Total Transferred |  |  | 270000 | 270000

## #9476.01 McGough Construction
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  | Major Program 4B02
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526111909 | 2026-04-21 | PO Procore | 42023.48 | 42023.48 |  |  | 42023.48
PRC 3352611PA1909 | 2026-05-19 | Inv. 101368.010-CA01 |  | 42023.48 | 1176.12 | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  |  |  | 42023.48 |  | 1176.12 | 40847.36
|  | Totals: | 42023.48 |  | 1176.12 |  | 40847.36
|  | CM Services | 40743.48 |  | 1176.12 |  | 39567.36
|  | Reimbursables | 1280 |  |  |  | 1280
|  | Total: | 42023.48 |  | 1176.12 |  | 40847.36

## #9476.01 PM TIME
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 736J
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 8000 | 55.91 | 55.91 | 7944.09
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 8000 | 578.9 | 634.81 | 7365.19
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 8000 | 26.17 | 660.98 | 7339.02
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 8000 | 318.7 | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
[5 empty] | 8000 |  | 979.68 | 7020.32
|  |  | Totals: | 8000 |  | 979.68 |  | 7020.32
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kleene, Jennifer ​Huggins, Joni​ Sorry about that! Please create a DAS Costs budget of $8,000.00 for 9476.01. Regards, Jennifer Jennifer Kleene Kleene, Jennifer ​Huggins, Joni​ Sorry about that! Please create a DAS Costs budget of $8,000.00 for 9476.01. Regards, Jennifer Jennifer Kleene

## #9476.01 Misc
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526180913 | 2026-06-29 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2899 | 318.17 | 318.17
318.17
318.17
318.17
318.17
318.17
318.17
318.17
318.17
318.17
318.17
318.17
|  |  |  | Totals: |  | 318.17

## #9476.01 HGM Associates
HHS STS New Garage Building - Phase 2
Project # 9476.01
Program code 947601 |  |  | Major Program 4B02
HGM Associates |  |  | Vendor: 00002109941
Acct. Codes-0506-335-DA26-9260 |  |  | RFP947600-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526117910 | 2026-04-27 | PO Procore | 12655 | 12655 |  |  | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  |  |  | 12655 |  | 0 | 12655
|  | Totals: | 12655 |  | 0 |  | 12655
|  | Bidding Assistance | 1790 |  |  |  | 1790
|  | Construction Phase | 10865 |  |  |  | 10865
|  | Total: | 12655 |  | 0 |  | 12655

## RECAP #9480.01
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
| Program code 948001 |  |  | Major Program 3D02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 242065.68
C | TB Rigid Edge Exteriors |  | 96143.6 | 96143.6 | 0
C | PM TIME |  | 10005.97 | 10005.97 | 0
C | Misc. |  | 0 | 0 | 0
C | Genesis Architectural |  | 16700 | 16700 | 0
C | McGough Construction |  | 30122 | 30122 | 0
C | Hilsabeck Schacht |  | 29700 | 29700 | 0
C | MTS Contracting |  | 3518.11 | 3518.11 | 0
C | Kinzler Construction |  | 55876 | 55876 | 0
| Total Project Cost | 242065.68 | 242065.68 | 242065.68 | 0 | 0
Closed 06/09/26

## #9480.01 Funds Rec'd
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL26216003 | 2025-08-06 | 230000 | 230000
|  |  | MOU Amendment #1 | IET 400EL26274001 | 2025-10-02 | 35000 | 35000
|  |  | Returning Funds - Closing Project | IET 33526160909 | 2026-06-09 | -22934.32 | -22934.32
| Total Requested | 0 | Total Transferred |  |  | 242065.68 | 242065.68

## #9480.01 TB Rigid Edge Exterior
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
TB Rigid Edge Exteriors |  |  | Vendor: 00003193199
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526230902 | 2025-08-18 | PO Procore | 70820.24 | 70820.24 |  |  | 70820.24
PO 33526230902 | 2025-09-16 | CO #1 | 4076.18 | 74896.42 |  | 0 | 74896.42
PO 33526230902 | 2025-10-21 | CO #2 | 23398.77 | 98295.19 |  | 0 | 98295.19
PO 33526230902 | 2025-12-23 | CO #3 | 540 | 98835.19 |  | 0 | 98835.19
PRC 3352623PA0902 | 2026-01-21 | Inv. 9480.01-001 |  | 98835.19 | 72339.73 | 72339.73 | 26495.46 | 2237.32
PO 33526230902 | 2026-03-09 | CO #4 | -2691.59 | 96143.6 |  | 72339.73 | 23803.87
PRC 3352623PB0902 | 2026-03-27 | Inv. 1046-2 |  | 96143.6 | 19949.55 | 92289.28 | 3854.32 | 2854.32
PRC 3352623PC0902 | 2026-05-04 | Inv. 1046-3 |  | 96143.6 | 970 | 93259.28 | 2884.32 | 2884.32
PRC 3352623PD0902 | 2026-05-11 | Inv. 1046-4 -Retainage |  | 96143.6 | 2884.32 | 96143.6 | 6.8212e-12
|  |  |  | 96143.6 |  | 96143.6 | 6.8212e-12
|  |  |  | 96143.6 |  | 96143.6 | 6.8212e-12
|  |  |  | 96143.6 |  | 96143.6 | 6.8212e-12
|  |  |  | 96143.6 |  | 96143.6 | 6.8212e-12
|  | Totals: | 96143.6 |  | 96143.6 |  | 0 | FINAL
Retainage 3%

## #9480.01 PM TIME
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 733M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10005.97 | 10005.97 |  |  | 10005.97
CDE 33526262901 | 2025-09-18 | 9500 | Moving Expense from 9480.00 |  | 10005.97 | 1355.98 | 1355.98 | 8649.99
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10005.97 | 527.07 | 1883.05 | 8122.92
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10005.97 | 2712.3 | 4595.35 | 5410.62
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10005.97 | 113.05 | 4708.4 | 5297.57
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10005.97 | 1116.8 | 5825.2 | 4180.77
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10005.97 | 187.5 | 6012.7 | 3993.27
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10005.97 | 1193.7 | 7206.4 | 2799.57
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10005.97 | 72.78 | 7279.18 | 2726.79
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10005.97 | 826.7 | 8105.88 | 1900.09
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 10005.97 | 21.39 | 8127.27 | 1878.7
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 10005.97 | 270.1 | 8397.37 | 1608.6
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10005.97 | 45.91 | 8443.28 | 1562.69
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10005.97 | 522.7 | 8965.98 | 1039.99
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10005.97 | 27.7 | 8993.68 | 1012.29
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10005.97 | 223.6 | 9217.28 | 788.69
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 10005.97 | 8.6 | 9225.88 | 780.09
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10005.97 | 89.2 | 9315.08 | 690.89
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10005.97 | 51.89 | 9366.97 | 639
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10005.97 | 639 | 10005.97 | -7.9581e-13
[5 empty] | 10005.97 |  | 10005.97 | -7.9581e-13
|  |  | Totals: | 10005.97 |  | 10005.97 |  | 0
Note on E9: Jurgenson, John [DAS]: DAS Costs Budget for DA26 9480.01 Inbox Kleene, Jennifer 2:58 PM (2 minutes ago) to me Please create a DAS Costs budget for $4,000.00 for DA26 9480.01. Regards, Jennifer DAS Cost Budget Increases $Joni Kleene, Jennifer 9:49 AM (1 minute ago) to me Please increase the DAS Cost budget for MM24 9277.00 by $3,000.00 Please increase the DAS Cost budget for DA26 9480.01 by $2,000.00 From: Kleene, Jennifer <jennifer.kleene@das.iowa.gov> Sent: Monday, June 8, 2026 3:25 PM To: DAS Finance Payables Infrastructure <dasfinanceinfrastructure@das.iowa.gov> Cc: Cross, Charlee <charlee.cross@das.iowa.gov> Subject: Re: May PM Time has posted Please increase the PM Time budget for 9413.00 by $1,459.75. Please increase the PM Time budget for 9441.00 by $70.50. Please increase the PM Time budget for 9480.01 by $5.97. Regards, Jennifer Jennifer Kleene

## #9480.01 Misc
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9480.01 Genesis Architectural
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split w/DA25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526181901 | 2025-08-22 | CO #1 Opening in DA26 | 16700 | 16700 |  |  | 16700
PRC 3352618PB1901 | 2025-09-23 | Inv. 2503-02(Split w/DA25) |  | 16700 | 7810 | 7810 | 8890
PO 33526181901 | 2025-12-15 | Closed PO to correct accounting lines link |  | 16700 |  | 7810 | 8890
PO 33526181901A | 2025-12-15 | Reopened PO To correct links in IA |  | 16700 |  | 7810 | 8890
PRC 3352618PC1901A | 2025-12-15 | Inv. 2503-03 |  | 16700 | 6140 | 13950 | 2750
PRC 3352618PD1901A | 2026-06-02 | Inv. 2503-04 FINAL |  | 16700 | 2750 | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  |  |  | 16700 |  | 16700 | 0
|  | Totals: | 16700 |  | 16700 |  | 0 | FINAL
|  | DA25 Closed 09/23/25 | 10750 |  | 10750 |  | 0
|  | Total: | 27450 |  | 27450 |  | 0

## #9480.01 McGough Construction
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Mc Gough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGought11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526252403 | 2025-09-09 | PO Procore | 30122 | 30122 |  |  | 30122
PRC 3352625PA2403 | 2025-09-16 | Inv. 101368.011-CA01 |  | 30122 | 2589.8 | 2589.8 | 27532.2
PRC 3352625PB2403 | 2025-10-16 | Inv. 101368.011-CA02 |  | 30122 | 9881.74 | 12471.54 | 17650.46
PRC 3352625PC2403 | 2025-11-17 | Inv. 101368.011-CA03 |  | 30122 | 9467.15 | 21938.69 | 8183.31
PRC 3352625PD2403 | 2025-12-10 | Inv. 101368.011-CA04 |  | 30122 | 3417.43 | 25356.12 | 4765.88
PRC 3352625PE2403 | 2026-01-09 | Inv. 101368.011-CA05 |  | 30122 | 1006.8 | 26362.92 | 3759.08
PRC 3352625PF2403 | 2026-02-16 | Inv. 101368.011-CA06 |  | 30122 | 1123.22 | 27486.14 | 2635.86
PRC 3352625PG2403 | 2026-03-17 | Inv. 101368.011-CA07 |  | 30122 | 1426.96 | 28913.1 | 1208.9
PRC 3352625PH2403 | 2026-06-02 | Inv. 101368.011-CA08 - FINAL |  | 30122 | 1208.9 | 30122 | -1.3642e-12
|  |  |  | 30122 |  | 30122 | -1.3642e-12
|  |  |  | 30122 |  | 30122 | -1.3642e-12
|  |  |  | 30122 |  | 30122 | -1.3642e-12
|  |  |  | 30122 |  | 30122 | -1.3642e-12
|  | Totals: | 30122 |  | 30122 |  | 0 | FINAL
|  | CM Services | 29082 |  | 29082 |  | 0
|  | Reimbursables | 1040 |  | 1040 |  | 0
|  | Total: | 30122 |  | 30122 |  | 0

## #9480.01 Hilsabeck Schacht
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526272906 | 2025-09-29 | PO Procore | 29700 | 29700 |  |  | 29700
PRC 3352627PA2906 | 2025-11-04 | Inv. HS2172 |  | 29700 | 21940.43 | 21940.43 | 7759.57 | 678.57
PRC 3352627PB2906 | 2025-12-03 | Inv. 9480.01-02 |  | 29700 | 5898.57 | 27839 | 1861 | 861
PRC 3352627PC2906 | 2026-01-26 | Inv. 9480.01-03 |  | 29700 | 970 | 28809 | 891 | 891
PRC 3352627PD2906 | 2026-02-05 | Inv. 9480.01-Retainage |  | 29700 | 891 | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  |  |  | 29700 |  | 29700 | 0
|  | Totals: | 29700 |  | 29700 |  | 0 | FINAL

## #9480.01 MTS Contracting
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0506-335-DA26-9255 |  |  | MA00520243D
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526272908 | 2025-09-29 | PO Procore | 4907.48 | 4907.48 |  |  | 4907.48
PRC 3352627PA2908 | 2025-12-16 | Inv. 25-6194 - FINAL | -1389.37 | 3518.11 | 3518.11 | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  |  |  | 3518.11 |  | 3518.11 | 0
|  | Totals: | 3518.11 |  | 3518.11 |  | 0 | FINAL
|  | Tuckpointing | 1874.5 |  | 1874.5 |  | 0
|  | Materials & Supplies | 1643.61 |  | 1643.61 |  | 0
|  | Total: | 3518.11 |  | 3518.11 |  | 0

## #9480.01 Kinzler Construction
HHS STS Canteen Roof Repair Construction (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Kinzler Construction |  |  | Vendor: 00003169106
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526273902 | 2025-09-30 | PO Procore | 57958 | 57958 |  |  | 57958
PO 33526273902 | 2025-10-20 | CO #1 | -2082 | 55876 |  | 0 | 55876
PRC 3352627PA3902 | 2025-11-24 | Inv. 2519028 |  | 55876 | 53229.72 | 53229.72 | 2646.28 | 1646.28
PRC 3352627PB3902 | 2025-12-04 | Inv. 2519028.0014 |  | 55876 | 970 | 54199.72 | 1676.28 | 1676.28
PRC 3352627PC3902 | 2026-01-20 | Inv. 9480.01-Retainage |  | 55876 | 1676.28 | 55876 | -1.1369e-12
| 2026-03-31 | Warrant Cancelled- Lost in Mail |  | 55876 | -1676.28 | 54199.72 | 1676.28
GAX 33526091900 | 2026-04-01 | Inv. 9480.01-Retainage-Reissue |  | 55876 | 1676.28 | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  |  |  | 55876 |  | 55876 | -1.1369e-12
|  | Totals: | 55876 |  | 55876 |  | 0 | FINAL

## RECAP #9481.00
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1400000
Horizon Architecture |  | 49974.5 | 0 | 49974.5
PM TIME |  | 10000 | 3999.47 | 6000.53
Misc. |  | 783.75 | 783.75 | 0
McGough Construction |  | 12584.85 | 5114.32 | 7470.53
Total Project Cost | 1400000 | 73343.1 | 9897.54 | 63445.56 | 1326656.9

## #9481.00 Funds Rec'd
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812V26001 | 2025-07-29 | 1400000 | 1400000
| Total Requested | 0 | Total Transferred |  |  | 1400000 | 1400000

## #9481.00 Horizon Architecture
Horizon Architecture
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948100-01
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526142920 | 2026-05-22 | PO Procore | 49974.5 | 49974.5 |  |  | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  |  |  | 49974.5 |  | 0 | 49974.5
|  | Totals: | 49974.5 |  | 0 |  | 49974.5
|  | Design Development | 14106.5 |  |  |  | 14106.5
|  | Construction Documents | 20228 |  |  |  | 20228
|  | Bidding | 2372 |  |  |  | 2372
|  | Construction Admin | 13268 |  |  |  | 13268
|  | Total: | 49974.5 |  | 0 |  | 49974.5

## #9481.00 PM TIME
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733O
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 300.34 | 300.34 | 9699.66
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 571.2 | 871.54 | 9128.46
CDE 33526317909 | 2025-11-13 | 2507 | Moving PM Time from 9481.00 DA26 to 9997.26 MM26 |  | 10000 | -300.34 | 571.2 | 9428.8
CDE 33526317909 | 2025-11-13 | 9500 | Moving PM Time from 9481.00 DA26 to 9997.26 MM26 |  | 10000 | -571.2 | 0 | 10000
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | -5.66 | -5.66 | 10005.66
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 1308.2 | 1302.54 | 8697.46
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10000 | 108.95 | 1411.49 | 8588.51
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10000 | 1240 | 2651.49 | 7348.51
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10000 | 101.68 | 2753.17 | 7246.83
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 1246.3 | 3999.47 | 6000.53
[5 empty] | 10000 |  | 3999.47 | 6000.53
[5 empty] | 10000 |  | 3999.47 | 6000.53
|  |  | Totals: | 10000 |  | 3999.47 |  | 6000.53
Note on E9: Huggins, Joni [DAS]: Adams, Brandon 1:51 PM (1 hour ago) to me DA24 9414.00 (3,176.95) increase by $6,000 DA26 9481.00 (1302.54) set pm budget at $10,000 MM23 9450.00 (491.54) increase by $491.54 and close MM25 9442.00 (1,198.60) increase by $2,000 Regards, Brandon Adams

## #9481.00 Misc
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202601115300001 | 2025-08-07 | 2507 |  | Space Planning Services July 1-31,2025 | Inv. DAS2026011153 | 570 | 570
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Space Planning Services August 1-31,2025 | Inv. DAS2026021153 | 166.25 | 736.25
IET DAS202604115300001 | 2025-11-07 | 2507 |  | Space Planning Services October 1-31,2025 | Inv. DAS2026041153 | 47.5 | 783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
783.75
|  |  |  | Totals: |  | 783.75

## #9481.00 McGough Construction
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGought11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526146913 | 2026-05-26 | PO Procore | 12584.85 | 12584.85 |  |  | 12584.85
PRC 3352614PA6913 | 2026-06-09 | Inv. 101368.013-PC01 |  | 12584.85 | 5114.32 | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  |  |  | 12584.85 |  | 5114.32 | 7470.53
|  | Totals: | 12584.85 |  | 5114.32 |  | 7470.53

## RECAP #9482.00
IDB - Chiller Replacement
Project # 9482.00
| Program code 948200 |  |  | Major Program 4F09
Recap
Acct. Codes-0506-335-DA26
Project Manager - James T
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 559000
C | McGough Construction |  | 12990.91 | 12990.91 | 0
| PM TIME |  | 23000 | 14769.5 | 8230.5
| Misc. |  | 2729.49 | 2729.49 | 0
| KCL Engineering |  | 45090 | 30090 | 15000
C | Systems Management |  | 1240 | 1240 | 0
| McGough Construction (2) |  | 32715.96 | 3354.67 | 29361.29
| Air-Con Mechanical |  | 419975 | 4074 | 415901
| Total Project Cost | 559000 | 537741.36 | 69248.57 | 468492.79 | 21258.64

## #9482.00 Funds Rec'd
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - James T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 13150026212001 | 2025-07-31 | 50000 | 50000
|  |  | MOU #2 | IET 13126CHILLERMOU | 2026-02-26 | 509000 | 509000
| Total Requested | 0 | Total Transferred |  |  | 559000 | 559000

## #9482.00 McGough Construction
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526223900 | 2025-08-11 | PO Procore | 8969.4 | 8969.4 |  |  | 8969.4
PRC 3352622PA3900 | 2025-09-12 | Inv. 101368.012-PC01 |  | 8969.4 | 1188 | 1188 | 7781.4
PRC 3352622PB3900 | 2025-10-14 | Inv. 101368.012-PC02 |  | 8969.4 | 1360.26 | 2548.26 | 6421.14
PRC 3352622PC3900 | 2025-11-06 | Inv. 101368.012-PC03 |  | 8969.4 | 1226.61 | 3774.87 | 5194.53
PRC 3352622PD3900 | 2025-12-11 | Inv. 101368.012-PC04 |  | 8969.4 | 1630.53 | 5405.4 | 3564
PRC 3352622PE3900 | 2026-01-12 | Inv. 101368.012-PC05 |  | 8969.4 | 2028.51 | 7433.91 | 1535.49
PO 33526223900 | 2026-03-16 | CO #1 | 1741.91 | 10711.31 |  | 7433.91 | 3277.4
PO 33526223900 | 2026-03-24 | CO #2 | 2279.6 | 12990.91 |  | 7433.91 | 5557
PRC 3352622PF3900 | 2026-04-08 | Inv. 101368.012-PC06 - FINAL |  | 12990.91 | 5557 | 12990.91 | 0
|  |  |  | 12990.91 |  | 12990.91 | 0
|  |  |  | 12990.91 |  | 12990.91 | 0
|  |  |  | 12990.91 |  | 12990.91 | 0
|  |  |  | 12990.91 |  | 12990.91 | 0
|  | Totals: | 12990.91 |  | 12990.91 |  | 0 | FINAL

## #9482.00 PM TIME
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - James T |  |  |  | eDAS: 733P
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 23000 | 23000 |  |  | 23000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 23000 | 57.26 | 57.26 | 22942.74
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 23000 | 631.8 | 689.06 | 22310.94
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 23000 | 84.01 | 773.07 | 22226.93
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 23000 | 645.1 | 1418.17 | 21581.83
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 23000 | 146.86 | 1565.03 | 21434.97
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 23000 | 755.5 | 2320.53 | 20679.47
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 23000 | 239.96 | 2560.49 | 20439.51
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 23000 | 2379.7 | 4940.19 | 18059.81
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 23000 | 180.55 | 5120.74 | 17879.26
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 23000 | 1150.5 | 6271.24 | 16728.76
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 23000 | 92.08 | 6363.32 | 16636.68
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 23000 | 1044.3 | 7407.62 | 15592.38
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 23000 | 110.16 | 7517.78 | 15482.22
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 23000 | 1368 | 8885.78 | 14114.22
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 23000 | 185.73 | 9071.51 | 13928.49
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 23000 | 2138.3 | 11209.81 | 11790.19
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 23000 | 197.88 | 11407.69 | 11592.31
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 23000 | 1611.6 | 13019.29 | 9980.71
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 23000 | 88 | 13107.29 | 9892.71
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 23000 | 919.8 | 14027.09 | 8972.91
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 23000 | 56.41 | 14083.5 | 8916.5
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 23000 | 686 | 14769.5 | 8230.5
[5 empty] | 23000 |  | 14769.5 | 8230.5
|  |  | Totals: | 23000 |  | 14769.5 |  | 8230.5
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 2:04 PM (2 minutes ago) to me Could you please add $3000.00 to the PM time budget from the unallocated funds in project 9482.00? Thank you very much! -- Oliver Shimp, PE Shimp, Oliver 8:23 AM (36 minutes ago) to me Thank you for letting me know! Please add $15,000.00 to the PM time code. Phew! I was nervous about this one. thanks again, Oliver

## #9482.00 Misc
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T |  |  |  | Shipping Code: 403
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526033919 | 2026-02-03 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV052846 | 52.16 | 52.16
GAX 33526036902 | 2026-02-06 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. TQ10461 | 853.25 | 905.41
GAX 33526063910 | 2026-03-04 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. TQ20114 | 1595 | 2500.41
PRC 33526092919 | 2026-04-02 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2529 | 229.08 | 2729.49
2729.49
2729.49
2729.49
2729.49
2729.49
2729.49
2729.49
2729.49
|  |  |  | Totals: |  | 2729.49

## #9482.00 KCL Engineering
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948200-01
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266903 | 2025-09-23 | PO Procore | 30090 | 30090 |  |  | 30090
PRC 3352626PA6903 | 2025-11-20 | Inv. 12870 |  | 30090 | 9990 | 9990 | 20100
PRC 3352626PB6903 | 2026-03-23 | Inv. 13048 |  | 30090 | 20100 | 30090 | 0
PO 33526266903A | 2026-03-24 | CO #1 Extending PO | 10000 | 40090 |  | 30090 | 10000
PO 33526266903A | 2026-06-19 | CO #2 | 5000 | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  |  |  | 45090 |  | 30090 | 15000
|  | Totals: | 45090 |  | 30090 |  | 15000
|  | Design Development Docs | 9990 |  | 9990 |  | 0
|  | Construction Docs | 20100 |  | 20100 |  | 0
|  | CO #1 | 10000 |  |  |  | 10000
|  | CO #2 | 5000 |  |  |  | 5000
|  | Total: | 45090 |  | 30090 |  | 15000

## #9482.00 Systems Management
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Systems Management |  |  | Vendor: 00003202455
Acct. Codes-0506-335-DA26-9255 |  |  | SRVV5
Project Manager - James T |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526006903 | 2026-01-06 | PO Procore | 1240 | 1240 |  |  | 1240
PRC 3352600PA6903 | 2026-06-18 | Inv. 4139 |  | 1240 | 1240 | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  |  |  | 1240 |  | 1240 | 0
|  | Totals: | 1240 |  | 1240 |  | 0 | FINAL

## #9482.00 McGough Constructi (2)
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526075907 | 2026-03-16 | PO Procore | 32715.96 | 32715.96 |  |  | 32715.96
PRC 3352607PA5907 | 2026-04-08 | Inv. 101368.012-CA01 |  | 32715.96 | 2399.41 | 2399.41 | 30316.55
PRC 3352607PB5907 | 2026-05-19 | Inv. 101368.012-CA02 |  | 32715.96 | 370.78 | 2770.19 | 29945.77
PRC 3352607PC5907 | 2026-06-15 | Inv. 101368.012-CA03 |  | 32715.96 | 584.48 | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  |  |  | 32715.96 |  | 3354.67 | 29361.29
|  | Totals: | 32715.96 |  | 3354.67 |  | 29361.29
|  | CM Service | 32699.96 |  | 3354.67 |  | 29345.29
|  | Reimbursables | 16 |  |  |  | 16
|  | Total: | 32715.96 |  | 3354.67 |  | 29361.29

## #9482.00 Air-Con Mechanical
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Air Con Mechanical |  |  | Vendor: 00002115651
Acct. Codes-0506-335-DA26-9255 |  |  | RFB978200-01
Project Manager - James T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526075908 | 2026-03-16 | PO Procore | 419975 | 419975 |  |  | 419975
PRC 3352607PA5908 | 2026-03-27 | Inv. 5394 |  | 419975 | 4074 | 4074 | 415901 | 126
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  |  |  | 419975 |  | 4074 | 415901
|  | Totals: | 419975 |  | 4074 |  | 415901

## RECAP #9486.00
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
| Program code 948600 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 918852.06
C | DCI Group |  | 5949.11 | 5949.11 | 0
C | PM TIME |  | 7609.51 | 7609.51 | 0
C | Misc. |  | 0 | 0 | 0
C | Ralph N Smith Flooring |  | 826985 | 826985 | 0
C | DCI Group (2) |  | 78308.44 | 78308.44 | 0
| Total Project Cost | 918852.06 | 918852.06 | 918852.06 | 0 | 0
Closed 05/21/26

## #9486.00 Funds Rec'd
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925401 | 2025-07-29 | 1000000 | 1000000
|  |  | Allocating funds to sub project 9486.01 | CDR 33526117912 | 2026-04-27 | -25000 | -25000
|  |  | Allocating funds to sub project 9486.01 - Closing 9486.00 | CDR 33526141900 | 2026-05-21 | -56147.94 | -56147.94
| Total Requested | 0 | Total Transferred |  |  | 918852.06 | 918852.06

## #9486.00 DCI Group
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255902 | 2025-09-12 | PO Procore | 6725.74 | 6725.74 |  |  | 6725.74
PRC 3352625PA5902 | 2025-10-13 | Inv. 25-023 PC 01 |  | 6725.74 | 2488.21 | 2488.21 | 4237.53
PRC 3352625PB5902 | 2025-12-03 | Inv. 25-023 PC 02 FINAL | -776.63 | 5949.11 | 3460.9 | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  |  |  | 5949.11 |  | 5949.11 | 0
|  | Totals: | 5949.11 |  | 5949.11 |  | 0 | FINAL

## #9486.00 PM TIME
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 7609.51 | 7609.51 |  |  | 7609.51
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 7609.51 | 33.7 | 33.7 | 7575.81
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 7609.51 | 368.8 | 402.5 | 7207.01
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 7609.51 | 94.58 | 497.08 | 7112.43
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 7609.51 | 732.6 | 1229.68 | 6379.83
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 7609.51 | 91.24 | 1320.92 | 6288.59
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 7609.51 | 474.7 | 1795.62 | 5813.89
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 7609.51 | 71.84 | 1867.46 | 5742.05
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 7609.51 | 712.1 | 2579.56 | 5029.95
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 7609.51 | 72.16 | 2651.72 | 4957.79
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 7609.51 | 460.4 | 3112.12 | 4497.39
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 7609.51 | 68.26 | 3180.38 | 4429.13
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 7609.51 | 778 | 3958.38 | 3651.13
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 7609.51 | 62.08 | 4020.46 | 3589.05
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 7609.51 | 769.3 | 4789.76 | 2819.75
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 7609.51 | 78.57 | 4868.33 | 2741.18
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 7609.51 | 906.5 | 5774.83 | 1834.68
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 7609.51 | 108.49 | 5883.32 | 1726.19
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 7609.51 | 881.2 | 6764.52 | 844.99
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 7609.51 | 73.99 | 6838.51 | 771
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 7609.51 | 771 | 7609.51 | -2.2737e-13
[5 empty] | 7609.51 |  | 7609.51 | -2.2737e-13
|  |  | Totals: | 7609.51 |  | 7609.51 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate 9486.00-.01 : Internal Budget Shifts and Project Setup (DA26 - MOU) $Joni Tonyan, Brad 1:35 PM (14 minutes ago) to me, Joni, Brad, David, Scott Joni, As we discussed moments ago IVH/DAS/DCI Group would like to set up project 9486.01 as a sub job to the base project 9486.00. Details below on the next steps: 1. Setup Project 9486.01- DVA IVH Fox and Ulery Carpet Replacement - Sound Issues 2. 9486.00 - Reduce PM time budget from $30,000 to $10,000 and shift balance to general fund yet within project 9486.00 3. 9486.00 - Shift $25,000 from DA26 to sub project 9486.01 4. Set up a PM time budget of $5,000 4. Balance of $20,000 in general fund for 9486.01 Thank you and please reach out if you have any questions. Confirm when this is complete so we can start to issue the design contract. Brad Tonyan, CPM, LEED Green Associate

## #9486.00 Misc
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9486.00 Ralph N Smith Flooring
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Ralph N Smith Flooring |  |  | Vendor: 00002106937
Acct. Codes-0506-335-DA26-9255 |  |  | MA #21175A
Project Manager - Brandon A |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526273904 | 2025-09-30 | DO Procore | 783113 | 783113 |  |  | 783113
PRC 3352627PA3904 | 2025-10-31 | Inv. 9486.00-01 |  | 783113 | 293919 | 293919 | 489194
DO 33526273904 | 2025-12-05 | CO #1 | 12260 | 795373 |  | 293919 | 501454
PRC 3352627PB3904 | 2025-12-29 | Inv. 9486.00-02 |  | 795373 | 116843 | 410762 | 384611
PRC 3352627PC3904 | 2026-01-16 | Inv. 9486.00-03 |  | 795373 | 98971 | 509733 | 285640
PRC 3352627PD3904 | 2026-02-06 | Inv. 9486.00-04 |  | 795373 | 91697 | 601430 | 193943
DO 33526273904 | 2026-03-24 | CO #2 | 31612 | 826985 |  | 601430 | 225555
PRC 3352627PE3904 | 2026-03-30 | Inv. 9486.00-05 |  | 826985 | 93758 | 695188 | 131797
PRC 3352627PF3904 | 2026-04-22 | Inv. 9486.00-06 |  | 826985 | 131797 | 826985 | 0
|  |  |  | 826985 |  | 826985 | 0
|  |  |  | 826985 |  | 826985 | 0
|  |  |  | 826985 |  | 826985 | 0
|  |  |  | 826985 |  | 826985 | 0
|  | Totals: | 826985 |  | 826985 |  | 0

## #9486.00 DCI Group (2)
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
DCI Group(2) |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310903 | 2025-11-06 | PO Procore | 128119.75 | 128119.75 |  |  | 128119.75
PRC 3352631PA0903 | 2025-12-23 | Inv. 25-023 CA 01 |  | 128119.75 | 5787.75 | 5787.75 | 122332
PRC 3352631PB0903 | 2026-01-26 | Inv. 25-023 CA-02 |  | 128119.75 | 9970.96 | 15758.71 | 112361.04
PRC 3352631PC0903 | 2026-02-13 | Inv. 25-023 CA 03 |  | 128119.75 | 5942.93 | 21701.64 | 106418.11
PRC 3352631PD0903 | 2026-03-20 | Inv. 25-023 CA 04 |  | 128119.75 | 25390.8 | 47092.44 | 81027.31
PRC 3352631PE0903 | 2026-04-21 | Inv. 25-023 CA 05 |  | 128119.75 | 18830.29 | 65922.73 | 62197.02
PRC 3352631PF0903 | 2026-05-20 | Inv. 25-023 CA #06 - FINAL | -49811.31 | 78308.44 | 12385.71 | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  |  |  | 78308.44 |  | 78308.44 | 0
|  | Totals: | 78308.44 |  | 78308.44 |  | 0 | FINAL
|  | CM Staff Hours | 37730.44 |  | 37730.44 |  | 0
|  | Reimbursables | 1422.35 |  | 1422.35 |  | 0
|  | CM Fee | 39155.65 |  | 39155.65 |  | 0
|  | Total: | 78308.44 |  | 78308.44 |  | 0

## RECAP #9486.01
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 81147.94
Horizon Architecture |  | 12633 | 3309.5 | 9323.5
PM TIME |  | 5000 | 688.21 | 4311.79
Misc. |  | 0 | 0 | 0
DCI Group |  | 14988.92 | 2343.3 | 12645.62
Total Project Cost | 81147.94 | 32621.92 | 6341.01 | 26280.91 | 48526.02

## #9486.01 Funds Rec'd
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Allocating funds from main project 9486.00 | CDR 33526117912 | 2026-04-27 | 25000 | 25000
|  |  | Allocating funds from main project 9486.00- closing main 9486.00 | CDR 33526141900 | 2026-05-21 | 56147.94 | 56147.94
| Total Requested | 0 | Total Transferred |  |  | 81147.94 | 81147.94

## #9486.01 Horizon Architecture
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  | Major Program 4B03
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0506-335-DA26-9260 |  |  | TSB
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526118915 | 2026-04-28 | PO Procore | 12633 | 12633 |  |  | 12633
PRC 3352611PA8915 | 2026-06-16 | Inv. 9486.01-01 |  | 12633 | 3309.5 | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  |  |  | 12633 |  | 3309.5 | 9323.5
|  | Totals: | 12633 |  | 3309.5 |  | 9323.5
|  | Construction Docs | 6619 |  | 3309.5 |  | 3309.5
|  | Bidding Assistance | 1215 |  |  |  | 1215
|  | Construction Admin | 4799 |  |  |  | 4799
|  | Total: | 12633 |  | 3309.5 |  | 9323.5

## #9486.01 PM TIME
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 736M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 5000 | 15.22 | 15.22 | 4984.78
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 5000 | 162.5 | 177.72 | 4822.28
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 5000 | 38.19 | 215.91 | 4784.09
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 5000 | 472.3 | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
[5 empty] | 5000 |  | 688.21 | 4311.79
|  |  | Totals: | 5000 |  | 688.21 |  | 4311.79
Note on E9: Huggins, Joni [DAS]: 9486.00-.01 : Internal Budget Shifts and Project Setup (DA26 - MOU) FY26 Tonyan, Brad 1:35 PM (1 hour ago) to me, Joni, Brad, David, Scott Joni, As we discussed moments ago IVH/DAS/DCI Group would like to set up project 9486.01 as a sub job to the base project 9486.00. Details below on the next steps: 1. Setup Project 9486.01- DVA IVH Fox and Ulery Carpet Replacement - Sound Issues 2. 9486.00 - Reduce PM time budget from $30,000 to $10,000 and shift balance to general fund yet within project 9486.00 3. 9486.00 - Shift $25,000 from DA26 to sub project 9486.01 4. Set up a PM time budget of $5,000 4. Balance of $20,000 in general fund for 9486.01 Thank you and please reach out if you have any questions. Confirm when this is complete so we can start to issue the design contract. Brad Tonyan, CPM, LEED Green Associate

## #9486.01 Misc
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9486.01 DCI Group
DVA IVH Fox and Ulery Carpet Replacement - Sound Issues
Project # 9486.01
Program code 948601 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526153911 | 2026-06-02 | PO Procore | 14988.92 | 14988.92 |  |  | 14988.92
PRC 3352615PA3911 | 2026-06-16 | Inv. 25-023 PC #01 |  | 14988.92 | 2343.3 | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  |  |  | 14988.92 |  | 2343.3 | 12645.62
|  | Totals: | 14988.92 |  | 2343.3 |  | 12645.62
|  | Construction Management | 13988.92 |  | 2291.8 |  | 11697.12
|  | Reimbursables | 1000 |  | 51.5 |  | 948.5
|  | Total: | 14988.92 |  | 2343.3 |  | 12645.62

## RECAP #9487.00
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
| Program code 948700 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 1600000
C | DCI Group |  | 26121.39 | 26121.39 | 0
| PM TIME |  | 20000 | 11127.53 | 8872.47
| Misc. |  | 13213.1 | 13213.1 | 0
C | Genesis Architectural |  | 13500 | 13500 | 0
C | Genesis Architectural (2) |  | 4150 | 4150 | 0
| Genesis Architectural (3) |  | 71600 | 43100 | 28500
| DCI Group (2) |  | 210626.27 | 0 | 210626.27
| Keystone |  | 1100000 | 0 | 1100000
| Total Project Cost | 1600000 | 1459210.76 | 111212.02 | 1347998.74 | 140789.24

## #9487.00 Funds Rec'd
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925400 | 2025-07-29 | 500000 | 500000
|  |  | MOU Amendment #1 | IET052226100 | 2026-05-22 | 1100000 | 1100000
| Total Requested | 0 | Total Transferred |  |  | 1600000 | 1600000

## #9487.00 DCI Group
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255904 | 2025-09-12 | PO Procore | 29130.18 | 29130.18 |  |  | 29130.18
PRC 3352625PA5904 | 2025-12-03 | Inv. 25-024PC 01 |  | 29130.18 | 7266.66 | 7266.66 | 21863.52
PRC 3352625PB5904 | 2025-12-23 | Inv. 25-024 PC 02 |  | 29130.18 | 1220.22 | 8486.88 | 20643.3
PRC 3352625PC5904 | 2026-01-26 | Inv. 25-024 PC 03 |  | 29130.18 | 2810.82 | 11297.7 | 17832.48
PRC 3352625PD5904 | 2026-02-13 | Inv. 25-024 PC 04 |  | 29130.18 | 4564.35 | 15862.05 | 13268.13
PRC 3352625PE5904 | 2026-03-20 | Inv. 25-024 PC 05 |  | 29130.18 | 7005.12 | 22867.17 | 6263.01
PRC 3352625PF5904 | 2026-04-17 | Inv. 25-024 PC 06 |  | 29130.18 | 2203.72 | 25070.89 | 4059.29
PO 33526255904 | 2026-05-22 | CO #1 | 896 | 30026.18 |  | 25070.89 | 4955.29
PRC 3352625PG5904 | 2026-06-22 | Inv. 25-024 PC #07 - Final | -3904.79 | 26121.39 | 1050.5 | 26121.39 | 0
|  |  |  | 26121.39 |  | 26121.39 | 0
|  |  |  | 26121.39 |  | 26121.39 | 0
|  |  |  | 26121.39 |  | 26121.39 | 0
|  |  |  | 26121.39 |  | 26121.39 | 0
|  | Totals: | 26121.39 |  | 26121.39 |  | 0 | FINAL
|  | CM Services | 24374.76 |  | 24374.76 |  | 0
|  | Reimbursables | 850.63 |  | 850.63 |  | 0
|  | CO #1 | 896 |  | 896 |  | 0
|  | Total: | 26121.39 |  | 26121.39 |  | 0

## #9487.00 PM TIME
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 733U
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 33.7 | 33.7 | 19966.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 368.8 | 402.5 | 19597.5
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 99.87 | 502.37 | 19497.63
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 776.9 | 1279.27 | 18720.73
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 127.29 | 1406.56 | 18593.44
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 666.1 | 2072.66 | 17927.34
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 79.99 | 2152.65 | 17847.35
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 794.7 | 2947.35 | 17052.65
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 59.49 | 3006.84 | 16993.16
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 377.3 | 3384.14 | 16615.86
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 89.21 | 3473.35 | 16526.65
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 1008.2 | 4481.55 | 15518.45
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 107.3 | 4588.85 | 15411.15
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 1336.3 | 5925.15 | 14074.85
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 78.57 | 6003.72 | 13996.28
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 906.5 | 6910.22 | 13089.78
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 108.49 | 7018.71 | 12981.29
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 881.2 | 7899.91 | 12100.09
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 20000 | 136.08 | 8035.99 | 11964.01
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 20000 | 1420.5 | 9456.49 | 10543.51
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 20000 | 125.74 | 9582.23 | 10417.77
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 20000 | 1545.3 | 11127.53 | 8872.47
[5 empty] | 20000 |  | 11127.53 | 8872.47
|  |  | Totals: | 20000 |  | 11127.53 |  | 8872.47
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9487.00 Misc
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526068905 | 2026-03-09 | 9500 | BRUM | Waldinger #(00002116105) | Inv. 94204T-001 | 6702.99 | 6702.99
GAX 33526112903 | 2026-04-22 | 9500 | CNST | Waldinger #(00002116105) | Inv. 94204T-002 | 4047.47 | 10750.46
PRC 33526142910 | 2026-05-22 | 9500 | CNST | ATC Group #(00002134218) | Inv. 2712816 | 2002 | 12752.46
PRC 33526153915 | 2026-06-02 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV058197 | 460.64 | 13213.1
13213.1
13213.1
13213.1
13213.1
13213.1
13213.1
13213.1
13213.1
|  |  |  | Totals: |  | 13213.1

## #9487.00 Genesis Architectural
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP 948700-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526275905 | 2025-10-03 | PO Procore | 13500 | 13500 |  |  | 13500
PRC 3352627PA5905 | 2025-12-03 | Inv. 2515-01 |  | 13500 | 7020 | 7020 | 6480
PRC 3352627PB5905 | 2025-12-15 | Inv. 2515-02 |  | 13500 | 5910 | 12930 | 570
PRC 3352627PC5905 | 2026-05-12 | Inv. 2515-03 FINAL |  | 13500 | 570 | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  |  |  | 13500 |  | 13500 | 0
|  | Totals: | 13500 |  | 13500 |  | 0 | FINAL
|  | 50% Schematic Phase | 7800 |  | 7800 |  | 0
|  | 100% Schematic Phase | 5700 |  | 5700 |  | 0
|  | Total: | 13500 |  | 13500 |  | 0

## #9487.00 Genesis Architectu (2)
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Genesis Architectural (2) |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP 948700-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030915 | 2026-01-30 | PO Procore | 4150 | 4150 |  |  | 4150
PRC 3352603PA0915 | 2026-05-12 | Inv. 2515-04 FINAL |  | 4150 | 4150 | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  |  |  | 4150 |  | 4150 | 0
|  | Totals: | 4150 |  | 4150 |  | 0 | FINAL

## #9487.00 Genesis Architectu (3)
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Genesis Architectural (3) |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP 948700-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526092907 | 2026-04-02 | PO Procore | 71600 | 71600 |  |  | 71600
PRC 3352609PA2907 | 2026-05-11 | Inv. 2515-05 |  | 71600 | 43100 | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  |  |  | 71600 |  | 43100 | 28500
|  | Totals: | 71600 |  | 43100 |  | 28500
|  | Design Development 50% | 16340 |  | 16340 |  | 0
|  | Construction Document 95% | 21760 |  | 21760 |  | 0
|  | Construction Document 100% | 5000 |  | 5000 |  | 0
|  | Bid Phase | 5100 |  |  |  | 5100
|  | Coordination & Site Visit | 23400 |  |  |  | 23400
|  | Total: | 71600 |  | 43100 |  | 28500

## #9487.00 DCI Group (2)
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526148907 | 2026-05-28 | PO Procore | 210626.27 | 210626.27 |  |  | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  |  |  | 210626.27 |  | 0 | 210626.27
|  | Totals: | 210626.27 |  | 0 |  | 210626.27
|  | CM Services | 137842.27 |  |  |  | 137842.27
|  | Reimbursables | 17784 |  |  |  | 17784
|  | CO #1 | 55000 |  |  |  | 55000
|  | Total: | 210626.27 |  | 0 |  | 210626.27

## #9487.00 Keystone Construction
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Keystone Construction |  |  | Vendor: 00003165138
Acct. Codes-0506-335-DA26-9255 |  |  | RFB948700-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526156912 | 2026-06-04 | PO Procore | 1100000 | 1100000 |  |  | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  |  |  | 1100000 |  | 0 | 1100000
|  | Totals: | 1100000 |  | 0 |  | 1100000

## RECAP #9488.00
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 5663847
Samuels Group |  | 71389.88 | 62808.63 | 8581.25
PM TIME |  | 145000 | 22750.38 | 122249.62
Misc. |  | 3018.65 | 3018.65 | 0
SVPA Architects |  | 417400 | 332600 | 84800
Downs Electric, Inc |  | 739475 | 0 | 739475
Prairie Construction |  | 3269000 | 0 | 3269000
Elkhorn West Construction |  | 116625 | 0 | 116625
Samuels Group(2) |  | 766820.2 | 0 | 766820.2
Total Project Cost | 5663847 | 5528728.73 | 421177.66 | 5107551.07 | 135118.27

## #9488.00 Funds Rec'd
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26001 | 2025-08-15 | 4163847 | 4163847
|  |  | MOU Amendment #1 | IET 23812V26017 | 2026-03-04 | 1500000 | 1500000
| Total Requested | 0 | Total Transferred |  |  | 5663847 | 5663847

## #9488.00 Samuels Group
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526273900 | 2025-09-30 | PO Procore | 71389.88 | 71389.88 |  |  | 71389.88
PRC 3352627PA3900 | 2025-12-04 | Inv. 7813.01948800 |  | 71389.88 | 2720.91 | 2720.91 | 68668.97
PRC 3352627PB3900 | 2026-01-09 | Inv. 7813.02948800 |  | 71389.88 | 14355.26 | 17076.17 | 54313.71
PRC 3352627PC3900 | 2026-02-03 | Inv. 7813.03948800 |  | 71389.88 | 8929.44 | 26005.61 | 45384.27
PRC 3352627PD3900 | 2026-03-03 | Inv. 7813.04948800 |  | 71389.88 | 7930.4 | 33936.01 | 37453.87
PRC 3352627PE3900 | 2026-04-09 | Inv. 7813.05948800 |  | 71389.88 | 7678.84 | 41614.85 | 29775.03
PRC 3352627PF3900 | 2026-05-22 | Inv. 7813.06948800 |  | 71389.88 | 15413.63 | 57028.48 | 14361.4
PRC 3352627PG3900 | 2026-06-16 | Inv. 7813.07948800 |  | 71389.88 | 5780.15 | 62808.63 | 8581.25
|  |  |  | 71389.88 |  | 62808.63 | 8581.25
|  |  |  | 71389.88 |  | 62808.63 | 8581.25
|  |  |  | 71389.88 |  | 62808.63 | 8581.25
|  |  |  | 71389.88 |  | 62808.63 | 8581.25
|  |  |  | 71389.88 |  | 62808.63 | 8581.25
|  | Totals: | 71389.88 |  | 62808.63 |  | 8581.25
|  | CM Services | 63389.88 |  | 62445.63 |  | 944.25
|  | Reimbursables | 1000 |  | 363 |  | 637
|  | Reimbursables(Geotechnical) | 7000 |  |  |  | 7000
|  | Total: | 71389.88 |  | 62808.63 |  | 8581.25

## #9488.00 PM TIME
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 733W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 145000 | 145000 |  |  | 145000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 145000 | 85.66 | 85.66 | 144914.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 145000 | 657.1 | 742.76 | 144257.24
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 145000 | 132.45 | 875.21 | 144124.79
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 145000 | 681.1 | 1556.31 | 143443.69
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 145000 | 212.65 | 1768.96 | 143231.04
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 145000 | 2112.8 | 3881.76 | 141118.24
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 145000 | 286.09 | 4167.85 | 140832.15
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 145000 | 1818.7 | 5986.55 | 139013.45
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 145000 | 225.29 | 6211.84 | 138788.16
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 145000 | 2555.5 | 8767.34 | 136232.66
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 145000 | 140.6 | 8907.94 | 136092.06
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 145000 | 1751.3 | 10659.24 | 134340.76
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 145000 | 316.06 | 10975.3 | 134024.7
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 145000 | 3645.7 | 14621 | 130379
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 145000 | 259.58 | 14880.58 | 130119.42
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 145000 | 2105.7 | 16986.28 | 128013.72
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 145000 | 326.85 | 17313.13 | 127686.87
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 145000 | 3414.4 | 20727.53 | 124272.47
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 145000 | 148.15 | 20875.68 | 124124.32
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 145000 | 1874.7 | 22750.38 | 122249.62
[5 empty] | 145000 |  | 22750.38 | 122249.62
[5 empty] | 145000 |  | 22750.38 | 122249.62
[5 empty] | 145000 |  | 22750.38 | 122249.62
|  |  | Totals: | 145000 |  | 22750.38 |  | 122249.62
Note on E9: On Sat, Sep 20, 2025 at 2:15 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Sorry about that, Please establish DAS time for $145,000.00 in 9488.00. Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau

## #9488.00 Misc
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code: B90
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526146911 | 2026-05-26 | 9500 | CNST | ATC Group #(00002134218) | Inv. 2710754 | 1906 | 1906
PRC 33526146916 | 2026-05-26 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV058353 | 1112.65 | 3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
3018.65
|  |  |  | Totals: |  | 3018.65

## #9488.00 SVPA Architects
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
SVPA Architects |  |  | Vendor: 00002109254
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948800-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526310900 | 2025-11-06 | PO Procore | 417400 | 417400 |  |  | 417400
PRC 3352631PA0900 | 2025-12-16 | Inv. 0041003 |  | 417400 | 49030 | 49030 | 368370
PRC 3352631PB0900 | 2026-01-26 | Inv. 0041049 |  | 417400 | 43130 | 92160 | 325240
PRC 3352631PC0900 | 2026-02-24 | Inv. 0041130 |  | 417400 | 56640 | 148800 | 268600
PRC 3352631PD0900 | 2026-03-23 | Inv. 0041202 |  | 417400 | 74240 | 223040 | 194360
PRC 3352631PE0900 | 2026-04-16 | Inv. 0041249 |  | 417400 | 82480 | 305520 | 111880
PRC 3352631PF0900 | 2026-05-20 | Inv. 0041317 |  | 417400 | 8080 | 313600 | 103800
PRC 3352631PG0900 | 2026-06-16 | Inv. 0041465 |  | 417400 | 19000 | 332600 | 84800
|  |  |  | 417400 |  | 332600 | 84800
|  |  |  | 417400 |  | 332600 | 84800
|  |  |  | 417400 |  | 332600 | 84800
|  |  |  | 417400 |  | 332600 | 84800
|  |  |  | 417400 |  | 332600 | 84800
|  | Totals: | 417400 |  | 332600 |  | 84800
|  | Schematic Design | 72800 |  | 72800 |  | 0
|  | Design Development | 54600 |  | 54600 |  | 0
|  | Construction Documents | 145600 |  | 145600 |  | 0
|  | Bidding/ Negotiation | 18200 |  | 18200 |  | 0
|  | Construction Admin | 72800 |  |  |  | 72800
|  | Furniture | 16000 |  | 4000 |  | 12000
|  | Renovation Schematic Design | 21400 |  | 21400 |  | 0
|  | Renovation Design Development | 16000 |  | 16000 |  | 0
|  | Total: | 417400 |  | 332600 |  | 84800

## #9488.00 Downs Electric
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Downs Electric |  |  | Vendor: 00003216356
Acct. Codes-0506-335-DA26-9255 |  |  | RFB948800-01
Project Manager - Jennie E |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526168914 | 2026-06-17 | PO Procore | 739475 | 739475 |  |  | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  |  |  | 739475 |  | 0 | 739475
|  | Totals: | 739475 |  | 0 |  | 739475

## #9488.00 PrairieConstruction
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Prairie Construction |  |  | Vendor: 00003237923
Acct. Codes-0506-335-DA26-9255 |  |  | RFB948800-01
Project Manager - Jennie E |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526168915 | 2026-06-17 | PO Procore | 3269000 | 3269000 |  |  | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  |  |  | 3269000 |  | 0 | 3269000
|  | Totals: | 3269000 |  | 0 |  | 3269000

## #9488.00 Elkhorn West Construct
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Elkhorn West Construction |  |  | Vendor: 00002142795
Acct. Codes-0506-335-DA26-9255 |  |  | RFB948800-01
Project Manager - Jennie E |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526168916 | 2026-06-17 | PO Procore | 116625 | 116625 |  |  | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  |  |  | 116625 |  | 0 | 116625
|  | Totals: | 116625 |  | 0 |  | 116625

## #9488.00 Samuels Group (2)
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Samuels Group (2) |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176922 | 2026-06-25 | PO Procore | 766820.2 | 766820.2 |  |  | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  |  |  | 766820.2 |  | 0 | 766820.2
|  | Totals: | 766820.2 |  | 0 |  | 766820.2
|  | CM Services | 488368.2 |  |  |  | 488368.2
|  | Reimbursables(Mileage) | 43108 |  |  |  | 43108
|  | Reimbursables(Temp Fence | 7500 |  |  |  | 7500
|  | Reimbursables(Trailer/Power/Heat) | 8400 |  |  |  | 8400
|  | Reimbursables(Power/Utility Service) | 3600 |  |  |  | 3600
|  | Reimbursables(Dumpsters) | 12000 |  |  |  | 12000
|  | Reimbursables(Building Temp) | 9040 |  |  |  | 9040
|  | Reimbursables(Temp Toilets) | 4800 |  |  |  | 4800
|  | Reimbursables(Special Inspections) | 25000 |  |  |  | 25000
|  | 4% SG Fees | 165004 |  |  |  | 165004
|  | Total: | 766820.2 |  | 0 |  | 766820.2

## RECAP #9489.00
DOC & ASP TWID Repairs
Project # 9489.00
| Program code 948900 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 50000
C | McGough Construction |  | 4908.62 | 4908.62 | 0
| PM TIME |  | 5000 | 4872.04 | 127.96
| Misc. |  | 0 | 0 | 0
| Total Project Cost | 50000 | 9908.62 | 9780.66 | 127.96 | 40091.38

## #9489.00 Funds Rec'd
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26002 | 2025-08-19 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9489.00 McGough Construction
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526279900 | 2025-10-06 | PO Procore | 16402.42 | 16402.42 |  |  | 16402.42
PRC 3352627PA9900 | 2026-02-13 | Inv. 101368.014PC-01 - FINAL PC | -11493.8 | 4908.62 | 4908.62 | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  |  |  | 4908.62 |  | 4908.62 | 0
|  | Totals: | 4908.62 |  | 4908.62 |  | 0 | FINAL
|  | CM Services | 4768.62 |  | 4768.62 |  | 0
|  | Reimbursables | 140 |  | 140 |  | 0
|  | Total: | 4908.62 |  | 4908.62 |  | 0

## #9489.00 PM TIME
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 734A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 5000 | 54.39 | 54.39 | 4945.61
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 5000 | 415.5 | 469.89 | 4530.11
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 5000 | 28.98 | 498.87 | 4501.13
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 5000 | 286.6 | 785.47 | 4214.53
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 5000 | 12.23 | 797.7 | 4202.3
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 5000 | 79.3 | 877 | 4123
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 5000 | 38.27 | 915.27 | 4084.73
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 5000 | 435.2 | 1350.47 | 3649.53
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 5000 | 142.26 | 1492.73 | 3507.27
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 5000 | 1771 | 3263.73 | 1736.27
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 5000 | 31.01 | 3294.74 | 1705.26
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 5000 | 356.5 | 3651.24 | 1348.76
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 5000 | 33.1 | 3684.34 | 1315.66
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 5000 | 268.4 | 3952.74 | 1047.26
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 5000 | 48.08 | 4000.82 | 999.18
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 5000 | 501.2 | 4502.02 | 497.98
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 5000 | 27.82 | 4529.84 | 470.16
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 5000 | 342.2 | 4872.04 | 127.96
[5 empty] | 5000 |  | 4872.04 | 127.96
[5 empty] | 5000 |  | 4872.04 | 127.96
[5 empty] | 5000 |  | 4872.04 | 127.96
|  |  | Totals: | 5000 |  | 4872.04 |  | 127.96
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (23 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon.

## #9489.00 Misc
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 163
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9490.00
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
| Program code 949000 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 20787.56
C | VendorA |  | 0 | 0 | 0
C | PM TIME |  | 2127.56 | 2127.56 | -4.5475e-13
C | Misc. |  | 18660 | 18660 | 0
| Total Project Cost | 20787.56 | 20787.56 | 20787.56 | 0 | 0
Closed 11/12/25

## #9490.00 Funds Rec'd
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 245269490 | 2025-08-29 | 25000 | 25000
|  |  | Return funds to agency- closing program | IET 33526316900 | 2025-11-12 | -4212.44 | -4212.44
| Total Requested | 0 | Total Transferred |  |  | 20787.56 | 20787.56

## #9490.00 Vendor A
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9490.00 PM TIME
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 734C
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 2127.56 | 2127.56 |  |  | 2127.56
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 2127.56 | 94.58 | 94.58 | 2032.98
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 2127.56 | 732.6 | 827.18 | 1300.38
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 2127.56 | 127.29 | 954.47 | 1173.09
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 2127.56 | 666.1 | 1620.57 | 506.99
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 2127.56 | 46.49 | 1667.06 | 460.5
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 2127.56 | 460.5 | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
[5 empty] | 2127.56 |  | 2127.56 | 1.1369e-13
|  |  | Totals: | 2127.56 |  | 2127.56 |  | -4.5475e-13
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9490.00 Misc
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526259906 | 2025-09-16 | 9500 | DSGN | Shive Hattery V#(00002108803) | Inv. 2250015060-1 | 14700 | 14700
GAX 33526294900 | 2025-10-21 | 9500 | DSGN | Shive Hattery V#(00002108803) | Inv. 2250015060-2 | 3960 | 18660
18660
18660
18660
18660
18660
18660
18660
18660
18660
18660
|  |  |  | Totals: |  | 18660

## RECAP #9492.00
ATOD Racking Modification
Project # 9492.00
| Program code 949200 |  |  | Major Program 4H06
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Funds received per MOU | 79014.54
C | Samuels Group |  | 14675.17 | 14675.17 | 0
C | PM TIME |  | 6839.37 | 6839.37 | 0
C | Misc. |  | 0 | 0 | 0
C | Quick Enterprise LLC |  | 57500 | 57500 | 0
| Total Project Cost | 79014.54 | 79014.54 | 79014.54 | 0 | 0
Closed 06/16/26

## #9492.00 Funds Rec'd
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DAS9492RACKING | 2025-09-18 | 86150 | 86150
|  |  | Returning funds to agency-Closing Project | IET 33526167913 | 2026-06-16 | -7135.46 | -7135.46
| Total Requested | 0 | Total Transferred |  |  | 79014.54 | 79014.54

## #9492.00 Samuels Group
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526269901 | 2025-09-26 | PO Procore | 14675.17 | 14675.17 |  |  | 14675.17
PRC 3352626PA9901 | 2025-12-11 | Inv. 7815.00 CA |  | 14675.17 | 8361.58 | 8361.58 | 6313.59
PRC 3352626PB9901 | 2026-01-14 | Inv. 7815.01 CA |  | 14675.17 | 1685.6 | 10047.18 | 4627.99
PRC 3352626PC9901 | 2026-02-05 | Inv. 7815.02 CA |  | 14675.17 | 1975.83 | 12023.01 | 2652.16
PRC 3352626PD9901 | 2026-04-30 | Inv. 7815.03 CA FINAL |  | 14675.17 | 2652.16 | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  |  |  | 14675.17 |  | 14675.17 | 0
|  | Totals: | 14675.17 |  | 14675.17 |  | 0 | FINAL

## #9492.00 PM TIME
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 911G
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 6839.37 | 6839.37 |  |  | 6839.37
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 6839.37 | 36.12 | 36.12 | 6803.25
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 6839.37 | 276.6 | 312.72 | 6526.65
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 6839.37 | 117.29 | 430.01 | 6409.36
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 6839.37 | 604.5 | 1034.51 | 5804.86
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 6839.37 | 115.91 | 1150.42 | 5688.95
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 6839.37 | 1149.1 | 2299.52 | 4539.85
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 6839.37 | 199.27 | 2498.79 | 4340.58
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 6839.37 | 1269.7 | 3768.49 | 3070.88
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 6839.37 | 107.3 | 3875.79 | 2963.58
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 6839.37 | 1217.6 | 5093.39 | 1745.98
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 6839.37 | 74.43 | 5167.82 | 1671.55
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 6839.37 | 924.6 | 6092.42 | 746.95
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 6839.37 | 23.17 | 6115.59 | 723.78
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 6839.37 | 266.8 | 6382.39 | 456.98
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 6839.37 | 39.48 | 6421.87 | 417.5
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 6839.37 | 417.5 | 6839.37 | -5.6843e-14
[5 empty] | 6839.37 |  | 6839.37 | -5.6843e-14
[5 empty] | 6839.37 |  | 6839.37 | -5.6843e-14
[5 empty] | 6839.37 |  | 6839.37 | -5.6843e-14
|  |  | Totals: | 6839.37 |  | 6839.37 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (24 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon. Re: December PM Time has been posted $Joni Shimp, Oliver 11:37 AM (1 hour ago) to me For my projects could you please, 5800 9473.00, Add $5,000.00 from unallocated to PM time. DA26 9492.00, Add $3,000.00 from unallocated to PM time. MM24 9386.01, Add $6,000.00 from unallocated to PM time. Thank you! Oliver

## #9492.00 Misc
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9492.00 Quick Enterprise LLC
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Quick Enterprise LLC |  |  | Vendor: 00003198873
Acct. Codes-0506-335-DA26-9255 |  |  | RFQ949200-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526309900 | 2025-11-05 | PO Procore | 27500 | 27500 |  |  | 27500
PO 33526309900 | 2025-12-10 | CO #1 | 30000 | 57500 |  | 0 | 57500
PRC 3352630PA9900 | 2026-03-03 | Inv. 16402 |  | 57500 | 55508.25 | 55508.25 | 1991.75 | 1716.75
PRC 3352630PB9900 | 2026-04-16 | Inv. 16409 |  | 57500 | 266.75 | 55775 | 1725 | 1725
PRC 3352630PC9900 | 2026-04-23 | Inv. 16410 "Retainage" |  | 57500 | 1725 | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  |  |  | 57500 |  | 57500 | 0
|  | Totals: | 57500 |  | 57500 |  | 0 | FINAL
3% Retainage

## RECAP #9515.00
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 100000
Kezlo Group |  | 29400 | 21850 | 7550
PM TIME |  | 10000 | 6178.4 | 3821.6
Misc. |  | 0 | 0 | 0
Total Project Cost | 100000 | 39400 | 28028.4 | 11371.6 | 60600

## #9515.00 Funds Rec'd
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 33528JA26KAS0126 | 2026-01-28 | 25000 | 25000
|  |  | MOU | IET 33508MY26KAS0226 | 2026-05-08 | 75000 | 75000
| Total Requested | 0 | Total Transferred |  |  | 100000 | 100000

## #9515.00 Kezlo Group
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  | Major Program 4E08
Kezlo Group |  |  | Vendor: 00003234487
Acct. Codes-0506-335-DA26-9260 |  |  | RFP951500-01
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526132905 | 2026-05-12 | PO Procore | 29400 | 29400 |  |  | 29400
PRC 3352613PA2905 | 2026-06-15 | Inv. 26-039.01 |  | 29400 | 21850 | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  |  |  | 29400 |  | 21850 | 7550
|  | Totals: | 29400 |  | 21850 |  | 7550
|  | Construction Docs | 21850 |  | 21850 |  | 0
|  | Bidding Assistance | 620 |  |  |  | 620
|  | Construction Phase | 6930 |  |  |  | 6930
|  | Total: | 29400 |  | 21850 |  | 7550

## #9515.00 PM TIME
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  |  | Major Program 4E08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 735M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 10000 | 10000 |  |  | 10000
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 10000 | 62.08 | 62.08 | 9937.92
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 10000 | 700.4 | 762.48 | 9237.52
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 10000 | 68.26 | 830.74 | 9169.26
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 10000 | 852.4 | 1683.14 | 8316.86
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10000 | 33.1 | 1716.24 | 8283.76
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10000 | 383.8 | 2100.04 | 7899.96
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10000 | 273.26 | 2373.3 | 7626.7
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10000 | 2237.6 | 4610.9 | 5389.1
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10000 | 907.5 | 5518.4 | 4481.6
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 660 | 6178.4 | 3821.6
[5 empty] | 10000 |  | 6178.4 | 3821.6
[5 empty] | 10000 |  | 6178.4 | 3821.6
|  |  | Totals: | 10000 |  | 6178.4 |  | 3821.6
Note on E9: Adams, Brandon 12:33 PM (37 minutes ago) to me Please set the PM Time to $2,500. Regards, Adams, Brandon ​Huggins, Joni​ Please increase DA26 9515.00 PM time by $4,500 Regards, Brandon Adams

## #9515.00 Misc
DPS District 1 Intel Remodel
Project # 9515.00
Program code 951500 |  |  |  | Major Program 4E08
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 1515
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9516.00
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  | Major Program 4E19
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 185000
DCI Group |  | 22487.1 | 0 | 22487.1
PM TIME |  | 1819.65 | 1819.65 | 0
Misc. |  | 0 | 0 | 0
Substance LLC |  | 139350 | 0 | 139350
Total Project Cost | 185000 | 163656.75 | 1819.65 | 161837.1 | 21343.25

## #9516.00 Funds Rec'd
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  | Major Program 4E19
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 627DB2610507 | 2026-04-16 | 185000 | 185000
| Total Requested | 0 | Total Transferred |  |  | 185000 | 185000

## #9516.00 PM TIME
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 736I
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 1819.65 | 1819.65 |  |  | 1819.65
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 1819.65 | 104.43 | 104.43 | 1715.22
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 1819.65 | 1093.8 | 1198.23 | 621.42
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 1819.65 | 46.92 | 1245.15 | 574.5
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 1819.65 | 574.5 | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
[5 empty] | 1819.65 |  | 1819.65 | 1.1369e-13
|  |  | Totals: | 1819.65 |  | 1819.65 |  | 0
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Elliott, Jennie Huggins, Joni​ Please increase PM time in each of these project to accommodate May PM time. DA26 9516.00 increase PM time budget by $621.42 FLEE 9479.00 increase PM time budget by $832.31 PARK 9518.00 increase PM time budget by $1,401.88 Thank you, Jennie Elliott

## #9516.00 Misc
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  |  | Major Program 4E19
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9516.00 DCI Group
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526110913 | 2026-04-20 | PO Procore | 22487.1 | 22487.1 |  |  | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  |  |  | 22487.1 |  | 0 | 22487.1
|  | Totals: | 22487.1 |  | 0 |  | 22487.1
|  | CM Services | 17487.1 |  |  |  | 17487.1
|  | Reimbursables | 5000 |  |  |  | 5000
|  | Total: | 22487.1 |  | 0 |  | 22487.1

## #9516.00 Substance LLC
IDR State of Iowa Building Renovation
Project # 9516.00
Program code 951600 |  |  | Major Program 4E19
Substance LLC |  |  | Vendor: 00002126433
Acct. Codes-0506-335-DA26-9260 |  |  | RFP951600-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526148909 | 2026-06-02 | PO Procore | 139350 | 139350 |  |  | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  |  |  | 139350 |  | 0 | 139350
|  | Totals: | 139350 |  | 0 |  | 139350
|  | Data Collection | 18150 |  |  |  | 18150
|  | Schematic Design | 46800 |  |  |  | 46800
|  | Design Development | 74400 |  |  |  | 74400
|  | Total: | 139350 |  | 0 |  | 139350

## RECAP #9517.00
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 300000
DCI Group |  | 54794.54 | 17176.69 | 37617.85
PM TIME |  | 15000 | 5724.07 | 9275.93
Misc. |  | 0 | 0 | 0
Shive Hattery |  | 134870 | 113815 | 21055
Total Project Cost | 300000 | 204664.54 | 136715.76 | 67948.78 | 95335.46

## #9517.00 Funds Rec'd
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET010526100 | 2026-01-05 | 300000 | 300000
| Total Requested | 0 | Total Transferred |  |  | 300000 | 300000

## #9517.00 DCI Group
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526009906 | 2026-01-09 | PO Procore | 48848.62 | 48848.62 |  |  | 48848.62
PRC 3352600PA9906 | 2026-02-16 | Inv. 9517.00 PC 01 |  | 48848.62 | 6181.76 | 6181.76 | 42666.86
PO 33526009906 | 2026-03-09 | CO #1 | 5945.92 | 54794.54 |  | 6181.76 | 48612.78
PRC 3352600PB9906 | 2026-03-26 | Inv. 9517.00 PC 02 |  | 54794.54 | 4156.18 | 10337.94 | 44456.6
PRC 3352600PC9906 | 2026-04-15 | Inv. 9517.00 PC 03 |  | 54794.54 | 2162.87 | 12500.81 | 42293.73
PRC 3352600PD9906 | 2026-05-12 | Inv. 9517.00 PC #04 |  | 54794.54 | 2820.75 | 15321.56 | 39472.98
PRC 3352600PE9906 | 2026-06-15 | Inv. 9517.00 PC #05 |  | 54794.54 | 1855.13 | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  |  |  | 54794.54 |  | 17176.69 | 37617.85
|  | Totals: | 54794.54 |  | 17176.69 |  | 37617.85
|  | CM Services | 39848.62 |  | 17176.69 |  | 22671.93
|  | Reimbursables | 9000 |  |  |  | 9000
|  | CO #1 | 5945.92 |  |  |  | 5945.92
|  | Total: | 54794.54 |  | 17176.69 |  | 37617.85

## #9517.00 PM TIME
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  |  | Major Program 4E09
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 735N
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 15000 | 15000 |  |  | 15000
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 15000 | 130.35 | 130.35 | 14869.65
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 15000 | 1619 | 1749.35 | 13250.65
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 15000 | 85.64 | 1834.99 | 13165.01
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 15000 | 991.8 | 2826.79 | 12173.21
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 15000 | 129.57 | 2956.36 | 12043.64
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 15000 | 1050.1 | 4006.46 | 10993.54
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 15000 | 93.73 | 4100.19 | 10899.81
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 15000 | 974 | 5074.19 | 9925.81
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 15000 | 48.58 | 5122.77 | 9877.23
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 15000 | 601.3 | 5724.07 | 9275.93
[5 empty] | 15000 |  | 5724.07 | 9275.93
[5 empty] | 15000 |  | 5724.07 | 9275.93
|  |  | Totals: | 15000 |  | 5724.07 |  | 9275.93

## #9517.00 Misc
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  |  | Major Program 4E09
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T. |  |  |  | Shipping Code: 1012
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9517.00 Shive Hattery
DVA IVC Columbarium And Irrigation System Expansion
Project # 9517.00
Program code 951700 |  |  | Major Program 4E09
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0506-335-DA26-9260 |  |  | SS-0034
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526020902 | 2026-01-20 | PO Procore | 126620 | 126620 |  |  | 126620
PRC 3352602PA0902 | 2026-03-16 | Inv. 2250022390-1 |  | 126620 | 65560 | 65560 | 61060
PRC 3352602PB0902 | 2026-04-23 | Inv. 2250022390-2 |  | 126620 | 35860 | 101420 | 25200
PO 33526020902 | 2026-05-12 | CO #1 | 8250 | 134870 |  | 101420 | 33450
PRC 3352602PC0902 | 2026-06-26 | Inv. 2250022390-3 |  | 134870 | 12395 | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  |  |  | 134870 |  | 113815 | 21055
|  | Totals: | 134870 |  | 113815 |  | 21055
|  | Columbarium Schematic | 33540 |  | 33540 |  | 0
|  | Columbarium Design | 24300 |  | 24300 |  | 0
|  | Columbarium Document | 15800 |  | 15800 |  | 0
|  | Columbarium Bidding | 3180 |  |  |  | 3180
|  | Columbarium Construction | 15400 |  |  |  | 15400
|  | IVC Irrigation Water Supply Documents | 18400 |  | 18400 |  | 0
|  | IVC Irrigation Controls Documents | 16000 |  | 16000 |  | 0
|  | CO #1 | 8250 |  | 5775 |  | 2475
|  | Total: | 134870 |  | 113815 |  | 21055

## RECAP #9532.00
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  | Major Program 4E08
Recap
Acct. Codes-0506-335-DA26
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 295000
McGough Construction |  | 12352.15 | 4983.89 | 7368.26
PM TIME |  | 8000 | 3778.71 | 4221.29
Misc. |  | 0 | 0 | 0
OPN Architects |  | 35310 | 5400.9 | 29909.1
Total Project Cost | 295000 | 55662.15 | 14163.5 | 41498.65 | 239337.85

## #9532.00 Funds Rec'd
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  | Major Program 4E08
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - James T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 33505FE26KAS1026 | 2026-02-06 | 100000 | 100000
|  |  | MOU Transfer #2 | IET 33513FE26KAS0726 | 2026-02-13 | 195000 | 195000
| Total Requested | 0 | Total Transferred |  |  | 295000 | 295000

## #9532.00 McGough Construction
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  | Major Program 4E08
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - James T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526047909 | 2026-02-16 | PO Procore | 12352.15 | 12352.15 |  |  | 12352.15
PRC 3352604PA7909 | 2026-03-17 | Inv. 101537.006-PC01 |  | 12352.15 | 1421.62 | 1421.62 | 10930.53
PRC 3352604PB7909 | 2026-04-15 | Inv. 101537.006-PC02 |  | 12352.15 | 1550.69 | 2972.31 | 9379.84
PRC 3352604PC7909 | 2026-05-19 | Inv. 101537.006-PC03 |  | 12352.15 | 823.14 | 3795.45 | 8556.7
PRC 3352604PD7909 | 2026-06-03 | Inv. 101537.006-PC04 |  | 12352.15 | 1188.44 | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  |  |  | 12352.15 |  | 4983.89 | 7368.26
|  | Totals: | 12352.15 |  | 4983.89 |  | 7368.26

## #9532.00 PM TIME
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  |  | Major Program 4E08
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - James T |  |  |  | eDAS: 735Y
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 8000 | 93.92 | 93.92 | 7906.08
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 8000 | 1080.9 | 1174.82 | 6825.18
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 8000 | 86.97 | 1261.79 | 6738.21
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 8000 | 711.2 | 1972.99 | 6027.01
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 8000 | 69.47 | 2042.46 | 5957.54
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 8000 | 726.1 | 2768.56 | 5231.44
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 8000 | 75.95 | 2844.51 | 5155.49
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 8000 | 934.2 | 3778.71 | 4221.29
[5 empty] | 8000 |  | 3778.71 | 4221.29
[5 empty] | 8000 |  | 3778.71 | 4221.29
[5 empty] | 8000 |  | 3778.71 | 4221.29
[5 empty] | 8000 |  | 3778.71 | 4221.29
|  |  | Totals: | 8000 |  | 3778.71 |  | 4221.29

## #9532.00 Misc
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  |  | Major Program 4E08
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - James T |  |  |  | Shipping Code: S24
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9532.00 OPN Architects
DPS-DCI ANK Room A155, A156 and A157 Renovation
Project # 9532.00
Program code 953200 |  |  | Major Program 4E08
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA26-9260 |  |  | RFP953200-01
Project Manager - James T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526092910 | 2026-04-02 | PO Procore | 35310 | 35310 |  |  | 35310
PRC 3352609PA2910 | 2026-05-19 | Inv. 26819000-1 |  | 35310 | 2700.45 | 2700.45 | 32609.55
PRC 3352609PB2910 | 2026-06-03 | Inv. 26819000-2 |  | 35310 | 2700.45 | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  |  |  | 35310 |  | 5400.9 | 29909.1
|  | Totals: | 35310 |  | 5400.9 |  | 29909.1
|  | Design Development Docs | 10590 |  | 5400.9 |  | 5189.1
|  | Construction Docs | 10290 |  |  |  | 10290
|  | Bidding Phase | 2460 |  |  |  | 2460
|  | Construction Phase | 11970 |  |  |  | 11970
|  | Total: | 35310 |  | 5400.9 |  | 29909.1

## RECAP #9534.00
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  | Major Program 4H06
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 274331.09
Samuels Group |  | 9399.56 | 6813.42 | 2586.14
PM TIME |  | 5000 | 4257.48 | 742.52
Misc. |  | 0 | 0 | 0
10Fold Architecture + Engineering |  | 22132 | 2340 | 19792
Total Project Cost | 274331.09 | 36531.56 | 13410.9 | 23120.66 | 237799.53

## #9534.00 Funds Rec'd
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  | Major Program 4H06
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DAS022526RAMP | 2026-02-26 | 274331.09 | 274331.09
| Total Requested | 0 | Total Transferred |  |  | 274331.09 | 274331.09

## #9534.00 Samuels Group
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  | Major Program 4H06
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526062910 | 2026-03-03 | PO Procore | 9399.56 | 9399.56 |  |  | 9399.56
PRC 3352606PA2910 | 2026-04-30 | Inv. 7863.9534.01 PC |  | 9399.56 | 3440.3 | 3440.3 | 5959.26
PRC 3352606PB2910 | 2026-06-15 | Inv. 7863.9534.02 PC |  | 9399.56 | 3373.12 | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  |  |  | 9399.56 |  | 6813.42 | 2586.14
|  | Totals: | 9399.56 |  | 6813.42 |  | 2586.14
|  | CM Services | 9399.56 |  | 6813.42 |  | 2586.14
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 9399.56 |  | 6813.42 |  | 2586.14

## #9534.00 PM TIME
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  |  | Major Program 4H06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 736A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 5000 | 23.17 | 23.17 | 4976.83
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 5000 | 266.8 | 289.97 | 4710.03
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 5000 | 131.67 | 421.64 | 4578.36
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 5000 | 1074.2 | 1495.84 | 3504.16
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 5000 | 143.91 | 1639.75 | 3360.25
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 5000 | 1504.2 | 3143.95 | 1856.05
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 5000 | 84.23 | 3228.18 | 1771.82
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 5000 | 1029.3 | 4257.48 | 742.52
[5 empty] | 5000 |  | 4257.48 | 742.52
[5 empty] | 5000 |  | 4257.48 | 742.52
[5 empty] | 5000 |  | 4257.48 | 742.52
[5 empty] | 5000 |  | 4257.48 | 742.52
|  |  | Totals: | 5000 |  | 4257.48 |  | 742.52
Note on E9: Huggins, Joni [DAS]: Re: February PM Time Posted $Joni Shimp, Oliver Mar 13, 2026, 8:26 AM (3 days ago) to me Good Morning, Thank for you the list, could you please make the following adjustments? DA25 9358.01 $(361.98) Please move $5,000.00 from unallocated to PM Time DA26 9534.00 $(298.97) Please move $5,000.00 from unallocated to PM Time

## #9534.00 Misc
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  |  | Major Program 4H06
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9534.00 10Fold Architecture
IDR ATOD Will call Ramp Replacement
Project # 9534.00
Program code 953400 |  |  | Major Program 4H06
10Fold Architecture + Engineering |  |  | Vendor: 00003101228
Acct. Codes-0506-335-DA26-9260 |  |  | RFP953400-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526112907 | 2026-04-22 | PO Procore | 22132 | 22132 |  |  | 22132
PRC 3352611PA2907 | 2026-05-19 | Inv. 9534.00-01 |  | 22132 | 2340 | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  |  |  | 22132 |  | 2340 | 19792
|  | Totals: | 22132 |  | 2340 |  | 19792
|  | Design Development Docs | 5200 |  | 2340 |  | 2860
|  | Construction Docs | 6680 |  |  |  | 6680
|  | Bidding/Negotiation | 840 |  |  |  | 840
|  | Construction Phase | 8860 |  |  |  | 8860
|  | Reimbursables | 552 |  |  |  | 552
|  | Total: | 22132 |  | 2340 |  | 19792

## RECAP #9535.00
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  | Major Program 4G01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 810000
Story Construction |  | 19055.65 | 4055.5 | 15000.15
PM TIME |  | 18000 | 2122.26 | 15877.74
Misc. |  | 0 | 0 | 0
Genesis Architectural Design |  | 28800 | 0 | 28800
Total Project Cost | 810000 | 65855.65 | 6177.76 | 59677.89 | 744144.35

## #9535.00 Funds Rec'd
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  | Major Program 4G01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DASMOU953500 | 2026-03-04 | 810000 | 810000
| Total Requested | 0 | Total Transferred |  |  | 810000 | 810000

## #9535.00 Story Construction
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  | Major Program 4G01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526075906 | 2026-03-16 | PO Procore | 19055.65 | 19055.65 |  |  | 19055.65
PRC 3352607PA5906 | 2026-05-26 | Inv. 35266 |  | 19055.65 | 2836.53 | 2836.53 | 16219.12
PRC 3352607PB5906 | 2026-06-17 | Inv. 35302 |  | 19055.65 | 1218.97 | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  |  |  | 19055.65 |  | 4055.5 | 15000.15
|  | Totals: | 19055.65 |  | 4055.5 |  | 15000.15
|  | CM Services | 18996.65 |  | 3996.5 |  | 15000.15
|  | Reimbursables | 59 |  | 59 |  | 0
|  | Total: | 19055.65 |  | 4055.5 |  | 15000.15

## #9535.00 PM TIME
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 736B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 18000 | 18000 |  |  | 18000
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 18000 | 60.04 | 60.04 | 17939.96
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 18000 | 493.1 | 553.14 | 17446.86
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 18000 | 81.38 | 634.52 | 17365.48
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 18000 | 846.5 | 1481.02 | 16518.98
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 18000 | 48.14 | 1529.16 | 16470.84
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 18000 | 593.1 | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
[5 empty] | 18000 |  | 2122.26 | 15877.74
|  |  | Totals: | 18000 |  | 2122.26 |  | 15877.74

## #9535.00 Misc
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  |  | Major Program 4G01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9535.00 Genesis Architectural
HHS WRC Linden Court Bay Window Replacement
Project # 9535.00
Program code 953500 |  |  | Major Program 4G01
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | RFP953500-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526131913 | 2026-05-11 | PO Procore | 28800 | 28800 |  |  | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  |  |  | 28800 |  | 0 | 28800
|  | Totals: | 28800 |  | 0 |  | 28800
|  | Construction Docs | 17100 |  |  |  | 17100
|  | Bid Phase | 1600 |  |  |  | 1600
|  | Construction Phase | 10100 |  |  |  | 10100
|  | Total: | 28800 |  | 0 |  | 28800

## RECAP #9540.00
HHS CHMHI CCUSO Strategic Space Plan Study
Project # 9540.00
Program code 954000 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 150000
Clark & Enersen, Inc |  | 89500 | 0 | 89500
PM TIME |  | 12000 | 4879.29 | 7120.71
Misc. |  | 0 | 0 | 0
Total Project Cost | 150000 | 101500 | 4879.29 | 96620.71 | 48500

## #9540.00 Funds Rec'd
HHS CHMHI CCUSO Strategic Space Plan Study
Project # 9540.00
Program code 954000 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 41JP2603262601 | 2026-03-26 | 150000 | 150000
| Total Requested | 0 | Total Transferred |  |  | 150000 | 150000

## #9540.00 Clark & Enersen
HHS CHMHI CCUSO Strategic Space Plan Study
Project # 9540.00
Program code 954000 |  |  | Major Program 4B02
Clark & Enersen |  |  | Vendor: 00003237886
Acct. Codes-0506-335-DA26-9260 |  |  | RFP954000-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
33526173911 | 2026-06-22 | PO Procore | 89500 | 89500 |  |  | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  |  |  | 89500 |  | 0 | 89500
|  | Totals: | 89500 |  | 0 |  | 89500
|  | Initial Eval/Kick-Off | 51015 |  |  |  | 51015
|  | 50% Documents | 19690 |  |  |  | 19690
|  | 95% Documents | 9845 |  |  |  | 9845
|  | 100% Documents | 8950 |  |  |  | 8950
|  | Total: | 89500 |  | 0 |  | 89500

## #9540.00 PM TIME
HHS CHMHI CCUSO Strategic Space Plan Study
Project # 9540.00
Program code 954000 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 736H
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 12000 | 12000 |  |  | 12000
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 12000 | 124.6 | 124.6 | 11875.4
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 12000 | 1010.2 | 1134.8 | 10865.2
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 12000 | 217.9 | 1352.7 | 10647.3
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 12000 | 2386.8 | 3739.5 | 8260.5
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 12000 | 85.89 | 3825.39 | 8174.61
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 12000 | 1053.9 | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
[5 empty] | 12000 |  | 4879.29 | 7120.71
|  |  | Totals: | 12000 |  | 4879.29 |  | 7120.71
Note on E9: Huggins, Joni [DAS]: Re: March PM Time Posted $Joni Elliott, Jennie Fri, Apr 10, 2:19 PM (3 days ago) to me Please establish a PM Time Budget of $12,000 in project 9540.00. Thank you! Jennie Elliott

## #9540.00 Misc
HHS CHMHI CCUSO Strategic Space Plan Study
Project # 9540.00
Program code 954000 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E. |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## Funds Rec'd incorrectly
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | FY26 Funds recv'd for 9211.01 | IET IET091125100 | 2025-09-11 | 46034.4 | 46034.4
|  |  | Transfer Funds to Correct Unit | CDR 33526255900 | 2025-09-12 | -46034.4 | -46034.4
|  |  | MOU 9476.00 Transfer to DAS | IET 400EL26246001 | 2025-09-03 | 224341.04 | 224341.04
|  |  | Transfer Funds to Correct Unit | IET 400EL26247007 | 2025-09-04 | -224341.04 | -224341.04
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Recap
Acct. Codes-0506-335-DA26
Project Manager - XXXXXX
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Funds Rec'd
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services |  |  |  |  | 0
|  | Reimbursables |  |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  |  | eDAS:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - XXXXXX |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0