## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 7583147
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 7583147
|  | Less: Total Assigned |  | 1429533.27
|  | Total Unassigned / Unallocated |  | 6153613.73
DA26 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9438.00 | DOC FDCF Warehouse Loading Dock Ramp Repairs | Jennie E. | 0 | 15650 | 0 | 14182.75 | 0 | 14182.75 | 1467.25
| 9471.00 | DCO FDCF Bldg G Water Heater Replacement (29C20) | Jennie E. | 0 | 27500 | 27500 | 24537 | 0 | 24537 | 2963
| 9480.01 | HHS STS Canteen Roof Repair Construction (29C20) | Jennifer K. | 0 | 265000 | 265000 | 218283.9 | 11755.78 | 206528.12 | 46716.1
| 9481.00 | DOC 5JD 150 DSM St Renovation | Brandon A. | 0 | 1400000 | 1400000 | 736.25 | 736.25 | 0 | 1399263.75
| 9482.00 | IDB - Chiller Replacement | Oliver S. | 0 | 50000 | 50000 | 44059.4 | 2606.17 | 41453.23 | 5940.6
| 9486.00 | DVA IVH Fox and Ulery Carpet Replacement | Brad T. | 0 | 1000000 | 1000000 | 819838.74 | 1229.68 | 818609.06 | 180161.26
| 9487.00 | DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20) | Brad T. | 0 | 500000 | 500000 | 49130.18 | 1279.27 | 47850.91 | 450869.82
| 9488.00 | DOC 4JD New Central Office Building | Jennie E. | 0 | 4163847 | 4163847 | 216389.88 | 742.76 | 215647.12 | 3947457.12
| 9489.00 | DOC & ASP TWID Repairs | Oliver S. | 0 | 50000 | 50000 | 5000 | 469.89 | 4530.11 | 45000
| 9490.00 | DOC NCF Forced Main Sewer Pipe Failure (29C20) | Brad T. | 0 | 25000 | 25000 | 17700 | 15527.18 | 2172.82 | 7300
| 9492.00 | ATOD Racking Modification | Oliver S. | 0 | 86150 | 86150 | 19675.17 | 312.72 | 19362.45 | 66474.83
|  | DA26 (MOU) Totals |  | 0 | 7583147 | 7567497 | 1429533.27 | 34659.7 | 1394873.57 | 6153613.73
7548487.3

## RECAP #9438.00
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 15650
Jasper Construction |  | 14182.75 | 0 | 14182.75
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 15650 | 14182.75 | 0 | 14182.75 | 1467.25

## #9438.00 Funds Rec'd
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25208202502 | 2025-08-21 | 15650 | 15650
| Total Requested | 0 | Total Transferred |  |  | 15650 | 15650

## #9438.00 Jasper Construction
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  | Major Program 4B01
Jasper Construction |  |  | Vendor: 00003016436
Acct. Codes-0506-335-DA26-9255 |  |  | RFQ943800-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Split w/ MM23
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266902 | 2025-09-23 | PO Procore | 14182.75 | 14182.75 |  |  | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  |  |  | 14182.75 |  | 0 | 14182.75
|  | Totals: | 14182.75 |  | 0 |  | 14182.75
|  | MM23 | 41860 |  | 0 |  | 41860
|  | Total: | 56042.75 |  | 0 |  | 56042.75

## #9438.00 PM TIME
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E. |  |  |  | eDAS: 734H
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9438.00 Misc
DOC FDCF Warehouse Loading Dock Ramp Repairs
Project # 9438.00
Program code 943800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9471.00
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 27500
Midstate Plumbing |  | 24537 | 0 | 24537
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 27500 | 24537 | 0 | 24537 | 2963

## #9471.00 Funds Rec'd
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | 25208072504 | 2025-08-12 | 27500 | 27500
| Total Requested | 0 | Total Transferred |  |  | 27500 | 27500

## #9471.00 MidState Plumbing
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  | Major Program 4E01
Midstate Plumbing |  |  | Vendor: 00002108635
Acct. Codes-0506-335-DA26-9255 |  |  | RFB947100-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526226907 | 2025-08-14 | PO Procore | 24537 | 24537 |  |  | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  |  |  | 24537 |  | 0 | 24537
|  | Totals: | 24537 |  | 0 |  | 24537
|  | MM23 | 124741 |  | 0 |  | 124741
|  | Total: | 149278 |  | 0 |  | 149278

## #9471.00 PM TIME
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 734B
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9471.00 Misc
DOC FDCF Bldg G Water Heater Replacement (29C20)
Project # 9471.00
Program code 947100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9480.01
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 265000
TB Rigid Edge Exteriors |  | 74896.42 | 0 | 74896.42
PM TIME |  | 4000 | 1355.98 | 2644.02
Misc. |  | 0 | 0 | 0
Genesis Architectural |  | 16700 | 7810 | 8890
McGough Construction |  | 30122 | 2589.8 | 27532.2
Hilsabeck Schacht |  | 29700 | 0 | 29700
MTS Contracting |  | 4907.48 | 0 | 4907.48
Kinzler Construction |  | 57958 | 0 | 57958
Total Project Cost | 265000 | 218283.9 | 11755.78 | 206528.12 | 46716.1

## #9480.01 Funds Rec'd
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 400EL26216003 | 2025-08-06 | 230000 | 230000
|  |  | MOU Amendment #1 | IET 400EL26274001 | 2025-10-02 | 35000 | 35000
| Total Requested | 0 | Total Transferred |  |  | 265000 | 265000

## #9480.01 TB Rigid Edge Exterior
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
TB Rigid Edge Exteriors |  |  | Vendor: 00003193199
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526230902 | 2025-08-18 | PO Procore | 70820.24 | 70820.24 |  |  | 70820.24
PO 33526230902 | 2025-09-16 | CO #1 | 4076.18 | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  |  |  | 74896.42 |  | 0 | 74896.42
|  | Totals: | 74896.42 |  | 0 |  | 74896.42

## #9480.01 PM TIME
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennifer K. |  |  |  | eDAS: 733M
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 4000 | 4000 |  |  | 4000
CDE 33526262901 | 2025-09-18 | 9500 | Moving Expense to 9480.01 |  | 4000 | 1355.98 | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
[5 empty] | 4000 |  | 1355.98 | 2644.02
|  |  | Totals: | 4000 |  | 1355.98 |  | 2644.02
Note on E9: Jurgenson, John [DAS]: DAS Costs Budget for DA26 9480.01 Inbox Kleene, Jennifer 2:58 PM (2 minutes ago) to me Please create a DAS Costs budget for $4,000.00 for DA26 9480.01. Regards, Jennifer

## #9480.01 Misc
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  |  | Major Program 3D02
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennifer K. |  |  |  | Shipping Code: 200
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9480.01 Genesis Architectural
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0506-335-DA26-9260 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Split w/DA25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526181901 | 2025-08-22 | CO #1 Opening in DA26 | 16700 | 16700 |  |  | 16700
PRC 3352618PB1901 | 2025-09-23 | Inv. 2503-02(Split w/DA25) |  | 16700 | 7810 | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  |  |  | 16700 |  | 7810 | 8890
|  | Totals: | 16700 |  | 7810 |  | 8890
|  | DA25 Closed 09/23/25 | 10750 |  | 10750 |  | 0
|  | Total: | 27450 |  | 18560 |  | 8890

## #9480.01 McGough Construction
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Mc Gough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGought11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526252403 | 2025-09-09 | PO Procore | 30122 | 30122 |  |  | 30122
PRC 3352625PA2403 | 2025-09-16 | Inv. 101368.011-CA01 |  | 30122 | 2589.8 | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  |  |  | 30122 |  | 2589.8 | 27532.2
|  | Totals: | 30122 |  | 2589.8 |  | 27532.2
|  | CM Services | 29082 |  | 2589.8 |  | 26492.2
|  | Reimbursables | 1040 |  |  |  | 1040
|  | Total: | 30122 |  | 2589.8 |  | 27532.2

## #9480.01 Hilsabeck Schacht
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Hilsabeck Schacht |  |  | Vendor: 00003178029
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526272906 | 2025-09-29 | PO Procore | 29700 | 29700 |  |  | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  |  |  | 29700 |  | 0 | 29700
|  | Totals: | 29700 |  | 0 |  | 29700

## #9480.01 MTS Contracting
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
MTS Contracting |  |  | Vendor: 00003067019
Acct. Codes-0506-335-DA26-9255 |  |  | MA00520243D
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526272908 | 2025-09-29 | PO Procore | 4907.48 | 4907.48 |  |  | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  |  |  | 4907.48 |  | 0 | 4907.48
|  | Totals: | 4907.48 |  | 0 |  | 4907.48
|  | Tuckpointing | 3097 |  |  |  | 3097
|  | Materials & Supplies | 1810.48 |  |  |  | 1810.48
|  | Total: | 4907.48 |  | 0 |  | 4907.48

## #9480.01 Kinzler Construction
HHS STS Canteen Roof Repair Design (29C20)
Project # 9480.01
Program code 948001 |  |  | Major Program 3D02
Kinzler Construction |  |  | Vendor: 00003169106
Acct. Codes-0506-335-DA26-9255 |  |  | Emergency
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526273902 | 2025-09-30 | PO Procore | 57958 | 57958 |  |  | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  |  |  | 57958 |  | 0 | 57958
|  | Totals: | 57958 |  | 0 |  | 57958

## RECAP #9481.00
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1400000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 736.25 | 736.25 | 0
Total Project Cost | 1400000 | 736.25 | 736.25 | 0 | 1399263.75

## #9481.00 Funds Rec'd
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23812V26001 | 2025-07-29 | 1400000 | 1400000
| Total Requested | 0 | Total Transferred |  |  | 1400000 | 1400000

## #9481.00 Vendor A
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9481.00 PM TIME
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733O
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9481.00 Misc
DOC 5JD 150 DSM St Renovation
Project # 9481.00
Program code 948100 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
IET DAS202601115300001 | 2025-08-07 | 2507 |  | Space Planning Services July 1-31,2025 | Inv. DAS2026011153 | 570 | 570
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Space Planning Services August 1-31,2025 | Inv. DAS2026021153 | 166.25 | 736.25
736.25
736.25
736.25
736.25
736.25
736.25
736.25
736.25
736.25
|  |  |  | Totals: |  | 736.25

## RECAP #9482.00
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 50000
McGough Construction |  | 8969.4 | 1188 | 7781.4
PM TIME |  | 5000 | 1418.17 | 3581.83
Misc. |  | 0 | 0 | 0
KCL Engineering |  | 30090 | 0 | 30090
Total Project Cost | 50000 | 44059.4 | 2606.17 | 41453.23 | 5940.6

## #9482.00 Funds Rec'd
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 13150026212001 | 2025-07-31 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9482.00 McGough Construction
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526223900 | 2025-08-11 | PO Procore | 8969.4 | 8969.4 |  |  | 8969.4
PRC 3352622PA3900 | 2025-09-12 | Inv. 101368.012-PC01 |  | 8969.4 | 1188 | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  |  |  | 8969.4 |  | 1188 | 7781.4
|  | Totals: | 8969.4 |  | 1188 |  | 7781.4

## #9482.00 PM TIME
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S. |  |  |  | eDAS: 733P
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 0 | 57.26 | 57.26 | 4942.74
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 0 | 631.8 | 689.06 | 4310.94
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 84.01 | 773.07 | 4226.93
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 645.1 | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
[5 empty] | 0 |  | 1418.17 | 3581.83
|  |  | Totals: | 5000 |  | 1418.17 |  | 3581.83
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9482.00 Misc
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  |  | Major Program 4F09
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9482.00 KCL Engineering
IDB - Chiller Replacement
Project # 9482.00
Program code 948200 |  |  | Major Program 4F09
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0506-335-DA26-9260 |  |  | RFP948200-01
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526266903 | 2025-09-23 | PO Procore | 30090 | 30090 |  |  | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  |  |  | 30090 |  | 0 | 30090
|  | Totals: | 30090 |  | 0 |  | 30090
|  | Design Development Docs | 9990 |  |  |  | 9990
|  | Construction Docs | 20100 |  |  |  | 20100
|  | Total: | 30090 |  | 0 |  | 30090

## RECAP #9486.00
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1000000
DCI Group |  | 6725.74 | 0 | 6725.74
PM TIME |  | 30000 | 1229.68 | 28770.32
Misc. |  | 0 | 0 | 0
Ralph N Smith Flooring |  | 783113 | 0 | 783113
Total Project Cost | 1000000 | 819838.74 | 1229.68 | 818609.06 | 180161.26

## #9486.00 Funds Rec'd
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925401 | 2025-07-29 | 1000000 | 1000000
0
| Total Requested | 0 | Total Transferred |  |  | 1000000 | 1000000

## #9486.00 DCI Group
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255902 | 2025-09-12 | PO Procore | 6725.74 | 6725.74 |  |  | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  |  |  | 6725.74 |  | 0 | 6725.74
|  | Totals: | 6725.74 |  | 0 |  | 6725.74

## #9486.00 PM TIME
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 30000 | 30000 |  |  | 30000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 30000 | 33.7 | 33.7 | 29966.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 30000 | 368.8 | 402.5 | 29597.5
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 30000 | 94.58 | 497.08 | 29502.92
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 30000 | 732.6 | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
[5 empty] | 30000 |  | 1229.68 | 28770.32
|  |  | Totals: | 30000 |  | 1229.68 |  | 28770.32
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9486.00 Misc
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9486.00 Ralph N Smith Flooring
DVA IVH Fox and Ulery Carpet Replacement
Project # 9486.00
Program code 948600 |  |  | Major Program 4B03
Ralph N Smith Flooring |  |  | Vendor: 00002106937
Acct. Codes-0506-335-DA26-9255 |  |  | MA #21175A
Project Manager - Brandon A |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526273904 | 2025-09-30 | DO Procore | 783113 | 783113 |  |  | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  |  |  | 783113 |  | 0 | 783113
|  | Totals: | 783113 |  | 0 |  | 783113

## RECAP #9487.00
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 500000
DCI Group |  | 29130.18 | 0 | 29130.18
PM TIME |  | 20000 | 1279.27 | 18720.73
Misc. |  | 0 | 0 | 0
Total Project Cost | 500000 | 49130.18 | 1279.27 | 47850.91 | 450869.82

## #9487.00 Funds Rec'd
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA26-0304
Project Manager - Brandon A
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET072925400 | 2025-07-29 | 500000 | 500000
| Total Requested | 0 | Total Transferred |  |  | 500000 | 500000

## #9487.00 DCI Group
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  | Major Program 4B03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255904 | 2025-09-12 | PO Procore | 29130.18 | 29130.18 |  |  | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  |  |  | 29130.18 |  | 0 | 29130.18
|  | Totals: | 29130.18 |  | 0 |  | 29130.18
|  | CM Services | 28130.18 |  |  |  | 28130.18
|  | Reimbursables | 1000 |  |  |  | 1000
|  | Total: | 29130.18 |  | 0 |  | 29130.18

## #9487.00 PM TIME
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brandon A |  |  |  | eDAS: 733U
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 20000 | 20000 |  |  | 20000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 33.7 | 33.7 | 19966.3
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 368.8 | 402.5 | 19597.5
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 99.87 | 502.37 | 19497.63
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 776.9 | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
[5 empty] | 20000 |  | 1279.27 | 18720.73
|  |  | Totals: | 20000 |  | 1279.27 |  | 18720.73
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9487.00 Misc
DVA IVH Loftus and Malloy Water Infiltration-Flooding (29C20)
Project # 9487.00
Program code 948700 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brandon A |  |  |  | Shipping Code: 558
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9488.00
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 4163847
Samuels Group |  | 71389.88 | 0 | 71389.88
PM TIME |  | 145000 | 742.76 | 144257.24
Misc. |  | 0 | 0 | 0
Total Project Cost | 4163847 | 216389.88 | 742.76 | 215647.12 | 3947457.12

## #9488.00 Funds Rec'd
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26001 | 2025-08-15 | 4163847 | 4163847
| Total Requested | 0 | Total Transferred |  |  | 4163847 | 4163847

## #9488.00 Samuels Group
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  | Major Program 4B01
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526273900 | 2025-09-30 | PO Procore | 71389.88 | 71389.88 |  |  | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  |  |  | 71389.88 |  | 0 | 71389.88
|  | Totals: | 71389.88 |  | 0 |  | 71389.88
|  | CM Services | 63389.88 |  |  |  | 63389.88
|  | Reimbursables | 1000 |  |  |  | 1000
|  | Reimbursables(Geotechnical) | 7000 |  |  |  | 7000
|  | Total: | 71389.88 |  | 0 |  | 71389.88

## #9488.00 PM TIME
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Jennie E |  |  |  | eDAS: 733W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 145000 | 145000 |  |  | 145000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 85.66 | 85.66 | 144914.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 657.1 | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
[5 empty] | 0 |  | 742.76 | 144257.24
|  |  | Totals: | 145000 |  | 742.76 |  | 144257.24
Note on E9: On Sat, Sep 20, 2025 at 2:15 PM Elliott, Jennie <jennie.elliott@iowa.gov> wrote: Sorry about that, Please establish DAS time for $145,000.00 in 9488.00. Thank you, Jennie Elliott Owner's Representative, State Design & Construction Resources Bureau

## #9488.00 Misc
DOC 4JD New Central Office Building
Project # 9488.00
Program code 948800 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Jennie E |  |  |  | Shipping Code: B90
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9489.00
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 50000
VendorA |  | 0 | 0 | 0
PM TIME |  | 5000 | 469.89 | 4530.11
Misc. |  | 0 | 0 | 0
Total Project Cost | 50000 | 5000 | 469.89 | 4530.11 | 45000

## #9489.00 Funds Rec'd
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Oliver S
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 25543A26002 | 2025-08-19 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9489.00 Vendor A
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9489.00 PM TIME
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S |  |  |  | eDAS: 734A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 54.39 | 54.39 | 4945.61
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 415.5 | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
[5 empty] | 0 |  | 469.89 | 4530.11
|  |  | Totals: | 5000 |  | 469.89 |  | 4530.11
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (23 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon.

## #9489.00 Misc
DOC & ASP TWID Repairs
Project # 9489.00
Program code 948900 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9490.00
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 25000
VendorA |  | 0 | 0 | 0
PM TIME |  | 3000 | 827.18 | 2172.82
Misc. |  | 14700 | 14700 | 0
Total Project Cost | 25000 | 17700 | 15527.18 | 2172.82 | 7300

## #9490.00 Funds Rec'd
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 245269490 | 2025-08-29 | 25000 | 25000
| Total Requested | 0 | Total Transferred |  |  | 25000 | 25000

## #9490.00 Vendor A
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9490.00 PM TIME
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Brad T. |  |  |  | eDAS: 734C
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 3000 | 3000 |  |  | 3000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 94.58 | 94.58 | 2905.42
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 732.6 | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
[5 empty] | 0 |  | 827.18 | 2172.82
|  |  | Totals: | 3000 |  | 827.18 |  | 2172.82
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #9490.00 Misc
DOC NCF Forced Main Sewer Pipe Failure (29C20)
Project # 9490.00
Program code 949000 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526259906 | 2025-09-16 | 9500 | DSGN | Shive Hattery V#(00002108803) | Inv. 2250015060-1 | 14700 | 14700
14700
14700
14700
14700
14700
14700
14700
14700
14700
14700
14700
|  |  |  | Totals: |  | 14700

## RECAP #9492.00
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Recap
Acct. Codes-0506-335-DA26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 86150
Samuels Group |  | 14675.17 | 0 | 14675.17
PM TIME |  | 5000 | 312.72 | 4687.28
Misc. |  | 0 | 0 | 0
Total Project Cost | 86150 | 19675.17 | 312.72 | 19362.45 | 66474.83

## #9492.00 Funds Rec'd
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - Oliver S.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DAS9492RACKING | 2025-09-18 | 86150 | 86150
| Total Requested | 0 | Total Transferred |  |  | 86150 | 86150

## #9492.00 Samuels Group
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  | Major Program 4H06
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526269901 | 2025-09-26 | PO Procore | 14675.17 | 14675.17 |  |  | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  |  |  | 14675.17 |  | 0 | 14675.17
|  | Totals: | 14675.17 |  | 0 |  | 14675.17

## #9492.00 PM TIME
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - Oliver S. |  |  |  | eDAS: 911G
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 0 | 36.12 | 36.12 | 4963.88
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 0 | 276.6 | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
[5 empty] | 0 |  | 312.72 | 4687.28
|  |  | Totals: | 5000 |  | 312.72 |  | 4687.28
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate Shimp, Oliver 9:16 AM (24 minutes ago) to me Good Morning, Could you please make the following adjustments to these projects? X674 9464.00 - Increase total project budget and PM time by $52.40 MM26 9491.00 - Please increase PM Time budget by $5,000.00 MM24 9386.01 - Please increase PM Time budget by $1950.87 9392.00 - Please increase PM Time budget by $5,000.00 DA26 9489.00 - Please increase PM Time budget by $5,000.00 9492.00 - Please increase PM Time budget by $5,000.00, The funds for this are expected soon.

## #9492.00 Misc
ATOD Racking Modification
Project # 9492.00
Program code 949200 |  |  |  | Major Program 4H06
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - Oliver S. |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## Funds Rec'd incorrectly
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | FY26 Funds recv'd for 9211.01 | IET IET091125100 | 2025-09-11 | 46034.4 | 46034.4
|  |  | Transfer Funds to Correct Unit | CDR 33526255900 | 2025-09-12 | -46034.4 | -46034.4
|  |  | MOU 9476.00 Transfer to DAS | IET 400EL26246001 | 2025-09-03 | 224341.04 | 224341.04
|  |  | Transfer Funds to Correct Unit | IET 400EL26247007 | 2025-09-04 | -224341.04 | -224341.04
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Recap
Acct. Codes-0506-335-DA26
Project Manager - XXXXXX
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Funds Rec'd
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Funds Rec'd
Acct Code: 0506-335-DA26-xxxx
Project Manager - XXXXXX
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #XXXX.XX Vendor A
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program XXXX
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA26-xxxx
Project Manager - XXXXXX |  |  |  | eDAS:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 0 | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: Funds Recv'd 9486.00 & 9487.00 $Joni Tonyan, Brad 10:50 AM (12 minutes ago) to me, Joni Joni, Please set up the following PM time budgets on these projects: DA26 9486.00 - $30,000 DA26 9487.00 - $20,000 Thank you, Brad Tonyan, CPM, LEED Green Associate

## #XXXX.XX Misc
Project Name
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program XXXX
Misc
Acct. Codes-0506-335-DA26-xxxx |  |  |  | Do not code PM, EADOC, or Builders Risk here
Project Manager - XXXXXX
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0