## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation R52 | 22000000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22000000
| . | Less: Total Assigned |  | 12364012
|  | Total Unassigned / Unallocated |  | 9635988
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9997.26 | Project Management Time | Geoff W. | 75000 |  | 75000 | 75000 | 44048.9 | 30951.1 | 0 | 30951.1
| 9483.00 | DVA IVH Dack and Malloy Building Roof Replacements | Brad T. | 2630000 |  | 2630000 | 138802.14 | 5171.33 | 133630.81 | 2491197.86 | 72510.19
| 9484.00 | ILEA JOH Hydraulic Elevator Replacement | Brad T. | 575000 |  | 575000 | 107045.32 | 36235.96 | 70809.36 | 467954.68 | 16747.54
| 9491.00 | DOC 7 JD RTU #2 Replacement | Oliver S. | 170000 |  | 170000 | 45806.88 | 8098.98 | 37707.9 | 124193.12 | 4898.8
C | 9494.00 | IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs | Jennie E. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
C | 9495.00 | HHS IMHI Boiler #3 Replacement | Oliver S.(JE) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 9496.00 | DOC NCCF Replace Windows in Education Building | Jennie E. | 250000 |  | 250000 | 10000 | 482.17 | 9517.83 | 240000 | 9517.83
| 9497.00 | HHS IMHI Warehouse Roof Replacement | Oliver S. | 495000 |  | 495000 | 35616.73 | 858.68 | 34758.05 | 459383.27 | 9141.32
| 9498.00 | DAS TH Parking Lot Retaining Wall Repairs | James T. | 105000 |  | 105000 | 17713.54 | 1458.4 | 16255.14 | 87286.46 | 6065.01
| 9499.00 | IPBS 6535 Corporate Drive Parking Lot Replacement | Oliver S. (BA) | 640965 |  | 640965 | 15000 | 1439.34 | 13560.66 | 625965 | 13560.66
| 9500.00 | DOC MPCF Spill Containment for Diesel Tank | Brandon A. | 400000 |  | 400000 | 25864.97 | 1332.36 | 24532.61 | 374135.03 | 8667.64
| 9501.00 | DOC NCCF Air Handler Replacment and Condenser Coils Unit A and B | Jennie E. | 275000 |  | 275000 | 10000 | 482.17 | 9517.83 | 265000 | 9517.83
| 9502.00 | DOC MPCF Hot and Cold Water Mains Replacement | Brandon A. | 505000 |  | 505000 | 35742.15 | 3955.5 | 31786.65 | 469257.85 | 17605.91
| 9503.00 | HHS WRC CDC Freezer Repair | Jennifer K. | 440000 |  | 440000 | 39928.59 | 688.94 | 39239.65 | 400071.41 | 7811.06
| 9504.00 | HHS WRC Food Service Elevator Replacement | Jennifer K. | 400000 |  | 400000 | 8000 | 393.62 | 7606.38 | 392000 | 7606.38
| 9505.00 | DOC FDCF Sally Port Operator Replacement | Jennie E. | 385000 |  | 385000 | 11800 | 306.16 | 11493.84 | 373200 | 11493.84
| 9506.00 | DOC MPCF Perimeter Fence and Wagon Gates | Brandon A. | 1680747 |  | 1680747 | 32731.62 | 810.27 | 31921.35 | 1648015.38 | 17189.73
| 9507.00 | DOC IMCC Cooling Tower Replacement | Geoff W(JK) | 700000 |  | 700000 | 15000 | 491.58 | 14508.42 | 685000 | 14508.42
| 9508.00 | DOC FDCF Unit A Roof Replacement | Geoff W(JE) | 1707300 |  | 1707300 | 55497.16 | 745.63 | 54751.53 | 1651802.84 | 35254.37
C | 9509.00 | DOC FDCF Boone Unit Roof Replacement | Geoff W(JE) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
C | 9510.00 | DOC FDCF Grove Unit Roof Replacement | Geoff W(JE) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 9511.00 | DPS P13 Upper Parking Lot Replacement | Brandon A. | 205000 |  | 205000 | 27864.97 | 910.8 | 26954.17 | 177135.03 | 11089.2
| 9512.00 | IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit | Oliver S. (BA) | 75000 |  | 75000 | 4000 | 1475.8 | 2524.2 | 71000 | 2524.2
| 9513.00 | HHS CHMHI Tuckpointing Phase 2.2 | Jennie E. | 640000 |  | 640000 | 20000 | 438.69 | 19561.31 | 620000 | 19561.31
| 9514.00 | DAS Union Sunday School Structural Investigation | Oliver S. | 10000 |  | 10000 | 8765 | 1400.83 | 7364.17 | 1235 | 599.17
|  | Major Maintenance Totals |  | 12364012 | 0 | 12364012 | 740179.07 | 111226.11 | 628952.96 | 11623832.93 | 295870.41
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 9635988
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 21259820.93
[6 empty] | Total funds Available |  |  | 22000000
[6 empty] | Total obligated by contract or PO |  |  | -740179.07 | 21259820.93
[6 empty] | Variance |  |  |  | 0

## RECAP #9997.26
Project Management Time
Project # 9997.26
Program code 999726 |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 75000
VendorA |  | 0 | 0 | 0
PM TIME |  | 75000 | 44048.9 | 30951.1
Misc. |  | 0 | 0 | 0
Total Project Cost | 75000 | 75000 | 44048.9 | 30951.1 | 0

## #9997.26 PM TIME
Project Management Time
Project # 9997.26
Program code 999726 |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733L
Project Manager - Geoff W.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
[5 empty] | 75000 |  | 0 | 75000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 75000 | 1463.15 | 1463.15 | 73536.85
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 75000 | 6111.2 | 7574.35 | 67425.65
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9436.00 |  | 75000 | -110.44 | 7463.91 | 67536.09
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9440.00 |  | 75000 | -144.14 | 7319.77 | 67680.23
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9420.00 |  | 75000 | -169.68 | 7150.09 | 67849.91
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9436.00 |  | 75000 | -1211.1 | 5938.99 | 69061.01
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9440.00 |  | 75000 | -1595.5 | 4343.49 | 70656.51
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9420.00 |  | 75000 | -1854.9 | 2488.59 | 72511.41
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 75000 | 2070.07 | 4558.66 | 70441.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 75000 | 2472.3 | 7030.96 | 67969.04
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 75000 | 3801.19 | 10832.15 | 64167.85
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 75000 | 2413.6 | 13245.75 | 61754.25
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 75000 | 2021.01 | 15266.76 | 59733.24
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 75000 | 27910.6 | 43177.36 | 31822.64
CDE 33526317909 | 2025-11-13 | 2507 | Move from DA26 9481.00 |  | 75000 | 300.34 | 43477.7 | 31522.3
CDE 33526317909 | 2025-11-13 | 9500 | Move from DA26 9481.00 |  | 75000 | 571.2 | 44048.9 | 30951.1
[5 empty] | 75000 |  | 44048.9 | 30951.1
|  |  | Totals: | 75000 |  | 44048.9 |  | 30951.1
Note on E9: Jurgenson, John [DAS]: Re: FY 26 9997.26 PM Time Inbox Cross, Charlee 8:33 AM (1 minute ago) to me Yes. Thank you! Charlee Cross Chief Operating Officer General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, Iowa 50319 515-725-2281 (desk) 515-802-1653 (mobile) charlee.cross@iowa.gov https://das.iowa.gov On Thu, Jul 3, 2025 at 8:25 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Charlee May I have permission to set up a 9997.26 FY26 PM time budget as we have in the past with a $75,000.00 budget?

## RECAP #9483.00
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 2630000
DCI Group |  | 28802.14 | 2681.52 | 26120.62
PM TIME |  | 75000 | 2489.81 | 72510.19
Misc. |  | 0 | 0 | 0
Genesis Architectural |  | 35000 | 0 | 35000
Total Project Cost | 2630000 | 138802.14 | 5171.33 | 133630.81 | 2491197.86

## #9483.00 DCI Group
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259901 | 2025-09-16 | PO Procore | 28802.14 | 28802.14 |  |  | 28802.14
PRC 3352625PA9901 | 2025-10-17 | Inv. 25-021 PC 01 |  | 28802.14 | 2681.52 | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  |  |  | 28802.14 |  | 2681.52 | 26120.62
|  | Totals: | 28802.14 |  | 2681.52 |  | 26120.62
|  | CM Services | 27302.14 |  | 2681.52 |  | 24620.62
|  | Reimbursables | 1500 |  |  |  | 1500
|  | Total: | 28802.14 |  | 2681.52 |  | 26120.62

## #9483.00 PM TIME
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  |  | Major Program 4D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733Q
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 75000 | 47.89 | 47.89 | 74952.11
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 75000 | 532.2 | 580.09 | 74419.91
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 75000 | 94.58 | 674.67 | 74325.33
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 75000 | 732.6 | 1407.27 | 73592.73
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 75000 | 100.03 | 1507.3 | 73492.7
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 75000 | 522.8 | 2030.1 | 72969.9
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 75000 | 42.41 | 2072.51 | 72927.49
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 75000 | 417.3 | 2489.81 | 72510.19
[5 empty] | 75000 |  | 2489.81 | 72510.19
[5 empty] | 75000 |  | 2489.81 | 72510.19
[5 empty] | 75000 |  | 2489.81 | 72510.19
[5 empty] | 75000 |  | 2489.81 | 72510.19
|  |  | Totals: | 75000 |  | 2489.81 |  | 72510.19
Note on E9: Huggins, Joni [DAS]: Re: FY26 - New Project Set Up Request in MM26 $Joni Tonyan, Brad Wed, Jul 16, 2:29 PM (16 hours ago) to me Joni, Yes, please see below: 9483.00 - Set up PM time of $75,000 9484.00 - Set up PM time of $20,000 Thank you, Brad Tonyan, CPM, LE

## #9483.00 Misc
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  |  | Major Program 4D02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 558
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9483.00 Genesis Architectural
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM26-9260 |  |  | RFB948300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526328905 | 2025-11-24 | PO Procore | 35000 | 35000 |  |  | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  |  |  | 35000 |  | 0 | 35000
|  | Totals: | 35000 |  | 0 |  | 35000
|  | 50% CD Design Phase | 10000 |  |  |  | 10000
|  | 100% Construction Docs | 12000 |  |  |  | 12000
|  | Bidding Phase Services | 1500 |  |  |  | 1500
|  | Construction Phase Services | 11500 |  |  |  | 11500
|  | Total: | 35000 |  | 0 |  | 35000

## RECAP #9484.00
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 575000
DCI Group |  | 18125.32 | 7483.1 | 10642.22
PM TIME |  | 20000 | 3252.46 | 16747.54
Misc. |  | 0 | 0 | 0
OPN Architects |  | 68920 | 25500.4 | 43419.6
Total Project Cost | 575000 | 107045.32 | 36235.96 | 70809.36 | 467954.68

## #9484.00 DCI Group
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255901 | 2025-09-12 | PO Procore | 18125.32 | 18125.32 |  |  | 18125.32
PRC 3352625PA5901 | 2025-09-23 | Inv. 25-022 PC 01 |  | 18125.32 | 2093.64 | 2093.64 | 16031.68
PRC 3352625PB5901 | 2025-10-08 | Inv. 25-022 PC 02 |  | 18125.32 | 2180.88 | 4274.52 | 13850.8
PRC 3352625PC5901 | 2025-11-18 | Inv. 25-022 PC 03 |  | 18125.32 | 3208.58 | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  |  |  | 18125.32 |  | 7483.1 | 10642.22
|  | Totals: | 18125.32 |  | 7483.1 |  | 10642.22
|  | CM Services | 16125.32 |  | 7483.1 |  | 8642.22
|  | Reimbursables | 2000 |  |  |  | 2000
|  | Total: | 18125.32 |  | 7483.1 |  | 10642.22

## #9484.00 PM TIME
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733R
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 47.89 | 47.89 | 19952.11
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 532.2 | 580.09 | 19419.91
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 105.15 | 685.24 | 19314.76
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 820.1 | 1505.34 | 18494.66
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 154.88 | 1660.22 | 18339.78
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 808.3 | 2468.52 | 17531.48
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 71.84 | 2540.36 | 17459.64
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 712.1 | 3252.46 | 16747.54
[5 empty] | 20000 |  | 3252.46 | 16747.54
[5 empty] | 20000 |  | 3252.46 | 16747.54
[5 empty] | 20000 |  | 3252.46 | 16747.54
[5 empty] | 20000 |  | 3252.46 | 16747.54
|  |  | Totals: | 20000 |  | 3252.46 |  | 16747.54
Note on E9: Huggins, Joni [DAS]: Re: FY26 - New Project Set Up Request in MM26 $Joni Tonyan, Brad Wed, Jul 16, 2:29 PM (16 hours ago) to me Joni, Yes, please see below: 9483.00 - Set up PM time of $75,000 9484.00 - Set up PM time of $20,000 Thank you, Brad Tonyan, CPM, LEED Green Assoc

## #9484.00 Misc
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 570
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9484.00 OPN Architects
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM26-9260 |  |  | RFP#948400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259909 | 2025-09-16 | PO Procore | 68920 | 68920 |  |  | 68920
PRC 3352625PA9909 | 2025-11-05 | Inv. 25832000-1 |  | 68920 | 25500.4 | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  |  |  | 68920 |  | 25500.4 | 43419.6
|  | Totals: | 68920 |  | 25500.4 |  | 43419.6
|  | Investigation & Design Docs | 17435 |  | 17435 |  | 0
|  | Construction Docs | 28010 |  | 8065.4 |  | 19944.6
|  | Bidding & Negotiaion | 3220 |  |  |  | 3220
|  | Construction Phase | 20255 |  |  |  | 20255
|  | Total: | 68920 |  | 25500.4 |  | 43419.6

## RECAP #9491.00
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver Shimp
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 170000
DCI Group |  | 18131.88 | 2997.78 | 15134.1
PM TIME |  | 10000 | 5101.2 | 4898.8
Misc. |  | 0 | 0 | 0
KCL Engineering |  | 17675 | 0 | 17675
Total Project Cost | 170000 | 45806.88 | 8098.98 | 37707.9 | 124193.12

## #9491.00 DCI Group
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Oliver Shimp |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259900 | 2025-09-16 | PO Procore | 18131.88 | 18131.88 |  |  | 18131.88 | `
PRC 3352625PA9900 | 2025-10-28 | Inv. 25-033 PC 01 |  | 18131.88 | 2473.03 | 2473.03 | 15658.85
PRC 3352625PB9900 | 2025-11-21 | Inv. 25-033 PC 02 |  | 18131.88 | 524.75 | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  |  |  | 18131.88 |  | 2997.78 | 15134.1
|  | Totals: | 18131.88 |  | 2997.78 |  | 15134.1
|  | CM Services | 17631.88 |  | 2882.78 |  | 14749.1
|  | Reimbursables | 500 |  | 115 |  | 385
|  | Total: | 18131.88 |  | 2997.78 |  | 15134.1

## #9491.00 PM TIME
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 911F
Project Manager - Oliver Shimp
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 10000 | 167.7 | 167.7 | 9832.3
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 10000 | 1292.9 | 1460.6 | 8539.4
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10000 | 431 | 1891.6 | 8108.4
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10000 | 2215.6 | 4107.2 | 5892.8
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 91 | 4198.2 | 5801.8
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 903 | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
[5 empty] | 10000 |  | 5101.2 | 4898.8
|  |  | Totals: | 10000 |  | 5101.2 |  | 4898.8
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Mon, Nov 10, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget.

## #9491.00 Misc
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: C21
Project Manager - Oliver Shimp
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9491.00 KCL Engineering
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM26-9260 |  |  | 949100-01
Project Manager - Oliver Shimp |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526296902 | 2025-10-23 | PO Procore | 17675 | 17675 |  |  | 17675 | `
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  |  |  | 17675 |  | 0 | 17675
|  | Totals: | 17675 |  | 0 |  | 17675
|  | Design Development Docs | 4775 |  |  |  | 4775
|  | Construction Docs | 5900 |  |  |  | 5900
|  | Bidding/Negotiation | 1600 |  |  |  | 1600
|  | Construction Phase | 5400 |  |  |  | 5400
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 17675 |  | 0 |  | 17675

## RECAP #9494.00
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per PM 10/10/25

## #9494.00 Vendor A
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9494.00 PM TIME
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734J
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9494.00 Misc
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9495.00
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver S. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closing Per Geoff Wheelock Email 10/03/25
Note on B17: Huggins, Joni [DAS]: Re: MM26 Projects Set Up $Joni Wheelock, Geoff Oct 3, 2025, 12:22 PM (3 days ago) to me Good afternoon, I apologize for having to ask to make this change. Can you please make the following changes: Increase budget for 9474.00 to be $1,500,000 Close 9495 - This project number can be reused for a different project we will be looking to set up in Q3. If you would like to know which project so you don't have to close the job please let me know. The reason for this change is because 9474 is the design portion of 9495 and it makes more sense to continue utilizing the remaining excess of MM25 for the continuation of that project, freeing up MM26 funds for true FY26 project setups. If you have any questions please feel free to reach out. Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9495.00 Vendor A
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Oliver S. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9495.00 PM TIME
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734K
Project Manager - Oliver S. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 0 | 274.14 | 274.14 | -274.14
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 0 | 1410.3 | 1684.44 | -1684.44
CDE 33526281901 | 2025-10-07 | 2507 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 0 | -274.14 | 1410.3 | -1410.3
CDE 33526281901 | 2025-10-07 | 9500 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 0 | -1410.3 | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
|  |  | Totals: | 0 |  | 0 |  | 0

## #9495.00 Misc
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Oliver S. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9496.00
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - ennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
VendorA |  | 0 | 0 | 0
PM TIME |  | 10000 | 482.17 | 9517.83
Misc. |  | 0 | 0 | 0
Total Project Cost | 250000 | 10000 | 482.17 | 9517.83 | 240000

## #9496.00 Vendor A
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - ennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9496.00 PM TIME
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734L
Project Manager - ennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 44.07 | 44.07 | 9955.93
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 438.1 | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
|  |  | Totals: | 10000 |  | 482.17 |  | 9517.83
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Nov 2, 2025, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9496.00 Misc
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - ennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9497.00
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 495000
Story Construction |  | 25616.73 | 0 | 25616.73
PM TIME |  | 10000 | 858.68 | 9141.32
Misc. |  | 0 | 0 | 0
Total Project Cost | 495000 | 35616.73 | 858.68 | 34758.05 | 459383.27

## #9497.00 Story Construction
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Oliver S. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526288901 | 2025-10-15 | PO 33526288901 | 25616.73 | 25616.73 |  |  | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  |  |  | 25616.73 |  | 0 | 25616.73
|  | Totals: | 25616.73 |  | 0 |  | 25616.73
|  | CM Services | 25259.73 |  |  |  | 25259.73
|  | Reimbursables | 357 |  |  |  | 357
|  | Total: | 25616.73 |  | 0 |  | 25616.73

## #9497.00 PM TIME
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734M
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 78.78 | 78.78 | 9921.22
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 779.9 | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
[5 empty] | 10000 |  | 858.68 | 9141.32
|  |  | Totals: | 10000 |  | 858.68 |  | 9141.32
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Nov 10, 2025, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget. MM26 9497.00 (858.68) Please increase the PM time budget by $10,000.00 to $10,000.00 from the unallocated budget.

## #9497.00 Misc
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 556
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9498.00
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM26
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 105000
DCI Group |  | 10713.54 | 523.41 | 10190.13
PM TIME |  | 7000 | 934.99 | 6065.01
Misc. |  | 0 | 0 | 0
Total Project Cost | 105000 | 17713.54 | 1458.4 | 16255.14 | 87286.46

## #9498.00 DCI Group
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP181335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526301907 | 2025-10-28 | PO Procore | 10713.54 | 10713.54 |  |  | 10713.54
PRC 3352630PA1907 | 2025-11-21 | Inv. 9498.00 PC 01 |  | 10713.54 | 523.41 | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  |  |  | 10713.54 |  | 523.41 | 10190.13
|  | Totals: | 10713.54 |  | 523.41 |  | 10190.13

## #9498.00 PM TIME
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734N
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7000 | 7000 |  |  | 7000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 7000 | 38.8 | 38.8 | 6961.2
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 7000 | 199.7 | 238.5 | 6761.5
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 7000 | 63.69 | 302.19 | 6697.81
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 7000 | 632.8 | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
[5 empty] | 7000 |  | 934.99 | 6065.01
|  |  | Totals: | 7000 |  | 934.99 |  | 6065.01

## #9498.00 Misc
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9499.00
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver S (BA)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 640965
VendorA |  | 0 | 0 | 0
PM TIME |  | 15000 | 1439.34 | 13560.66
Misc. |  | 0 | 0 | 0
Total Project Cost | 640965 | 15000 | 1439.34 | 13560.66 | 625965

## #9499.00 Vendor A
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Oliver S (BA) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9499.00 PM TIME
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734O
Project Manager - Oliver S (BA)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 128.14 | 128.14 | 14871.86
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 1311.2 | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
[5 empty] | 15000 |  | 1439.34 | 13560.66
|  |  | Totals: | 15000 |  | 1439.34 |  | 13560.66

## #9499.00 Misc
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Oliver S (BA)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9500.00
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 400000
McGough Construction |  | 15864.97 | 0 | 15864.97
PM TIME |  | 10000 | 1332.36 | 8667.64
Misc. |  | 0 | 0 | 0
Total Project Cost | 400000 | 25864.97 | 1332.36 | 24532.61 | 374135.03

## #9500.00 McGough Construction
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526329902 | 2025-11-25 | PO Procore | 15864.97 | 15864.97 |  |  | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  | Totals: | 15864.97 |  | 0 |  | 15864.97
|  | CM Services | 15444.97 |  |  |  | 15444.97
|  | Reimbursables | 420 |  |  |  | 420
|  | Total: | 15864.97 |  | 0 |  | 15864.97

## #9500.00 PM TIME
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734P
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 10000 | 44.41 | 44.41 | 9955.59
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 10000 | 229.2 | 273.61 | 9726.39
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 228.95 | 502.56 | 9497.44
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 829.8 | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
[5 empty] | 10000 |  | 1332.36 | 8667.64
|  |  | Totals: | 10000 |  | 1332.36 |  | 8667.64

## #9500.00 Misc
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9501.00
DOC NCCF Air Handler Replacment and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 275000
VendorA |  | 0 | 0 | 0
PM TIME |  | 10000 | 482.17 | 9517.83
Misc. |  | 0 | 0 | 0
Total Project Cost | 275000 | 10000 | 482.17 | 9517.83 | 265000

## #9501.00 Vendor A
DOC NCCF Air Handler Replacment and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9501.00 PM TIME
DOC NCCF Air Handler Replacment and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Q
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 44.07 | 44.07 | 9955.93
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 438.1 | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
[5 empty] | 10000 |  | 482.17 | 9517.83
|  |  | Totals: | 10000 |  | 482.17 |  | 9517.83
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9501.00 Misc
DOC NCCF Air Handler Replacment and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  |  | Major Program 4F03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9502.00
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 505000
VendorA |  | 15742.15 | 1561.41 | 14180.74
PM TIME |  | 20000 | 2394.09 | 17605.91
Misc. |  | 0 | 0 | 0
Total Project Cost | 505000 | 35742.15 | 3955.5 | 31786.65 | 469257.85

## #9502.00 McGough Construction
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526279901 | 2025-10-06 | POProcore | 15742.15 | 15742.15 |  |  | 15742.15
PRC 3352627PA9901 | 2025-11-06 | Inv. 101368.015-PC01 |  | 15742.15 | 1561.41 | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  |  |  | 15742.15 |  | 1561.41 | 14180.74
|  | Totals: | 15742.15 |  | 1561.41 |  | 14180.74
|  | CM Services | 15042.15 |  | 1421.41 |  | 13620.74
|  | Reimbursables | 700 |  | 140 |  | 560
|  | Total: | 15742.15 |  | 1561.41 |  | 14180.74

## #9502.00 PM TIME
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734R
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 66.83 | 66.83 | 19933.17
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 345.2 | 412.03 | 19587.97
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 49.36 | 461.39 | 19538.61
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 1932.7 | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
[5 empty] | 20000 |  | 2394.09 | 17605.91
|  |  | Totals: | 20000 |  | 2394.09 |  | 17605.91

## #9502.00 Misc
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9503.00
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 440000
Story Construction |  | 25378.59 | 0 | 25378.59
PM TIME |  | 8500 | 688.94 | 7811.06
Misc. |  | 0 | 0 | 0
SystemWorks |  | 6050 | 0 | 6050
Total Project Cost | 440000 | 39928.59 | 688.94 | 39239.65 | 400071.41

## #9503.00 Story Construction
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526289900 | 2025-10-16 | PO Procore | 25378.59 | 25378.59 |  |  | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  |  |  | 25378.59 |  | 0 | 25378.59
|  | Totals: | 25378.59 |  | 0 |  | 25378.59
|  | CM Services | 25260.59 |  |  |  | 25260.59
|  | Reimbursables | 118 |  |  |  | 118
|  | Total: | 25378.59 |  | 0 |  | 25378.59

## #9503.00 PM TIME
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734S
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8500 | 8500 |  |  | 8500
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8500 | 63.24 | 63.24 | 8436.76
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8500 | 625.7 | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
[5 empty] | 8500 |  | 688.94 | 7811.06
|  |  | Totals: | 8500 |  | 688.94 |  | 7811.06

## #9503.00 Misc
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 564
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9503.00 SystemWorks
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM26-9255 |  |  | MA 00521396C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526290900 | 2025-10-17 | PO Procore | 6050 | 6050 |  |  | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  |  |  | 6050 |  | 0 | 6050
|  | Totals: | 6050 |  | 0 |  | 6050

## RECAP #9504.00
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 400000
VendorA |  | 0 | 0 | 0
PM TIME |  | 8000 | 393.62 | 7606.38
Misc. |  | 0 | 0 | 0
Total Project Cost | 400000 | 8000 | 393.62 | 7606.38 | 392000

## #9504.00 Vendor A
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennifer K. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9504.00 PM TIME
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734T
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8000 | 35.92 | 35.92 | 7964.08
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8000 | 357.7 | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
[5 empty] | 8000 |  | 393.62 | 7606.38
|  |  | Totals: | 8000 |  | 393.62 |  | 7606.38

## #9504.00 Misc
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9505.00
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 385000
VendorA |  | 0 | 0 | 0
PM TIME |  | 11800 | 306.16 | 11493.84
Misc. |  | 0 | 0 | 0
Total Project Cost | 385000 | 11800 | 306.16 | 11493.84 | 373200

## #9505.00 Vendor A
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9505.00 PM TIME
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734U
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11800 | 11800 |  |  | 11800
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 11800 | 27.76 | 27.76 | 11772.24
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 11800 | 278.4 | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
[5 empty] | 11800 |  | 306.16 | 11493.84
|  |  | Totals: | 11800 |  | 306.16 |  | 11493.84
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9505.00 Misc
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9506.00
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1680747
McGough Construction |  | 14731.62 | 0 | 14731.62
PM TIME |  | 18000 | 810.27 | 17189.73
Misc. |  | 0 | 0 | 0
Total Project Cost | 1680747 | 32731.62 | 810.27 | 31921.35 | 1648015.38

## #9506.00 McGough Construction
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526323905 | 2025-11-19 | PO Procore | 14731.62 | 14731.62 |  |  | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  |  |  | 14731.62 |  | 0 | 14731.62
|  | Totals: | 14731.62 |  | 0 |  | 14731.62
|  | CM Services | 14311.62 |  |  |  | 14311.62
|  | Reimbursables | 420 |  |  |  | 420
|  | Total: | 14731.62 |  | 0 |  | 14731.62

## #9506.00 PM TIME
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734V
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18000 | 18000 |  |  | 18000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 18000 | 44.41 | 44.41 | 17955.59
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 18000 | 229.2 | 273.61 | 17726.39
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 18000 | 49.36 | 322.97 | 17677.03
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 18000 | 487.3 | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
[5 empty] | 18000 |  | 810.27 | 17189.73
|  |  | Totals: | 18000 |  | 810.27 |  | 17189.73

## #9506.00 Misc
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9507.00
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.(JK)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 700000
VendorA |  | 0 | 0 | 0
PM TIME |  | 15000 | 491.58 | 14508.42
Misc. |  | 0 | 0 | 0
Total Project Cost | 700000 | 15000 | 491.58 | 14508.42 | 685000

## #9507.00 Vendor A
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Geoff W.(JK) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9507.00 PM TIME
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734W
Project Manager - Geoff W.(JK)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 45.28 | 45.28 | 14954.72
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 446.3 | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
[5 empty] | 15000 |  | 491.58 | 14508.42
|  |  | Totals: | 15000 |  | 491.58 |  | 14508.42
Note on E9: Huggins, Joni [DAS]: Project #s 9507 & 9508 $Joni Wheelock, Geoff Mon, Nov 24, 4:37 PM (15 hours ago) to me Could you please set up a PM Time budget for these referenced projects in the amount of: 9507.00 = $15,000 9508.00 = $36,000 I greatly appreciate your help on this. Thank you,

## #9507.00 Misc
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Geoff W.(JK)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9508.00
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.(JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1707300
Story Construction |  | 19497.16 | 0 | 19497.16
PM TIME |  | 36000 | 745.63 | 35254.37
Misc. |  | 0 | 0 | 0
Total Project Cost | 1707300 | 55497.16 | 745.63 | 54751.53 | 1651802.84

## #9508.00 Story Construction
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Geoff W.(JE) |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526308900 | 2025-11-04 | PO Procore | 19497.16 | 19497.16 |  |  | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  |  |  | 19497.16 |  | 0 | 19497.16
|  | Totals: | 19497.16 |  | 0 |  | 19497.16
|  | CM Services | 19294.66 |  |  |  | 19294.66
|  | Reimbursables | 202.5 |  |  |  | 202.5
|  | Total: | 19497.16 |  | 0 |  | 19497.16

## #9508.00 PM TIME
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734X
Project Manager - Geoff W.(JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 36000 | 36000 |  |  | 36000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 36000 | 68.53 | 68.53 | 35931.47
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 36000 | 677.1 | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
[5 empty] | 36000 |  | 745.63 | 35254.37
|  |  | Totals: | 36000 |  | 745.63 |  | 35254.37
Note on E9: Huggins, Joni [DAS]: PM Time Budget Request $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me, Geoff Please establish a PM Time budget in the project as follows: 9508.00 - FDCF Unit A, B, & G Roof Repl - $9,500.00 Thank you, Jennie Elliott Project #s 9507 & 9508 $Joni Wheelock, Geoff Nov 24, 2025, 4:37 PM (15 hours ago) to me Could you please set up a PM Time budget for these referenced projects in the amount of: 9507.00 = $15,000 9508.00 = $36,000 I greatly appreciate your help on this. Thank you,

## #9508.00 Misc
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 178
Project Manager - Geoff W.(JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9509.00
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per Geoff 11/25/25
Note on B17: Huggins, Joni [DAS]: Project 9508/9509/9510 $Joni Wheelock, Geoff Mon, Nov 24, 12:42 PM (19 hours ago) to me, Jennie Good Morning, These projects were all being rolled up into 9508 with their respective budgets being moved into 9508. Can you please assist with closing out 9509 & 9510 and moving all items to the 9508 project? Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9509.00 Vendor A
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Geoff W. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9509.00 PM TIME
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Y
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9509.00 Misc
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9510.00
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per Geoff 11/25/25
Note on B17: Huggins, Joni [DAS]: Project 9508/9509/9510 $Joni Wheelock, Geoff Mon, Nov 24, 12:42 PM (19 hours ago) to me, Jennie Good Morning, These projects were all being rolled up into 9508 with their respective budgets being moved into 9508. Can you please assist with closing out 9509 & 9510 and moving all items to the 9508 project? Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9510.00 Vendor A
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Geoff W. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9510.00 PM TIME
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Z
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9510.00 Misc
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9511.00
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 205000
McGough Construction |  | 15864.97 | 0 | 15864.97
PM TIME |  | 12000 | 910.8 | 11089.2
Misc. |  | 0 | 0 | 0
Total Project Cost | 205000 | 27864.97 | 910.8 | 26954.17 | 177135.03

## #9511.00 McGough Construction
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526322901 | 2025-11-18 | PO Procore | 15864.97 | 15864.97 |  |  | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  |  |  | 15864.97 |  | 0 | 15864.97
|  | Totals: | 15864.97 |  | 0 |  | 15864.97
|  | CM Services | 15444.97 |  |  |  | 15444.97
|  | Reimbursables | 420 |  |  |  | 420
|  | Total: | 15864.97 |  | 0 |  | 15864.97

## #9511.00 PM TIME
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735A
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12000 | 12000 |  |  | 12000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 12000 | 55.62 | 55.62 | 11944.38
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 12000 | 287.2 | 342.82 | 11657.18
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 12000 | 60.38 | 403.2 | 11596.8
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 12000 | 507.6 | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
[5 empty] | 12000 |  | 910.8 | 11089.2
|  |  | Totals: | 12000 |  | 910.8 |  | 11089.2

## #9511.00 Misc
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9512.00
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager -Oliver S. (BA)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 75000
VendorA |  | 0 | 0 | 0
PM TIME |  | 4000 | 1475.8 | 2524.2
Misc. |  | 0 | 0 | 0
Total Project Cost | 75000 | 4000 | 1475.8 | 2524.2 | 71000

## #9512.00 Vendor A
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager -Oliver S. (BA) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9512.00 PM TIME
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735B
Project Manager -Oliver S. (BA)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 4000 | 4000 |  |  | 4000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 4000 | 91 | 91 | 3909
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 4000 | 1384.8 | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
[5 empty] | 4000 |  | 1475.8 | 2524.2
|  |  | Totals: | 4000 |  | 1475.8 |  | 2524.2

## #9512.00 Misc
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager -Oliver S. (BA)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9513.00
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 640000
VendorA |  | 0 | 0 | 0
PM TIME |  | 20000 | 438.69 | 19561.31
Misc. |  | 0 | 0 | 0
Total Project Cost | 640000 | 20000 | 438.69 | 19561.31 | 620000

## #9513.00 Vendor A
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9513.00 PM TIME
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735C
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 39.99 | 39.99 | 19960.01
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 398.7 | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
[5 empty] | 20000 |  | 438.69 | 19561.31
|  |  | Totals: | 20000 |  | 438.69 |  | 19561.31
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Nov 2, 2025, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9513.00 Misc
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9514.00
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver S.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 10000
Horizon Architecture |  | 6765 | 0 | 6765
PM TIME |  | 2000 | 1400.83 | 599.17
Misc. |  | 0 | 0 | 0
Total Project Cost | 10000 | 8765 | 1400.83 | 7364.17 | 1235

## #9514.00 Horizon Architecture
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  | Major Program 4E19
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM26-9260 |  |  | SRVV5
Project Manager - Oliver S. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526287905 | 2025-10-14 | PO Procore | 6765 | 6765 |  |  | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  |  |  | 6765 |  | 0 | 6765
|  | Totals: | 6765 |  | 0 |  | 6765

## #9514.00 PM TIME
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 735D
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 2000 | 2000 |  |  | 2000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 2000 | 128.13 | 128.13 | 1871.87
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 2000 | 1272.7 | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
[5 empty] | 2000 |  | 1400.83 | 599.17
|  |  | Totals: | 2000 |  | 1400.83 |  | 599.17
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Nov 10, 2025, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget. MM26 9497.00 (858.68) Please increase the PM time budget by $10,000.00 to $10,000.00 from the unallocated budget. MM26 9514.00 (1,400.83) Please increase the PM time budget by $2,000.00 to $2,000.00 from the unallocated budget.

## #9514.00 Misc
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: C16
Project Manager - Oliver S.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #XXXX.XX
DAS Union Sunday School Structural Investigation
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Recap
Acct. Codes-0017-335-MM26
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 10000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 10000 | 0 | 0 | 0 | 10000

## #XXXX.XX Vendor A
DAS Union Sunday School Structural Investigation
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
DAS Union Sunday School Structural Investigation
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS
Project Manager -
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
DAS Union Sunday School Structural Investigation
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager -
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0