## Language
2024 Iowa Acts, Chapter 1155, Section 1 (FY2025)

## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation R52 | 22000000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22000000
| . | Less: Total Assigned |  | 21543988.5
|  | Total Unassigned / Unallocated |  | 456011.5
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9997.26 | Project Management Time | Geoff W. | 75000 |  | 75000 | 75000 | 47812.3 | 27187.7 | 0 | 27187.7
| 9440.01 | DAS CC Historical Building Elevators Replacement PH1 | Brad T. | 1750000 |  | 1750000 | 671239.86 | 111688.87 | 559550.99 | 1078760.14 | 25082.76
| 9455.00 | IDOE ISD Giangreco Hall Water Infiltration Mitigation | Jennie E | 3700000 |  | 3700000 | 2531529.39 | 290959.04 | 2240570.35 | 1168470.61 | 0
| 9483.00 | DVA IVH Dack and Malloy Building Roof Replacements | Brad T. | 2820000 |  | 2820000 | 2704825.67 | 892871.89 | 1811953.78 | 115174.33 | 60210.02
| 9484.00 | ILEA JOH Hydraulic Elevator Replacement | Brad T. | 475000 |  | 475000 | 411207.55 | 297111.18 | 114096.37 | 63792.45 | 8132.24
| 9491.00 | DOC 7 JD RTU #2 Replacement | James T. | 320000 |  | 320000 | 266688.96 | 43598.97 | 223089.99 | 53311.04 | 241.98
C | 9494.00 | IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs | Jennie E. | 0 |  | 0 | 0 | 0 | 0 | 0
C | 9495.00 | HHS IMHI Boiler #3 Replacement | Oliver S.(JE) | 0 |  | 0 | 0 | 0 | 0 | 0
| 9496.00 | DOC NCCF Replace Windows in Education Building | Jennie E. | 370000 |  | 370000 | 326173.92 | 48251.48 | 277922.44 | 43826.08 | 4922.85
| 9497.00 | HHS IMHI Warehouse Roof Replacement | James T. | 495000 |  | 495000 | 235116.54 | 63049.55 | 172066.99 | 259883.46 | 2470.79
| 9498.00 | DAS TH Parking Lot Retaining Wall Repairs | James T. | 140000 |  | 140000 | 73901.73 | 57662.94 | 16238.79 | 66098.27 | 106.15
| 9499.00 | IPBS 6535 Corporate Drive Parking Lot Replacement | Brandon A. | 440965 |  | 440965 | 410793.51 | 386098.13 | 24695.38 | 30171.49 | 1278.82
| 9500.00 | DOC MPCF Spill Containment for Diesel Tank | Brandon A. | 550000 |  | 550000 | 505936.55 | 64869.51 | 441067.04 | 44063.45 | 2571.05
| 9501.00 | DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B | Jennie E. | 275000 |  | 275000 | 231488.81 | 43496.58 | 187992.23 | 43511.19 | 5088.41
| 9502.00 | DOC MPCF Hot and Cold Water Mains Replacement | Brandon A. | 955000 |  | 955000 | 865893.42 | 550112.55 | 315780.87 | 89106.58 | 428.48
| 9503.00 | HHS WRC CDC Freezer Repair | Jennifer K. | 440000 |  | 440000 | 100770.06 | 56097.5 | 44672.56 | 339229.94 | 2445.92
| 9504.00 | HHS WRC Food Service Elevator Replacement | Jennifer K. | 400000 |  | 400000 | 118266.08 | 77119.39 | 41146.69 | 281733.92 | 3343.07
| 9505.00 | DOC FDCF Sally Port Operator Replacement | Jennie E. | 491000 |  | 491000 | 486945.01 | 65373.3 | 421571.71 | 4054.99 | 4534.24
| 9506.00 | DOC MPCF Perimeter Fence and Wagon Gates | Brandon A. | 1680747 |  | 1680747 | 196579.32 | 134913.91 | 61665.41 | 1484167.68 | 4804.14
| 9507.00 | DOC IMCC Cooling Tower Replacement | Geoff W(JK) | 700000 |  | 700000 | 451832 | 734.36 | 451097.64 | 248168 | 14265.64
| 9508.00 | DOC FDCF Unit A Roof Replacement | Geoff W(JE) | 1707300 |  | 1707300 | 1268098.9 | 85929.67 | 1182169.23 | 439201.1 | 29147.6
C | 9509.00 | DOC FDCF Boone Unit Roof Replacement | Geoff W(JE) | 0 |  | 0 | 0 | 0 | 0 | 0
C | 9510.00 | DOC FDCF Grove Unit Roof Replacement | Geoff W(JE) | 0 |  | 0 | 0 | 0 | 0 | 0
| 9511.00 | DPS P13 Upper Parking Lot Replacement | Brandon A. | 265000 |  | 265000 | 240998.92 | 57460.66 | 183538.26 | 24001.08 | 3500.86
C | 9512.00 | IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit | Brandon A. | 32103.42 |  | 32103.42 | 32103.42 | 32103.42 | 3.638e-12 | 0
| 9513.00 | HHS CHMHI Tuckpointing Phase 2.2 | Jennie E. | 640000 |  | 640000 | 413258.29 | 75404.7 | 337853.59 | 226741.71 | 10144.59
C | 9514.00 | DAS Union Sunday School Structural Investigation | Geoff W | 8573.08 |  | 8573.08 | 8573.08 | 8573.08 | 0 | 0
| 9519.00 | HHS IMHI Infirmary Building Roof Repair | James T. | 250000 |  | 250000 | 73840.22 | 26577.33 | 47262.89 | 176159.78 | 11862.5
| 9521.00 | DPS D1 1333 Ohio Roof Replacement | Brandon A. | 800000 |  | 800000 | 675988.56 | 41012.23 | 634976.33 | 124011.44 | 33745.51
| 9524.00 | DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair | Brandon A. | 250000 |  | 250000 | 70911.31 | 12001.5 | 58909.81 | 179088.69 | 2064.35
| 9527.00 | HHS CHMHI Four Corners Elevator Replacement | Jennie E. | 500000 |  | 500000 | 99485.76 | 26766.42 | 72719.34 | 400514.24 | 6522.27
| 9529.00 | HHS CHMHI Wirth Hall Tunnel Repairs | Jennie E. | 800000 |  | 800000 | 130765.88 | 15094.57 | 115671.31 | 669234.12 | 19008.22
| 9530.00 | DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair | Jennie E. | 213300 |  | 213300 | 61986.29 | 14243.88 | 47742.41 | 151313.71 | 3637.43
|  | Major Maintenance Totals |  | 21543988.5 | 0 | 21543988.5 | 13740199.01 | 3626988.91 | 10113210.1 | 7803789.49 | 259559.89
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 456011.5
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 8259800.99
[6 empty] | Total funds Available |  |  | 22000000
[6 empty] | Total obligated by contract or PO |  |  | -13740199.01 | 8259800.99
[6 empty] | Variance |  |  |  | 0
Note on E16: Huggins, Joni [DAS]: 9455.00 - Giangreco Hall Water Infiltration Mitigation - MM26 - Return of Funds $Joni Elliott, Jennie Sat, Jan 24, 1:07 PM (2 days ago) to me, Geoff, Jennifer Please reduce the Overall Budget for 9455.00 in MM26 from $4,600,000.00 down to $3,700,000.00. The remaining $900,000.00 can be returned to the Total Unassigned/Unallocated budget in MM26. Thank you, Jennie Elliott
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please make the following shifts within MM26: Project 9484.00 - Reduce budget by $100,000 as bids came in better than expected. Shift the $100,000 into project 9483.00. Project 9483.00 - If OK with Geoff and Jennifer please pull another $90,000 from the non-allocated funds of $131,688 to fund the balance of needed funds on the current project. Thank you, Brad Tonyan, CPM, LEED Green Associate Please make the following shifts within MM26: Project 9484.00 - Reduce budget by $100,000 as bids came in better than expected. Shift the $100,000 into project 9483.00. Project 9483.00 - If OK with Geoff and Jennifer please pull another $90,000 from the non-allocated funds of $131,688 to fund the balance of needed funds on the current project. Thank you, Brad Tonyan, CPM, LEED Green Associate
Note on E19: Huggins, Joni [DAS]: Major Maintenance Fund Return 3-2-2026 $Joni Shimp, Oliver Mon, Mar 2, 12:52 PM (20 hours ago) to me, Geoff, Brandon, Jennifer Good Afternoon, Could you please return the below dollar amounts from their projects to their respective Major Maintenance funds? MM26 9491.00 DOC 7 JD RTU #2 Replacement; return $150,000.00 of unallocated to MM26 pool
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Elliott, Jennie ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff​ Finance, Can you please transfer an additional $120,000.00 from the total unassigned/unallocated line in MM26 to project 9496.00 - DOC NCCF Replace Windows in Education Building. Thank you, Jennie Elliott
Note on E24: Huggins, Joni [DAS]: 9498.00 - DAS TH Parking Lot Retaining Wall Repairs - MM26 Budget $Joni Trower, James 9:19 AM (3 hours ago) to me Finance - Please add $35,000 in MM26 funds to project 9498.00. Of that $35,000, please increase PM Time by $2,000. Thanks, James Trower
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adams, Brandon ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff;​Kleene, Jennifer​ Finance, Please make the following changes: MM26 - 9499.00 DOE IPBS 6535 Parking Lot Replacement - Please return $200,000 to MM26 MM26 - 9511.00 DPS Post 13 Upper Parking Lot Replacement - Please increase funds by $60,000 Regards, Brandon Adams
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adams, Brandon ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff;​Kleene, Jennifer​ Finance, Please increase project MM26 9500.00 MPCF Diesel Tanks by $150,000 with MM26 funds. Regards, Brandon Adams
Note on E29: Huggins, Joni [DAS]: MM26 9502.00 Added Funds $Joni Adams, Brandon 10:37 AM (0 minutes ago) to me, Geoff, Jennifer Finance, Please add $450,000 to MM26 9502.00 DOC MPCF Hot and Cold Water Main Replacement project from MM26 funds. Regards, Brandon Adams
Note on E31: Huggins, Joni [DAS]: 9505.00 - DOC FDCF Sally Port Operator Replacement - MM26 $Joni Elliott, Jennie 2:14 PM (2 minutes ago) to me, Geoff Please increase the budget in MM26 for project 9505.00 by $106,000. This should bring the total project budget to $491,000.00 Thank you, Jennie Elliott
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adams, Brandon ​DAS Finance Payables Infrastructure​ Wheelock, Geoff;​Kleene, Jennifer​ Finance, Please make the following changes: MM26 - 9499.00 DOE IPBS 6535 Parking Lot Replacement - Please return $200,000 to MM26 MM26 - 9511.00 DPS Post 13 Upper Parking Lot Replacement - Please increase funds by $60,000 Regards, Brandon Adams
Note on E40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shimp, Oliver ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff​ Good Morning, Project MM26 9514.00 DAS Union Sunday School Investigation can be closed. PM Time and Misc. Contracts are all final completed. Please return any remaining funds to the MM26 funding pool. Thank you, Oliver Shimp
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adams, Brandon ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff;​Kleene, Jennifer;​Elliott, Jennie;​Tonyan, Brad;​Trower, James​ Finance, Can you please return funds for the following projects: MM25 - 9422.00 DOC ASP Tuck Pointing 7,8 & 9 - $450,000 MM26 - 9521.00 DPS D1 1333 Ohio Roof Replacement - $700,000 Regards, Brandon Adams

## RECAP #9997.26
Project Management Time
Project # 9997.26
Program code 999726 |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 75000
VendorA |  | 0 | 0 | 0
PM TIME |  | 75000 | 47812.3 | 27187.7
Misc. |  | 0 | 0 | 0
Total Project Cost | 75000 | 75000 | 47812.3 | 27187.7 | 0

## #9997.26 PM TIME
Project Management Time
Project # 9997.26
Program code 999726 |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733L
Project Manager - Geoff W.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
[5 empty] | 75000 |  | 0 | 75000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 75000 | 1463.15 | 1463.15 | 73536.85
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 75000 | 6111.2 | 7574.35 | 67425.65
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9436.00 |  | 75000 | -110.44 | 7463.91 | 67536.09
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9440.00 |  | 75000 | -144.14 | 7319.77 | 67680.23
CDE 33526246821 | 2025-09-11 | 2507 | Move expense to 9420.00 |  | 75000 | -169.68 | 7150.09 | 67849.91
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9436.00 |  | 75000 | -1211.1 | 5938.99 | 69061.01
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9440.00 |  | 75000 | -1595.5 | 4343.49 | 70656.51
CDE 33526246821 | 2025-09-11 | 9500 | Move expense to 9420.00 |  | 75000 | -1854.9 | 2488.59 | 72511.41
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 75000 | 2070.07 | 4558.66 | 70441.34
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 75000 | 2472.3 | 7030.96 | 67969.04
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 75000 | 3801.19 | 10832.15 | 64167.85
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 75000 | 2413.6 | 13245.75 | 61754.25
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 75000 | 2021.01 | 15266.76 | 59733.24
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 75000 | 27910.6 | 43177.36 | 31822.64
CDE 33526317909 | 2025-11-13 | 2507 | Move from DA26 9481.00 |  | 75000 | 300.34 | 43477.7 | 31522.3
CDE 33526317909 | 2025-11-13 | 9500 | Move from DA26 9481.00 |  | 75000 | 571.2 | 44048.9 | 30951.1
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 75000 | 2222.7 | 46271.6 | 28728.4
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 75000 | 1513.8 | 47785.4 | 27214.6
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 75000 | 1572.63 | 49358.03 | 25641.97
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 75000 | 2305.9 | 51663.93 | 23336.07
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 75000 | 1295.7 | 52959.63 | 22040.37
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 75000 | 1468.4 | 54428.03 | 20571.97
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 75000 | 1448.3 | 55876.33 | 19123.67
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 75000 | 1782.4 | 57658.73 | 17341.27
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 75000 | 2230.7 | 59889.43 | 15110.57
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 75000 | 1361.8 | 61251.23 | 13748.77
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 75000 | 1894.52 | 63145.75 | 11854.25
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 75000 | 2057 | 65202.75 | 9797.25
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 75000 | 1497.61 | 66700.36 | 8299.64
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 75000 | 1588.9 | 68289.26 | 6710.74
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 75000 | 1518.39 | 69807.65 | 5192.35
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 75000 | -22605 | 47202.65 | 27797.35
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 75000 | 609.65 | 47812.3 | 27187.7
[5 empty] | 75000 |  | 47812.3 | 27187.7
[5 empty] | 75000 |  | 47812.3 | 27187.7
|  |  | Totals: | 75000 |  | 47812.3 |  | 27187.7
Note on E9: Jurgenson, John [DAS]: Re: FY 26 9997.26 PM Time Inbox Cross, Charlee 8:33 AM (1 minute ago) to me Yes. Thank you! Charlee Cross Chief Operating Officer General Services Enterprise Iowa Department of Administrative Services 109 SE 13th Street Des Moines, Iowa 50319 515-725-2281 (desk) 515-802-1653 (mobile) charlee.cross@iowa.gov https://das.iowa.gov On Thu, Jul 3, 2025 at 8:25 AM Jurgenson, John <john.jurgenson@iowa.gov> wrote: Hello Charlee May I have permission to set up a 9997.26 FY26 PM time budget as we have in the past with a $75,000.00 budget?

## RECAP #9440.01
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1750000
DCI Group |  | 18399.16 | 8664.89 | 9734.27
PM TIME |  | 30000 | 4917.24 | 25082.76
Misc. |  | 1617.74 | 1617.74 | 0
OPN Architects |  | 143190 | 96489 | 46701
DCI Group (2) |  | 219929.96 | 0 | 219929.96
Bergstrum Construction |  | 146245 | 0 | 146245
VanMaanen Electric |  | 111858 | 0 | 111858
Total Project Cost | 1750000 | 671239.86 | 111688.87 | 559550.99 | 1078760.14

## #9440.01 DCI Group
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526055913 | 2026-02-24 | PO Procore | 18399.16 | 18399.16 |  |  | 18399.16
PRC 3352605PA5913 | 2026-04-15 | Inv. 9440.01 PC 01 |  | 18399.16 | 1104.72 | 1104.72 | 17294.44
PRC 3352605PB5913 | 2026-05-12 | Inv. 9440.01 PC #02 |  | 18399.16 | 1700.85 | 2805.57 | 15593.59
PRC 3352605PC5913 | 2026-06-04 | Inv. 9440.01 PC #03 |  | 18399.16 | 2741.83 | 5547.4 | 12851.76
PRC 3352605PD5913 | 2026-07-13 | Inv. 9440.01 PC #04 |  | 18399.16 | 3117.49 | 8664.89 | 9734.27 | FY26
PO 33527055913 | 2026-07-22 | Roll to FY27 | 0 | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  |  |  | 18399.16 |  | 8664.89 | 9734.27
|  | Totals: | 18399.16 |  | 8664.89 |  | 9734.27
|  | CM Services | 17399.16 |  | 8664.89 |  | 8734.27
|  | Reimbursables | 1000 |  |  |  | 1000
|  | Total: | 18399.16 |  | 8664.89 |  | 9734.27

## #9440.01 PM TIME
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  |  | Major Program: 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911I
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 30000 | 30000 |  |  | 30000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 30000 | 48.78 | 48.78 | 29951.22
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 30000 | 561.5 | 610.28 | 29389.72
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 30000 | 51.76 | 662.04 | 29337.96
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 30000 | 419.3 | 1081.34 | 28918.66
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 30000 | 104.88 | 1186.22 | 28813.78
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 30000 | 1094.9 | 2281.12 | 27718.88
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 30000 | 97.92 | 2379.04 | 27620.96
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 30000 | 1201.5 | 3580.54 | 26419.46
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 30000 | 103.54 | 3684.08 | 26315.92
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 30000 | 1191.4 | 4875.48 | 25124.52
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 30000 | 41.76 | 4917.24 | 25082.76
[5 empty] | 30000 |  | 4917.24 | 25082.76
|  |  | Totals: | 30000 |  | 4917.24 |  | 25082.76

## #9440.01 Misc
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  |  | Major Program: 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 035
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526187907 | 2026-07-06 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2720306 | 1350.5 | 1350.5
PRC 33526202900 | 2026-07-21 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2989 | 267.24 | 1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
1617.74
|  |  |  | Totals: |  | 1617.74

## #9440.01 OPN Architects
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM26-9260 |  |  | RFP944000-01
Project Manager - Brad T |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526062911 | 2026-03-03 | PO Procore | 143190 | 143190 |  |  | 143190
PRC 3352606PA2911 | 2026-05-13 | Inv. 26817000-1 |  | 143190 | 2790.96 | 2790.96 | 140399.04
PRC 3352606PB2911 | 2026-06-03 | Inv. 26817000-2 |  | 143190 | 10234.56 | 13025.52 | 130164.48
PRC 3352606PC2911 | 2026-07-13 | Inv. 26817000-3 |  | 143190 | 83463.48 | 96489 | 46701 | FY26
PO 33527062911 | 2026-07-22 | Roll to FY27 | 0 | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  |  |  | 143190 |  | 96489 | 46701
|  | Totals: | 143190 |  | 96489 |  | 46701
Elevator #3
|  | 50% CDs | 15910 |  | 15910 |  | 0
|  | 100% CDs | 15910 |  | 15910 |  | 0
|  | Bid | 343 |  | 343 |  | 0
|  | Construction Admin | 15567 |  |  |  | 15567
|  | Sub Total | 47730 |  | 32163 |  | 15567
Elevator #4
|  | 50% CDs | 15910 |  | 15910 |  | 0
|  | 100% CDs | 15910 |  | 15910 |  | 0
|  | Bid | 343 |  | 343 |  | 0
|  | Construction Admin | 15567 |  |  |  | 15567
|  | Sub Total | 47730 |  | 32163 |  | 15567
Elevator #5
|  | 50% CDs | 15910 |  | 15910 |  | 0
|  | 100% CDs | 15910 |  | 15910 |  | 0
|  | Bid | 343 |  | 343 |  | 0
|  | Construction Admin | 15567 |  |  |  | 15567
|  | Sub Total | 47730 |  | 32163 |  | 15567
|  | Grand Total | 143190 |  | 96489 |  | 46701

## #9440.01 DCI Group (2)
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527204905 | 2026-07-23 | PO Procore | 219929.96 | 219929.96 |  |  | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  |  |  | 219929.96 |  | 0 | 219929.96
|  | Totals: | 219929.96 |  | 0 |  | 219929.96
|  | CM Services | 154008.01 |  |  |  | 154008.01
|  | Reimbursables | 5000 |  |  |  | 5000
|  | Fee | 60921.95 |  |  |  | 60921.95
|  | Total: | 219929.96 |  | 0 |  | 219929.96

## #9440.01 Bergstrom Construction
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0017-335-MM26-9255 |  |  | RFB944001-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527204906 | 2026-07-23 | PO Procore | 146245 | 146245 |  |  | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  |  |  | 146245 |  | 0 | 146245
|  | Totals: | 146245 |  | 0 |  | 146245

## #9440.01 VanMaanen Electric
DAS CC Historical Building Elevators Replacement PH1
Project # 9440.01
Program code 944001 |  |  | Major Program: 4D03
VanMaanen Electric |  |  | Vendor: 00002091370
Acct. Codes-0017-335-MM26-9255 |  |  | RFB #944001-01
Project Manager - Brad T |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527208910 | 2026-07-27 | PO Procore | 111858 | 111858 |  |  | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  |  |  | 111858 |  | 0 | 111858
|  | Totals: | 111858 |  | 0 |  | 111858

## RECAP #9455.00
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
| Program code 945500 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 3700000
| McKinnis Roofing & Sheet Metal |  | 2454306 | 213735.65 | 2240570.35
| PM TIME |  | 0 | 0 | 0
| Misc. |  | 10361 | 10361 | 0
C | Samuels Group |  | 66862.39 | 66862.39 | 0
| Total Project Cost | 3700000 | 2531529.39 | 290959.04 | 2240570.35 | 1168470.61

## #9455.00 McKinnis Roofing
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
McKinnis Roofing |  |  | Vendor: 00003217305
Acct. Codes-0017-335-MM26-9255 |  |  | RFB945500-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Spilt w/DA27
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526002900 | 2026-01-02 | PO Procore | 2454306 | 2454306 |  |  | 2454306
PRC 3352600PA2900 | 2026-06-19 | Inv. 49368 |  | 2454306 | 213735.65 | 213735.65 | 2240570.35 | 6610.38 | FY26
PO 33527002900 | 2026-07-31 | Roll to FY27 | 0 | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  |  |  | 2454306 |  | 213735.65 | 2240570.35
|  | Totals: | 2454306 |  | 213735.65 |  | 2240570.35

## #9455.00 PM TIME
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735L
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 0 | 96.6 | 96.6 | -96.6
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 0 | 1061.8 | 1158.4 | -1158.4
CDE 33526140900 | 2026-05-20 | 2507 | Moving April Finance Support to MM25 |  | 0 | -96.6 | 1061.8 | -1061.8
CDE 33526140900 | 2026-05-20 | 9500 | Moving April DAS Support to MM25 |  | 0 | -1061.8 | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9455.00 Misc
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 231A
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526065905 | 2026-03-06 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 880061 | 6639 | 6639
PRC 33526187908 | 2026-07-06 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 899580 | 3722 | 10361
10361
10361
10361
10361
10361
10361
10361
10361
10361
10361
|  |  |  | Totals: |  | 10361

## #9455.00 Samuels Group
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Split w/DA27
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526029913 | 2026-01-29 | PO Procore | 750625.68 | 750625.68 |  |  | 750625.68
PRC 3352602PA9913 | 2026-02-04 | Inv. 7850.51945500 |  | 750625.68 | 1793.69 | 1793.69 | 748831.99
PRC 3352602PB9913 | 2026-03-03 | Inv. 7850.52945500 |  | 750625.68 | 2668.08 | 4461.77 | 746163.91
PRC 3352602PC9913 | 2026-04-09 | Inv. 7850.53945500 |  | 750625.68 | 3139.91 | 7601.68 | 743024
PRC 3352602PD9913 | 2026-05-21 | Inv. 7850.54945500 |  | 750625.68 | 23878.53 | 31480.21 | 719145.47
PRC 3352602PE9913 | 2026-06-16 | Inv. 7850.55945500 |  | 750625.68 | 17483.14 | 48963.35 | 701662.33
PRC 3352602PF9913 | 2026-07-06 | Inv. 7850.56945500 |  | 750625.68 | 17899.04 | 66862.39 | 683763.29
PO 33526029913 | 2026-07-23 | CO #1(Split w/ DA27) | -683763.29 | 66862.39 |  | 66862.39 | 0
|  |  |  | 66862.39 |  | 66862.39 | 0
|  |  |  | 66862.39 |  | 66862.39 | 0
|  |  |  | 66862.39 |  | 66862.39 | 0
|  |  |  | 66862.39 |  | 66862.39 | 0
|  |  |  | 66862.39 |  | 66862.39 | 0
|  | Totals: | 66862.39 |  | 66862.39 |  | 0
|  | CM Services | 570253.44 |  | 47964 |  | 522289.44
|  | Reimbursables (Hotels, Mileage, Meals) | 61600 |  | 3836.45 |  | 57763.55
|  | Reimbursables(Temp Trailer $600 monthly) | 12600 |  | 455 |  | 12145
|  | Reimbursables(Temp Power Utilities) | 8000 |  | 2125.22 |  | 5874.78
|  | 4% Samuels GroupFee | 98172.24 |  | 12481.72 |  | 85690.52
|  | CO #1 | -683763.29 |  |  |  | -683763.29
|  | Total: | 66862.39 |  | 66862.39 |  | 0
|  | DA27 | 683763.29 |  | 0 |  | 683763.29
|  | Total: | 750625.68 |  | 66862.39 |  | 683763.29

## RECAP #9483.00
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
| Program code 948300 |  |  | Major Program 4D02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 2820000
C | DCI Group |  | 34876.44 | 34876.44 | 0
| PM TIME |  | 75000 | 14789.98 | 60210.02
| Misc. |  | 5209.09 | 5209.09 | 0
| Genesis Architectural |  | 35000 | 27525 | 7475
| Academy Roofing |  | 2287400 | 766970 | 1520430
| DCI Group (2) |  | 267340.14 | 43501.38 | 223838.76
| Total Project Cost | 2820000 | 2704825.67 | 892871.89 | 1811953.78 | 115174.33

## #9483.00 DCI Group
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259901 | 2025-09-16 | PO Procore | 28802.14 | 28802.14 |  |  | 28802.14
PRC 3352625PA9901 | 2025-10-17 | Inv. 25-021 PC 01 |  | 28802.14 | 2681.52 | 2681.52 | 26120.62
PRC 3352625PB9901 | 2025-12-03 | Inv. 25-021 PC 02 |  | 28802.14 | 1660.86 | 4342.38 | 24459.76
PRC 3352625PC9901 | 2025-12-22 | Inv. 25-021 PC 03 |  | 28802.14 | 2057.76 | 6400.14 | 22402
PRC 3352625PD9901 | 2026-01-26 | Inv. 25-021 PC 04 |  | 28802.14 | 3636.54 | 10036.68 | 18765.46
PRC 3352625PE9901 | 2026-02-24 | Inv. 25-021 PC 05 |  | 28802.14 | 4439.11 | 14475.79 | 14326.35
PRC 3352625PF9901 | 2026-03-20 | Inv. 25-021 PC 06 |  | 28802.14 | 6508.76 | 20984.55 | 7817.59
PRC 3352625PG9901 | 2026-04-17 | Inv. 25-021 PC 07 |  | 28802.14 | 6453.33 | 27437.88 | 1364.26
PO 33526259901 | 2026-06-18 | CO #1 | 7232.56 | 36034.7 |  | 27437.88 | 8596.82
PRC 3352625PH9901 | 2026-06-18 | Inv. 25-021 PC #08 FINAL | -1158.26 | 34876.44 | 7438.56 | 34876.44 | 0
|  |  |  | 34876.44 |  | 34876.44 | 0
|  |  |  | 34876.44 |  | 34876.44 | 0
|  |  |  | 34876.44 |  | 34876.44 | 0
|  | Totals: | 34876.44 |  | 34876.44 |  | 0 | FINAL
|  | CM Services | 27283.38 |  | 27283.38 |  | 0
|  | Reimbursables | 360.5 |  | 360.5 |  | 0
|  | CO #1 | 7232.56 |  | 7232.56 |  | 0
|  | Total: | 34876.44 |  | 34876.44 |  | 0

## #9483.00 PM TIME
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  |  | Major Program 4D02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733Q
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 75000 | 47.89 | 47.89 | 74952.11
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 75000 | 532.2 | 580.09 | 74419.91
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 75000 | 94.58 | 674.67 | 74325.33
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 75000 | 732.6 | 1407.27 | 73592.73
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 75000 | 100.03 | 1507.3 | 73492.7
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 75000 | 522.8 | 2030.1 | 72969.9
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 75000 | 42.41 | 2072.51 | 72927.49
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 75000 | 417.3 | 2489.81 | 72510.19
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 75000 | 131.64 | 2621.45 | 72378.55
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 75000 | 838.8 | 3460.25 | 71539.75
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 75000 | 84.69 | 3544.94 | 71455.06
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 75000 | 961.7 | 4506.64 | 70493.36
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 75000 | 114.24 | 4620.88 | 70379.12
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 75000 | 1416.7 | 6037.58 | 68962.42
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 75000 | 97.23 | 6134.81 | 68865.19
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 75000 | 1120.8 | 7255.61 | 67744.39
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 75000 | 217.75 | 7473.36 | 67526.64
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 75000 | 1762.4 | 9235.76 | 65764.24
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 75000 | 155.82 | 9391.58 | 65608.42
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 75000 | 1623.5 | 11015.08 | 63984.92
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 75000 | 158.08 | 11173.16 | 63826.84
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 75000 | 1931.8 | 13104.96 | 61895.04
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 75000 | 130.66 | 13235.62 | 61764.38
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 75000 | 1502.1 | 14737.72 | 60262.28
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 75000 | 52.26 | 14789.98 | 60210.02
[5 empty] | 75000 |  | 14789.98 | 60210.02
[5 empty] | 75000 |  | 14789.98 | 60210.02
|  |  | Totals: | 75000 |  | 14789.98 |  | 60210.02
Note on E9: Huggins, Joni [DAS]: Re: FY26 - New Project Set Up Request in MM26 $Joni Tonyan, Brad Wed, Jul 16, 2:29 PM (16 hours ago) to me Joni, Yes, please see below: 9483.00 - Set up PM time of $75,000 9484.00 - Set up PM time of $20,000 Thank you, Brad Tonyan, CPM, LE

## #9483.00 Misc
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  |  | Major Program 4D02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 558
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526076900 | 2026-03-17 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2701106 | 2712.5 | 2712.5
GAX 33526083901 | 2026-03-24 | 9500 | CNST | Academy Roofing V#(00003010234) | Inv. 30585 | 2100.15 | 4812.65
PRC 33526120911 | 2026-04-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV057582 | 396.44 | 5209.09
5209.09
5209.09
5209.09
5209.09
5209.09
5209.09
5209.09
5209.09
5209.09
|  |  |  | Totals: |  | 5209.09

## #9483.00 Genesis Architectural
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM26-9260 |  |  | RFB948300-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526328905 | 2025-11-24 | PO Procore | 35000 | 35000 |  |  | 35000
PRC 3352632PA8905 | 2026-04-07 | Inv. 2516-01 |  | 35000 | 22000 | 22000 | 13000
PRC 3352632PB8905 | 2026-07-07 | Inv. 2516-02 |  | 35000 | 5525 | 27525 | 7475 | FY26
PO 33527328905 | 2026-07-22 | Roll to FY27 | 0 | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  |  |  | 35000 |  | 27525 | 7475
|  | Totals: | 35000 |  | 27525 |  | 7475
|  | 50% CD Design Phase | 10000 |  | 10000 |  | 0
|  | 100% Construction Docs | 12000 |  | 12000 |  | 0
|  | Bidding Phase Services | 1500 |  | 1500 |  | 0
|  | Construction Phase Services | 11500 |  | 4025 |  | 7475
|  | Total: | 35000 |  | 27525 |  | 7475

## #9483.00 Academy Roofing
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
Academy Roofing |  |  | Vendor: 00003010234
Acct. Codes-0017-335-MM26-9255 |  |  | RFB948300-01
Project Manager - Brad T. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526126918 | 2026-05-06 | PO Procore | 2287400 | 2287400 |  |  | 2287400
PRC 3352612PA6918 | 2026-07-17 | Inv. 9483.00-#1 |  | 2287400 | 766970 | 766970 | 1520430 | 23720.72 | FY26
PO 33527126918 | 2026-07-22 | Roll to FY27 | 0 | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  |  |  | 2287400 |  | 766970 | 1520430
|  | Totals: | 2287400 |  | 766970 |  | 1520430

## #9483.00 DCI Group (2)
DVA IVH Dack and Malloy Building Roof Replacements
Project # 9483.00
Program code 948300 |  |  | Major Program 4D02
DCI Group(2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526142915 | 2026-05-22 | PO Procore | 267340.14 | 267340.14 |  |  | 267340.14
PRC 3352614PA2915 | 2026-07-06 | Inv. 25-021 CA #01 |  | 267340.14 | 23227.12 | 23227.12 | 244113.02
PRC 3352614PB2915 | 2026-07-13 | Inv. 25-021 CA 02 |  | 267340.14 | 20274.26 | 43501.38 | 223838.76 | FY26
PO 33527142915 | 2026-07-22 | Roll to FY27 | 0 | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  |  |  | 267340.14 |  | 43501.38 | 223838.76
|  | Totals: | 267340.14 |  | 43501.38 |  | 223838.76
|  | CM Services | 164692.14 |  | 28952.98 |  | 135739.16
|  | Reimbursables | 11152 |  | 824 |  | 10328
|  | Fee | 91496 |  | 13724.4 |  | 77771.6
|  | Total: | 267340.14 |  | 43501.38 |  | 223838.76

## RECAP #9484.00
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
| Program code 948400 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brad T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 475000
C | DCI Group |  | 17210.76 | 17210.76 | 0
| PM TIME |  | 20000 | 11867.76 | 8132.24
| Misc. |  | 223.08 | 223.08 | 0
| OPN Architects |  | 68920 | 66852.4 | 2067.6
| GTG Construction |  | 85952.23 | 47190.5 | 38761.73
| Schumacher Elevator |  | 123444 | 101663.86 | 21780.14
| DCI Group (2) |  | 74210.77 | 30856.11 | 43354.66
C | J. Pettiecord, Inc |  | 21246.71 | 21246.71 | 0
| Total Project Cost | 475000 | 411207.55 | 297111.18 | 114096.37 | 63792.45

## #9484.00 DCI Group
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526255901 | 2025-09-12 | PO Procore | 18125.32 | 18125.32 |  |  | 18125.32
PRC 3352625PA5901 | 2025-09-23 | Inv. 25-022 PC 01 |  | 18125.32 | 2093.64 | 2093.64 | 16031.68
PRC 3352625PB5901 | 2025-10-08 | Inv. 25-022 PC 02 |  | 18125.32 | 2180.88 | 4274.52 | 13850.8
PRC 3352625PC5901 | 2025-11-18 | Inv. 25-022 PC 03 |  | 18125.32 | 3208.58 | 7483.1 | 10642.22
PRC 3352625PD5901 | 2025-12-22 | Inv. 25-022 PC 04 |  | 18125.32 | 6703.07 | 14186.17 | 3939.15
PRC 3352625PE5901 | 2026-01-21 | Inv. 25-022 PC 05 FINAL | -914.56 | 17210.76 | 3024.59 | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  |  |  | 17210.76 |  | 17210.76 | 0
|  | Totals: | 17210.76 |  | 17210.76 |  | 0 | FINAL
|  | CM Services | 16114.76 |  | 16114.76 |  | 0
|  | Reimbursables | 1096 |  | 1096 |  | 0
|  | Total: | 17210.76 |  | 17210.76 |  | 0

## #9484.00 PM TIME
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 733R
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 20000 | 47.89 | 47.89 | 19952.11
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 20000 | 532.2 | 580.09 | 19419.91
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 20000 | 105.15 | 685.24 | 19314.76
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 20000 | 820.1 | 1505.34 | 18494.66
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 154.88 | 1660.22 | 18339.78
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 808.3 | 2468.52 | 17531.48
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 71.84 | 2540.36 | 17459.64
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 712.1 | 3252.46 | 16747.54
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 105.54 | 3358 | 16642
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 670.4 | 4028.4 | 15971.6
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 128.69 | 4157.09 | 15842.91
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 1465.3 | 5622.39 | 14377.61
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 104.43 | 5726.82 | 14273.18
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 1295.3 | 7022.12 | 12977.88
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 75.26 | 7097.38 | 12902.62
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 862.2 | 7959.58 | 12040.42
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 93.15 | 8052.73 | 11947.27
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 756 | 8808.73 | 11191.27
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 20000 | 62.08 | 8870.81 | 11129.19
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 20000 | 649.5 | 9520.31 | 10479.69
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 20000 | 63.47 | 9583.78 | 10416.22
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 20000 | 772.4 | 10356.18 | 9643.82
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 20000 | 117.11 | 10473.29 | 9526.71
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 20000 | 1347.3 | 11820.59 | 8179.41
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 20000 | 47.17 | 11867.76 | 8132.24
[5 empty] | 20000 |  | 11867.76 | 8132.24
[5 empty] | 20000 |  | 11867.76 | 8132.24
|  |  | Totals: | 20000 |  | 11867.76 |  | 8132.24
Note on E9: Huggins, Joni [DAS]: Re: FY26 - New Project Set Up Request in MM26 $Joni Tonyan, Brad Wed, Jul 16, 2:29 PM (16 hours ago) to me Joni, Yes, please see below: 9483.00 - Set up PM time of $75,000 9484.00 - Set up PM time of $20,000 Thank you, Brad Tonyan, CPM, LEED Green Assoc

## #9484.00 Misc
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 570
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526356903 | 2025-12-22 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2382 | 223.08 | 223.08
223.08
223.08
223.08
223.08
223.08
223.08
223.08
223.08
223.08
223.08
223.08
|  |  |  | Totals: |  | 223.08

## #9484.00 OPN Architects
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM26-9260 |  |  | RFP#948400-01
Project Manager - Brad T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259909 | 2025-09-16 | PO Procore | 68920 | 68920 |  |  | 68920
PRC 3352625PA9909 | 2025-11-05 | Inv. 25832000-1 |  | 68920 | 25500.4 | 25500.4 | 43419.6
PRC 3352625PB9909 | 2025-12-04 | Inv. 25832000-2 |  | 68920 | 19297.6 | 44798 | 24122
PRC 3352625PC9909 | 2026-01-12 | Inv. 25832000-3 |  | 68920 | 3446 | 48244 | 20676
PRC 3352625PD9909 | 2026-02-12 | Inv. 25832000-4 |  | 68920 | 3101.4 | 51345.4 | 17574.6
PRC 3352625PE9909 | 2026-03-10 | Inv. 25832000-5 |  | 68920 | 3101.4 | 54446.8 | 14473.2
PRC 3352625PF9909 | 2026-04-03 | Inv. 25832000-6 |  | 68920 | 3101.4 | 57548.2 | 11371.8
PRC 3352625PG9909 | 2026-05-12 | Inv. 25832000-7 |  | 68920 | 3101.4 | 60649.6 | 8270.4
PRC 3352625PH9909 | 2026-06-03 | Inv. 25832000-8 |  | 68920 | 3101.4 | 63751 | 5169
PRC 3352625PI9909 | 2026-07-09 | Inv. 25832000-9 |  | 68920 | 3101.4 | 66852.4 | 2067.6 | FY26
PO 33527259909 | 2026-07-22 | Roll to FY27 | 0 | 68920 |  | 66852.4 | 2067.6
|  |  |  | 68920 |  | 66852.4 | 2067.6
|  |  |  | 68920 |  | 66852.4 | 2067.6
|  | Totals: | 68920 |  | 66852.4 |  | 2067.6
|  | Investigation & Design Docs | 17435 |  | 17435 |  | 0
|  | Construction Docs | 28010 |  | 28010 |  | 0
|  | Bidding & Negotiation | 3220 |  | 3220 |  | 0
|  | Construction Phase | 20255 |  | 18187.4 |  | 2067.6
|  | Total: | 68920 |  | 66852.4 |  | 2067.6

## #9484.00 GTG Construction
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
GTG Construction |  |  | Vendor: 00003032746
Acct. Codes-0017-335-MM26-9255 |  |  | RFP#948400-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526363904 | 2025-12-29 | PO Procore | 82600 | 82600 |  |  | 82600
PRC 3352636PA3904 | 2026-02-03 | Inv. 9484.00-001 |  | 82600 | 3880 | 3880 | 78720 | 120
PRC 3352636PB3904 | 2026-03-24 | Inv. 9484.00-002 |  | 82600 | 485 | 4365 | 78235 | 135
PRC 3352636PC3904 | 2026-03-26 | Inv. 9484.00-003 |  | 82600 | 970 | 5335 | 77265 | 165
PO 33526363904 | 2026-06-25 | CO #1 | 3352.23 | 85952.23 |  | 5335 | 80617.23
PRC 3352636PD3904 | 2026-07-21 | Inv. 9484.00-004 |  | 85952.23 | 41855.5 | 47190.5 | 38761.73 | 1459.5 | FY26
PO 33527363904 | 2026-07-22 | Roll to FY27 | 0 | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  |  |  | 85952.23 |  | 47190.5 | 38761.73
|  | Totals: | 85952.23 |  | 47190.5 |  | 38761.73
3% Retainage

## #9484.00 Schumacher Elevator
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
Schumacher Elevator |  |  | Vendor: 00002108471
Acct. Codes-0017-335-MM26-9255 |  |  | RFB #948400-01
Project Manager - Brad T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526009905 | 2026-01-09 | PO Procore | 123444 | 123444 |  |  | 123444
PO 33526009905 | 2026-06-25 | CO #1(No Cost CO) | 0 | 123444 |  | 0 | 123444
PRC 3352600PA9905 | 2026-07-15 | Inv. 90686471 |  | 123444 | 101663.86 | 101663.86 | 21780.14 | 3144.24 | FY26
PO 33527009905 | 2026-07-22 | Roll to FY27 | 0 | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  |  |  | 123444 |  | 101663.86 | 21780.14
|  | Totals: | 123444 |  | 101663.86 |  | 21780.14

## #9484.00 DCI Group (2)
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Brad T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526033911 | 2026-02-02 | PO Procore | 74210.77 | 74210.77 |  |  | 74210.77
PRC 3352603PA3911 | 2026-03-24 | Inv. 23-022 CA 01 |  | 74210.77 | 4451.88 | 4451.88 | 69758.89
PRC 3352603PB3911 | 2026-04-15 | Inv. 23-022 CA 02 |  | 74210.77 | 2027.2 | 6479.08 | 67731.69
PRC 3352603PC3911 | 2026-05-12 | Inv. 23-022 CA #03 |  | 74210.77 | 3804.32 | 10283.4 | 63927.37
PRC 3352603PD3911 | 2026-06-15 | Inv. 25-022 CA #04 |  | 74210.77 | 6525.17 | 16808.57 | 57402.2
PRC 3352603PE3911 | 2026-07-10 | Inv. 25-022 CA #05 |  | 74210.77 | 12558.13 | 29366.7 | 44844.07
PRC 3352603PF3911 | 2026-07-15 | Inv. 25-022 CA 06 |  | 74210.77 | 1489.41 | 30856.11 | 43354.66 | FY26
PO 33527033911 | 2026-07-22 | Roll to FY27 | 0 | 74210.77 |  | 30856.11 | 43354.66
|  |  |  | 74210.77 |  | 30856.11 | 43354.66
|  |  |  | 74210.77 |  | 30856.11 | 43354.66
|  |  |  | 74210.77 |  | 30856.11 | 43354.66
|  |  |  | 74210.77 |  | 30856.11 | 43354.66
|  |  |  | 74210.77 |  | 30856.11 | 43354.66
|  | Totals: | 74210.77 |  | 30856.11 |  | 43354.66
|  | CM Services | 69210.77 |  | 29366.7 |  | 39844.07
|  | Reimbursables | 5000 |  | 1489.41 |  | 3510.59
|  | Total: | 74210.77 |  | 30856.11 |  | 43354.66

## #9484.00 J.Pettiecord
ILEA JOH Hydraulic Elevator Replacement
Project # 9484.00
Program code 948400 |  |  | Major Program 4D03
J. Pettiecord, Inc |  |  | Vendor: 00002120072
Acct. Codes-0017-335-MM26-9255 |  |  | SRVV5
Project Manager - Brad T. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526167910 | 2026-06-16 | PO Procore | 21960 | 21960 |  |  | 21960
PRC 3352616PA7910 | 2026-07-13 | Inv. 77080 | -713.29 | 21246.71 | 21246.71 | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  |  |  | 21246.71 |  | 21246.71 | 9.0949e-13
|  | Totals: | 21246.71 |  | 21246.71 |  | 0 | FINAL
|  | Remediation | 20500 |  | 20500 |  | 0
|  | Permit Application Prep | 250 |  | 250 |  | 0
|  | Landfill Disposal | 496.71 |  | 496.71 |  | 0
|  | Total: | 21246.71 |  | 21246.71 |  | 0

## RECAP #9491.00
DOC 7 JD RTU #2 Replacement
Project # 9491.00
| Program code 949100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM26
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 320000
C | DCI Group |  | 7888.53 | 7888.53 | 0
| PM TIME |  | 15000 | 14758.02 | 241.98
| Misc. |  | 200 | 200 | 0
| KCL Engineering |  | 17675 | 15875 | 1800
| Modern Piping Services |  | 203524 | 3948.37 | 199575.63
| DCI Group(2) |  | 22401.43 | 929.05 | 21472.38
| Total Project Cost | 320000 | 266688.96 | 43598.97 | 223089.99 | 53311.04

## #9491.00 DCI Group
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526259900 | 2025-09-16 | PO Procore | 18131.88 | 18131.88 |  |  | 18131.88 |  | `
PRC 3352625PA9900 | 2025-10-28 | Inv. 25-033 PC 01 |  | 18131.88 | 2473.03 | 2473.03 | 15658.85
PRC 3352625PB9900 | 2025-11-21 | Inv. 25-033 PC 02 |  | 18131.88 | 524.75 | 2997.78 | 15134.1
PRC 3352625PC9900 | 2025-12-29 | Inv. 25-033 PC 03 |  | 18131.88 | 1060.41 | 4058.19 | 14073.69
PRC 3352625PD9900 | 2026-01-22 | Inv. 25-033 PC 04 |  | 18131.88 | 1234.88 | 5293.07 | 12838.81
PRC 3352625PE9900 | 2026-02-24 | Inv. 25-033 PC 05 |  | 18131.88 | 1053.62 | 6346.69 | 11785.19
PRC 3352625PF9900 | 2026-03-24 | Inv. 25-033 PC 06 FINAL | -10243.35 | 7888.53 | 1541.84 | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  |  |  | 7888.53 |  | 7888.53 | 0
|  | Totals: | 7888.53 |  | 7888.53 |  | 0 | FINAL
|  | CM Services | 7716.03 |  | 7716.03 |  | 0
|  | Reimbursables | 172.5 |  | 172.5 |  | 0
|  | Total: | 7888.53 |  | 7888.53 |  | 0

## #9491.00 PM TIME
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 911F
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 15000 | 167.7 | 167.7 | 14832.3
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 15000 | 1292.9 | 1460.6 | 13539.4
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 15000 | 431 | 1891.6 | 13108.4
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 15000 | 2215.6 | 4107.2 | 10892.8
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 91 | 4198.2 | 10801.8
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 903 | 5101.2 | 9898.8
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 15000 | 168.32 | 5269.52 | 9730.48
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 15000 | 1072.3 | 6341.82 | 8658.18
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 15000 | 107.3 | 6449.12 | 8550.88
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 15000 | 1217.6 | 7666.72 | 7333.28
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 15000 | 77.31 | 7744.03 | 7255.97
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 15000 | 965.6 | 8709.63 | 6290.37
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 15000 | 154.72 | 8864.35 | 6135.65
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 15000 | 1782.4 | 10646.75 | 4353.25
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 15000 | 66.22 | 10712.97 | 4287.03
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 15000 | 537.4 | 11250.37 | 3749.63
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 15000 | 80.17 | 11330.54 | 3669.46
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 15000 | 836.1 | 12166.64 | 2833.36
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 15000 | 200.13 | 12366.77 | 2633.23
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 15000 | 2310.6 | 14677.37 | 322.63
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 15000 | 80.65 | 14758.02 | 241.98
|  |  | Totals: | 15000 |  | 14758.02 |  | 241.98
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Mon, Nov 10, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget. Re: February PM Time Posted $Joni Shimp, Oliver Mar 13, 2026, 8:26 AM (3 days ago) to me Good Morning, Thank for you the list, could you please make the following adjustments? DA25 9358.01 $(361.98) Please move $5,000.00 from unallocated to PM Time DA26 9534.00 $(298.97) Please move $5,000.00 from unallocated to PM Time MM24 9226.00 $(290.03) Please move $5,000.00 from unallocated to PM Time. MM24 9392.00 $(264.99) Please move $3,000 from unallocated to PM Time MM25 9451.00 $(130.91) Please move $2,000.00 from unallocated to PM Time MM26 9491.00 $(646.75) Please move $5,000.00 from unallocated to PM Time MM26 9512.00 $(560.94) Please move $5,000 from unallocated to PM Time X674 9464.00 $(96.94) I'll have Brent add additional $100 to this project. Thank you, Oliver Shimp

## #9491.00 Misc
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  |  | Major Program 4B01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: C21
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526092918 | 2026-04-02 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2586 | 200 | 200
200
200
200
200
200
200
200
200
200
200
200
|  |  |  | Totals: |  | 200

## #9491.00 KCL Engineering
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM26-9260 |  |  | 949100-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526296902 | 2025-10-23 | PO Procore | 17675 | 17675 |  |  | 17675 |  | `
PRC 3352629PA6902 | 2025-12-29 | Inv. 13053 |  | 17675 | 4775 | 4775 | 12900
PRC 3352629PB6902 | 2026-03-23 | Inv. 13260 |  | 17675 | 5900 | 10675 | 7000
PRC 3352629PC6902 | 2026-06-29 | Inv. 13910 |  | 17675 | 5200 | 15875 | 1800 | FY26
PO 33527296902 | 2026-07-22 | Roll to FY27 | 0 | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  |  |  | 17675 |  | 15875 | 1800
|  | Totals: | 17675 |  | 15875 |  | 1800
|  | Design Development Docs | 4775 |  | 4775 |  | 0
|  | Construction Docs | 5900 |  | 5900 |  | 0
|  | Bidding/Negotiation | 1600 |  | 1600 |  | 0
|  | Construction Phase | 5400 |  | 3600 |  | 1800
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 17675 |  | 15875 |  | 1800

## #9491.00 Modern Piping Service
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
Modern Piping Service |  |  | Vendor: 00002108094
Acct. Codes-0017-335-MM26-9255 |  |  | RFB949100-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526057908 | 2026-02-26 | PO Procore | 203524 | 203524 |  |  | 203524
PRC 3352605PA7908 | 2026-07-27 | Inv. 29732 |  | 203524 | 3948.37 | 3948.37 | 199575.63 | 122.11 | FY26
PO 33527057908 | 2026-07-30 | Roll to FY27 | 0 | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  |  |  | 203524 |  | 3948.37 | 199575.63
|  | Totals: | 203524 |  | 3948.37 |  | 199575.63

## #9491.00 DCI Group (2)
DOC 7 JD RTU #2 Replacement
Project # 9491.00
Program code 949100 |  |  | Major Program 4B01
DCI Group (2) |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526173917 | 2026-06-22 | PO Procore | 22401.43 | 22401.43 |  |  | 22401.43
PRC 3352617PA3917 | 2026-07-09 | Inv. 9491.00-01 |  | 22401.43 | 929.05 | 929.05 | 21472.38 | FY26
PO 33527173917 | 2026-07-22 | Roll to FY27 | 0 | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  |  |  | 22401.43 |  | 929.05 | 21472.38
|  | Totals: | 22401.43 |  | 929.05 |  | 21472.38
|  | CM Services | 20901.43 |  | 929.05 |  | 19972.38
|  | Reimbursables | 1500 |  |  |  | 1500
|  | Total: | 22401.43 |  | 929.05 |  | 21472.38

## RECAP #9494.00
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26 |  |  | Close Date: | 2025-10-10
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per PM 10/10/25

## #9494.00 Vendor A
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Jennie E. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9494.00 PM TIME
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734J
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9494.00 Misc
IDOE ISD Giangreco Hall Gutter, Dentil and Roof Repairs
Project # 9494.00
Program code 949400 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9495.00
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Oliver S. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closing Per Geoff Wheelock Email 10/03/25
Note on B17: Huggins, Joni [DAS]: Re: MM26 Projects Set Up $Joni Wheelock, Geoff Oct 3, 2025, 12:22 PM (3 days ago) to me Good afternoon, I apologize for having to ask to make this change. Can you please make the following changes: Increase budget for 9474.00 to be $1,500,000 Close 9495 - This project number can be reused for a different project we will be looking to set up in Q3. If you would like to know which project so you don't have to close the job please let me know. The reason for this change is because 9474 is the design portion of 9495 and it makes more sense to continue utilizing the remaining excess of MM25 for the continuation of that project, freeing up MM26 funds for true FY26 project setups. If you have any questions please feel free to reach out. Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9495.00 Vendor A
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Oliver S. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9495.00 PM TIME
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734K
Project Manager - Oliver S. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 0 | 274.14 | 274.14 | -274.14
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 0 | 1410.3 | 1684.44 | -1684.44
CDE 33526281901 | 2025-10-07 | 2507 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 0 | -274.14 | 1410.3 | -1410.3
CDE 33526281901 | 2025-10-07 | 9500 | Moving cost from MM26 9495.00 to MM25 9474.00 |  | 0 | -1410.3 | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
[5 empty] | 0 |  | 0 | -2.2737e-13
|  |  | Totals: | 0 |  | 0 |  | 0

## #9495.00 Misc
HHS IMHI Boiler #3 Replacement
Project # 9495.00
Program code 949500 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Oliver S. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9496.00
DOC NCCF Replace Windows in Education Building
Project # 9496.00
| Program code 949600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 370000
C | McGough Construction |  | 17972.33 | 17972.33 | 0
| PM TIME |  | 10000 | 5077.15 | 4922.85
| Misc. |  | 2168 | 2168 | 0
| CMB Architects |  | 37360 | 23034 | 14326
| McGough Construction(2) |  | 32155.59 | 0 | 32155.59
| Timekey Enterprise |  | 226518 | 0 | 226518
| Total Project Cost | 370000 | 326173.92 | 48251.48 | 277922.44 | 43826.08

## #9496.00 McGough Construction
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023915 | 2026-01-23 | PO Procore | 17978.83 | 17978.83 |  |  | 17978.83
PRC 3352602PA3915 | 2026-02-12 | Inv. 101537.004PC-01 |  | 17978.83 | 1050.85 | 1050.85 | 16927.98
PRC 3352602PB3915 | 2026-03-10 | Inv. 101537.004PC-02 |  | 17978.83 | 2475.96 | 3526.81 | 14452.02
PRC 3352602PC3915 | 2026-04-13 | Inv. 101537.004PC-03 |  | 17978.83 | 4984.45 | 8511.26 | 9467.57
PRC 3352602PD3915 | 2026-05-22 | Inv. 101537.004PC-04 |  | 17978.83 | 3975.23 | 12486.49 | 5492.34
PRC 3352602PE3915 | 2026-06-16 | Inv. 101537.004PC-05 |  | 17978.83 | 4131.71 | 16618.2 | 1360.63
PRC 3352602PF3915 | 2026-07-06 | Inv. 101537.004PC-06 Final | -6.5 | 17972.33 | 1354.13 | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  |  |  | 17972.33 |  | 17972.33 | 3.638e-12
|  | Totals: | 17972.33 |  | 17972.33 |  | 0 | FINAL
|  | CM Services | 17378.83 |  | 17378.83 |  | 0
|  | Reimbursables | 593.5 |  | 593.5 |  | 0
|  | Total: | 17972.33 |  | 17972.33 |  | 0

## #9496.00 PM TIME
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734L
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 44.07 | 44.07 | 9955.93
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 438.1 | 482.17 | 9517.83
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | 6.95 | 489.12 | 9510.88
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 44.3 | 533.42 | 9466.58
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 10000 | 34.96 | 568.38 | 9431.62
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 10000 | 437.4 | 1005.78 | 8994.22
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10000 | 116.64 | 1122.42 | 8877.58
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10000 | 1343.9 | 2466.32 | 7533.68
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10000 | 78.24 | 2544.56 | 7455.44
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10000 | 631.4 | 3175.96 | 6824.04
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 10000 | 96.6 | 3272.56 | 6727.44
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10000 | 1034.3 | 4306.86 | 5693.14
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10000 | 15.79 | 4322.65 | 5677.35
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 218.8 | 4541.45 | 5458.55
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 10000 | 37.38 | 4578.83 | 5421.17
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 10000 | 483.3 | 5062.13 | 4937.87
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 10000 | 15.02 | 5077.15 | 4922.85
|  |  | Totals: | 10000 |  | 5077.15 |  | 4922.85
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Nov 2, 2025, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9496.00 Misc
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 177
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526146910 | 2026-05-26 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2710054 | 1968 | 1968
PRC 33526166911 | 2026-06-15 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2877 | 200 | 2168
2168
2168
2168
2168
2168
2168
2168
2168
2168
2168
|  |  |  | Totals: |  | 2168

## #9496.00 CMB Architects
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
CMB Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM26-9260 |  |  | RFP949600-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526062916 | 2026-03-03 | PO Procore | 37360 | 37360 |  |  | 37360
PRC 3352606PA2916 | 2026-03-20 | Inv. 67012 |  | 37360 | 1500 | 1500 | 35860
PRC 3352606PB2916 | 2026-04-16 | Inv. 67135 |  | 37360 | 5345 | 6845 | 30515
PRC 3352606PC2916 | 2026-05-20 | Inv. 67285 |  | 37360 | 8295 | 15140 | 22220
PRC 3352606PD2916 | 2026-06-19 | Inv. 67486 |  | 37360 | 7140 | 22280 | 15080
PRC 3352606PE2916 | 2026-07-06 | Inv. 67577 |  | 37360 | 754 | 23034 | 14326 | FY26
PO 33527062916 | 2026-07-22 | Roll to FY27 | 0 | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  |  |  | 37360 |  | 23034 | 14326
|  | Totals: | 37360 |  | 23034 |  | 14326
|  | Design Development | 4080 |  | 4080 |  | 0
|  | Construction Docs | 11060 |  | 11060 |  | 0
|  | Bidding/Negotiation | 7140 |  | 7140 |  | 0
|  | Construction Phase | 15080 |  | 754 |  | 14326
|  | Total: | 37360 |  | 23034 |  | 14326

## #9496.00 McGough Constructi (2)
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
McGough Construction(2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176923 | 2026-06-25 | PO Procore | 32155.59 | 32155.59 |  |  | 32155.59 | FY26
PO 33527176923 | 2026-07-22 | Roll to FY27 | 0 | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  |  |  | 32155.59 |  | 0 | 32155.59
|  | Totals: | 32155.59 |  | 0 |  | 32155.59
|  | CM Services | 29755.69 |  |  |  | 29755.69
|  | Reimbursables | 2400 |  |  |  | 2400
|  | Total: | 32155.69 |  | 0 |  | 32155.69

## #9496.00 Timekey Enterprise
DOC NCCF Replace Windows in Education Building
Project # 9496.00
Program code 949600 |  |  | Major Program 4E01
Timekey Enterprise |  |  | Vendor: 00003220172
Acct. Codes-0017-335-MM26-9255 |  |  | RFB949600-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526181916 | 2026-06-30 | PO Procore | 226518 | 226518 |  |  | 226518 | FY26
PO 33527181916 | 2026-07-22 | Roll to FY27 | 0 | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  |  |  | 226518 |  | 0 | 226518
|  | Totals: | 226518 |  | 0 |  | 226518

## RECAP #9497.00
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
| Program code 949700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - James T.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 495000
C | Story Construction |  | 25486.51 | 25486.51 | 0
| PM TIME |  | 14000 | 11529.21 | 2470.79
| Misc. |  | 3471.03 | 3471.03 | 0
| ECS Midwest, LLC |  | 20365 | 11815 | 8550
| Story Construction (2) |  | 26723.02 | 10747.8 | 15975.22
| Service Roofing |  | 137100.46 | 0 | 137100.46
| Advanced Environmental |  | 7970.52 | 0 | 7970.52
| Total Project Cost | 495000 | 235116.54 | 63049.55 | 172066.99 | 259883.46

## #9497.00 Story Construction
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526288901 | 2025-10-15 | PO Procore | 25616.73 | 25616.73 |  |  | 25616.73
PRC 3352628PA8901 | 2026-01-22 | Inv. 35119 |  | 25616.73 | 6302.63 | 6302.63 | 19314.1
PRC 3352628PB8901 | 2026-02-20 | Inv. 35153 |  | 25616.73 | 6208.65 | 12511.28 | 13105.45
PRC 3352628PC8901 | 2026-03-19 | Inv. 35196 |  | 25616.73 | 4112.67 | 16623.95 | 8992.78
PRC 3352628PD8901 | 2026-04-16 | Inv. 35229 |  | 25616.73 | 4388.93 | 21012.88 | 4603.85
PRC 3352628PE8901 | 2006-05-22 | Inv. 35260 FINAL | -130.22 | 25486.51 | 4473.63 | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  |  |  | 25486.51 |  | 25486.51 | -1.5632e-12
|  | Totals: | 25486.51 |  | 25486.51 |  | 0 | FINAL
|  | CM Services | 25248.51 |  | 25248.51 |  | 0
|  | Reimbursables | 238 |  | 238 |  | 0
|  | Total: | 25486.51 |  | 25486.51 |  | 0

## #9497.00 PM TIME
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734M
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 14000 | 14000 |  |  | 14000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 14000 | 78.78 | 78.78 | 13921.22
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 14000 | 779.9 | 858.68 | 13141.32
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 14000 | 81.07 | 939.75 | 13060.25
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 14000 | 516.2 | 1455.95 | 12544.05
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 14000 | 191.99 | 1647.94 | 12352.06
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 14000 | 2175.5 | 3823.44 | 10176.56
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 14000 | 71.12 | 3894.56 | 10105.44
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 14000 | 885.2 | 4779.76 | 9220.24
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 14000 | 54.18 | 4833.94 | 9166.06
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 14000 | 623.3 | 5457.24 | 8542.76
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 14000 | 142.81 | 5600.05 | 8399.95
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 14000 | 1164.4 | 6764.45 | 7235.55
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 14000 | 184.6 | 6949.05 | 7050.95
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 14000 | 1922.8 | 8871.85 | 5128.15
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 14000 | 63.47 | 8935.32 | 5064.68
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 14000 | 771.3 | 9706.62 | 4293.38
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 14000 | 141.37 | 9847.99 | 4152.01
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 14000 | 1625.2 | 11473.19 | 2526.81
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 14000 | 56.02 | 11529.21 | 2470.79
[5 empty] | 14000 |  | 11529.21 | 2470.79
[5 empty] | 14000 |  | 11529.21 | 2470.79
|  |  | Totals: | 14000 |  | 11529.21 |  | 2470.79
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Nov 10, 2025, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget. MM26 9497.00 (858.68) Please increase the PM time budget by $10,000.00 to $10,000.00 from the unallocated budget.

## #9497.00 Misc
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 556
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526014910 | 2026-01-14 | 9500 | CNST | Advanced Environmental V#(00002125877) | Inv. 12418 | 1600 | 1600
PRC 33526022905 | 2026-01-22 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2444 | 317.35 | 1917.35
PRC 33526079901 | 2026-03-20 | 9500 | CNST | Advanced Environmental V#(00002125877) | Inv. 12622 | 1300 | 3217.35
PRC 33526126914 | 2026-05-06 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2781 | 253.68 | 3471.03
3471.03
3471.03
3471.03
3471.03
3471.03
3471.03
3471.03
3471.03
|  |  |  | Totals: |  | 3471.03

## #9497.00 ECS Midwest
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
ECS Midwest |  |  | Vendor: 00003234598
Acct. Codes-0017-335-MM26-9260 |  |  | 949700-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526020905 | 2026-01-20 | PO Procore | 20365 | 20365 |  |  | 20365
PRC 3352602PA0905 | 2026-03-04 | Inv. 2133019 |  | 20365 | 4100 | 4100 | 16265
PRC 3352602PB0905 | 2026-03-19 | Inv. 2141568 |  | 20365 | 3200 | 7300 | 13065
PRC 3352602PC0905 | 2026-04-16 | Inv. 2146813 |  | 20365 | 1865 | 9165 | 11200
PRC 3352602PD0905 | 2026-05-20 | Inv. 2156238 |  | 20365 | 2100 | 11265 | 9100
PRC 3352602PE0905 | 2026-07-13 | Inv. 2175269 |  | 20365 | 550 | 11815 | 8550 | FY26
PO 33527020905 | 2026-07-22 | Roll to FY27 | 0 | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  |  |  | 20365 |  | 11815 | 8550
|  | Totals: | 20365 |  | 11815 |  | 8550
|  | CM Services | 9165 |  | 9165 |  | 0
|  | Bid/Negotiation Phase | 2100 |  | 2100 |  | 0
|  | Construction Phase | 9100 |  | 550 |  | 8550
|  | Total: | 20365 |  | 11815 |  | 8550

## #9497.00 Story Construction (2)
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526120910 | 2026-04-30 | PO Procore | 26723.02 | 26723.02 |  |  | 26723.02
PRC 3352612PA0910 | 2026-06-17 | Inv. 35297 |  | 26723.02 | 5258.03 | 5258.03 | 21464.99
PRC 3352612PB0910 | 2026-07-15 | Inv. 35340 |  | 26723.02 | 5489.77 | 10747.8 | 15975.22 | FY26
PO 33527120910 | 2026-07-22 | Roll to FY27 | 0 | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  |  |  | 26723.02 |  | 10747.8 | 15975.22
|  | Totals: | 26723.02 |  | 10747.8 |  | 15975.22
|  | CM Services | 26366.02 |  | 10747.8 |  | 15618.22
|  | Reimbursables | 357 |  |  |  | 357
|  | Total: | 26723.02 |  | 10747.8 |  | 15975.22

## #9497.00 Service Roofing
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Service Roofing |  |  | Vendor: 00003226751
Acct. Codes-0017-335-MM26-9255 |  |  | RFB949700-01
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526140915 | 2026-05-20 | PO Procore | 137100.46 | 137100.46 |  |  | 137100.46 | FY26
PO 33527140915 | 2026-07-22 | Roll to FY27 | 0 | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  |  |  | 137100.46 |  | 0 | 137100.46
|  | Totals: | 137100.46 |  | 0 |  | 137100.46

## #9497.00 Advanced Environmental
HHS IMHI Warehouse Roof Replacement
Project # 9497.00
Program code 949700 |  |  | Major Program 4E02
Advanced Environmental |  |  | Vendor: 00002125877
Acct. Codes-0017-335-MM26-9255 |  |  | MA21063C
Project Manager - James T. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176910 | 2026-06-25 | PO Procore | 7970.52 | 7970.52 |  |  | 7970.52 | FY26
PO 33527176910 | 2026-07-22 | Roll to FY27 | 0 | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  |  |  | 7970.52 |  | 0 | 7970.52
|  | Totals: | 7970.52 |  | 0 |  | 7970.52
|  | Asbestos Abatement Services Line 1 | 6388.2 |  |  |  | 6388.2
|  | Abatement & Remediation Line 7 | 700 |  |  |  | 700
|  | Asbestos Abatement Services Line 11 | 400 |  |  |  | 400
|  | Travel Expenses Line 12 | 482.32 |  |  |  | 482.32
|  | Total: | 7970.52 |  | 0 |  | 7970.52

## RECAP #9498.00
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-MM26 |  |  | Closing Date:
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 140000
DCI Group |  | 37093.23 | 31988.68 | 5104.55
PM TIME |  | 9000 | 8893.85 | 106.15
Misc. |  | 342.5 | 342.5 | 0
OPN Architects |  | 27466 | 16437.91 | 11028.09
Total Project Cost | 140000 | 73901.73 | 57662.94 | 16238.79 | 66098.27

## #9498.00 DCI Group
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP181335228-DCI11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526301907 | 2025-10-28 | PO Procore | 10713.54 | 10713.54 |  |  | 10713.54
PRC 3352630PA1907 | 2025-11-21 | Inv. 9498.00 PC 01 |  | 10713.54 | 523.41 | 523.41 | 10190.13
PRC 3352630PB1907 | 2025-12-29 | Inv. 9498.00 PC 02 |  | 10713.54 | 1483 | 2006.41 | 8707.13
PRC 3352630PC1907 | 2026-01-23 | Inv. 9498.00 PC 03 |  | 10713.54 | 436.18 | 2442.59 | 8270.95
PO 33526301907 | 2026-01-28 | CO #1 | 10000 | 20713.54 |  | 2442.59 | 18270.95
PRC 3352630PD1907 | 2026-02-16 | Inv. 9498.00 PC 04 |  | 20713.54 | 1226.03 | 3668.62 | 17044.92
PRC 3352630PE1907 | 2026-03-24 | Inv. 9498.00 PC 06 |  | 20713.54 | 4667.47 | 8336.09 | 12377.45
PRC 3352630PF1907 | 2026-04-23 | Inv. 9498.00 PC 06A |  | 20713.54 | 8768.96 | 17105.05 | 3608.49
PO 33526301907 | 2026-04-27 | CO #2 | 8560 | 29273.54 |  | 17105.05 | 12168.49
PRC 3352630PG1907 | 2026-05-12 | Inv. 9498.00 PC #07 |  | 29273.54 | 10584.44 | 27689.49 | 1584.05
PO 33526301907 | 2026-06-08 | CO #3 | 7819.69 | 37093.23 |  | 27689.49 | 9403.74
PRC 3352630PH1907 | 2026-06-09 | Inv. 9498.00 PC #08 |  | 37093.23 | 1046.82 | 28736.31 | 8356.92
PRC 3352630PI1907 | 2026-07-13 | Inv. 9498.00 PC 09 |  | 37093.23 | 3252.37 | 31988.68 | 5104.55 | FY26
PO 33527301907 | 2026-07-22 | Roll to FY27 | 0 | 37093.23 |  | 31988.68 | 5104.55
|  |  |  | 37093.23 |  | 31988.68 | 5104.55
|  |  |  | 37093.23 |  | 31988.68 | 5104.55
|  | Totals: | 37093.23 |  | 31988.68 |  | 5104.55

## #9498.00 PM TIME
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734N
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 9000 | 9000 |  |  | 9000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 9000 | 38.8 | 38.8 | 8961.2
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 9000 | 199.7 | 238.5 | 8761.5
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 9000 | 63.69 | 302.19 | 8697.81
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 9000 | 632.8 | 934.99 | 8065.01
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 9000 | 149.15 | 1084.14 | 7915.86
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 9000 | 948.7 | 2032.84 | 6967.16
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 9000 | 83.48 | 2116.32 | 6883.68
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 9000 | 949.7 | 3066.02 | 5933.98
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 9000 | 66.16 | 3132.18 | 5867.82
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 9000 | 822.9 | 3955.08 | 5044.92
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 9000 | 62.46 | 4017.54 | 4982.46
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 9000 | 720.6 | 4738.14 | 4261.86
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 9000 | 92.7 | 4830.84 | 4169.16
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 9000 | 754.4 | 5585.24 | 3414.76
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 9000 | 99.91 | 5685.15 | 3314.85
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 9000 | 1042.9 | 6728.05 | 2271.95
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 9000 | 60.61 | 6788.66 | 2211.34
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 9000 | 747.8 | 7536.46 | 1463.54
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 9000 | 105.19 | 7641.65 | 1358.35
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 9000 | 1210 | 8851.65 | 148.35
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 9000 | 42.2 | 8893.85 | 106.15
[5 empty] | 9000 |  | 8893.85 | 106.15
[5 empty] | 9000 |  | 8893.85 | 106.15
|  |  | Totals: | 9000 |  | 8893.85 |  | 106.15
Note on E9: Huggins, Joni [DAS]: 9498.00 - DAS TH Parking Lot Retaining Wall Repairs - MM26 Budget $Joni Trower, James 9:19 AM (3 hours ago) to me Finance - Please add $35,000 in MM26 funds to project 9498.00. Of that $35,000, please increase PM Time by $2,000. Thanks, James Trower

## #9498.00 Misc
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 003
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33527211910 | 2026-07-30 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV060036 | 342.5 | 342.5
342.5
342.5
342.5
342.5
342.5
342.5
342.5
342.5
342.5
342.5
342.5
|  |  |  | Totals: |  | 342.5

## #9498.00 OPN Architects
DAS TH Parking Lot Retaining Wall Repairs
Project # 9498.00
Program code 949800 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM26-9260 |  |  | RFP949800-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526337908 | 2025-12-03 | PO Procore | 27466 | 27466 |  |  | 27466
PRC 3352633PA7908 | 2026-02-20 | Inv. 24853006-1 |  | 27466 | 1084.71 | 1084.71 | 26381.29
PRC 3352633PB7908 | 2026-04-03 | Inv. 24853006-2 |  | 27466 | 9176.4 | 10261.11 | 17204.89
PRC 3352633PC7908 | 2026-06-08 | Inv. 24853006-3 |  | 27466 | 3071.75 | 13332.86 | 14133.14
PRC 3352633PD7908 | 2026-07-07 | Inv. 24853006-4 |  | 27466 | 3105.05 | 16437.91 | 11028.09 | FY26
PO 33527337908 | 2026-07-22 | Roll to FY27 | 0 | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  |  |  | 27466 |  | 16437.91 | 11028.09
|  | Totals: | 27466 |  | 16437.91 |  | 11028.09

## RECAP #9499.00
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
| Program code 949900 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 440965
C | Boyd Jones |  | 16566.1 | 16566.1 | 0
| PM TIME |  | 15000 | 13721.18 | 1278.82
| Misc. |  | 6429.93 | 6429.93 | 0
C | Larson Engineering |  | 33530 | 33530 | 0
| Boyd Jones (2) |  | 29267.48 | 27413.18 | 1854.3
| Core Construction Services |  | 310000 | 288437.74 | 21562.26
| Total Project Cost | 440965 | 410793.51 | 386098.13 | 24695.38 | 30171.49

## #9499.00 Boyd Jones
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526342905 | 2025-12-08 | PO Procore | 17986.57 | 17986.57 |  |  | 17986.57
PRC 3352634PA2905 | 2025-01-06 | Inv. 9499.00-01 |  | 17986.57 | 3657.72 | 3657.72 | 14328.85
PRC 3352634PB2905 | 2026-02-16 | Inv. 9499.00-02 |  | 17986.57 | 1902.69 | 5560.41 | 12426.16
PRC 3352634PC2905 | 2026-03-19 | Inv. 9499.00-03 |  | 17986.57 | 5535.28 | 11095.69 | 6890.88
PRC 3352634PD2905 | 2026-04-16 | Inv. 9499.00-04 |  | 17986.57 | 5470.41 | 16566.1 | 1420.47
PO 33526342905 | 2026-07-28 | Closing PO Per PM | -1420.47 | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  |  |  | 16566.1 |  | 16566.1 | 0
|  | Totals: | 16566.1 |  | 16566.1 |  | 0
|  | CM Services | 16563.1 |  | 16563.1 |  | 0
|  | Reimbursables | 3 |  | 3 |  | 0
|  | Total: | 16566.1 |  | 16566.1 |  | 0

## #9499.00 PM TIME
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734O
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 128.14 | 128.14 | 14871.86
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 1311.2 | 1439.34 | 13560.66
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 15000 | 145.53 | 1584.87 | 13415.13
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 15000 | 904.2 | 2489.07 | 12510.93
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 15000 | 130.35 | 2619.42 | 12380.58
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 15000 | 1478.4 | 4097.82 | 10902.18
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 15000 | 74.43 | 4172.25 | 10827.75
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 15000 | 924.6 | 5096.85 | 9903.15
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 15000 | 77.35 | 5174.2 | 9825.8
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 15000 | 891.2 | 6065.4 | 8934.6
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 15000 | 131.67 | 6197.07 | 8802.93
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 15000 | 1074.2 | 7271.27 | 7728.73
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 15000 | 196.51 | 7467.78 | 7532.22
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 15000 | 2048.1 | 9515.88 | 5484.12
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 15000 | 129.5 | 9645.38 | 5354.62
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 15000 | 1590.1 | 11235.48 | 3764.52
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 15000 | 192.31 | 11427.79 | 3572.21
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 15000 | 2216.5 | 13644.29 | 1355.71
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 15000 | 76.89 | 13721.18 | 1278.82
|  |  | Totals: | 15000 |  | 13721.18 |  | 1278.82

## #9499.00 Misc
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 225
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
GAX 33526120912 | 2026-04-30 | 9500 | CNST | GPRS V#(00003035582) | Inv. 959633 | 1150 | 1150
GAX 33526169915 | 2026-06-18 | 9500 | CNST | GPRS V#(00003035582) | Inv. 1001437 | 700 | 1850
PRC 33526181915 | 2026-06-30 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2931 | 200 | 2050
GAX 33526194903 | 2026-07-13 | 9500 | CNST | A Plus Lawn & Landscape V#(00003096472) | Inv. 2262561 | 2602.83 | 4652.83
PRC 33527204900 | 2026-07-23 | 9500 | CNST | Baker Group V#(00002109043) | Inv. 328431 | 1777.1 | 6429.93
6429.93
6429.93
6429.93
6429.93
6429.93
6429.93
6429.93
|  |  |  | Totals: |  | 6429.93

## #9499.00 Larson Engineering
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Larson Engineering |  |  | Vendor: VS000002162
Acct. Codes-0017-335-MM26-9260 |  |  | 949900-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023912 | 2026-01-23 | PO Procore | 33530 | 33530 |  |  | 33530
PRC 3352602PA3912 | 2026-02-20 | Inv. 9499.00-01 |  | 33530 | 14300 | 14300 | 19230
PRC 3352602PB3912 | 2026-03-26 | Inv. 9499.00-02 |  | 33530 | 10420 | 24720 | 8810
PRC 3352602PC3912 | 2026-04-13 | Inv. 9499.00-03 |  | 33530 | 2350 | 27070 | 6460
PRC 3352602PD3912 | 2026-05-26 | Inv. 9499.00-04 |  | 33530 | 646 | 27716 | 5814
PRC 3352602PE3912 | 2026-07-13 | Inv. 9499.00-05 - Final |  | 33530 | 5814 | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  |  |  | 33530 |  | 33530 | 0
|  | Totals: | 33530 |  | 33530 |  | 0 | FINAL
|  | Topographic Survey | 2000 |  | 2000 |  | 0
|  | Geotechnical Investigation | 3200 |  | 3200 |  | 0
|  | Design Development | 9100 |  | 9100 |  | 0
|  | Construction Documents | 10420 |  | 10420 |  | 0
|  | Bidding/Negotiation | 2350 |  | 2350 |  | 0
|  | Construction Phase | 6460 |  | 6460 |  | 0
|  | Total: | 33530 |  | 33530 |  | 0

## #9499.00 Boyd Jones (2)
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Boyd Jones (2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526089910 | 2026-03-30 | PO Procore | 29267.48 | 29267.48 |  |  | 29267.48
PRC 3352608PA9910 | 2026-05-19 | Inv. 9499.00-001 |  | 29267.48 | 6557.86 | 6557.86 | 22709.62
PRC 3352608PB9910 | 2026-07-07 | Inv. 9499.00-002 |  | 29267.48 | 15145.31 | 21703.17 | 7564.31
PRC 3352608PC9910 | 2026-07-13 | Inv. 9499.00-003 |  | 29267.48 | 5710.01 | 27413.18 | 1854.3 | FY26
PO 33527089910 | 2026-07-22 | Roll to FY27 | 0 | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  |  |  | 29267.48 |  | 27413.18 | 1854.3
|  | Totals: | 29267.48 |  | 27413.18 |  | 1854.3
|  | CM Services | 29141.48 |  | 27326.18 |  | 1815.3
|  | Reimbursables | 126 |  | 87 |  | 39
|  | Total: | 29267.48 |  | 27413.18 |  | 1854.3
Vendor used Inv. 9499.00-0X in previous tabe, pleaes use Inv. 9499.00-001 in this tab.

## #9499.00 Core Construction
IPBS 6535 Corporate Drive Parking Lot Replacement
Project # 9499.00
Program code 949900 |  |  | Major Program 4E19
Core Construction |  |  | Vendor: 00003201207
Acct. Codes-0017-335-MM26-9255 |  |  | 949900-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526098913 | 2026-04-08 | PO Procore | 310000 | 310000 |  |  | 310000
PCR 3352609PA8913 | 2026-06-10 | Inv. 9499.00-001 |  | 310000 | 30301.83 | 30301.83 | 279698.17 | 937.17
PCR 3352609PB8913 | 2026-06-25 | Inv. 9499.00-002 |  | 310000 | 248681.4 | 278983.23 | 31016.77 | 8628.35
PCR 3352609PC8913 | 2026-07-14 | Inv. 9499.00-003 |  | 310000 | 9454.51 | 288437.74 | 21562.26 | 8920.76 | FY26
PO 33527098913 | 2026-07-28 | Roll to FY27 | 0 | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  |  |  | 310000 |  | 288437.74 | 21562.26
|  | Totals: | 310000 |  | 288437.74 |  | 21562.26

## RECAP #9500.00
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
| Program code 950000 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 550000
C | McGough Construction |  | 12611.76 | 12611.76 | 0
| PM TIME |  | 15000 | 12428.95 | 2571.05
| Misc. |  | 2362.65 | 2362.65 | 0
| KCL Engineering |  | 36975 | 29942 | 7033
C | Terracon Consultants |  | 5968 | 5968 | 0
| McGough Construction(2) |  | 64134.14 | 1556.15 | 62577.99
| Acterra Group Inc |  | 368885 | 0 | 368885
| Total Project Cost | 550000 | 505936.55 | 64869.51 | 441067.04 | 44063.45

## #9500.00 McGough Construction
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526329902 | 2025-11-25 | PO Procore | 15864.97 | 15864.97 |  |  | 15864.97
PRC 3352632PA9902 | 2026-02-19 | Inv. 101537.001-PC01 |  | 15864.97 | 3389.6 | 3389.6 | 12475.37
PRC 3352632PB9902 | 2026-03-23 | Inv. 101537.001-PC02 |  | 15864.97 | 1648.24 | 5037.84 | 10827.13
PRC 3352632PC9902 | 2026-04-24 | Inv. 101537.001-PC03 |  | 15864.97 | 2182.7 | 7220.54 | 8644.43
PRC 3352632PD9902 | 2026-05-19 | Inv. 101537.001-PC04 |  | 15864.97 | 1132.44 | 8352.98 | 7511.99
PRC 3352632PE9902 | 2026-06-09 | Inv. 101537.001-PC05 |  | 15864.97 | 3245.06 | 11598.04 | 4266.93
PRC 3352632PF9902 | 2026-07-13 | Inv. 101537.001-PC06 FINAL | -3253.21 | 12611.76 | 1013.72 | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  |  |  | 12611.76 |  | 12611.76 | 0
|  | Totals: | 12611.76 |  | 12611.76 |  | 0 | FINAL
|  | CM Services | 12411.76 |  | 12411.76 |  | 0
|  | Reimbursables | 200 |  | 200 |  | 0
|  | Total: | 12611.76 |  | 12611.76 |  | 0

## #9500.00 PM TIME
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734P
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 15000 | 44.41 | 44.41 | 14955.59
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 15000 | 229.2 | 273.61 | 14726.39
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 228.95 | 502.56 | 14497.44
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 829.8 | 1332.36 | 13667.64
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 15000 | -113.17 | 1219.19 | 13780.81
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 15000 | 81.3 | 1300.49 | 13699.51
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 15000 | 142.26 | 1442.75 | 13557.25
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 15000 | 1617.8 | 3060.55 | 11939.45
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 15000 | 120.86 | 3181.41 | 11818.59
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 15000 | 1504.7 | 4686.11 | 10313.89
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 15000 | 162.54 | 4848.65 | 10151.35
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 15000 | 1873.7 | 6722.35 | 8277.65
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 15000 | 168.54 | 6890.89 | 8109.11
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 15000 | 1380.4 | 8271.29 | 6728.71
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 15000 | 166.51 | 8437.8 | 6562.2
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 15000 | 1732.9 | 10170.7 | 4829.3
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 15000 | 101.68 | 10272.38 | 4727.62
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 15000 | 1246.3 | 11518.68 | 3481.32
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 15000 | 70.68 | 11589.36 | 3410.64
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 15000 | 811.2 | 12400.56 | 2599.44
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 15000 | 28.39 | 12428.95 | 2571.05
|  |  | Totals: | 15000 |  | 12428.95 |  | 2571.05
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adams, Brandon Please increase the following PM Time: Unit MM23 Project 9465.00 (854.26) Increase by $1,500 Unit MM23 Project 9533.00 (1,179.31) Increase by $2,500 Unit MM24 Project 9541.00 (1,954.84) Increase by $8,000 Unit MM26 Project 9500.00 (170.70) Increase by $5,000 Regards, Brandon Adams

## #9500.00 Misc
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526174913 | 2026-06-23 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2902 | 223.9 | 223.9
GAX 33526194905 | 2026-07-13 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. 06267019 | 2138.75 | 2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
2362.65
|  |  |  | Totals: |  | 2362.65

## #9500.00 KCL Engineering
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
KCL Engineering |  |  | Vendor: 00002103747
Acct. Codes-0017-335-MM26-9260 |  |  | RFP950000-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526034919 | 2026-02-04 | PO Procore | 35000 | 35000 |  |  | 35000
PRC 3352603PA4919 | 2026-03-23 | Inv. 13599 |  | 35000 | 12674 | 12674 | 22326
PO 33526034919 | 2026-04-14 | CO #1 | 1975 | 36975 |  | 12674 | 24301
PRC 3352603PB4919 | 2026-05-26 | Inv. 14051 |  | 36975 | 14988 | 27662 | 9313
PRC 3352603PC4919 | 2026-06-09 | Inv. 14164 |  | 36975 | 2280 | 29942 | 7033 | FY26
PO 33527034919 | 2026-07-22 | Roll to FY27 | 0 | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  |  |  | 36975 |  | 29942 | 7033
|  | Totals: | 36975 |  | 29942 |  | 7033
|  | Design Development Docs | 12674 |  | 12674 |  | 0
|  | Construction Docs | 13013 |  | 13013 |  | 0
|  | Bidding Assistance | 2280 |  | 2280 |  | 0
|  | Construction Phase | 7033 |  |  |  | 7033
|  | CO #1 | 1975 |  | 1975 |  | 0
|  | Total: | 36975 |  | 29942 |  | 7033

## #9500.00 Terracon Consultants
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM26-9260 |  |  | MA25049
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526049912 | 2026-02-18 | PO Procore | 7210 | 7210 |  |  | 7210
PO 33526049912 | 2026-05-20 | CO #1 | -1242 | 5968 |  | 0 | 5968
PRC 3352604PA9912 | 2026-05-29 | Inv. TQ60135 |  | 5968 | 5968 | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  |  |  | 5968 |  | 5968 | 0
|  | Totals: | 5968 |  | 5968 |  | 0 | FINAL
|  | Geotechnical Line3 | 420 |  | 420 |  | 0
|  | Soil Moisture Content Line2 | 210 |  | 210 |  | 0
|  | Soil Atterberg limits Line 2 | 260 |  | 260 |  | 0
|  | Labor Project Mngr Line 5 | 3380 |  | 3380 |  | 0
|  | Testing Tech Line 6 | 1750 |  | 1750 |  | 0
|  | Travel Line 7 300miles@.50 | 150 |  | 150 |  | 0
|  | Specialized Vehicles Line 8 | 1040 |  | 1040 |  | 0
|  | CO #1 | -1242 |  | -1242 |  | 0
|  | Total: | 5968 |  | 5968 |  | 0

## #9500.00 McGough Constructi (2)
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
McGough Construction(2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526177912 | 2026-06-26 | PO Procore | 64134.14 | 64134.14 |  |  | 64134.14
PRC 3352617PA7912 | 2026-07-15 | Inv. 101537.001-CA01 |  | 64134.14 | 1556.15 | 1556.15 | 62577.99 | FY26
PO 33527177912 | 2026-07-22 | Roll to FY27 | 0 | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  |  |  | 64134.14 |  | 1556.15 | 62577.99
|  | Totals: | 64134.14 |  | 1556.15 |  | 62577.99
|  | CM Services | 61194.14 |  | 1416.15 |  | 59777.99
|  | Reimbursables | 2940 |  | 140 |  | 2800
|  | Total: | 64134.14 |  | 1556.15 |  | 62577.99

## #9500.00 Acterra Group
DOC MPCF Spill Containment for Diesel Tank
Project # 9500.00
Program code 950000 |  |  | Major Program 4E01
Acterra Group Inc |  |  | Vendor: 00003207238
Acct. Codes-0017-335-MM26-9255 |  |  | RFB950000-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527204903 | 2026-07-23 | PO Procore | 368885 | 368885 |  |  | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  |  |  | 368885 |  | 0 | 368885
|  | Totals: | 368885 |  | 0 |  | 368885

## RECAP #9501.00
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
| Program code 950100 |  |  | Major Program 4F03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 275000
C | McGough Construction |  | 14579.65 | 14579.65 | 0
| PM TIME |  | 10000 | 4911.59 | 5088.41
| Misc. |  | 1148.08 | 1148.08 | 0
| IMEG Corp |  | 34940 | 22857.26 | 12082.74
| McGough Construction (2) |  | 33340.08 | 0 | 33340.08
| Winger Contracting |  | 137481 | 0 | 137481
| Total Project Cost | 275000 | 231488.81 | 43496.58 | 187992.23 | 43511.19

## #9501.00 McGough Construction
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023914 | 2026-01-23 | PO Procore | 17978.83 | 17978.83 |  |  | 17978.83
PRC 3352602PA3914 | 2026-02-24 | Inv. 101537.005PC-01 |  | 17978.83 | 1050.85 | 1050.85 | 16927.98
PRC 3352602PB3914 | 2026-03-10 | Inv. 101537.005PC-02 |  | 17978.83 | 2475.96 | 3526.81 | 14452.02
PRC 3352602PC3914 | 2026-04-13 | Inv. 101537.005PC-03 |  | 17978.83 | 2641.12 | 6167.93 | 11810.9
PRC 3352602PD3914 | 2026-05-21 | Inv. 101537.005PC-04 |  | 17978.83 | 2978.43 | 9146.36 | 8832.47
PRC 3352602PE3914 | 2026-06-16 | Inv. 101537.005PC-05 |  | 17978.83 | 3061.89 | 12208.25 | 5770.58
PRC 3352602PF3914 | 2026-07-06 | Inv. 101537.005PC-06 Final | -3399.18 | 14579.65 | 2371.4 | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  |  |  | 14579.65 |  | 14579.65 | 5.457e-12
|  | Totals: | 14579.65 |  | 14579.65 |  | 0 | FINAL
|  | CM Services | 14400.15 |  | 14400.15 |  | 0
|  | Reimbursables | 179.5 |  | 179.5 |  | 0
|  | Total: | 14579.65 |  | 14579.65 |  | 0

## #9501.00 PM TIME
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  |  | Major Program 4F03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Q
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 10000 | 44.07 | 44.07 | 9955.93
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 10000 | 438.1 | 482.17 | 9517.83
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 10000 | 6.95 | 489.12 | 9510.88
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 10000 | 44.3 | 533.42 | 9466.58
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 10000 | 39.04 | 572.46 | 9427.54
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 10000 | 481.7 | 1054.16 | 8945.84
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10000 | 87.3 | 1141.46 | 8858.54
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10000 | 1008.2 | 2149.66 | 7850.34
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10000 | 109.25 | 2258.91 | 7741.09
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10000 | 884.5 | 3143.41 | 6856.59
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 10000 | 29.23 | 3172.64 | 6827.36
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10000 | 306.4 | 3479.04 | 6520.96
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10000 | 31.13 | 3510.17 | 6489.83
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 410.7 | 3920.87 | 6079.13
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 10000 | 70.23 | 3991.1 | 6008.9
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 10000 | 892.1 | 4883.2 | 5116.8
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 10000 | 28.39 | 4911.59 | 5088.41
|  |  | Totals: | 10000 |  | 4911.59 |  | 5088.41
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9501.00 Misc
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  |  | Major Program 4F03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 177
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526146909 | 2026-05-26 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2710053 | 903 | 903
PRC 33526169918 | 2026-06-18 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2879 | 245.08 | 1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
1148.08
|  |  |  | Totals: |  | 1148.08

## #9501.00 IMEG Corp
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
IMEG Corp |  |  | Vendor: 00003224175
Acct. Codes-0017-335-MM26-9260 |  |  | RFP950100-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526082902 | 2026-03-23 | PO Procore | 34940 | 34940 |  |  | 34940
PRC 3352608PA2902 | 2026-07-27 | Inv. 9501.00-01 |  | 34940 | 22857.26 | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  |  |  | 34940 |  | 22857.26 | 12082.74
|  | Totals: | 34940 |  | 22857.26 |  | 12082.74
|  | Design Documents | 8360 |  | 8360 |  | 0
|  | Construction Documents | 12705 |  | 12705 |  | 0
|  | Bidding Assistance | 1520 |  | 1520 |  | 0
|  | Construction Phase | 10855 |  |  |  | 10855
|  | Reimbursables | 1500 |  | 272.26 |  | 1227.74
|  | Total: | 34940 |  | 22857.26 |  | 12082.74

## #9501.00 McGough Constructi (2)
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
McGough Construction(2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176921 | 2026-06-25 | PO Procore | 33340.08 | 33340.08 |  |  | 33340.08 | FY26
PO 33527176921 | 2026-07-22 | Roll to FY27 | 0 | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  |  |  | 33340.08 |  | 0 | 33340.08
|  | Totals: | 33340.08 |  | 0 |  | 33340.08
|  | CM Services | 30340.08 |  |  |  | 30340.08
|  | Reimbursables | 3000 |  |  |  | 3000
|  | Total: | 33340.08 |  | 0 |  | 33340.08

## #9501.00 Winger Contracting
DOC NCCF Air Handler Replacement and Condenser Coils Unit A and B
Project # 9501.00
Program code 950100 |  |  | Major Program 4F03
Winger Contracting Co |  |  | Vendor: 00003116692
Acct. Codes-0017-335-MM26-9255 |  |  | RFB950100-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526180912 | 2026-06-29 | PO Procore | 137481 | 137481 |  |  | 137481 | FY26
PO 33527180912 | 2026-07-22 | Roll to FY27 | 0 | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  |  |  | 137481 |  | 0 | 137481
|  | Totals: | 137481 |  | 0 |  | 137481

## RECAP #9502.00
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
| Program code 950200 |  |  | Major Program 4F04
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 955000
C | McGough Construction |  | 13841.84 | 13841.84 | 0
| PM TIME |  | 20000 | 19571.52 | 428.48
| Misc. |  | 3778.29 | 3778.29 | 0
| Modus Engineering |  | 32000 | 28256 | 3744
| McGough Construction (2) |  | 96273.29 | 44818.4 | 51454.89
| Modern Piping Service |  | 700000 | 439846.5 | 260153.5
| Total Project Cost | 955000 | 865893.42 | 550112.55 | 315780.87 | 89106.58

## #9502.00 McGough Construction
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526279901 | 2025-10-06 | PO Procore | 15742.15 | 15742.15 |  |  | 15742.15
PRC 3352627PA9901 | 2025-11-06 | Inv. 101368.015-PC01 |  | 15742.15 | 1561.41 | 1561.41 | 14180.74
PRC 3352627PB9901 | 2025-12-10 | Inv. 101368.015-PC02 |  | 15742.15 | 2989.96 | 4551.37 | 11190.78
PRC 3352627PC9901 | 2026-01-12 | Inv. 101368.015-PC03 |  | 15742.15 | 2440.91 | 6992.28 | 8749.87
PRC 3352627PD9901 | 2026-02-16 | Inv. 101368.015-PC04 |  | 15742.15 | 3461.18 | 10453.46 | 5288.69
PRC 3352627PE9901 | 2026-03-23 | Inv. 101368.015-PC05 - FINAL | -1900.31 | 13841.84 | 3388.38 | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  |  |  | 13841.84 |  | 13841.84 | 0
|  | Totals: | 13841.84 |  | 13841.84 |  | 0 | FINAL
|  | CM Services | 13281.84 |  | 13281.84 |  | 0
|  | Reimbursables | 560 |  | 560 |  | 0
|  | Total: | 13841.84 |  | 13841.84 |  | 0

## #9502.00 PM TIME
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734R
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 20000 | 66.83 | 66.83 | 19933.17
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 20000 | 345.2 | 412.03 | 19587.97
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 49.36 | 461.39 | 19538.61
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 1932.7 | 2394.09 | 17605.91
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 464.91 | 2859 | 17141
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 2160.1 | 5019.1 | 14980.9
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 208.86 | 5227.96 | 14772.04
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 2371.8 | 7599.76 | 12400.24
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 181.29 | 7781.05 | 12218.95
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 2255.4 | 10036.45 | 9963.55
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 233.73 | 10270.18 | 9729.82
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 2690 | 12960.18 | 7039.82
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 319.62 | 13279.8 | 6720.2
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 2618.6 | 15898.4 | 4101.6
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 20000 | 180.53 | 16078.93 | 3921.07
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 20000 | 1885.6 | 17964.53 | 2035.47
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 20000 | 60.16 | 18024.69 | 1975.31
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 20000 | 738.5 | 18763.19 | 1236.81
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 20000 | 62.85 | 18826.04 | 1173.96
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 20000 | 720.4 | 19546.44 | 453.56
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 20000 | 25.08 | 19571.52 | 428.48
|  |  | Totals: | 20000 |  | 19571.52 |  | 428.48

## #9502.00 Misc
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  |  | Major Program 4F04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526345900 | 2025-12-11 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV054322 | 112.5 | 112.5
PRC 33526063911 | 2026-03-04 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2576 | 200 | 312.5
PRC 33526085904 | 2026-03-26 | 9500 | CNST | Advanced Environmental V#(00002125877) | Inv. 12626 | 630.04 | 942.54
GAX 33526173915 | 2026-06-22 | 9500 | CNST | Terracon Consultants V#(00002116512) | Inv. TQ27483 | 2515 | 3457.54
PRC 33526181912 | 2026-06-30 | 9500 | CNST | Advanced Environmental V#(00002125877) | Inv. 12958 | 320.75 | 3778.29
3778.29
3778.29
3778.29
3778.29
3778.29
3778.29
3778.29
|  |  |  | Totals: |  | 3778.29

## #9502.00 Modus Engineering
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
Modus Engineering |  |  | Vendor: 00003034025
Acct. Codes-0017-335-MM26-9260 |  |  | RFP950200-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526357904 | 2025-12-23 | PO Procore | 32000 | 32000 |  |  | 32000
PRC 3352635PA7904 | 2026-01-29 | Inv. 22640 |  | 32000 | 13440 | 13440 | 18560
PRC 3352635PB7904 | 2026-03-23 | Inv. 22756 |  | 32000 | 10560 | 24000 | 8000
PRC 3352635PC7904 | 2026-03-23 | Inv. 22880 |  | 32000 | 1600 | 25600 | 6400
PRC 3352635PD7904 | 2026-05-26 | Inv. 65071 |  | 32000 | 800 | 26400 | 5600
PRC 3352635PE7904 | 2026-06-18 | Inv. 23320 |  | 32000 | 928 | 27328 | 4672
PRC 3352635PF7904 | 2026-07-13 | Inv. 23442 |  | 32000 | 928 | 28256 | 3744 | FY26
PO 33527357904 | 2026-07-22 | Roll to FY27 | 0 | 32000 |  | 28256 | 3744
|  |  |  | 32000 |  | 28256 | 3744
|  |  |  | 32000 |  | 28256 | 3744
|  |  |  | 32000 |  | 28256 | 3744
|  |  |  | 32000 |  | 28256 | 3744
|  |  |  | 32000 |  | 28256 | 3744
|  | Totals: | 32000 |  | 28256 |  | 3744
|  | Construction Docs | 24000 |  | 24000 |  | 0
|  | Bidding/Negotiation | 1600 |  | 1600 |  | 0
|  | Construction Phase | 6400 |  | 2656 |  | 3744
|  | Total: | 32000 |  | 28256 |  | 3744

## #9502.00 McGough Constructi (2)
DOC MPCF Hot and Cold Water Mains Replacement
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526069901 | 2026-03-10 | PO Procore | 96273.29 | 96273.29 |  |  | 96273.29
PRC 3352606PA9901 | 2026-04-14 | Inv. 101368.015-CA01 |  | 96273.29 | 2958.4 | 2958.4 | 93314.89
PRC 3352606PB9901 | 2026-05-26 | Inv. 101368.015-CA02 |  | 96273.29 | 9549.59 | 12507.99 | 83765.3
PRC 3352606PC9901 | 2026-06-15 | Inv. 101368.015-CA03 |  | 96273.29 | 18012.75 | 30520.74 | 65752.55
PRC 3352606PD9901 | 2026-07-13 | Inv. 101368.015-CA04 |  | 96273.29 | 14297.66 | 44818.4 | 51454.89 | FY26
PO 33527069901 | 2026-07-22 | Roll to FY27 | 0 | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  |  |  | 96273.29 |  | 44818.4 | 51454.89
|  | Totals: | 96273.29 |  | 44818.4 |  | 51454.89
|  | CM Services | 56653.29 |  | 22858.4 |  | 33794.89
|  | Reimbursables | 4620 |  | 1260 |  | 3360
|  | Fee | 35000 |  | 20700 |  | 14300
|  | Total: | 96273.29 |  | 44818.4 |  | 51454.89

## #9502.00 Modern Piping
2026-07-22 | Roll to FY27 | 0
Project # 9502.00
Program code 950200 |  |  | Major Program 4F04
Modern Piping Service |  |  | Vendor: 00002108094
Acct. Codes-0017-335-MM26-9255 |  |  | RFB950200-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526075914 | 2026-03-16 | PO Procore | 700000 | 700000 |  |  | 700000
PO 33526075914 | 2026-04-15 | CO#1(No Cost CO) | 0 | 700000 |  | 0 | 700000
PRC 3352607PA5914 | 2026-06-02 | Inv. 83444 |  | 700000 | 255110 | 255110 | 444890 | 7890
PRC 3352607PB5914 | 2026-06-23 | Inv. 84097 |  | 700000 | 146470 | 401580 | 298420 | 12420
PRC 3352607PC5914 | 2026-07-16 | Inv. 84856 |  | 700000 | 38266.5 | 439846.5 | 260153.5 | 13603.5 | FY26
PO 33527075914 | 2026-07-22 | Roll to FY27 | 0 | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  |  |  | 700000 |  | 439846.5 | 260153.5
|  | Totals: | 700000 |  | 439846.5 |  | 260153.5

## RECAP #9503.00
HHS WRC CDC Freezer Repair
Project # 9503.00
| Program code 950300 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennifer K.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 440000
| Story Construction |  | 32546.06 | 20719.42 | 11826.64
| PM TIME |  | 8500 | 6054.08 | 2445.92
| Misc. |  | 0 | 0 | 0
C | SystemWorks |  | 6890 | 6890 | 0
| 10Fold Architecture + Engineering |  | 46490 | 16090 | 30400
C | Story Construction (2) |  | 6344 | 6344 | 0
| Total Project Cost | 440000 | 100770.06 | 56097.5 | 44672.56 | 339229.94

## #9503.00 Story Construction
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526289900 | 2025-10-16 | PO Procore | 25378.59 | 25378.59 |  |  | 25378.59
PRC 3352628PA9900 | 2026-01-16 | Inv. 35121 |  | 25378.59 | 1588.62 | 1588.62 | 23789.97
PRC 3352628PB9900 | 2026-04-17 | Inv. 35232 |  | 25378.59 | 7557.34 | 9145.96 | 16232.63
PRC 3352628PC9900 | 2026-05-26 | Inv. 35263 |  | 25378.59 | 5969.18 | 15115.14 | 10263.45
PRC 3352628PD9900 | 2026-06-19 | Inv. 35299 |  | 25378.59 | 3498.46 | 18613.6 | 6764.99
PRC 3352628PE9900 | 2026-07-15 | Inv. 35343 |  | 25378.59 | 2105.82 | 20719.42 | 4659.17 | FY26
PO 33527289900 | 2026-07-22 | Roll to FY27 | 0 | 25378.59 |  | 20719.42 | 4659.17
PO 33527289900 | 2026-07-23 | CO #1 | 7167.47 | 32546.06 |  | 20719.42 | 11826.64
|  |  |  | 32546.06 |  | 20719.42 | 11826.64
|  |  |  | 32546.06 |  | 20719.42 | 11826.64
|  |  |  | 32546.06 |  | 20719.42 | 11826.64
|  |  |  | 32546.06 |  | 20719.42 | 11826.64
|  |  |  | 32546.06 |  | 20719.42 | 11826.64
|  | Totals: | 32546.06 |  | 20719.42 |  | 11826.64
|  | CM Services | 25260.59 |  | 20660.42 |  | 4600.17
|  | Reimbursables | 118 |  | 59 |  | 59
|  | CO #1 | 7167.47 |  |  |  | 7167.47
|  | Total: | 32546.06 |  | 20719.42 |  | 11826.64

## #9503.00 PM TIME
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734S
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8500 | 8500 |  |  | 8500
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8500 | 63.24 | 63.24 | 8436.76
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8500 | 625.7 | 688.94 | 7811.06
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 8500 | 44.83 | 733.77 | 7766.23
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 8500 | 288.7 | 1022.47 | 7477.53
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 8500 | 21.39 | 1043.86 | 7456.14
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 8500 | 270.1 | 1313.96 | 7186.04
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 8500 | 63.67 | 1377.63 | 7122.37
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 8500 | 732.1 | 2109.73 | 6390.27
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 8500 | 197.88 | 2307.61 | 6192.39
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 8500 | 1613.2 | 3920.81 | 4579.19
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 8500 | 85.13 | 4005.94 | 4494.06
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 8500 | 890.8 | 4896.74 | 3603.26
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 8500 | 67.23 | 4963.97 | 3536.03
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 8500 | 820.5 | 5784.47 | 2715.53
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 8500 | 20.95 | 5805.42 | 2694.58
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 8500 | 240.7 | 6046.12 | 2453.88
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 8500 | 7.96 | 6054.08 | 2445.92
|  |  | Totals: | 8500 |  | 6054.08 |  | 2445.92

## #9503.00 Misc
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 564
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9503.00 SystemWorks
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
SystemWorks |  |  | Vendor: 00002144353
Acct. Codes-0017-335-MM26-9255 |  |  | MA 00521396C
Project Manager - Jennifer K. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526290900 | 2025-10-17 | PO Procore | 6050 | 6050 |  |  | 6050
PO 33526290900 | 2026-02-10 | CO #1 | 840 | 6890 |  | 0 | 6890
PRC 3352629PA0900 | 2026-03-09 | Inv. 12814 |  | 6890 | 6890 | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  |  |  | 6890 |  | 6890 | 0
|  | Totals: | 6890 |  | 6890 |  | 0 | FINAL

## #9503.00 10Fold Architecture
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
10Fold Architecture + Engineering |  |  | Vendor: 00003101228
Acct. Codes-0017-335-MM26-9260 |  |  | 950300-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526093915 | 2026-04-03 | PO Procore | 38000 | 38000 |  |  | 38000
PO 33526093915 | 2026-04-22 | CO #1 | 1500 | 39500 |  | 0 | 39500
PRC 3352609PA3915 | 2026-05-19 | Inv. 9503.00-01 |  | 39500 | 5005 | 5005 | 34495
PRC 3352609PB3915 | 2026-06-08 | Inv. 9503.00-02 |  | 39500 | 4095 | 9100 | 30400
PO 33526093915 | 2026-07-21 | CO #2 | 6990 | 46490 |  | 9100 | 37390
PRC 3352609PC3915 | 2026-07-23 | Inv. 9503.00-03 |  | 46490 | 6990 | 16090 | 30400 | FY26
PO 33527093915 | 2026-07-30 | Roll to FY27 | 0 | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  |  |  | 46490 |  | 16090 | 30400
|  | Totals: | 46490 |  | 16090 |  | 30400
|  | Design Development Docs | 7600 |  | 7600 |  | 0
|  | Construction Docs | 17100 |  |  |  | 17100
|  | Bidding Assistance | 3040 |  |  |  | 3040
|  | Construction Phase | 10260 |  |  |  | 10260
|  | CO #1 | 1500 |  | 1500 |  | 0
|  | CO #2 | 6990 |  | 6990 |  | 0
|  | Total: | 46490 |  | 16090 |  | 30400

## #9503.00 Story Construction (2)
HHS WRC CDC Freezer Repair
Project # 9503.00
Program code 950300 |  |  | Major Program 4E19
Story Construction (2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | SRVV5
Project Manager - Jennifer K. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526160907 | 2026-06-09 | PO Procore | 6344 | 6344 |  |  | 6344
PRC 3352616PA0907 | 2026-07-17 | Inv. 35354 |  | 6344 | 6344 | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  |  |  | 6344 |  | 6344 | 0
|  | Totals: | 6344 |  | 6344 |  | 0
|  | Labor | 4351 |  | 4351 |  | 0
|  | Material | 1224 |  | 1224 |  | 0
|  | Equip,emt | 769 |  | 769 |  | 0
|  | Total: | 6344 |  | 6344 |  | 0

## RECAP #9504.00
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 400000
Story Construction |  | 26309.62 | 16336 | 9973.62
PM TIME |  | 8000 | 4656.93 | 3343.07
Misc. |  | 1156.46 | 1156.46 | 0
OPN Architects |  | 82800 | 54970 | 27830
Total Project Cost | 400000 | 118266.08 | 77119.39 | 41146.69 | 281733.92

## #9504.00 Story Construction
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  | Major Program 4E19
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526030910 | 2026-01-30 | PO Procore | 26309.62 | 26309.62 |  |  | 26309.62
PRC 3352603PA0910 | 2026-03-18 | Inv. 35197 |  | 26309.62 | 3615.78 | 3615.78 | 22693.84
PRC 3352603PB0910 | 2026-04-17 | Inv. 35230 |  | 26309.62 | 2829.56 | 6445.34 | 19864.28
PRC 3352603PC0910 | 2026-05-26 | Inv. 35261 |  | 26309.62 | 2384.19 | 8829.53 | 17480.09
PRC 3352603PD0910 | 2026-06-19 | Inv. 35298 |  | 26309.62 | 3015.68 | 11845.21 | 14464.41
PRC 3352603PE0910 | 2026-07-15 | Inv. 35341 |  | 26309.62 | 4490.79 | 16336 | 9973.62 | FY26
PO 33527030910 | 2026-07-22 | Roll to FY27 | 0 | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  |  |  | 26309.62 |  | 16336 | 9973.62
|  | Totals: | 26309.62 |  | 16336 |  | 9973.62
|  | CM Services | 26191.62 |  | 16247.5 |  | 9944.12
|  | Reimbursables | 118 |  | 88.5 |  | 29.5
|  | Total: | 26309.62 |  | 16336 |  | 9973.62

## #9504.00 PM TIME
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734T
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 8000 | 35.92 | 35.92 | 7964.08
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 8000 | 357.7 | 393.62 | 7606.38
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 8000 | 6.5 | 400.12 | 7599.88
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 8000 | 41 | 441.12 | 7558.88
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 8000 | 25.47 | 466.59 | 7533.41
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 8000 | 314.4 | 780.99 | 7219.01
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 8000 | 90.61 | 871.6 | 7128.4
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 8000 | 1047 | 1918.6 | 6081.4
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 8000 | 126.71 | 2045.31 | 5954.69
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 8000 | 1031 | 3076.31 | 4923.69
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 8000 | 81.38 | 3157.69 | 4842.31
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 8000 | 846.5 | 4004.19 | 3995.81
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 8000 | 18.66 | 4022.85 | 3977.15
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 8000 | 227.4 | 4250.25 | 3749.75
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 8000 | 31.65 | 4281.9 | 3718.1
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 8000 | 362.1 | 4644 | 3356
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 8000 | 12.93 | 4656.93 | 3343.07
|  |  | Totals: | 8000 |  | 4656.93 |  | 3343.07

## #9504.00 Misc
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 564
Project Manager - Jennifer K.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526181914 | 2026-06-30 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2719799 | 1071 | 1071
PRC 33527204901 | 2026-07-23 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2981 | 85.46 | 1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
1156.46
|  |  |  | Totals: |  | 1156.46

## #9504.00 OPN Architects
HHS WRC Food Service Elevator Replacement
Project # 9504.00
Program code 950400 |  |  | Major Program 4E19
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-MM26-9260 |  |  | 950400-01
Project Manager - Jennifer K. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526083910 | 2026-03-24 | PO Procore | 82800 | 82800 |  |  | 82800
PRC 3352608PA3910 | 2026-07-07 | Inv. 26816000-1 |  | 82800 | 54970 | 54970 | 27830 | FY26
PO 33527083910 | 2026-07-22 | Roll to FY27 | 0 | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  |  |  | 82800 |  | 54970 | 27830
|  | Totals: | 82800 |  | 54970 |  | 27830
|  | Construction Documents | 54970 |  | 54970 |  | 0
|  | Bidding Assistance | 3430 |  |  |  | 3430
|  | Construction Phase | 24400 |  |  |  | 24400
|  | Total: | 82800 |  | 54970 |  | 27830

## RECAP #9505.00
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
| Program code 950500 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 491000
| Shive Hattery |  | 43927 | 35520.6 | 8406.4
| PM TIME |  | 11800 | 7265.76 | 4534.24
| Misc. |  | 0 | 0 | 0
C | Boyd Jones |  | 17817.49 | 17817.49 | 0
| Midwest Fence & Gate |  | 380950 | 0 | 380950
| Boyd Jones (2) |  | 32450.52 | 4769.45 | 27681.07
| Total Project Cost | 491000 | 486945.01 | 65373.3 | 421571.71 | 4054.99

## #9505.00 Shive Hattery
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM26-9260 |  |  | 950500-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526008908 | 2026-01-08 | PO Procore | 43927 | 43927 |  |  | 43927
PRC 3352600PA8908 | 2026-03-18 | Inv. 2250021640-1 |  | 43927 | 30063 | 30063 | 13864
PRC 3352600PB8908 | 2026-04-27 | Inv. 2250021640-2 |  | 43927 | 3356 | 33419 | 10508
PRC 3352600PC8908 | 2026-06-26 | Inv. 2250021640-3 |  | 43927 | 2101.6 | 35520.6 | 8406.4 | FY26
PO 33527008908 | 2026-07-22 | Roll to FY27 | 0 | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  |  |  | 43927 |  | 35520.6 | 8406.4
|  | Totals: | 43927 |  | 35520.6 |  | 8406.4
|  | Schematic Design Docs | 10008 |  | 10008 |  | 0
|  | Design Development Docs | 11466 |  | 11466 |  | 0
|  | Construction Docs | 8589 |  | 8589 |  | 0
|  | Bidding Assistance | 3356 |  | 3356 |  | 0
|  | Construction Phase | 10508 |  | 2101.6 |  | 8406.4
|  | Total: | 43927 |  | 35520.6 |  | 8406.4

## #9505.00 PM TIME
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734U
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 11800 | 11800 |  |  | 11800
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 11800 | 27.76 | 27.76 | 11772.24
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 11800 | 278.4 | 306.16 | 11493.84
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 11800 | 139.35 | 445.51 | 11354.49
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 11800 | 887.5 | 1333.01 | 10466.99
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 11800 | 40.69 | 1373.7 | 10426.3
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 11800 | 464.2 | 1837.9 | 9962.1
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 11800 | 105.64 | 1943.54 | 9856.46
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 11800 | 1312.8 | 3256.34 | 8543.66
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 11800 | 103.85 | 3360.19 | 8439.81
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 11800 | 1199 | 4559.19 | 7240.81
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 11800 | 41.38 | 4600.57 | 7199.43
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 11800 | 336.2 | 4936.77 | 6863.23
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 11800 | 155.38 | 5092.15 | 6707.85
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 11800 | 1619.1 | 6711.25 | 5088.75
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 11800 | 19.1 | 6730.35 | 5069.65
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 11800 | 268 | 6998.35 | 4801.65
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 11800 | 20.95 | 7019.3 | 4780.7
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 11800 | 238.5 | 7257.8 | 4542.2
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 11800 | 7.96 | 7265.76 | 4534.24
|  |  | Totals: | 11800 |  | 7265.76 |  | 4534.24
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9505.00 Misc
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9505.00 Boyd Jones
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | 950500-01
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526020906 | 2026-01-20 | PO Procore | 17836.71 | 17836.71 |  |  | 17836.71
PRC 3352602PA0906 | 2026-01-30 | Inv. 9505.00-01 |  | 17836.71 | 5544.32 | 5544.32 | 12292.39
PRC 3352602PB0906 | 2026-02-06 | Inv. 9505.00-02 |  | 17836.71 | 1630.1 | 7174.42 | 10662.29
PRC 3352602PC0906 | 2026-03-18 | Inv. 9505.00-03 |  | 17836.71 | 4842.11 | 12016.53 | 5820.18
PRC 3352602PD0906 | 2026-04-22 | Inv. 9505.00-04 |  | 17836.71 | 5800.96 | 17817.49 | 19.22
PO 33526020906 | 2026-07-17 | Closing PO Per PM email | -19.22 | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  |  |  | 17817.49 |  | 17817.49 | -6.537e-13
|  | Totals: | 17817.49 |  | 17817.49 |  | 0
|  | CM Services | 17505.49 |  | 17505.49 |  | 0
|  | Reimbursables | 312 |  | 312 |  | 0
|  | Total: | 17817.49 |  | 17817.49 |  | 0

## #9505.00 Midwest Fence & Gate
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Midwest Fence & Gate |  |  | Vendor: 00002122529
Acct. Codes-0017-335-MM26-9255 |  |  | 950500-01
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526106905 | 2026-04-16 | PO Procore | 380950 | 380950 |  |  | 380950 | FY26
PO 33527106905 | 2026-07-22 | Roll to FY27 | 0 | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  |  |  | 380950 |  | 0 | 380950
|  | Totals: | 380950 |  | 0 |  | 380950

## #9505.00 Boyd Jones (2)
DOC FDCF Sally Port Operator Replacement
Project # 9505.00
Program code 950500 |  |  | Major Program 4E01
Boyd Jones(2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021 For Boyd Jones
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526131914 | 2026-05-11 | PO Procore | 32450.52 | 32450.52 |  |  | 32450.52
PRC 3352613PA1914 | 2026-06-16 | Inv. 9505.00-001 |  | 32450.52 | 3861.47 | 3861.47 | 28589.05
PRC 3352613PB1914 | 2026-07-06 | Inv. 9505.00-002 |  | 32450.52 | 907.98 | 4769.45 | 27681.07 | FY26
PO 33527131914 | 2026-07-22 | Roll to FY27 | 0 | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  |  |  | 32450.52 |  | 4769.45 | 27681.07
|  | Totals: | 32450.52 |  | 4769.45 |  | 27681.07
|  | CM Services | 31010.52 |  | 4763.45 |  | 26247.07
|  | Reimbursables | 1440 |  | 6 |  | 1434
|  | Total: | 32450.52 |  | 4769.45 |  | 27681.07
Vendor used Inv 9505.00-01 on another tab, please use Inv. 9505.00-00x

## RECAP #9506.00
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1680747
McGough Construction |  | 14731.62 | 7754.35 | 6977.27
PM TIME |  | 18000 | 13195.86 | 4804.14
Misc. |  | 3788.7 | 3788.7 | 0
Bolton and Menk |  | 152244 | 108009.5 | 44234.5
Terracon Consultants |  | 7815 | 2165.5 | 5649.5
Total Project Cost | 1680747 | 196579.32 | 134913.91 | 61665.41 | 1484167.68

## #9506.00 McGough Construction
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526323905 | 2025-11-19 | PO Procore | 14731.62 | 14731.62 |  |  | 14731.62
PRC 3352632PA3905 | 2026-02-16 | Inv. 101537.002-PC01 |  | 14731.62 | 2109 | 2109 | 12622.62
PRC 3352632PB3905 | 2026-03-19 | Inv. 101537.002-PC02 |  | 14731.62 | 888.72 | 2997.72 | 11733.9
PRC 3352632PC3905 | 2026-04-09 | Inv. 101537.002-PC03 |  | 14731.62 | 791.5 | 3789.22 | 10942.4
PRC 3352632PD3905 | 2026-05-19 | Inv. 101537.002-PC04 |  | 14731.62 | 700.18 | 4489.4 | 10242.22
PRC 3352632PE3905 | 2026-06-15 | Inv. 101537.002-PC05 |  | 14731.62 | 1613.45 | 6102.85 | 8628.77
PRC 3352632PF3905 | 2026-07-13 | Inv. 101537.002-PC06 |  | 14731.62 | 1651.5 | 7754.35 | 6977.27 | FY26
PO 33527323905 | 2026-07-22 | Roll to FY27 | 0 | 14731.62 |  | 7754.35 | 6977.27
|  |  |  | 14731.62 |  | 7754.35 | 6977.27
|  |  |  | 14731.62 |  | 7754.35 | 6977.27
|  |  |  | 14731.62 |  | 7754.35 | 6977.27
|  |  |  | 14731.62 |  | 7754.35 | 6977.27
|  |  |  | 14731.62 |  | 7754.35 | 6977.27
|  | Totals: | 14731.62 |  | 7754.35 |  | 6977.27
|  | CM Services | 14311.62 |  | 7694.35 |  | 6617.27
|  | Reimbursables | 420 |  | 60 |  | 360
|  | Total: | 14731.62 |  | 7754.35 |  | 6977.27

## #9506.00 PM TIME
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734V
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18000 | 18000 |  |  | 18000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 18000 | 44.41 | 44.41 | 17955.59
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 18000 | 229.2 | 273.61 | 17726.39
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 18000 | 49.36 | 322.97 | 17677.03
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 18000 | 487.3 | 810.27 | 17189.73
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 18000 | 66.42 | 876.69 | 17123.31
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 18000 | 423.8 | 1300.49 | 16699.51
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 18000 | 157.03 | 1457.52 | 16542.48
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 18000 | 1779.1 | 3236.62 | 14763.38
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 18000 | 108.95 | 3345.57 | 14654.43
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 18000 | 1353.8 | 4699.37 | 13300.63
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 18000 | 116.64 | 4816.01 | 13183.99
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 18000 | 1345 | 6161.01 | 11838.99
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 18000 | 186.29 | 6347.3 | 11652.7
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 18000 | 1523.6 | 7870.9 | 10129.1
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 18000 | 219.55 | 8090.45 | 9909.55
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 18000 | 2293.8 | 10384.25 | 7615.75
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 18000 | 117.01 | 10501.26 | 7498.74
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 18000 | 1431.6 | 11932.86 | 6067.14
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 18000 | 97.81 | 12030.67 | 5969.33
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 18000 | 1126.3 | 13156.97 | 4843.03
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 18000 | 38.89 | 13195.86 | 4804.14
|  |  | Totals: | 18000 |  | 13195.86 |  | 4804.14

## #9506.00 Misc
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 171
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526034910 | 2026-02-04 | 9500 | CNST | Beeline & Blue V#(00002108204) | Inv. INV054777 | 13.5 | 13.5
GAX 33526110919 | 2026-04-20 | 9500 | CNST | Mt Pleasant Electric Contractors V#(00002108917) | Inv. B78792 | 400 | 413.5
GAX 33526131915 | 2026-05-11 | 9500 | CNST | Mt Pleasant Electric Contractors V#(00002108917) | Inv. B78832 | 3375.2 | 3788.7
3788.7
3788.7
3788.7
3788.7
3788.7
3788.7
3788.7
3788.7
3788.7
|  |  |  | Totals: |  | 3788.7

## #9506.00 Bolton and Menk
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
Bolton and Menk |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM26-9260 |  |  | RFP950600-02
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526069909 | 2026-03-10 | PO Procore | 152244 | 152244 |  |  | 152244
PRC 3352606PA9909 | 2026-04-09 | Inv. 9506.00-01 |  | 152244 | 20929.2 | 20929.2 | 131314.8
PRC 3352606PB9909 | 2026-05-19 | Inv. 9506.00-02 |  | 152244 | 48834.8 | 69764 | 82480
PRC 3352606PC9909 | 2026-06-18 | Inv. 9506.00-03 |  | 152244 | 25497 | 95261 | 56983
PRC 3352606PD9909 | 2026-07-13 | Inv. 9506.00-04 |  | 152244 | 12748.5 | 108009.5 | 44234.5 | FY26
PO 33527069909 | 2026-07-22 | Roll to FY27 | 0 | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  |  |  | 152244 |  | 108009.5 | 44234.5
|  | Totals: | 152244 |  | 108009.5 |  | 44234.5
|  | Design Development | 69764 |  | 69764 |  | 0
|  | Construction Docs | 50994 |  | 38245.5 |  | 12748.5
|  | Bidding/Negotiation | 2592 |  |  |  | 2592
|  | Construction Phase | 28894 |  |  |  | 28894
|  | Total: | 152244 |  | 108009.5 |  | 44234.5

## #9506.00 Terracon
DOC MPCF Perimeter Fence and Wagon Gates
Project # 9506.00
Program code 950600 |  |  | Major Program 4E01
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM26-9255 |  |  | MA25049
Project Manager - Brandon A. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526103911 | 2026-04-13 | PO Procore | 7815 | 7815 |  |  | 7815
PRC 3352610PA3911 | 2026-07-30 | Inv. 20786 |  | 7815 | 2165.5 | 2165.5 | 5649.5 | FY26
PO 33527103911 | 2026-07-30 | Roll to FY27 | 0 | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  |  |  | 7815 |  | 2165.5 | 5649.5
|  | Totals: | 7815 |  | 2165.5 |  | 5649.5
| Line 3 | Geotechnical Soil- 6@$70 | 420 |  | 350 |  | 70
| Line 2 | Soil & Land Mgmt. 2@$130 | 260 |  |  |  | 260
| Line 2 | Soil & Land Mgmt. 14@415 | 210 |  |  |  | 210
| Line 2 | Soil & Land Mgmt. 2@$150 | 300 |  |  |  | 300
| Line 5 | Project Mngr 34@$130 | 4420 |  | 487.5 |  | 3932.5
| Line 6 | Testing Tech 23@$70 | 1610 |  | 735 |  | 875
| Line 7 | Travel 150@.5 | 75 |  | 73 |  | 2
| Line 8` | Specialized Vehicles 1@520 | 520 |  | 520 |  | 0
|  | Total: | 7815 |  | 2165.5 |  | 5649.5

## RECAP #9507.00
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.(JK)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 700000
SYSKool |  | 436832 | 0 | 436832
PM TIME |  | 15000 | 734.36 | 14265.64
Misc. |  | 0 | 0 | 0
Total Project Cost | 700000 | 451832 | 734.36 | 451097.64 | 248168

## #9507.00 SYSKool
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  | Major Program 4E01
SysKool-IMCC Cooling Tower |  |  | Vendor: 00002097390
Acct. Codes-0017-335-MM26-9255 |  |  | MA26319
Project Manager - Geoff W.(JK) |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526168913 | 2026-06-17 | PO Procore | 436832 | 436832 |  |  | 436832 | FY26
PO 33527168913 | 2026-07-30 | Roll to FY27 | 0 | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  |  |  | 436832 |  | 0 | 436832
|  | Totals: | 436832 |  | 0 |  | 436832

## #9507.00 PM TIME
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734W
Project Manager - Geoff W.(JK)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 15000 | 15000 |  |  | 15000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 15000 | 45.28 | 45.28 | 14954.72
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 15000 | 446.3 | 491.58 | 14508.42
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 15000 | 18.08 | 509.66 | 14490.34
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 15000 | 224.7 | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
[5 empty] | 15000 |  | 734.36 | 14265.64
|  |  | Totals: | 15000 |  | 734.36 |  | 14265.64
Note on E9: Huggins, Joni [DAS]: Project #s 9507 & 9508 $Joni Wheelock, Geoff Mon, Nov 24, 4:37 PM (15 hours ago) to me Could you please set up a PM Time budget for these referenced projects in the amount of: 9507.00 = $15,000 9508.00 = $36,000 I greatly appreciate your help on this. Thank you,

## #9507.00 Misc
DOC IMCC Cooling Tower Replacement
Project # 9507.00
Program code 950700 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 175
Project Manager - Geoff W.(JK)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9508.00
DOC FDCF Unit A Roof Replacement
Project # 9508.00
| Program code 950800 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W.(JE)
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 1707300
C | Story Construction |  | 19193.36 | 19193.36 | 0
| PM TIME |  | 36000 | 6852.4 | 29147.6
| Misc. |  | 6445.22 | 6445.22 | 0
| Cannon Moss Brygger Architects |  | 56340 | 37283 | 19057
| Story Construction (2) |  | 150120.32 | 5485.69 | 144634.63
| White Castle Roofing & Contracting |  | 1000000 | 10670 | 989330
| Total Project Cost | 1707300 | 1268098.9 | 85929.67 | 1182169.23 | 439201.1

## #9508.00 Story Construction
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Geoff W.(JE) |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526308900 | 2025-11-04 | PO Procore | 19497.16 | 19497.16 |  |  | 19497.16
PRC 3352630PA8900 | 2025-12-29 | Inv. 35080 |  | 19497.16 | 2918.78 | 2918.78 | 16578.38
PRC 3352630PB8900 | 2026-01-20 | Inv. 35120 |  | 19497.16 | 1893.34 | 4812.12 | 14685.04
PRC 3352630PC8900 | 2026-02-23 | Inv. 35154 |  | 19497.16 | 2210.73 | 7022.85 | 12474.31
PRC 3352630PD8900 | 2026-03-17 | Inv. 35198 |  | 19497.16 | 2264.64 | 9287.49 | 10209.67
PRC 3352630PE8900 | 2026-04-16 | Inv. 35231 |  | 19497.16 | 3229.54 | 12517.03 | 6980.13
PRC 3352630PF8900 | 2026-06-03 | Inv. 35262FINAL | -303.8 | 19193.36 | 6676.33 | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  |  |  | 19193.36 |  | 19193.36 | 1.9895e-12
|  | Totals: | 19193.36 |  | 19193.36 |  | 0 | FINAL
|  | CM Services | 18990.86 |  | 18990.86 |  | 0
|  | Reimbursables | 202.5 |  | 202.5 |  | 0
|  | Total: | 19193.36 |  | 19193.36 |  | 0

## #9508.00 PM TIME
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734X
Project Manager - Geoff W.(JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 36000 | 36000 |  |  | 36000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 36000 | 68.53 | 68.53 | 35931.47
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 36000 | 677.1 | 745.63 | 35254.37
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 36000 | 167.12 | 912.75 | 35087.25
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 36000 | 1065.2 | 1977.95 | 34022.05
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 36000 | 73.99 | 2051.94 | 33948.06
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 36000 | 836.5 | 2888.44 | 33111.56
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 36000 | 113.03 | 3001.47 | 32998.53
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 36000 | 1400.8 | 4402.27 | 31597.73
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 36000 | 49.67 | 4451.94 | 31548.06
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 36000 | 576.8 | 5028.74 | 30971.26
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 36000 | 83.22 | 5111.96 | 30888.04
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 36000 | 674 | 5785.96 | 30214.04
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 36000 | 8.6 | 5794.56 | 30205.44
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 36000 | 87 | 5881.56 | 30118.44
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 36000 | 51 | 5932.56 | 30067.44
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 36000 | 623.7 | 6556.26 | 29443.74
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 36000 | 16.43 | 6572.69 | 29427.31
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 36000 | 273.4 | 6846.09 | 29153.91
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 36000 | 6.31 | 6852.4 | 29147.6
|  |  | Totals: | 36000 |  | 6852.4 |  | 29147.6
Note on E9: Huggins, Joni [DAS]: PM Time Budget Request $Joni Elliott, Jennie Sun, Nov 2, 4:38 PM (2 days ago) to me, Geoff Please establish a PM Time budget in the project as follows: 9508.00 - FDCF Unit A, B, & G Roof Reply - $9,500.00 Thank you, Jennie Elliott Project #s 9507 & 9508 $Joni Wheelock, Geoff Nov 24, 2025, 4:37 PM (15 hours ago) to me Could you please set up a PM Time budget for these referenced projects in the amount of: 9507.00 = $15,000 9508.00 = $36,000 I greatly appreciate your help on this. Thank you,

## #9508.00 Misc
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 178
Project Manager - Geoff W.(JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526021912 | 2026-01-21 | 9500 | CNST | ACT Group V#(00002134218) | Inv. 2693264 | 2616 | 2616
GAX 33526126917 | 2026-05-06 | 9500 | CNST | Academy Roofing V#(00003010234) | Inv. 30866 | 3500 | 6116
PRC 33526146917 | 2026-05-26 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2784 | 329.22 | 6445.22
6445.22
6445.22
6445.22
6445.22
6445.22
6445.22
6445.22
6445.22
6445.22
|  |  |  | Totals: |  | 6445.22

## #9508.00 CMB Architects
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
CMB Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM26-9260 |  |  | 950800-001
Project Manager - Geoff W.(JE) |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526007909 | 2026-01-07 | PO Procore | 56340 | 56340 |  |  | 56340
PRC 3352600PA7909 | 2026-02-09 | Inv. 66908 |  | 56340 | 7254 | 7254 | 49086
PRC 3352600PB7909 | 2026-03-09 | Inv. 67011 |  | 56340 | 12090 | 19344 | 36996
PRC 3352600PC7909 | 2026-04-27 | Inv. 67134 |  | 56340 | 5810 | 25154 | 31186
PRC 3352600PD7909 | 2026-05-19 | Inv. 67284 |  | 56340 | 8766 | 33920 | 22420
PRC 3352600PE7909 | 2026-06-15 | Inv. 67485 |  | 56340 | 1121 | 35041 | 21299
PRC 3352600PF7909 | 2026-07-06 | Inv. 67576 |  | 56340 | 2242 | 37283 | 19057 | FY26
PO 33527007909 | 2026-07-22 | Roll to FY27 | 0 | 56340 |  | 37283 | 19057
|  |  |  | 56340 |  | 37283 | 19057
|  |  |  | 56340 |  | 37283 | 19057
|  |  |  | 56340 |  | 37283 | 19057
|  |  |  | 56340 |  | 37283 | 19057
|  |  |  | 56340 |  | 37283 | 19057
|  | Totals: | 56340 |  | 37283 |  | 19057
|  | Construction Documents | 24180 |  | 24180 |  | 0
|  | Bidding Assistance | 9740 |  | 9740 |  | 0
|  | Construction Phase | 22420 |  | 3363 |  | 19057
|  | Total: | 56340 |  | 37283 |  | 19057

## #9508.00 Story Construction (2)
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
Story Construction(2) |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Geoff W.(JE) |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526146908 | 2026-05-26 | PO Procore | 150120.32 | 150120.32 |  |  | 150120.32
PRC 3352614PA6908 | 2026-07-17 | Inv. 35342 |  | 150120.32 | 5485.69 | 5485.69 | 144634.63 | FY26
PO 33527146908 | 2026-07-22 | Roll to FY27 | 0 | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  |  |  | 150120.32 |  | 5485.69 | 144634.63
|  | Totals: | 150120.32 |  | 5485.69 |  | 144634.63
|  | CM Services | 96677.82 |  | 5485.69 |  | 91192.13
|  | Reimbursables | 3442.5 |  |  |  | 3442.5
|  | Fees | 50000 |  |  |  | 50000
|  | Total: | 150120.32 |  | 5485.69 |  | 144634.63

## #9508.00 White Castle Roofing
DOC FDCF Unit A Roof Replacement
Project # 9508.00
Program code 950800 |  |  | Major Program 4E02
White Castle Roofing & Contracting |  |  | Vendor: 00003233003
Acct. Codes-0017-335-MM26-9255 |  |  | RFB950800-01
Project Manager - Geoff W.(JE) |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526153910 | 2026-06-02 | PO Procore | 1000000 | 1000000 |  |  | 1000000
PRC 3352615PA3910 | 2026-07-21 | Inv. 9508.00-01 |  | 1000000 | 10670 | 10670 | 989330 | 330 | FY26
PO 33527153910 | 2026-07-28 | Roll to FY27 | 0 | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  |  |  | 1000000 |  | 10670 | 989330
|  | Totals: | 1000000 |  | 10670 |  | 989330

## RECAP #9509.00
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per Geoff 11/25/25
Note on B17: Huggins, Joni [DAS]: Project 9508/9509/9510 $Joni Wheelock, Geoff Mon, Nov 24, 12:42 PM (19 hours ago) to me, Jennie Good Morning, These projects were all being rolled up into 9508 with their respective budgets being moved into 9508. Can you please assist with closing out 9509 & 9510 and moving all items to the 9508 project? Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9509.00 Vendor A
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Geoff W. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9509.00 PM TIME
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Y
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9509.00 Misc
DOC FDCF Boone Unit Roof Replacement
Project # 9509.00
Program code 950900 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9510.00
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W. (JE)
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0
Closed per Geoff 11/25/25
Note on B17: Huggins, Joni [DAS]: Project 9508/9509/9510 $Joni Wheelock, Geoff Mon, Nov 24, 12:42 PM (19 hours ago) to me, Jennie Good Morning, These projects were all being rolled up into 9508 with their respective budgets being moved into 9508. Can you please assist with closing out 9509 & 9510 and moving all items to the 9508 project? Thank you, Geoff Wheelock Bureau Chief, State Design & Construction

## #9510.00 Vendor A
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - Geoff W. (JE) |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #9510.00 PM TIME
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 734Z
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9510.00 Misc
DOC FDCF Grove Unit Roof Replacement
Project # 9510.00
Program code 951000 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Geoff W. (JE)
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9511.00
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
| Program code 951100 |  |  | Major Program 4E12
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 265000
C | McGough Construction |  | 11743.31 | 11743.31 | 0
| PM TIME |  | 17000 | 13499.14 | 3500.86
| Misc. |  | 200 | 200 | 0
| Bolton And Menk |  | 35303 | 24882.8 | 10420.2
C | Terracon Consultants |  | 4810.5 | 4810.5 | 0
| McGough Construction (2) |  | 30776.85 | 1364.97 | 29411.88
| Jones Contracting Corp |  | 141165.26 | 959.94 | 140205.32
| Total Project Cost | 265000 | 240998.92 | 57460.66 | 183538.26 | 24001.08

## #9511.00 McGough Construction
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526322901 | 2025-11-18 | PO Procore | 15864.97 | 15864.97 |  |  | 15864.97
PRC 3352632PA2901 | 2026-02-13 | Inv. 101537.003-PC01 |  | 15864.97 | 3588.59 | 3588.59 | 12276.38
PRC 3352632PB2901 | 2026-03-20 | Inv. 101537.003-PC02 |  | 15864.97 | 1310.83 | 4899.42 | 10965.55
PRC 3352632PC2901 | 2026-04-14 | Inv. 101537.003-PC03 |  | 15864.97 | 1534.28 | 6433.7 | 9431.27
PRC 3352632PD2901 | 2026-05-19 | Inv. 101537.003-PC04 |  | 15864.97 | 1789.98 | 8223.68 | 7641.29
PRC 3352632PE2901 | 2026-06-09 | Inv. 101537.003-PC05 |  | 15864.97 | 2697.7 | 10921.38 | 4943.59
PRC 3352632PF2901 | 2026-07-13 | Inv. 101537.003-PC06 PC FINAL | -4121.66 | 11743.31 | 821.93 | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  |  |  | 11743.31 |  | 11743.31 | 0
|  | Totals: | 11743.31 |  | 11743.31 |  | 0 | FINAL
|  | CM Services | 11651.31 |  | 11651.31 |  | 0
|  | Reimbursables | 92 |  | 92 |  | 0
|  | Total: | 11743.31 |  | 11743.31 |  | 0

## #9511.00 PM TIME
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  |  | Major Program 4E12
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735A
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 17000 | 17000 |  |  | 17000
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 17000 | 55.62 | 55.62 | 16944.38
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 17000 | 287.2 | 342.82 | 16657.18
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 17000 | 60.38 | 403.2 | 16596.8
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 17000 | 507.6 | 910.8 | 16089.2
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 17000 | 65.21 | 976.01 | 16023.99
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 17000 | 464.7 | 1440.71 | 15559.29
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 17000 | 142.26 | 1582.97 | 15417.03
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 17000 | 1617.8 | 3200.77 | 13799.23
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 17000 | 149.64 | 3350.41 | 13649.59
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 17000 | 1854.1 | 5204.51 | 11795.49
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 17000 | 137.72 | 5342.23 | 11657.77
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 17000 | 1585 | 6927.23 | 10072.77
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 17000 | 168.54 | 7095.77 | 9904.23
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 17000 | 1380.4 | 8476.17 | 8523.83
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 17000 | 136.53 | 8612.7 | 8387.3
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 17000 | 1426.5 | 10039.2 | 6960.8
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 17000 | 170.11 | 10209.31 | 6790.69
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 17000 | 2077.2 | 12286.51 | 4713.49
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 17000 | 93.73 | 12380.24 | 4619.76
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 17000 | 1080.9 | 13461.14 | 3538.86
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 17000 | 38 | 13499.14 | 3500.86
|  |  | Totals: | 17000 |  | 13499.14 |  | 3500.86

## #9511.00 Misc
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  |  | Major Program 4E12
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 859
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526169913 | 2026-06-18 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2878 | 200 | 200
200
200
200
|  |  |  | ` |  |  | 200
200
200
200
200
200
200
200
|  |  |  | Totals: |  | 200

## #9511.00 Bolton and Menk
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
Bolton and Menk |  |  | Vendor: 00002104085
Acct. Codes-0017-335-MM26-9260 |  |  | RFP951100-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526034918 | 2026-02-04 | PO Procore | 35303 | 35303 |  |  | 35303
PRC 3352603PA4918 | 2026-03-23 | Inv. 9511.00-01 |  | 35303 | 9019.5 | 9019.5 | 26283.5
PRC 3352603PB4918 | 2026-04-09 | Inv. 9511.00-02 |  | 35303 | 10110.5 | 19130 | 16173
PRC 3352603PC4918 | 2026-05-19 | Inv. 9511.00-03 |  | 35303 | 2368 | 21498 | 13805
PRC 3352603PD4918 | 2026-06-19 | Inv. 9511.00-04 |  | 35303 | 2227 | 23725 | 11578
PRC 3352603PE4918 | 2026-07-13 | Inv. 9511.00-05 |  | 35303 | 1157.8 | 24882.8 | 10420.2 | FY26
PO 33527034918 | 2026-07-22 | Roll to FY27 | 0 | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  |  |  | 35303 |  | 24882.8 | 10420.2
|  | Totals: | 35303 |  | 24882.8 |  | 10420.2
|  | Design Development Docs | 12026 |  | 12026 |  | 0
|  | Construction Docs | 9472 |  | 9472 |  | 0
|  | Bidding/Negotiation | 2227 |  | 2227 |  | 0
|  | Construction Phase | 11578 |  | 1157.8 |  | 10420.2
|  | Total: | 35303 |  | 24882.8 |  | 10420.2

## #9511.00 Terracon Consultants
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
Terracon Consultants |  |  | Vendor: 00002116513
Acct. Codes-0017-335-MM26-9260 |  |  | MA25049
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33526062913 | 2026-03-03 | DO Procore | 5825 | 5825 |  |  | 5825
DO 33526062913 | 2026-05-20 | CO #1 | -1014.5 | 4810.5 |  | 0 | 4810.5
PRC 3352606PA2913 | 2026-05-29 | Inv. TQ61650 |  | 4810.5 | 4810.5 | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  |  |  | 4810.5 |  | 4810.5 | 0
|  | Totals: | 4810.5 |  | 4810.5 |  | 0 | FINAL
|  | Line 2 - Moisture test 12@15 | 180 |  | 180 |  | 0
|  | Line 2 - Atterberg Limits 0@130 | 0 |  |  |  | 0
|  | Line 3 - Standard Penetration 4.5@70 | 315 |  | 315 |  | 0
|  | Line 5 - Labor Project Mngr 18.25@130 | 2372.5 |  | 2372.5 |  | 0
|  | Line 6 - Labor Testing 19.75@70 | 1382.5 |  | 1382.5 |  | 0
|  | Line 7 - 81 Miles @.05 | 40.5 |  | 40.5 |  | 0
|  | Line 8 - Specialized vehicles 1@520 | 520 |  | 520 |  | 0
CO #1 adjustments in the lines
|  | Total: | 4810.5 |  | 4810.5 |  | 0

## #9511.00 McGough Construction 2
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
McGough Construction (2) |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526160908 | 2026-06-09 | PO Procore | 30776.85 | 30776.85 |  |  | 30776.85
PRC 3352616PA0908 | 2026-07-13 | Inv. 101537.003-CA01 |  | 30776.85 | 1364.97 | 1364.97 | 29411.88 | FY26
PO 33527160908 | 2026-07-22 | Roll to FY27 | 0 | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  |  |  | 30776.85 |  | 1364.97 | 29411.88
|  | Totals: | 30776.85 |  | 1364.97 |  | 29411.88
|  | CM Services | 29236.85 |  | 1224.97 |  | 28011.88
|  | Reimbursables | 1540 |  | 140 |  | 1400
|  | Total: | 30776.85 |  | 1364.97 |  | 29411.88

## #9511.00 Jones Contracting
DPS P13 Upper Parking Lot Replacement
Project # 9511.00
Program code 951100 |  |  | Major Program 4E12
Jones Contracting Corp |  |  | Vendor: 00003084562
Acct. Codes-0017-335-MM26-9255 |  |  | RFB951100-01
Project Manager - Brandon A. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526166907 | 2026-06-15 | PO Procore | 141165.26 | 141165.26 |  |  | 141165.26
PRC 3352616PA6907 | 2026-06-30 | Inv. 19-1894 |  | 141165.26 | 959.94 | 959.94 | 140205.32 | 29.69 | FY26
PO 33527166907 | 2026-07-22 | Roll to FY27 | 0 | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  |  |  | 141165.26 |  | 959.94 | 140205.32
|  | Totals: | 141165.26 |  | 959.94 |  | 140205.32

## RECAP #9512.00
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
| Program code 951200 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager -Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 32103.42
C | Larson Engineering |  | 5820 | 5820 | 0
C | PM TIME |  | 9299.81 | 9299.81 | 0
C | Misc. |  | 0 | 0 | 0
C | Boyd Jones |  | 4851.13 | 4851.13 | 0
C | Boyd Jones (2) |  | 12132.48 | 12132.48 | 0
| Total Project Cost | 32103.42 | 32103.42 | 32103.42 | 3.638e-12 | 0
Closed 07/15/26

## #9512.00 Larson Engineering
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  | Major Program 4E19
Larson Engineering |  |  | Vendor: VS000002162
Acct. Codes-0017-335-MM26-9260 |  |  | 949900-01
Project Manager -Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526023913 | 2026-01-23 | PO Procore | 5820 | 5820 |  |  | 5820
PRC 3352602PA3913 | 2026-03-31 | Inv. 9512.00-01 |  | 5820 | 2075 | 2075 | 3745
PRC 3352602PB3913 | 2026-04-02 | Inv. 9512.00-02 |  | 5820 | 2055 | 4130 | 1690
PRC 3352602PC3913 | 2026-05-20 | Inv. 9512.00-03 |  | 5820 | 515 | 4645 | 1175
PRC 3352602PD3913 | 2026-05-27 | Inv. 9512.00-04 |  | 5820 | 117.5 | 4762.5 | 1057.5
PRC 3352602PE3913 | 2026-07-14 | Inv. 9512.00-05 - Final |  | 5820 | 1057.5 | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  |  |  | 5820 |  | 5820 | 0
|  | Totals: | 5820 |  | 5820 |  | 0 | FINAL
|  | Topographic Survey | 900 |  | 900 |  | 0
|  | Design Development | 1175 |  | 1175 |  | 0
|  | Construction Documents | 2055 |  | 2055 |  | 0
|  | Bidding/Negotiation | 515 |  | 515 |  | 0
|  | Construction Phase | 1175 |  | 1175 |  | 0
|  | Total: | 5820 |  | 5820 |  | 0

## #9512.00 PM TIME
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735B
Project Manager -Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 9299.81 | 9299.81 |  |  | 9299.81
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 9299.81 | 91 | 91 | 9208.81
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 9299.81 | 1384.8 | 1475.8 | 7824.01
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 9299.81 | 147.18 | 1622.98 | 7676.83
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 9299.81 | 669.9 | 2292.88 | 7006.93
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 9299.81 | 38.27 | 2331.15 | 6968.66
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 9299.81 | 435.2 | 2766.35 | 6533.46
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 9299.81 | 61.64 | 2827.99 | 6471.82
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 9299.81 | 764.4 | 3592.39 | 5707.42
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 9299.81 | 77.35 | 3669.74 | 5630.07
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 9299.81 | 891.2 | 4560.94 | 4738.87
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 9299.81 | 121.29 | 4682.23 | 4617.58
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 9299.81 | 985.1 | 5667.33 | 3632.48
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 9299.81 | 99.91 | 5767.24 | 3532.57
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 9299.81 | 1045.1 | 6812.34 | 2487.47
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 9299.81 | 112.05 | 6924.39 | 2375.42
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 9299.81 | 1372.6 | 8296.99 | 1002.82
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 9299.81 | 78.07 | 8375.06 | 924.75
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 9299.81 | 893.8 | 9268.86 | 30.95
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 9299.81 | 30.95 | 9299.81 | 1.1831e-12
|  |  | Totals: | 9299.81 |  | 9299.81 |  | 0
Note on E9: Huggins, Joni [DAS]: Re: February PM Time Posted $Joni Shimp, Oliver Mar 13, 2026, 8:26 AM (3 days ago) to me Good Morning, Thank for you the list, could you please make the following adjustments? DA25 9358.01 $(361.98) Please move $5,000.00 from unallocated to PM Time DA26 9534.00 $(298.97) Please move $5,000.00 from unallocated to PM Time MM24 9226.00 $(290.03) Please move $5,000.00 from unallocated to PM Time. MM24 9392.00 $(264.99) Please move $3,000 from unallocated to PM Time MM25 9451.00 $(130.91) Please move $2,000.00 from unallocated to PM Time MM26 9491.00 $(646.75) Please move $5,000.00 from unallocated to PM Time MM26 9512.00 $(560.94) Please move $5,000 from unallocated to PM Time X674 9464.00 $(96.94) I'll have Brent add additional $100 to this project. Thank you, Oliver Shimp

## #9512.00 Misc
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 220
Project Manager -Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9512.00 Boyd Jones
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  | Major Program 4E19
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager -Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526090908 | 2026-03-31 | PO Procore | 4929.04 | 4929.04 |  |  | 4929.04
PRC 3352609PA0908 | 2026-04-17 | Inv. 9512.00-01 |  | 4929.04 | 4851.13 | 4851.13 | 77.91
PO 33526090908 | 2026-07-13 | Closing PO Per PM | -77.91 | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  |  |  | 4851.13 |  | 4851.13 | -1.4211e-13
|  | Totals: | 4851.13 |  | 4851.13 |  | 0 | FINAL
|  | CM Services | 4848.13 |  | 4848.13 |  | 0
|  | Reimbursable | 3 |  | 3 |  | 0
|  | Total: | 4851.13 |  | 4851.13 |  | 0

## #9512.00 Boyd Jones (2)
IDOE IPBS 6450 Corporate Drive Repair Auditorium Exterior Fire Exit
Project # 9512.00
Program code 951200 |  |  | Major Program 4E19
Boyd Jones(2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager -Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526126921 | 2026-05-06 | PO Procore | 12210.48 | 12210.48 |  |  | 12210.48
PRC 3352612PA6921 | 2026-05-12 | Inv. 9512.00-001 |  | 12210.48 | 3712.5 | 3712.5 | 8497.98
PRC 3352612PB6921 | 2026-06-26 | Inv. 9512.00-002 |  | 12210.48 | 6430.05 | 10142.55 | 2067.93
PRC 3352612PC6921 | 2026-07-07 | Inv. 9512.00-003-FINAL | -78 | 12132.48 | 1989.93 | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  |  |  | 12132.48 |  | 12132.48 | -6.8212e-13
|  | Totals: | 12132.48 |  | 12132.48 |  | 0 | FINAL
|  | CM Services | 12129.48 |  | 12129.48 |  | 0
|  | Reimbursable | 3 |  | 3 |  | 0
|  | Total: | 12132.48 |  | 12132.48 |  | 0
Inv. 9512.00-0X was used in a previous tab by this vendor, please use 9512.00-00X

## RECAP #9513.00
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
| Program code 951300 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 640000
C | DCI Group |  | 21492.29 | 21492.29 | 0
| PM TIME |  | 20000 | 9855.41 | 10144.59
| Misc. |  | 2157 | 2157 | 0
| Kezlo Group |  | 54900 | 41900 | 13000
| Bi-State Masonry |  | 314709 | 0 | 314709
| Total Project Cost | 640000 | 413258.29 | 75404.7 | 337853.59 | 226741.71

## #9513.00 DCI Group
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  | Major Program 4E10
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526344905 | 2025-12-10 | PO Procore | 22074.79 | 22074.79 |  |  | 22074.79
PRC 3352634PA4905 | 2026-01-21 | Inv. 9513.00 PC 01 |  | 22074.79 | 4109.38 | 4109.38 | 17965.41
PRC 3352634PB4905 | 2026-02-16 | Inv. 9513.00 PC 02 |  | 22074.79 | 894.15 | 5003.53 | 17071.26
PRC 3352634PC4905 | 2026-03-24 | Inv. 9513.00 PC 03 |  | 22074.79 | 2460.08 | 7463.61 | 14611.18
PRC 3352634PD4905 | 2026-04-15 | Inv. 9513.00 PC 04 |  | 22074.79 | 3817.41 | 11281.02 | 10793.77
PRC 3352634PE4905 | 2026-05-21 | Inv. 9513.00 PC #05 |  | 22074.79 | 6818.4 | 18099.42 | 3975.37
PRC 3352634PF4905 | 2026-06-16 | Inv. 9513.00 PC #06 |  | 22074.79 | 1808.58 | 19908 | 2166.79
PRC 3352634PG4905 | 2026-07-13 | Inv. 9513.00 PC 07 FINAL | -582.5 | 21492.29 | 1584.29 | 21492.29 | -9.0949e-13
|  |  |  | 21492.29 |  | 21492.29 | -9.0949e-13
|  |  |  | 21492.29 |  | 21492.29 | -9.0949e-13
|  |  |  | 21492.29 |  | 21492.29 | -9.0949e-13
|  |  |  | 21492.29 |  | 21492.29 | -9.0949e-13
|  |  |  | 21492.29 |  | 21492.29 | -9.0949e-13
|  | Totals: | 21492.29 |  | 21492.29 |  | 0 | FINAL
|  | CM Services | 20574.79 |  | 20574.79 |  | 0
|  | Reimbursables | 917.5 |  | 917.5 |  | 0
|  | Total: | 21492.29 |  | 21492.29 |  | 0

## #9513.00 PM TIME
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 735C
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 20000 | 39.99 | 39.99 | 19960.01
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 20000 | 398.7 | 438.69 | 19561.31
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 20000 | 160.17 | 598.86 | 19401.14
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 20000 | 1019.8 | 1618.66 | 18381.34
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 20000 | 73.99 | 1692.65 | 18307.35
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 20000 | 836.5 | 2529.15 | 17470.85
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 20000 | 92.08 | 2621.23 | 17378.77
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 20000 | 1138.9 | 3760.13 | 16239.87
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 95.57 | 3855.7 | 16144.3
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 1102.8 | 4958.5 | 15041.5
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 181.78 | 5140.28 | 14859.72
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 1474.3 | 6614.58 | 13385.42
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 20000 | 146.77 | 6761.35 | 13238.65
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 20000 | 1531 | 8292.35 | 11707.65
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 20000 | 43.17 | 8335.52 | 11664.48
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 20000 | 527.5 | 8863.02 | 11136.98
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 20000 | 66.16 | 8929.18 | 11070.82
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 20000 | 899.5 | 9828.68 | 10171.32
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 20000 | 26.73 | 9855.41 | 10144.59
|  |  | Totals: | 20000 |  | 9855.41 |  | 10144.59
Note on E9: Huggins, Joni [DAS]: PM Time Budgets to Establish $Joni Elliott, Jennie Nov 2, 2025, 4:38 PM (2 days ago) to me Please establish a PM Time budget in these projects as follows: 9496.00 - NCCF Replace Window in Educ. Bldg - $10,000.00 9501.00 - NCCF Air Handler Replacement Units A & B - $10,000.00 9505.00 - FDCF Sally Port Operator Replace - $11,800.00 9513.00 - CHMHI Tuckpointing Phase 2.2 - $20,000.00 Thank you, Jennie Elliott

## #9513.00 Misc
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  |  | Major Program 4E10
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 548
Project Manager - Jennie E.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526166910 | 2026-06-15 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2716054 | 1757 | 1757
PRC 33526174920 | 06/23/26 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2898 | 200 | 1957
PRC 33526201903 | 2026-07-20 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2991 | 200 | 2157
2157
2157
2157
2157
2157
2157
2157
2157
2157
|  |  |  | Totals: |  | 2157

## #9513.00 Kezlo Group
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  | Major Program 4E10
Kezlo Group |  |  | Vendor: 00003234487
Acct. Codes-0017-335-MM26-9260 |  |  | RFP951300-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526007911 | 2026-01-07 | PO Procore | 54900 | 54900 |  |  | 54900
PRC 3352600PA7911 | 2026-02-24 | Inv. 25-139.01 |  | 54900 | 24800 | 24800 | 30100
PRC 3352600PB7911 | 2026-04-13 | Inv. 25-139.02 |  | 54900 | 15200 | 40000 | 14900
PRC 3352600PC7911 | 2026-05-06 | Inv 9513.00-03 |  | 54900 | 1900 | 41900 | 13000 | FY26
PO 33527007911 | 2026-07-22 | Roll to FY27 | 0 | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  |  |  | 54900 |  | 41900 | 13000
|  | Totals: | 54900 |  | 41900 |  | 13000
|  | 50% CD's | 24800 |  | 24800 |  | 0
|  | 100% CD's | 15200 |  | 15200 |  | 0
|  | Bidding/Negotiation | 1900 |  | 1900 |  | 0
|  | Construction Phase | 13000 |  |  |  | 13000
|  | Total: | 54900 |  | 41900 |  | 13000

## #9513.00 Bi-State Masonry
HHS CHMHI Tuckpointing Phase 2.2
Project # 9513.00
Program code 951300 |  |  | Major Program 4E10
Bi-State Masonry |  |  | Vendor: 00002141136
Acct. Codes-0017-335-MM26-9255 |  |  | RFB951300-02
Project Manager - Jennie E. |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527208913 | 2026-07-27 | PO Procore | 314709 | 314709 |  |  | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  |  |  | 314709 |  | 0 | 314709
|  | Totals: | 314709 |  | 0 |  | 314709

## RECAP #9514.00
DAS Union Sunday School Structural Investigation
Project # 9514.00
| Program code 951400 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM26
Project Manager - Geoff W
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 8573.08
C | Horizon Architecture |  | 6765 | 6765 | 0
C | PM TIME |  | 1808.08 | 1808.08 | 0
C | Misc. |  | 0 | 0 | 0
| Total Project Cost | 8573.08 | 8573.08 | 8573.08 | 0 | 0
Closed 06/18/26

## #9514.00 Horizon Architecture
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  | Major Program 4E19
Horizon Architecture |  |  | Vendor: 00003108847
Acct. Codes-0017-335-MM26-9260 |  |  | SRVV5
Project Manager - Geoff W |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526287905 | 2025-10-14 | PO Procore | 6765 | 6765 |  |  | 6765
PRC 3352628PA7905 | 2026-02-16 | Inv. 9514.00-01 |  | 6765 | 6426.75 | 6426.75 | 338.25
PRC 3352628PB7905 | 2026-06-15 | Inv. 9514.00-02 - Final |  | 6765 | 338.25 | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  |  |  | 6765 |  | 6765 | 0
|  | Totals: | 6765 |  | 6765 |  | 0 | FINAL

## #9514.00 PM TIME
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS: 735D
Project Manager - Geoff W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 1808.08 | 1808.08 |  |  | 1808.08
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 1808.08 | 128.13 | 128.13 | 1679.95
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 1808.08 | 1272.7 | 1400.83 | 407.25
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 1808.08 | 128.13 | 1528.96 | 279.12
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 1808.08 | -128.13 | 1400.83 | 407.25
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 1808.08 | 71.5 | 1472.33 | 335.75
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 1808.08 | -71.5 | 1400.83 | 407.25
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 1808.08 | 15.22 | 1416.05 | 392.03
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 1808.08 | 174.4 | 1590.45 | 217.63
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 1808.08 | 16.43 | 1606.88 | 201.2
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 1808.08 | 201.2 | 1808.08 | -2.558e-13
[5 empty] | 1808.08 |  | 1808.08 | -2.558e-13
[5 empty] | 1808.08 |  | 1808.08 | -2.558e-13
[5 empty] | 1808.08 |  | 1808.08 | -2.558e-13
[5 empty] | 1808.08 |  | 1808.08 | -2.558e-13
[5 empty] | 1808.08 |  | 1808.08 | -2.558e-13
|  |  | Totals: | 1808.08 |  | 1808.08 |  | 0
Note on E9: Huggins, Joni [DAS]: Shimp, Oliver Nov 10, 2025, 3:36 PM (2 days ago) to me Good Afternoon Joni, Thank you for putting these together, Could you please make the following adjustments to these projects? DA25 9358.01 (154.79) Please increase the PM time budget for this project by $500.00 to $5,557.50 from the unallocated budget. MM24 9386.01 (988.08) Please increase the PM time budget by $3,000.00 to $25,450.87 from the unallocated budget. MM24 9393.00 (532.02) Please ask James Trower to confirm this project PM time cost MM26 9491.00 (101.20) Please increase the PM time budget by $5,000.00 to $10,000.00 from the unallocated budget. MM26 9497.00 (858.68) Please increase the PM time budget by $10,000.00 to $10,000.00 from the unallocated budget. MM26 9514.00 (1,400.83) Please increase the PM time budget by $2,000.00 to $2,000.00 from the unallocated budget. Shimp, Oliver ​DAS Finance Payables Infrastructure​ ​Wheelock, Geoff​ Good Morning, Project MM26 9514.00 DAS Union Sunday School Investigation can be closed. PM Time and Misc. Contracts are all final completed. Please return any remaining funds to the MM26 funding pool. Thank you, Oliver Shimp

## #9514.00 Misc
DAS Union Sunday School Structural Investigation
Project # 9514.00
Program code 951400 |  |  |  | Major Program 4E19
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: C16
Project Manager - Geoff W
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9519.00
HHS IMHI Infirmary Building Roof Repair
Project # 9519.00
Program code 951900 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - James T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
Story Construction |  | 26248.22 | 8175.63 | 18072.59
PM TIME |  | 20000 | 8137.5 | 11862.5
Misc. |  | 0 | 0 | 0
10Fold Architecture + Engineering |  | 27592 | 10264.2 | 17327.8
Total Project Cost | 250000 | 73840.22 | 26577.33 | 47262.89 | 176159.78

## #9519.00 Story Construction
HHS IMHI Infirmary Building Roof Repair
Project # 9519.00
Program code 951900 |  |  | Major Program 4E02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - James T. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526092911 | 2026-04-02 | PO Procore | 26248.22 | 26248.22 |  |  | 26248.22
PRC 3352609PA2911 | 2026-05-28 | Inv. 35267 |  | 26248.22 | 1046.24 | 1046.24 | 25201.98
PRC 3352609PB2911 | 2026-06-17 | Inv. 35303 |  | 26248.22 | 3808.01 | 4854.25 | 21393.97
PRC 3352609PC2911 | 2026-07-15 | Inv. 35347 |  | 26248.22 | 3321.38 | 8175.63 | 18072.59 | FY26
PO 33527092911 | 2026-07-22 | Roll to FY27 | 0 | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  |  |  | 26248.22 |  | 8175.63 | 18072.59
|  | Totals: | 26248.22 |  | 8175.63 |  | 18072.59
|  | CM Services | 25891.22 |  | 7937.63 |  | 17953.59
|  | Reimbursables | 357 |  | 238 |  | 119
|  | Total: | 26248.22 |  | 8175.63 |  | 18072.59

## #9519.00 PM TIME
HHS IMHI Infirmary Building Roof Repair
Project # 9519.00
Program code 951900 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911J
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 20000 | 15.35 | 15.35 | 19984.65
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 20000 | 178.8 | 194.15 | 19805.85
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 20000 | 66.22 | 260.37 | 19739.63
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 20000 | 537.4 | 797.77 | 19202.23
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 20000 | 48.08 | 845.85 | 19154.15
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 20000 | 501.2 | 1347.05 | 18652.95
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 20000 | 217.04 | 1564.09 | 18435.91
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 20000 | 2658.8 | 4222.89 | 15777.11
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 20000 | 302.46 | 4525.35 | 15474.65
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 20000 | 3490.5 | 8015.85 | 11984.15
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 20000 | 121.65 | 8137.5 | 11862.5
[5 empty] | 20000 |  | 8137.5 | 11862.5
|  |  | Totals: | 20000 |  | 8137.5 |  | 11862.5
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trower, James ​Huggins, Joni;​DAS Finance Payables Infrastructure​ Finance - Please increase PM Time by $15,000 for project 9519.00 (MM26) Thanks, James Trower, Licensed Architect, LEED AP

## #9519.00 Misc
HHS IMHI Infirmary Building Roof Repair
Project # 9519.00
Program code 951900 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 556
Project Manager - James T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9519.00 10Fold Architecture
HHS IMHI Infirmary Building Roof Repair
Project # 9519.00
Program code 951900 |  |  | Major Program 4E02
10Fold Architecture + Engineering |  |  | Vendor: 00003101228
Acct. Codes-0017-335-MM26-9260 |  |  | 951900-01
Project Manager - James T. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526166905 | 2026-06-15 | PO Procore | 27592 | 27592 |  |  | 27592
PRC 3352616PA6905 | 2026-07-06 | Inv. 9519.00-01 |  | 27592 | 10264.2 | 10264.2 | 17327.8 | FY26
PO 33527166905 | 2026-07-22 | Roll to FY27 | 0 | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  |  |  | 27592 |  | 10264.2 | 17327.8
|  | Totals: | 27592 |  | 10264.2 |  | 17327.8
|  | Construction Documents | 17107 |  | 10264.2 |  | 6842.8
|  | Bidding Assistance | 3035 |  |  |  | 3035
|  | Construction Phase | 7450 |  |  |  | 7450
|  | Total: | 27592 |  | 10264.2 |  | 17327.8

## RECAP #9521.00
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
| Program code 952100 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 800000
C | Boyd Jones |  | 13757.74 | 13757.74 | 0
| PM TIME |  | 45000 | 11254.49 | 33745.51
| Misc. |  | 200 | 200 | 0
| Genesis Architectural |  | 22700 | 15800 | 6900
| Academy Roofing |  | 534000 | 0 | 534000
| Boyd Jones(2) |  | 60330.82 | 0 | 60330.82
| Total Project Cost | 800000 | 675988.56 | 41012.23 | 634976.33 | 124011.44

## #9521.00 Boyd Jones
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  | Major Program 4E02
Boyd Jones |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526054910 | 2026-02-23 | PO Procore | 14752.31 | 14752.31 |  |  | 14752.31
PRC 3352605PA4910 | 2026-04-20 | Inv. 9521.00-01 |  | 14752.31 | 1431.36 | 1431.36 | 13320.95
PRC 3352605PB4910 | 2026-05-11 | Inv. 9521.00-02 |  | 14752.31 | 1934.21 | 3365.57 | 11386.74
PRC 3352605PC4910 | 2026-06-30 | Inv. 9521.00-03 |  | 14752.31 | 4048.67 | 7414.24 | 7338.07
PRC 3352605PD4910 | 2026-07-10 | Inv. 9521.00-04 - Final | -994.57 | 13757.74 | 6343.5 | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  |  |  | 13757.74 |  | 13757.74 | -2.16e-12
|  | Totals: | 13757.74 |  | 13757.74 |  | 0 | FINAL
|  | CM Services | 13702.24 |  | 13702.24 |  | 0
|  | Reimbursables | 55.5 |  | 55.5 |  | 0
|  | Total: | 13757.74 |  | 13757.74 |  | 0

## #9521.00 PM TIME
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911L
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 45000 | 45000 |  |  | 45000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 45000 | 137.72 | 137.72 | 44862.28
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 45000 | 1585 | 1722.72 | 43277.28
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 45000 | 354.38 | 2077.1 | 42922.9
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 45000 | 2904 | 4981.1 | 40018.9
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 45000 | 254.07 | 5235.17 | 39764.83
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 45000 | 2651.1 | 7886.27 | 37113.73
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 45000 | 117.01 | 8003.28 | 36996.72
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 45000 | 1431.6 | 9434.88 | 35565.12
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 45000 | 140.92 | 9575.8 | 35424.2
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 45000 | 1621.9 | 11197.7 | 33802.3
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 45000 | 56.79 | 11254.49 | 33745.51
[5 empty] | 45000 |  | 11254.49 | 33745.51
|  |  | Totals: | 45000 |  | 11254.49 |  | 33745.51

## #9521.00 Misc
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  |  | Major Program 4E02
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 1515
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33526174912 | 2026-06-23 | 9500 | CNST | Rapids Reproductions V#(00002111375) | Inv. INVCL2903 | 200 | 200
200
200
200
200
200
200
200
200
200
200
200
|  |  |  | Totals: |  | 200

## #9521.00 Genesis Architectural
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  | Major Program 4E02
Genesis Architectural |  |  | Vendor: 00002092152
Acct. Codes-0017-335-MM26-9260 |  |  | 952100-01
Project Manager - Brandon A |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526092909 | 2026-04-02 | PO Procore | 22700 | 22700 |  |  | 22700
PRC 3352609PA2909 | 2026-06-26 | Inv. 2604-01 |  | 22700 | 6600 | 6600 | 16100
PRC 3352609PB2909 | 2026-07-07 | Inv. 2604-02 |  | 22700 | 9200 | 15800 | 6900 | FY26
PO 33527092909 | 2026-07-22 | Roll to FY27 | 0 | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  |  |  | 22700 |  | 15800 | 6900
|  | Totals: | 22700 |  | 15800 |  | 6900
|  | Design Development Phase | 6600 |  | 6600 |  | 0
|  | Construction Docs | 7600 |  | 7600 |  | 0
|  | Bid Phase | 1600 |  | 1600 |  | 0
|  | Construction Phase | 6900 |  |  |  | 6900
|  | Total: | 22700 |  | 15800 |  | 6900

## #9521.00 Academy Roofing
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  | Major Program 4E02
Academy Roofing |  |  | Vendor: 00003010234
Acct. Codes-0017-335-MM26-9255 |  |  | RFP952100-01
Project Manager - Brandon A |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526176918 | 2026-06-25 | PO Procore | 534000 | 534000 |  |  | 534000 | FY26
PO 33527176918 | 2026-07-28 | Roll to FY27 | 0 | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  |  |  | 534000 |  | 0 | 534000
|  | Totals: | 534000 |  | 0 |  | 534000

## #9521.00 Boyd Jones (2)
DPS D1 1333 Ohio Roof Replacement
Project # 9521.00
Program code 952100 |  |  | Major Program 4E02
Boyd Jones(2) |  |  | Vendor: 00003193325
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-BoydJones11012021
Project Manager - Brandon A |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526190910 | 2026-07-09 | PO Procore | 60330.82 | 60330.82 |  |  | 60330.82 | FY26
PO 33527190910 | 2026-07-28 | Roll to FY27 | 0 | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  |  |  | 60330.82 |  | 0 | 60330.82
|  | Totals: | 60330.82 |  | 0 |  | 60330.82
|  | CM Services | 32580.82 |  |  |  | 32580.82
|  | Reimbursables | 1050 |  |  |  | 1050
|  | Fee | 26700 |  |  |  | 26700
|  | Total: | 60330.82 |  | 0 |  | 60330.82

## RECAP #9524.00
DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair
Project # 9524.00
Program code 952400 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
McGough Construction |  | 18911.31 | 4065.85 | 14845.46
PM TIME |  | 10000 | 7935.65 | 2064.35
Misc. |  | 0 | 0 | 0
Shive Hattery |  | 42000 | 0 | 42000
Total Project Cost | 250000 | 70911.31 | 12001.5 | 58909.81 | 179088.69

## #9524.00 McGough Construction
DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair
Project # 9524.00
Program code 952400 |  |  | Major Program 4E01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526174919 | 2026-06-23 | PO Procore | 18911.31 | 18911.31 |  |  | 18911.31
PRC 3352617PA4919 | 2026-07-13 | Inv. 101537.013PC-01 |  | 18911.31 | 4065.85 | 4065.85 | 14845.46 | FY26
PO 33527174919 | 2026-07-28 | Roll to FY27 | 0 | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  |  |  | 18911.31 |  | 4065.85 | 14845.46
|  | Totals: | 18911.31 |  | 4065.85 |  | 14845.46
|  | CM Services | 18136.31 |  | 3995.85 |  | 14140.46
|  | Reimbursables | 775 |  | 70 |  | 705
|  | Total: | 18911.31 |  | 4065.85 |  | 14845.46

## #9524.00 PM TIME
DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair
Project # 9524.00
Program code 952400 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911O
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10000 | 52.54 | 52.54 | 9947.46
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10000 | 610.7 | 663.24 | 9336.76
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10000 | 98.12 | 761.36 | 9238.64
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10000 | 797.6 | 1558.96 | 8441.04
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 10000 | 145.56 | 1704.52 | 8295.48
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10000 | 1513.5 | 3218.02 | 6781.98
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10000 | 121.98 | 3340 | 6660
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 1496.1 | 4836.1 | 5163.9
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 10000 | 239.93 | 5076.03 | 4923.97
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 10000 | 2763.5 | 7839.53 | 2160.47
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 10000 | 96.12 | 7935.65 | 2064.35
[5 empty] | 10000 |  | 7935.65 | 2064.35
|  |  | Totals: | 10000 |  | 7935.65 |  | 2064.35

## #9524.00 Misc
DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair
Project # 9524.00
Program code 952400 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9524.00 Shive Hattery
DOC ASP SallyPort Tunnel & Living Unit B Tunnel Repair
Project # 9524.00
Program code 952400 |  |  | Major Program 4E01
Shive Hattery |  |  | Vendor: 00002108803
Acct. Codes-0017-335-MM26-9260 |  |  | RFP952400-01
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527208912 | 2026-07-27 |  | 42000 | 42000 |  |  | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  |  |  | 42000 |  | 0 | 42000
|  | Totals: | 42000 |  | 0 |  | 42000
|  | Design Development Documents | 18000 |  |  |  | 18000
|  | Construction Documents | 13000 |  |  |  | 13000
|  | Bidding Assistance | 1000 |  |  |  | 1000
|  | Construction Phase & Closeout | 10000 |  |  |  | 10000
|  | Total: | 42000 |  | 0 |  | 42000

## RECAP #9527.00
HHS CHMHI Four Corners Elevator Replacement
Project # 9527.00
Program code 952700 |  |  | Major Program 4D03
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 500000
DCI Group |  | 30675.76 | 4673.69 | 26002.07
PM TIME |  | 10000 | 3477.73 | 6522.27
Misc. |  | 0 | 0 | 0
CMBA Architects |  | 58810 | 18615 | 40195
Total Project Cost | 500000 | 99485.76 | 26766.42 | 72719.34 | 400514.24

## #9527.00 DCI Group
HHS CHMHI Four Corners Elevator Replacement
Project # 9527.00
Program code 952700 |  |  | Major Program 4D03
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526113911 | 2026-04-24 | PO Procore | 30675.76 | 30675.76 |  |  | 30675.76
PRC 3352611PA3911 | 2026-05-22 | Inv. 9527.00 PC #01 |  | 30675.76 | 2598.28 | 2598.28 | 28077.48
PRC 3352611PB3911 | 2026-06-18 | Inv. 9527.00 PC #02 |  | 30675.76 | 1043.64 | 3641.92 | 27033.84
PRC 3352611PC3911 | 2026-07-10 | Inv. 9527.00 PC #03 |  | 30675.76 | 1031.77 | 4673.69 | 26002.07 | FY26
PO 33527113911 | 2026-07-22 | Roll to FY27 | 0 | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  |  |  | 30675.76 |  | 4673.69 | 26002.07
|  | Totals: | 30675.76 |  | 4673.69 |  | 26002.07
|  | CM Services | 29175.76 |  | 4549.69 |  | 24626.07
|  | Reimbursables | 1500 |  | 124 |  | 1376
|  | Total: | 30675.76 |  | 4673.69 |  | 26002.07

## #9527.00 PM TIME
HHS CHMHI Four Corners Elevator Replacement
Project # 9527.00
Program code 952700 |  |  |  | Major Program 4D03
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911R
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 10000 | 10000 |  |  | 10000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 10000 | 37.63 | 37.63 | 9962.37
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 10000 | 431.4 | 469.03 | 9530.97
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 10000 | 88.19 | 557.22 | 9442.78
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 10000 | 716.1 | 1273.32 | 8726.68
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 10000 | 58.77 | 1332.09 | 8667.91
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 10000 | 612.3 | 1944.39 | 8055.61
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 10000 | 39.41 | 1983.8 | 8016.2
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 10000 | 478.3 | 2462.1 | 7537.9
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 10000 | 73.99 | 2536.09 | 7463.91
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 10000 | 911.6 | 3447.69 | 6552.31
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 10000 | 30.04 | 3477.73 | 6522.27
[5 empty] | 10000 |  | 3477.73 | 6522.27
|  |  | Totals: | 10000 |  | 3477.73 |  | 6522.27

## #9527.00 Misc
HHS CHMHI Four Corners Elevator Replacement
Project # 9527.00
Program code 952700 |  |  |  | Major Program 4D03
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 548
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9527.00 CMBA Architects
HHS CHMHI Four Corners Elevator Replacement
Project # 9527.00
Program code 952700 |  |  | Major Program 4D03
CMBA Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM26-9260 |  |  | RFP952700-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526140914 | 2026-05-20 | PO Procore | 58810 | 58810 |  |  | 58810
PRC 3352614PA0914 | 2026-06-19 | Inv. 67483 |  | 58810 | 3877.5 | 3877.5 | 54932.5
PRC 3352614PB0914 | 2026-07-06 | Inv. 67578 |  | 58810 | 14737.5 | 18615 | 40195 | FY26
PO 33527140914 | 2026-07-22 | Roll to FY27 | 0 | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  |  |  | 58810 |  | 18615 | 40195
|  | Totals: | 58810 |  | 18615 |  | 40195
|  | Construction Docs | 37230 |  | 18615 |  | 18615
|  | Bidding/Negotiation | 6200 |  |  |  | 6200
|  | Construction Phase | 15380 |  |  |  | 15380
|  | Total: | 58810 |  | 18615 |  | 40195

## RECAP #9529.00
HHS CHMHI Wirth Hall Tunnel Repairs
Project # 9529.00
Program code 952900 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 800000
DCI Group |  | 32405.88 | 4168.29 | 28237.59
PM TIME |  | 22000 | 2991.78 | 19008.22
Misc. |  | 0 | 0 | 0
CMB Architects |  | 76360 | 7934.5 | 68425.5
Total Project Cost | 800000 | 130765.88 | 15094.57 | 115671.31 | 669234.12

## #9529.00 DCI Group
HHS CHMHI Wirth Hall Tunnel Repairs
Project # 9529.00
Program code 952900 |  |  | Major Program 4G01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526113910 | 2026-04-24 | PO Procore | 32405.88 | 32405.88 |  |  | 32405.88
PRC 3352611PA3910 | 2026-05-22 | Inv. 9529.00 PC #01 |  | 32405.88 | 2642.99 | 2642.99 | 29762.89
PRC 3352611PB3910 | 2026-06-18 | Inv. 9529.00 PC #02 |  | 32405.88 | 1167.64 | 3810.63 | 28595.25
PRC 3352611PC3910 | 2026-07-10 | Inv. 9529.00 PC #03 |  | 32405.88 | 357.66 | 4168.29 | 28237.59 | FY26
PO 33527113910 | 2026-07-22 | Roll to FY27 | 0 | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  |  |  | 32405.88 |  | 4168.29 | 28237.59
|  | Totals: | 32405.88 |  | 4168.29 |  | 28237.59
|  | CM Services | 30905.88 |  | 3920.29 |  | 26985.59
|  | Reimbursables | 1500 |  | 248 |  | 1252
|  | Total: | 32405.88 |  | 4168.29 |  | 28237.59

## #9529.00 PM TIME
HHS CHMHI Wirth Hall Tunnel Repairs
Project # 9529.00
Program code 952900 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911T
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22000 | 22000 |  |  | 22000
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 22000 | 37.63 | 37.63 | 21962.37
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 22000 | 431.4 | 469.03 | 21530.97
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 22000 | 98.56 | 567.59 | 21432.41
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 22000 | 800.3 | 1367.89 | 20632.11
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 22000 | 71.12 | 1439.01 | 20560.99
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 22000 | 743.6 | 2182.61 | 19817.39
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 22000 | 46.92 | 2229.53 | 19770.47
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 22000 | 574.5 | 2804.03 | 19195.97
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 22000 | 7.84 | 2811.87 | 19188.13
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 22000 | 176.6 | 2988.47 | 19011.53
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 22000 | 3.31 | 2991.78 | 19008.22
[5 empty] | 22000 |  | 2991.78 | 19008.22
|  |  | Totals: | 22000 |  | 2991.78 |  | 19008.22

## #9529.00 Misc
HHS CHMHI Wirth Hall Tunnel Repairs
Project # 9529.00
Program code 952900 |  |  |  | Major Program 4G01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 548
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9529.00 CMB Architects
HHS CHMHI Wirth Hall Tunnel Repairs
Project # 9529.00
Program code 952900 |  |  | Major Program 4G01
CMB Architects |  |  | Vendor: 00003050901
Acct. Codes-0017-335-MM26-9260 |  |  | RFP952900-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526134910 | 2026-05-14 | PO Procore | 76360 | 76360 |  |  | 76360
PRC 3352613PA4910 | 2026-06-15 | Inv. 67484 |  | 76360 | 1948.84 | 1948.84 | 74411.16
PRC 3352613PB4910 | 2026-07-06 | Inv. 67580 |  | 76360 | 5985.66 | 7934.5 | 68425.5 | FY26
PO 33527134910 | 2026-07-22 | Roll to FY27 | 0 | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  |  |  | 76360 |  | 7934.5 | 68425.5
|  | Totals: | 76360 |  | 7934.5 |  | 68425.5
|  | Design Development | 31740 |  | 7934.5 |  | 23805.5
|  | Construction Docs | 22140 |  |  |  | 22140
|  | Bidding/Negotiation | 7320 |  |  |  | 7320
|  | Construction Phase | 15160 |  |  |  | 15160
|  | Total: | 76360 |  | 7934.5 |  | 68425.5

## RECAP #9530.00
DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair
Project # 9530.00
Program code 953000 |  |  | Major Program 4E01
Recap
Acct. Codes-0017-335-MM26
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 213300
Story Construction |  | 25832.29 | 6163.81 | 19668.48
PM TIME |  | 7500 | 3862.57 | 3637.43
Misc. |  | 0 | 0 | 0
10Fold Architecture |  | 28654 | 4217.5 | 24436.5
Total Project Cost | 213300 | 61986.29 | 14243.88 | 47742.41 | 151313.71

## #9530.00 Story Construction
DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair
Project # 9530.00
Program code 953000 |  |  | Major Program 4E01
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0017-335-MM26-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526078911 | 2026-03-19 | PO Procore | 25832.29 | 25832.29 |  |  | 25832.29
PRC 3352607PA8911 | 2026-05-26 | Inv. 35265 |  | 25832.29 | 994.51 | 994.51 | 24837.78
PRC 3352607PB8911 | 2026-06-17 | Inv. 35301 |  | 25832.29 | 2720.96 | 3715.47 | 22116.82
PRC 3352607PC8911 | 2026-07-15 | Inv. 35345 |  | 25832.29 | 2448.34 | 6163.81 | 19668.48 | FY26
PO 33527078911 | 2026-07-22 | Roll to FY27 | 0 | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  |  |  | 25832.29 |  | 6163.81 | 19668.48
|  | Totals: | 25832.29 |  | 6163.81 |  | 19668.48
|  | CM Services | 25562.29 |  | 6028.81 |  | 19533.48
|  | Reimbursables | 270 |  | 135 |  | 135
|  | Total: | 25832.29 |  | 6163.81 |  | 19668.48

## #9530.00 PM TIME
DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair
Project # 9530.00
Program code 953000 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS 911U
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 7500 | 7500 |  |  | 7500
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 7500 | 49.67 | 49.67 | 7450.33
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 7500 | 576.8 | 626.47 | 6873.53
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 7500 | 31.45 | 657.92 | 6842.08
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 7500 | 253.1 | 911.02 | 6588.98
IET DAS202610115300001 | 2026-05-07 | 2507 | Finance Support for April 01-30, 2026 |  | 7500 | 129.9 | 1040.92 | 6459.08
IET DAS202610115300001 | 2026-05-07 | 9500 | DAS Support for April 01-30, 2026 |  | 7500 | 1355.9 | 2396.82 | 5103.18
IET DAS202611115300001 | 2026-06-08 | 2507 | Finance Support for May 01-31, 2026 |  | 7500 | 70.54 | 2467.36 | 5032.64
IET DAS202611115300001 | 2026-06-08 | 9500 | DAS Support for May 01-31, 2026 |  | 7500 | 861.5 | 3328.86 | 4171.14
IET DAS202612115300001 | 2026-07-08 | 2507 | Finance Support for June 01-30, 2026 |  | 7500 | 41.13 | 3369.99 | 4130.01
IET DAS202612115300001 | 2026-07-08 | 9500 | DAS Support for June 01-30, 2026 |  | 7500 | 475.9 | 3845.89 | 3654.11
IET DAS202613115300001 | 2026-07-15 | 2507 | Finance Support for June 01-30, 2026 (Period 13) |  | 7500 | 16.68 | 3862.57 | 3637.43
[5 empty] | 7500 |  | 3862.57 | 3637.43
|  |  | Totals: | 7500 |  | 3862.57 |  | 3637.43

## #9530.00 Misc
DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair
Project # 9530.00
Program code 953000 |  |  |  | Major Program 4E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code: 178
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9530.00 10Fold Architecture
DOC FDCF Unit L Pre-Cast Sealant & Warehouse W Freezer Floor Repair
Project # 9530.00
Program code 953000 |  |  | Major Program 4E01
10Fold Architecture |  |  | Vendor: 00003101228
Acct. Codes-0017-335-MM26-9260 |  |  | 95300-01
Project Manager - Jennie E |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526148908 | 2026-05-28 | PO Procore | 28654 | 28654 |  |  | 28654
PRC 3352614PA8908 | 2026-07-09 | Inv. 9530.00-01 |  | 28654 | 4217.5 | 4217.5 | 24436.5 | FY26
PO 33527148908 | 2026-07-22 | Roll to FY27 | 0 | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  |  |  | 28654 |  | 4217.5 | 24436.5
|  | Totals: | 28654 |  | 4217.5 |  | 24436.5
|  | Construction Docs | 16870 |  | 4217.5 |  | 12652.5
|  | Bidding Assistance | 2217 |  |  |  | 2217
|  | Construction Phase | 9567 |  |  |  | 9567
|  | Total: | 28654 |  | 4217.5 |  | 24436.5

## RECAP #XXXX.XX
Project Title
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Recap
Acct. Codes-0017-335-MM26 |  |  | Close Date:
Project Manager -
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
Project Title
Project # XXXX.XX
Program code XXXXXX |  |  | Major Program
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM26-xxxx
Project Manager - |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services | 0 |  |  |  | 0
|  | Reimbursables | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
Project Title
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM26-xxxx |  |  |  | eDAS
Project Manager -
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
Project Title
Project # XXXX.XX
Program code XXXXXX |  |  |  | Major Program
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-MM26-xxxx |  |  |  | Shipping Code:
Project Manager -
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0