## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation 061T | 5000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 5000000
| . | Less: Total Assigned |  | 5000000
|  | Total Unassigned / Unallocated |  | 0
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9485.00 | DAS SHB Archives Storage Renovation | Brandon A. | 5000000 |  | 5000000 | 2325388.72 | 42727.54 | 2282661.18 | 2674611.28
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 5000000 | 0 | 5000000 | 2325388.72 | 42727.54 | 2282661.18 | 2674611.28
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 2674611.28
[6 empty] | Total funds Available |  |  | 5000000
[6 empty] | Total obligated by contract or PO |  |  | -2325388.72 | 2674611.28
[6 empty] | Variance |  |  |  | 0

## RECAP #9485.00
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-061T
Project Manager - Brandon A.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 5000000
Neumann Monson |  | 54560 | 22506 | 32054
PM TIME |  | 60000 | 9776.86 | 50223.14
Misc. |  | 1257.35 | 1257.35 | 0
DCI Group |  | 24141.07 | 9187.33 | 14953.74
Midwest Storage Solutions |  | 2185430.3 | 0 | 2185430.3
Total Project Cost | 5000000 | 2325388.72 | 42727.54 | 2282661.18 | 2674611.28

## #9485.00 Neumann Monson
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
Neumann Monson |  |  | Vendor: 00002116371
Acct. Codes-0017-335-061T-9260 |  |  | RFP 0215335040
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526217908 | 2025-08-05 | PO Procore | 54560 | 54560 |  |  | 54560
PRC 3352621PA7908 | 2025-09-13 | Inv. 9485.00-01 |  | 54560 | 22506 | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  |  |  | 54560 |  | 22506 | 32054
|  | Totals: | 54560 |  | 22506 |  | 32054
|  | Construction Docs | 30008 |  | 22506 |  | 7502
|  | Bidding | 8184 |  |  |  | 8184
|  | Construction Admin | 16368 |  |  |  | 16368
|  | Total: | 54560 |  | 22506 |  | 32054

## #9485.00 PM TIME
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-061T-xxxx |  |  |  | eDAS: 733S
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 60000 | 60000 |  |  | 60000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 60000 | 131.15 | 131.15 | 59868.85
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 60000 | 1440.1 | 1571.25 | 58428.75
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 60000 | 383.62 | 1954.87 | 58045.13
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 60000 | 2953.2 | 4908.07 | 55091.93
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 60000 | 793.19 | 5701.26 | 54298.74
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 60000 | 4075.6 | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
[5 empty] | 60000 |  | 9776.86 | 50223.14
|  |  | Totals: | 60000 |  | 9776.86 |  | 50223.14
Note on E9: Huggins, Joni [DAS]: PM Time $Joni Adams, Brandon 1:58 PM (25 minutes ago) to me Finance, Can you please set my budget for PM Time for the following projects: DA26 9481.00 - $35,000 061T 9485.00 - $60,000 Regards, Brandon Adams

## #9485.00 Misc
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  |  | Major Program 3E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-061T-xxxx |  |  |  | Shipping Code: 035
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Sapce Planning Services August 1-31,2025 | Inv. DAS2026021153 | 166.25 | 166.25
IET DAS202603115300001 | 2025-10-07 | 2507 |  | Space Planning 09/01-09/31/25 | Inv.DAS2026031153 | 855 | 1021.25
IET 33526282902 | 2025-10-09 | 9255 | CNST | ICN Bill 09/01/25-09/30/25 | Inv. 730753-017 | 236.1 | 1257.35
1257.35
1257.35
1257.35
1257.35
1257.35
1257.35
1257.35
1257.35
1257.35
|  |  |  | Totals: |  | 1257.35

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-061T
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-061T-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services: | 0 |  |  |  | 0
|  | Reimbursables: | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-061T-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-061T-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0