## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation 061T | 5000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 5000000
| . | Less: Total Assigned |  | 5000000
|  | Total Unassigned / Unallocated |  | 0
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9485.00 | DAS SHB Archives Storage Renovation | Brandon A. | 5000000 |  | 5000000 | 3498219.32 | 478936.46 | 3019282.86 | 1501780.68
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 5000000 | 0 | 5000000 | 3498219.32 | 478936.46 | 3019282.86 | 1501780.68
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 0
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 1501780.68
[6 empty] | Total funds Available |  |  | 5000000
[6 empty] | Total obligated by contract or PO |  |  | -3498219.32 | 1501780.68
[6 empty] | Variance |  |  |  | 0

## RECAP #9485.00
DAS SHB Archives Storage Renovation
Project # 9485.00
| Program code 948500 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-061T
Project Manager - Brandon A.
|  | TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
| Budget | 5000000
| Neumann Monson |  | 54560 | 43593.44 | 10966.56
| PM TIME |  | 60000 | 26247.03 | 33752.97
| Misc. |  | 103076.96 | 103076.96 | 0
C | DCI Group |  | 20570.42 | 20570.42 | 0
| Midwest Storage Solutions |  | 2201964.97 | 128818.32 | 2073146.65
| GTG Construction |  | 244201.14 | 16587 | 227614.14
| Waldinger Corp |  | 300923.74 | 59206.88 | 241716.86
| JF Ahern dba Ahern Fire Protection |  | 8158 | 0 | 8158
| DCI Group (2) |  | 310847.47 | 75330.27 | 235517.2
| Iowa Prison Industries |  | 193916.62 | 5506.14 | 188410.48
| Total Project Cost | 5000000 | 3498219.32 | 478936.46 | 3019282.86 | 1501780.68

## #9485.00 Neumann Monson
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
Neumann Monson |  |  | Vendor: 00002116371
Acct. Codes-0017-335-061T-9260 |  |  | RFP 0215335040
Project Manager - Brandon A. |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526217908 | 2025-08-05 | PO Procore | 54560 | 54560 |  |  | 54560
PRC 3352621PA7908 | 2025-09-13 | Inv. 9485.00-01 |  | 54560 | 22506 | 22506 | 32054
PRC 3352621PB7908 | 2026-02-02 | Inv. 9485.00-02 |  | 54560 | 18632.24 | 41138.24 | 13421.76
PRC 3352621PC7908 | 2026-03-10 | Inv. 9485.00-03 |  | 54560 | 2455.2 | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  |  |  | 54560 |  | 43593.44 | 10966.56
|  | Totals: | 54560 |  | 43593.44 |  | 10966.56
|  | Construction Docs | 30008 |  | 30008 |  | 0
|  | Bidding | 8184 |  | 8184 |  | 0
|  | Construction Admin | 16368 |  | 5401.44 |  | 10966.56
|  | Total: | 54560 |  | 43593.44 |  | 10966.56

## #9485.00 PM TIME
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-061T-xxxx |  |  |  | eDAS: 733S
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 60000 | 60000 |  |  | 60000
IET DAS202601115300001 | 2025-08-07 | 2507 | Finance Support for July 01-31, 2025 |  | 60000 | 131.15 | 131.15 | 59868.85
IET DAS202601115300001 | 2025-08-07 | 9500 | DAS Support for July 01-31, 2025 |  | 60000 | 1440.1 | 1571.25 | 58428.75
IET DAS202602115300001 | 2025-09-08 | 2507 | Finance Support for August 01-31, 2025 |  | 60000 | 383.62 | 1954.87 | 58045.13
IET DAS202602115300001 | 2025-09-08 | 9500 | DAS Support for August 01-31, 2025 |  | 60000 | 2953.2 | 4908.07 | 55091.93
IET DAS202603115300001 | 2025-10-07 | 2507 | Finance Support for September 01-30, 2025 |  | 60000 | 793.19 | 5701.26 | 54298.74
IET DAS202603115300001 | 2025-10-07 | 9500 | DAS Support for September 01-30, 2025 |  | 60000 | 4075.6 | 9776.86 | 50223.14
IET DAS202604115300001 | 2025-11-07 | 2507 | Finance Support for October 01-31, 2025 |  | 60000 | 55.09 | 9831.95 | 50168.05
IET DAS202604115300001 | 2025-11-07 | 9500 | DAS Support for October 01-31, 2025 |  | 60000 | 2513.2 | 12345.15 | 47654.85
IET DAS202605115300001 | 2025-12-05 | 2507 | Finance Support for November 1-30, 2025 |  | 60000 | 607.13 | 12952.28 | 47047.72
IET DAS202605115300001 | 2025-12-05 | 9500 | DAS Support for November 1-30, 2025 |  | 60000 | 2770.2 | 15722.48 | 44277.52
IET DAS202606115300001 | 2026-01-08 | 2507 | Finance Support for December 1-31, 2025 |  | 60000 | 194.85 | 15917.33 | 44082.67
IET DAS202606115300001 | 2026-01-08 | 9500 | DAS Support for December 1-31, 2025 |  | 60000 | 2210.5 | 18127.83 | 41872.17
IET DAS202607115300001 | 2026-02-09 | 2507 | Finance Support for January 1-31, 2026 |  | 60000 | 278.34 | 18406.17 | 41593.83
IET DAS202607115300001 | 2026-02-09 | 9500 | DAS Support for January 1-31, 2026 |  | 60000 | 3459.4 | 21865.57 | 38134.43
IET DAS202608115300001 | 2026-03-09 | 2507 | Finance Support for February 1-28, 2026 |  | 60000 | 179.11 | 22044.68 | 37955.32
IET DAS202608115300001 | 2026-03-09 | 9500 | DAS Support for February 1-28, 2026 |  | 60000 | 2065.6 | 24110.28 | 35889.72
IET DAS202609115300001 | 2026-04-06 | 2507 | Finance Support for March 01-31, 2026 |  | 60000 | 232.65 | 24342.93 | 35657.07
IET DAS202609115300001 | 2026-04-06 | 9500 | DAS Support for March 01-31, 2026 |  | 60000 | 1904.1 | 26247.03 | 33752.97
[5 empty] | 60000 |  | 26247.03 | 33752.97
[5 empty] | 60000 |  | 26247.03 | 33752.97
[5 empty] | 60000 |  | 26247.03 | 33752.97
|  |  | Totals: | 60000 |  | 26247.03 |  | 33752.97
Note on E9: Huggins, Joni [DAS]: PM Time $Joni Adams, Brandon 1:58 PM (25 minutes ago) to me Finance, Can you please set my budget for PM Time for the following projects: DA26 9481.00 - $35,000 061T 9485.00 - $60,000 Regards, Brandon Adams

## #9485.00 Misc
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  |  | Major Program 3E01
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-061T-xxxx |  |  |  | Shipping Code: 035
Project Manager - Brandon A.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
IET DAS202602115300001 | 2025-09-08 | 2507 |  | Space Planning Services August 1-31,2025 | Inv. DAS2026021153 | 166.25 | 166.25
IET DAS202603115300001 | 2025-10-07 | 2507 |  | Space Planning September 1-30,2025 | Inv. DAS2026031153 | 855 | 1021.25
IET 33526282902 | 2025-10-09 | 9255 | CNST | ICN Bill 09/01/25-09/30/25 | Inv. 730753-017 | 236.1 | 1257.35
GAX 33526311900 | 2025-11-07 | 9500 | CNST | Brittany Puhrmann V#(00003208057) | Inv. 9485.00-01 | 3750 | 5007.35
IET DAS202604115300001 | 2025-11-07 | 2507 |  | Space Planning Services October 1-31,2025 | Inv. DAS2026041153 | 1615 | 6622.35
IET DAS202604115300001 | 2025-11-07 | 2507 |  | Electrical Services October 1-31,2025 | Inv. DAS2026041153 | 247.67 | 6870.02
IET 33526316908 | 2025-11-12 | 9255 | CNST | ICN Bill 10/01-10/31/25 | Inv. 732691-9485.00 | 117 | 6987.02
GAX 33526317904 | 2025-11-13 | 9500 | CNST | Paige Wilkinson V#(00003192964) | Inv. 9485.00-001 | 1000 | 7987.02
PRCI 33526317907 | 2025-11-13 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357297 | 8362.5 | 16349.52
PRC 33526329903 | 2025-11-25 | 9500 | CNST | Rapids Reproduction V#(00002111375) | Inv. INVCL2322 | 322.6 | 16672.12
GAX 33526338905 | 2025-12-04 | 9500 | CNST | Brittany Puhrmann V#(00003208057) | Inv. 9485.00-02 | 3750 | 20422.12
GAX 33526346903 | 2025-12-12 | 9500 | CNST | Paige Wilkinson V#(00003192964) | Inv. 9485.00-02 | 1000 | 21422.12
GAX 33526002901 | 2026-01-02 | 9500 | CNST | Brittany Puhrmann V#(00003208057) | Inv. 9485.00-03 | 3750 | 25172.12
GAX 33526009900 | 2026-01-09 | 9500 | CNST | Uline V#(00002100517) | Inv. 202140593 | 503.22 | 25675.34
IET DAS202606115300001 | 2026-01-08 | 2507 |  | Space Planning December 1-31,2025 | Inv. DAS2026061153 | 1068.75 | 26744.09
GAX 33526029900 | 2026-01-29 | 9500 | CNST | Crown Equipment V#(00003010134) | Inv. 163278176 & 163277934 | 1592 | 28336.09
GAX 33526029901 | 2026-01-29 | 9500 | CNST | Brittany Puhrmann V#(00003208057) | Inv. 9485.00-04 | 3750 | 32086.09
PRC 33526035900 | 2026-02-05 | 9500 | CNST | Holmes Murphy V#(00002110543) | Inv. 876858 | 2518 | 34604.09
PRCI 33526047912 | 2026-02-16 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357329 | 21554.5 | 56158.59
IET DAS202608115300001 | 2026-03-09 | 2507 |  | Space Planning Services February 1-28, 2026 | Inv. DAS2026081153 | 285 | 56443.59
PRCI 33526075910 | 2026-03-16 | 9500 | CNST | Iowa Prison Industries V#(250DOCIPI00) | Inv. 357340 | 28553.3 | 84996.89
GAX 33526079914 | 2026-03-20 | 9500 | CNST | Brittany Puhrmann V#(00003208057) | Inv. 9485.00-05 & 06 | 7500 | 92496.89
GAX 33526082903 | 2026-03-23 | 9500 | CNST | Neumann Brothers V#(00002106354) | Inv. 57584 | 4750 | 97246.89
PRC 33526082905 | 2026-03-23 | 9500 | CNST | ConvergeOne V#(00002104875) | Inv. INV1116469 & 1117939 | 5177.5 | 102424.39
IET DAS202609115300001 | 2026-04-06 | 2507 |  | Electrical Services: March 01-31, 2026 | Inv. DAS2026091153 | 361.77 | 102786.16
IET DAS202609115300001 | 2026-04-06 | 2507 |  | Fire Watch Services: March 01-31, 2026 | Inv. DAS2026091153 | 148.3 | 102934.46
IET DAS202609115300001 | 2026-04-06 | 2507 |  | Space Planning Services: March 01-31, 2026 | Inv. DAS2026091153 | 142.5 | 103076.96
103076.96
103076.96
103076.96
103076.96
|  |  |  | Totals: |  | 103076.96

## #9485.00 DCI Group
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-061T-9255 |  |  | RFP18213355228-DCI11012021
Project Manager - Brandon A. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526224900 | 2025-08-12 | PO Procore | 24141.07 | 24141.07 |  |  | 24141.07
PRC 3352622PA4900 | 0919/25 | Inv. 25-026 PC 01 |  | 24141.07 | 2821.53 | 2821.53 | 21319.54
PRC 3352622PB4900 | 2025-10-08 | Inv. 25-026 PC 02 |  | 24141.07 | 6365.8 | 9187.33 | 14953.74
PRC 3352622PC4900 | 2025-11-18 | Inv. 25-026 PC 03 |  | 24141.07 | 5960.6 | 15147.93 | 8993.14
PRC 3352622PD4900 | 2025-12-22 | Inv. 25-026 PC 04 Final | -3570.65 | 20570.42 | 5422.49 | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  |  |  | 20570.42 |  | 20570.42 | 0
|  | Totals: | 20570.42 |  | 20570.42 |  | 0 | FINAL
|  | CM Staff Hours | 19118.42 |  | 19118.42 |  | 0
|  | Reimbursables | 1452 |  | 1452 |  | 0
|  | Total: | 20570.42 |  | 20570.42 |  | 0

## #9485.00 Midwest Storage
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
Midwest Storage Solutions |  |  | Vendor: VS000001934
Acct. Codes-0017-335-061T-9255 |  |  | MA25204
Project Manager - Brandon A. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526303900 | 2025-10-30 | PO Procore | 2185430.3 | 2185430.3 |  |  | 2185430.3
PO 33526303900 | 2025-12-15 | CO #1 | 16534.67 | 2201964.97 |  | 0 | 2201964.97
PRC 3352630PA3900 | 2026-03-04 | Inv. 11140 |  | 2201964.97 | 100221.91 | 100221.91 | 2101743.06 | 3099.65
PRC 3352630PB3900 | 2026-03-19 | Inv. 11169 |  | 2201964.97 | 28596.41 | 128818.32 | 2073146.65 | 3984.08
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  |  |  | 2201964.97 |  | 128818.32 | 2073146.65
|  | Totals: | 2201964.97 |  | 128818.32 |  | 2073146.65
3% Retainage

## #9485.00 GTG Construction
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
GTG Construction |  |  | Vendor: 00003032746
Acct. Codes-0017-335-061T-9255 |  |  | RFB#948500-01
Project Manager - Brandon A. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526338906 | 2025-12-04 | PO Procore | 233000 | 233000 |  |  | 233000
PO 33526338906 | 2025-12-29 | CO #1 | 10169.25 | 243169.25 |  | 0 | 243169.25
PRC 3352633PA8906 | 2026-01-23 | Inv. 9485.00 01 |  | 243169.25 | 6693 | 6693 | 236476.25 | 207
PO 33526338906 | 2026-02-23 | CO #2 | 253.31 | 243422.56 |  | 6693 | 236729.56
PRC 3352633PB8906 | 2026-02-24 | Inv. 9485.00 002 |  | 243422.56 | 1940 | 8633 | 234789.56 | 267
PO 33526338906 | 2026-03-03 | CO #3 | 778.58 | 244201.14 |  | 8633 | 235568.14
PRC 3352633PC8906 | 2026-04-29 | Inv. 9485.00 003 |  | 244201.14 | 7954 | 16587 | 227614.14 | 513
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  |  |  | 244201.14 |  | 16587 | 227614.14
|  | Totals: | 244201.14 |  | 16587 |  | 227614.14
3% Retainage

## #9485.00 Waldinger Corp
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
Waldinger Corp |  |  | Vendor: 00002116105
Acct. Codes-0017-335-061T-9255 |  |  | RFB#948500-01
Project Manager - Brandon A. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33526349901 | 2025-12-15 | PO Procore | 256545 | 256545 |  |  | 256545
PRC 3352634PA9901 | 2026-02-05 | Inv. 93053E-001 |  | 256545 | 6035.46 | 6035.46 | 250509.54 | 186.66
PRC 3352634PB9901 | 2026-03-04 | Inv. 93053E-002 |  | 256545 | 15265.28 | 21300.74 | 235244.26 | 658.78
PO 33526349901 | 2026-04-13 | CO #1 | 2667.61 | 259212.61 |  | 21300.74 | 237911.87
PRC 3352634PC9901 | 2026-04-20 | Inv. 9485.00 03 |  | 259212.61 | 37906.14 | 59206.88 | 200005.73 | 1831.13
PO 33526349901 | 2026-04-27 | CO #2 | 41711.13 | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  |  |  | 300923.74 |  | 59206.88 | 241716.86
|  | Totals: | 300923.74 |  | 59206.88 |  | 241716.86
3% Retainage

## #9485.00 JF Ahern
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
JF Ahern |  |  | Vendor: 00002102310
Acct. Codes-0017-335-061T-9255 |  |  | RFB#948500-01
Project Manager - Brandon A. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526356900 | 2025-12-22 | PO Procore | 8158 | 8158 |  |  | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  |  |  | 8158 |  | 0 | 8158
|  | Totals: | 8158 |  | 0 |  | 8158

## #9485.00 DCI Group (2)
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-061T-9255 |  |  | RFP18213355228-DCI11012021
Project Manager - Brandon A. |  |  | Activity code: BRIN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526365901 | 2025-12-31 | PO Procore | 310847.47 | 310847.47 |  |  | 310847.47
PRC 3352636PA5901 | 2026-02-16 | Inv. 25-026 CA 01 |  | 310847.47 | 20666.73 | 20666.73 | 290180.74
PRC 3352636PB5901 | 2026-03-20 | Inv. 25-026 CA 02 |  | 310847.47 | 25740.74 | 46407.47 | 264440
PRC 3352636PC5901 | 2026-04-16 | Inv. 25-026 CA 03 |  | 310847.47 | 28922.8 | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  |  |  | 310847.47 |  | 75330.27 | 235517.2
|  | Totals: | 310847.47 |  | 75330.27 |  | 235517.2
|  | CM Services | 178522.14 |  | 34590.77 |  | 143931.37
|  | Reimbursables | 25000 |  | 8541.9 |  | 16458.1
|  | Fee | 107325.33 |  | 32197.6 |  | 75127.73
|  | Total: | 310847.47 |  | 75330.27 |  | 235517.2

## #9485.00 IA Prison Industries
DAS SHB Archives Storage Renovation
Project # 9485.00
Program code 948500 |  |  | Major Program 3E01
IA Prison Industries |  |  | Vendor: 250DOCIPI00
Acct. Codes-0017-335-061T-9255 |  |  | 9485.00-01
Project Manager - Brandon A. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33526033916 | 2026-02-03 | PO Procore | 193916.62 | 193916.62 |  |  | 193916.62
PRCI 3352603PA3916 | 2026-02-05 | Inv. 357305 |  | 193916.62 | 2601.25 | 2601.25 | 191315.37
PRCI 3352603PB3916 | 2026-04-10 | Inv. 357357 |  | 193916.62 | 2904.89 | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  |  |  | 193916.62 |  | 5506.14 | 188410.48
|  | Totals: | 193916.62 |  | 5506.14 |  | 188410.48
|  | Contract Total: | 193916.62 |  | 5506.14
|  | Paid out of Misc |  |  | 21554.5
|  | Paid out of Misc |  |  | 28553.3
|  | Totals: | 193916.62 |  | 55613.94 |  | 138302.68

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-061T
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-061T-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services: | 0 |  |  |  | 0
|  | Reimbursables: | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-061T-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-061T-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0