## FINANCIAL
.
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | 506 Project Budget | 506 Project Funds Received | Total Project Budget | Contracted Amount | Expended Amount | Encumbered Not Expended | Not Encumbered
|  | Vertical Infrastructure Funds | 7429627.97
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 7429627.97
Less: Total Assigned
|  | Total Unassigned / Unallocated |  | 7429627.97
DA24 (MOU) Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
| 9455.00 | IDOE ISD Giangreco Hall Water Infiltration Mitigation | Jennie E. | 0 | 4430000 | 4430000 | 1069931.44 | 220792.61 | 849138.83 | 3360068.56
| 9516.01 | IDR State of Iowa Building Renovation | Jennie E. | 0 | 1206500 | 1206500 | 1037478.08 | 121478.51 | 915999.57 | 169021.92
| 9522.00 | DOC NCF Dietary and Laundry Hot Water Tank Replacement | Brad T. | 0 | 10000 | 10000 | 0 | 0 | 0 | 10000
| 9534.01 | IDR ATOD Will call Ramp Replacement | Jennie E. | 0 | 291000 | 291000 | 253603.2 | 0 | 253603.2 | 37396.8
| 9543.00 | DOC 6JD IC Hope-Stratton HVAC Phase 2 | Jennifer K. | 0 | 212127.97 | 212127.97 | 19783.15 | 314.27 | 19468.88 | 192344.82
| 9545.00 | HHS WRC Campus Generator Study | Jennifer K. | 0 | 50000 | 50000 | 31180.4 | 1068.78 | 30111.62 | 18819.6
| 9546.00 | ATOD Server Room Pre-Action Clean Agent System | Jennie E. | 0 | 230000 | 230000 | 13318.02 | 0 | 13318.02 | 216681.98
| 9571.00 | DVA IVH Sheeler Entrance Improvements | Brad T. | 0 | 1000000 | 1000000 | 35000 | 0 | 35000 | 965000
|  | DA27 (MOU) Totals |  | 0 | 7429627.97 | 7429627.97 | 2460294.29 | 343654.17 | 2116640.12 | 4969333.68
7085973.8

## RECAP #9455.00
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget | Pending Reimbursements
Funds received per MOU | 4430000
OPN Architects |  | 55359.8 | 24501.6 | 30858.2
PM TIME |  | 175000 | 2547.06 | 172452.94
Misc. |  | 0 | 0 | 0
Samuels Group |  | 683763.29 | 37935.6 | 645827.69
McKinnis Roofing |  | 155808.35 | 155808.35 | 0 |  | 4731736.54
Total Project Cost | 4430000 | 1069931.44 | 220792.61 | 849138.83 | 3360068.56 | 4731736.54

## #9455.00 Funds Rec'd
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Funds Rec'd
Acct Code: 0506-335-DA27-0304
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 070126CK008 | 2026-07-02 | 4430000 | 4430000
| Total Requested | 0 | Total Transferred |  |  | 4430000 | 4430000

## #9455.00 OPN Architects
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0506-335-DA27-9260 |  |  | RFP945500-01
Project Manager - Jennie E. |  |  | Activity code: DSGN
Split w/MM25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527114900 | 2026-07-23 | CO #1 Splitting w/MM25 | 55359.8 | 55359.8 |  |  | 55359.8
PRC 3352711PK4900 | 2026-08-17 | Inv. 24843001-11 |  | 55359.8 | 12250.8 | 12250.8 | 43109
PRC 3352711PL4900 | 2026-09-14 | Inv. 24843001-12 |  | 55359.8 | 12250.8 | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  |  |  | 55359.8 |  | 24501.6 | 30858.2
|  | Totals: | 55359.8 |  | 24501.6 |  | 30858.2
|  | MM25 Closed 07/23/26 | 288420.2 |  | 288420.2 |  | 0
|  | Total: | 343780 |  | 312921.8 |  | 30858.2

## #9455.00 PM TIME
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | edas: 736W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 175000 | 175000 |  |  | 175000
IET DAS202701115300001 | 2026-08-07 | 2507 | Finance Support for July 01-31, 2026 |  | 175000 | 101.66 | 101.66 | 174898.34
IET DAS202701115300001 | 2026-08-07 | 9500 | DAS Support for July 01-31, 2026 |  | 175000 | 1311.7 | 1413.36 | 173586.64
IET DAS202702115300001 | 2026-09-07 | 2507 | Finance Support for August 01-31, 2026 |  | 175000 | 105.9 | 1519.26 | 173480.74
IET DAS202702115300001 | 2026-09-07 | 9500 | DAS Support for August 01-31, 2026 |  | 175000 | 1027.8 | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
[5 empty] | 175000 |  | 2547.06 | 172452.94
|  |  | Totals: | 175000 |  | 2547.06 |  | 172452.94

## #9455.00 Misc
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  |  | Major Program 4F04
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9455.00 Samuels Group
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Split w/MM26
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527029913 | 2026-07-23 | CO #1 Splitting w/MM26 | 683763.29 | 683763.29 |  |  | 683763.29
PRC 3352702PG9913 | 2026-08-11 | Inv. 7850.57945500 |  | 683763.29 | 15156.45 | 15156.45 | 668606.84
PRC 3352702PH9913 | 2026-09-14 | Inv. 7850.58945500 |  | 683763.29 | 22779.15 | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  |  |  | 683763.29 |  | 37935.6 | 645827.69
|  | Totals: | 683763.29 |  | 37935.6 |  | 645827.69
|  | MM26 Closed 07/23/26 | 66862.39 |  | 66862.39 |  | 0
|  | Total: | 750625.68 |  | 104797.99 |  | 645827.69

## #9455.00 McKinnis
IDOE ISD Giangreco Hall Water Infiltration Mitigation
Project # 9455.00
Program code 945500 |  |  | Major Program 4F04
McKinnis Roofing |  |  | Vendor: 00003217305
Acct. Codes-0506-335-DA27-9255 |  |  | RFB945500-01
Project Manager - Jennie E. |  |  | Activity code: BRIN
Spilt w/MM26
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance | Retainage
PO 33527002900 | 2026-08-04 | CO #1 Splitting w/MM26 | 155808.35 | 155808.35 |  |  | 155808.35
PO 33527002900 | 2026-08-04 | CO #1 Adding Funds |  | 155808.35 |  | 0 | 155808.35
PRC 3352700PB2900 | 2026-09-08 | Inv. 49434(100% to DA27) |  | 155808.35 | 155808.35 | 155808.35 | 0 | 4818.82
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  |  |  | 155808.35 |  | 155808.35 | 0
|  | Totals: | 155808.35 |  | 155808.35 |  | 0
PO number above is assigned to Procore PO, and created in IA Advantage as Unencumbered on Unit DA27 line due to Paper Contract for FY27
Will create payments as funds become available to charge against this project.
|  | DA27 Contract Total: | 4887544.89 |  | 155808.35 |  | 4731736.54
|  | MM26 Retainage Only | 220346.03 |  | 213735.65 |  | 6610.38
|  | Total: | 5107890.92 |  | 369544 |  | 4738346.92

## RECAP #9516.01
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1206500
Bergstrom Construction |  | 196010 | 110200.77 | 85809.23
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Proctor Mechanical |  | 87612 | 0 | 87612
Mahoney Fire |  | 17300 | 0 | 17300
Waldinger Electrical |  | 205556 | 0 | 205556
Iowa Illinois Office Solutions (Paragon Interior) |  | 382520.29 | 0 | 382520.29
DCI Group |  | 67533.49 | 11277.74 | 56255.75
CTI |  | 80946.3 | 0 | 80946.3
Total Project Cost | 1206500 | 1037478.08 | 121478.51 | 915999.57 | 169021.92

## #9516.01 Funds Rec'd
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 627JP2719501 | 2026-07-15 | 1055000 | 1055000
|  |  | MOU Amendment #1 | IET 627DB2723002 | 2026-08-19 | 151500 | 151500
| Total Requested | 0 | Total Transferred |  |  | 1206500 | 1206500

## #9516.01 Bergstrom Construction
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Bergstrom Construction |  |  | Vendor: 00002110114
Acct. Codes-0506-335-DA27-9255 |  |  | MA 23199B
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33527204907 | 2026-07-23 | DO Procore | 196010 | 196010 |  |  | 196010
PRC 3352720PA4907 | 2026-09-22 | Inv. 8921-1 |  | 196010 | 110200.77 | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  |  |  | 196010 |  | 110200.77 | 85809.23
|  | Totals: | 196010 |  | 110200.77 |  | 85809.23
|  | Labor | 34236 |  | 7649.7 |  | 26586.3
|  | Materials | 161774 |  | 102551.07 |  | 59222.93
|  | Total: | 196010 |  | 110200.77 |  | 85809.23

## #9516.01 PM TIME
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | edas:736X
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9516.01 Misc
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  |  | Major Program 4E19
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | Shipping Code: 035
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9516.01 Proctor Mechanical
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Proctor Mechanical |  |  | Vendor: 00003166259
Acct. Codes-0506-335-DA27-9255 |  |  | MA 21010A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33527204908 | 2026-07-23 | DO Procore | 87612 | 87612 |  |  | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  |  |  | 87612 |  | 0 | 87612
|  | Totals: | 87612 |  | 0 |  | 87612
|  | Labor | 64262 |  |  |  | 64262
|  | Materials | 23350 |  |  |  | 23350
|  | Total: | 87612 |  | 0 |  | 87612

## #9516.01 Mahoney Fire
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Mahoney Fire |  |  | Vendor: 00003035382
Acct. Codes-0506-335-DA27-9255 |  |  | MA 230050570A
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33527204909 | 2026-07-23 | DO Procore | 17300 | 17300 |  |  | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  |  |  | 17300 |  | 0 | 17300
|  | Totals: | 17300 |  | 0 |  | 17300
|  | Labor | 12110 |  |  |  | 12110
|  | Materials | 5190 |  |  |  | 5190
|  | Total: | 17300 |  | 0 |  | 17300

## #9516.01 Waldinger Electrical
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Waldinger Electrical |  |  | Vendor: 00002116105
Acct. Codes-0506-335-DA27-9255 |  |  | MA26349
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33527204910 | 2026-07-23 | DO Procore | 205556 | 205556 |  |  | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  |  |  | 205556 |  | 0 | 205556
|  | Totals: | 205556 |  | 0 |  | 205556
|  | Labor | 125540 |  |  |  | 125540
|  | Materials | 73050 |  |  |  | 73050
|  | Equipment | 6966 |  |  |  | 6966
|  | Total: | 205556 |  | 0 |  | 205556

## #9516.01 Paragon Interiors
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
Paragon Interiors |  |  | Vendor: 00003209438
Acct. Codes-0506-335-DA27-9255 |  |  | MA
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527045900 | 2026-07-23 | PO Procore | 382520.29 | 382520.29 |  |  | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  |  |  | 382520.29 |  | 0 | 382520.29
|  | Totals: | 382520.29 |  | 0 |  | 382520.29

## #9516.01 DCI Group
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527232915 | 2026-08-20 | PO Procore | 67533.49 | 67533.49 |  |  | 67533.49
PRC 3352723PA2915 | 2026-09-14 | Inv. 9516.00 CA 01 |  | 67533.49 | 11277.74 | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  |  |  | 67533.49 |  | 11277.74 | 56255.75
|  | Totals: | 67533.49 |  | 11277.74 |  | 56255.75
|  | CM Staff | 65533.49 |  | 11277.74 |  | 54255.75
|  | Reimbursables | 2000 |  |  |  | 2000
|  | Total: | 67533.49 |  | 11277.74 |  | 56255.75

## #9516.01 CTI
IDR State of Iowa Building Renovation
Project # 9516.01
Program code 951601 |  |  | Major Program 4E19
CTI |  |  | Vendor: 00002133110
Acct. Codes-0506-335-DA27-9255 |  |  | MA#005 22036E
Project Manager - Jennie E. |  |  | Activity code: CNST
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
DO 33527273915 | 2026-08-20 | DO Procore | 80946.3 | 80946.3 |  |  | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  |  |  | 80946.3 |  | 0 | 80946.3
|  | Totals: | 80946.3 |  | 0 |  | 80946.3
|  | Equipment | 41812.2 |  |  |  | 41812.2
|  | Implementation Services | 39134.1 |  |  |  | 39134.1
|  | Total: | 80946.3 |  | 0 |  | 80946.3

## RECAP #9522.00
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  | Major Program 4E01
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 10000
Vendor A |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 10000 | 0 | 0 | 0 | 10000

## #9522.00 Funds Rec'd
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  | Major Program 4E01
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - Brad T.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 24579522 | 2026-08-19 | 10000 | 10000
| Total Requested | 0 | Total Transferred |  |  | 10000 | 10000

## #9522.00 Vendor A
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  | Major Program 4E01
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA27-XXXX
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9522.00 PM TIME
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  |  | Major Program 4E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Brad T. |  |  |  | edas: 736Z
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9522.00 Misc
DOC NCF Dietary and Laundry Hot Water Tank Replacement
Project # 9522.00
Program code 952200 |  |  |  | Major Program 4E01
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Brad T. |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9534.01
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  | Major Program 4H06
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 291000
Absolute Group |  | 198662 | 0 | 198662
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Samuels Group |  | 54941.2 | 0 | 54941.2
Total Project Cost | 291000 | 253603.2 | 0 | 253603.2 | 37396.8

## #9534.01 Funds Rec'd
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  | Major Program 4H06
Funds Rec'd
Acct Code: 0506-335-DA27-0304
Project Manager - Jennie E
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | Funds recvd incorrectly to 9534.00-Moving funds From 9534.00 to 9534.01 | CDR 33527230900 | 2026-08-18 | 291000 | 291000
| Total Requested | 0 | Total Transferred |  |  | 291000 | 291000

## #9534.01 Absolute Group
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  | Major Program 4H06
Absolute Group |  |  | Vendor: 00003022169
Acct. Codes-0506-335-DA27-9255 |  |  | RFB954300-01
Project Manager - Jennie E |  |  | Activity code: BRUM
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527246923 | 2026-09-03 | PO Procore | 198662 | 198662 |  |  | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  |  |  | 198662 |  | 0 | 198662
|  | Totals: | 198662 |  | 0 |  | 198662

## #9534.01 PM TIME
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  |  | Major Program 4H06
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E |  |  |  | edas: 737D
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9534.01 Misc
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  |  | Major Program 4H06
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9534.01 Samuels Group
IDR ATOD Will call Ramp Replacement
Project # 9534.01
Program code 953401 |  |  | Major Program 4H06
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527257919 | 2026-09-14 | PO Procore | 54941.2 | 54941.2 |  |  | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  |  |  | 54941.2 |  | 0 | 54941.2
|  | Totals: | 54941.2 |  | 0 |  | 54941.2
|  | CM Services | 51941.2 |  |  |  | 51941.2
|  | Reimbursables-Temp | 2500 |  |  |  | 2500
|  | Reimbursables-Miles | 500 |  |  |  | 500
|  | Total: | 54941.2 |  | 0 |  | 54941.2

## RECAP #9543.00
DOC 6JD IC Hope-Stratton HVAC Phase 2
Project # 9543.00
Program code 954300 |  |  | Major Program 4B01
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennifer K.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 212127.97
McGough Construction |  | 11783.15 | 0 | 11783.15
PM TIME |  | 8000 | 314.27 | 7685.73
Misc. |  | 0 | 0 | 0
Total Project Cost | 212127.97 | 19783.15 | 314.27 | 19468.88 | 192344.82

## #9543.00 Funds Rec'd
DOC 6JD IC Hope-Stratton HVAC Phase 2
Project # 9543.00
Program code 954300 |  |  | Major Program 4B01
Funds Rec'd
Acct Code: 0506-335-DA27-0304
Project Manager - Jennifer K.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET 23813U27004 | 2026-08-25 | 150000 | 150000
|  |  | MOU 2nd Transfer | IET 226A062700278 | 2026-08-31 | 62127.97 | 62127.97
| Total Requested | 0 | Total Transferred |  |  | 212127.97 | 212127.97

## #9543.00 McGough Construction
DOC 6JD IC Hope-Stratton HVAC Phase 2
Project # 9543.00
Program code 954300 |  |  | Major Program 4B01
McGough Construction |  |  | Vendor: 00003193334
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-McGough11012021
Project Manager - Jennifer K. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527251921 | 2026-09-08 | PO Procore | 11783.15 | 11783.15 |  |  | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  |  |  | 11783.15 |  | 0 | 11783.15
|  | Totals: | 11783.15 |  | 0 |  | 11783.15
|  | CM Services | 11468.15 |  |  |  | 11468.15
|  | Reimbursables | 315 |  |  |  | 315
|  | Total: | 11783.15 |  | 0 |  | 11783.15

## #9543.00 PM TIME
DOC 6JD IC Hope-Stratton HVAC Phase 2
Project # 9543.00
Program code 954300 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennifer K. |  |  |  | edas: 737A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 8000 | 8000 |  |  | 8000
IET DAS202702115300001 | 2026-09-07 | 2507 | Finance Support for August 01-31, 2026 |  | 8000 | 29.57 | 29.57 | 7970.43
IET DAS202702115300001 | 2026-09-07 | 9500 | DAS Support for August 01-31, 2026 |  | 8000 | 284.7 | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
[5 empty] | 8000 |  | 314.27 | 7685.73
|  |  | Totals: | 8000 |  | 314.27 |  | 7685.73
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer DAS Finance Payables Infrastructure Please create a DAS Costs budget of $8,000.00 for DA27 Project 9543.00. Regards, Jennifer

## #9543.00 Misc
DOC 6JD IC Hope-Stratton HVAC Phase 2
Project # 9543.00
Program code 954300 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennifer K. |  |  |  | Shipping Code: 122A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9545.00
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  | Major Program 4B02
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 50000
Story Construction |  | 7295.4 | 0 | 7295.4
PM TIME |  | 5000 | 1068.78 | 3931.22
Misc. |  | 0 | 0 | 0
Innovative Engineers |  | 18885 | 0 | 18885
Total Project Cost | 50000 | 31180.4 | 1068.78 | 30111.62 | 18819.6

## #9545.00 Funds Rec'd
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  | Major Program 4B02
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - Jennifer K
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET DASMOU954500 | 2026-08-25 | 50000 | 50000
| Total Requested | 0 | Total Transferred |  |  | 50000 | 50000

## #9545.00 Story Construction
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  | Major Program 4B02
Story Construction |  |  | Vendor: 00002110695
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-Story11012021
Project Manager - Jennifer K |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527246915 | 2026-09-03 | PO Procore | 7295.4 | 7295.4 |  |  | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  |  |  | 7295.4 |  | 0 | 7295.4
|  | Totals: | 7295.4 |  | 0 |  | 7295.4

## #9545.00 PM TIME
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  |  | Major Program 4B02
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennifer K |  |  |  | edas: 737F
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 5000 | 5000 |  |  | 5000
IET DAS202702115300001 | 2026-09-07 | 2507 | Finance Support for August 01-31, 2026 |  | 5000 | 99.48 | 99.48 | 4900.52
IET DAS202702115300001 | 2026-09-07 | 9500 | DAS Support for August 01-31, 2026 |  | 5000 | 969.3 | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
[5 empty] | 5000 |  | 1068.78 | 3931.22
|  |  | Totals: | 5000 |  | 1068.78 |  | 3931.22
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer DAS Finance Payables Infrastructure Please create a DAS Costs budget of $5,000.00 for DA27 Project 9545.00. Regards, Jennifer

## #9545.00 Misc
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  |  | Major Program 4B02
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennifer K |  |  |  | Shipping Code: 564
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## #9545.00 Innovative Engineers
HHS WRC Campus Generator Study
Project # 9545.00
Program code 954500 |  |  | Major Program 4B02
Innovative Engineers |  |  | Vendor: 00003080298
Acct. Codes-0506-335-DA27-9260 |  |  | Emergency
Project Manager - Jennifer K |  |  | Activity code: DSGN
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527259921 | 2026-09-16 | PO Procore | 18885 | 18885 |  |  | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  |  |  | 18885 |  | 0 | 18885
|  | Totals: | 18885 |  | 0 |  | 18885
|  | Preliminary Report | 11250 |  |  |  | 11250
|  | Review | 2410 |  |  |  | 2410
|  | Recommend | 2570 |  |  |  | 2570
|  | Final | 2655 |  |  |  | 2655
|  | Total: | 18885 |  | 0 |  | 18885

## RECAP #9546.00
ATOD Server Room Pre-Action Clean Agent System
Project # 9546.00
Program code 954600 |  |  | Major Program 4F04
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Jennie E.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 230000
Samuels Group |  | 13318.02 | 0 | 13318.02
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 230000 | 13318.02 | 0 | 13318.02 | 216681.98

## #9546.00 Funds Rec'd
ATOD Server Room Pre-Action Clean Agent System
Project # 9546.00
Program code 954600 |  |  | Major Program 4F04
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - Jennie E.
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | DAS091026SERVERROOM | 2026-09-10 | 230000 | 230000
| Total Requested | 0 | Total Transferred |  |  | 230000 | 230000

## #9546.00 Samuels Group
ATOD Server Room Pre-Action Clean Agent System
Project # 9546.00
Program code 954600 |  |  | Major Program 4F04
Samuels Group |  |  | Vendor: 00003033402
Acct. Codes-0506-335-DA27-9255 |  |  | RFP1821335228-Samuels11012021
Project Manager - Jennie E. |  |  | Activity code: CMGR
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527260924 | 2026-09-17 | PO Procore | 13318.02 | 13318.02 |  |  | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  |  |  | 13318.02 |  | 0 | 13318.02
|  | Totals: | 13318.02 |  | 0 |  | 13318.02
|  | CM Services | 13218.02 |  |  |  | 13218.02
|  | Reimbursables | 100 |  |  |  | 100
|  | Total: | 13318.02 |  | 0 |  | 13318.02

## #9546.00 PM TIME
ATOD Server Room Pre-Action Clean Agent System
Project # 9546.00
Program code 954600 |  |  |  | Major Program 4F04
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | edas: 737G
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9546.00 Misc
ATOD Server Room Pre-Action Clean Agent System
Project # 9546.00
Program code 954600 |  |  |  | Major Program 4F04
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Jennie E. |  |  |  | Shipping Code: 137
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9571.00
DVA IVH Sheeler Entrance Improvements
Project # 9571.00
Program code 957100 |  |  | Major Program 4B03
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 1000000
VendorA |  | 0 | 0 | 0
PM TIME |  | 35000 | 0 | 35000
Misc. |  | 0 | 0 | 0
Total Project Cost | 1000000 | 35000 | 0 | 35000 | 965000

## #9571.00 Funds Rec'd
DVA IVH Sheeler Entrance Improvements
Project # 9571.00
Program code 957100 |  |  | Major Program 4B03
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - Brad T
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU | IET IET092322100 | 2026-09-23 | 1000000 | 1000000
| Total Requested | 0 | Total Transferred |  |  | 1000000 | 1000000

## #9571.00 Vendor A
DVA IVH Sheeler Entrance Improvements
Project # 9571.00
Program code 957100 |  |  | Major Program 4B03
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Brad T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9571.00 PM TIME
DVA IVH Sheeler Entrance Improvements
Project # 9571.00
Program code 957100 |  |  |  | Major Program 4B03
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Brad T |  |  |  | edas: 737L
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget | 35000 | 35000 |  |  | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
|  |  | Totals: | 35000 |  | 0 |  | 35000

## #9571.00 Misc
DVA IVH Sheeler Entrance Improvements
Project # 9571.00
Program code 957100 |  |  |  | Major Program 4B03
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - Brad T |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## Funds Rec'd Incorrectly
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
|  |  | MOU 9534.01 funds recvd as 9534.00 | IET DAS081126RAMP | 2026-08-17 | 291000 | 291000
|  |  | Moving funds to 9534.01 | CDR 33527230900 | 2026-08-18 | -291000 | -291000
|  |  | FY27 Funds Rcv'd Inccorrect Unit from Agency | IET DAS081226RAMP | 2026-08-21 | 23762.26 | 23762.26
|  |  | Moving FY27 to Correct Unit - DA26 9534.00 | CDR 33527233901 | 2026-08-21 | -23762.26 | -23762.26
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0506-335-DA27 |  |  | Closing Date:
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Funds received per MOU | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #xxxx.xx Funds Rec'd
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Funds Rec'd
Acct Code: 0506-335-DA27-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx
Date | DAS Document # | Amount | Vendor | Document # | Date of Transfer | Amount | Total amount of transfer
0
| Total Requested | 0 | Total Transferred |  |  | 0 | 0

## #xxxx.xx Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0506-335-DA27-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #xxxx.xx PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0506-335-DA27-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  |  | edas:
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #xxxx.xx Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Acct. Codes-0506-335-DA27-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  |  | Shipping Code:
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0