## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation | 22000000
|  | Additional Funds | 0
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 22000000
| . | Less: Total Assigned |  | 19782036.87
|  | Total Unassigned / Unallocated |  | 2217963.13
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9997.27 | Project Management Time | Geoff W. | 75000 |  | 75000 | 75000 | 1619.15 | 73380.85 | 0
| 9542.01 | DOC IMCC Admin Basement Water Mitigation | Jennifer K | 2350000 |  | 2350000 | 0 | 0 | 0 | 2350000 | 0
| 9547.00 | DOC 2JD FDCCC Metal Roof Replacement | Brad T. | 450000 |  | 450000 | 20000 | 0 | 20000 | 430000 | 20000
| 9548 | DAS CC Historical Building HVAC Replacement Design | Jennie E | 300000 |  | 300000 | 0 | 0 | 0 | 300000 | 0
| 9549 | HHS CHMHI Administration Building Window Replacement Phase 1 and 2 | Jennie E | 2736000 |  | 2736000 | 0 | 0 | 0 | 2736000 | 0
| 9550 | DOC FDCF Replace Power Plant and Warehouse Roofs | Jennie E | 858500 |  | 858500 | 0 | 0 | 0 | 858500 | 0
| 9551 | DOC ICIW IPI Building Heating Unit Replacements | Brandon A. | 800000 |  | 800000 | 25000 | 0 | 25000 | 775000 | 25000
| 9554 | DOC IMCC Tunnel Waterproofing | Jennifer K | 850000 |  | 850000 | 0 | 0 | 0 | 850000 | 0
| 9555 | DOC IMCC Vehicle Gate VG1, 1A and VG18 Replacements | Jennifer K | 875000 |  | 875000 | 26250 | 0 | 26250 | 848750 | 26250
| 9556 | DOC IMCC Main Building AHU Control and Old Boiler Room Condensate Tank Replacements | Jennifer K | 1130000 |  | 1130000 | 25000 | 0 | 25000 | 1105000 | 25000
| 9557 | HHS IMHI Infirmary Tuckpointing and Window Replacement | James T | 3258036.87 |  | 3258036.87 | 0 | 0 | 0 | 3258036.87 | 0
| 9558 | IDOE IPBS 6535 Building Tuckpointing | Brandon A. | 250000 |  | 250000 | 8000 | 0 | 8000 | 242000 | 8000
| 9559 | IDVA IVH West and Cottage Parking Lot Replacements and Garage Tuckpointing | Brad T. | 1500000 |  | 1500000 | 35000 | 0 | 35000 | 1465000 | 35000
| 9560 | DOC MPCF Campus-Wide PIV Replacement and MLO Parking Lot Repair | Brandon A. | 1000000 |  | 1000000 | 20000 | 0 | 20000 | 980000 | 20000
| 9561 | DOC NCCF R&D Window Replacement | Jennie E | 195000 |  | 195000 | 0 | 0 | 0 | 195000 | 0
| 9562 | DOC NCF Living Unit B and E Large Capacity Water Vessel Replacements and CRC Generator Replacement | Brad T. | 773500 |  | 773500 | 30000 | 0 | 30000 | 743500 | 30000
| 9563 | DPS P01 South Alley Retaining Wall Replacement | Brandon A. | 110000 |  | 110000 | 4000 | 0 | 4000 | 106000 | 4000
| 9564 | DPS P11 Parking Lot Replacement | James T | 535000 |  | 535000 | 0 | 0 | 0 | 535000 | 0
| 9565 | DPS P12 Retaining Wall Re-Build | James T | 50000 |  | 50000 | 0 | 0 | 0 | 50000 | 0
| 9566 | HHS STS Bakery Cooler Enclosure Replacement and Corbett-Miller Hall Tuckpointing | Jennifer K | 250000 |  | 250000 | 12000 | 0 | 12000 | 238000 | 12000
| 9567 | DAS USS Union Sunday School Masonry Repairs and Roof Replacement | James T | 456000 |  | 456000 | 0 | 0 | 0 | 456000 | 0
| 9568 | HHS WRC Dispatch Garage Roof Replacement and Birches Tuckpointing | Jennifer K | 980000 |  | 980000 | 22500 | 0 | 22500 | 957500 | 22500
|  | Major Maintenance Totals |  | 19782036.87 | 0 | 19782036.87 | 302750 | 1619.15 | 301130.85 | 19479286.87 | 227750
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 2217963.13
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 21697250
[6 empty] | Total funds Available |  |  | 22000000
[6 empty] | Total obligated by contract or PO |  |  | -302750 | 21697250
[6 empty] | Variance |  |  |  | 0

## RECAP #9997.27
Project Management Time
Project # 9997.27
Program code 999727 |  |  | Major Program 3E01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Geoff W
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 75000
VendorA |  | 0 | 0 | 0
PM TIME |  | 75000 | 1619.15 | 73380.85
Misc. |  | 0 | 0 | 0
Total Project Cost | 75000 | 75000 | 1619.15 | 73380.85 | 0

## #9997.27 PM TIME
Project Management Time
Project # 9997.27
Program code 999727 |  |  |  | Major Program 3E01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS 911V
Project Manager - Geoff W
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 75000 | 75000 |  |  | 75000
IET DAS202701115300001 | 2026-08-07 | 2507 | Finance Support for July 01-31, 2026 |  | 75000 | 107.19 | 107.19 | 74892.81
IET DAS202701115300001 | 2026-08-07 | 9500 | DAS Support for July 01-31, 2026 |  | 75000 | 491.7 | 598.89 | 74401.11
IET DAS202702115300001 | 2026-09-07 | 2507 | Finance Support for August 01-31, 2026 |  | 75000 | 215.66 | 814.55 | 74185.45
IET DAS202702115300001 | 2026-09-07 | 9500 | DAS Support for August 01-31, 2026 |  | 75000 | 804.6 | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
[5 empty] | 75000 |  | 1619.15 | 73380.85
|  |  | Totals: | 75000 |  | 1619.15 |  | 73380.85

## RECAP #9542.01
DOC IMCC Admin Basement Water Mitigation
Project # 9542.01
Program code 954201 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 2350000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 2350000 | 0 | 0 | 0 | 2350000

## #9542.01 Vendor A
DOC IMCC Admin Basement Water Mitigation
Project # 9542.01
Program code 954201 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9542.01 PM TIME
DOC IMCC Admin Basement Water Mitigation
Project # 9542.01
Program code 954201 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: 737K
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9542.01 Misc
DOC IMCC Admin Basement Water Mitigation
Project # 9542.01
Program code 954201 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9547.00
DOC 2JD FDCCC Metal Roof Replacement
Project # 9547.00
Program code 954700 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brad T.
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 450000
VendorA |  | 0 | 0 | 0
PM TIME |  | 20000 | 0 | 20000
Misc. |  | 0 | 0 | 0
Total Project Cost | 450000 | 20000 | 0 | 20000 | 430000

## #9547.00 Vendor A
DOC 2JD FDCCC Metal Roof Replacement
Project # 9547.00
Program code 954700 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brad T. |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9547.00 PM TIME
DOC 2JD FDCCC Metal Roof Replacement
Project # 9547.00
Program code 954700 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E017
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
|  |  | Totals: | 20000 |  | 0 |  | 20000

## #9547.00 Misc
DOC 2JD FDCCC Metal Roof Replacement
Project # 9547.00
Program code 954700 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brad T.
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9548.00
DAS CC Historical Building HVAC Replacement Design
Project # 9548.00
Program code 954800 |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 300000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 300000 | 0 | 0 | 0 | 300000

## #9548.00 Vendor A
DAS CC Historical Building HVAC Replacement Design
Project # 9548.00
Program code 954800 |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9548.00 PM TIME
DAS CC Historical Building HVAC Replacement Design
Project # 9548.00
Program code 954800 |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E01B
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9548.00 Misc
DAS CC Historical Building HVAC Replacement Design
Project # 9548.00
Program code 954800 |  |  |  | Major Program xxxx
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9549.00
HHS CHMHI Administration Building Window Replacement Phase 1 and 2
Project # 9549.00
Program code 954900 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 2736000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 2736000 | 0 | 0 | 0 | 2736000

## #9549.00 Vendor A
HHS CHMHI Administration Building Window Replacement Phase 1 and 2
Project # 9549.00
Program code 954900 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9549.00 PM TIME
HHS CHMHI Administration Building Window Replacement Phase 1 and 2
Project # 9549.00
Program code 954900 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E01D
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9549.00 Misc
HHS CHMHI Administration Building Window Replacement Phase 1 and 2
Project # 9549.00
Program code 954900 |  |  |  | Major Program 4E19
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9550.00
DOC FDCF Replace Power Plant and Warehouse Roofs
Project # 9550.00
Program code 955000 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 858500
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 858500 | 0 | 0 | 0 | 858500

## #9550.00 Vendor A
DOC FDCF Replace Power Plant and Warehouse Roofs
Project # 9550.00
Program code 955000 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9550.00 PM TIME
DOC FDCF Replace Power Plant and Warehouse Roofs
Project # 9550.00
Program code 955000 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS:E01E
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9550.00 Misc
DOC FDCF Replace Power Plant and Warehouse Roofs
Project # 9550.00
Program code 955000 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9551.00
DOC ICIW IPI Building Heating Unit Replacements
Project # 9551.00
Program code 955100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 800000
VendorA |  | 0 | 0 | 0
PM TIME |  | 25000 | 0 | 25000
Misc. |  | 0 | 0 | 0
Total Project Cost | 800000 | 25000 | 0 | 25000 | 775000

## #9551.00 Vendor A
DOC ICIW IPI Building Heating Unit Replacements
Project # 9551.00
Program code 955100 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9551.00 PM TIME
DOC ICIW IPI Building Heating Unit Replacements
Project # 9551.00
Program code 955100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E01F
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 25000 | 25000 |  |  | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
|  |  | Totals: | 25000 |  | 0 |  | 25000
Note on E9: Huggins, Joni [DAS]: Adams, Brandon DAS Finance Payables Infrastructure Finance, Can you please set up the following PM Time budgets: MM27 - 9560.00 - $20,000 MM27 - 9551.00 - $25,000 MM27 - 9558.00 - $8,000 MM27 - 9563.00 - $4,000 Regards, Brandon Adams

## #9551.00 Misc
DOC ICIW IPI Building Heating Unit Replacements
Project # 9551.00
Program code 955100 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9554.00
DOC IMCC Tunnel Waterproofing
Project # 9554.00
Program code 955400 |  |  | Major Program 4E17
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 850000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 850000 | 0 | 0 | 0 | 850000

## #9554.00 Vendor A
DOC IMCC Tunnel Waterproofing
Project # 9554.00
Program code 955400 |  |  | Major Program 4E17
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9554.00 PM TIME
DOC IMCC Tunnel Waterproofing
Project # 9554.00
Program code 955400 |  |  |  | Major Program 4E17
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E01J
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9554.00 Misc
DOC IMCC Tunnel Waterproofing
Project # 9554.00
Program code 955400 |  |  |  | Major Program 4E17
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9555.00
DOC IMCC Vehicle Gate VG1, 1A and VG18 Replacements
Project # 9555.00
Program code 955500 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 875000
VendorA |  | 0 | 0 | 0
PM TIME |  | 26250 | 0 | 26250
Misc. |  | 0 | 0 | 0
Total Project Cost | 875000 | 26250 | 0 | 26250 | 848750

## #9555.00 Vendor A
DOC IMCC Vehicle Gate VG1, 1A and VG18 Replacements
Project # 9555.00
Program code 955500 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9555.00 PM TIME
DOC IMCC Vehicle Gate VG1, 1A and VG18 Replacements
Project # 9555.00
Program code 955500 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E01W
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 26250 | 26250 |  |  | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
[5 empty] | 26250 |  | 0 | 26250
|  |  | Totals: | 26250 |  | 0 |  | 26250

## #9555.00 Misc
DOC IMCC Vehicle Gate VG1, 1A and VG18 Replacements
Project # 9555.00
Program code 955500 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9556.00
DOC IMCC Main Building AHU Control and Old Boiler Room Condensate Tank Replacements
Project # 9556.00
Program code 955600 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1130000
VendorA |  | 0 | 0 | 0
PM TIME |  | 25000 | 0 | 25000
Misc. |  | 0 | 0 | 0
Total Project Cost | 1130000 | 25000 | 0 | 25000 | 1105000

## #9556.00 Vendor A
DOC IMCC Main Building AHU Control and Old Boiler Room Condensate Tank Replacements
Project # 9556.00
Program code 955600 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9556.00 PM TIME
DOC IMCC Main Building AHU Control and Old Boiler Room Condensate Tank Replacements
Project # 9556.00
Program code 955600 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E024
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 25000 | 25000 |  |  | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
[5 empty] | 25000 |  | 0 | 25000
|  |  | Totals: | 25000 |  | 0 |  | 25000

## #9556.00 Misc
DOC IMCC Main Building AHU Control and Old Boiler Room Condensate Tank Replacements
Project # 9556.00
Program code 955600 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9557.00
HHS IMHI Infirmary Tuckpointing and Window Replacement
Project # 9557.00
Program code 955700 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 3258036.87
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 3258036.87 | 0 | 0 | 0 | 3258036.87

## #9557.00 Vendor A
HHS IMHI Infirmary Tuckpointing and Window Replacement
Project # 9557.00
Program code 955700 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - James T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9557.00 PM TIME
HHS IMHI Infirmary Tuckpointing and Window Replacement
Project # 9557.00
Program code 955700 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E028
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9557.00 Misc
HHS IMHI Infirmary Tuckpointing and Window Replacement
Project # 9557.00
Program code 955700 |  |  |  | Major Program 4E10
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9558.00
IDOE IPBS 6535 Building Tuckpointing
Project # 9558.00
Program code 955800 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
VendorA |  | 0 | 0 | 0
PM TIME |  | 8000 | 0 | 8000
Misc. |  | 0 | 0 | 0
Total Project Cost | 250000 | 8000 | 0 | 8000 | 242000

## #9558.00 Vendor A
IDOE IPBS 6535 Building Tuckpointing
Project # 9558.00
Program code 955800 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9558.00 PM TIME
IDOE IPBS 6535 Building Tuckpointing
Project # 9558.00
Program code 955800 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02C
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 8000 | 8000 |  |  | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
[5 empty] | 8000 |  | 0 | 8000
|  |  | Totals: | 8000 |  | 0 |  | 8000
Note on E9: Huggins, Joni [DAS]: Adams, Brandon DAS Finance Payables Infrastructure Finance, Can you please set up the following PM Time budgets: MM27 - 9560.00 - $20,000 MM27 - 9551.00 - $25,000 MM27 - 9558.00 - $8,000 MM27 - 9563.00 - $4,000 Regards, Brandon Adams

## #9558.00 Misc
IDOE IPBS 6535 Building Tuckpointing
Project # 9558.00
Program code 955800 |  |  |  | Major Program 4E10
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9559.00
IDVA IVH West and Cottage Parking Lot Replacements and Garage Tuckpointing
Project # 9559.00
Program code 955900 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager -Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1500000
VendorA |  | 0 | 0 | 0
PM TIME |  | 35000 | 0 | 35000
Misc. |  | 0 | 0 | 0
Total Project Cost | 1500000 | 35000 | 0 | 35000 | 1465000

## #9559.00 Vendor A
IDVA IVH West and Cottage Parking Lot Replacements and Garage Tuckpointing
Project # 9559.00
Program code 955900 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager -Brad T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9559.00 PM TIME
IDVA IVH West and Cottage Parking Lot Replacements and Garage Tuckpointing
Project # 9559.00
Program code 955900 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02E
Project Manager -Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 35000 | 35000 |  |  | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
[5 empty] | 35000 |  | 0 | 35000
|  |  | Totals: | 35000 |  | 0 |  | 35000

## #9559.00 Misc
IDVA IVH West and Cottage Parking Lot Replacements and Garage Tuckpointing
Project # 9559.00
Program code 955900 |  |  |  | Major Program 4E10
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager -Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9560.00
DOC MPCF Campus-Wide PIV Replacement and MLO Parking Lot Repair
Project # 9560.00
Program code 956000 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 1000000
VendorA |  | 0 | 0 | 0
PM TIME |  | 20000 | 0 | 20000
Misc. |  | 0 | 0 | 0
Total Project Cost | 1000000 | 20000 | 0 | 20000 | 980000

## #9560.00 Vendor A
DOC MPCF Campus-Wide PIV Replacement and MLO Parking Lot Repair
Project # 9560.00
Program code 956000 |  |  | Major Program 4G01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9560.00 PM TIME
DOC MPCF Campus-Wide PIV Replacement and MLO Parking Lot Repair
Project # 9560.00
Program code 956000 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02G
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 20000 | 20000 |  |  | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
[5 empty] | 20000 |  | 0 | 20000
|  |  | Totals: | 20000 |  | 0 |  | 20000
Note on E9: Huggins, Joni [DAS]: Adams, Brandon DAS Finance Payables Infrastructure Finance, Can you please set up the following PM Time budgets: MM27 - 9560.00 - $20,000 MM27 - 9551.00 - $25,000 MM27 - 9558.00 - $8,000 MM27 - 9563.00 - $4,000 Regards, Brandon Adams

## #9560.00 Misc
DOC MPCF Campus-Wide PIV Replacement and MLO Parking Lot Repair
Project # 9560.00
Program code 956000 |  |  |  | Major Program 4G01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9561.00
DOC NCCF R&D Window Replacement
Project # 9561.00
Program code 956100 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennie E
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 195000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 195000 | 0 | 0 | 0 | 195000

## #9561.00 Vendor A
DOC NCCF R&D Window Replacement
Project # 9561.00
Program code 956100 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennie E |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9561.00 PM TIME
DOC NCCF R&D Window Replacement
Project # 9561.00
Program code 956100 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02J
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9561.00 Misc
DOC NCCF R&D Window Replacement
Project # 9561.00
Program code 956100 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennie E
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9562.00
DOC NCF Living Unit B and E Large Capacity Water Vessel Replacements and CRC Generator Replacement
Project # 9562.00
Program code 956200 |  |  | Major Program 4B01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brad T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 773500
VendorA |  | 0 | 0 | 0
PM TIME |  | 30000 | 0 | 30000
Misc. |  | 0 | 0 | 0
Total Project Cost | 773500 | 30000 | 0 | 30000 | 743500

## #9562.00 Vendor A
DOC NCF Living Unit B and E Large Capacity Water Vessel Replacements and CRC Generator Replacement
Project # 9562.00
Program code 956200 |  |  | Major Program 4B01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brad T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9562.00 PM TIME
DOC NCF Living Unit B and E Large Capacity Water Vessel Replacements and CRC Generator Replacement
Project # 9562.00
Program code 956200 |  |  |  | Major Program 4B01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02P
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 30000 | 30000 |  |  | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
[5 empty] | 30000 |  | 0 | 30000
|  |  | Totals: | 30000 |  | 0 |  | 30000

## #9562.00 Misc
DOC NCF Living Unit B and E Large Capacity Water Vessel Replacements and CRC Generator Replacement
Project # 9562.00
Program code 956200 |  |  |  | Major Program 4B01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brad T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9563.00
DPS P01 South Alley Retaining Wall Replacement
Project # 9563.00
Program code 956300 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Brandon A
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 110000
VendorA |  | 0 | 0 | 0
PM TIME |  | 4000 | 0 | 4000
Misc. |  | 0 | 0 | 0
Total Project Cost | 110000 | 4000 | 0 | 4000 | 106000

## #9563.00 Vendor A
DPS P01 South Alley Retaining Wall Replacement
Project # 9563.00
Program code 956300 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Brandon A |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9563.00 PM TIME
DPS P01 South Alley Retaining Wall Replacement
Project # 9563.00
Program code 956300 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02R
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 4000 | 4000 |  |  | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
[5 empty] | 4000 |  | 0 | 4000
|  |  | Totals: | 4000 |  | 0 |  | 4000
Note on E9: Huggins, Joni [DAS]: Adams, Brandon DAS Finance Payables Infrastructure Finance, Can you please set up the following PM Time budgets: MM27 - 9560.00 - $20,000 MM27 - 9551.00 - $25,000 MM27 - 9558.00 - $8,000 MM27 - 9563.00 - $4,000 Regards, Brandon Adams

## #9563.00 Misc
DPS P01 South Alley Retaining Wall Replacement
Project # 9563.00
Program code 956300 |  |  |  | Major Program 4E19
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Brandon A
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9564.00
DPS P11 Parking Lot Replacement
Project # 9564.00
Program code 956400 |  |  | Major Program 4G01
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 535000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 535000 | 0 | 0 | 0 | 535000

## #9564.00 Vendor A
DPS P11 Parking Lot Replacement
Project # 9564.00
Program code 956400 |  |  | Major Program 4G01
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - James T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9564.00 PM TIME
DPS P11 Parking Lot Replacement
Project # 9564.00
Program code 956400 |  |  |  | Major Program 4G01
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E02X
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9564.00 Misc
DPS P11 Parking Lot Replacement
Project # 9564.00
Program code 956400 |  |  |  | Major Program 4G01
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9565.00
DPS P12 Retaining Wall Re-Build
Project # 9565.00
Program code 956500 |  |  | Major Program 4E19
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 50000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 50000 | 0 | 0 | 0 | 50000

## #9565.00 Vendor A
DPS P12 Retaining Wall Re-Build
Project # 9565.00
Program code 956500 |  |  | Major Program 4E19
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - James T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9565.00 PM TIME
DPS P12 Retaining Wall Re-Build
Project # 9565.00
Program code 956500 |  |  |  | Major Program 4E19
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E032
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9565.00 Misc
DPS P12 Retaining Wall Re-Build
Project # 9565.00
Program code 956500 |  |  |  | Major Program 4E19
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9566.00
HHS STS Bakery Cooler Enclosure Replacement and Corbett-Miller Hall Tuckpointing
Project # 9566.00
Program code 956600 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 250000
VendorA |  | 0 | 0 | 0
PM TIME |  | 12000 | 0 | 12000
Misc. |  | 0 | 0 | 0
Total Project Cost | 250000 | 12000 | 0 | 12000 | 238000

## #9566.00 Vendor A
HHS STS Bakery Cooler Enclosure Replacement and Corbett-Miller Hall Tuckpointing
Project # 9566.00
Program code 956600 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9566.00 PM TIME
HHS STS Bakery Cooler Enclosure Replacement and Corbett-Miller Hall Tuckpointing
Project # 9566.00
Program code 956600 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E03B
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 12000 | 12000 |  |  | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
[5 empty] | 12000 |  | 0 | 12000
|  |  | Totals: | 12000 |  | 0 |  | 12000
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer DAS Finance Payables Infrastructure Please create a DAS Costs budget of $12,000.00 for MM27 9566.00. Regards, Jennifer

## #9566.00 Misc
HHS STS Bakery Cooler Enclosure Replacement and Corbett-Miller Hall Tuckpointing
Project # 9566.00
Program code 956600 |  |  |  | Major Program 4E10
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9567.00
DAS USS Union Sunday School Masonry Repairs and Roof Replacement
Project # 9567.00
Program code 956700 |  |  | Major Program 4E02
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 456000
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 456000 | 0 | 0 | 0 | 456000

## #9567.00 Vendor A
DAS USS Union Sunday School Masonry Repairs and Roof Replacement
Project # 9567.00
Program code 956700 |  |  | Major Program 4E02
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - James T |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9567.00 PM TIME
DAS USS Union Sunday School Masonry Repairs and Roof Replacement
Project # 9567.00
Program code 956700 |  |  |  | Major Program 4E02
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E03E
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #9567.00 Misc
DAS USS Union Sunday School Masonry Repairs and Roof Replacement
Project # 9567.00
Program code 956700 |  |  |  | Major Program 4E02
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #9568.00
HHS WRC Dispatch Garage Roof Replacement and Birches Tuckpointing
Project # 9568.00
Program code 956800 |  |  | Major Program 4E10
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - Jennifer K
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 980000
VendorA |  | 0 | 0 | 0
PM TIME |  | 22500 | 0 | 22500
Misc. |  | 0 | 0 | 0
Total Project Cost | 980000 | 22500 | 0 | 22500 | 957500

## #9568.00 Vendor A
HHS WRC Dispatch Garage Roof Replacement and Birches Tuckpointing
Project # 9568.00
Program code 956800 |  |  | Major Program 4E10
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - Jennifer K |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #9568.00 PM TIME
HHS WRC Dispatch Garage Roof Replacement and Birches Tuckpointing
Project # 9568.00
Program code 956800 |  |  |  | Major Program 4E10
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS: E03H
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 22500 | 22500 |  |  | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
[5 empty] | 22500 |  | 0 | 22500
|  |  | Totals: | 22500 |  | 0 |  | 22500
Note on E9: Huggins, Joni [DAS]: Kleene, Jennifer DAS Finance Payables Infrastructure Please create a DAS Costs budget of $22,500.00 for project 9568.00. Regards, Jennifer Jennifer Kleene

## #9568.00 Misc
HHS WRC Dispatch Garage Roof Replacement and Birches Tuckpointing
Project # 9568.00
Program code 956800 |  |  |  | Major Program 4E10
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - Jennifer K
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-MM24 |  |  | Close Date:
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-MM24-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-MM24-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Acct. Codes-0017-335-MM24-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0