## FINANCIAL
Status | PROJECT NUMBER | PROJECT TITLE | Project Mgr. | Vertical Infrastructure Project Allocation | Additional Funds | Total Project Budget | Contracted Amount | Expended Amount | Contracted Not Expended | Not Encumbered
|  | Total Appropriation 83B | 1000000
Additional Funds
|  | Sales Tax Refunds |  | 0
|  | Total Funds & Sales Tax Refunds |  | 1000000
| . | Less: Total Assigned |  | 767000
|  | Total Unassigned / Unallocated |  | 233000
Major Maintenance Projects
|  |  |  | hard code | link to project recap | link to this page budget column | link to project recap | link to project recap | link to project recap | link to project recap
Funds Received
| 9448.00 | DAS TH Residence Roof, Porch, & South Garden Wall Repairs | James T. | 767000 |  | 767000 | 96951.2 | 757 | 96194.2 | 670048.8
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Major Maintenance Totals |  | 767000 | 0 | 767000 | 96951.2 | 757 | 96194.2 | 670048.8
[6 empty] | Total funds not allocated to the projects listed above |  |  |  | 233000
|  | For these projects the recap budget page will link to the Vertical Infrastructure project allocation and not the Total Budget column |  |  |  | Subtotal |  |  |  | 903048.8
[6 empty] | Total funds Available |  |  | 1000000
[6 empty] | Total obligated by contract or PO |  |  | -96951.2 | 903048.8
[6 empty] | Variance |  |  |  | 0

## RECAP #9448.00
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
Recap
Acct. Codes-0017-335-0002 |  |  | Close Date:
Project Manager - James T
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 767000
DCI Group |  | 27194.2 | 0 | 27194.2
PM TIME |  | 18000 | 0 | 18000
Misc. |  | 757 | 757 | 0
OPN Architects |  | 51000 | 0 | 51000
Total Project Cost | 767000 | 96951.2 | 757 | 96194.2 | 670048.8

## #9448.00 DCI Group
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
DCI Group |  |  | Vendor: 00003025029
Acct. Codes-0017-335-0002-9255 |  |  | RFP1821335228-DCI11012021
Project Manager - James T |  |  | Activity code: CMGR
Split w/MM25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527217916 | 2026-09-22 | CO #2(Opening in THIL) | 27194.2 | 27194.2 |  |  | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  |  |  | 27194.2 |  | 0 | 27194.2
|  | Totals: | 27194.2 |  | 0 |  | 27194.2
|  | MM25 | 44745.69 |  | 44723.85 |  | 21.84
|  | Total: | 71939.89 |  | 44723.85 |  | 27216.04

## #9448.00 PM TIME
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-0002-xxxx |  |  |  | eDAS: 737B
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount | 18000 | 18000 |  |  | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
[5 empty] | 18000 |  | 0 | 18000
|  |  | Totals: | 18000 |  | 0 |  | 18000
Note on E9: Huggins, Joni [DAS]: Trower, James Huggins, Joni Project 9448.00: MM25 9448.00 -812.51 Increase MM25 Funds PM Time by $15,000 Setup PM Time for THILL Funds by $18,000 Project 9528.00: MM25 9528.00 -360.49 Increase MM25 Funds PM Time by $7,000

## #9448.00 Misc
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  |  | Major Program 4D04
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-0002-xxxx |  |  |  | Shipping Code: 035
Project Manager - James T
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
PRC 33527218908 | 2026-08-06 | 9500 | CNST | ATC Group V#(00002134218) | Inv. 2726446 | 757 | 757
757
757
757
757
757
757
757
757
757
757
757
|  |  |  | Totals: |  | 757

## #9448.00 OPN Architects
DAS TH Residence Roof, Porch, & South Garden Wall Repairs
Project # 9448.00
Program code 944800 |  |  | Major Program 4D04
OPN Architects |  |  | Vendor: 00003035830
Acct. Codes-0017-335-0002-9260 |  |  | RFP944800-01
Project Manager - James T |  |  | Activity code: DSGN
Split w/MM25
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
PO 33527232900 | 2026-09-28 | CO #3 (Opening PO in THIL) | 51000 | 51000 |  |  | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  |  |  | 51000 |  | 0 | 51000
|  | Totals: | 51000 |  | 0 |  | 51000
|  | MM25 | 192227 |  | 122098.49 |  | 70128.51
|  | Total: | 243227 |  | 122098.49 |  | 121128.51

## RECAP #XXXX.XX
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Recap
Acct. Codes-0017-335-0002 |  |  | Close Date:
Project Manager - xxxxxxxxxxxxxxxxxxx
| TRANSFERS | CONTRACTED | EXPENDED | CONTRACTED, NOT EXPENDED | UNDER(OVER) Budget
Budget | 0
VendorA |  | 0 | 0 | 0
PM TIME |  | 0 | 0 | 0
Misc. |  | 0 | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0

## #XXXX.XX Vendor A
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  | Major Program xxxx
Vendor A |  |  | Vendor:
Acct. Codes-0017-335-0002-xxxx
Project Manager - xxxxxxxxxxxxxxxxxxx |  |  | Activity code:
Doc # | Date | Activity | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  | Totals: | 0 |  | 0 |  | 0
|  | CM Services: | 0 |  |  |  | 0
|  | Reimbursables: | 0 |  |  |  | 0
|  | Total: | 0 |  | 0 |  | 0

## #XXXX.XX PM TIME
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
PM TIME |  |  |  | Internal documents
Acct. Codes-0017-335-0002-xxxx |  |  |  | eDAS
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Contract & C.O.'s | Contract Total | Payment Amount | Total Paid | Balance
|  |  | Budget amount |  | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
|  |  | Totals: | 0 |  | 0 |  | 0

## #XXXX.XX Misc
xxx xxxxxxxxxxxxxxxxxxxxx
Project # xxxx.xx
Program code xxxxxx |  |  |  | Major Program xxxx
Misc
Do not code PM, EADOC, or Builders Risk here
Acct. Codes-0017-335-0002-xxxx |  |  |  | Shipping Code:
Project Manager - xxxxxxxxxxxxxxxxxxx
Doc # | Date | Object Code | Activity Code | Activity | Invoice | Payment Amount | Total Paid
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: |  | 0